## Temp-PPT (hidden)
Subject | Domain | 472 |  |  | MOM |  |  | NOC |  | Total Tasks | D | New | 472 |  |  | MOM |  |  | T0-T5 | NOC |  | Total Tasks
|  |  | Closed | Open |  | Closed | Open |  | Closed | Open | Old | A |  | Closed | Open |  | Closed | Open |  |  | Closed | Open
DC/NOC | Network | 57 | 22 | 35 | 294 | 43 | 251 | [5 empty] | 53 | 31 | 22 | 272 | 169 | 103
DC/NOC | Security | 45 | 6 | 39 | 109 | 0 | 109 | [5 empty] | 46 | 16 | 30 | 158 | 19 | 139
DC/NOC | Servers
DC/NOC | Virtulization
DC/NOC | Storage
DC/NOC | Backup
DC/NOC | Applications/Tools | 189 | 58 | 131 | 597 | 22 | 575 | 678 | 0 | 678 |  |  | 194 | 74 | 120 | 629 | 180 | 449 |  | 678 | 254 | 424
DC/NOC | Process Flows
DC/NOC | Helpdesk (Contact Center) |  |  |  | 83 | 4 | 79 | [8 empty] | 83 | 3 | 80
ISP &TSP | Perimeter
ISP &TSP | Security
ISP &TSP | DWDM | 25 | 11 | 14 | 2 | 0 | 2 | [5 empty] | 25 | 12 | 13 | 2 |  | 2
ISP &TSP | IPMPLS | 37 | 16 | 21 | 1 | 0 | 1 | [5 empty] | 35 | 17 | 18
ISP &TSP | GPON | 101 | 81 | 20 | 5 | 0 | 5 | [5 empty] | 101 | 91 | 10 | 3 | 3 | 1
| Active Infrastructure | [14 empty] | 4 | 1 | 3
Infrastructure | Passive Infrastructure
DR |  | 18 | 9 | 9 | 3 | 0 | 3 | [5 empty] | 18 | 9 | 9 | 3 | 1 | 2
AT |  |  |  |  | 1 | 0 | 1
BBNL |  |  |  |  | 5 | 4 | 1
Field Related issues |  |  |  |  | 24 | 0 | 24 | [8 empty] | 24 | 2 | 22
OEM Related Issues |  |  |  |  | 100 | 5 | 95 | [8 empty] | 100 | 66 | 34
Regulatory |  |  |  |  | 45 | 0 | 45
WhatsApp |  |  |  |  | 2 | 0 | 2
Test Lab |  |  |  |  | 7 | 0 | 7
|  | 472 | 203 | 269 | 1278 | 78 | 1200 | 678 | 0 | 678 |  |  | 472 | 250 | 222 | 1278 | 444 | 835 | 0 | 678 | 254 | 424
Count of UniqueID
[28 empty] | CLOSED | OPEN | (blank) | Grand Total
[27 empty] | 472 | 250 | 222 |  | 472
[27 empty] | Applications/Tools | 74 | 120 |  | 194
[27 empty] | DR | 9 | 9 |  | 18
[27 empty] | DWDM | 12 | 13 |  | 25
[27 empty] | GPON | 91 | 10 |  | 101
[27 empty] | IPMPLS | 17 | 18 |  | 35
[27 empty] | Network | 31 | 22 |  | 53
[27 empty] | Security | 16 | 30 |  | 46
[27 empty] | MOM | 443 | 835 |  | 1278
[27 empty] | Applications | 8 | 6 |  | 14
[27 empty] | Applications/Tools | 172 | 443 |  | 615
[27 empty] | DR | 1 | 2 |  | 3
[27 empty] | DWDM |  | 2 |  | 2
[27 empty] | Field Related issues | 2 | 22 |  | 24
[27 empty] | GPON | 1 | 3 |  | 4
[27 empty] | Helpdesk (Contact Center) | 3 | 80 |  | 83
[27 empty] | IPMPLS | 2 | 1 |  | 3
[27 empty] | Network | 169 | 103 |  | 272
[27 empty] | OEM Related Issues | 66 | 34 |  | 100
[27 empty] | Security | 19 | 139 |  | 158
[27 empty] | NOC | 254 | 424 |  | 678
[27 empty] | Applications/Tools | 254 | 424 |  | 678
(blank)
(blank)
[27 empty] | Grand Total | 947 | 1481 |  | 2428
Status Switch
[23 empty] | OPEN | OPEN
[23 empty] | COMPLETED & APPROVED | CLOSED
[23 empty] | WIP | OPEN
[23 empty] | REOPENED | OPEN
[23 empty] | CLOSURE REVIEW PENDING | OPEN
[23 empty] | DEPENDENCY(Client/Ext) | OPEN
[23 empty] | CLOSED | CLOSED
[23 empty] | DEPENDENCY(Client/Ext.) | OPEN
[23 empty] | Completed | CLOSED
[23 empty] | NOT FEASIBLE | OPEN
OPEN
[23 empty] | COMPLETED | CLOSED
[23 empty] | BLANK | OPEN
[23 empty] | Track-472 | Overall | OPEN | CLOSED
[23 empty] | Security & Regulatory Compliance | 46 | 33 | 13
[23 empty] | DWDM | 25 | 13 | 12
DWDM
Security & Regulatory Compliance
Security & Regulatory Compliance
[23 empty] | BSS | 26 | 24 | 2
BSS
BSS
BSS
BSS
BSS
BSS
BSS
BSS
BSS
BSS
BSS
BSS
BSS
BSS
BSS
BSS
BSS
BSS
BSS
BSS
BSS
[23 empty] | IP/MPLS | 34 | 16 | 18
IP/MPLS
IP/MPLS
Security & Regulatory Compliance
Security & Regulatory Compliance
BSS
IP/MPLS
IP/MPLS
Security & Regulatory Compliance
Security & Regulatory Compliance
Security & Regulatory Compliance
Security & Regulatory Compliance
Security & Regulatory Compliance
[23 empty] | DC-IT | 27 | 8 | 19
DC-IT
DC-IT
DC-IT
DC-IT
DC-IT
DC-IT
DC-IT
DC-IT
DC-IT
DC-IT
DC-IT
DC-IT
DC-IT
DC-IT
DC-IT
DC-IT
DC-IT
DC-IT
DC-IT
DC-IT
DC-IT
DC-IT
DC-IT
[23 empty] | DR | 18 | 9 | 9
DR
DR
DR
DR
DR
DR
DR
DR
DR
DR
DR
DR
DR
DR
DR
DR
DR
DWDM
DWDM
DWDM
DWDM
DWDM
DWDM
DWDM
DWDM
DWDM
DWDM
DWDM
DWDM
DWDM
DWDM
DWDM
DWDM
DWDM
DWDM
DWDM
DWDM
DWDM
DWDM
DWDM
[23 empty] | GIS | 54 | 3 | 49
GIS
GIS
GIS
GIS
GIS
GIS
GIS
GIS
GIS
GIS
GIS
GIS
GIS
GIS
GIS
GIS
GIS
GIS
GIS
GIS
GIS
GIS
GIS
GIS
GIS
GIS
GIS
GIS
GIS
GIS
GIS
GIS
GIS
GIS
GIS
GIS
GIS
GIS
GIS
GIS
GIS
GIS
GIS
GIS
GIS
GIS
GIS
GIS
GIS
GIS
GIS
GIS
GIS
[23 empty] | GPON | 101 | 8 | 93
GPON
GPON
GPON
GPON
GPON
GPON
GPON
GPON
GPON
GPON
GPON
GPON
GPON
GPON
GPON
GPON
GPON
GPON
GPON
GPON
GPON
GPON
IP/MPLS
IP/MPLS
IP/MPLS
IP/MPLS
IP/MPLS
IP/MPLS
IP/MPLS
IP/MPLS
IP/MPLS
IP/MPLS
IP/MPLS
IP/MPLS
IP/MPLS
IP/MPLS
IP/MPLS
IP/MPLS
IP/MPLS
IP/MPLS
IP/MPLS
IP/MPLS
[23 empty] | NSO | 31 | 30 | 1
NSO
NSO
NSO
NSO
NSO
NSO
NSO
NSO
NSO
NSO
NSO
NSO
NSO
NSO
NSO
NSO
NSO
NSO
NSO
NSO
[23 empty] | OSS | 82 | 58 | 24
OSS
OSS
OSS
OSS
OSS
OSS
OSS
OSS
OSS
OSS
OSS
OSS
OSS
OSS
OSS
OSS
OSS
OSS
OSS
OSS
OSS
OSS
OSS
OSS
OSS
OSS
OSS
OSS
OSS
OSS
OSS
OSS
OSS
OSS
OSS
OSS
OSS
OSS
OSS
OSS
OSS
OSS
OSS
OSS
OSS
OSS
OSS
OSS
OSS
OSS
OSS
OSS
OSS
OSS
OSS
OSS
OSS
OSS
OSS
OSS
OSS
OSS
OSS
OSS
OSS
OSS
OSS
OSS
OSS
OSS
DC-IT
GPON
OSS
OSS
Security & Regulatory Compliance
Security & Regulatory Compliance
OSS
Security & Regulatory Compliance
OSS
Security & Regulatory Compliance
Security & Regulatory Compliance
Security & Regulatory Compliance
Security & Regulatory Compliance
Security & Regulatory Compliance
Security & Regulatory Compliance
Security & Regulatory Compliance
Security & Regulatory Compliance
Security & Regulatory Compliance
OSS
Security & Regulatory Compliance
OSS
Security & Regulatory Compliance
Security & Regulatory Compliance
Security & Regulatory Compliance
Security & Regulatory Compliance
Security & Regulatory Compliance
Security & Regulatory Compliance
Security & Regulatory Compliance
Security & Regulatory Compliance
Security & Regulatory Compliance
Security & Regulatory Compliance
Security & Regulatory Compliance
Security & Regulatory Compliance
Security & Regulatory Compliance
Security & Regulatory Compliance
Security & Regulatory Compliance
Security & Regulatory Compliance
Security & Regulatory Compliance
Security & Regulatory Compliance
IP/MPLS
IP/MPLS
IP/MPLS
IP/MPLS
IP/MPLS
IP/MPLS
IP/MPLS
IP/MPLS
IP/MPLS
[23 empty] | TNOC-Ops | 26 | 11 | 15
[23 empty] | BSS | 1 | 1 | 0
BSS
TNOC-Ops
Security & Regulatory Compliance
TNOC-Ops
TNOC-Ops
TNOC-Ops
TNOC-Ops
TNOC-Ops
TNOC-Ops
TNOC-Ops
TNOC-Ops
TNOC-Ops
OSS
TNOC-Ops
TNOC-Ops
TNOC-Ops
TNOC-Ops
TNOC-Ops
TNOC-Ops
TNOC-Ops
TNOC-Ops
TNOC-Ops
TNOC-Ops
TNOC-Ops
TNOC-Ops
GPON
GPON
NSO
NSO
NSO
NSO
NSO
NSO
NSO
NSO
NSO
BSS
DC-IT
IP/MPLS
NSO
Security & Regulatory Compliance
Security & Regulatory Compliance
OSS
OSS
OSS
OSS
OSS
DC-IT
TNOC-Ops
TNOC-Ops
TNOC-Ops
GPON
GPON
GPON
GPON
GPON
GPON
GPON
GPON
GPON
GPON
GPON
GPON
GPON
GPON
GPON
GPON
GPON
GPON
GPON
GPON
GPON
GPON
GPON
GPON
GPON
GPON
GPON
GPON
GPON
GPON
GPON
GPON
GPON
GPON
GPON
GPON
GPON
GPON
GPON
GPON
GPON
GPON
GPON
GPON
GPON
GPON
GPON
GPON
GPON
GPON
GPON
GPON
GPON
GPON
GPON
GPON
GPON
GPON
GPON
GPON
GPON
GPON
GPON
GPON
GPON
GPON
GPON
GPON
GPON
GPON
GPON
GPON
GPON
GPON
GPON
Security & Regulatory Compliance
[23 empty] | Total | 471 | 214 | 255

## Temp-Convertors (hidden)
Cat | Values
MOM | DR
MOM | AT
MOM | BBNL
MOM | Field Related issues
MOM | OEM Related Issues
MOM | Regulatory
MOM | WhatsApp
MOM | Test Lab
MOM | Network
MOM | Security
MOM | Applications/Tools
MOM | Helpdesk (Contact Center)
MOM | DWDM
MOM | IPMPLS
MOM | GPON
472 | Network
472 | Security
472 | Applications/Tools
472 | DWDM
472 | IPMPLS
472 | GPON
472 | DR
NOC | Applications/Tools
Cat | Type | CONCAT | Tfiber | Column1
472 | BSS | 472BSS | Applications/Tools
472 | BSS | 472BSS | Applications/Tools
472 | DC-IT | 472DC-IT | Network
472 | DR | 472DR | DR
472 | DWDM | 472DWDM | DWDM
472 | GIS | 472GIS | Applications/Tools
472 | GPON | 472GPON | GPON
472 | IP/MPLS | 472IP/MPLS | IPMPLS
472 | NSO | 472NSO | Applications/Tools
472 | OSS | 472OSS | Applications/Tools
472 | Security & Regulatory Compliance | 472Security & Regulatory Compliance | Security
472 | TNOC-Ops | 472TNOC-Ops | Network
MOM | NOC Operationalization | MOMNOC Operationalization | Network
MOM | IP/MPLS | MOMIP/MPLS | IPMPLS
MOM | WFM | MOMWFM | Applications/Tools
MOM | BSS | MOMBSS | Applications/Tools
MOM | OSS | MOMOSS | Applications/Tools
MOM | GIS | MOMGIS | Applications/Tools
MOM | PM Tool Issue | MOMPM Tool Issue | Applications
MOM | T&D Environment | MOMT&D Environment | Applications
MOM | GPON | MOMGPON | GPON
MOM | DR | MOMDR | DR
MOM | Helpdesk | MOMHelpdesk | Helpdesk (Contact Center)
MOM | Field Related | MOMField Related | Field Related issues
MOM | Security & Regulatory Compliance | MOMSecurity & Regulatory Compliance | Security
MOM | DC-IT | MOMDC-IT | Network
MOM | OEM Related | MOMOEM Related | OEM Related Issues
MOM | NSO | MOMNSO | Applications/Tools
MOM | All Domain | MOMAll Domain | Applications/Tools
MOM | IPDR | MOMIPDR | Applications/Tools
MOM | DWDM | MOMDWDM | DWDM
NOC | GPON | NOCGPON | Applications/Tools
NOC | All Domain | NOCAll Domain | Applications/Tools
NOC | OSS | NOCOSS | Applications/Tools
NOC | DWDM | NOCDWDM | Applications/Tools
NOC | IP/MPLS | NOCIP/MPLS | Applications/Tools
NOC | Helpdesk | NOCHelpdesk | Applications/Tools
NOC | BSS | NOCBSS | Applications/Tools
NOC | WFM | NOCWFM | Applications/Tools
NOC | DC Passive Infra | NOCDC Passive Infra | Applications/Tools
NOC | OSS and NSO | NOCOSS and NSO | Applications/Tools
NOC | IPDR | NOCIPDR | Applications/Tools
NOC | NSO | NOCNSO | Applications/Tools

## Sheet1 (hidden)
Category | MOM
Owner(L&T) | (All)
Count of Owner(L&T) | Column Labels
Row Labels |  | Closed | CLOSURE REVIEW PENDING | COMPLETED & APPROVED | Dependancy on NSO, part of 472-points, Point No. 103 & 237 | Dependancy on NSO, part of 472-points, Point No. 104 & 238 | DEPENDENCY(Client/Ext.) | OPEN | WIP | (blank) | Completed | COMPLETED | NOT FEASIBLE | DUPLICATE POINT (M688) | DUPLICATE POINT (M739) | NOT_FEASIBLE | Grand Total
All Domain | 1 | [15 empty] | 1
BSS | [7 empty] | 344 | 5 |  | 12 |  |  | 1 | 1 |  | 363
DC-IT | [7 empty] | 1 | [8 empty] | 1
DR |  |  |  | 1 |  |  |  | 2 | [8 empty] | 3
DWDM |  |  |  |  | 1 | 1 | [10 empty] | 2
Field Related | 23 | [6 empty] | 1 | [8 empty] | 24
GIS | [7 empty] | 1 | 3 |  | 35 | 7 | 8 |  |  |  | 54
GPON |  |  |  | 1 |  |  | 2 |  | 1 | [7 empty] | 4
Helpdesk |  |  | 58 | 3 |  |  |  | 1 | 21 | [7 empty] | 83
IP/MPLS | 1 | 2 | [14 empty] | 3
NOC Operationalization | 163 | 77 |  | 1 |  |  |  | 23 |  | 6 | 1 | [5 empty] | 271
NSO | 55 | [15 empty] | 55
OEM Related | 100 | [15 empty] | 100
OSS | [7 empty] | 4 | 10 |  | 25 | 3 |  |  |  | 2 | 44
PM Tool Issue | 1 | [9 empty] | 1 | [5 empty] | 2
WFM | 23 | 1 | [5 empty] | 6 | 2 |  | 55 | 3 | 7 |  |  |  | 97
Security & Regulatory Compliance | 157 | [6 empty] | 1 | [8 empty] | 158
T&D Environment | 1 |  | 4 | 5 |  |  |  | 2 | [8 empty] | 12
IPDR | 1 | [15 empty] | 1
Grand Total | 526 | 80 | 62 | 11 | 1 | 1 | 2 | 386 | 42 | 6 | 129 | 13 | 15 | 1 | 1 | 2 | 1278

## All Domain Summary
|  | 2429 | 588 | 469 | 5 | 1 | 2 | 6 | 25 | 5 | 15 | 1 | 3 |  |  | 362 | 1 | 41 | 3 | 1527
Domain | Owner | Total Points | Closed Points | Artefacts to be updated | Dependancy | [10 empty] | WIP |  | Duplicate | Not Feasible
[5 empty] | HPE | Nokia | Tejas | Tejas & Nokia | Nokia & NSO | NSO | T Fiber | T Fiber, TPA,L&T | All Packages | Project | O&M | L&T | TPA
DWDM | Suresh Kumar | 28 | 14 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 5 | 0 | 1 |  |  | 1 | 1 | 2
GPON | Sayed Pasha | 156 | 107 | 0 | 0 | 1 | 2 | 6 | 25 | 2 | 0 | 0 | 2 |  |  | 1 | 0 | 12
NOC Operations | Ahmad Siddiqui | 58 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 13 | 0 | 0
NSO | Jayanth | 119 | 1
GIS | Kaushalendra Kumar | 106 | 51 | 38 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 6 | 0 | 6 | 1
WFM | Kaushalendra Kumar | 114 | 0 | 83 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 15 | 0 | 13 | 2
old BSS | Sandeep Deshmukh | 528
New BSS | Sandeep Deshmukh | 20 | [13 empty] | 20
DC Active Infra | Ravi Kishore | 51 | 29 | 0
DC Network and IPMPLS | R S Rao | 35 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  |  | 2 | 0 | 0
Project Execution | Srinivas Kodali | 30 | [11 empty] | 23 | 7 | 0 | 0 | 0 | 0
Service Delivery Head | Siva Prasad | 308 | 164 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 119 | 0 | 0
Security | Bajiba Shaik | 199 | 51 | 0
Helpdesk | Siva Kumar | 136 | 73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 63 | 0 | 0
DC Passive Infra | Srinivas Kommreddy | 3
OSS | Venkatesh | 536 | 21 | 323 | [6 empty] | 8 |  |  |  |  | 122 |  | 8
| T Fiber | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
COMPLETED & APPROVED

## Master_Tracker(2428) (hidden)
274
Slno | UniqueID | Category | Meeting Date | Priority | Ramana | Ramana-Domain | Domain | Sub-Domain | Action Point | Impact | Priority | Baseline Status | xx | Application | Module | Remarks | Remarks | Organization | Owner | Owner(L&T) | Target Date to Complete | Open | Revised Status (L&T) As on 18-Sep-2025 | Approved BY (TF) | Approval Date(TF) | Link of evidences | R | S | T | U | V | W | X | Tfiber-Cat | Derived Status (L&T) | OSS | OSS Remarks | Ramana Remarks as on 19-Sep-2025 | T Fiber Appoved Date | Artefacts | Target Date | Qty
1 | T1 | 472 | NA |  |  |  | Security & Regulatory Compliance | Configuration | Integration testing of All supported devices is complete and adding all the devices is underway. |  |  | Open |  |  |  |  | what ever request has come all are integrated with ISE , any new device request comes same will be added . Also Aleppo PO get relaesed for ADintegration , it will also get integrated with AD. |  |  | Sarmendra |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | 472Security & Regulatory Compliance | Security | OPEN | [6 empty] | 1
2 | T2 | 472 | NA |  |  |  | DWDM | Integration with Alepo | RADIUS Configuration Testing on Ciena Node & EMS (MCP) |  |  | Colosed | [7 empty] | Suresh Kumar |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-05-06 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\DWDM\Artefact - T106 | [6 empty] | 472DWDM | DWDM | CLOSED |  |  |  | 2025-05-06 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\DWDM\Artefact - T106 |  | 1
3 | T3 | 472 | NA |  |  |  | Security & Regulatory Compliance | Integration | Accouting data from Ciena MCP and field nodes to be captured in Alepo AAA |  | Critical | Open |  |  |  |  | MCP upgradation is in pipeline . same will be completed by 25 Sep 2025 |  |  | Sarmendra |  | Open | WIP | [9 empty] | 472Security & Regulatory Compliance | Security | OPEN | [6 empty] | 1
4 | T3 | 472 | NA |  |  |  | DWDM | Integration with Alepo | TACACS+/Radius testing for AAA on ciena node |  |  | Open |  |  |  |  | 20-09-2025: 8.1 MCP software Patch upgradation will be completed by 27-Sep-25, After completetion of upgrdation AAA functionalities will be tested for ciena devices by using radius 13-09-25:MCP upgradation is in progress, will be able to check the logs by next week 28-08-2025: Activity is in progress, target to complete by 25th Sep'25 Authentication and Authorization tested and found OK for Node and MCP. 19-08-2025: Due to issue in disk partition and file type of storage, activity is not started 10-08-2025: OEM confirmation recieved and activity is planned from 18th August'25. 05-July-2025: DC OSS to DR MCP communication is through now, need to integrate and test before activity 12-July-2025: DC OSS to DR MCP integration testing done. Alarms and Autoticketing functioning as expected. Upgradation activity will be scheduled as per OEM confirmation, Target date - 30-07-25 26-July-2025: Schedule awaited from OEM 30-June-2025: DC OSS to DR MCP connectivity to be extended for PE approval, WIP. Target date - 30-07-25 15-06-25: Targeting to close the upgradation by month end, 30-06-25 30-05-2025: Accounting issue resolved in latest MCP version, verified in 8.2 Ver (Node logs are now capturing in MCP). Upgradation schedule awaited from Teleindia for our MCP from 7.1-P02 5/21/2025: Correlation to identified to find the user logged in at the specific time 28APR'25: As discussed with Sanjay sir, if user id not avaialble pls. try for correlation with IP. Some how Correlation to be done. In Accounting, Node and MCP logs are successfully reporting in Alepo with below limitation. Node Logs - Active profile name (ADMIN/RADIUS) is displayed against User ID (Ciena confirmed it is as per design no changes are possible) | L&T |  | Suresh Kumar |  | Open | WIP | [9 empty] | 472DWDM | DWDM | OPEN | [6 empty] | 1
5 | T4 | 472 | NA |  |  |  | Security & Regulatory Compliance | Security | Alepo confirmed that Alepo AAA supports TACACS, Alepo to test Nokia and Ciena nodes integration on TACACS , with supporting artefacts of testing. 1.TACACS Testing with Tejas, Nokia, Ciena 2. Alepo Testing with Tejas, Nokia and Ciena |  |  | Open |  |  |  |  | 1.TACACS Testing with Tejas, Nokia, Ciena completed 2. Alepo Testing with Tejas, Nokia and Ciena |  |  | Sarmendra |  |  | CLOSURE REVIEW PENDING | [9 empty] | 472Security & Regulatory Compliance | Security | OPEN |  |  |  |  | Artefacts to be Submitted |  | 1
6 | T5 | 472 | NA |  |  |  | Security & Regulatory Compliance | Functional AT | Had a meeting with Ashwani from Alepo and sent him updated test cases. He is working on data gathering and will send us back by Tuesday. |  |  | Open |  |  |  |  | FAT were submitted to customer, Customer observation in being work out. Target to resubmission.- 23.07.25 |  |  | Sarmendra |  |  | CLOSURE REVIEW PENDING | [9 empty] | 472Security & Regulatory Compliance | Security | OPEN |  |  |  |  | Artefacts to be Submitted |  | 1
7 | T6 | 472 | NA |  |  |  | BSS | Installation | Installation of BSS Application |  |  | Open |  |  |  |  | 29-08-2025: Design and Solution document to be shared with GM NOC and Physical instllation of BSS need to validate according to solution from L&T Side before submitting for for review with T Fiber 26-06-2025: We have offered Installation AT. TFIBER has asked DC architecture review including license validity |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | 472BSS | Applications/Tools | OPEN | [6 empty] | 1
8 | T7 | 472 | NA |  |  |  | BSS | Integration | Initial Integration with Third Party Applications (OSS & NSO) |  |  | Open |  |  |  |  | 26-06-2025: OSS Integration is done. NSO integration is pending. Awaiting NSO Team. |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | 472BSS | Applications/Tools | OPEN | [6 empty] | 1
9 | T8 | 472 | NA |  |  |  | BSS | Integration | OSS interfaces |  |  | Open |  |  |  |  | 26-06-2025: Feasibility API & Ticket API integration is completed. |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | 472BSS | Applications/Tools | OPEN | [6 empty] | 1
10 | T9 | 472 | NA |  |  |  | BSS | Integration | NSO interfaces |  |  | Open |  |  |  |  | 26-06-2025: Awaiting NSO Team |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | 472BSS | Applications/Tools | OPEN | [6 empty] | 1
11 | T10 | 472 | NA |  |  |  | BSS | Integration | GeM Portal |  |  | Open | [7 empty] | Manoj Nibrad |  | Open | Open | On-Hold confirmation mail received from NOC Director | 2025-07-16 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\BSS\Artifact_T10 | [6 empty] | 472BSS | Applications/Tools | CLOSED |  |  |  | 2025-07-16 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\BSS\Artifact_T10 |  | 1
12 | T11 | 472 | NA |  |  |  | BSS | Development and unit testing | Import Sub-Departments, Import Leads, Campaign Management, Opportunity/Quote/order Management, order booking and Service Order workflow for tested services |  |  | Open |  |  |  |  | 29-08-2025: All points are completed Import Sub-Departments, Import Leads, Opportunity/Quote/order Management, order booking and Service Order workflow for tested services Demo to be conducted to TFIBER. "Campaign Management" is Pending where inputs are required from TFIBER Business team 26-06-2025: Awaiting few inputs from TFIBER |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | 472BSS | Applications/Tools | OPEN | [6 empty] | 1
13 | T12 | 472 | NA |  |  |  | BSS | Development and unit testing | Product/Service Catalogue integration |  |  | Open |  |  |  |  | 29-08-2025: Feature is available to admin User(Product Team) to configure new product based on requirement. BSS Team will provide Demo to the TFIBER (business team([Uday]/Solution Team[Sanjay]) for their acceptance. 26-06-2025: Artifacts submitted. Closure review is pending with TFIBER |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | 472BSS | Applications/Tools | OPEN | [6 empty] | 1
14 | T13 | 472 | NA |  |  |  | BSS | Development and unit testing | Billing, Discounts & Adjustments, Invoice generation, Bill Formatting |  |  | Open |  |  |  |  | 29-08-2025: Feature is made available in the BSS application, BSS Team will provide demo to TFIBER Team (Business [Uday] & Finance[Bhaskar]) 26-06-2025: Artifacts submitted. Closure review is pending with TFIBER |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | 472BSS | Applications/Tools | OPEN | [6 empty] | 1
15 | T14 | 472 | NA |  |  |  | BSS | Development and unit testing | Feasibility API response from OSS for service provisioning request |  |  | Open |  |  |  |  | 29-08-2025: Feaibility API is already integrated with BSS and demonstrated in GIBB demo and it is applicable for all products. 26-06-2025: Artifacts submitted. Closure review is pending with TFIBER |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | 472BSS | Applications/Tools | OPEN | [6 empty] | 1
16 | T15 | 472 | NA |  |  |  | BSS | Development and unit testing | SMS notification, email gateway, Field engineer mobile app readiness |  |  | Open |  |  |  |  | 29-08-2025: Integration is already completed and applicable for all product same has demonstrated to TFIBER during GIBB demo session. 26-06-2025: Artifacts submitted. Closure review is pending with TFIBER |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | 472BSS | Applications/Tools | OPEN | [6 empty] | 1
17 | T16 | 472 | NA |  |  |  | BSS | Development and unit testing | Service Assurance and trouble tickets |  |  | Open |  |  |  |  | 29-08-2025: Integration with Service Manager is done for technical ticket and BSS have functionality to handle the non-technical ticket in BSS itself. BSS team will demonstrate this functionality to TFIBER. Sanjay Sir needs to confirm demo date. 26-06-2025: Artifacts submitted. Closure review is pending with TFIBER |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | 472BSS | Applications/Tools | OPEN | [6 empty] | 1
18 | T17 | 472 | NA |  |  |  | BSS | Development and unit testing | Customer Self care portal development for T-CELL, T-NET, L0 |  |  | Open |  |  |  |  | 29-08-2025: Webportal is available. BSS team needs to demonstrate to TFIBER team. Sanjay Sir needs to confirm demo date. 26-06-2025: Artifacts submitted. Closure review is pending with TFIBER |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | 472BSS | Applications/Tools | OPEN | [6 empty] | 1
19 | T18 | 472 | NA |  |  |  | BSS | Integration | Integration modules Like on board Un-Assist & dependent module to be completed for all products from system to be initiated a workshop and to be closed in next 2 Weeks |  |  | Open |  |  |  |  | 29-08-2025: Seek input from Business team (Uday) and deploy post assisted completion. 26-06-2025: Input awaited from TFIBER |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | 472BSS | Applications/Tools | OPEN | [6 empty] | 1
20 | T19 | 472 | NA |  |  |  | BSS | MoM Action | T-Cell service definition for workflow implementation in BSS for creating Spoke primary and secondary |  |  | Open |  |  |  |  | 29-08-2025:Update product concept note similar to GIBB and share with TFIBER for review 26-06-2025: We can deliver this post getting product concept note from TFIBER |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | 472BSS | Applications/Tools | OPEN | [6 empty] | 1
21 | T20 | 472 | NA |  |  |  | BSS | Development and unit testing | Rules for primary and secondary spoke implementation in BSS- - GP with shortest distance will be primary - To display dropdown and concerned user group to select and confirm |  |  | Open |  |  |  |  | #N/A |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | 472BSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
22 | T21 | 472 | NA |  |  |  | BSS | MoM Action | BSS firewall ports required for Security compliance |  |  | Open |  |  |  |  | BSS has to forward list of Port as per deiffrent modules of application |  |  | Sarmendra |  | Open | WIP | [9 empty] | 472BSS | Applications/Tools | OPEN | [6 empty] | 1
23 | T22 | 472 | NA |  |  |  | BSS | Security | Roadmap for password policy implementation in CSP |  |  | Open |  |  |  |  | Ciriteria for Paswword policy hase been Shared wioth BSS team . BSS team has to implement and submit report for verifications. |  |  | Sarmendra |  | Open | WIP | [9 empty] | 472BSS | Applications/Tools | OPEN | [6 empty] | 1
24 | T23 | 472 | NA |  |  |  | BSS | Security | DMZ requirements for CSP |  |  | Open |  |  |  |  | IP amd URL required by BSS foir NAT through DMZ has been Completed |  |  | Sarmendra |  | Open | WIP | [9 empty] | 472BSS | Applications/Tools | OPEN | [6 empty] | 1
25 | T24 | 472 | NA |  |  |  | BSS | MoM Action | PoP location confirmation usergroup for connectivity to O&M |  |  | Open |  |  |  |  | 29-08-2025: Seek input from O&M team (Umesh) 26-06-2025: Input awaited from TFIBER |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | 472BSS | Applications/Tools | OPEN | [6 empty] | 1
26 | T25 | 472 | NA |  |  |  | BSS | MoM Action | Product concept note configuration in BSS queries to be shared |  |  | Open |  |  |  |  | 29-08-2025: Queries to be prepared and share with TFIBER for discussion. 17-07-2025: Business Team of TFIBER needs to finalize and confirm all product. 26-06-2025: Need Product concept note from TFIBER |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | 472BSS | Applications/Tools | OPEN | [6 empty] | 1
27 | T26 | 472 | NA |  |  |  | BSS | MoM Action | Location id logic for NSO provisioning |  |  | Open |  |  |  |  | 29-08-2025: Ciruit ID logic PPT shared by Sivakumar, needs to use and implement in BSS. 26-06-2025: Timeline 30th July is considering NSO support is available in 2-3 days |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | 472BSS | Applications/Tools | OPEN | [6 empty] | 1
28 | T27 | 472 | NA |  |  |  | BSS | Integration | Tariff plan parameters viz. 5G, 4G finalisation. (BSS should capture QOS parameter & Requirements) |  |  | Open |  |  |  |  | 29-08-2025: Product Can be configured in BSS product catalogue Demo to be given to TFIBER 26-06-2025: Input awaited from TFIBER |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | 472BSS | Applications/Tools | OPEN | [6 empty] | 1
29 | T28 | 472 | NA |  |  |  | IP/MPLS | Functional AT | Internal AT 83% complete. Waiting Cisco to update data sent by Vikram and then we will submit to TPA ( for pending cases, we just need a maintanence window to test as it is impacting activity) This is for ISE |  |  | Open |  |  |  |  | FAT documents were submitted to TPA , However it has some common observation which will be discussed with TPA team by Mr Sharma. Subsequently , correction will be made in FAT doc |  |  | Sarmendra |  | Open | WIP | [9 empty] | 472IP/MPLS | IPMPLS | OPEN | [6 empty] | 1
30 | T29 | 472 | NA |  |  |  | IP/MPLS | Functional AT | CSM is having memory issues. Need to sort it out before we do AT. Working on settling that with Cisco. Memory will be allocated and tested in the first week of July |  |  | Open |  |  |  |  | CSM has been replaced by ASDM |  |  | Sarmendra |  | Open | WIP | [9 empty] | 472IP/MPLS | IPMPLS | OPEN | [6 empty] | 1
31 | T30 | 472 | NA |  |  |  | IP/MPLS | Functional AT | Internal AT 72% complete. Waiting on Cisco to update data sent by Vikram and then we will submit to TPA. ( for pending cases, we just need a maintanence window to test as it is impacting activity) |  |  | Open |  |  |  |  | FAT documents were submitted to TPA , However it has some common observation which will be discussed with TPA team by Mr Sharma. Subsequently , correction will be made in FAT doc |  |  | Sarmendra |  | Open | WIP | [9 empty] | 472IP/MPLS | IPMPLS | OPEN | [6 empty] | 1
32 | T31 | 472 | NA |  |  |  | Security & Regulatory Compliance | Security | Internal Audit for all applications |  |  | Open |  |  |  |  | Application audited partally , howver PT audit couldnot be done due to lack of necessary tools. Same has been requested with LTTS team , but it could not be materialised. |  |  | Sarmendra |  | Open | WIP | [9 empty] | 472Security & Regulatory Compliance | Security | OPEN | [6 empty] | 1
33 | T32 | 472 | NA |  |  |  | Security & Regulatory Compliance | Security | Internal audit for network elements |  |  | Open |  |  |  |  | Network elemants auditted including NOC end points , However PT for same is pending. |  |  | Sarmendra |  | Open | WIP | [9 empty] | 472Security & Regulatory Compliance | Security | OPEN | [6 empty] | 1
34 | T33 | 472 | NA |  |  |  | BSS | Security | Security policies to evolve related to DOT/CDOT etc |  |  | Open |  |  |  |  | 29-08-2025: Collect data from Sivakumar and read user to access the data by DOT. 26-06-2025: Waiting for inputs for multiple deliverables |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | 472BSS | Applications/Tools | OPEN | [6 empty] | 1
35 | T34 | 472 | NA |  |  |  | IP/MPLS | Security | external Audit for all applications (Tfiber will be arranging a partner for third party audit) |  |  | Open |  |  |  |  | Awaited TSTG Audit party to engage |  |  | Sarmendra |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | 472IP/MPLS | IPMPLS | OPEN | [6 empty] | 1
36 | T35 | 472 | NA |  |  |  | IP/MPLS | Security | external audit for network elements(Tfiber will be arranging a partner for third party audit) |  |  | Open |  |  |  |  | Awaited TSTG Audit party to engage |  |  | Sarmendra |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | 472IP/MPLS | IPMPLS | OPEN | [6 empty] | 1
37 | T36 | 472 | NA |  |  |  | Security & Regulatory Compliance | Security | Physical user access |  |  | Open |  |  |  |  | Has completed , Artefacts will be resubmitted. |  |  | Sarmendra |  | Open | REOPENED |  |  | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\NW-Security\T36 | [6 empty] | 472Security & Regulatory Compliance | Security | OPEN |  |  |  |  | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\NW-Security\T36 |  | 1
38 | T37 | 472 | NA |  |  |  | Security & Regulatory Compliance | Security | Virtual user access-VPN |  |  | Open |  |  |  |  | Has completed , Artefacts will be resubmitted. |  |  | Sarmendra |  | Open | REOPENED | [9 empty] | 472Security & Regulatory Compliance | Security | OPEN | [6 empty] | 1
39 | T38 | 472 | NA |  |  |  | Security & Regulatory Compliance | Security | Role based severity access |  |  | Open |  |  |  |  | Completed and Review pending. Artfacts submitted |  |  | Sarmendra |  | Open | WIP | [9 empty] | 472Security & Regulatory Compliance | Security | OPEN | [6 empty] | 1
40 | T39 | 472 | NA |  |  |  | Security & Regulatory Compliance | Security | ISE integration with Cisco elements |  |  | Open |  |  |  |  | Artefacts will be submitted. |  |  | Sarmendra |  |  | CLOSURE REVIEW PENDING | [9 empty] | 472Security & Regulatory Compliance | Security | OPEN |  |  |  |  | Artefacts to be Submitted |  | 1
41 | T40 | 472 | NA |  |  |  | Security & Regulatory Compliance | Regulatory | Regulatory Compliance with respect DoT policies 1. Security Policy-Complied 2. Security Architecture of Telecom Network-Complied 3. Information Security Risk Assessment and Risk Treatment processes and their implementation plan-WIP, Target: Dec 2024 reviewed with customer. 4. Recruitment processes and employee's record-WIP, Target:12-10-2025 5. Controls for effectiveness of security management-WIP, Target: 28 -02-2025 6. Evidence of monitoring, measurement results and management reviews of security management-WIP, Target: 28-02-2025 7. Security Audit programs and audit results-Complied 8. Inventory management and classification of information assets and their handling Completed 9. Procedure for responding to information and network security incidents-WIP, Target: 28-02-2025 - SIRT reviewed 10. Main S/W updation and changes-WIP, Target: 28-02-2025 11. Supply chain of products (HW/SW). To be taken from manufacturer/supplier-Communicated to Sekhar. WIP, Target: 14-02-2025 12. SW details and documentation obtained from manufacturers/supplier-Communicated to Sekhar WIP, Target: 14-02-2025 13. O&M procedures in the form of manual-O&M manual and OEM wise manuals WIP, Target: 14-02-2025 14. Processes for internal and external communication relevant to the security management-WIP, Target: 07-3-2025 |  |  | Open |  |  |  |  | Confirmation of purchase of ISE. License needed to upgrade for HA |  |  | Sarmendra |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | 472Security & Regulatory Compliance | Security | OPEN |  |  |  |  | #VALUE! |  | 1
42 | T41 | 472 | NA |  |  |  | DC-IT | Servers and Strorage (Deployment and Installations) | 1. Compute & Storage |  |  | Open |  |  |  |  | 11-Oct-25: As per the OEM's/SME's request, storage is allocated as per requirements. Artifacts are Captured. OEM Confirmation Emails to be captured as a Reference. |  |  | Ravi Kishore |  | Open | REOPENED |  |  | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\DC IT-Infra\Artifact for - T41 | [6 empty] | 472DC-IT | Network | OPEN | [6 empty] | 1
43 | T42 | 472 | NA |  |  |  | DC-IT | Servers and Strorage (Deployment and Installations) | 2. Virtulization |  |  | Colosed | [7 empty] | Ravi Kishore |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-05-14 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\DC IT-Infra\Artifact for -T42 | [6 empty] | 472DC-IT | Network | CLOSED |  |  |  | 2025-05-14 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\DC IT-Infra\Artifact for -T42 |  | 1
44 | T43 | 472 | NA |  |  |  | DC-IT | Servers and Strorage (Deployment and Installations) | 3. Anti-virus |  |  | Colosed | [7 empty] | Ravi Kishore |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-05-14 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\DC IT-Infra\Artifact for -T43 | [6 empty] | 472DC-IT | Network | CLOSED |  |  |  | 2025-05-14 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\DC IT-Infra\Artifact for -T43 |  | 1
45 | T44 | 472 | NA |  |  |  | DC-IT | Servers and Strorage (Deployment and Installations) | 4. VM's Deployment Application Installations |  |  | Colosed | [7 empty] | Ravi Kishore |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-05-14 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\DC IT-Infra\Artifact for -T44 | [6 empty] | 472DC-IT | Network | CLOSED |  |  |  | 2025-05-14 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\DC IT-Infra\Artifact for -T44 |  | 1
46 | T45 | 472 | NA |  |  |  | DC-IT | Commvault Backup | Application Installation |  |  | Colosed | [7 empty] | Ravi Kishore |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-05-14 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\DC IT-Infra\Artifact for - T45 | [6 empty] | 472DC-IT | Network | CLOSED |  |  |  | 2025-05-14 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\DC IT-Infra\Artifact for - T45 |  | 1
47 | T46 | 472 | NA |  |  |  | DC-IT | Commvault Backup | Application Configuration |  |  | Colosed | [7 empty] | Ravi Kishore |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-05-14 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\DC IT-Infra\Artifact for - T46 | [6 empty] | 472DC-IT | Network | CLOSED |  |  |  | 2025-05-14 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\DC IT-Infra\Artifact for - T46 |  | 1
48 | T47 | 472 | NA |  |  |  | DC-IT | Commvault Backup | Application Installation AT |  |  | Colosed | [7 empty] | Ravi Kishore |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-05-14 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\DC IT-Infra\Artifact for - T47 | [6 empty] | 472DC-IT | Network | CLOSED |  |  |  | 2025-05-14 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\DC IT-Infra\Artifact for - T47 |  | 1
49 | T48 | 472 | NA |  |  |  | DC-IT | Commvault Backup | Application Functional AT |  |  | Open |  |  |  |  | Working on the Extra Test cases which are received from the TPA & T-Fiber. |  |  | Ravi Kishore |  | Open | WIP |  |  | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\DC IT-Infra\Artifact for - T48 | [6 empty] | 472DC-IT | Network | OPEN | [6 empty] | 1
50 | T49 | 472 | NA |  |  |  | DC-IT | LLD | LLD Approved conditionally with few punch points. Updated LLD to be submitted |  |  | Open |  |  |  |  | Working on DC IT-Infra Server and storage-MoM Points received from the T-Fiber. |  |  | Ravi Kishore |  | Open | WIP |  |  | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\DC IT-Infra\Artifact for - T49 | [6 empty] | 472DC-IT | Network | OPEN | [6 empty] | 1
51 | T50 | 472 | NA |  |  |  | DC-IT | MoM Action | Radware , A10 Configuration file needed to be shared to RaviKishore |  |  | Open |  |  |  |  | Artfacts submitted . point Closure on 10 Jul 25 |  |  | Sarmendra |  |  | COMPLETED & APPROVED |  |  | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\NW-Security\T50 | [6 empty] | 472DC-IT | Network | CLOSED |  |  |  |  | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\NW-Security\T50 |  | 1
52 | T51 | 472 | NA |  |  |  | DC-IT | Commvault Backup | Backup retention and Backup activity (such as when incremental backup,full backup are scheduled and time duration required to complete such backup). Application Wise Backup Retention should be as per DOT Guidelines |  |  | Colosed | [7 empty] | Ravi Kishore |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-05-14 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\DC IT-Infra\Artifact for - T51 | [6 empty] | 472DC-IT | Network | CLOSED |  |  |  | 2025-05-14 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\DC IT-Infra\Artifact for - T51 |  | 1
53 | T52 | 472 | NA |  |  |  | DC-IT | Commvault Backup | Backup solution should have hot , cold and archieve storage inorder to decrease the backup size/capacity in long run. |  |  | Colosed | [7 empty] | Ravi Kishore |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-05-14 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\DC IT-Infra\Artifact for - T52 | [6 empty] | 472DC-IT | Network | CLOSED |  |  |  | 2025-05-14 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\DC IT-Infra\Artifact for - T52 |  | 1
54 | T53 | 472 | NA |  |  |  | DC-IT | SSD storage migration – EPNM/PI | EPNM/PI VMs migration to SSD Storage |  |  | Colosed | [7 empty] | Ravi Kishore |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-05-14 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\DC IT-Infra\Artifact for - T53 | [6 empty] | 472DC-IT | Network | CLOSED |  |  |  | 2025-05-14 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\DC IT-Infra\Artifact for - T53 |  | 1
55 | T54 | 472 | NA |  |  |  | DC-IT | SSD storage migration – ISE/FMC | ISE & FMC VMs migration to SSD Storage |  |  | Colosed | [7 empty] | Ravi Kishore |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-05-14 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\DC IT-Infra\Artifact for - T54 | [6 empty] | 472DC-IT | Network | CLOSED |  |  |  | 2025-05-14 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\DC IT-Infra\Artifact for - T54 |  | 1
56 | T55 | 472 | NA |  |  |  | DC-IT | MoM Action | VM Placing should be verified & rectified, Same service VM needs to be placed in different Physical Server/host. |  |  | Colosed | [7 empty] | Ravi Kishore |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-05-14 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\DC IT-Infra\Artifact for - T55 | [6 empty] | 472DC-IT | Network | CLOSED |  |  |  | 2025-05-14 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\DC IT-Infra\Artifact for - T55 |  | 1
57 | T56 | 472 | NA |  |  |  | DC-IT | MoM Action | SOP documents needs to be provided |  |  | Open |  |  |  |  | SOP documents submitted to Operations team. Remaining pending documents to be prepared periodically. |  |  | Ravi Kishore |  | Open | REOPENED |  |  | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\DC IT-Infra\Artifact for - T56 | [6 empty] | 472DC-IT | Network | OPEN | [6 empty] | 1
58 | T57 | 472 | NA |  |  |  | DC-IT | LLD | Approved conditionally with few punch points. Updated LLD to be submitted |  |  | Open |  |  |  |  | 14-Aug-25 : Discussion was done with TPA and Tfiber and submitted updated LLD document. 18-Jun-25 : Updated DC Network LLD submitted on 18-Jun-25 for TFiber review | L&T |  | RS Rao |  |  | COMPLETED & APPROVED | [9 empty] | 472DC-IT | Network | CLOSED |  |  |  | 2025-08-14 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\DC Network LLD V1.7 14-Aug-2025.pdf |  | 1
59 | T58 | 472 | NA |  |  |  | DC-IT | Cisco EPNM | Cisco EPNM infrastructure AT |  |  | Open |  |  |  |  | 22-Sep-25: IPMPLS Domain team to submit detailed remarks on raised queries. 08-Jul-2025 - Sandeep will come back by EoD today on extension of Cisco support renewal 01-Jul-25 : Revised FAT documents submission pending (TPA observations to be included) OEM(Cisco) suport is required to show the new test cases, Inputs provided to OEM on 14th May & 30th Jun. OEM onboarding is in progress & LnT Contracts team coordinating | L&T | RS Rao | RS Rao |  | Open | Open | [9 empty] | 472DC-IT | Network | OPEN | [6 empty] | 1
60 | T59 | 472 | NA |  |  |  | DC-IT | Cisco PI | Cisco prime infrastructure AT |  |  | Open |  |  |  |  | 22-Sep-25: IPMPLS Domain team to submit detailed remarks on raised queries. 08-Jul-2025 - Sandeep will come back by EoD today on extension of Cisco support renewal 01-Jul-25 : Revised FAT documents submission pending (TPA observations to be included) OEM(Cisco) suport is required to show the new test cases, Inputs provided to OEM on 14th May & 30th Jun. OEM onboarding is in progress & LnT Contracts team is coordinating | L&T | RS Rao | RS Rao |  | Open | Open | [9 empty] | 472DC-IT | Network | OPEN | [6 empty] | 1
61 | T60 | 472 | NA |  |  |  | DC-IT | NTP | Installation |  |  | Colosed | [7 empty] | RS Rao |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-05-05 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\Primary NTP - T60,T61,T62.pdf \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\Secondary NTP - T60,T61,T62.pdf | [6 empty] | 472DC-IT | Network | CLOSED |  |  |  | 2025-05-05 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\Primary NTP - T60,T61,T62.pdf \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\Secondary NTP - T60,T61,T62.pdf |  | 1
62 | T61 | 472 | NA |  |  |  | DC-IT | NTP | Configuration |  |  | Colosed | [7 empty] | RS Rao |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-05-05 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\Primary NTP - T60,T61,T62.pdf \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\Secondary NTP - T60,T61,T62.pdf | [6 empty] | 472DC-IT | Network | CLOSED |  |  |  | 2025-05-05 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\Primary NTP - T60,T61,T62.pdf \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\Secondary NTP - T60,T61,T62.pdf |  | 1
63 | T62 | 472 | NA |  |  |  | DC-IT | NTP | NTP Installation AT |  |  | Colosed | [7 empty] | RS Rao |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-05-05 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\Primary NTP - T60,T61,T62.pdf \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\Secondary NTP - T60,T61,T62.pdf | [6 empty] | 472DC-IT | Network | CLOSED |  |  |  | 2025-05-05 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\Primary NTP - T60,T61,T62.pdf \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\Secondary NTP - T60,T61,T62.pdf |  | 1
64 | T63 | 472 | NA |  |  |  | DC-IT | NTP | NTP Functional AT |  |  | Open | [7 empty] | RS Rao |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-07-03 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\NTP FAT & Acceptance - T63.pdf | [6 empty] | 472DC-IT | Network | CLOSED |  |  |  | 2025-07-03 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\NTP FAT & Acceptance - T63.pdf |  | 1
65 | T64 | 472 | NA |  |  |  | DC-IT | Functional AT | DC Network Infra AT |  |  | Open |  |  |  |  | 22-Sep-25: IPMPLS Domain team to submit detailed remarks on raised queries. 08-Jul-2025 - Sandeep will come back by EoD today on extension of Cisco support renewal 01-Jul-25 : Revised FAT documents submission pending (TPA observations to be included) OEM(Cisco) suport is required to show the new test cases, Inputs provided to OEM on 14th May & 30th Jun. OEM onboarding is in progress & LnT Contracts team is coordinating | L&T | RS Rao | RS Rao |  | Open | Open | [9 empty] | 472DC-IT | Network | OPEN | [6 empty] | 1
66 | T65 | 472 | NA |  |  |  | DR | Servers and Strorage (Deployment and Installations) | Virtulization |  |  | Colosed | [7 empty] | Ravi Kishore |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-05-14 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\DR\Artifact for - T65 | [6 empty] | 472DR | DR | CLOSED |  |  |  | 2025-05-14 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\DR\Artifact for - T65 |  | 1
67 | T66 | 472 | NA |  |  |  | DR | DC (TNOC-DR) | Network Readiness |  |  | Colosed | [7 empty] | Ravi Kishore |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-05-14 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\DR\Artifact for - T66 | [6 empty] | 472DR | DR | CLOSED |  |  |  | 2025-05-14 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\DR\Artifact for - T66 |  | 1
68 | T67 | 472 | NA |  |  |  | DR | Mahbubnagar-DR | Network Readiness |  |  | Colosed | [7 empty] | Ravi Kishore |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-05-14 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\DR\Artifact for -T67 | [6 empty] | 472DR | DR | CLOSED |  |  |  | 2025-05-14 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\DR\Artifact for - T66 |  | 1
69 | T68 | 472 | NA |  |  |  | DR | Design & Documentation | LLD: Approved conditionally with few punch points. Updated LLD to be submitted |  |  | Open |  |  |  |  | Working on additional points shared by Tfiber. |  |  | Ravi Kishore |  | Open | WIP |  |  | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\DR\Artifact for -T68 | [6 empty] | 472DR | DR | OPEN | [6 empty] | 1
70 | T69 | 472 | NA |  |  |  | DR | Design & Documentation | HLD: Revised solution to submitted |  |  | Open |  |  |  |  | Working on additional points shared by Tfiber. |  |  | Ravi Kishore |  | Open | WIP |  |  | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\DR\Artifact for -T69 | [6 empty] | 472DR | DR | OPEN | [6 empty] | 1
71 | T70 | 472 | NA |  |  |  | DR | Design & Documentation | DC-DR redunancy Test |  |  | Colosed | [7 empty] | Ravi Kishore |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-05-14 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\DR\Artifact for - T70 | [6 empty] | 472DR | DR | CLOSED |  |  |  | 2025-05-14 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\DR\Artifact for - T70 |  | 1
72 | T71 | 472 | NA |  |  |  | DR | MoM Action | UTM Features (DR FW) |  |  | Open |  |  |  |  | Meeting scheduled with CTRL S to verify the UTM features |  |  | Sarmendra |  | Open | WIP | [9 empty] | 472DR | DR | OPEN | [6 empty] | 1
73 | T72 | 472 | NA |  |  |  | DR | MoM Action | To configure LACP between L3 Switch and Core Router |  |  | Open |  |  |  |  | 11-Oct-25: CtrlS has to give proposal for procurement for addtional BoQ. IT infra SME need to Re-intiate a mail to get BoQ 22-Sep-25: The existing switch which was placed at DR by CtrlS doesnt have feature on LACP Bundling. CtrlS is planning to relplace the exising switch with LACP supported switch. DC Infra admin need to provide tentative timelines for replacement. 08-Jul-2025 Sandeep will ensure on CTRL-S support and update by EoD 01-Jul-25 : Ticket (SR01301726) raised with CtrlS on 27-Jun, Config & testing to be carried out. This is additional task as per CtrlS and commercials may be involved. LnT Contracts team also talking to CtrlS account team to complete the task. 24-Dec-25 : SR01036770 opened with CtrlS for LACP configuration and it is not O&M activity as per CtrlS ops. team. escalated to LnT Contracts team for supoort. | CtrlS | Venkat | Ravi Kishore |  | Open | WIP | [9 empty] | 472DR | DR | OPEN | [6 empty] | 1
74 | T73 | 472 | NA |  |  |  | DR | MoM Action | To configure LACP between Core Router and Firewall |  |  | Open |  |  |  |  | 11-Oct-25: CtrlS has to give proposal for procurement for addtional BoQ. IT infra SME need to Re-intiate a mail to get BoQ 22-Sep-25: The existing switch which was placed at DR by CtrlS doesnt have feature on LACP Bundling. CtrlS is planning to relplace the exising switch with LACP supported switch. DC Infra admin need to provide tentative timelines for replacement. 01-Jul-25 : Ticket (SR01301726) raised with CtrlS on 27-Jun, Config & testing to be carried out. This is additional task as per CtrlS and commercials may be involved. LnT Contracts team also talking to CtrlS account team to complete the task. 24-Dec-25 : SR01036770 opened with CtrlS for LACP configuration and it is not O&M activity as per CtrlS ops. team. escalated to LnT Contracts team for supoort. | CtrlS | Venkat | Ravi Kishore |  | Open | WIP | [9 empty] | 472DR | DR | OPEN | [6 empty] | 1
75 | T74 | 472 | NA |  |  |  | DR | MoM Action | To configure LACP between Firewall and L2 Switch |  |  | Open |  |  |  |  | 11-Oct-25: CtrlS has to give proposal for procurement for addtional BoQ. IT infra SME need to Re-intiate a mail to get BoQ 22-Sep-25: The existing switch which was placed at DR by CtrlS doesnt have feature on LACP Bundling. CtrlS is planning to relplace the exising switch with LACP supported switch. DC Infra admin need to provide tentative timelines for replacement. 01-Jul-25 : Ticket (SR01301726) raised with CtrlS on 27-Jun, Config & testing to be carried out. This is additional task as per CtrlS and commercials may be involved. LnT Contracts team also talking to CtrlS account team to complete the task. 24-Dec-25 : SR01036770 opened with CtrlS for LACP configuration and it is not O&M activity as per CtrlS ops. team. escalated to LnT Contracts team for supoort. | CtrlS | Venkat | Ravi Kishore |  | Open | WIP | [9 empty] | 472DR | DR | OPEN | [6 empty] | 1
76 | T75 | 472 | NA |  |  |  | DR | MoM Action | To confirm on backups for DR Virtual machines |  |  | Colosed | [7 empty] | Ravi Kishore |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-05-14 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\DR\Artifact for - T75 | [6 empty] | 472DR | DR | CLOSED |  |  |  | 2025-05-14 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\DR\Artifact for - T75 |  | 1
77 | T76 | 472 | NA |  |  |  | DR | MoM Action | Backup storage to 25 TB |  |  | Colosed | [7 empty] | Ravi Kishore |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-05-14 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\DR\Artifact for - T76 | [6 empty] | 472DR | DR | CLOSED |  |  |  | 2025-05-14 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\DR\Artifact for - T76 |  | 1
78 | T77 | 472 | NA |  |  |  | DR | MoM Action | To submit the SOPs for DC-DR switchover, DC-DR failover and failback |  |  | Open |  |  |  |  | Tejas, Nokia, GIS & Ciena MCP documnets are received. Remaining all Applications domains SOP's to be updated. |  |  | Ravi Kishore |  | Open | REOPENED |  |  | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\DR\Artifact for - T77 | [6 empty] | 472DR | DR | OPEN | [6 empty] | 1
79 | T78 | 472 | NA |  |  |  | DR | MoM Action | to monitor the DR Servers |  |  | Open |  |  |  |  | DR servers monitoring through DR vCentre happening. DR is maintained by CtrlS team as per contract. Feasibility to be checked to integrated through OSS OBM. |  |  | Ravi Kishore |  | Open | WIP |  |  | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\DR\Artifact for - T78 | [6 empty] | 472DR | DR | OPEN | [6 empty] | 1
80 | T79 | 472 | NA |  |  |  | DR | MoM Action | To confirm that DNS switchover between DC and DR locations should be automatic |  |  | Colosed | [7 empty] | Ravi Kishore |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-05-14 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\DR\Artifact for - T79 | [6 empty] | 472DR | DR | CLOSED |  |  |  | 2025-05-14 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\DR\Artifact for - T79 |  | 1
81 | T80 | 472 | NA |  |  |  | DR | MoM Action | Mahubnagar as NTP |  |  | Colosed | [7 empty] | RS Rao |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-05-05 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\Primary NTP - T60,T61,T62.pdf \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\Secondary NTP - T60,T61,T62.pdf | [6 empty] | 472DR | DR | CLOSED |  |  |  | 2025-05-05 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\Primary NTP - T60,T61,T62.pdf \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\Secondary NTP - T60,T61,T62.pdf |  | 1
82 | T81 | 472 | NA |  |  |  | DR | Configuration | All application to be migrated to implement DR LB configuration |  |  | Open |  |  |  |  | 11-Oct-25: Approved DR HLD document to be shared with T Fiber for further discussion. Noikia app is integrated with DR LB . Balance application migration on DR LB is in Pipeline |  |  | Ravi Kishore |  | Open | WIP | [9 empty] | 472DR | DR | OPEN | [6 empty] | 1
83 | T82 | 472 | NA |  |  |  | DR | MoM Action | To confirm the applications which support Veem Replication for Reconfiguration |  |  | Colosed | [7 empty] | Ravi Kishore |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-05-14 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\DR\Artifact for - T82 | [6 empty] | 472DR | DR | CLOSED |  |  |  | 2025-05-14 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\DR\Artifact for - T82 |  | 1
84 | T83 | 472 | NA |  |  |  | DWDM | Network Deployment & integration | Zonal Links Integration (12/15) |  |  | Open |  |  |  |  | 20-Sep-25: Nirmal, Jainoor, Gudihatnoor & Bhimni RFE pending due to forest permission 31-July-2025:As per discussion with Ramanaiah sir, need to discuss these points with T Fiber Project team for further action, till that time this point kept on hold Depend on 04 Facilities RFE in Pkg-C Asifabad - Warangal & Karimnagar - Asifabad - Links integrated as per interim plan, actual integration pending Nizamabad - Asifabad - E2E link integration pending 28th-Apr'25: As per Sandeep Sanmani - Forest permission still pending 6/25/2025: Status is same no visibility on forest permission, Target date would be D+21 05-July-25: No progress on the forest permission | T Fiber | Srinivas Jukuri(Project) | Suresh Kumar |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | 472DWDM | DWDM | OPEN | [6 empty] | 1
85 | T84 | 472 | NA |  |  |  | DWDM | Network Deployment & integration | Nodes Live & Operational (67/71) |  |  | Open |  |  |  |  | 31-July-2025:As per discussion with Ramanaiah sir, need to discuss these points with T Fiber Project team for further action, till that time this point kept on hold Nirmal, Jainoor, Gudihatnoor & Bhimni RFE pending due to forest permission 28th-Apr'25: As per Sandeep Sanmani - Forest permission still pending 15-06-25: No progress on the permission, target - D+15 05-July-25: No progress on the forest permission | T Fiber | Srinivas Jukuri(Project) | Suresh Kumar |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | 472DWDM | DWDM | OPEN | [6 empty] | 1
86 | T85 | 472 | NA |  |  |  | DWDM | Network Deployment & integration | Zonal Rings readiness with 1+R protection (5/7) |  |  | Open |  |  |  |  | 31-July-2025:As per discussion with Ramanaiah sir, need to discuss these points with T Fiber Project team for further action, till that time this point kept on hold 02 rings depend on 04 Facilities RFE readiness in Pkg-C, which is pending due to forest permission 28th-Apr'25: As per Sandeep Sanmani - Forest permission still pending 6/25/2025: No visibility on forest permission, target date would be D+30 05-July-25: No progress on the forest permission | T Fiber | Srinivas Jukuri(Project) | Suresh Kumar |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | 472DWDM | DWDM | OPEN | [6 empty] | 1
87 | T86 | 472 | NA |  |  |  | DWDM | Network Deployment & AT Status | Nodal AT (67/71) |  |  | Open |  |  |  |  | 31-July-2025:As per discussion with Ramanaiah sir, need to discuss these points with T Fiber Project team for further action, till that time this point kept on hold Nirmal, Jainoor, Gudihatnoor & Bhimni RFE pending due to forest permission 28th-Apr'25: As per Sandeep Sanmani - Forest permission still pending 15-06-25: No progress on the permission, target - D+15 05-July-25: No progress on the forest permission | T Fiber | Srinivas Jukuri(Project) | Suresh Kumar |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | 472DWDM | DWDM | OPEN | [6 empty] | 1
88 | T87 | 472 | NA |  |  |  | DWDM | Network Deployment & integration | Mandal Ring Integration through OADM |  |  | Open |  |  |  |  | 31-July-2025:As per discussion with Ramanaiah sir, need to discuss these points with T Fiber Project team for further action, till that time this point kept on hold Mandal services are provisioned (10G) as per integration plan by all packages 6/25/2025: 203 services provisioned out of 270 planned. Remaining can be provisioned as per the requirement | T Fiber | Srinivas Jukuri(Project) | Suresh Kumar |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | 472DWDM | DWDM | OPEN | [6 empty] | 1
89 | T88 | 472 | NA |  |  |  | DWDM | Network Deployment & AT Status | Zonal Link AT (7/15) |  |  | Open |  |  |  |  | 31-July-2025:As per discussion with Ramanaiah sir, need to discuss these points with T Fiber Project team for further action, till that time this point kept on hold 04 Link AT's approved by T Fiber and 03 Link AT's pending due to letter from Ciena awaited (No impact due to ILA to OADM upgradation) 05 Link AT pending due to high losses in the spans, depend on all packages 02 Links integrated as per interim plan, so not considered for Link AT 20May'25: Declaration letter submitted to T Fiber for 03 links AT approval 25-06-2025: Dependancy on field, no progress. 30-June-2025: As discussed in the meeting, need to arrange meeting with all stakeholders | All Packages |  | Suresh Kumar |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | 472DWDM | DWDM | OPEN |  |  | 20-Sep-25: Mr.Suresh will update the status |  |  |  | 1
90 | T89 | 472 | NA |  |  |  | DWDM | Design & Documentation | HLD (Revised) with OADM Solution |  |  | Colosed | [7 empty] | Suresh Kumar |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-05-06 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\DWDM\Artefact - T89 | [6 empty] | 472DWDM | DWDM | CLOSED |  |  |  | 2025-05-06 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\DWDM\Artefact - T89 |  | 1
91 | T90 | 472 | NA |  |  |  | DWDM | Design & Documentation | LLD (Revised) with OADM Solution (Ciena) |  |  | Colosed | [7 empty] | Suresh Kumar |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-05-06 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\DWDM\Artefact - T90 | [6 empty] | 472DWDM | DWDM | CLOSED |  |  |  | 2025-05-06 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\DWDM\Artefact - T90 |  | 1
92 | T91 | 472 | NA |  |  |  | DWDM | Design & Documentation | Nodal ATP |  |  | Colosed | [7 empty] | Suresh Kumar |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-05-06 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\DWDM\Artefact - T91 & T92 | [6 empty] | 472DWDM | DWDM | CLOSED |  |  |  | 2025-05-06 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\DWDM\Artefact - T91 & T92 |  | 1
93 | T92 | 472 | NA |  |  |  | DWDM | Design & Documentation | Link ATP |  |  | Colosed | [7 empty] | Suresh Kumar |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-05-06 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\DWDM\Artefact - T91 & T92 | [6 empty] | 472DWDM | DWDM | CLOSED |  |  |  | 2025-05-06 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\DWDM\Artefact - T91 & T92 |  | 1
94 | T93 | 472 | NA |  |  |  | DWDM | Design & Documentation | Ring ATP |  |  | Colosed | [7 empty] | Suresh Kumar |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-05-06 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\DWDM\Artefact - T93 | [6 empty] | 472DWDM | DWDM | CLOSED |  |  |  | 2025-05-06 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\DWDM\Artefact - T93 |  | 1
95 | T94 | 472 | NA |  |  |  | DWDM | Design & Documentation | DWDM EMS (MCP) Functional ATP |  |  | Open |  |  |  |  | 20-Sep-25: MCP FAT document submitted to TPA on XX-XX-XXXX. Meeting need to be scheduled on 22-Sep-25 with TPA to get the clarifications on delay. 13-Sep-25: Response awaited from TPA team 29-August-2025: Spoken with Mr. Bijju, response awaited 26-July-25: FAT document approval pending 08-July-2025: 1. MCP FAT document prepared as per RFP requirements and TPA remarks 2. 100G traffic throughput will be shown during Ring ATP 07-July-2025: 1. SME not aware of MCP FAT Check list, but prepared FAT document and sent to TPA for validation 05-July-2025: Submitted AT document to T Fiber TPA 30-June-2025: target to submit by 2nd July'25, based on OEM reply Revised version to be submitted as per T Fiber remarks on 29th Apr'25 | TPA | Biju | Suresh Kumar |  | Open | WIP | [9 empty] | 472DWDM | DWDM | OPEN |  |  | Pending from TPA |  |  |  | 1
96 | T95 | 472 | NA |  |  |  | DWDM | Integration with OSS | DWDM Network Alarms Integration |  |  | Colosed | [7 empty] | Suresh Kumar |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-05-06 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\DWDM\Artefact - T95 | [6 empty] | 472DWDM | DWDM | CLOSED |  |  |  | 2025-05-06 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\DWDM\Artefact - T95 |  | 1
97 | T96 | 472 | NA |  |  |  | DWDM | Integration with OSS | Hardware Inventory Integration in HPE OSS |  |  | Colosed | [7 empty] | Suresh Kumar |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-05-06 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\DWDM\Artefact - T96 | [6 empty] | 472DWDM | DWDM | CLOSED |  |  |  | 2025-05-06 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\DWDM\Artefact - T96 |  | 1
98 | T97 | 472 | NA |  |  |  | DWDM | Integration with OSS | DWDM Network Topology |  |  | Open |  |  |  |  | 26-July-2025: HPE conveyed that Topology border unable to make bold or hilight 12-July-2025: Update awaited from HPE 07-July-2025: Topology is visible but border is not highlighted. HP checking for the possibility to impose of border map on topology. Required 02 weeks post confirmation 05-July-2025: In discussion with HPE, required 02 weeks post confirmation, 21st July 30-June-2025: As discussed with Suresh P checking with HPE. Tentative date: 16th July. As discussed in the meeting, call to be arranged along with OSS SME and HP team | HPE | Anand | Suresh Kumar |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | 472DWDM | DWDM | OPEN | [6 empty] | 1
99 | T98 | 472 | NA |  |  |  | DWDM | Integration with OSS | Auto Ticket & RCA for Fiber Cuts |  |  | Colosed | [7 empty] | Suresh Kumar |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-05-06 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\DWDM\Artefact - T98 | [6 empty] | 472DWDM | DWDM | CLOSED |  |  |  | 2025-05-06 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\DWDM\Artefact - T98 |  | 1
100 | T99 | 472 | NA |  |  |  | DWDM | Integration with OSS | Auto Ticket & RCA for Hardware Failures |  |  | Open | [7 empty] | Suresh Kumar |  |  | COMPLETED & APPROVED | [9 empty] | 472DWDM | DWDM | Open |  |  |  |  | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\DWDM\Artefact - T99 |  | 1
101 | T100 | 472 | NA |  |  |  | DWDM | Integration with OSS | Auto Ticket & RCA for Infra Failures |  |  | Open |  |  |  |  | 20-Sep-25: Required configuration changes was done by HPE team. DWDM team will validate and confirm by 23-Sep-25 13-09-25: Few issues observed, corrected by HP. Validation is in progress 10-08-2025: HP team confirmed cause of failure updated, validation is in progress 26-July-2025: Raised the concerns to HP team, cause of failure yet to update by them, Target date awaited9 12-July-2025: Configuration updated in production and RCA TT's for node down are generating. But having issue in cause of failure, same informed to HP team. Target date - 18-07-25 05-July-2025: Cofiguration in production planned on 8th July'25 30-June-25: WIP with HPE, target date 09-07-25 As discussed in the meeting, call to be arranged along with OSS SME and HP team 15-06-2025: WIP with HPE, target date 30-06-2025 21-05-2025: RCA Yet to be started by HPE, date: 30th June 2025 30APR'25: Node down Auto TT is ok but RCA pending | L&T |  | Suresh Kumar |  |  | COMPLETED & APPROVED | [9 empty] | 472DWDM | DWDM | CLOSED |  |  |  | 2025-09-23 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\DWDM\Artefact 100 |  | 1
102 | T101 | 472 | NA |  |  |  | DWDM | Integration with OSS | Network and service performance monitoring KPIs report in HPE OSS |  |  | Colosed | [7 empty] | Suresh Kumar |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-05-06 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\DWDM\Artefact - T101 | [6 empty] | 472DWDM | DWDM | CLOSED |  |  |  | 2025-05-06 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\DWDM\Artefact - T101 |  | 1
103 | T102 | 472 | NA |  |  |  | DWDM | Integration with OSS | Bandwidth Utilization Data in HPE OSS |  |  | Colosed | [7 empty] | Suresh Kumar |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-05-06 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\DWDM\Artefact - T102 | [6 empty] | 472DWDM | DWDM | CLOSED |  |  |  | 2025-05-06 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\DWDM\Artefact - T102 |  | 1
104 | T103 | 472 | NA |  |  |  | DWDM | Integration with OSS | Service Inventory Data Availibilty in HPE OSS |  |  | Open |  |  |  |  | Post 24.06.25 review and direction, working for a alternate options for NSO. will come back as earliest with closure plan. | NSO | Jayanth | Suresh Kumar |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | 472DWDM | DWDM | OPEN | [6 empty] | 1
105 | T104 | 472 | NA |  |  |  | DWDM | Integration with OSS | Planned Event Service Impact analysis report |  |  | Open |  |  |  |  | Post 24.06.25 review and direction, working for a alternate options for NSO. will come back as earliest with closure plan. | NSO | Jayanth | Suresh Kumar |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | 472DWDM | DWDM | OPEN | [6 empty] | 1
106 | T105 | 472 | NA |  |  |  | DWDM | Integration with NSO | 1+1 , 1+0 and 1+R service provisioning testing through NSO |  |  | Open |  |  |  |  | Post 24.06.25 review and direction, working for a alternate options for NSO. will come back as earliest with closure plan. | NSO | Jayanth | Suresh Kumar |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | 472DWDM | DWDM | OPEN | [6 empty] | 1
107 | T108 | 472 | NA |  |  |  | GIS | Data gathering | Data Gathering for RFS Mandals |  |  | Open | Conflict |  |  |  | 256 Mandal uploaded and AT Completed for 250 Mandals,Ongoing & Approved |  |  | Kaushalendra Kumar |  | Open | Ongoing | Approval Email received from NOC Director & TPA | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T108 | [6 empty] | 472GIS | Applications/Tools | #N/A |  |  |  | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T108 | Ongoing Activity | 1
108 | T109 | 472 | NA |  |  |  | GIS | Data gathering | Data Upload of RFS Mandals |  |  | Open | Conflict |  |  |  | 256 Mandal uploaded and AT Completed for 250 Mandals,Ongoing & Approved |  |  | Kaushalendra Kumar |  | Open | Ongoing | Approval Email received from NOC Director & TPA | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T109 | [6 empty] | 472GIS | Applications/Tools | #N/A |  |  |  | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T109 | Ongoing Activity | 1
109 | T110 | 472 | NA |  |  |  | GIS | Basic Readiness | Each Package 5 Mandal (Total-15 Mandal) Upload |  |  | Colosed |  | 1 |  |  | As a PoC, 15 Mandals data uploaded for testing purpose |  |  | Kaushalendra Kumar |  |  | Completed & Approved | Approval Email received from NOC Director & TPA | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T110 | [6 empty] | 472GIS | Applications/Tools | CLOSED |  |  |  | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T110 |  | 1
110 | T111 | 472 | NA |  |  |  | GIS | Deployment | GIS Hardware & Software deployment at DC |  |  | Colosed |  | 1 |  |  | HA Re-Testing Planned with TPA & TFIBER on 2nd June 2025 |  |  | Kaushalendra Kumar |  |  | Completed & Approved | Approval Email received from NOC Director & TPA | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T111 | [6 empty] | 472GIS | Applications/Tools | CLOSED |  |  |  | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T111 |  | 1
111 | T112 | 472 | NA |  |  |  | GIS | Deployment | High Availability & Load Balancer Testing |  |  | Open |  |  |  |  | Awaiting for approval from TFIBER & TPA |  |  | Kaushalendra Kumar |  |  | Completed & Approved | Approved By TFIBER NOC AD | 2025-07-07 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T112 | [6 empty] | 472GIS | Applications/Tools | CLOSED |  |  |  | 2025-07-07 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T112 |  | 1
112 | T113 | 472 | NA |  |  |  | GIS | Deployment | PCs & Licences (G-tech, DI, Geo Media) |  |  | Open |  |  |  |  | Tool & PCs has been installed in NOC GIS room. for Licesnes dependecy on T FIber. During the meeting, the Managing Director of T-Fiber directed that only the minimum number of additional licenses will be procured, and T-Fiber will handle the procurement |  |  | Kaushalendra Kumar |  |  | Completed & Approved |  |  | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T113 | [6 empty] | 472GIS | Applications/Tools | CLOSED |  |  |  | After Jun-25 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T113 |  | 1
113 | T114 | 472 | NA |  |  |  | GIS | Deployment | G-Tech |  |  | Colosed |  | 1 | [5 empty] | Kaushalendra Kumar |  |  | Completed & Approved | Approval Email received from NOC Director & TPA | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T114 | [6 empty] | 472GIS | Applications/Tools | CLOSED |  |  |  | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T114 |  | 1
114 | T115 | 472 | NA |  |  |  | GIS | Deployment | Network Portal |  |  | Colosed |  | 1 |  |  | Network Portal in Production and provided by the approval NoC team but need to demonstarte for Core team |  |  | Kaushalendra Kumar |  |  | Completed & Approved | Approval Email received from NOC Director & TPA | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T115 | [6 empty] | 472GIS | Applications/Tools | CLOSED |  |  |  | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T115 |  | 1
115 | T116 | 472 | NA |  |  |  | GIS | Deployment | Mobile App |  |  | Colosed |  | 1 |  |  | Mobile App in Production and provided by the approval NoC team but need to demonstarte for Core team |  |  | Kaushalendra Kumar |  |  | Completed & Approved | Approval Email received from NOC Director & TPA | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T116 | [6 empty] | 472GIS | Applications/Tools | CLOSED |  |  |  | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T116 |  | 1
116 | T117 | 472 | NA |  |  |  | GIS | DC-DR | Requirement Vs Solution |  |  | Open |  |  |  |  | #N/A |  |  | Kaushalendra Kumar |  |  | Completed & Approved | Completed & Approved by TNOC-AD | 2025-07-09 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T117 | [6 empty] | 472GIS | Applications/Tools | CLOSED |  |  |  | 2025-07-09 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T117 |  | 1
117 | T118 | 472 | NA |  |  |  | GIS | DC-DR | DC-DR Testing |  |  | Open |  |  |  |  | DC-DR Testing completed & Document has been kept on share drive,Awaiting TFIBER Approval |  |  | Kaushalendra Kumar |  |  | Completed & Approved | Completed & Approved by TNOC-AD | 2025-07-09 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T118 | [6 empty] | 472GIS | Applications/Tools | CLOSED |  |  |  | 2025-07-09 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T118 |  | 1
118 | T119 | 472 | NA |  |  |  | GIS | Basic Readiness | Google Map API configuration |  |  | Colosed |  | 1 | [5 empty] | Kaushalendra Kumar |  |  | Completed & Approved | Approval Email received from NOC Director & TPA | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T119 | [6 empty] | 472GIS | Applications/Tools | CLOSED |  |  |  | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T119 |  | 1
119 | T120 | 472 | NA |  |  |  | GIS | Basic Readiness | Fixing of telco Boundaries in GIS |  |  | Colosed |  | 1 | [5 empty] | Kaushalendra Kumar |  |  | Completed & Approved | Approval Email received from NOC Director & TPA | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T120 | [6 empty] | 472GIS | Applications/Tools | CLOSED |  |  |  | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T120 |  | 1
120 | T121 | 472 | NA |  |  |  | GIS | Basic Readiness | Data Model Optimization |  |  | Colosed |  | 1 | [5 empty] | Kaushalendra Kumar |  |  | Completed & Approved | Approval Email received from NOC Director & TPA | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\ | [6 empty] | 472GIS | Applications/Tools | CLOSED |  |  |  | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\ |  | 1
121 | T122 | 472 | NA |  |  |  | GIS | Basic Readiness | ISP/OSP object modelling in tool as per T-Fibre |  |  | Colosed |  | 1 | [5 empty] | Kaushalendra Kumar |  |  | Completed & Approved | Approval Email received from NOC Director & TPA | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T122 | [6 empty] | 472GIS | Applications/Tools | CLOSED |  |  |  | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T122 |  | 1
122 | T123 | 472 | NA |  |  |  | GIS | Basic Readiness | Make & Model deployment against all object as per T-Fibre Project |  |  | Colosed |  | 1 | [5 empty] | Kaushalendra Kumar |  |  | Completed & Approved | Approval Email received from NOC Director & TPA | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T123 | [6 empty] | 472GIS | Applications/Tools | CLOSED |  |  |  | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T123 |  | 1
123 | T124 | 472 | NA |  |  |  | GIS | Basic Readiness | Device (Active/Passive) ( All Type as per T-Fibre Project) & Port Modelling In Tool |  |  | Colosed |  | 1 | [5 empty] | Kaushalendra Kumar |  |  | Completed & Approved | Approval Email received from NOC Director & TPA | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\ | [6 empty] | 472GIS | Applications/Tools | CLOSED |  |  |  | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\ |  | 1
124 | T125 | 472 | NA |  |  |  | GIS | Basic Readiness | Correction In Fttx Network placement rules (GP To GI) |  |  | Colosed |  | 1 | [5 empty] | Kaushalendra Kumar |  |  | Completed & Approved | Approval Email received from NOC Director & TPA | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\ | [6 empty] | 472GIS | Applications/Tools | CLOSED |  |  |  | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\ |  | 1
125 | T126 | 472 | NA |  |  |  | GIS | Basic Readiness | Fine tuning or Enable of Cart feature. ( Pan, Zoom, Vertex, Selection method, ruler Etc.) |  |  | Colosed |  | 1 | [5 empty] | Kaushalendra Kumar |  |  | Completed & Approved | Approval Email received from NOC Director & TPA | 2025-06-02 | D:\T-Fiber Project\Hexagon GIS\Artefacts Of T-NOC Tracker\T126 | [6 empty] | 472GIS | Applications/Tools | CLOSED |  |  |  | 2025-06-02 | D:\T-Fiber Project\Hexagon GIS\Artefacts Of T-NOC Tracker\T126 |  | 1
126 | T127 | 472 | NA |  |  |  | GIS | Basic Readiness | Trace Feature ( Link/Spare/Topology) |  |  | Colosed |  | 1 | [5 empty] | Kaushalendra Kumar |  |  | Completed & Approved | Approval Email received from NOC Director & TPA | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T127 | [6 empty] | 472GIS | Applications/Tools | CLOSED |  |  |  | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T127 |  | 1
127 | T128 | 472 | NA |  |  |  | GIS | Basic Readiness | Reports (Fibre Utilisation, BOQ, Area selection, ISP/OSP Quantify) |  |  | Colosed |  | 1 | [5 empty] | Kaushalendra Kumar |  |  | Completed & Approved | Approval Email received from NOC Director & TPA | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T128 | [6 empty] | 472GIS | Applications/Tools | CLOSED |  |  |  | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T128 |  | 1
128 | T129 | 472 | NA |  |  |  | GIS | Basic Readiness | Document/Image Upload feature |  |  | Colosed |  | 1 | [5 empty] | Kaushalendra Kumar |  |  | Completed & Approved | Approval Email received from NOC Director & TPA | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\ | [6 empty] | 472GIS | Applications/Tools | CLOSED |  |  |  | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\ |  | 1
129 | T130 | 472 | NA |  |  |  | GIS | Basic Readiness | Port level & Fibre stand lever attribute |  |  | Colosed |  | 1 | [5 empty] | Kaushalendra Kumar |  |  | Completed & Approved | Approval Email received from NOC Director & TPA | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T130 | [6 empty] | 472GIS | Applications/Tools | CLOSED |  |  |  | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T130 |  | 1
130 | T131 | 472 | NA |  |  |  | GIS | Basic Readiness | Topology Highlight feature |  |  | Colosed |  | 1 | [5 empty] | Kaushalendra Kumar |  |  | Completed & Approved | Approval Email received from NOC Director & TPA | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T131 | [6 empty] | 472GIS | Applications/Tools | CLOSED |  |  |  | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T131 |  | 1
131 | T132 | 472 | NA |  |  |  | GIS | Basic Readiness | Data Model G-TECH Alignment |  |  | Colosed |  | 1 | [5 empty] | Kaushalendra Kumar |  |  | Completed & Approved | Approval Email received from NOC Director & TPA | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T132 | [6 empty] | 472GIS | Applications/Tools | CLOSED |  |  |  | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T132 |  | 1
132 | T133 | 472 | NA |  |  |  | GIS | Basic Readiness | DI alignment as per new 35 Layer data model |  |  | Colosed |  | 1 | [5 empty] | Kaushalendra Kumar |  |  | Completed & Approved | Approval Email received from NOC Director & TPA | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\ | [6 empty] | 472GIS | Applications/Tools | CLOSED |  |  |  | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\ |  | 1
133 | T134 | 472 | NA |  |  |  | GIS | Basic Readiness | Active to Passive, Active to active connectivity correction |  |  | Colosed |  | 1 | [5 empty] | Kaushalendra Kumar |  |  | Completed & Approved | Approval Email received from NOC Director & TPA | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T134 | [6 empty] | 472GIS | Applications/Tools | CLOSED |  |  |  | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T134 |  | 1
134 | T135 | 472 | NA |  |  |  | GIS | Basic Readiness | DI processing timing optimisation |  |  | Colosed |  | 1 | [5 empty] | Kaushalendra Kumar |  |  | Completed & Approved | Approval Email received from NOC Director & TPA | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\ | [6 empty] | 472GIS | Applications/Tools | CLOSED |  |  |  | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\ |  | 1
135 | T136 | 472 | NA |  |  |  | GIS | Basic Readiness | Rack to Rack Connectivity |  |  | Colosed |  | 1 | [5 empty] | Kaushalendra Kumar |  |  | Completed & Approved | Approval Email received from NOC Director & TPA | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T136 | [6 empty] | 472GIS | Applications/Tools | CLOSED |  |  |  | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T136 |  | 1
136 | T137 | 472 | NA |  |  |  | GIS | Advance Readiness | Graphical Symbology deployment against all object |  |  | Colosed |  | 1 | [5 empty] | Kaushalendra Kumar |  |  | Completed & Approved | Approval Email received from NOC Director & TPA | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T137 | [6 empty] | 472GIS | Applications/Tools | CLOSED |  |  |  | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T137 |  | 1
137 | T138 | 472 | NA |  |  |  | GIS | Advance Readiness | Fixing Of Labelling (Sequencing & Attributes) |  |  | Colosed |  | 1 | [5 empty] | Kaushalendra Kumar |  |  | Completed & Approved | Approval Email received from NOC Director & TPA | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T138 | [6 empty] | 472GIS | Applications/Tools | CLOSED |  |  |  | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T138 |  | 1
138 | T139 | 472 | NA |  |  |  | GIS | Advance Readiness | Object search options to user |  |  | Colosed |  | 1 | [5 empty] | Kaushalendra Kumar |  |  | Completed & Approved | Approval Email received from NOC Director & TPA | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T139 | [6 empty] | 472GIS | Applications/Tools | CLOSED |  |  |  | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T139 |  | 1
139 | T140 | 472 | NA |  |  |  | GIS | Advance Readiness | G-tech to .shp & Kml conversion |  |  | Colosed |  | 1 | [5 empty] | Kaushalendra Kumar |  |  | Completed & Approved | Approval Email received from NOC Director & TPA | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T140 | [6 empty] | 472GIS | Applications/Tools | CLOSED |  |  |  | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T140 |  | 1
140 | T141 | 472 | NA |  |  |  | GIS | Advance Readiness | Plotting & Print Feature |  |  | Colosed |  | 1 | [5 empty] | Kaushalendra Kumar |  |  | Completed & Approved | Approval Email received from NOC Director & TPA | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T141 | [6 empty] | 472GIS | Applications/Tools | CLOSED |  |  |  | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T141 |  | 1
141 | T142 | 472 | NA |  |  |  | GIS | Advance Readiness | 4 More API from Google Map |  |  | Colosed |  | 1 | [5 empty] | Kaushalendra Kumar |  |  | Completed & Approved | Approval Email received from NOC Director & TPA | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T142 | [6 empty] | 472GIS | Applications/Tools | CLOSED |  |  |  | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T142 |  | 1
142 | T143 | 472 | NA |  |  |  | GIS | Advance Readiness | Fibre Utilisation Reports |  |  | Colosed |  | 1 | [5 empty] | Kaushalendra Kumar |  |  | Completed & Approved | Approval Email received from NOC Director & TPA | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T143 | [6 empty] | 472GIS | Applications/Tools | CLOSED |  |  |  | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T143 |  | 1
143 | T144 | 472 | NA |  |  |  | GIS | Advance Readiness | Consolidated reports from GIS |  |  | Colosed |  | 1 | [5 empty] | Kaushalendra Kumar |  |  | Completed & Approved | Approval Email received from NOC Director & TPA | 2025-06-02 | D:\T-Fiber Project\Hexagon GIS\Artefacts Of T-NOC Tracker\T144 | [6 empty] | 472GIS | Applications/Tools | CLOSED |  |  |  | 2025-06-02 | D:\T-Fiber Project\Hexagon GIS\Artefacts Of T-NOC Tracker\T144 |  | 1
144 | T145 | 472 | NA |  |  |  | GIS | Advance Readiness | Link trace Reports |  |  | Colosed |  | 1 | [5 empty] | Kaushalendra Kumar |  |  | Completed & Approved | Approval Email received from NOC Director & TPA | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T145 | [6 empty] | 472GIS | Applications/Tools | CLOSED |  |  |  | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T145 |  | 1
145 | T146 | 472 | NA |  |  |  | GIS | Advance Readiness | Consolidation/Customization of Dashboard feature in G-tech, Network Portal |  |  | Colosed |  | 1 | [5 empty] | Kaushalendra Kumar |  |  | Completed & Approved | Approval Email received from NOC Director & TPA | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T146 | [6 empty] | 472GIS | Applications/Tools | CLOSED |  |  |  | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T146 |  | 1
146 | T147 | 472 | NA |  |  |  | GIS | Advance Readiness | Network data availability in G-Tech & Network portal & Geo media |  |  | Colosed |  | 1 | [5 empty] | Kaushalendra Kumar |  |  | Completed & Approved | Approval Email received from NOC Director & TPA | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T147 | [6 empty] | 472GIS | Applications/Tools | CLOSED |  |  |  | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T147 |  | 1
147 | T148 | 472 | NA |  |  |  | GIS | Advance Readiness | Final Demo to customer |  |  | Colosed |  | 1 | [5 empty] | Kaushalendra Kumar |  |  | Completed & Approved | Approval Email received from NOC Director & TPA | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T148 | [6 empty] | 472GIS | Applications/Tools | CLOSED |  |  |  | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T148 |  | 1
148 | T149 | 472 | NA |  |  |  | GIS | Mobile Applications | Network availability in Mobile application with G-MAP |  |  | Colosed |  | 1 | [5 empty] | Kaushalendra Kumar |  |  | Completed & Approved | Approval Email received from NOC Director & TPA | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T149 | [6 empty] | 472GIS | Applications/Tools | CLOSED |  |  |  | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T149 |  | 1
149 | T150 | 472 | NA |  |  |  | GIS | Mobile Applications | Red line, Red Point Feature deployment in Mobile application |  |  | Colosed |  | 1 | [5 empty] | Kaushalendra Kumar |  |  | Completed & Approved | Approval Email received from NOC Director & TPA | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T150 | [6 empty] | 472GIS | Applications/Tools | CLOSED |  |  |  | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T150 |  | 1
150 | T151 | 472 | NA |  |  |  | GIS | Mobile Applications | JOB creation testing in GIS tool from GIS Mobile app |  |  | Colosed |  | 1 | [5 empty] | Kaushalendra Kumar |  |  | Completed & Approved | Approval Email received from NOC Director & TPA | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T151 | [6 empty] | 472GIS | Applications/Tools | CLOSED |  |  |  | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T151 |  | 1
151 | T152 | 472 | NA |  |  |  | GIS | Design & Documentation | Feasible Points closure of workshop |  |  | Colosed |  | 1 | [5 empty] | Kaushalendra Kumar |  |  | Completed & Approved | Approval Email received from NOC Director & TPA | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T152 | [6 empty] | 472GIS | Applications/Tools | CLOSED |  |  |  | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T152 |  | 1
152 | T153 | 472 | NA |  |  |  | GIS | Resources | Resources onboarding, Licences arrangement, Workstation plan |  |  | Open |  |  |  |  | Resource & PCs has been deployed in NOC GIS room. for Licesnes dependecy on T FIber. |  |  | Kaushalendra Kumar |  |  | Completed & Approved |  |  | Resources and workstations have already been deployed in the NOC GIS Room. Decisions regarding additional licenses need to be made by L&T and TFIBER | [6 empty] | 472GIS | Applications/Tools | CLOSED |  |  |  | After Jun-25 | Artefacts not Required |  | 1
153 | T154 | 472 | NA |  |  |  | GIS | Data gathering | T-NOC Creation in GIS Tool with connectivity |  |  | Colosed |  | 1 | [5 empty] | Kaushalendra Kumar |  |  | Completed & Approved | Approval Email received from NOC Director & TPA | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T154 | [6 empty] | 472GIS | Applications/Tools | CLOSED |  |  |  | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T154 |  | 1
154 | T155 | 472 | NA |  |  |  | GIS | Design & Documentation | SOP Creation |  |  | Colosed |  | 1 | [5 empty] | Kaushalendra Kumar |  |  | Completed & Approved | Approval Email received from NOC Director & TPA | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T155 | [6 empty] | 472GIS | Applications/Tools | CLOSED |  |  |  | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T155 |  | 1
155 | T156 | 472 | NA |  |  |  | GIS | MoM Action | MB kilometers vs UG and arial to path and over all route length to be added in webapplication |  |  | Colosed |  | 1 | [5 empty] | Kaushalendra Kumar |  |  | Completed & Approved | Approval Email received from NOC Director & TPA | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T156 | [6 empty] | 472GIS | Applications/Tools | CLOSED |  |  |  | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T156 |  | 1
156 | T157 | 472 | NA |  |  |  | GIS | MoM Action | 3 Formats of Lat long (DMS, DMM & Mtr) required in Hexagon tool |  |  | Colosed |  | 1 | [5 empty] | Kaushalendra Kumar |  |  | Completed & Approved | Approval Email received from NOC Director & TPA | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T157 | [6 empty] | 472GIS | Applications/Tools | CLOSED |  |  |  | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T157 |  | 1
157 | T158 | 472 | NA |  |  |  | GIS | MoM Action | GIS LLD submitted to T-Fiber on 02.03.2025, to be discussed with T-Fiber |  |  | Open |  |  |  |  | Resubmission done after discussion. Date-19.03.25. queries on LLD with mail dated 25.03.25 |  |  | Kaushalendra Kumar |  |  | Completed & Approved |  |  | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T158 | [6 empty] | 472GIS | Applications/Tools | CLOSED |  |  |  | After Jun-25 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T158 |  | 1
158 | T159 | 472 | NA |  |  |  | GIS | Integration | Physical Device sync-up with OSS System |  |  | Open |  |  |  |  | Integration with OSS Is WIP |  |  | Kaushalendra Kumar |  | Open | WIP |  |  | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T159 | [6 empty] | 472GIS | Applications/Tools | OPEN |  |  |  |  | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T159 | 2025-10-20 | 1
159 | T160 | 472 | NA |  |  |  | GIS | Integration | Common Span Path |  |  | Open |  |  |  |  | Integration with OSS Is WIP |  |  | Kaushalendra Kumar |  | Open | WIP |  |  | Dependency On Physical Device Syn-up (Integration) & alarm corelation | [6 empty] | 472GIS | Applications/Tools | OPEN |  |  |  |  | Dependency On Physical Device Syn-up (Integration) & alarm corelation | 2025-11-05 | 1
160 | T161 | 472 | NA |  |  |  | GIS | Integration | Auto feasibility |  |  | Open |  |  |  |  | BSS(knot) has demonstrated the Auto Feasibility feature for single location business cases. If, Customer is expecting Bulk feasibility capabilities, which is not a feature of GIS, required external tool. |  |  | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING |  |  | Multiple demonstrations were provided to showcase auto-feasibility during the GIBB demo | [6 empty] | 472GIS | Applications/Tools | OPEN |  |  |  |  | Multiple demonstrations were provided to showcase auto-feasibility during the GIBB demo |  | 1
161 | T162 | 472 | NA |  |  |  | GPON | Tejas-Design & Documentation | Customer Requirement Document |  |  | Colosed | [7 empty] | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T162 | [6 empty] | 472GPON | GPON | CLOSED |  |  |  | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T162 |  | 1
162 | T163 | 472 | NA |  |  |  | GPON | Tejas-Design & Documentation | HLD |  |  | Colosed | [7 empty] | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T163 Please refer Section-3 in E2E Network HLD | [6 empty] | 472GPON | GPON | CLOSED |  |  |  | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T163 Please refer Section-3 in E2E Network HLD |  | 1
163 | T164 | 472 | NA |  |  |  | GPON | Nokkia-Design & Documentation | LLD for 152 Mandals |  |  | Colosed | [7 empty] | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T164 | [6 empty] | 472GPON | GPON | CLOSED |  |  |  | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T164 |  | 1
164 | T165 | 472 | NA |  |  |  | GPON | Tejas | Latest EMS Integration with OSS (Hold due to CR) |  |  | Colosed | [7 empty] | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T165 | [6 empty] | 472GPON | GPON | CLOSED |  |  |  | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T165 |  | 1
165 | T166 | 472 | NA |  |  |  | GPON | Tejas | * Testing done for new build in T-Fiber test lab . * Plan event for OLTs new SW upgradation in production environment. |  |  | Open |  | Tejas OEM | OLT |  | 13-Oct-25: GPON SME has to provide the breakup for all Pending OLT upgradation activities, need to send a mail to concern packages with respective pending OLT upgradation. 20-Sep-25: All the reachable OLT to EMS are upgraded successfully. And Not reachbale OLTs need to be upgraded, There is a dependecny on All 3 Packages field teams to make reachability to EMS. GPON SME need to submit detailed report on Scope vs upgraded and Pending devices breakup(Package wise). | All Packages | Srinivas Kodali(PKG_A), Venu& Mahesh(PKG B&C) | Sayyad Pasha |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | 472GPON | GPON | OPEN | [6 empty] | 1
166 | T167 | 472 | NA |  |  |  | GPON | Tejas | TACACS Feature |  |  | Colosed | [7 empty] | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T167 | [6 empty] | 472GPON | GPON | CLOSED |  |  |  | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T372 |  | 1
167 | T168 | 472 | NA |  |  |  | GPON | Tejas | Authentication & Authorization with RAIDUS |  |  | Colosed | [7 empty] | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T168 | [6 empty] | 472GPON | GPON | CLOSED |  |  |  | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T168 |  | 1
168 | T169 | 472 | NA |  |  |  | GPON | Tejas | EMS authentication & Authorization with Alepo |  |  | Colosed | [7 empty] | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T169 | [6 empty] | 472GPON | GPON | CLOSED |  |  |  | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T169 |  | 1
169 | T170 | 472 | NA |  |  |  | GPON | Nokia | Accounting Feature with New build & Logs filteration |  |  | Colosed | [7 empty] | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T170 | [6 empty] | 472GPON | GPON | CLOSED |  |  |  | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T170 |  | 1
170 | T171 | 472 | NA |  |  |  | GPON | Tejas | Accounting Feature with New build & Logs filteration |  |  | Colosed | [7 empty] | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T171 | [6 empty] | 472GPON | GPON | CLOSED |  |  |  | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T170 |  | 1
171 | T172 | 472 | NA |  |  |  | GPON | Tejas | Tejas EMS ATP |  |  | Colosed | [7 empty] | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T172 | [6 empty] | 472GPON | GPON | CLOSED |  |  |  | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T172 |  | 1
172 | T173 | 472 | NA |  |  |  | GPON | Tejas | DC-DR Switchover Activity |  |  | Colosed | [7 empty] | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T173 | [6 empty] | 472GPON | GPON | CLOSED |  |  |  | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T173 |  | 1
173 | T174 | 472 | NA |  |  |  | GPON | Tejas | NBI API availability for BW query Dependent on new OLT build, which supposed to released on 31- March23. |  |  | Colosed | [7 empty] | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T174 | [6 empty] | 472GPON | GPON | CLOSED |  |  |  | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T174 |  | 1
174 | T175 | 472 | NA |  |  |  | GPON | Nokia | CR for Nokia API integration to close BW query and PMS related issues |  |  | Open |  | Nokia OEM | AMS |  | Having dependency on Service Inventory and NSO | NSO | Jayanth | Sayyad Pasha |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | 472GPON | GPON | OPEN | [6 empty] | 1
175 | T176 | 472 | NA |  |  |  | GPON | Nokia | OLT devices status in OSS is not as per AMS. |  |  | Colosed | [7 empty] | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T176 | [6 empty] | 472GPON | GPON | CLOSED |  |  |  | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T176 |  | 1
176 | T177 | 472 | NA |  |  |  | GPON | Nokia | ONT devices have been recovered and validated as per AMS count. |  |  | Colosed | [7 empty] | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T177 | [6 empty] | 472GPON | GPON | CLOSED |  |  |  | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T177 |  | 1
177 | T178 | 472 | NA |  |  |  | GPON | Nokia | Authentication and authorization have been tested with Nokia devices except CB OLT. |  |  | Colosed | [7 empty] | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T178 | [6 empty] | 472GPON | GPON | CLOSED |  |  |  | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T178 |  | 1
178 | T179 | 472 | NA |  |  |  | GPON | Nokia | Tejas ONT firmware upgradation not happing through Nokia OLT. Joint troubleshooting is required with Tejas and Nokia. |  |  | Colosed | [7 empty] | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T179 | [6 empty] | 472GPON | GPON | CLOSED |  |  |  | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T179 |  | 1
179 | T180 | 472 | NA |  |  |  | GPON | Nokia | Nokia ONT to support NAT, DHCP, both Router and Bridge mode |  |  | Open |  | Nokia OEM | ONT |  | Nokia has provided the SOP, which has been tested and is working as expected. However, Nokia ONTs connected to Tejas OLTs cannot be enabled directly through the Tejas OLT. As discussed with TFiber, we have prepared an SOP for the field team and are currently working on mapping the Nokia ONTs under Tejas OLTs to nearby Nokia OLTs |  |  | Sayyad Pasha |  |  | COMPLETED & APPROVED | [9 empty] | 472GPON | GPON | CLOSED |  |  |  | 2025-09-20 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T180 |  | 1
180 | T181 | 472 | NA |  |  |  | GPON | Nokia | Accounting logs are forwarded to Alepo server, same was reflecting in Alepo server but it was forwarding towards syslog server. |  |  | Colosed | [7 empty] | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T181 | [6 empty] | 472GPON | GPON | CLOSED |  |  |  | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T181 |  | 1
181 | T182 | 472 | NA |  |  |  | GPON | Nokia | Nokia EMS functional ATP to be closed with customer |  |  | Open |  | Nokia OEM | AMS |  | Working with OEM 20-Sep-25: ATP document submitted to TPA, And TPA Shared 12 observations related to RFP compliance.Same has been given to OEM for closure. Nokia team provided clarifications for 10 points and 2 points are WIP. GPON team has to share clarifications of 10 points to TPA and need to confirm timelines for remaining 2 points on 23-Sep-25. | Nokia | Sivakasi | Sayyad Pasha |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | 472GPON | GPON | OPEN | [6 empty] | 1
182 | T183 | 472 | NA |  |  |  | GPON | Nokia | DC-DR Switchover activity need to plan. |  |  | Colosed | [7 empty] | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T183 | [6 empty] | 472GPON | GPON | CLOSED |  |  |  | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T183 |  | 1
183 | T184 | 472 | NA |  |  |  | GPON | Nokia | Nokia OLTs reachability is pending for DR Servers. |  |  | Colosed | [7 empty] | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T184 | [6 empty] | 472GPON | GPON | CLOSED |  |  |  | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T184 |  | 1
184 | T185 | 472 | NA |  |  |  | IP/MPLS | Service Solution | HSI (High Speed Internet to Household) |  |  | Colosed | [7 empty] | RS Rao |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-05-05 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\House Hold HSI Services Design LLD V1.2 - T185.pdf | [6 empty] | 472IP/MPLS | IPMPLS | CLOSED |  |  |  | 2025-05-05 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\House Hold HSI Services Design LLD V1.2 - T185.pdf |  | 1
185 | T186 | 472 | NA |  |  |  | IP/MPLS | Service Solution | IPTV to Household |  |  | Colosed | [7 empty] | RS Rao |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-05-05 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\House Hold IPTV Services Design LLD V1.2 - T186.pdf | [6 empty] | 472IP/MPLS | IPMPLS | CLOSED |  |  |  | 2025-05-05 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\House Hold IPTV Services Design LLD V1.2 - T186.pdf |  | 1
186 | T187 | 472 | NA |  |  |  | IP/MPLS | Service Solution | VOIP to Household |  |  | Colosed | [7 empty] | RS Rao |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-05-05 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\House Hold VoIP Services Design LLD V1.2 - t187.pdf | [6 empty] | 472IP/MPLS | IPMPLS | CLOSED |  |  |  | 2025-05-05 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\House Hold VoIP Services Design LLD V1.2 - t187.pdf |  | 1
187 | T188 | 472 | NA |  |  |  | IP/MPLS | Service Solution | Internet to GI (Govt. Institution) |  |  | Colosed | [7 empty] | RS Rao |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-05-05 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\T-FIBER T-Net for GI Broadband Service Design LLD V1.1 - T188.pdf | [6 empty] | 472IP/MPLS | IPMPLS | CLOSED |  |  |  | 2025-05-05 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\T-FIBER T-Net for GI Broadband Service Design LLD V1.1 - T188.pdf |  | 1
188 | T189 | 472 | NA |  |  |  | IP/MPLS | Service Solution | CCTV Unicast |  |  | Colosed | [7 empty] | RS Rao |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-05-05 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\Centrailzed CCTV Surveillance Monitoring over T-Fiber Network-Solution Doucment_Initial Draft V1.0 - T189.pdf | [6 empty] | 472IP/MPLS | IPMPLS | CLOSED |  |  |  | 2025-05-05 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\Centrailzed CCTV Surveillance Monitoring over T-Fiber Network-Solution Doucment_Initial Draft V1.0 - T189.pdf |  | 1
189 | T190 | 472 | NA |  |  |  | IP/MPLS | Service Solution | CCTV Multicast |  |  | Colosed | [7 empty] | RS Rao |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-05-05 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\CCTV Multicast Solution LLD V1.2 - T190.pdf | [6 empty] | 472IP/MPLS | IPMPLS | CLOSED |  |  |  | 2025-05-05 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\CCTV Multicast Solution LLD V1.2 - T190.pdf |  | 1
190 | T191 | 472 | NA |  |  |  | IP/MPLS | Service Solution | Cell Tower L2VPN |  |  | Colosed | [7 empty] | RS Rao |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-05-05 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\TFIBER T-CELL Service Design & Solution V4.3 T197, T336, T337, T338.pdf | [6 empty] | 472IP/MPLS | IPMPLS | CLOSED |  |  |  | 2025-05-05 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\TFIBER T-CELL Service Design & Solution V4.3 T197, T336, T337, T338.pdf |  | 1
191 | T192 | 472 | NA |  |  |  | IP/MPLS | Service Solution | Dhanush Telemedicine Application |  |  | Colosed | [7 empty] | RS Rao |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-05-05 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\T-FIBER DHANUSH TELEMEDICINE SOLUTION LLD V1.0 - T192.pdf | [6 empty] | 472IP/MPLS | IPMPLS | CLOSED |  |  |  | 2025-05-05 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\T-FIBER DHANUSH TELEMEDICINE SOLUTION LLD V1.0 - T192.pdf |  | 1
192 | T193 | 472 | NA |  |  |  | IP/MPLS | Service Solution | SDC content to Household and GI |  |  | Open |  |  |  |  | 22-Sep-25: Need to review plan and approve 12-Sep-25 : Peering plan submitted as per discussion on 11-Sep-25 01-Jul-25 : Design document submitted with suggested approaches. Require inputs from TFiber to conduct PoC and finalize service design. | T Fiber | Sanjay | RS Rao |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | 472IP/MPLS | IPMPLS | OPEN | [6 empty] | 1
193 | T194 | 472 | NA |  |  |  | BSS | Service Catalogue | Incremental Product/ Services finalization in T-Fiber network |  |  | Open |  |  |  |  | 01-Jul-25 : Dependecy on Tfiber in PCN (Product Concept Note) finalisation. Tracked in BSS action item T12 (part of 472 tracker) |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | 472BSS | Applications/Tools | OPEN | [6 empty] | 1
194 | T195 | 472 | NA |  |  |  | IP/MPLS | Service Provisioning | Service Provisioning PoC for SCCM/NSO - L2, L3 VPN |  |  | Open |  |  |  |  | Post 24.06.25 review and direction, working for a alternate options for NSO. will come back as earliest with closure plan. |  |  | Jayant Madavi |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | 472IP/MPLS | IPMPLS | OPEN | [6 empty] | 1
195 | T196 | 472 | NA |  |  |  | IP/MPLS | Service Provisioning | Service Provisioning PoC for SCCM/NSO - QoS (all scenarios) |  |  | Open |  |  |  |  | Post 24.06.25 review and direction, working for a alternate options for NSO. will come back as earliest with closure plan. |  |  | Jayant Madavi |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | 472IP/MPLS | IPMPLS | OPEN | [6 empty] | 1
196 | T197 | 472 | NA |  |  |  | IP/MPLS | Service Provisioning | Service Provisioning PoC for SCCM/NSO - MVPN (all scenarios) |  |  | Open |  |  |  |  | Post 24.06.25 review and direction, working for a alternate options for NSO. will come back as earliest with closure plan. |  |  | Jayant Madavi |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | 472IP/MPLS | IPMPLS | OPEN | [6 empty] | 1
197 | T198 | 472 | NA |  |  |  | IP/MPLS | Network AT | Simulation and testing network for parameters like network convergence etc |  |  | Open |  |  |  |  | 22-Sep-2025: Need to have discussion on Network AT parameters 8-Jul-2025 - Sandeep will come back by EoD today on extension of Cisco support renewal 01-Jul-25 : OEM(Cisco) suport is required to perform network AT, Inputs provided to OEM. OEM to provide Network AT procedure including all tests and test procedures. OEM onboarding is in progress & LnT Contracts team is coordinating | TPA, T Fiber, L&T | Biju,Sanjay, RS Rao | RS Rao |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | 472IP/MPLS | IPMPLS | OPEN | [6 empty] | 1
198 | T199 | 472 | NA |  |  |  | IP/MPLS | Design & Documentation | HLD |  |  | Colosed | [7 empty] | RS Rao |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-05-05 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\E2E_Network HLD_Part1_V2.0_ 29.10.2020(Approved) - T199.pdf | [6 empty] | 472IP/MPLS | IPMPLS | CLOSED |  |  |  | 2025-05-05 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\E2E_Network HLD_Part1_V2.0_ 29.10.2020(Approved) - T199.pdf |  | 1
199 | T200 | 472 | NA |  |  |  | IP/MPLS | Design & Documentation | Approved conditionally with few punch points. Updated LLD to be submitted |  |  | Open | [5 empty] | Duplicate |  | RS Rao |  |  | COMPLETED & APPROVED | AD-UT, Tfiber (Sanjay ji) | 2025-08-21 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\IP MPLS Network LLD V1.7 14-Aug-2025.pdf | [6 empty] | 472IP/MPLS | IPMPLS | CLOSED |  |  | Duplicate | 2025-08-21 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\IP MPLS Network LLD V1.7 14-Aug-2025.pdf |  | 1
200 | T201 | 472 | NA |  |  |  | IP/MPLS | OSS | FMS Fault Management System (Device, Link ticketing etc) |  |  | Open |  |  |  |  | 22-Sep-25: Auto ticketing verification is depending on OSS, reqiured configguration or changes done in OSS. Now auto ticket is working atrefatcs to be submitted for Node and Link. 08-Jul-25 : Requirement given to OSS for implementation. FMS parameters given 1. Node down (Router, Switch, DC Network Switches, DWDM, OTN, OADM, OLT, UPS) : Field alarm should be received in NNMi. NNMi has to forward the alarm to OBM, NPS and to TeMiP. UCA has to carryout correlation and accordingly pass the root cause to SM to generate TT. once TT is generated it is assigned to respective District Engineer along with mail. After Fault resolution, TT should be resolved in system with alarm clearance and NoC has to close the TT with RFO. Link down, Protocol down, RSP/Card/PSU down, High Temperature, Latency, Packet Loss, Jitter. End-to-end implementation and demonstration pending in OSS | L&T | Suresh Pawar | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | 472IP/MPLS | IPMPLS | OPEN | CLOSURE REVIEW PENDING | 0 |  |  |  |  | 1
201 | T202 | 472 | NA |  |  |  | IP/MPLS | OSS | PMS Performance Management System (Utilization, Errors etc) |  |  | Open |  |  |  |  | 25-Sep-25: Implementation completed, Need to validate and cofirm 07-Jul-25 : Requirement given to OSS for implementation. PMS parameters given - CPU, Memory, Backplane and Link utilization, CRC errors, Optical power, QoS parameters . End-to-end implementation and demonstration pending in OSS | L&T | Suresh Pawar | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | 472IP/MPLS | IPMPLS | OPEN | COMPLETED | 0 |  |  |  |  | 1
202 | T203 | 472 | NA |  |  |  | IP/MPLS | OSS | Dashboard (Network Parameter Dash Boards) |  |  | Open |  |  |  |  | 25-Sep-25: Implementation completed, Need to validate and cofirm 07-Jul-25 : Requirement given to OSS for implementation. Dash Board required - Top CPU, Memory, Link utilization, Temperature, All Critical alarms . Demonstration pending in OSS | L&T | Suresh Pawar | Suresh Pawar |  | Open | WIP | [9 empty] | 472IP/MPLS | IPMPLS | OPEN | OPEN | 0 |  |  |  |  | 1
203 | T204 | 472 | NA |  |  |  | IP/MPLS | OSS | Reports (Invetory, Device avability, Link Availability) |  |  | Open |  |  |  |  | 25-Sep-25: Reports are available in UOC, Artefacts to be submitted for clsore 07-Jul-25 : Requirement given to OSS for implementation. Reports required - Node availability, Link availability, Link utilization, Inventory, CPU utilization, Memory Utilization, Latecy. Demonstration pending in OSS | L&T | Suresh Pawar | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | 472IP/MPLS | IPMPLS | OPEN | COMPLETED | 0 |  |  |  |  | 1
204 | T205 | 472 | NA |  |  |  | NSO | Installation | Installation of NSO Applications |  |  | Open |  |  |  |  | Post 24.06.25 review and direction, working for a alternate options for NSO. will come back as earliest with closure plan. |  |  | Jayant Madavi |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | 472NSO | Applications/Tools | OPEN | [6 empty] | 1
205 | T206 | 472 | NA |  |  |  | NSO | Integration | Integration with Third Party Applications/Nodes |  |  | Open |  |  |  |  | Post 24.06.25 review and direction, working for a alternate options for NSO. will come back as earliest with closure plan. |  |  | Jayant Madavi |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | 472NSO | Applications/Tools | OPEN | [6 empty] | 1
206 | T207 | 472 | NA |  |  |  | NSO | Integration | OSS |  |  | Open |  |  |  |  | Post 24.06.25 review and direction, working for a alternate options for NSO. will come back as earliest with closure plan. |  |  | Jayant Madavi |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | 472NSO | Applications/Tools | OPEN | [6 empty] | 1
207 | T208 | 472 | NA |  |  |  | NSO | Integration | BSS |  |  | Open |  |  |  |  | Post 24.06.25 review and direction, working for a alternate options for NSO. will come back as earliest with closure plan. |  |  | Jayant Madavi |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | 472NSO | Applications/Tools | OPEN | [6 empty] | 1
208 | T209 | 472 | NA |  |  |  | NSO | Integration | Nodes |  |  | Open |  |  |  |  | Post 24.06.25 review and direction, working for a alternate options for NSO. will come back as earliest with closure plan. |  |  | Jayant Madavi |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | 472NSO | Applications/Tools | OPEN | [6 empty] | 1
209 | T210 | 472 | NA |  |  |  | NSO | Integration | EMS-GPON |  |  | Open |  |  |  |  | Post 24.06.25 review and direction, working for a alternate options for NSO. will come back as earliest with closure plan. |  |  | Jayant Madavi |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | 472NSO | Applications/Tools | OPEN | [6 empty] | 1
210 | T211 | 472 | NA |  |  |  | NSO | Integration | EMS-DWDM |  |  | Open |  |  |  |  | Post 24.06.25 review and direction, working for a alternate options for NSO. will come back as earliest with closure plan. |  |  | Jayant Madavi |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | 472NSO | Applications/Tools | OPEN | [6 empty] | 1
211 | T212 | 472 | NA |  |  |  | NSO | Development and unit testing | Service verification and provisioning - IP MPLS |  |  | Open |  |  |  |  | Post 24.06.25 review and direction, working for a alternate options for NSO. will come back as earliest with closure plan. |  |  | Jayant Madavi |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | 472NSO | Applications/Tools | OPEN | [6 empty] | 1
212 | T213 | 472 | NA |  |  |  | NSO | Development and unit testing | Service verification and activation - GPON Nokia and Tejas |  |  | Open |  |  |  |  | Post 24.06.25 review and direction, working for a alternate options for NSO. will come back as earliest with closure plan. |  |  | Jayant Madavi |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | 472NSO | Applications/Tools | OPEN | [6 empty] | 1
213 | T214 | 472 | NA |  |  |  | NSO | Development and unit testing | SCCM provisioning request for HSI, IPTV, T-Wire,T-VPN,VoIP,CCTV SDD |  |  | Open |  |  |  |  | Post 24.06.25 review and direction, working for a alternate options for NSO. will come back as earliest with closure plan. |  |  | Jayant Madavi |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | 472NSO | Applications/Tools | OPEN | [6 empty] | 1
214 | T215 | 472 | NA |  |  |  | NSO | Development and unit testing | NSO module final implementation |  |  | Open |  |  |  |  | Post 24.06.25 review and direction, working for a alternate options for NSO. will come back as earliest with closure plan. |  |  | Jayant Madavi |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | 472NSO | Applications/Tools | OPEN | [6 empty] | 1
215 | T216 | 472 | NA |  |  |  | NSO | Integration | NSO integration with SCCM |  |  | Open |  |  |  |  | Post 24.06.25 review and direction, working for a alternate options for NSO. will come back as earliest with closure plan. |  |  | Jayant Madavi |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | 472NSO | Applications/Tools | OPEN | [6 empty] | 1
216 | T217 | 472 | NA |  |  |  | NSO | MoM Action | Cisco NSO to test all the cisco elements including SG350 Horizontal switch to deliver service |  |  | Open |  |  |  |  | Post 24.06.25 review and direction, working for a alternate options for NSO. will come back as earliest with closure plan. |  |  | Jayant Madavi |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | 472NSO | Applications/Tools | OPEN | [6 empty] | 1
217 | T218 | 472 | NA |  |  |  | NSO | MoM Action | NSO LLD |  |  | Open |  |  |  |  | Post 24.06.25 review and direction, working for a alternate options for NSO. will come back as earliest with closure plan. |  |  | Jayant Madavi |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | 472NSO | Applications/Tools | OPEN | [6 empty] | 1
218 | T219 | 472 | NA |  |  |  | NSO | MoM Action | Service catalog with product concept note for all services with target requirement date. |  |  | Open |  |  |  |  | Post 24.06.25 review and direction, working for a alternate options for NSO. will come back as earliest with closure plan. |  |  | Jayant Madavi |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | 472NSO | Applications/Tools | OPEN | [6 empty] | 1
219 | T220 | 472 | NA |  |  |  | NSO | MoM Action | T-Cell Service definition sign off |  |  | Open |  |  |  |  | Post 24.06.25 review and direction, working for a alternate options for NSO. will come back as earliest with closure plan. |  |  | Jayant Madavi |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | 472NSO | Applications/Tools | OPEN | [6 empty] | 1
220 | T221 | 472 | NA |  |  |  | NSO | MoM Action | MAG/GAC ports reservation feasibility for services booked in BSS with payments made |  |  | Open |  |  |  |  | Post 24.06.25 review and direction, working for a alternate options for NSO. will come back as earliest with closure plan. |  |  | Jayant Madavi |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | 472NSO | Applications/Tools | OPEN | [6 empty] | 1
221 | T222 | 472 | NA |  |  |  | NSO | MoM Action | Tejas NED readiness |  |  | Open |  |  |  |  | Post 24.06.25 review and direction, working for a alternate options for NSO. will come back as earliest with closure plan. |  |  | Jayant Madavi |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | 472NSO | Applications/Tools | OPEN | [6 empty] | 1
222 | T223 | 472 | NA |  |  |  | NSO | MoM Action | IPTV tested needs to be finalised for additional configuration for multicast and tested as per lab availability and final sign off |  |  | Open |  |  |  |  | Post 24.06.25 review and direction, working for a alternate options for NSO. will come back as earliest with closure plan. |  |  | Jayant Madavi |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | 472NSO | Applications/Tools | OPEN | [6 empty] | 1
223 | T224 | 472 | NA |  |  |  | NSO | MoM Action | BSS to provide actual feasibility parameters e.g PE port number(s) from OSS . Right now values are hard-coded . In turn OSS to get these details from GIS. We havent seen an e2e workign scenario on this yet. |  |  | Open |  |  |  |  | Post 24.06.25 review and direction, working for a alternate options for NSO. will come back as earliest with closure plan. |  |  | Jayant Madavi |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | 472NSO | Applications/Tools | OPEN | [6 empty] | 1
224 | T225 | 472 | NA |  |  |  | NSO | MoM Action | VLAN logic : Vlan logic for HSI-SVLAN has beed provided per zone information. But most of deployments are coming with vlan 256 of PIONEER for any service . This needs to be looked at. VLAN ID should be changed to as per plan shared by Aravindhan. |  |  | Open |  |  |  |  | Post 24.06.25 review and direction, working for a alternate options for NSO. will come back as earliest with closure plan. |  |  | Jayant Madavi |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | 472NSO | Applications/Tools | OPEN | [6 empty] | 1
225 | T226 | 472 | NA |  | OSS | OSS | OSS | IPMPLS | Alarm & Auto TT |  |  | Open |  |  |  |  | 1. OT Stack upgrade is under discussion 2. Resync stabilization is WIP : Action Plan to submitted by 9th Sept 2025 |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | 472OSS | Applications/Tools | OPEN | COMPLETED | 1. OT Stack upgrade is under discussion 2. Resync stabilization is WIP : Action Plan to submitted by 9th Sept 2025 |  |  |  |  | 1
226 | T227 | 472 | NA |  | OSS | OSS | OSS | Other Applications Integrations with OSS | Create trouble ticket by BSS CRM |  |  | Colosed | [7 empty] | Suresh Pawar |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-05-26 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\OSS\T227 | [6 empty] | 472OSS | Applications/Tools | CLOSED | COMPLETED & APPROVED | 0 |  | 2025-05-26 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\OSS\T227 |  | 1
227 | T228 | 472 | NA |  | OSS | OSS | OSS | Other Applications Integrations with OSS | Creation of technical incident by Helpdesk |  |  | Open |  |  |  |  | 17-05-2025: Under observation. Seek approval from Sivakumar 26-06-2025: closed from OSS end, help desk to start using |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | 472OSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1
228 | T229 | 472 | NA |  | OSS | OSS | OSS | DWDM Integration with OSS | DWDM Network Alarms integration has been completed in HPE OSS. However, all alarm counts are not in sync with Ciena MCP to HPE vTeMIP. |  |  | Colosed | [7 empty] | Suresh Pawar |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-05-29 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\OSS\T229 | [6 empty] | 472OSS | Applications/Tools | CLOSED | COMPLETED & APPROVED | 0 |  | 2025-05-29 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\OSS\T229 |  | 1
229 | T230 | 472 | NA |  | OSS | OSS | OSS | DWDM Integration with OSS | Hardware inventory integration has been completed in HPE OSS. |  |  | Colosed | [7 empty] | Suresh Pawar |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-05-26 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\OSS\T230 | [6 empty] | 472OSS | Applications/Tools | CLOSED | COMPLETED & APPROVED | 0 |  | 2025-05-26 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\OSS\T230 |  | 1
230 | T231 | 472 | NA |  | OSS | OSS | OSS | DWDM Integration with OSS | Ciena DWDM Network Topology has been created in HPE OSS topology MAP along with neighbour NE details. Adding the geographical map in the background of HPE OSS is possible with openstreet map.. Not posisble to integarted with GIS map |  |  | Open |  |  |  |  | 09-09-2025: topology available but bordering not feasible |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | 472OSS | Applications/Tools | OPEN | COMPLETED | 09-09-2025: topology available but bordering not feasible |  |  | #N/A |  | 1
231 | T232 | 472 | NA |  | OSS | OSS | OSS | DWDM Integration with OSS | Auto Ticket Generation- Fiber Cut |  |  | Colosed |  |  |  |  | 15-09-2025: Demonstrated in the Demo/UAT call |  |  | Suresh Pawar |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-05-26 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\OSS\T232 | [6 empty] | 472OSS | Applications/Tools | CLOSED | COMPLETED & APPROVED | 15-09-2025: Demonstrated in the Demo/UAT call |  | 2025-05-26 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\OSS\T232 |  | 1
232 | T233 | 472 | NA |  | OSS | OSS | OSS | DWDM Integration with OSS | Auto Ticket Generation- Hardwares Failures |  |  | Open | [7 empty] | Suresh Pawar |  |  | COMPLETED & APPROVED |  |  | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\OSS\T233 | [6 empty] | 472OSS | Applications/Tools | CLOSED | COMPLETED & APPROVED | 0 |  |  | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\OSS\T233 |  | 1
233 | T234 | 472 | NA |  | OSS | OSS | OSS | DWDM Integration with OSS | Auto Ticket Generation- Infra Failure |  |  | Colosed | [7 empty] | Suresh Pawar |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-05-26 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\OSS\T234 | [6 empty] | 472OSS | Applications/Tools | CLOSED | COMPLETED & APPROVED | 0 |  | 2025-05-26 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\OSS\T234 |  | 1
234 | T235 | 472 | NA |  | OSS | OSS | OSS | DWDM Integration with OSS | Network and service performance monitoring KPIs report in HPE OSS |  |  | Colosed | [7 empty] | Suresh Pawar |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-05-26 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\OSS\T235 | [6 empty] | 472OSS | Applications/Tools | CLOSED | COMPLETED & APPROVED | 0 |  | 2025-05-26 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\DWDM\Artefact - T101 |  | 1
235 | T236 | 472 | NA |  | OSS | OSS | OSS | DWDM Integration with OSS | Bandwidth utilization data in HPE OSS is available and under validation. |  |  | Colosed | [7 empty] | Suresh Pawar |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-05-26 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\OSS\T236 | [6 empty] | 472OSS | Applications/Tools | CLOSED | COMPLETED & APPROVED | 0 |  | 2025-05-26 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\OSS\T236 |  | 1
236 | T237 | 472 | NA |  | OSS | OSS | OSS | DWDM Integration with OSS | Service inventory data availability in HPE OSS |  |  | Open |  |  |  |  | 17-05-2025: Dependancy on NSO 26-06-2025: Cisco to be onboarded then it will take ~30 days to complete(timeline is given concidering NSO support available on 1st July) |  |  | Suresh Pawar |  | Open | WIP | [9 empty] | 472OSS | Applications/Tools | OPEN | OPEN | 0 |  |  |  |  | 1
237 | T238 | 472 | NA |  | OSS | OSS | OSS | DWDM Integration with OSS | For planned event service impact analysis data / report |  |  | Open |  |  |  |  | 17-05-2025: Dependancy on NSO 26-06-2025: Cisco to be onboarded then it will take ~30 days to complete(timeline is given concidering NSO support available on 1st July) |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | 472OSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1
238 | T239 | 472 | NA |  | OSS | OSS | OSS | IPMPLS Integration with OSS | FMS (Inventory, Alarm, Auto TT) Ref 226 |  |  | Open |  |  |  |  | 24-05-2025:Working with some operational challenges like frequent NNMi and OBM hung issue, queue increase. |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | 472OSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1
239 | T240 | 472 | NA |  | OSS | OSS | OSS | IPMPLS Integration with OSS | PMS reports for IPMPLS domain network elements |  |  | Open |  |  |  |  | 17-05-2025: Data collection rom internal (SME & NOC team) and then OT support is required for NPS to enable all permormance parameters. 24-06-2025: NPS reports available and NOC came back with some observation of wrong data, for which OT has asked evidences which are awaited from NOC |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | 472OSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1
240 | T241 | 472 | NA |  | OSS | OSS | OSS | IPMPLS Integration with OSS | Dashboards for IPMPLS Domain |  |  | Open |  |  |  |  | 17-05-2025: OOB dashboards are already available in NNMi, L&T NOC team needs to review and confirm if any descripancy observed. |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | 472OSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1
241 | T242 | 472 | NA |  | OSS | OSS | OSS | IPMPLS Integration with OSS | Reports |  |  | Open |  |  |  |  | 24-05-2025: Operational Challenges 26-06-2025: Multiple reports are already available, need clarity if anything is missing from IPMPLS |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | 472OSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1
242 | T243 | 472 | NA |  | OSS | OSS | OSS | GPON-NOKIA Integration with OSS | CR for Nokia API integration to close BW query and PMS related issues |  |  | Open |  |  |  |  | 13-Sep-2025: Having dependency on A&O/NSO and service inventory deployment. 29-Aug-2025: Having dependency on A&O/NSO and service inventory deployment. 07-July-2025: L&T Remarks: As per the Tfiber suggestion, this is feasible and will be considered during A&O OEM solution deployemenet. 05-July-2025 : TFiber Comments: Available bandwidth has to be calculated before provisioning service to a customer. Available bandwidth can be achieved either from OSS or from Service Inventory systems- which already have the services provisioned data Internal discussion planned on 07-July-2025 30-June-2025 : To arrange a call with Tfiber for the discussion and conclusion Nokia provided the available upload bandwidth on PON Port but Nokia claiming that devices/AMS does not support to provide the available download bandwidth of a PON Port. This feature is not available with Nokia |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | 472OSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1
243 | T244 | 472 | NA |  | OSS | OSS | OSS | Other Applications Integrations with OSS | Fetch trouble ticket status for ticket(s) by BSS CRM |  |  | Colosed | [7 empty] | Suresh Pawar |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-05-26 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\OSS\T244 | [6 empty] | 472OSS | Applications/Tools | CLOSED | COMPLETED & APPROVED | 0 |  | 2025-05-26 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\OSS\T244 |  | 1
244 | T245 | 472 | NA |  | OSS | OSS | OSS | Passive Infra Integration with OSS | Integration with DG - HPE |  |  | Colosed | [7 empty] | Suresh Pawar |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-05-26 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\OSS\T245 | [6 empty] | 472OSS | Applications/Tools | CLOSED | COMPLETED & APPROVED | 0 |  | 2025-05-26 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\OSS\T245 |  | 1
245 | T246 | 472 | NA |  | OSS | OSS | OSS | Passive Infra Integration with OSS | Integration with UPS - HPE |  |  | Colosed | [7 empty] | Suresh Pawar |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-05-26 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\OSS\T246 | [6 empty] | 472OSS | Applications/Tools | CLOSED | COMPLETED & APPROVED | 0 |  | 2025-05-26 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\OSS\T246 |  | 1
246 | T247 | 472 | NA |  | OSS | OSS | OSS | Other Applications Integrations with OSS | Inventory Synch - Physical devices with GIS |  |  | Open |  |  |  |  | 24-05-2025:WIP with HPE 26-06-2025: To be tested post GIS integration |  |  | Suresh Pawar |  | Open | WIP | [9 empty] | 472OSS | Applications/Tools | OPEN | OPEN | 0 |  |  |  |  | 1
247 | T248 | 472 | NA |  | OSS | OSS | OSS | GPON | Nokia API integration - . PMS ( Chassi OLT ), Inventory, Device Status (ONT ) |  |  | Open |  |  |  |  | 17-05-2025: HPE team will deliver post application upgradation 23-06-2025: for Device status, HPE said the the Nokia alarm format is wrong; post having calls with Nokia HPE reviewing the NBI documentation. 17-07-2025: Solution deplyed for one package, for other 2 package need to raise PE on 22nd July |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | 472OSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1
248 | T249 | 472 | NA |  | OSS | OSS | OSS | GPON-NOKIA Integration with OSS | OLT & ONT devices status in OSS is not as per AMS |  |  | Open |  |  |  |  | 06-06-2025: HPE requested a call with Nokia 11-06-2025: Nokia call happened and inputs were shared with HPE 23-06-2025: Post having calls with Nokia one more time last week they have share NBI documents with HPE today which they are reviewing. 22-07-2025: count matching, confirmation awaited from NOC |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | 472OSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1
249 | T250 | 472 | NA |  | OSS | OSS | OSS | GPON-NOKIA Integration with OSS | ONT devices have been recovered and validated as per AMS count |  |  | Open |  |  |  |  | 15-06-2025: validation pending from NOC |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | 472OSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1
250 | T251 | 472 | NA |  | OSS | OSS | OSS | Other Applications Integrations with OSS | Fetch SLA violation by BSS billing |  |  | Open |  |  |  |  | 26-06-2025: table to exposed with BSS, awating sevice ID from BSS and same needs to implemented in Network | KNOT |  | Suresh Pawar |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | 472OSS | Applications/Tools | OPEN | Not Relevant to OSS | 0 |  |  |  |  | 1
251 | T252 | 472 | NA |  | OSS | OSS | OSS | Other Applications Integrations with OSS | Circuit performance data to BSS CRM |  |  | Open |  |  |  |  | 26-06-2025: table to exposed with BSS, awating sevice ID from BSS and same needs to implemented in Network |  |  | Suresh Pawar |  | Open | WIP | [9 empty] | 472OSS | Applications/Tools | OPEN | Not Relevant to OSS | 0 |  |  |  |  | 1
252 | T253 | 472 | NA |  | OSS | OSS | OSS | DWDM | Alarm Sync issue with MCP |  |  | Colosed | [7 empty] | Suresh Pawar |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-05-29 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\OSS\T253 | [6 empty] | 472OSS | Applications/Tools | CLOSED | COMPLETED & APPROVED | 0 |  | 2025-05-29 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\OSS\T253 |  | 1
253 | T254 | 472 | NA |  | OSS | OSS | OSS | GPON | Co-located OLT topology view |  |  | Open |  |  |  |  | 17-05-2025: As per previous joint discussion with TFIBER and HPE team, this is not required.(to be discuss and remove/close) 26-06-2025: Completed, need confirmation from NOC |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | 472OSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1
254 | T255 | 472 | NA |  | OSS | OSS | OSS | Other Applications Integrations with OSS | Send SMS communication to SMS gateway |  |  | Open | [7 empty] | Suresh Pawar |  |  | COMPLETED & APPROVED |  |  | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\OSS\T255 | [6 empty] | 472OSS | Applications/Tools | CLOSED | COMPLETED & APPROVED | 0 |  |  | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\OSS\T255 |  | 1
255 | T256 | 472 | NA |  | OSS | OSS | OSS | IPMPLS | EPNM & PI Inventory |  |  | Open |  |  |  |  | 09-09-2025: to show only integrated devices, need take up with HPE to change select query to excluse non SNMP device |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | 472OSS | Applications/Tools | OPEN | COMPLETED | 09-09-2025: to show only integrated devices, need take up with HPE to change select query to excluse non SNMP device |  |  |  |  | 1
256 | T257 | 472 | NA |  | OSS | OSS | OSS | Other Applications Integrations with OSS | Syslog Sync to Syslog Server |  |  | Open |  |  |  |  | 17-06-2025: Support required from Sys-log team/Sarmendra & Ravikishore |  |  | Suresh Pawar |  | Open | WIP | [9 empty] | 472OSS | Applications/Tools | OPEN | OPEN | 0 |  |  |  |  | 1
257 | T258 | 472 | NA |  | OSS | OSS | OSS | GIS | GIS integration |  |  | Open |  |  |  |  | 17-05-2025: WIP with HPE team |  |  | Suresh Pawar |  | Open | WIP | [9 empty] | 472OSS | Applications/Tools | OPEN | OPEN | 0 |  |  |  |  | 1
258 | T259 | 472 | NA |  | OSS | OSS | OSS | E2E | TOPOLOGY |  |  | Open |  |  |  |  | 17-05-2025: WIP with HPE team |  |  | Suresh Pawar |  | Open | WIP | [9 empty] | 472OSS | Applications/Tools | OPEN | OPEN | 0 |  |  |  |  | 1
259 | T260 | 472 | NA |  | OSS | OSS | OSS | E2E | Cross domain RCA corelation |  |  | Open |  |  |  |  | 17-05-2025: WIP with HPE team |  |  | Suresh Pawar |  | Open | WIP | [9 empty] | 472OSS | Applications/Tools | OPEN | OPEN | 0 |  |  |  |  | 1
260 | T261 | 472 | NA |  | OSS | OSS | OSS | Infra | Data enrichment - Location information PKG A B C, etc |  |  | Open |  |  |  |  | 17-05-2025: GIS Integration with UTM is WIP(OT dependancy) 24-06-2025: OT has shared the API for attributes required by HPE |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | 472OSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1
261 | T262 | 472 | NA |  | OSS | OSS | OSS | DC - Active infra Alarm and Auto TT | DC-Active infra Alarm, RCA and Auto TT |  |  | Open |  |  |  |  | 17-05-2025: URL unreachable alarms are there but tickets are not getting generated. OT support required. 26-06-2025: Functionality is delivered,under stabilization. |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | 472OSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1
262 | T263 | 472 | NA |  | OSS | OSS | OSS | Documentation - LLD, FAT, HA Testing | OSS Documentation - LLD, FAT, HA Testing |  |  | Open |  |  |  |  | 17-05-2025: OT support is required. 26-06-2025: OT & HPE working on preparing the document concidering the BSOW |  |  | Suresh Pawar |  | Open | WIP | [9 empty] | 472OSS | Applications/Tools | OPEN | OPEN | 0 |  |  |  |  | 1
263 | T264 | 472 | NA |  | OSS | OSS | OSS | MoM Action | Network Downtime, fault reported to be mapped with BSS to consider during billing process |  |  | Open |  |  |  |  | 26-06-2025: Post NSO integration |  |  | Suresh Pawar |  | Open | WIP | [9 empty] | 472OSS | Applications/Tools | OPEN | Not Relevant to OSS | 0 |  |  |  |  | 1
264 | T265 | 472 | NA |  | OSS | OSS | OSS | MoM Action | Feasibility Engine |  |  | Open |  |  |  |  | 24-05-2025: WIP with HPE, OT dendancy for data. 26-06-2025: OT has provided necessary data to HPE, HPE to complete remaining development |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | 472OSS | Applications/Tools | OPEN | COMPLETED | API |  |  |  |  | 1
265 | T266 | 472 | NA |  | OSS | OSS | OSS | MoM Action | Commercial engine to be designed along with rules to Budgetory calculation for network and customer feasibilies |  |  | Open |  |  |  |  | 26-06-2025: this needs to be taken care by BSS side |  |  | Suresh Pawar |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | 472OSS | Applications/Tools | OPEN | Not Relevant to OSS | 0 |  |  |  |  | 1
266 | T267 | 472 | NA |  | OSS | OSS | OSS | MoM Action | Port Block (reservation) against Service ID |  |  | Open |  |  |  |  | DUPLICATE POINT |  |  | Suresh Pawar |  | Open | Duplicate | [9 empty] | 472OSS | Applications/Tools | OPEN | DUPLICATE | 0 |  |  |  |  | 1
267 | T268 | 472 | NA |  | OSS | OSS | OSS | Design & Documentation | LLD |  |  | Open |  |  |  |  | DUPLICATE POINT |  |  | Suresh Pawar |  | Open | Duplicate | [9 empty] | 472OSS | Applications/Tools | OPEN | DUPLICATE | 0 |  |  |  |  | 1
268 | T269 | 472 | NA |  | OSS | OSS | OSS | MoM Action | Change management process (eg. planned /Unplanned ) activities to be demonstrated |  |  | Open |  |  |  |  | 17-05-2025: OT Team has to work and deliver 26-06-2025: change managemnt is delivered, NOC team has to confirm |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | 472OSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1
269 | T270 | 472 | NA |  | OSS | OSS | OSS | MoM Action | Device status in OSS ciena inventory, details received from Ciena |  |  | Colosed | [7 empty] | Suresh Pawar |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-05-26 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\OSS\T270 | [6 empty] | 472OSS | Applications/Tools | CLOSED | COMPLETED & APPROVED | 0 |  | 2025-05-26 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\OSS\T270 |  | 1
270 | T271 | 472 | NA |  | OSS | OSS | OSS | GPON | ONT & OLT vendor name should be mapped to OSS Inventory & PMS Inventory. |  |  | Open | [7 empty] | Suresh Pawar |  |  | COMPLETED & APPROVED |  |  | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\OSS\T271 | [6 empty] | 472OSS | Applications/Tools | CLOSED | COMPLETED & APPROVED | 0 |  |  | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\OSS\T271 |  | 1
271 | T272 | 472 | NA |  | OSS | OSS | OSS | Design & Documentation | Infra team to maintain the SSL connectivity |  |  | Open |  |  |  |  | 17-05-2025: Dependancy on HPE upgrade and OT PS Team support 23-06-2025: New VM was requested by OT and same is provided. OT will to the testing in TND and confirm for production by 27th June 2025 |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | 472OSS | Applications/Tools | OPEN | COMPLETED | SSL configuartion completed in Service Manager |  |  |  |  | 1
272 | T273 | 472 | NA |  | OSS | OSS | OSS | Deployment and Installations | Deployment process - Process of building network & passive device connectivity to T-NOC through SG350, ONT (One port Voice, 2nd - Data, 3rd - Video & 4th port to T-NOC for SNMP traps) . Along with , and also all other Services to be test and provision in SG350 |  |  | Open |  |  |  |  | 09-09-2025: Needs to be closed along with IPMPLS(RS Rao) & GPON(Sayyad) |  |  | Suresh Pawar |  | Open | Open | [9 empty] | 472OSS | Applications/Tools | OPEN | OPEN | 09-09-2025: Needs to be closed along with IPMPLS(RS Rao) & GPON(Sayyad) |  |  |  |  | 1
273 | T274 | 472 | NA |  | OSS | OSS | OSS | Development and unit testing | In OSS Script File, both Nokia Primary and Secondary IPs are mentioned, however OSS is considering only the first mentioned IP even if Secondary IP is master. Due to this alarms are not reflecting in OSS. Infra team has to setup Virtual IP. |  |  | Colosed | [7 empty] | Suresh Pawar |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-05-26 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\OSS\T274 | [6 empty] | 472OSS | Applications/Tools | CLOSED | COMPLETED & APPROVED | 0 |  | 2025-05-26 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\OSS\T274 |  | 1
274 | T275 | 472 | NA |  | OSS | OSS | OSS | MoM Action | In OSS management dashboard, Block count should count only Mandal OLTs and not GP OLTs. |  |  | Open | [7 empty] | Suresh Pawar |  |  | COMPLETED & APPROVED |  |  | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\OSS\T275 | [6 empty] | 472OSS | Applications/Tools | CLOSED | COMPLETED & APPROVED | 0 |  |  | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\OSS\T275 |  | 1
275 | T276 | 472 | NA |  | OSS | OSS | OSS | MoM Action | DG Set integration with OSS is in progress for Package A, details for DG set integration with OSS awaited from Package B and C. |  |  | Open |  |  |  |  | 26-06-2025: Functionality is delivered, but system is not stable; same issue is escalated to HPE and OT. 22-07-2025: genset alarms are working now, confirmation required from NOC |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | 472OSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1
276 | T277 | 472 | NA |  | OSS | OSS | OSS | MoM Action | UPS and DG Device status, GP Name and LGD code & Block Name and LGD code are not available in the Passive Infra (Non-IT) inventory |  |  | Open |  |  |  |  | 09-09-2025: Status available in NNMi & PowerBI. All other atributes available in UOC |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | 472OSS | Applications/Tools | OPEN | COMPLETED | 09-09-2025: Status available in NNMi & PowerBI. All other atributes available in UOC |  |  |  |  | 1
277 | T278 | 472 | NA |  | OSS | OSS | OSS | Firewall | OSS firewall ports required for Security compliance |  |  | Open |  |  |  |  | 09-09-2025: Security team is already taking care with help of MTR sharma |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | 472OSS | Applications/Tools | OPEN | COMPLETED | 09-09-2025: Security team is already taking care with help of MTR sharma |  |  |  |  | 1
278 | T279 | 472 | NA |  | OSS | OSS | OSS | Security | Security policies to evolve related to DOT/CDOT etc.. from internal and intigration |  |  | Open |  |  |  |  | 26-06-2025: Dependacy on Cross domain delivery |  |  | Suresh Pawar |  | Open | WIP | [9 empty] | 472OSS | Applications/Tools | OPEN | OPEN | 0 |  |  |  |  | 1
279 | T280 | 472 | NA |  | OSS | OSS | OSS | Correlations | Cross domain Corelation and exact reason for any outage in Network till ONT Port with E2E topology |  |  | Open |  |  |  |  | 17-05-2025: WIP with HPE team |  |  | Suresh Pawar |  | Open | Duplicate | [9 empty] | 472OSS | Applications/Tools | OPEN | DUPLICATE | 0 |  |  |  |  | 1
280 | T281 | 472 | NA |  | OSS | OSS | OSS | MoM Action | Problem Management report for various recurring outages for the given period like i) one Unique LGD code >5 times in a Month ii) Fiber cut SPAN/Link >2 times in a month iii) Unique LGD code Down for >2 times with Same RFO iv) etc. |  |  | Open | [7 empty] | Suresh Pawar |  | Open | WIP | [9 empty] | 472OSS | Applications/Tools | OPEN | OPEN | 0 |  |  | #N/A |  | 1
281 | T282 | 472 | NA |  | OSS | OSS | OSS | MoM Action | For ONT Down cases, Some of the Alarms and cause code given by OEM is not matching with RFO provided by field engg., for example incase of Particular ONT goes down at GP level then exact RFO should be available for NOC to correlate with outages due to UPS power or other issue? |  |  | Open |  |  |  |  | 15-09-2025: Demostrated in the Demo/UAT call |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | 472OSS | Applications/Tools | OPEN | COMPLETED | 15-09-2025: Demostrated in the Demo/UAT call |  |  | #VALUE! |  | 1
282 | T283 | 472 | NA |  | OSS | OSS | OSS | Dashboards | Alert Mechanism (event rule) when power supply is through UPS which is running on Battery backup mode then there should be alert in the form of SMS sent to field team so outages can be avoided or minimized proactively. threshold can be configured (TBD) )for given range for Battery backup status i) <50%- - Minor ii) <40%-Major iii) <30% -Critical) |  |  | Open | [7 empty] | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | 472OSS | Applications/Tools | OPEN | COMPLETED | pending |  |  | #VALUE! |  | 1
283 | T284 | 472 | NA |  | OSS | OSS | OSS | Dashboards | Weekly, Monthly E2E Network Availability Trend for each Packages and over all per District, Zone level. |  |  | Open |  |  |  |  | Weekly Availability is not getting calculated hence it is not-feasible |  |  | Suresh Pawar |  | Open | WIP | [9 empty] | 472OSS | Applications/Tools | OPEN | NOT-FEASIBLE | 0 |  |  |  |  | 1
284 | T285 | 472 | NA |  | OSS | OSS | OSS | Dashboards | District wise Performance report for period of infra, fiber, ISP, config issues etc. |  |  | Open |  |  |  |  | 09-09-2025: user can download reports as on his requirement |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | 472OSS | Applications/Tools | OPEN | COMPLETED | 09-09-2025: user can download reports as on his requirement - TT report |  |  |  |  | 1
285 | T286 | 472 | NA |  | OSS | OSS | OSS | Dashboards | Individual NOC Engineer and shift Lead Performance Measurement for handling the TT's |  |  | Open |  |  |  |  | 17-05-2025: Artefacts needs to be collected from Sivakumar and seek approval. 26-06-2025: Waiting for Sivakumar's approval |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | 472OSS | Applications/Tools | OPEN | COMPLETED | closure |  |  |  |  | 1
286 | T287 | 472 | NA |  | OSS | OSS | OSS | MoM Action | Exact SPAN/Link details must be taken from GIS(Including Lat,Long) for Fiber cut/outage scenario to undserstand fix is permanent or temporarary in nature and impact on Multiple Nodes/GP’s . |  |  | Open |  |  |  |  | 17-05-2025: Common span scenarios solution needs to be finalization pending with L&T and will be finalized based on data coming from GIS integration. 26-06-2025: Dependancy on GIS integration. Expected to be completed by 16th July and then ~30 days needed for Common span |  |  | Suresh Pawar |  | Open | WIP | [9 empty] | 472OSS | Applications/Tools | OPEN | OPEN | 0 |  |  |  |  | 1
287 | T288 | 472 | NA |  |  | DC-Infrastructure | OSS | MoM Action | Report for Backup Status (success/failure) of all VM (source it from Vcenter Report) |  |  | Open | [7 empty] | Ravi Kishore |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-07-05 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\OSS\Artifact-T288 | [6 empty] | 472OSS | Applications/Tools | CLOSED |  |  |  | 2025-07-05 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\OSS\Artifact-T288 |  | 1
288 | T289 | 472 | NA |  | OSS | OSS | OSS | MoM Action | DC Active infra-Health check-up /Utilization and Resource Availability report.—Hardware and Servers. (Source it from Vcenter to OSS tool) |  |  | Open |  |  |  |  | 26-06-2025: data available in OBM, need confirmation from DC team |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | 472OSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1
289 | T290 | 472 | NA |  | OSS | OSS | OSS | MoM Action | IP MPLS node status report to be automated(Zonal / Mandal/GP) along with Alias Name(Like Actual Mandal /GP names) -Feasibility check required if Alias can be updated & fetched by OSS tool |  |  | Open |  |  |  |  | 26-06-2025: IPMPLS node status available in NNMi, need confirmation from NOC |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | 472OSS | Applications/Tools | OPEN | COMPLETED | pending |  |  |  |  | 1
290 | T291 | 472 | NA |  | OSS | OSS | OSS | Dashboards | IP MPLS Node/Link/Port availability & Utilization |  |  | Open |  |  |  |  | 17-05-2025: Utilization is already available. Node and Link availability is WIP. OT Support not available to check port availability, it needs to resume. 26-06-2025: all data available now except Link availability, need confirmation from NOC |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | 472OSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1
291 | T292 | 472 | NA |  | OSS | OSS | OSS | MoM Action | Customised dashboard template with available set of fields for different set of users views |  |  | Open |  |  |  |  | 17-05-2025: OOB is available, to be reviewed with NOC |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | 472OSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1
292 | T293 | 472 | NA |  | OSS | OSS | OSS | Dashboards | Service VLAN status report from EMS (Nokia and Tejas) |  |  | Open |  |  |  |  | 24-05-2025: Inhouse solution being built by rishik |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | 472OSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1
293 | T294 | 472 | NA |  | OSS | OSS | OSS | MoM Action | OSS MTTR report to include additional columns like RFO, Sub RFO, Resolution etc. |  |  | Open | [7 empty] | Suresh Pawar |  |  | COMPLETED & APPROVED |  |  | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\OSS\T294 | [6 empty] | 472OSS | Applications/Tools | CLOSED | COMPLETED & APPROVED | 0 |  |  | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\OSS\T294 |  | 1
294 | T295 | 472 | NA |  | OSS | OSS | OSS | MoM Action | Service Management tool has having duplicate tickets for same node which is impacting availability, outage reports. Issue needs to be fixed. |  |  | Open |  |  |  |  | 12-06-2025: duplicate ticket booking needs to be handle by HPE, HPE working on a script to handle it. 26-06-2025: Script deplyed by HPE, need confirmation from NOC |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | 472OSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1
295 | T296 | 472 | NA |  | OSS | OSS | OSS | MoM Action | Service Management dashboard should list planned outages and corelate TT if that is on same device or NW component. |  |  | Open |  |  |  |  | 17-05-2025: OT & NSO support required |  |  | Suresh Pawar |  | Open | WIP | [9 empty] | 472OSS | Applications/Tools | OPEN | OPEN | 0 |  |  |  |  | 1
296 | T297 | 472 | NA |  |  |  | DC-IT | Servers and Strorage (Deployment and Installations) | VM's Deployment Application Installations |  |  | Open |  |  |  |  | Applications installation completed in the given VM's. Storage/resource Allocation details captured in the TNOC IT Infra Server & Storage-LLD_v_1.5 & DC Inventory master sheet. Artifacts are captured. |  |  | Ravi Kishore |  |  | COMPLETED & APPROVED |  |  | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\DC IT-Infra\Artifact for - T297 | [6 empty] | 472DC-IT | Network | CLOSED |  |  |  |  | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\DC IT-Infra\Artifact for - T297 |  | 1
297 | T298 | 472 | NA |  |  |  | GPON | Tejas-MoM Action | Deployment process - Process of building network & passive device connectivity to T-NOC through SG350, ONT (One port Voice, 2nd - Data, 3rd - Video & 4 th port to T-NOC for SNMP traps) . Along with , and also all other Services to be test and provision in SG350 |  |  | Colosed | [7 empty] | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T298 | [6 empty] | 472GPON | GPON | CLOSED |  |  |  | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T298 |  | 1
298 | T299 | 472 | NA |  | OSS | Security | OSS | Integrating AD so that there is single user ID for all apps and they can integrate better in future if there is a need | Integration testing done for all apps that are ready currently except Alepo. Apps like HP OSS, Cisco ISE and other such applications are already integrated. We can switch IDs to AD anytime |  |  | Open |  |  |  |  | Once AD integration happen for Aleppo this point also will be closed along with T333. |  |  | Sarmendra |  | Open | WIP | [9 empty] | 472OSS | Applications/Tools | OPEN | [6 empty] | 1
299 | T300 | 472 | NA |  | OSS | Security | OSS | Configuration and best practices | User IDs created. Need to work with users for testing for NOC desktops |  |  | Open |  |  |  |  | Artifacts will be created and submitted on 03 Jul 25 |  |  | Sarmendra |  |  | COMPLETED & APPROVED |  |  | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\NW-Security\T300 | [6 empty] | 472OSS | Applications/Tools | CLOSED |  |  |  |  | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\NW-Security\T300 |  | 1
300 | T301 | 472 | NA |  |  |  | Security & Regulatory Compliance | Configuration | On A-10 -Configuration done on LB side. WAF will be configure with License |  |  | Open |  |  |  |  | A10 AMC not renewed , Awaiting AMC renewal with WAF features |  |  | Sarmendra |  | Open | WIP | [9 empty] | 472Security & Regulatory Compliance | Security | OPEN | [6 empty] | 1
301 | T302 | 472 | NA |  |  |  | Security & Regulatory Compliance | Functional AT | Will start next week as KT happened this week for all the new resources |  |  | Open |  |  |  |  | KT has been done. |  |  | Sarmendra |  |  | CLOSURE REVIEW PENDING | [9 empty] | 472Security & Regulatory Compliance | Security | OPEN |  |  |  |  | Artefacts to be Submitted |  | 1
302 | T303 | 472 | NA |  | OSS | Security | OSS | Configuration | OSS- Redware LB-There were configuration issues and have been sorted our by having multiple sessions over the past few weeks |  |  | Open |  |  |  |  | Artifact created and will be submitted to customer on 03 Jul 25. |  |  | Sarmendra |  |  | CLOSURE REVIEW PENDING | [9 empty] | 472OSS | Applications/Tools | OPEN |  |  |  |  | Artefacts to be Submitted |  | 1
303 | T304 | 472 | NA |  |  |  | Security & Regulatory Compliance | Functional AT | Radware LB - Will start next week as KT happened this week for all the new resources |  |  | Open |  |  |  |  | KT has been done. |  |  | Sarmendra |  | Open | WIP | [9 empty] | 472Security & Regulatory Compliance | Security | OPEN | [6 empty] | 1
304 | T305 | 472 | NA |  | OSS | DC-Infrastructure | OSS | Configuration | We have identified memory needed. Need help with space allocation for VM and also need license for a syslog server. ( we can also use Default Linux daemon) Syslog |  |  | Open |  |  |  |  | [17/09/2025] Syslog integration with both Redhat and Windows servers Completed. |  |  | Ravi Kishore |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-09-19 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\OSS\T305 | [6 empty] | 472OSS | Applications/Tools | CLOSED |  |  |  | 2025-09-19 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\OSS\T305 |  | 1
305 | T306 | 472 | NA |  |  |  | Security & Regulatory Compliance | Documentation | Customer has requested a complete Security LLD that states how our security architechture is and how different security products talk to each other |  |  | Open |  |  |  |  | Completed and Review pending. New changes will be incorporated as an addendum to design. |  |  | Sarmendra |  | Open | WIP | [9 empty] | 472Security & Regulatory Compliance | Security | OPEN | [6 empty] | 1
306 | T307 | 472 | NA |  |  |  | Security & Regulatory Compliance | User Access Rights | Cisco: PKGA-testing in WIP, PKGB&C-will be replicated after PKGA completion GPON: Segregation is done, implementation is WIP DWDM: Segregation is done, implementation is WIP HPE OSS: User to access mapping is done, implementation WIP by hp team Other Apps: Will have meetings this week and sort it out. |  |  | Open |  |  |  |  | #VALUE! |  |  | Sarmendra |  | Open | WIP | [9 empty] | 472Security & Regulatory Compliance | Security | OPEN |  |  |  |  | #VALUE! |  | 1
307 | T308 | 472 | NA |  |  |  | Security & Regulatory Compliance | IPDR | Developing in-house solution, also exploring with external vendors. 3 vendors declined. |  |  | Open |  |  |  |  | 27.06.25 , IPDR solution operational , pending document will be submitted by 1st week of Jul'25 |  |  | Jayant Madavi |  | Open | WIP | [9 empty] | 472Security & Regulatory Compliance | Security | OPEN | [6 empty] | 1
308 | T309 | 472 | NA |  |  |  | Security & Regulatory Compliance | Storage | Storage requirement worked out and given to contract team. PO to be issued(Syslog) |  |  | Open |  |  |  |  | 25-Sep-2025: Artefacts to be uploaded, Need to provide current consumption of storage, incremental log will be added to existing storage after adding 18 TB additional storage . | L&T | Ravi Kishore | Sarmendra |  |  | COMPLETED & APPROVED | [9 empty] | 472Security & Regulatory Compliance | Security | CLOSED |  |  |  |  | Artefacts Need to upload |  | 1
309 | T310 | 472 | NA |  |  |  | Security & Regulatory Compliance | NAT | Developed in-house solution, also exploring with external vendors. 3 vendors declined. In-house solution is ready for demo, tested with the sample data.( |  |  | Open |  |  |  |  | 25-Sep-2025: Detailed discussion will be taken up later(Sanjay will brief background against this point) |  |  | Sarmendra |  |  | COMPLETED & APPROVED | [9 empty] | 472Security & Regulatory Compliance | Security | CLOSED |  |  |  |  | Artefacts Need to upload |  | 1
310 | T311 | 472 | NA |  |  |  | Security & Regulatory Compliance | QoS Reporting | QoS Reporting related to all parameters |  |  | Open |  |  |  |  | Completed and Review pending.FAT documents were submitted to TPA , However it has some common observation which will be discussed with TPA team by Mr Sharma. |  |  | Sarmendra |  | Open | WIP | [9 empty] | 472Security & Regulatory Compliance | Security | OPEN | [6 empty] | 1
311 | T312 | 472 | NA |  |  |  | Security & Regulatory Compliance | Regulatory compliance | SLA Reporting for Cell Tower and GIs |  |  | Colosed | [7 empty] | Siva Kumar |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-05-13 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\T312 | [6 empty] | 472Security & Regulatory Compliance | Security | CLOSED |  |  |  | 2025-05-13 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\T312 |  | 1
312 | T313 | 472 | NA |  |  |  | Security & Regulatory Compliance | Regulatory compliance | Communication made to T-Fiber. Procedure need to be finalized for remote access |  |  | Open | [7 empty] | Sarmendra |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | 472Security & Regulatory Compliance | Security | OPEN | [6 empty] | 1
313 | T314 | 472 | NA |  |  |  | Security & Regulatory Compliance | External Audit and VAPT | External Audit and VAPT (Tfiber will be arranging a partner for third party audit) |  |  | Open |  |  |  |  | T Fiber to conduct the Audit and VAPT |  |  | Sarmendra |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | 472Security & Regulatory Compliance | Security | OPEN | [6 empty] | 1
314 | T315 | 472 | NA |  |  | BMS | BMS | Fire and Safety Drill | Certificate and artefacts of last fire & safety drill submitted |  |  | Open | [7 empty] | Sarmendra |  |  | COMPLETED & APPROVED |  |  | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\NW-Security\T315 | [6 empty] | 472BMS | #N/A | CLOSED |  |  |  |  | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\NW-Security\T315 |  | 1
315 | T316 | 472 | NA |  |  |  | Security & Regulatory Compliance | User Traceability | User access traceability |  |  | Open | [7 empty] | Sarmendra |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-05-19 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\NW-Security\T316 | [6 empty] | 472Security & Regulatory Compliance | Security | CLOSED |  |  |  | 2025-05-19 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\NW-Security\T316 |  | 1
316 | T317 | 472 | NA |  | OSS | OSS | OSS | Certifications | ITIL Product certification |  |  | Open | [7 empty] | Suresh Pawar |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-09-12 | \\172.28.9.34\SHARE DRIVE\Artefacts_T-Fiber TNOC Tracker\OSS | [6 empty] | 472OSS | Applications/Tools | CLOSED | COMPLETED & APPROVED | 0 |  | 2025-09-12 | \\172.28.9.34\SHARE DRIVE\Artefacts_T-Fiber TNOC Tracker\OSS |  | 1
317 | T318 | 472 | NA |  |  |  | Security & Regulatory Compliance | Policy Implementation | Network Forensic |  |  | Colosed | [7 empty] | Sarmendra |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-05-19 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\NW-Security\T318 | [6 empty] | 472Security & Regulatory Compliance | Security | CLOSED |  |  |  | 2025-05-19 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\NW-Security\T318 |  | 1
318 | T319 | 472 | NA |  |  |  | Security & Regulatory Compliance | Policy Implementation | Network Hardening |  |  | Open |  |  |  |  | All unauthorised access has been blocked at firwall level. All USB is disables at NOC . All unysed port has been hardened |  |  | Sarmendra |  | Open | WIP | [9 empty] | 472Security & Regulatory Compliance | Security | OPEN | [6 empty] | 1
319 | T320 | 472 | NA |  |  |  | Security & Regulatory Compliance | Policy Implementation | Network Penetration Test |  |  | Open |  |  |  |  | PT will conducted once Ext audit team arrives |  |  | Sarmendra |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | 472Security & Regulatory Compliance | Security | OPEN | [6 empty] | 1
320 | T321 | 472 | NA |  |  |  | Security & Regulatory Compliance | MoM Action | Firewall policy compare from DC to DR validation check for redundancy |  |  | Open |  |  |  |  | May be clubed with point T 71 all Policy will be compared with current configuration of firewall and be submitted . |  |  | Sarmendra |  | Open | REOPENED | [9 empty] | 472Security & Regulatory Compliance | Security | OPEN | [6 empty] | 1
321 | T322 | 472 | NA |  |  |  | Security & Regulatory Compliance | MoM Action | Day 0 attacks for any government departments lifecycle (GIBB to be protected from the day of connection) |  |  | Open |  |  |  |  | will be closed with implementation of URL filtering facilities at IPS |  |  | Sarmendra |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | 472Security & Regulatory Compliance | Security | OPEN | [6 empty] | 1
322 | T323 | 472 | NA |  |  |  | Security & Regulatory Compliance | Storage | User access logs& Commands to be maintained for 2 years |  |  | Open |  |  |  |  | Completed and approved |  |  | Sarmendra |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-05-19 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\NW-Security\T323 | [6 empty] | 472Security & Regulatory Compliance | Security | CLOSED |  |  |  | 2025-05-19 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\NW-Security\T323 |  | 1
323 | T324 | 472 | NA |  |  |  | Security & Regulatory Compliance | Deployment and Installations | Syslog to maintain for 2 years |  |  | Colosed | [7 empty] | Ravi Kishore |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-05-14 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\Security\T324 | [6 empty] | 472Security & Regulatory Compliance | Security | CLOSED |  |  |  | 2025-05-14 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\Security\T324 |  | 1
324 | T325 | 472 | NA |  |  |  | Security & Regulatory Compliance | Policy Implementation | Organizational Security Policy |  |  | Open |  |  |  |  | Security policy has been made , however same need clarification from customer to incorporate deviation from actual points. |  |  | Sarmendra |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | 472Security & Regulatory Compliance | Security | OPEN | [6 empty] | 1
325 | T326 | 472 | NA |  |  |  | Security & Regulatory Compliance | Report | IPDR static IP report |  |  | Open | [7 empty] | Sarmendra |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-05-19 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\NW-Security\T326 | [6 empty] | 472Security & Regulatory Compliance | Security | CLOSED |  |  |  | 2025-05-19 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\NW-Security\T326 |  | 1
326 | T327 | 472 | NA |  |  |  | Security & Regulatory Compliance | Report | Syslog NAT report |  |  | Open | [7 empty] | Sarmendra |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-05-19 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\NW-Security\T327 | [6 empty] | 472Security & Regulatory Compliance | Security | CLOSED |  |  |  | 2025-05-19 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\NW-Security\T327 |  | 1
327 | T328 | 472 | NA |  |  |  | Security & Regulatory Compliance | AAA | ISE-Completed, Alepo-Completed for Nokia GPON, Accounting feature demo to be done for Tejas GPON and Ciena DWDM |  |  | Open |  |  |  |  | Confirmation of purchase of ISE. License needed to upgrade for HA |  |  | Sarmendra |  |  | CLOSURE REVIEW PENDING | [9 empty] | 472Security & Regulatory Compliance | Security | OPEN |  |  |  |  | Artefacts to be Submitted |  | 1
328 | T329 | 472 | NA |  |  |  | Security & Regulatory Compliance | MoM Action | Cisco ISE to be integrated with AD for Authentication |  |  | Colosed | [7 empty] | Sarmendra |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-05-19 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\NW-Security\T153 | [6 empty] | 472Security & Regulatory Compliance | Security | CLOSED |  |  |  | 2025-05-19 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\NW-Security\T153 |  | 1
329 | T330 | 472 | NA |  |  |  | Security & Regulatory Compliance | MoM Action | syslog storage requirement for respective OEM devices |  |  | Colosed | [7 empty] | Sarmendra |  |  | COMPLETED & APPROVED | [9 empty] | 472Security & Regulatory Compliance | Security | CLOSED |  |  |  |  | Artefacts Need to upload |  | 1
330 | T331 | 472 | NA |  |  |  | Security & Regulatory Compliance | MoM Action | Tejas OLT to integrate with Alepo AAA Tejas EMS to integrate with Alepo AAA |  |  | Open |  |  |  |  | Alepo AMC Support required for Evidence submission to customer |  |  | Sarmendra |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | 472Security & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1
331 | T332 | 472 | NA |  |  |  | Security & Regulatory Compliance | MoM Action | Nokia AMS to integrate with Alepo AAA |  |  | Open | [7 empty] | Sarmendra |  |  | COMPLETED & APPROVED | [9 empty] | 472Security & Regulatory Compliance | Security | CLOSED |  |  |  |  | Artefacts Need to upload |  | 1
332 | T333 | 472 | NA |  |  |  | Security & Regulatory Compliance | MoM Action | Alepo AAA to be integrated with AD |  |  | Open |  |  |  |  | SOW, CR and BOQ Shared for approval and consideration. |  |  | Sarmendra |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | 472Security & Regulatory Compliance | Security | OPEN | [6 empty] | 1
333 | T334 | 472 | NA |  |  |  | Security & Regulatory Compliance | Functional AT | Cisco Firewall, ISE, IPS/IDS Functional AT |  |  | Open |  |  |  |  | Completed and Review pending. |  |  | Sarmendra |  | Open | WIP | [9 empty] | 472Security & Regulatory Compliance | Security | OPEN | [6 empty] | 1
334 | T335 | 472 | NA |  |  |  | Security & Regulatory Compliance | Design & Documentation | Security LLD to finalised and submitted to T-Fiber for approval. Customer has requested a complete Security LLD that states how our security architechture is and how different security products talk to each other |  |  | Open |  |  |  |  | Duplicate of point 306 |  |  | Sarmendra |  | Open | WIP | [9 empty] | 472Security & Regulatory Compliance | Security | OPEN | [6 empty] | 1
335 | T336 | 472 | NA |  |  |  | IP/MPLS | T-Cell Solution Design | Egress QoS policy for ASR907 |  |  | Colosed | [7 empty] | RS Rao |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-05-05 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\TFIBER T-CELL Service Design & Solution V4.3 T197, T336, T337, T338.pdf | [6 empty] | 472IP/MPLS | IPMPLS | CLOSED |  |  |  | 2025-05-05 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\QOS for TFiber Network LLD V2.0 - T339, T340, T341, T342.pdf |  | 1
336 | T337 | 472 | NA |  |  |  | IP/MPLS | T-Cell Solution Design | Egress QoS policy for ASR920 – QoS policy to be applied on Gigabit interfaces instead of on Port Channel (LAG) which is not suitable for CIR application |  |  | Colosed | [7 empty] | RS Rao |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-05-05 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\TFIBER T-CELL Service Design & Solution V4.3 T197, T336, T337, T338.pdf | [6 empty] | 472IP/MPLS | IPMPLS | CLOSED |  |  |  | 2025-05-05 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\TFIBER T-CELL Service Design & Solution V4.3 T197, T336, T337, T338.pdf |  | 1
337 | T338 | 472 | NA |  |  |  | IP/MPLS | T-Cell Solution Design | Additional scenarios for generic Cell tower Solution shared with Cisco, Cisco to check and provide the design |  |  | Colosed | [7 empty] | RS Rao |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-05-05 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\TFIBER T-CELL Service Design & Solution V4.3 T197, T336, T337, T338.pdf | [6 empty] | 472IP/MPLS | IPMPLS | CLOSED |  |  |  | 2025-05-05 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\TFIBER T-CELL Service Design & Solution V4.3 T197, T336, T337, T338.pdf |  | 1
338 | T339 | 472 | NA |  |  |  | IP/MPLS | MPLS Core network QoS | Egress Policy structure and BW as per discussion |  |  | Colosed | [7 empty] | RS Rao |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-05-05 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\QOS for TFiber Network LLD V2.0 - T339, T340, T341, T342.pdf | [6 empty] | 472IP/MPLS | IPMPLS | CLOSED |  |  |  | 2025-05-05 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\QOS for TFiber Network LLD V2.0 - T339, T340, T341, T342.pdf |  | 1
339 | T340 | 472 | NA |  |  |  | IP/MPLS | MPLS Core network QoS | Egress QoS policy for ASR99xx |  |  | Colosed | [7 empty] | RS Rao |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-05-05 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\QOS for TFiber Network LLD V2.0 - T339, T340, T341, T342.pdf | [6 empty] | 472IP/MPLS | IPMPLS | CLOSED |  |  |  | 2025-05-05 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\QOS for TFiber Network LLD V2.0 - T339, T340, T341, T342.pdf |  | 1
340 | T341 | 472 | NA |  |  |  | IP/MPLS | MPLS Core network QoS | Egress QoS policy for ASR907 |  |  | Colosed | [7 empty] | RS Rao |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-05-05 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\QOS for TFiber Network LLD V2.0 - T339, T340, T341, T342.pdf | [6 empty] | 472IP/MPLS | IPMPLS | CLOSED |  |  |  | 2025-05-05 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\QOS for TFiber Network LLD V2.0 - T339, T340, T341, T342.pdf |  | 1
341 | T342 | 472 | NA |  |  |  | IP/MPLS | MPLS Core network QoS | Egress QoS policy for ASR920 |  |  | Colosed | [7 empty] | RS Rao |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-05-05 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\QOS for TFiber Network LLD V2.0 - T339, T340, T341, T342.pdf | [6 empty] | 472IP/MPLS | IPMPLS | CLOSED |  |  |  | 2025-05-05 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\QOS for TFiber Network LLD V2.0 - T339, T340, T341, T342.pdf |  | 1
342 | T343 | 472 | NA |  |  |  | IP/MPLS | Service Solution | Design Document require SDC content to GI |  |  | Open |  |  |  |  | 22-Sep-25: Need to review plan and approve 12-Sep-25 : Peering plan submitted as per discussion on 11-Sep-25 01-Jul-25 : Design document submitted with suggested approaches. Require inputs from TFiber to conduct PoC and finalize service design. | T Fiber | Sanjay | RS Rao |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | 472IP/MPLS | IPMPLS | OPEN | [6 empty] | 1
343 | T344 | 472 | NA |  |  |  | IP/MPLS | Service Solution | Solution document for GI connectivity (intranet & internet) TVPN |  |  | Open |  |  |  |  | 22-Sep-25:Artefacts to be uploaded 01-Jul-25 : Design document submitted with suggested approaches. Require inputs from TFiber to conduct PoC and finalize service design. | L&T | RS Rao | RS Rao |  |  | COMPLETED & APPROVED | [9 empty] | 472IP/MPLS | IPMPLS | CLOSED |  |  |  | 2025-09-23 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\T-FIBER RYTHUVEDIKA VC L3VPN Solution LLD V1.0.docx |  | 1
344 | T345 | 472 | NA |  |  |  | TNOC-Ops | NOC Operation | OEM Professional services for all products post NOC operationalization |  |  | Open |  |  |  |  | AMC and TAC support provided |  |  | Ahmad |  | Open | Open | [9 empty] | 472TNOC-Ops | Network | OPEN | [6 empty] | 1
345 | T346 | 472 | NA |  |  |  | BSS | TNOC-Ops | all EMS Devices for provisioning through BSS |  |  | Open |  |  |  |  | BSS will not directly interact with any EMS, it will be via A&O. |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | 472BSS | Applications/Tools | OPEN | [6 empty] | 1
346 | T347 | 472 | NA |  |  |  | BSS | Functional AT | Lead to Cash, Order to cash & Request to resolution to operate and demonestrate |  |  | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | 472BSS | Applications/Tools | OPEN | [6 empty] | 1
347 | T348 | 472 | NA | P3 |  |  | TNOC-Ops | NOC Operation | Placement of T-Fiber logo and Telangana State emblem in TNOC reception area |  |  | Open |  |  |  |  | Logo design agreed with customer. Additional places sign boards to be placed as part of CR, give to commercail for quotation. | T Fiber |  | Ahmad |  | Open | Open | [9 empty] | 472TNOC-Ops | Network | OPEN |  |  | Logo |  |  |  | 1
348 | T349 | 472 | NA |  |  |  | Security & Regulatory Compliance | Design & Documentation | TNOC operational framework with respect to processes (Incident, Problem, Major Event, Change, Version, Security, AAA, Planned Event, SLA Management etc) |  |  | Open |  |  |  |  | Customer has to choose what framework they ned to follow for end to end governance i.e COBIT, COSO, SABSA etc. |  |  | Sarmendra |  | Open | WIP | [9 empty] | 472Security & Regulatory Compliance | Security | OPEN | [6 empty] | 1
349 | T350 | 472 | NA | P3 |  |  | TNOC-Ops | NOC Operation | Manpower Structure for TNOC Operationalization |  |  | Colosed | [7 empty] | Ahmad |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-05-13 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\T166 | [6 empty] | 472TNOC-Ops | Network | CLOSED |  |  | Manpower | 2025-05-13 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\T166 |  | 1
350 | T351 | 472 | NA |  |  |  | TNOC-Ops | Design & Documentation | Helpdesk Readiness Plan |  |  | Open |  |  |  |  | 1. Soft training completed on 06&07 Sep 2. All Resources will be from L&T only- Resource available to handle current calls 3. updated process document shared, Pending for discussion 4. SOP Submitted for inbound and outbound calls- Discussion Pending 5. Regulatory reports were available(DOT) 6. Integration with OSS and BSS is Pending 7. Based on trainer suggestion, implemented day to day and weekly assestments 8. Neox call Manager functioanlity validated as standlone 9. All Features required for Call Manager completed including Business Helpdesk 10. LLD and RFP Compliance also ready for review |  |  | Siva Kumar |  | Open | WIP | [9 empty] | 472TNOC-Ops | Network | OPEN | [6 empty] | 1
351 | T352 | 472 | NA |  |  |  | TNOC-Ops | MoM Action | Induction Training program – To be developed and feedback mechanism to be considered, for newly on-boarded resources |  |  | Colosed | [7 empty] | Siva Kumar |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-05-13 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\T166 | [6 empty] | 472TNOC-Ops | Network | CLOSED |  |  |  | 2025-05-13 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\T166 |  | 1
352 | T353 | 472 | NA |  |  |  | TNOC-Ops | Helpdesk | Regulatory Compliance_PMR on QoS |  |  | Colosed | [7 empty] | Siva Kumar |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-05-13 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\T353 | [6 empty] | 472TNOC-Ops | Network | CLOSED |  |  |  | 2025-05-13 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\T353 |  | 1
353 | T354 | 472 | NA | P3 |  |  | TNOC-Ops | NOC Operation | Resource deployment at TNOC |  |  | Colosed | [7 empty] | Ahmad |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-05-13 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\T166 | [6 empty] | 472TNOC-Ops | Network | CLOSED |  |  | Not related to delivery | 2025-05-13 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\T166 |  | 1
354 | T355 | 472 | NA | P3 |  |  | TNOC-Ops | NOC Operation | Interlocking and Interdependencies with resources of package B & C operating at TNOC |  |  | Open | [7 empty] | Ahmad |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-05-26 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\T166 | [6 empty] | 472TNOC-Ops | Network | CLOSED |  |  | Not related to delivery | 2025-05-26 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\T166 |  | 1
355 | T356 | 472 | NA |  |  |  | TNOC-Ops | NOC Operation | OEM Escalation processes for NOC Applications, DBs, IT Infra and Network along with TATs aligned to SLA |  |  | Open | [7 empty] | Siva Kumar |  |  | COMPLETED & APPROVED | ad-ut-tfiber | 2025-07-08 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\TNOC | [6 empty] | 472TNOC-Ops | Network | CLOSED |  |  |  | 2025-07-08 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\TNOC |  | 1
356 | T357 | 472 | NA | P3 |  |  | TNOC-Ops | NOC Operation | Spare for Business continuity - RS&R for NOC and DR elements and assets |  |  | Open |  |  |  |  | List shared with commercial for ordering. WIP |  |  | Ahmad | Dependent on Commercials | Open | WIP | [9 empty] | 472TNOC-Ops | Network | OPEN |  |  | Spares for NOC |  |  |  | 1
357 | T358 | 472 | NA |  |  |  | TNOC-Ops | Functional AT | Network HOTO and KT from Respective Domain and Packages |  |  | Open |  |  |  | WIP | BSS, NSO and Security SOP training pending. Rest all done |  |  | Siva Kumar |  | Open | WIP | [9 empty] | 472TNOC-Ops | Network | OPEN | [6 empty] | 1
358 | T359 | 472 | NA |  | OSS | OSS | OSS | NOC Operation | OSS - stability and Operational issues with respect to inventory, ticketing and utilization modules |  |  | Open |  |  |  |  | 26-06-2025: Frequent stability issues are because of NNMi, OBM instability and Vendor asking for upgrade |  |  | Suresh Pawar |  | Open | WIP | [9 empty] | 472OSS | Applications/Tools | OPEN | OPEN | 0 |  |  |  |  | 1
359 | T360 | 472 | NA | P3 |  |  | TNOC-Ops | NOC Operation | Domain wise training |  |  | Open |  |  |  |  | BSS, NSO and Security SOP training pending. On the job training happening for OSS. Rest all domains done. |  |  | Ahmad |  | Open | Open | [9 empty] | 472TNOC-Ops | Network | OPEN |  |  | Training |  |  |  | 1
360 | T361 | 472 | NA |  |  |  | TNOC-Ops | Helpdesk | Updated Process document Submission after last Meeting with T Fiber Management |  |  | Colosed | [7 empty] | Siva Kumar |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-05-13 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\T361 | [6 empty] | 472TNOC-Ops | Network | CLOSED |  |  |  | 2025-05-13 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\T361 |  | 1
361 | T362 | 472 | NA |  |  |  | TNOC-Ops | Helpdesk | Categorisation of incoming calls to be detailed and IVR to bilingual(Incoming IVR call flow) |  |  | Colosed | [7 empty] | Siva Kumar |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-05-13 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\T362 | [6 empty] | 472TNOC-Ops | Network | CLOSED |  |  |  | 2025-05-13 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\T362 |  | 1
362 | T363 | 472 | NA |  |  |  | TNOC-Ops | Helpdesk | IVR Recording file required for call landing and Hold time |  |  | Colosed | [7 empty] | Siva Kumar |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-05-13 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\T363 | [6 empty] | 472TNOC-Ops | Network | CLOSED |  |  |  | 2025-05-13 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\T363 |  | 1
363 | T364 | 472 | NA |  |  |  | TNOC-Ops | Helpdesk | Integration with BSS and OSS |  |  | Open |  |  |  | WIP | 11-Sep-25: Basic integration completed with BSS and HPSM(Ticketing). IVR has to be freezed to implement same. As per Neox is one time configuration but Since its ongoing changes will happen in IVR, So it would be configurble as per L&T/T Fiber- Which to be discussed. 360 View also Pending from BSS |  |  | Siva Kumar |  | Open | WIP | [9 empty] | 472TNOC-Ops | Network | OPEN | [6 empty] | 1
364 | T365 | 472 | NA |  |  |  | TNOC-Ops | Helpdesk | Integration of SMS, E-Mail |  |  | Open |  |  |  | WIP | E-mail & SMS Integration completed. SMS testing pending due to no balance in SMS striker portal. 28 Apri-2025: TFIBER to share SMS GW details to integrate with OSS/BSS. Integration must be configurable without any cost impact to TFIBER. |  |  | Siva Kumar |  | Open | WIP | [9 empty] | 472TNOC-Ops | Network | OPEN | [6 empty] | 1
365 | T365 | 472 | NA |  |  |  | TNOC-Ops | Helpdesk | Integration of Whatsapp, Chatbot |  |  | Open |  |  |  | WIP | 11-Sep-25: Not Part of RFP and Existing product didn’t support, need to upgrade to Omni based Solution. |  |  | Siva Kumar |  | Open | WIP | [9 empty] | 472TNOC-Ops | Network | OPEN | [6 empty] | 1
366 | T366 | 472 | NA |  |  |  | TNOC-Ops | Helpdesk | Fancy 4 digit number for Helpdesk or Tollfree number Availability |  |  | Open | [7 empty] | Siva Kumar |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-07-19 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\T366 | [6 empty] | 472TNOC-Ops | Network | CLOSED |  |  |  | 2025-07-19 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\T366 |  | 1
367 | T367 | 472 | NA |  |  |  | TNOC-Ops | Helpdesk | Training for Agents and Helpdesk Manager |  |  | Colosed | [7 empty] | Siva Kumar |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-05-13 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\T367 | [6 empty] | 472TNOC-Ops | Network | CLOSED |  |  |  | 2025-05-13 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\T367 |  | 1
368 | T368 | 472 | NA |  |  |  | TNOC-Ops | Helpdesk | Interface mechanism between T-NOC Helpdesk and District Collector offices for complaints that may be made directly(Walk-in) to District Collector office, provision for a mini-Helpdesk node at each district, provide a facility/ hotline using which an authorised person can log a call / complaint on behalf of the District Collector Office, such mechanism to be similar to the Direct walk-in channel for customer complaints at T-NOC |  |  | Open | [7 empty] | Siva Kumar |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-07-19 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\T368 | [6 empty] | 472TNOC-Ops | Network | CLOSED |  |  |  | 2025-07-19 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\T368 |  | 1
369 | T369 | 472 | NA |  |  |  | TNOC-Ops | Helpdesk | If T-NOC is totally down for some reason like fire, earthquake, lockdown etc….then how Helpdesk will work from DR? |  |  | Open |  |  |  | WIP |  |  |  | Siva Kumar |  | Open | WIP | Not part of RFP | [8 empty] | 472TNOC-Ops | Network | OPEN | [6 empty] | 1
370 | T370 | 472 | NA |  |  |  | TNOC-Ops | Helpdesk | If all 10 lines are engaged for a longer time. Can the Helpdesk system call back to that missed call? |  |  | Open |  |  |  | WIP | 11-Sep-25: OEM confirmed this feature is not available/feasible Based on CDR record with Agent and Manager Login, Call back can be done manually with CDR or Agent Call report. It will be displayed in queue to agent. But Missed call to be handled by outbound team. Which required complete Set of call Center. If required Helpdesk Manager will review missed call to take action accordingly. |  |  | Siva Kumar |  | Open | WIP | [9 empty] | 472TNOC-Ops | Network | OPEN | [6 empty] | 1
371 | T371 | 472 | NA |  |  |  | GPON | Nokia | * Testing done for new build in T-Fiber test lab . * Plan event for OLTs new SW upgradation in production environment. |  |  | Open |  | Nokia OEM | OLT |  | All the OLTs reachabled to AMS are upgraded successfully. Having dependecny on PKG-A/B/C field teams to make unreachable OLTs to reachable | All Packages | Srinivas Kodali(PKG_A), Venu& Mahesh(PKG B&C) | Sayyad Pasha |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | 472GPON | GPON | OPEN | [6 empty] | 1
372 | T372 | 472 | NA |  |  |  | GPON | Nokia | TACACS Feature |  |  | Colosed | [7 empty] | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T372 | [6 empty] | 472GPON | GPON | CLOSED |  |  |  | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T372 |  | 1
373 | T373 | 472 | NA |  |  |  | NSO | Deployment and Installations | HSI (High Speed Internet to Household) implementation |  |  | Open |  |  |  |  | Post 24.06.25 review and direction, working for a alternate options for NSO. will come back as earliest with closure plan. |  |  | Jayant Madavi |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | 472NSO | Applications/Tools | OPEN | [6 empty] | 1
374 | T374 | 472 | NA |  |  |  | NSO | Deployment and Installations | IPTV to Household implementation |  |  | Open |  |  |  |  | Post 24.06.25 review and direction, working for a alternate options for NSO. will come back as earliest with closure plan. |  |  | Jayant Madavi |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | 472NSO | Applications/Tools | OPEN | [6 empty] | 1
375 | T375 | 472 | NA |  |  |  | NSO | Deployment and Installations | VOIP to Household implementation |  |  | Open |  |  |  |  | Post 24.06.25 review and direction, working for a alternate options for NSO. will come back as earliest with closure plan. |  |  | Jayant Madavi |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | 472NSO | Applications/Tools | OPEN | [6 empty] | 1
376 | T376 | 472 | NA |  |  |  | NSO | Deployment and Installations | Internet to GI (Govt. Institution) implementation |  |  | Open |  |  |  |  | Post 24.06.25 review and direction, working for a alternate options for NSO. will come back as earliest with closure plan. |  |  | Jayant Madavi |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | 472NSO | Applications/Tools | OPEN | [6 empty] | 1
377 | T377 | 472 | NA |  |  |  | NSO | Deployment and Installations | CCTV Unicast implementation |  |  | Open |  |  |  |  | Post 24.06.25 review and direction, working for a alternate options for NSO. will come back as earliest with closure plan. |  |  | Jayant Madavi |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | 472NSO | Applications/Tools | OPEN | [6 empty] | 1
378 | T378 | 472 | NA |  |  |  | NSO | Deployment and Installations | CCTV Multicast implementation |  |  | Open |  |  |  |  | Post 24.06.25 review and direction, working for a alternate options for NSO. will come back as earliest with closure plan. |  |  | Jayant Madavi |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | 472NSO | Applications/Tools | OPEN | [6 empty] | 1
379 | T379 | 472 | NA |  |  |  | NSO | Deployment and Installations | Cell Tower L2VPN implementation |  |  | Open |  |  |  |  | Post 24.06.25 review and direction, working for a alternate options for NSO. will come back as earliest with closure plan. |  |  | Jayant Madavi |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | 472NSO | Applications/Tools | OPEN | [6 empty] | 1
380 | T380 | 472 | NA |  |  |  | NSO | Deployment and Installations | Dhanush Telemedicine Application implementation |  |  | Open |  |  |  |  | Post 24.06.25 review and direction, working for a alternate options for NSO. will come back as earliest with closure plan. |  |  | Jayant Madavi |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | 472NSO | Applications/Tools | OPEN | [6 empty] | 1
381 | T381 | 472 | NA |  |  |  | NSO | Deployment and Installations | SDC content to Household and GI implementation |  |  | Open |  |  |  |  | Post 24.06.25 review and direction, working for a alternate options for NSO. will come back as earliest with closure plan. |  |  | Jayant Madavi |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | 472NSO | Applications/Tools | OPEN | [6 empty] | 1
382 | T382 | 472 | NA |  |  |  | BSS | Development and unit testing | EY need to present landing page for suggestion - Design features of web page |  |  | Open | [7 empty] | Manoj Nibrad |  | Open | Open | Approval Email received from NOC Director | 2025-07-16 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\BSS\Artifact_T382 | [6 empty] | 472BSS | Applications/Tools | CLOSED |  |  |  | 2025-07-16 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\BSS\Artifact_T382 |  | 1
383 | T383 | 472 | NA |  |  |  | DC-IT | Functional AT | Cisco prime infrastructure AT |  |  | Open |  |  |  |  | 22-Sep-25: IPMPLS Domain team to submit detailed remarks on raised queries. 08-Jul-2025 - Sandeep will come back by EoD today on extension of Cisco support renewal 01-Jul-25 : Revised FAT documents submission pending (TPA observations to be included) OEM(Cisco) suport is required to show the new test cases, Inputs provided to OEM on 14th May & 30th Jun. OEM onboarding is in progress & LnT Contracts team is coordinating | L&T | RS Rao | RS Rao |  | Open | Open | [9 empty] | 472DC-IT | Network | OPEN | [6 empty] | 1
384 | T384 | 472 | NA |  |  |  | IP/MPLS | Security | GCT implementation |  |  | Open |  |  |  |  | Confirmed from IP-MPLS team for GCT implementation. |  |  | Sarmendra |  | Open | WIP | [9 empty] | 472IP/MPLS | IPMPLS | OPEN | [6 empty] | 1
385 | T385 | 472 | NA |  |  |  | NSO | Design & Documentation | solution document - GI internet solution |  |  | Open | [7 empty] | RS Rao |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-05-05 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\T-FIBER T-Net for GI Broadband Service Design LLD V1.1 - T188.pdf | [6 empty] | 472NSO | Applications/Tools | CLOSED |  |  |  | 2025-05-05 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\T-FIBER T-Net for GI Broadband Service Design LLD V1.1 - T188.pdf |  | 1
386 | T386 | 472 | NA |  |  |  | Security & Regulatory Compliance | Testing | Network audit and certification by ISO certified agency(Tfiber will be arranging a partner for third party audit) |  |  | Open |  |  |  |  | Subject to start of certification process. |  |  | Sarmendra |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | 472Security & Regulatory Compliance | Security | OPEN | [6 empty] | 1
387 | T387 | 472 | NA |  |  |  | Security & Regulatory Compliance | Regulatory compliance | SLA Reporting for products other than Cell Tower and GIs |  |  | Colosed | [7 empty] | Siva Kumar |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-05-13 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\T387 | [6 empty] | 472Security & Regulatory Compliance | Security | CLOSED |  |  |  | 2025-05-13 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\T387 |  | 1
388 | T388 | 472 | NA |  | OSS | OSS | OSS | Helpdesk | OSS Integration with Helpdesk |  |  | Open |  |  |  |  | 17-05-2025: Artefacts needs to be collected from Sivakumar and seek approval. 26-06-2025: completed from OSS end |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | 472OSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1
389 | T389 | 472 | NA |  | OSS | OSS | OSS | OSS | BBNL Report stabilization |  |  | Open | [7 empty] | Suresh Pawar |  |  | COMPLETED & APPROVED |  |  | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\OSS\T389 | [6 empty] | 472OSS | Applications/Tools | CLOSED | COMPLETED & APPROVED | 0 |  |  | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\OSS\T389 |  | 1
390 | T390 | 472 | NA |  | OSS | OSS | OSS | OSS Dashboards | OSS Power BI Dashboard |  |  | Open |  |  |  |  | 09-09-2025: Requested reports are available, if any additional reports needed that can be incorporated |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | 472OSS | Applications/Tools | OPEN | COMPLETED | 09-09-2025: Requested reports are available, if any additional reports needed that can be incorporated |  |  |  |  | 1
391 | T391 | 472 | NA |  | OSS | OSS | OSS | OSS | Auto TT for Genset |  |  | Open |  |  |  |  | 26-06-2025: Confirmation awaited from NOC |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | 472OSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1
392 | T392 | 472 | NA |  | OSS | OSS | OSS | OSS | BBNL Status and Availability API integration |  |  | Open | [7 empty] | Suresh Pawar |  |  | COMPLETED & APPROVED |  |  | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\OSS\T392 | [6 empty] | 472OSS | Applications/Tools | CLOSED | COMPLETED & APPROVED | 0 |  |  | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\OSS\T392 |  | 1
393 | 394 | 472 | NA |  |  |  | DC-IT | License | Once excel license for VM |  |  | Open | [7 empty] | Ravi Kishore |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-07-08 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\TNOC\Artifact for - 394 | [6 empty] | 472DC-IT | Network | CLOSED |  |  |  | 2025-07-08 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\TNOC\Artifact for - 394 |  | 1
394 | 395 | 472 | NA |  |  |  | TNOC-Ops | Payments | SMS Gateway recharge |  |  | Open |  |  |  |  | SMS payment pending from Tfiber |  |  | Ahmad |  |  | COMPLETED & APPROVED | ad-ut-tfiber | 2025-07-08 | Not applicable | [6 empty] | 472TNOC-Ops | Network | CLOSED |  |  |  | 2025-07-08 | Artefacts not Required |  | 1
395 | 396 | 472 | NA |  |  |  | TNOC-Ops | AMC | AMC status including HPE/OT |  |  | Open |  |  |  |  | In Place |  |  | Ahmad |  |  | COMPLETED & APPROVED | ad-ut-tfiber | 2025-07-08 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\TNOC | [6 empty] | 472TNOC-Ops | Network | CLOSED |  |  |  | 2025-07-08 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\TNOC |  | 1
396 | 397 | 472 | NA |  |  |  | TNOC-Ops | Security | Access cards - 38 QTY |  |  | Open |  |  |  |  | Access card procured |  |  | Ahmad |  |  | COMPLETED & APPROVED | ad-ut-tfiber | 2025-07-08 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\TNOC | [6 empty] | 472TNOC-Ops | Network | CLOSED |  |  |  | 2025-07-08 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\TNOC |  | 1
397 | 398 | 472 | NA |  |  |  | GPON | Tejas | L&T is asked to submit response against untdertakings for the GPON Tejas issues |  |  | Colosed | [7 empty] | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\Tejas Undertaking | [6 empty] | 472GPON | GPON | CLOSED |  |  |  | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\Tejas Undertaking |  | 1
398 | 399 | 472 | NA |  |  |  | GPON | Tejas | Requested Tejas to enable the TR-069 for T-Fiber deployed elements |  |  | Open |  | Tejas OEM | ONT |  | 20-Sep-25: Artefacts submiited and approved MoM point Not in RFP and L&T confirmed this is not in scope. However, confirmation awaited from OEM on the shared list of parameters |  |  | Sayyad Pasha |  |  | COMPLETED & APPROVED | [9 empty] | 472GPON | GPON | CLOSED |  |  |  | 2025-09-20 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\399 |  | 1
399 | 400 | 472 | NA |  |  |  | GPON | Tejas | Accounting for Tejas OLT and EMS |  |  | Colosed | [7 empty] | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T167 | [6 empty] | 472GPON | GPON | CLOSED |  |  |  | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T167 |  | 1
400 | 401 | 472 | NA |  |  |  | GPON | Tejas | Accounting: All the parameters are not available in service created and Activated log(Including creation/activation of UNI) |  |  | Colosed | [7 empty] | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T167 | [6 empty] | 472GPON | GPON | CLOSED |  |  |  | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T167 |  | 1
401 | 402 | 472 | NA |  |  |  | GPON | Tejas | Accounting: All the parameters are not available in service deactivated and deleted log(Including deactivation/deletion of UNI) |  |  | Colosed | [7 empty] | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T167 | [6 empty] | 472GPON | GPON | CLOSED |  |  |  | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T167 |  | 1
402 | 403 | 472 | NA |  |  |  | GPON | Tejas | Accounting: Log is not available for OLT reboot |  |  | Colosed | [7 empty] | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T167 | [6 empty] | 472GPON | GPON | CLOSED |  |  |  | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T167 |  | 1
403 | 404 | 472 | NA |  |  |  | GPON | Tejas | Accounting: Log is not available for ONT reboot |  |  | Colosed | [7 empty] | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T167 | [6 empty] | 472GPON | GPON | CLOSED |  |  |  | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T167 |  | 1
404 | 405 | 472 | NA |  |  |  | GPON | Tejas | Accounting: Log is not available for the change of OLT location parameter from EMS |  |  | Colosed | [7 empty] | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T167 | [6 empty] | 472GPON | GPON | CLOSED |  |  |  | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T167 |  | 1
405 | 406 | 472 | NA |  |  |  | GPON | Tejas | Enabling TACACS in Tejas OLT |  |  | Colosed | [7 empty] | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T167 | [6 empty] | 472GPON | GPON | CLOSED |  |  |  | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T167 |  | 1
406 | 407 | 472 | NA |  |  |  | GPON | Tejas | CIR/PIR in OLT/EMS |  |  | Open |  | Tejas OEM | EMS/OLT |  | 20-Sep-25: CIR and PIR are different parameters but Tejas OLT considered only CIR not PIR, After combined recent meeting with OEM agreed to provide an alternate solution for config CIR and PIR seperately. Update awaited from OEM Tejas to provide the solution and demo for this issue. Update awaited from OEM | Tejas | Deepak | Sayyad Pasha |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | 472GPON | GPON | OPEN | [6 empty] | 1
407 | 408 | 472 | NA |  |  |  | GPON | Tejas | Port Description is not available for ONT Eth Ports |  |  | Colosed | [7 empty] | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\ONT Ports description | [6 empty] | 472GPON | GPON | CLOSED |  |  |  | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\ONT Ports description |  | 1
408 | 409 | 472 | NA |  |  |  | GPON | Tejas | Unable to modify the Service Name |  |  | Open | [7 empty] | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-07-03 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\409 | [6 empty] | 472GPON | GPON | CLOSED |  |  |  | 2025-07-03 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\409 |  | 1
409 | 410 | 472 | NA |  |  |  | GPON | Tejas | Special Characters not allowing in User Creation in EMS |  |  | Colosed | [7 empty] | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\Special Characters | [6 empty] | 472GPON | GPON | CLOSED |  |  |  | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\Special Characters |  | 1
410 | 411 | 472 | NA |  |  |  | GPON | Tejas | Unable to add 4th UNI in a service with 1Gb bandwidth |  |  | Colosed | [7 empty] | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\Report of ONT UNI in a Service | [6 empty] | 472GPON | GPON | CLOSED |  |  |  | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\Report of ONT UNI in a Service |  | 1
411 | 412 | 472 | NA |  |  |  | GPON | Tejas | End Customer MAC Address report from EMS |  |  | Colosed | [7 empty] | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\Ens users MAC address report | [6 empty] | 472GPON | GPON | CLOSED |  |  |  | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\Ens users MAC address report |  | 1
412 | 413 | 472 | NA |  |  |  | GPON | Tejas | If Mixed service deleted from EMS and discovered then service type is changing to HIS |  |  | Colosed | [7 empty] | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\Discovery of Mixed Service | [6 empty] | 472GPON | GPON | CLOSED |  |  |  | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\Discovery of Mixed Service |  | 1
413 | 414 | 472 | NA |  |  |  | GPON | Tejas | Live PM monitoring per UNI in EMS service Window |  |  | Open | [7 empty] | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-07-10 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\416 | [6 empty] | 472GPON | GPON | CLOSED |  |  |  | 2025-07-10 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\416 |  | 1
414 | 415 | 472 | NA |  |  |  | GPON | Tejas | Required Consolidated Service invenotry report with ONT UNI details from EMS |  |  | Colosed | [7 empty] | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\Serivce Report | [6 empty] | 472GPON | GPON | CLOSED |  |  |  | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\Serivce Report |  | 1
415 | 416 | 472 | NA |  |  |  | GPON | Tejas | Unable to Enable PM from EMS |  |  | Open | [7 empty] | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-07-07 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\414 | [6 empty] | 472GPON | GPON | CLOSED |  |  |  | 2025-07-07 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\414 |  | 1
416 | 417 | 472 | NA |  |  |  | GPON | Tejas | While creating service profile, maximum bandwidth is not taking 1024000 only considering 1000000 |  |  | Open | [7 empty] | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-TFiber | 2025-07-31 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\417 | [6 empty] | 472GPON | GPON | CLOSED |  |  |  | 2025-07-31 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\417 |  | 1
417 | 418 | 472 | NA |  |  |  | GPON | Tejas | Report of Syslog enabled in OLT |  |  | Colosed | [7 empty] | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\Report of Syslog enabled in Tejas OLTs | [6 empty] | 472GPON | GPON | CLOSED |  |  |  | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\Report of Syslog enabled in Tejas OLTs |  | 1
418 | 419 | 472 | NA |  |  |  | GPON | Tejas | Report of Radius enable in OLT |  |  | Colosed | [7 empty] | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\Report of Radius enabled in Tejas OLTs | [6 empty] | 472GPON | GPON | CLOSED |  |  |  | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\Report of Radius enabled in Tejas OLTs |  | 1
419 | 420 | 472 | NA |  |  |  | GPON | Tejas | OLT (SNMP-V3) status is not updating in EMS |  |  | Colosed | [7 empty] | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T167 | [6 empty] | 472GPON | GPON | CLOSED |  |  |  | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T167 |  | 1
420 | 421 | 472 | NA |  |  |  | GPON | Tejas | ONT status showing as Unexpected |  |  | Colosed | [7 empty] | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\ONT Unexpected State | [6 empty] | 472GPON | GPON | CLOSED |  |  |  | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\ONT Unexpected State |  | 1
421 | 422 | 472 | NA |  |  |  | GPON | Tejas | Unable to add multiple unis while creating mixed service |  |  | Colosed | [7 empty] | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\Create Service with Mulitple UNIs | [6 empty] | 472GPON | GPON | CLOSED |  |  |  | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\Create Service with Mulitple UNIs |  | 1
422 | 423 | 472 | NA |  |  |  | GPON | Tejas | ONT ETH Port status monitoring from OSS |  |  | Colosed | [7 empty] | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\Tejas LAN LOS | [6 empty] | 472GPON | GPON | CLOSED |  |  |  | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\Tejas LAN LOS |  | 1
423 | 424 | 472 | NA |  |  |  | GPON | Tejas | Unable to create service with same vlans on 2 diferent UNI ports |  |  | Colosed | [7 empty] | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\Service Report | [6 empty] | 472GPON | GPON | CLOSED |  |  |  | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\Service Report |  | 1
424 | 425 | 472 | NA |  |  |  | GPON | Tejas | OLT Node not reachable alarm clearance and regeneration |  |  | Open | [7 empty] | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-07-05 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\425 | [6 empty] | 472GPON | GPON | CLOSED |  |  |  | 2025-07-05 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\425 |  | 1
425 | 426 | 472 | NA |  |  |  | GPON | Tejas | Port Description is not available for all ONT UNI Ports |  |  | Colosed | [7 empty] | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\ONT Ports description | [6 empty] | 472GPON | GPON | CLOSED |  |  |  | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\ONT Ports description |  | 1
426 | 427 | 472 | NA |  |  |  | GPON | Tejas | In the Manage ONT Page we need have'(District name Location Name) 'In the Location field |  |  | Colosed | [7 empty] | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\OLT Partition Label in ONT Page | [6 empty] | 472GPON | GPON | CLOSED |  |  |  | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\OLT Partition Label in ONT Page |  | 1
427 | 428 | 472 | NA |  |  |  | GPON | Tejas | Automatically services converting from Active to Conflict - EMS |  |  | Colosed | [7 empty] | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T167 | [6 empty] | 472GPON | GPON | CLOSED |  |  |  | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T167 |  | 1
428 | 429 | 472 | NA |  |  |  | GPON | Tejas | DIAGUSER credentials getting reset after OLT Reboot |  |  | Colosed | [7 empty] | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\DIAGUSER Credentials are Not Resetting | [6 empty] | 472GPON | GPON | CLOSED |  |  |  | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\DIAGUSER Credentials are Not Resetting |  | 1
429 | 430 | 472 | NA |  |  |  | GPON | Tejas | while adding uni in EMS, list of downstream profiles are highlighting in the bottom |  |  | Open | [7 empty] | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-07-05 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\430 | [6 empty] | 472GPON | GPON | CLOSED |  |  |  | 2025-07-05 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\430 |  | 1
430 | 431 | 472 | NA |  |  |  | GPON | Tejas | Unable to add uni without translation in a translation service |  |  | Colosed | [7 empty] | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\Add UNI in Translated Service | [6 empty] | 472GPON | GPON | CLOSED |  |  |  | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\Add UNI in Translated Service |  | 1
431 | 432 | 472 | NA |  |  |  | GPON | Tejas | Nokia ONT ethernet port status is not updating under Tejas OLT | End user services working and not working status unable to monitor |  | Open |  | Tejas OEM | OLT/ONT |  | 13-Sep-2025: Testing is in progress for the ONT ETH status for different 3rd party ONTs under Tejas OLT 30-Aug-2025: Having dependency on both Tejas and Nokia. Also to test and verify the behaviour of the ONT ETH status for different 3rd party ONTs under Tejas OLT 18-Aug-2025 : Tejas updated as below As per ITU-T 988 standard, Section 9.5.1 – Physical path termination point Ethernet UNI, the Operational State attribute indicated whether the ME is capable of performing its function. As this is function of ONU, the operational state of the ONU Ethernet UNI is updated to OLT via AVC indications from the ONU. As per debugging done, the AVC indications are not received from Nokia ONU because of which OLT is not able to update UI about the “Operational State” of the ONU Ethernet port. 08-Aug-2025 : This point has been discussed in the call and TFiber asked to provide the solution. Tejas confirmed that they will check and confirm 02-Aug-2025 : This issue has been discussed with TFiber. When a LAN cable is connected to or removed from the ONT Ethernet port, the operational status is not updating in the OLT. However, the corresponding alarm is being generated and cleared as expected. This matter will be raised during the Tejas call scheduled for 04-Aug-2025 at 4:00 PM. 22-July-2025 : As per Nokia they are having the status update by alarm notification but not with the seperate byte for the status update. Same has been checking with Tejas to get the solution 18-July-2025 : A call scheduled with Nokia on 21-July-2025 to discuss on this issue 11-July-2025 : Also observed that ONT ethernet status is not updating only when Eth port is bridge mode whereas in Route status is updating. Same has been highlighted to Tejas. Working with both Nokia and Tejas for the closure 04-July-2025 : Nokia checking internally on the shared logs 03-July-2025 : Tejas responded that whenever ONT eth status is updating Nokia ONT is not sending the expected OMCI message. In the OMCI message, 3rd byte represents the status of ONT Eth which is not updating. Same has been checking with Nokia 30-June-2025 : Tejas analysing the shared logs on 23-June-2025 and Tejas has to revert with update Nokia ONT ethernet port status is not updating when connected under Tejas OLT however alarms are receiveing on ont eth port. Workaround applied as alarms available for the ONT ETH port status. Nokia has provided the required logs and Tejas is working on the same | Tejas | Deepak | Sayyad Pasha |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | 472GPON | GPON | OPEN | [6 empty] | 1
432 | 433 | 472 | NA |  |  |  | GPON | Tejas | Tejas ONT Software Upgrade which are connected under Nokia OLT |  |  | Open |  | Tejas OEM | ONT |  | 20-Sep-25: During the ONT software upgradation 11 ONTs got faulty, So GPON Team asked the Tejas team to provided RCA for the 11 ONTs and hold the upgradation activity temporarely. Tejas team provided the RCA 11 ONt Stating that 11 ONTs got faulty not because of upgradation activity . The reason for faulty is 3 ONTs of component and 8 ONTs of Memory corrupted due to multiple reboots. Note: Based on RCA, Now upgradation activity is being taken up(1312 ONTs upgradation completed out of 9530 as on today) 13-Sep-2025: Tejas confirmed that they don't have the 9logs to provide but shared the RCA by verifyting the ONTs at the time of repair 30-Aug2025: Having dependency on Tejas. Asked Tejas to provide the supporting logs. As per Tejas RCA ONT got faulty due to component faulty and memory corruption but these ONTs are working fine before the upgarde activity and only went faulty while performing the upgrade. Tejas have provide the clarity on this to proceed the upgrade for the remaining ONTs 08-Aug-2025 : Tejas provided the below RCA As per analysis, the ONT software upgrade from NOC is not the cause for ONT going down. On 3 ONTs a component was entering faulty state, this has been replaced. Remaining 8 ONTs had a file corruption in memory due to earlier multiple reboot events, this has been resolved by Re-Programming the ONT 02-Aug-2025 : Tejas yet to respond on this issue, same will be raised during the Tejas call scheduled for 04-Aug-2025 at 4:00 PM. 25-July-2025 : Tejas working on the delivered ONTs at their repair center. Tejas yet to share the update on this 14-July-2025 : ONTs delivered at Tejas repair center on 14-July-2025. Same has been communicated to Tejas team to expedite the process and share the RCA 14-July-2025 : ONT still not delivered at Tejas repai center, seems to be courier issue. Informed to concerned team to check and make it to delivier 07-July-2025 : ONTs are intransit to Tejas repair center To provide the contract of RMA on faulty devices replacement or repair 30-June-2025 : Successfully upgraded 600 ONTs in the production environment. All of them came up operational with no issue observed. However, 11 ONTs went unresponsive, and RMA raised for those. 23-June-2025 : RMA raised with Tejas for the ONTs ONTs which are running software version lower than 2.3.5.53 are upgrading locally | L&T |  | Sayyad Pasha |  | Open | WIP | [9 empty] | 472GPON | GPON | OPEN | [6 empty] | 1
433 | 434 | 472 | NA |  |  |  | GPON | Tejas | Script to change the pasword of DIAGUSER and tejas users |  |  | Colosed | [7 empty] | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\434 | [6 empty] | 472GPON | GPON | CLOSED |  |  |  | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\434 |  | 1
434 | 435 | 472 | NA |  |  |  | GPON | Tejas | Unable to configure downstream profiles to the ONT UNIs -- This option is available in production EMS but not available in latest released EMS |  |  | Colosed | [7 empty] | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T167 | [6 empty] | 472GPON | GPON | CLOSED |  |  |  | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T167 |  | 1
435 | 436 | 472 | NA |  |  |  | GPON | Tejas | MAC address of end device is not reflecting in COLT FDB entries whereas MAC address is available in service level FDB entries |  |  | Colosed | [7 empty] | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T167 | [6 empty] | 472GPON | GPON | CLOSED |  |  |  | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T167 |  | 1
436 | 437 | 472 | NA |  |  |  | GPON | Tejas | Whenever the ONT software is being downloaded to the OLT, the OLT management going down |  |  | Open | [7 empty] | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-TFiber | 2025-07-31 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\437 | [6 empty] | 472GPON | GPON | CLOSED |  |  |  | 2025-07-31 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\437 |  | 1
437 | 438 | 472 | NA |  |  |  | GPON | Tejas | The download bandwidth is not controlled for Nokia ONTs connected to the Tejas OLT |  |  | Colosed | [7 empty] | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T167 | [6 empty] | 472GPON | GPON | CLOSED |  |  |  | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T167 |  | 1
438 | 439 | 472 | NA |  |  |  | GPON | Tejas | Unable to add node in EMS with TACACS user |  |  | Colosed | [7 empty] | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T167 | [6 empty] | 472GPON | GPON | CLOSED |  |  |  | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T167 |  | 1
439 | 440 | 472 | NA |  |  |  | GPON | Tejas | API for ONT creation (Bridge/Route), location name update |  |  | Colosed | [7 empty] | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API | [6 empty] | 472GPON | GPON | CLOSED |  |  |  | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API |  | 1
440 | 441 | 472 | NA |  |  |  | GPON | Tejas | API for GI-BB Service, combo port, mixed service - Bridge Mode with/without translation, including uplink port configuration |  |  | Colosed | [7 empty] | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API | [6 empty] | 472GPON | GPON | CLOSED |  |  |  | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API |  | 1
441 | 442 | 472 | NA |  |  |  | GPON | Tejas | API for GI-BB Service, combo port, mixed service - Route Mode with/without translation, including uplink port configuration |  |  | Open | [7 empty] | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-TFiber | 2025-08-06 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\442 | [6 empty] | 472GPON | GPON | CLOSED |  |  |  | 2025-08-06 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\442 |  | 1
442 | 443 | 472 | NA |  |  |  | GPON | Tejas | API for TDIA Service, combo port, mixed service - Bridge Mode(Tag, Untag) including uplink port configuration |  |  | Colosed | [7 empty] | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API | [6 empty] | 472GPON | GPON | CLOSED |  |  |  | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API |  | 1
443 | 444 | 472 | NA |  |  |  | GPON | Tejas | API for TDIA Service, combo port, mixed service - Route Mode, including uplink port configuration |  |  | Colosed | [7 empty] | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API | [6 empty] | 472GPON | GPON | CLOSED |  |  |  | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API |  | 1
444 | 445 | 472 | NA |  |  |  | GPON | Tejas | API for Household Services, including uplink port configuration |  |  | Colosed | [7 empty] | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API | [6 empty] | 472GPON | GPON | CLOSED |  |  |  | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API |  | 1
445 | 446 | 472 | NA |  |  |  | GPON | Tejas | AP for IPTV services, including uplink port configuration |  |  | Colosed | [7 empty] | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API | [6 empty] | 472GPON | GPON | CLOSED |  |  |  | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API |  | 1
446 | 447 | 472 | NA |  |  |  | GPON | Tejas | API for VOIP services, including uplink port configuration |  |  | Colosed | [7 empty] | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API | [6 empty] | 472GPON | GPON | CLOSED |  |  |  | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API |  | 1
447 | 448 | 472 | NA |  |  |  | GPON | Tejas | API required to provision ONT along with selecting specific UNI port in ONT |  |  | Colosed | [7 empty] | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API | [6 empty] | 472GPON | GPON | CLOSED |  |  |  | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API |  | 1
448 | 449 | 472 | NA |  |  |  | GPON | Tejas | API required to provision ONT with multiple services along with selecting specific UNI port in ONT |  |  | Colosed | [7 empty] | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API | [6 empty] | 472GPON | GPON | CLOSED |  |  |  | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API |  | 1
449 | 450 | 472 | NA |  |  |  | GPON | Tejas | API required to provision ONT with same service on all ports |  |  | Colosed | [7 empty] | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API | [6 empty] | 472GPON | GPON | CLOSED |  |  |  | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API |  | 1
450 | 451 | 472 | NA |  |  |  | GPON | Tejas | API to configure multiple vlans on single ONT UNI Port |  |  | Colosed | [7 empty] | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API | [6 empty] | 472GPON | GPON | CLOSED |  |  |  | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API |  | 1
451 | 452 | 472 | NA |  |  |  | GPON | Tejas | API for the Q&Q services |  |  | Colosed | [7 empty] | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API | [6 empty] | 472GPON | GPON | CLOSED |  |  |  | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API |  | 1
452 | 453 | 472 | NA |  |  |  | GPON | Tejas | Configuration, API for extedning services to enterprise customers for cell towers |  |  | Colosed | [7 empty] | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API | [6 empty] | 472GPON | GPON | CLOSED |  |  |  | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API |  | 1
453 | 454 | 472 | NA |  |  |  | GPON | Tejas | API to configure Rythuvedika, MRO, School Services, CCTV |  |  | Colosed | [7 empty] | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API | [6 empty] | 472GPON | GPON | CLOSED |  |  |  | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API |  | 1
454 | 455 | 472 | NA |  |  |  | GPON | Tejas | API to verify and enable the PM |  |  | Colosed | [7 empty] | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API | [6 empty] | 472GPON | GPON | CLOSED |  |  |  | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API |  | 1
455 | 456 | 472 | NA |  |  |  | GPON | Tejas | API to configure Vlan and Profiles in OLT |  |  | Colosed | [7 empty] | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API | [6 empty] | 472GPON | GPON | CLOSED |  |  |  | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API |  | 1
456 | 457 | 472 | NA |  |  |  | GPON | Tejas | Verification of the services configured by NSO through Playbook(Cisco Tool) |  |  | Colosed | [7 empty] | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API to validate the configured Services | [6 empty] | 472GPON | GPON | CLOSED |  |  |  | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API to validate the configured Services |  | 1
457 | 458 | 472 | NA |  |  |  | GPON | Tejas | API to configure ONT UNI Port as tagged vlan |  |  | Colosed | [7 empty] | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API | [6 empty] | 472GPON | GPON | CLOSED |  |  |  | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API |  | 1
458 | 459 | 472 | NA |  |  |  | GPON | Tejas | API to validate the profiles, vlans available in OLT,ONT |  |  | Colosed | [7 empty] | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API to validate the configured Services | [6 empty] | 472GPON | GPON | CLOSED |  |  |  | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API to validate the configured Services |  | 1
459 | 460 | 472 | NA |  |  |  | GPON | Tejas | API to change the ONT ETH Port to Bridge to Route and Vice versa |  |  | Colosed | [7 empty] | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API | [6 empty] | 472GPON | GPON | CLOSED |  |  |  | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API |  | 1
460 | 461 | 472 | NA |  |  |  | GPON | Tejas | API to suspend/delete the service from a ONT UNI Port |  |  | Colosed | [7 empty] | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API | [6 empty] | 472GPON | GPON | CLOSED |  |  |  | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API |  | 1
461 | 462 | 472 | NA |  |  |  | GPON | Tejas | API to suspend/delete the complete service |  |  | Colosed | [7 empty] | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API | [6 empty] | 472GPON | GPON | CLOSED |  |  |  | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API |  | 1
462 | 463 | 472 | NA |  |  |  | GPON | Tejas | API to modify the service- ONT, UNI Port, bandwidth, vlan, description, unatgged to tag or vice versa., |  |  | Open |  | Tejas OEM | EMS/OLT |  | Having dependency on NSO and BSS | NSO | Jayanth | Sayyad Pasha |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | 472GPON | GPON | OPEN | [6 empty] | 1
463 | 464 | 472 | NA |  |  |  | GPON | Tejas | API to configure and delete the WAN profiles in WiFi ONT |  |  | Colosed | [7 empty] | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API | [6 empty] | 472GPON | GPON | CLOSED |  |  |  | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API |  | 1
464 | 465 | 472 | NA |  |  |  | GPON | Tejas | API to make PON Port admin up / down |  |  | Colosed | [7 empty] | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API | [6 empty] | 472GPON | GPON | CLOSED |  |  |  | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API |  | 1
465 | 466 | 472 | NA |  |  |  | GPON | Tejas | API to create/delete service Profile |  |  | Colosed | [7 empty] | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API | [6 empty] | 472GPON | GPON | CLOSED |  |  |  | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API |  | 1
466 | 467 | 472 | NA |  |  |  | GPON | Tejas | Required complete API and Template developer document |  |  | Colosed | [7 empty] | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API Document | [6 empty] | 472GPON | GPON | CLOSED |  |  |  | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API Document |  | 1
467 | 468 | 472 | NA |  |  |  | GPON | Nokia | ONT Ethernet Port PM Report |  |  | Colosed | [7 empty] | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\ONT ETH PM Report | [6 empty] | 472GPON | GPON | CLOSED |  |  |  | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\ONT ETH PM Report |  | 1
468 | 469 | 472 | NA |  |  |  | GPON | Nokia | ONT Wifi/Route Mode PM Report |  |  | Colosed | [7 empty] | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\ONT WiFi PM Report | [6 empty] | 472GPON | GPON | CLOSED |  |  |  | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\ONT WiFi PM Report |  | 1
469 | 470 | 472 | NA |  |  |  | GPON | Nokia | PM Report for 24hrs of OLT,ONT,ONT Eth Port(Bridge/Route), Wifi |  |  | Open | [7 empty] | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-TFiber | 2025-07-31 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\470 | [6 empty] | 472GPON | GPON | CLOSED |  |  |  | 2025-07-31 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\470 |  | 1
470 | 471 | 472 | NA |  |  |  | GPON | Nokia | ONT ETH Port status monitoring from OSS |  |  | Colosed | [7 empty] | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\Nokia LAN LOS | [6 empty] | 472GPON | GPON | CLOSED |  |  |  | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\Tejas LAN LOS |  | 1
471 | 472 | 472 | NA |  |  |  | GPON | Nokia | Unable to browse Internet when IPV6 configured in wifi ONT |  |  | Open | [7 empty] | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-TFiber | 2025-07-31 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\472 | [6 empty] | 472GPON | GPON | CLOSED |  |  |  | 2025-07-31 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\472 |  | 1
472 | M1 | MOM | 2023-02-06 |  |  |  | NOC Operationalization | Dashboards | Submit a fortnightly report (Kanban chart) for monitoring all activities in TNOC, including OSS, BSS, NSO, etc. |  | Critical | Open |  | OSS Dashboards |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1
473 | M10 | MOM | 2023-04-03 |  |  |  | GIS | Resource Related | Evaluation of License Sufficiency and Ramp-Up Plan |  | Critical | Open |  | OSS Dashboards |  |  | TFIBER is a critical dependency for closing the GIS licenses |  |  | Kaushalendra Kumar |  | Open | Open | [9 empty] | MOMGIS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
474 | M100 | MOM | 2023-08-01 |  |  |  | Helpdesk | Handbook & SOPs | Call Escalation Recording Process |  | Critical | open |  |  |  | Closed | 25-Sep-25: Artefacts to be uploaded |  |  | Siva Kumar |  |  | COMPLETED & APPROVED | [9 empty] | MOMHelpdesk | Helpdesk (Contact Center) | CLOSED |  |  |  | 2025-09-24 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\M100 |  | 1
475 | M1000 | MOM | 2024-01-25 |  |  |  | WFM |  | Adopt WFM by packages B & C and procure licenses |  | Critical | Open |  |  |  |  | TFIBER is a critical dependency for closing the WFM license |  |  | Kaushalendra Kumar |  | Open | Open | [9 empty] | MOMWFM | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
476 | M1001 | MOM | 2024-01-25 |  |  |  | Field Related |  | Complete implementation of Mandal rings for NoFN PH-1 to declare District Go-Live |  | Critical | Open |  |  |  |  | MR-06 & MR-25 Open due to ROW issue Rest all closed. |  |  | S Kodali |  | Open | Open | [9 empty] | MOMField Related | Field Related issues | OPEN |  |  | Project Team |  | #N/A |  | 1
477 | M1002 | MOM | 2024-01-25 |  |  |  | Field Related |  | Restore all social welfare and tribal welfare schools to serviceable condition |  | Critical | Open |  |  |  |  | Ongoing process as per priority from clients |  |  | S Kodali |  | Open | Open | [9 empty] | MOMField Related | Field Related issues | OPEN |  |  | Ongoing operations, O&M Team |  | #N/A |  | 1
478 | M1003 | MOM | 2024-01-25 |  |  |  | Field Related |  | Complete all GI connectivity by March '24 and secure GI payments |  | Critical | Open |  |  |  |  | Completed for |  |  | S Kodali |  | Open | Open | [9 empty] | MOMField Related | Field Related issues | OPEN |  |  | Project Team |  | #N/A |  | 1
479 | M1004 | MOM | 2024-01-25 |  |  |  | Field Related |  | Focus on top 4 priorities for network readiness |  | Critical | Open | [7 empty] | S Kodali |  | Open | Open | [9 empty] | MOMField Related | Field Related issues | OPEN |  |  | Project Team |  | #N/A |  | 1
480 | M1005 | MOM | 2024-01-25 |  |  |  | Field Related |  | Make the network ready for service review by State IT&EC Minister |  | Critical | Open | [7 empty] | S Kodali |  | Open | Open | [9 empty] | MOMField Related | Field Related issues | OPEN |  |  | Project Team |  | #N/A |  | 1
481 | M1006 | MOM | 2024-02-13 |  |  |  | Field Related |  | Issue with status of Sangareddy district E2E completion |  | Critical | Open |  |  |  |  | 9 Mandal E2E completed , 2 WIP , balance 12 Mandal target by Dec'25 2 mandals BER/ ROW permission issue/not feasable |  |  | S Kodali |  | Open | Open | [9 empty] | MOMField Related | Field Related issues | OPEN |  |  | Project Team |  | #N/A |  | 1
482 | M1007 | MOM | 2024-02-13 |  |  |  | Field Related |  | Status of GP migrations and POP completion |  | Critical | Open |  |  |  |  | 3520 GPs Completed as work front released till date. |  |  | S Kodali |  | Open | Open | [9 empty] | MOMField Related | Field Related issues | OPEN |  |  | Project Team |  | #N/A |  | 1
483 | M1008 | MOM | 2024-02-13 |  |  |  | Field Related |  | Pending mandals for End-End AT |  | Critical | Open |  |  |  |  | 42 mandals WIP as per work front availability |  |  | S Kodali |  | Open | Open | [9 empty] | MOMField Related | Field Related issues | OPEN |  |  | Project Team |  | #N/A |  | 1
484 | M1009 | MOM | 2024-02-13 |  |  |  | Security & Regulatory Compliance | Regulatory Compliance | Non-compliance with IP-MAC binding |  | Critical | Open |  |  |  |  | Port winding is possible , however it will cause difficulty with field units. need brainstormig before deployment of Mac binding |  |  | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1
485 | M101 | MOM | 2023-08-01 |  |  |  | Helpdesk | User Experience | Missed Call Feature on WhatsApp |  | Critical | open |  |  |  | WIP | 11-Sep-25: Existing product will not Support | L&T | Shiva kumar | Siva Kumar |  | Open | WIP | [9 empty] | MOMHelpdesk | Helpdesk (Contact Center) | OPEN | [6 empty] | 1
486 | M1010 | MOM | 2024-02-13 |  |  |  | OEM Related |  | Issues with application integration |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMOEM Related | OEM Related Issues | OPEN | [6 empty] | 1
487 | M1011 | MOM | 2024-02-13 |  |  |  | Security & Regulatory Compliance | Regulatory Compliance | Review of submitted policy documents |  | Critical | Open |  |  |  |  | 02 Policy has been cleared by TPA . Work on balance policy is in process |  |  | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1
488 | M1012 | MOM | 2024-02-13 |  |  |  | NOC Operationalization |  | Status of asset management automation |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMNOC Operationalization | Network | OPEN | [6 empty] | 1
489 | M1013 | MOM | 2024-02-13 |  |  |  | Security & Regulatory Compliance | Compliance | Matter of security for personnel access |  | Critical | Open |  |  |  |  | Request elaborate the point for discussion. Existing mechanism is regulating personnel access at NOC and sensitive places |  |  | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1
490 | M1014 | MOM | 2024-02-13 |  |  |  | Security & Regulatory Compliance | Compliance | Incomplete detailing in security report |  | Critical | Open |  |  |  |  | Request elaborate the point for discussion. or any specific criteria need to added or removed |  |  | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1
491 | M1015 | MOM | 2024-02-13 |  |  |  | Security & Regulatory Compliance | Regulatory Compliance | Review of SSL for applications |  | Critical | Open |  |  |  |  | All applications owner has been insisted to use SSL for application as per security measures. And it is being ensured that application moving to Producation environment are SSL complied |  |  | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1
492 | M1016 | MOM | 2024-02-13 |  |  |  | Security & Regulatory Compliance | Regulatory Compliance | Access control policy |  | Critical | Open |  |  |  |  | ACL policy is defined as per the requested user provided imformation. |  |  | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1
493 | M1017 | MOM | 2024-02-13 |  |  |  | Security & Regulatory Compliance | Regulatory Compliance | Concern about remote access management |  | Critical | Open |  |  |  |  | All remote management access is through VPN only . |  |  | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1
494 | M1018 | MOM | 2024-02-13 |  |  |  | Security & Regulatory Compliance | Compliance | Inquiry on DMZ details |  | Critical | Open |  |  |  |  | DMZ policy has been shared with team inluitive for verification |  |  | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1
495 | M1019 | MOM | 2024-02-13 |  |  |  | Security & Regulatory Compliance | Compliance | Status of leave and potential impacts |  | Critical | Open |  |  |  |  | Point not clear |  |  | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1
496 | M102 | MOM | 2023-08-01 |  |  |  | Helpdesk | User Experience | Automated Response for Email Complaints |  | Critical | Open |  |  |  | WIP |  |  |  | Siva Kumar |  | Open | WIP | [9 empty] | MOMHelpdesk | Helpdesk (Contact Center) | OPEN | [6 empty] | 1
497 | M1020 | MOM | 2024-02-13 |  |  |  | Security & Regulatory Compliance | Compliance | Directive for approval and proper usage of tool services and resources |  | Critical | Open |  |  |  |  | All people has been extended access through RBAC form approved by AD-NoC |  |  | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1
498 | M1021 | MOM | 2024-02-13 |  |  |  | Security & Regulatory Compliance | Regulatory Compliance | Requirements for RMC's reporting |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1
499 | M1022 | MOM | 2024-02-13 |  |  |  | Security & Regulatory Compliance | Regulatory Compliance | Proposal for security updates bulletin |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1
500 | M1023 | MOM | 2024-02-13 |  |  |  | Security & Regulatory Compliance | Regulatory Compliance | Implementation of SOC's best practices |  | Critical | Open |  |  |  |  | SOC's best practices are for SOC includes SIEM,XDR and SOAR integrated Mitre ATT&CKS database. |  |  | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1
501 | M1024 | MOM | 2024-02-16 |  |  |  | BSS |  | Ticketing process and tracking |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
502 | M1025 | MOM | 2024-02-16 |  |  |  | BSS |  | Task creation in billing module |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
503 | M1026 | MOM | 2024-02-16 |  |  |  | Helpdesk | Training Module | Recruitment and training of billing officers |  | Critical | open |  |  |  | Closed | 12-Sep-25: its part of Business Helpdesk(T FIber) |  |  | Siva Kumar |  |  | COMPLETED & APPROVED | [9 empty] | MOMHelpdesk | Helpdesk (Contact Center) | CLOSED |  |  |  | 2025-09-24 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\M116,723,1026 |  | 1
504 | M1027 | MOM | 2024-02-16 |  |  |  | BSS |  | Contact synchronization in Lead creation and conversion |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
505 | M1028 | MOM | 2024-02-16 |  |  |  | Security & Regulatory Compliance | Regulatory Compliance | Review of submitted security policy documents |  | Critical | Open |  |  |  |  | Point Duplicated |  |  | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1
506 | M1029 | MOM | 2024-02-16 |  |  |  | Security & Regulatory Compliance | Compliance | Asset management and data classification |  | Critical | Open |  |  |  |  | It need DLP solution to tag data as per classification |  |  | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1
507 | M103 | MOM | 2023-08-01 |  |  |  | Helpdesk | Resource Related | Helpdesk Manager Availability for 24 Hrs |  | Critical | open |  |  |  | Closed | 24-Sep-25: Existing Lead available during Business Hours, Remaining duration Shift Lead will Manage |  |  | Siva Kumar |  |  | COMPLETED & APPROVED | [9 empty] | MOMHelpdesk | Helpdesk (Contact Center) | CLOSED |  |  |  | 2025-09-24 | Artefacts not Required |  | 1
508 | M1030 | MOM | 2024-02-16 |  |  |  | Security & Regulatory Compliance | Regulatory Compliance | Control of user and visitor access |  | Critical | Open |  |  |  |  | Already physical record is being maintained |  |  | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1
509 | M1031 | MOM | 2024-02-16 |  |  |  | Security & Regulatory Compliance | Regulatory Compliance | Concerns about security reporting and compliance |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1
510 | M1032 | MOM | 2024-02-16 |  |  |  | Security & Regulatory Compliance | Regulatory Compliance | VPAT implementation and firmware patching |  | Critical | Open |  |  |  |  | VAPT will be conducted by Tfiber . Remediation for sam will be intiated thereafter |  |  | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1
511 | M1033 | MOM | 2024-02-16 |  |  |  | Security & Regulatory Compliance | Regulatory Compliance | Compliance to access management policy |  | Critical | Open |  |  |  |  | Access Management policy is as per RBAC approval. |  |  | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1
512 | M1034 | MOM | 2024-03-14 |  |  |  | NOC Operationalization | Launch Readiness | Assessing the progress achieved after the Governance meeting held on March 5, 2024. |  | Critical | Open |  |  |  | CLosed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1
513 | M1035 | MOM | 2024-03-14 |  |  |  | BSS |  | Addressing the delays in the End-to-End demonstration of products due to billing/invoice module issues. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
514 | M1036 | MOM | 2024-03-14 |  |  |  | NOC Operationalization | Launch Readiness | Achieving operationalization and readiness of T-NOC. |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMNOC Operationalization | Network | OPEN | [6 empty] | 1
515 | M1037 | MOM | 2024-03-14 |  |  |  | NOC Operationalization | Launch Readiness | Addressing product gaps and OEM execution delays for the readiness of 5 products. |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMNOC Operationalization | Network | OPEN | [6 empty] | 1
516 | M1038 | MOM | 2024-03-14 |  |  |  | WFM |  | Ensuring readiness of WFM integration, order fulfillment, service provisioning, and NOC critical points closure. |  | Critical | Open | [7 empty] | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMWFM | Applications/Tools | OPEN | [6 empty] | 1
517 | M1039 | MOM | 2024-03-14 |  |  |  | NSO | Service Delivery | Ensuring the service delivery organization is structured for an interim period. |  | Critical | Open | [7 empty] | Jayant Madavi |  | Open | Open | [9 empty] | MOMNSO | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
518 | M104 | MOM | 2023-08-01 |  |  |  | Helpdesk | Handbook & SOPs | Incident categorization to be exhaustive, response timelines to be defined and attached based on incident categorization. |  | Critical | open |  |  |  | Artefacts to be submitted | 24-Sep-25: Updated Document Shared 23-Aug-23 |  |  | Siva Kumar |  |  | COMPLETED & APPROVED | [9 empty] | MOMHelpdesk | Helpdesk (Contact Center) | CLOSED |  |  |  | 2025-09-24 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\M104,105,109,111,113,115,122,123,127,128,130,132,162 |  | 1
519 | M1040 | MOM | 2024-03-14 |  |  |  | Field Related | Network Availibilty | Achieving network availability reports compliance and readiness. |  | Critical | Open |  |  |  |  | closed under O&M scope |  |  | S Kodali |  | Open | Open | [9 empty] | MOMField Related | Field Related issues | OPEN |  |  | O&M Team |  | #N/A |  | 1
520 | M1041 | MOM | 2024-03-14 |  |  |  | OEM Related | Network Availibilty | Resolving OEM-related gaps and achieving automation roadmap targets. |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMOEM Related | OEM Related Issues | OPEN | [6 empty] | 1
521 | M1042 | MOM | 2024-03-14 |  |  |  | T&D Environment | Network Availibilty | Establishing a pre-production environment for testing applications before moving to production. |  | NON-Critical | Open |  |  |  |  | [15/09/25] Test Environment is actively used for T&D by Delivery and OEM teams. |  |  | Ravi Kishore |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMT&D Environment | Applications | OPEN |  |  |  |  | #N/A |  | 1
522 | M1043 | MOM | 2024-03-14 |  |  |  | NOC Operationalization | Launch Readiness | L&T to address the delays in demonstrating the End-to-End of the Dark Fiber product. |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMNOC Operationalization | Network | OPEN | [6 empty] | 1
523 | M1044 | MOM | 2024-03-14 |  |  |  | NOC Operationalization | NOC Readiness | L&T to complete 423 critical points and provide a summary of the status along with action required for balance points. |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1
524 | M1045 | MOM | 2024-03-14 |  |  |  | NOC Operationalization | NOC Readiness | L&T to ensure understanding of the interim T-NOC operationalization plan and work towards readiness. |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMNOC Operationalization | Network | OPEN | [6 empty] | 1
525 | M1046 | MOM | 2024-03-14 |  |  |  | BSS |  | L&T to be prepared for the next dry run demo and update the order management and quote management statuses. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
526 | M1047 | MOM | 2024-03-14 |  |  |  | NOC Operationalization | NOC Readiness | L&T to provide updates and clarifications on the payment gateway, ticket functionalities, and NSO readiness. |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMNOC Operationalization | Network | OPEN | [6 empty] | 1
527 | M1048 | MOM | 2024-03-14 |  |  |  | WFM |  | L&T to be prepared for the demonstration of WFM for order fulfillment/service provisioning. |  | Critical | Open | [7 empty] | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMWFM | Applications/Tools | OPEN | [6 empty] | 1
528 | M1049 | MOM | 2024-03-14 |  |  |  | T&D Environment |  | L&T to provide details on modules working in pre-production and production environments and seek approvals for transitions. |  | NON-Critical | Open |  |  |  |  | [15/09/25] Test Environment is actively used for T&D by Delivery and OEM teams. |  |  | Ravi Kishore |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMT&D Environment | Applications | OPEN |  |  |  |  | #N/A |  | 1
529 | M105 | MOM | 2023-08-01 |  |  |  | Helpdesk | Handbook & SOPs | Clarity required in the definition of roles and responsibilities of L1 and L2 agents, incident categorization to be handled at L1 level, type of queries, resolution time, escalation matrix to be better defined. |  | Critical | open |  |  |  | Artefacts to be submitted | 24-Sep-25: Updated Document Shared 23-Aug-23 |  |  | Siva Kumar |  |  | COMPLETED & APPROVED | [9 empty] | MOMHelpdesk | Helpdesk (Contact Center) | CLOSED |  |  |  | 2025-09-24 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\M104,105,109,111,113,115,122,123,127,128,130,132,162 |  | 1
530 | M1050 | MOM | 2024-03-14 |  |  |  | NOC Operationalization | Launch Readiness | The demonstration of the End-to-End of one product by 18th March 2024. |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMNOC Operationalization | Network | OPEN | [6 empty] | 1
531 | M1051 | MOM | 2024-03-14 |  |  |  | NOC Operationalization | Launch Readiness | T0 phase points to be completed by March 2024. |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1
532 | M1052 | MOM | 2024-03-14 |  |  |  | Field Related | District Completion Target | Complete E2E AT Certificate of Rangareddy, Mahbubnagar, Vikarabad & Narayanpet districts by 7th April 2024. |  | NON-Critical | Open | [7 empty] | S Kodali |  | Open | Open | [9 empty] | MOMField Related | Field Related issues | OPEN |  |  | Project Team |  | #N/A |  | 1
533 | M1053 | MOM | 2024-03-14 |  |  |  | T&D Environment |  | Provide a summary of applications in pre-production & production environments by 16th March 2024. |  | NON-Critical | Open |  |  |  |  | [15/09/25] Test Environment is actively used for T&D by Delivery and OEM teams. NOC submission provided in Tfiber has the T&D application from Oct-Mar2025 |  |  | Ravi Kishore |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMT&D Environment | Applications | OPEN |  |  |  |  | #N/A |  | 1
534 | M1054 | MOM | 2024-03-14 |  |  |  | OEM Related |  | Provide updates on the pre-production environment, OEM gaps, and integration of systems and applications by 16th March 2024. |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMOEM Related | OEM Related Issues | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1
535 | M1055 | MOM | 2024-03-14 |  |  |  | NOC Operationalization | Launch Readiness | Ensure all 5 products are ready by April 2024. |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMNOC Operationalization | Network | OPEN | [6 empty] | 1
536 | M1056 | MOM | 2024-03-14 |  |  |  | Field Related | Network Availibilty | Achieve 97% Network availability in Gadwal & Wanaparthy from 1st April 2024. |  | NON-Critical | Open |  |  |  |  | closed under O&M scope |  |  | S Kodali |  | Open | Open | [9 empty] | MOMField Related | Field Related issues | OPEN |  |  | O&M Team |  | Artefacts to be uploaded |  | 1
537 | M1057 | MOM | 2024-03-14 |  |  |  | Field Related | Network Availibilty | Achieve 90% Network availability in Mahbubnagar and Rangareddy for April 2024. |  | NON-Critical | Open |  |  |  |  | closed under O&M scope |  |  | S Kodali |  | Open | Open | [9 empty] | MOMField Related | Field Related issues | OPEN |  |  | O&M Team |  | Artefacts to be uploaded |  | 1
538 | M1058 | MOM | 2024-03-14 |  |  |  | NOC Operationalization | Network Availibilty | All critical points for T-NOC operationalization to be completed by 30th March 2024. |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMNOC Operationalization | Network | OPEN | [6 empty] | 1
539 | M1059 | MOM | 2024-06-11 |  |  |  | NOC Operationalization |  | Interim NOC O&M: L&T to complete pending tasks and seek T-Fiber approval for the start of Interim NOC O&M. |  | Critical | Open |  |  |  | NON Critical to be reviewd later | 22-Sep-25: SOPs, Handbook, T0-T6 and interim NOC Plan submitted to the T fiber on XX-XX-XXXX. T Fiber team has shared 65 queries on SOP and Hanbooks. And these 65 points have been incorporated as a different points in this master tracker.(Sub domain as Handbook and SOP). Pending tasks(44 SOP, Opertaions Handbook, Full NOC Readiness plan, NOC all KPI) completed and Interim NOC plan has been Submitted. Artefacts to be uploaded in NAS Interim NOC had started in OCt24 | L&T | Sivaprasad | Sivaprasad |  | Open | Open | [9 empty] | MOMNOC Operationalization | Network | OPEN | [6 empty] | 1
540 | M106 | MOM | 2023-08-01 |  |  |  | Helpdesk | Mini Helpdesk | Mechanism needed between T-NOC Helpdesk and District Collector offices for complaints that may be made directly to the District Collector office. Provision for a mini-Helpdesk node at each district, with a facility/hotline for an authorized person to log a call/complaint on behalf of the District Collector Office, similar to the direct walk-in channel for customer complaints at T-NOC. |  | NON-Critical | open |  |  |  | Closed | 24-Sep-25: Artefacts to be uploaded |  |  | Siva Kumar |  |  | COMPLETED & APPROVED | [9 empty] | MOMHelpdesk | Helpdesk (Contact Center) | CLOSED |  |  |  | 2025-09-24 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\M106 |  | 1
541 | M1060 | MOM | 2024-06-11 |  |  |  | NOC Operationalization |  | NOC Go-Live: L&T requested recognition of NOC Go-Live status despite manual provisioning; T-Fiber requires full automation for transition from interim to Full NOC. |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMNOC Operationalization | Network | OPEN | [6 empty] | 1
542 | M1061 | MOM | 2024-06-11 |  |  |  | NOC Operationalization |  | Functional Gaps in NOC Elements: L&T to meet with OEMs to identify scope gaps and evaluate alternate BSS solutions, presenting recommendations within a week. |  | Critical | Open |  |  |  | Closed, Artefacts to be uploaded | 23-Sep-25: Approved Artefacts to be Submitted | L&T | Sivaprasad | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  |  | Artefacts Need to upload |  | 1
543 | M1062 | MOM | 2024-06-11 |  |  |  | NOC Operationalization |  | Time Delays: L&T to comply with RFP and submit timelines for Full NOC readiness. |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMNOC Operationalization | Network | OPEN | [6 empty] | 1
544 | M1063 | MOM | 2024-06-11 |  |  |  | NOC Operationalization |  | WFM Tool Implementation: L&T to operationalize the WFM tool for Package A within one week. |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMNOC Operationalization | Network | OPEN | [6 empty] | 1
545 | M1064 | MOM | 2024-06-11 |  |  |  | NOC Operationalization |  | MB and LOA Amendment: L&T to complete MB duct reconciliation; T-Fiber to review data submitted by L&T. |  | Critical | Open |  |  |  | Will be discussed later | 23-Sep-25: NON Critical to be reviewd later | L&T | Sivaprasad | Sivaprasad |  | Open | Open | [9 empty] | MOMNOC Operationalization | Network | OPEN | [6 empty] | 1
546 | M1065 | MOM | 2024-06-11 |  |  |  | NOC Operationalization |  | Chemical Storage in GP PoPs: L&T to create guidelines for panchayat chemical storage handling. |  | Critical | Open |  |  |  | Will be discussed later | 23-Sep-25: NON Critical to be reviewd later | L&T | Sivaprasad | Sivaprasad |  | Open | Open | [9 empty] | MOMNOC Operationalization | Network | OPEN | [6 empty] | 1
547 | M1066 | MOM | 2024-06-11 |  |  |  | NOC Operationalization |  | PoP Relocation: L&T to re-offer rates for PoP relocation. |  | Critical | Open |  |  |  | Will be discussed later | 23-Sep-25: NON Critical to be reviewd later | L&T | Sivaprasad | Sivaprasad |  | Open | Open | [9 empty] | MOMNOC Operationalization | Network | OPEN | [6 empty] | 1
548 | M1067 | MOM | 2024-06-11 |  |  |  | NOC Operationalization |  | Centralized Billing for EB: L&T to submit a proposal for centralized billing. |  | Critical | Open |  |  |  | Will be discussed later | 23-Sep-25: NON Critical to be reviewd later | L&T | Sivaprasad | Sivaprasad |  | Open | Open | [9 empty] | MOMNOC Operationalization | Network | OPEN | [6 empty] | 1
549 | M1068 | MOM | 2024-06-11 |  |  |  | NOC Operationalization |  | L&T Cash Flow Pressures: L&T to submit invoices as per RFP compliance for payment release. |  | Critical | Open |  |  |  | Will be discussed later | 23-Sep-25: NON Critical to be reviewd later | L&T | Sivaprasad | Sivaprasad |  | Open | Open | [9 empty] | MOMNOC Operationalization | Network | OPEN | [6 empty] | 1
550 | M1069 | MOM | 2024-06-11 |  |  |  | NOC Operationalization |  | GST Payments: T-Fiber to explore options within regulatory norms to resolve GST payment issues. |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMNOC Operationalization | Network | OPEN | [6 empty] | 1
551 | M107 | MOM | 2023-08-01 |  |  |  | Helpdesk | Handbook & SOPs | Clarification needed on whether general enquiries are treated as incidents. |  | NON-Critical | open |  |  |  | Artefacts to be submitted | 25-Sep-25 Ans: All business queries will created as lead in BSS |  |  | Siva Kumar |  |  | COMPLETED & APPROVED | [9 empty] | MOMHelpdesk | Helpdesk (Contact Center) | CLOSED |  |  |  | 2025-09-24 | Artefacts not Required |  | 1
552 | M1070 | MOM | 2024-06-11 |  |  |  | NOC Operationalization |  | Interim O&M Payment: L&T to submit supporting documents for payment against Interim O&M. |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1
553 | M1071 | MOM | 2024-06-11 |  |  |  | NOC Operationalization |  | Full NOC Readiness Plan: L&T to submit a comprehensive plan for Full NOC readiness. |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1
554 | M1072 | MOM | 2024-06-11 |  |  |  | NOC Operationalization |  | GI Connectivity: L&T to address slow progress and start NoFN connectivity. |  | Critical | Open |  |  |  | Will be discussed later | 23-Sep-25: NON Critical to be reviewd later | L&T | Sivaprasad | Sivaprasad |  | Open | Open | [9 empty] | MOMNOC Operationalization | Network | OPEN | [6 empty] | 1
555 | M1073 | MOM | 2024-06-11 |  |  |  | Field Related |  | AT Completion: L&T to complete AT of 10 districts by July 2024, accounting for monsoon season. |  | Critical | Open | [7 empty] | S Kodali |  | Open | Open | [9 empty] | MOMField Related | Field Related issues | OPEN |  |  | Project Team |  | #N/A |  | 1
556 | M1074 | MOM | 2024-06-11 |  |  |  | Field Related |  | RV – GIs: L&T to identify new partners to connect Rhythu Vedikas. |  | Critical | Open | [7 empty] | S Kodali |  | Open | Open | [9 empty] | MOMField Related | Field Related issues | OPEN |  |  | Project Team |  | #N/A |  | 1
557 | M1075 | MOM | 2024-06-11 |  |  |  | NOC Operationalization |  | SLA Achievement: L&T to improve O&M availability to meet the target of 97%. |  | Critical | Open |  |  |  |  | 22-Sep-25: MSIs Field team is working on it. Multiple dependencies like fiber rerouting, equipment faults, AT WIP for balance nodes, etc. NOC to support in terms of TT, escalations, reports. |  |  | Ahmad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-22 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\TNOC\M1075 |  | 1
558 | M1076 | MOM | 2024-06-11 |  |  |  | NOC Operationalization |  | The urgency for L&T to demonstrate agreed SOPs are in place for Interim NOC O&M and to submit sample reports. |  | Critical | Open |  |  |  | Artefacts to be submitted | 24-Sep-25: 44 agreed SOP doc submitted and signed off. Artefacts will be uploaded today in NAS |  |  | Siva Kumar |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-24 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\M1076 |  | 1
559 | M1077 | MOM | 2024-06-11 |  |  |  | NOC Operationalization |  | The need for L&T to address the slow progress in GI connectivity and to start NoFN connectivity. |  | Critical | Open |  |  |  | Will be discussed later | 23-Sep-25: NON Critical to be reviewd later | L&T | Sivaprasad | Sivaprasad |  | Open | Open | [9 empty] | MOMNOC Operationalization | Network | OPEN | [6 empty] | 1
560 | M1078 | MOM | 2024-06-11 |  |  |  | Field Related |  | The expectation for L&T to complete AT for multiple districts by July 2024 and to increase resources to meet targets. |  | Critical | Open | [7 empty] | S Kodali |  | Open | Open | [9 empty] | MOMField Related | Field Related issues | OPEN |  |  | Project Team |  | #N/A |  | 1
561 | M1079 | MOM | 2024-06-11 |  |  |  | NOC Operationalization |  | The requirement for L&T to resolve issues with OEMs and to consider ready-made BSS solutions to mitigate risks. |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1
562 | M108 | MOM | 2023-08-01 |  |  |  | Helpdesk | Handbook & SOPs | Clarification needed on whether general enquiries are treated as incidents. |  | NON-Critical | open |  |  |  | Artefacts to be submitted | 25-Sep-25 Ans: All business queries will created as lead in BSS |  |  | Siva Kumar |  |  | COMPLETED & APPROVED | [9 empty] | MOMHelpdesk | Helpdesk (Contact Center) | CLOSED |  |  |  | 2025-09-24 | Artefacts not Required |  | 1
563 | M1080 | MOM | 2024-06-11 |  |  |  | NOC Operationalization |  | Asset Management Policy to be drafted and submitted by L&T before 29th June 2024. |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMNOC Operationalization | Network | OPEN | [6 empty] | 1
564 | M1081 | MOM | 2024-06-11 |  |  |  | Security & Regulatory Compliance | NOC Operationalization | Security Audit of ILL (10G) commissioning to be completed urgently and communicated to DOT prior to service launch. |  | Critical | Open |  |  |  |  | No Provisioning for ILL security. ISP audit will be relevant in this regard. |  |  | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1
565 | M1082 | MOM | 2024-06-11 |  |  |  | NOC Operationalization |  | L&T to set up a dedicated security team for the project to resolve all pending security actions. |  | Critical | Open |  |  |  | NON Critical to be reviewd later | 23-Sep-25: NON Critical to be reviewd later | L&T | Sivaprasad | Sivaprasad |  | Open | Open | [9 empty] | MOMNOC Operationalization | Network | OPEN | [6 empty] | 1
566 | M1083 | MOM | 2024-06-11 |  |  |  | NOC Operationalization |  | L&T to finalize the appointment of a Security SME, with Vikram Khatri being considered for the role. |  | Critical | Open |  |  |  | NON Critical to be reviewd later | 23-Sep-25: NON Critical to be reviewd later | L&T | Sivaprasad | Sivaprasad |  | Open | Open | [9 empty] | MOMNOC Operationalization | Network | OPEN | [6 empty] | 1
567 | M1084 | MOM | 2024-06-11 |  |  |  | NOC Operationalization |  | L&T to send pre-read material at least one day before the next meeting. |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1
568 | M1085 | MOM | 2024-06-11 |  |  |  | NOC Operationalization |  | Mr. Rajesh Thangavelu, Security in-charge, was absent from the meeting despite specific requests for his presence. |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1
569 | M1086 | MOM | 2024-06-11 |  |  |  | NOC Operationalization |  | No action items from earlier Minutes of Meetings (MOMs) were presented in the RMC Meeting. |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1
570 | M1087 | MOM | 2024-06-11 |  |  |  | NOC Operationalization |  | No formal intimation regarding the exit of the existing Security SME (Mr. Gandhi) by L&T. |  | Critical | Open |  |  |  | NON Critical to be reviewd later | 23-Sep-25: NON Critical to be reviewd later | L&T | Sivaprasad | Sivaprasad |  | Open | Open | [9 empty] | MOMNOC Operationalization | Network | OPEN | [6 empty] | 1
571 | M1088 | MOM | 2024-06-11 |  |  |  | Security & Regulatory Compliance | NOC Operationalization | Cisco firewall and ISE integration is still pending despite being from the same OEM. |  | Critical | Open |  |  |  |  | Firewall is being integrated with ISE. |  |  | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1
572 | M1089 | MOM | 2024-06-11 |  |  |  | NOC Operationalization |  | Address the absence of the central Security resource in future meetings. |  | Critical | Open |  |  |  | NON Critical to be reviewd later | 23-Sep-25: NON Critical to be reviewd later | L&T | Sivaprasad | Sivaprasad |  | Open | Open | [9 empty] | MOMNOC Operationalization | Network | OPEN | [6 empty] | 1
573 | M109 | MOM | 2023-08-01 |  |  |  | Helpdesk | Handbook & SOPs | Detailed documentation needed on critical, major, minor escalations, and their related thresholds. |  | NON-Critical | open |  |  |  | Closed | 24-Sep-25: Updated Document Shared 23-Aug-23 |  |  | Siva Kumar |  |  | COMPLETED & APPROVED | [9 empty] | MOMHelpdesk | Helpdesk (Contact Center) | CLOSED |  |  |  | 2025-09-24 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\M104,105,109,111,113,115,122,123,127,128,130,132,162 |  | 1
574 | M1090 | MOM | 2024-06-11 |  |  |  | NOC Operationalization |  | Provide closure status of all old action points in a single sheet before the next meeting. |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1
575 | M1091 | MOM | 2024-06-11 |  |  |  | Security & Regulatory Compliance | NOC Operationalization | Complete the scope for Vulnerability Assessment and Penetration Testing as defined and submit the results. |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1
576 | M1092 | MOM | 2024-06-11 |  |  |  | Security & Regulatory Compliance | NOC Operationalization | Address the issue of the Cisco firewall and ISE not being integrated. |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1
577 | M1093 | MOM | 2024-06-14 |  |  |  | OEM Related |  | All API Documents by HP to be submitted by L&T as soon as possible. |  | Critical | Open |  |  |  | Closed, Artefacts to be uploaded | 23-Sep-25: Approved Artefacts to be Submitted | L&T | Sivaprasad | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMOEM Related | OEM Related Issues | CLOSED |  |  |  |  | Artefacts Need to upload |  | 1
578 | M1094 | MOM | 2024-06-14 |  |  |  | OEM Related |  | BBNL integration solution to be provided by the end of June 2024, with testing beginning from 24th June 2024. |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMOEM Related | OEM Related Issues | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1
579 | M1095 | MOM | 2024-06-14 |  |  |  | OEM Related |  | Alarm enrichment with custom attributes and other new SOW items are in progress, with some attributes completed and others recently given. |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMOEM Related | OEM Related Issues | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1
580 | M1096 | MOM | 2024-06-14 |  |  |  | OEM Related |  | L&T to map documents as per RFP requirements and identify gaps for new SOW internally to their OEMs. |  | Critical | Open |  |  |  | Closed, Artefacts to be uploaded | 23-Sep-25: Approved Artefacts to be Submitted | L&T | Sivaprasad | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMOEM Related | OEM Related Issues | CLOSED |  |  |  |  | Artefacts Need to upload |  | 1
581 | M1097 | MOM | 2024-06-14 |  |  |  | OEM Related |  | HPE to provide Admin user privilege to L&T for filtering after a professional agreement is signed. |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMOEM Related | OEM Related Issues | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1
582 | M1098 | MOM | 2024-06-14 |  |  |  | OEM Related |  | OpenText to share all required documents by 24th June 2024. |  | Critical | Open |  |  |  | Closed, Artefacts to be uploaded | 23-Sep-25: Approved Artefacts to be Submitted | L&T | Sivaprasad | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMOEM Related | OEM Related Issues | CLOSED |  |  |  |  | Artefacts Need to upload |  | 1
583 | M1099 | MOM | 2024-06-14 |  |  |  | OEM Related |  | L&T to demonstrate the correlation engine and event alarm management for all domains. |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMOEM Related | OEM Related Issues | OPEN | [6 empty] | 1
584 | M11 | MOM | 2023-04-03 |  |  |  | NSO | Functional AT Plan | Use-Cases Testing under NSO |  | Critical | Open |  | OSS Dashboards | [5 empty] | Jayant Madavi |  | Open | Open | [9 empty] | MOMNSO | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
585 | M110 | MOM | 2023-08-01 |  |  |  | Helpdesk | Handbook & SOPs | Feedback Collection Review Mechanism |  | NON-Critical | Open |  |  |  | WIP |  |  |  | Siva Kumar |  | Open | WIP | [9 empty] | MOMHelpdesk | Helpdesk (Contact Center) | OPEN | [6 empty] | 1
586 | M1100 | MOM | 2024-06-14 |  |  |  | OEM Related |  | External API details provided by L&T are currently not functioning.(BBNL Integration) |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMOEM Related | OEM Related Issues | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1
587 | M1101 | MOM | 2024-06-14 |  |  |  | OEM Related |  | API extension for Alarm Enrichment is not functioning, and inventory API is operational. |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMOEM Related | OEM Related Issues | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1
588 | M1102 | MOM | 2024-06-14 |  |  |  | OEM Related |  | Service impact analysis is not available, and cross-domain RCA is not provided. |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMOEM Related | OEM Related Issues | OPEN | [6 empty] | 1
589 | M1103 | MOM | 2024-06-14 |  |  |  | OEM Related |  | Alarm forwarding API is not working, and there is a need for service impact and network impact information. |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMOEM Related | OEM Related Issues | OPEN | [6 empty] | 1
590 | M1104 | MOM | 2024-06-14 |  |  |  | OEM Related |  | There is no topology and zonal view of IPMPLS, and some performance management points are pending validation. |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMOEM Related | OEM Related Issues | OPEN | [6 empty] | 1
591 | M1105 | MOM | 2024-06-14 |  |  |  | OEM Related |  | L&T to submit all API documents, not just BBNL, and involve T-Fiber for review. |  | Critical | Open |  |  |  | Closed, Artefacts to be uploaded | 23-Sep-25: Approved Artefacts to be Submitted | L&T | Sivaprasad | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMOEM Related | OEM Related Issues | CLOSED |  |  |  |  | Artefacts Need to upload |  | 1
592 | M1106 | MOM | 2024-06-14 |  |  |  | OEM Related |  | L&T to demonstrate functionality and ensure alarm management is in place with the necessary enrichments. |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMOEM Related | OEM Related Issues | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1
593 | M1107 | MOM | 2024-06-14 |  |  |  | OEM Related |  | OpenText to demonstrate the NNMi KPI dashboard and complete the end-to-end demo for threshold values. |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMOEM Related | OEM Related Issues | OPEN | [6 empty] | 1
594 | M1108 | MOM | 2024-06-14 |  |  |  | OEM Related |  | L&T to define the scope with NSO for the Service Inventory module and ensure it is part of the deliverables. |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMOEM Related | OEM Related Issues | OPEN | [6 empty] | 1
595 | M1109 | MOM | 2024-06-14 |  |  |  | OEM Related |  | HPE to revisit all alarm scenarios, involve T-Fiber for review, and bring in industry best practices. |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMOEM Related | OEM Related Issues | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1
596 | M111 | MOM | 2023-08-01 |  |  |  | Helpdesk | Handbook & SOPs | Documentation required stating that L2 agents shall make outbound calls to customers. |  | NON-Critical | open |  |  |  | Closed | 24-Sep-25: Updated Document Shared 23-Aug-23 |  |  | Siva Kumar |  |  | COMPLETED & APPROVED | [9 empty] | MOMHelpdesk | Helpdesk (Contact Center) | CLOSED |  |  |  | 2025-09-24 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\M104,105,109,111,113,115,122,123,127,128,130,132,162 |  | 1
597 | M1110 | MOM | 2024-06-14 |  |  |  | OEM Related |  | HPE to review the RFP, compliance documents, solution documents, and HLD document, and offer the system for AT if everything is in compliance. |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMOEM Related | OEM Related Issues | OPEN | [6 empty] | 1
598 | M1111 | MOM | 2024-06-14 |  |  |  | OEM Related |  | L&T to provide API library access and complete API documents of OpenText to T-Fiber as soon as possible, with follow-up by Director-NOC, T-Fiber. |  | Critical | Open |  |  |  | Closed, Artefacts to be uploaded | 23-Sep-25: Approved Artefacts to be Submitted | L&T | Sivaprasad | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMOEM Related | OEM Related Issues | CLOSED |  |  |  |  | Artefacts Need to upload |  | 1
599 | M1112 | MOM | 2024-06-14 |  |  |  | OEM Related |  | BBNL integration task completion by 30th June 2024, with day-to-day progress monitoring by Director-NOC, T-Fiber. |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMOEM Related | OEM Related Issues | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1
600 | M1113 | MOM | 2024-06-14 |  |  |  | OEM Related |  | OpenText to provide a SMAX proposal with a detailed presentation for potential replacement analysis. |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMOEM Related | OEM Related Issues | OPEN | [6 empty] | 1
601 | M1114 | MOM | 2024-06-14 |  |  |  | OEM Related |  | L&T to arrange a demo for Server Performance Monitoring and submit all KPI details. |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMOEM Related | OEM Related Issues | OPEN | [6 empty] | 1
602 | M1115 | MOM | 2024-06-14 |  |  |  | OEM Related |  | OpenText to define custom reports for centralized and customizable service level reporting. |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMOEM Related | OEM Related Issues | OPEN | [6 empty] | 1
603 | M1116 | MOM | 2024-06-14 |  |  |  | OEM Related |  | OpenText to provide a 7-year direct support commitment and an approval system via email & mobile app. |  | Critical | Open |  |  |  | Closed, Artefacts to be uploaded | 23-Sep-25: Approved Artefacts to be Submitted | L&T | Sivaprasad | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMOEM Related | OEM Related Issues | CLOSED |  |  |  |  | Artefacts Need to upload |  | 1
604 | M1117 | MOM | 2024-06-14 |  |  |  | OEM Related |  | OpenText to provide a list of device models supported for SNMP polling. |  | Critical | Open |  |  |  | Closed, Artefacts to be uploaded | 23-Sep-25: Approved Artefacts to be Submitted | L&T | Sivaprasad | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMOEM Related | OEM Related Issues | CLOSED |  |  |  |  | Artefacts Need to upload |  | 1
605 | M1118 | MOM | 2024-06-14 |  |  |  | OEM Related |  | Full API library of vTemIP is unavailable, affecting self-testing of modules. |  | Critical | Open |  |  |  | Closed, Artefacts to be uploaded | 23-Sep-25: Approved Artefacts to be Submitted | L&T | Sivaprasad | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMOEM Related | OEM Related Issues | CLOSED |  |  |  |  | Artefacts Need to upload |  | 1
606 | M1119 | MOM | 2024-06-14 |  |  |  | OEM Related |  | Product support status from OpenText and incident management issues, including ticket grouping and content filtering. |  | Critical | Open |  |  |  | Closed, Artefacts to be uploaded | 23-Sep-25: Approved Artefacts to be Submitted | L&T | Sivaprasad | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMOEM Related | OEM Related Issues | CLOSED |  |  |  |  | Artefacts Need to upload |  | 1
607 | M112 | MOM | 2023-08-01 |  |  |  | Helpdesk | Handbook & SOPs | Inquiry about how the Helpdesk addresses cases where the number of the person calling differs from the number registered in the BSS database. |  | NON-Critical | open |  |  |  | WIP | 11-Sep-25: BSS Integration |  |  | Siva Kumar |  | Open | WIP | [9 empty] | MOMHelpdesk | Helpdesk (Contact Center) | OPEN | [6 empty] | 1
608 | M1120 | MOM | 2024-06-14 |  |  |  | OEM Related |  | Unavailability of a consolidated dashboard and cross-domain topology visibility. |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMOEM Related | OEM Related Issues | OPEN | [6 empty] | 1
609 | M1121 | MOM | 2024-06-14 |  |  |  | OEM Related |  | Instability of OBR and NNMi causing issues in IT event management. |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMOEM Related | OEM Related Issues | OPEN | [6 empty] | 1
610 | M1122 | MOM | 2024-06-14 |  |  |  | OEM Related |  | Concerns about the pending Network Automation and the process for implementing upgrades. |  | Critical | Open |  |  |  | WIP | DUPLICATE POINT (NOC624) | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMOEM Related | OEM Related Issues | OPEN | [6 empty] | 1
611 | M1123 | MOM | 2024-06-14 |  |  |  | OEM Related |  | OpenText to check and revert with timelines for API library access. |  | Critical | Open |  |  |  | Closed, Artefacts to be uploaded | 23-Sep-25: Approved Artefacts to be Submitted | L&T | Sivaprasad | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMOEM Related | OEM Related Issues | CLOSED |  |  |  |  | Artefacts Need to upload |  | 1
612 | M1124 | MOM | 2024-06-14 |  |  |  | OEM Related |  | OpenText to revisit the issue of limited ticket visibility in the UI and accommodate more data. |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMOEM Related | OEM Related Issues | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1
613 | M1125 | MOM | 2024-06-14 |  |  |  | OEM Related |  | L&T to establish a product service contract and ensure the operational team is fully engaged. |  | Critical | Open |  |  |  | Closed, Artefacts to be uploaded | 23-Sep-25: Approved Artefacts to be Submitted | L&T | Sivaprasad | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMOEM Related | OEM Related Issues | CLOSED |  |  |  |  | Artefacts Need to upload |  | 1
614 | M1126 | MOM | 2024-06-14 |  |  |  | OEM Related |  | OpenText to provide a solution for Service Level Reporting & availability and to demonstrate WAN-LAN connectivity mapping. |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMOEM Related | OEM Related Issues | OPEN | [6 empty] | 1
615 | M1127 | MOM | 2024-06-14 |  |  |  | OEM Related |  | L&T to discuss with OpenText about Network Automation for Deployment and configuration check module License. |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMOEM Related | OEM Related Issues | OPEN | [6 empty] | 1
616 | M1128 | MOM | 2024-06-14 |  |  |  | OEM Related |  | OpenText to deploy a dedicated resource in Hyderabad to close all open points and establish a standard test bed environment. |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMOEM Related | OEM Related Issues | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1
617 | M1129 | MOM | 2024-06-14 |  |  |  | OEM Related |  | All demonstrations should be conducted in the presence of T-Fiber representatives, and product compliance with ITIL Gold level certification needs to be rechecked. |  | Critical | Open |  |  |  | Closed, Artefacts to be uploaded | 23-Sep-25: Approved Artefacts to be Submitted | L&T | Sivaprasad | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMOEM Related | OEM Related Issues | CLOSED |  |  |  |  | Artefacts Need to upload |  | 1
618 | M113 | MOM | 2023-08-01 |  |  |  | Helpdesk | Handbook & SOPs | Clarification needed on the sphere of activity between NOC Technical administrators and Helpdesk agents. |  | NON-Critical | open |  |  |  | Artefacts to be submitted | 24-Sep-25: Updated Document Shared 23-Aug-23 |  |  | Siva Kumar |  |  | COMPLETED & APPROVED | [9 empty] | MOMHelpdesk | Helpdesk (Contact Center) | CLOSED |  |  |  | 2025-09-24 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\M104,105,109,111,113,115,122,123,127,128,130,132,162 |  | 1
619 | M1130 | MOM | 2024-06-28 |  |  |  | Security & Regulatory Compliance | Compliance | L&T Security Teams & Technical Head to resolve login issues for Pkg B & C teams by the end of the next week. |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1
620 | M1131 | MOM | 2024-06-28 |  |  |  | OSS | Product | L&T OSS SME to provide updates on the PMS issue with the secondary database after consultation with the OEM. |  | Critical | Open | [7 empty] | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMOSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  | #N/A |  | 1
621 | M1132 | MOM | 2024-06-28 |  |  |  | Security & Regulatory Compliance | Compliance | L&T to work with the vendor to define a solution for integrating AD with Alepo AAA. |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1
622 | M1133 | MOM | 2024-06-28 |  |  |  | Security & Regulatory Compliance | Compliance | GPON SME to discuss with OEM and understand the reporting for categorizing users in EMS & AMS systems. |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1
623 | M1134 | MOM | 2024-06-28 |  |  |  | Security & Regulatory Compliance | Compliance | L&T Security team & DC infra team to complete the RBAC list updates with domain-wise user information. |  | Critical | Closed | [7 empty] | Sarmendra |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | Artefacts to be Submitted |  | 1
624 | M1135 | MOM | 2024-06-28 |  |  |  | Security & Regulatory Compliance | Compliance | AD not integrating with Alepo AAA. |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1
625 | M1136 | MOM | 2024-06-28 |  |  |  | Security & Regulatory Compliance | Compliance | Local users not removed in EMS, AMS, etc., and not verified through AD/Alepo AAA. |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1
626 | M1137 | MOM | 2024-06-28 |  |  |  | Security & Regulatory Compliance | Compliance | Cisco EPNM has two separate profiles for a single user after login through TACACS, which needs resolution. |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1
627 | M1138 | MOM | 2024-06-28 |  |  |  | Security & Regulatory Compliance | Compliance | L&T does not have HPE Admin access and is missing some OT systems in OSS. |  | Critical | Open | [7 empty] | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN | COMPLETED | 0 |  |  | #N/A |  | 1
628 | M1139 | MOM | 2024-06-28 |  |  |  | Security & Regulatory Compliance | Compliance | ISE HA DC to DR not working due to pending ISE software upgrade. |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1
629 | M114 | MOM | 2023-08-01 |  |  |  | Helpdesk | Training | Training for Helpdesk Users and Managers |  | Critical | open |  |  |  | Closed | 24-Sep-25: Artefacts to be uploaded |  |  | Siva Kumar |  |  | COMPLETED & APPROVED | [9 empty] | MOMHelpdesk | Helpdesk (Contact Center) | CLOSED |  |  |  | 2025-09-24 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\M114,722,134 |  | 1
630 | M1140 | MOM | 2024-06-28 |  |  |  | Security & Regulatory Compliance | Compliance | L&T to share user details with Ravi for reconciliation in RBAC worksheets. |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1
631 | M1141 | MOM | 2024-06-28 |  |  |  | Security & Regulatory Compliance | Compliance | L&T to ensure all users are domain verified through AD/Alepo AAA and remove local users. |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1
632 | M1142 | MOM | 2024-06-28 |  |  |  | Security & Regulatory Compliance | Compliance | L&T to follow a consistent format for user IDs across all domains. |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1
633 | M1143 | MOM | 2024-06-28 |  |  |  | Security & Regulatory Compliance | Compliance | L&T OSS SME to initiate communication with OEMs for admin user control access. |  | Critical | Open | [7 empty] | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN | COMPLETED | 0 |  |  | #N/A |  | 1
634 | M1144 | MOM | 2024-06-28 |  |  |  | Security & Regulatory Compliance | Compliance | L&T to prepare a checklist, test user access domain-wise, and create users based on necessary approvals. |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1
635 | M1145 | MOM | 2024-06-28 |  |  |  | Security & Regulatory Compliance | Compliance | L&T to rebuild CSM with necessary resources (storage) as a long-term solution. |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1
636 | M1146 | MOM | 2024-06-28 |  |  |  | Security & Regulatory Compliance | Compliance | Mark Mr. Sandeep in any escalation emails for pending issues with L&T. |  | Critical | Open |  |  |  |  | Sandeep is marked in mails |  |  | Sarmendra |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | Artefacts to be Submitted |  | 1
637 | M1147 | MOM | 2024-07-12 |  |  |  | OEM Related |  | Cisco confirmed that Airtel uses NSO for IP/MPLS with around 70,000 devices, and Jio uses it for transport management and service provisioning. |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMOEM Related | OEM Related Issues | OPEN | [6 empty] | 1
638 | M1148 | MOM | 2024-07-12 |  |  |  | OEM Related |  | In T-Fiber, NSO interfaces with EMS for GPON (Nokia & Tejas) and directly with network elements for Cisco IP/MPLS. |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMOEM Related | OEM Related Issues | OPEN | [6 empty] | 1
639 | M1149 | MOM | 2024-07-12 |  |  |  | OEM Related |  | SVP, T-Fiber requested a comprehensive update on the project's progress, including accomplishments, pending tasks, and future plans. |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMOEM Related | OEM Related Issues | OPEN | [6 empty] | 1
640 | M115 | MOM | 2023-08-01 |  |  |  | Helpdesk | Handbook & SOPs | Detailed Helpdesk Process Steps |  | Critical | open |  |  |  | Closed | 24-Sep-25: Updated Document Shared 23-Aug-23 |  |  | Siva Kumar |  |  | COMPLETED & APPROVED | [9 empty] | MOMHelpdesk | Helpdesk (Contact Center) | CLOSED |  |  |  | 2025-09-24 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\M104,105,109,111,113,115,122,123,127,128,130,132,162 |  | 1
641 | M1150 | MOM | 2024-07-12 |  |  |  | OEM Related | Cisco | Cisco confirmed that lab licenses are provided free with production licenses and that it is standard practice to set up a pre-production environment. |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMOEM Related | OEM Related Issues | OPEN | [6 empty] | 1
642 | M1151 | MOM | 2024-07-12 |  |  |  | OEM Related | Cisco | Cisco assured to provide access to the Smartlicenses portal for T-Fiber and to share the full library of APIs for all A&O modules. |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMOEM Related | OEM Related Issues | OPEN | [6 empty] | 1
643 | M1152 | MOM | 2024-07-12 |  |  |  | OEM Related |  | Technical Support and Operations: |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMOEM Related | OEM Related Issues | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1
644 | M1153 | MOM | 2024-07-12 |  |  |  | OEM Related |  | Discussions were held about the method of operation for NED and product lifecycle management. |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMOEM Related | OEM Related Issues | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1
645 | M1154 | MOM | 2024-07-12 |  |  |  | OEM Related | Cisco | Cisco suggested a gradual handover process with a joint account of L&T and Cisco for a smooth transition. |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMOEM Related | OEM Related Issues | OPEN | [6 empty] | 1
646 | M1155 | MOM | 2024-07-12 |  |  |  | OEM Related | NSO | Director-P&E, T-Fiber inquired about the system responsible for maintaining the complete inventory within NSO. |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMOEM Related | OEM Related Issues | OPEN | [6 empty] | 1
647 | M1156 | MOM | 2024-07-12 |  |  |  | OEM Related | Cisco | Cisco mentioned that full orchestration currently requires human intervention, and a service discovery and reconciliation module is needed for full automation. |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMOEM Related | OEM Related Issues | OPEN | [6 empty] | 1
648 | M1157 | MOM | 2024-07-12 |  |  |  | OEM Related |  | Concerns were raised about customization in the pre-production phase and the need to complete customizations before going live. |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMOEM Related | OEM Related Issues | OPEN | [6 empty] | 1
649 | M1158 | MOM | 2024-07-12 |  |  |  | OEM Related | Cisco | Cisco emphasized the importance of a change management system for configuration changes and the need for a service audit feature. |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMOEM Related | OEM Related Issues | OPEN | [6 empty] | 1
650 | M1159 | MOM | 2024-07-12 |  |  |  | OEM Related | Cisco | Cisco to provide all API libraries and hand over NED with knowledge transfers. |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMOEM Related | OEM Related Issues | OPEN | [6 empty] | 1
651 | M116 | MOM | 2023-08-01 |  |  |  | Helpdesk | Handbook & SOPs | Clarification needed on addressing the subjective nature of "Non-Technical" calls. |  | Critical | open |  |  |  | Closed | 24-Sep-25: It will be Handled by Proposed T fiber Business Helpdesk |  |  | Siva Kumar |  |  | COMPLETED & APPROVED | [9 empty] | MOMHelpdesk | Helpdesk (Contact Center) | CLOSED |  |  |  | 2025-09-24 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\M116,723,1026 |  | 1
652 | M1160 | MOM | 2024-07-12 |  |  |  | OEM Related | OSS | Inventory module and bandwidth manager are still open issues. |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMOEM Related | OEM Related Issues | OPEN | [6 empty] | 1
653 | M1161 | MOM | 2024-07-12 |  |  |  | OEM Related | OSS | L&T to provide lifecycle processes and how change management and customization are done post-production. |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMOEM Related | OEM Related Issues | OPEN | [6 empty] | 1
654 | M1162 | MOM | 2024-07-12 |  |  |  | OEM Related | NSO | Cisco to provide E2E topology feasibility, including bandwidth management using NSO. |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMOEM Related | OEM Related Issues | OPEN | [6 empty] | 1
655 | M1163 | MOM | 2024-07-12 |  |  |  | OEM Related |  | Director-P&E, T-Fiber asked for the deployment of the system in a pre-production environment for thorough testing. |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMOEM Related | OEM Related Issues | OPEN | [6 empty] | 1
656 | M1164 | MOM | 2024-07-12 |  |  |  | OEM Related |  | SVP, T-Fiber requested access to all modules within the pre-production environment, along with necessary licenses. |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMOEM Related | OEM Related Issues | OPEN | [6 empty] | 1
657 | M1165 | MOM | 2024-07-12 |  |  |  | OEM Related |  | Director-P&E, T-Fiber emphasized the importance of the system being modular and raised concerns about functionality without BSS. |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMOEM Related | OEM Related Issues | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1
658 | M1166 | MOM | 2024-07-15 |  |  |  | OEM Related |  | L&T to inform T-Fiber and provide details once solution support is fully deployed. |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMOEM Related | OEM Related Issues | OPEN | [6 empty] | 1
659 | M1167 | MOM | 2024-07-15 |  |  |  | OEM Related |  | L&T to focus on solution reports and resolve operational issues related to UTM. |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMOEM Related | OEM Related Issues | OPEN | [6 empty] | 1
660 | M1168 | MOM | 2024-07-15 |  |  |  | OEM Related |  | HPE to consider features not possible for alternative solutions. |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMOEM Related | OEM Related Issues | OPEN | [6 empty] | 1
661 | M1169 | MOM | 2024-07-15 |  |  |  | OEM Related |  | L&T to provide automation in the purge-auto termination process without manual intervention. |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMOEM Related | OEM Related Issues | OPEN | [6 empty] | 1
662 | M117 | MOM | 2023-08-01 |  |  |  | Helpdesk | Handbook & SOPs | Assumptions for Estimated Calls per Day |  | Critical | open |  |  |  | Closed | 24-Sep-25: Artefacts to be uploaded |  |  | Siva Kumar |  |  | COMPLETED & APPROVED | [9 empty] | MOMHelpdesk | Helpdesk (Contact Center) | CLOSED |  |  |  | 2025-09-24 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\M117,126,728 |  | 1
663 | M1170 | MOM | 2024-07-15 |  |  |  | OEM Related |  | L&T to ensure GIS is the master source for passive infra and it should be a permanent solution. |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMOEM Related | OEM Related Issues | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1
664 | M1171 | MOM | 2024-07-15 |  |  |  | OEM Related |  | L&T to provide all relevant data to facilitate customization requirements for business. |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMOEM Related | OEM Related Issues | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1
665 | M1172 | MOM | 2024-07-15 |  |  |  | OEM Related |  | L&T assured that technical support would be available for the long term and operational training would continue until the complete delivery of the contract. |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMOEM Related | OEM Related Issues | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1
666 | M1173 | MOM | 2024-07-15 |  |  |  | OEM Related |  | L&T to demonstrate all points, including completed points, to ensure transparency on solutions implemented. |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMOEM Related | OEM Related Issues | OPEN | [6 empty] | 1
667 | M1174 | MOM | 2024-07-15 |  |  |  | OEM Related |  | L&T to prioritize tasks to support business along with T-Fiber to maintain efficient and effective operational workflows. |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMOEM Related | OEM Related Issues | OPEN | [6 empty] | 1
668 | M1175 | MOM | 2024-07-15 |  |  |  | OEM Related |  | L&T and HPE to provide timelines for operational, delivery, and technical support, as well as a plan for out-of-the-box features. |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMOEM Related | OEM Related Issues | OPEN | [6 empty] | 1
669 | M1176 | MOM | 2024-07-15 |  |  |  | OEM Related |  | L&T to provide updated LLD document and ensure that all Licenses are provided to T-Fiber as they are an asset of T-Fiber. |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMOEM Related | OEM Related Issues | OPEN | [6 empty] | 1
670 | M1177 | MOM | 2024-07-15 |  |  |  | OEM Related |  | L&T to submit customize reports and ensure that all open HP APIs should be made available to L&T and T-Fiber. |  | Critical | Open |  |  |  | Closed, Artefacts to be uploaded | 23-Sep-25: Approved Artefacts to be Submitted | L&T | Sivaprasad | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMOEM Related | OEM Related Issues | CLOSED |  |  |  |  | Artefacts Need to upload |  | 1
671 | M1178 | MOM | 2024-07-15 |  |  |  | OEM Related |  | L&T to ensure that the pre-production environment is set up and additional infrastructure needs are met. |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMOEM Related | OEM Related Issues | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1
672 | M1179 | MOM | 2024-07-15 |  |  |  | OEM Related |  | Director-P&E, T-Fiber emphasized the importance of delivering services and suggested scheduling calls to ensure delivery is on track. |  | Critical | Open |  |  |  | Closed, Artefacts to be uploaded | 23-Sep-25: Approved Artefacts to be Submitted | L&T | Sivaprasad | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMOEM Related | OEM Related Issues | CLOSED |  |  |  |  | Artefacts Need to upload |  | 1
673 | M118 | MOM | 2023-08-01 |  |  |  | Helpdesk | Handbook & SOPs | Readiness of Helpdesk to report on compliances and responsiveness and calculate penalties. |  | Critical | open |  |  |  | Artefacts to be submitted | 24-Sep-25:Artefacts to be submitted |  |  | Siva Kumar |  | Open | Open | [9 empty] | MOMHelpdesk | Helpdesk (Contact Center) | OPEN |  |  |  | 2025-09-24 |  |  | 1
674 | M1180 | MOM | 2024-07-15 |  |  |  | OEM Related |  | Director-P&E, T-Fiber requested an out-of-box demo as per the pre-bid agreement. |  | Critical | Open |  |  |  | Closed, Artefacts to be uploaded | 23-Sep-25: Approved Artefacts to be Submitted | L&T | Sivaprasad | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMOEM Related | OEM Related Issues | CLOSED |  |  |  |  | Artefacts Need to upload |  | 1
675 | M1181 | MOM | 2024-07-15 |  |  |  | OEM Related |  | A detailed discussion is required for DR with all stakeholders, including HPE, OT, and CTRL S, for a comprehensive approach. |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMOEM Related | OEM Related Issues | OPEN | [6 empty] | 1
676 | M1182 | MOM | 2024-07-22 |  |  |  | T&D Environment |  | MD, T-Fiber emphasized the necessity of a pre-production setup and directed L&T to submit an infrastructure proposal. |  | NON-Critical | Open |  |  |  |  | 11-Oct-25: T Fiber requested to submit reference document Historically the L&T submitted proposal was not approved. Need to work for the final setup |  |  | Ravi Kishore |  | Open | Open | [9 empty] | MOMT&D Environment | Applications | OPEN | [6 empty] | 1
677 | M1183 | MOM | 2024-07-22 |  |  |  | OEM Related |  | MD, T-Fiber asked L&T to work with the OEM for a higher license count for the Work Force Management Tool (WFM) and to explore features of government tools for comparison. |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMOEM Related | OEM Related Issues | OPEN | [6 empty] | 1
678 | M1184 | MOM | 2024-07-22 |  |  |  | OEM Related | All OEM's | Concerns were raised about the delay in onboarding OEMs like OpenText, HP, and Cisco. |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMOEM Related | OEM Related Issues | OPEN | [6 empty] | 1
679 | M1185 | MOM | 2024-07-22 |  |  |  | OEM Related |  | Concerns were raised about the lack of response from Nokia on Hybrid mode solutioning. |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMOEM Related | OEM Related Issues | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1
680 | M1186 | MOM | 2024-12-09 |  |  |  | NOC Operationalization |  | Principal Consultant to be added in WA groups (only NOC , Service Delivery, Project Delivery , and Technology wise group along with OEMs) |  | Critical | Closed |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1
681 | M1187 | MOM | 2024-12-09 |  |  |  | OEM Related |  | OEM wise physical meeting to be called |  | Critical | Closed |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMOEM Related | OEM Related Issues | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1
682 | M1188 | MOM | 2024-12-09 |  |  |  | Helpdesk |  | Helpdesk LLD/HLD to be discussed in detailed |  | Critical | Open |  |  |  | WIP |  |  |  | Siva Kumar |  | Open | WIP | [9 empty] | MOMHelpdesk | Helpdesk (Contact Center) | OPEN | [6 empty] | 1
683 | M1189 | MOM | 2024-12-09 |  |  |  | NOC Operationalization |  | Only one Issue Tracker to be maintained to track whatever is discussed during current week review |  | Critical | Closed |  |  |  | NON Critical to be reviewd later | 23-Sep-25: NON Critical to be reviewd later | L&T | Sivaprasad | Sivaprasad |  | Open | Open | [9 empty] | MOMNOC Operationalization | Network | OPEN | [6 empty] | 1
684 | M119 | MOM | 2023-08-01 |  |  |  | Helpdesk | Handbook & SOPs | Live Intrusion of Calls |  | Critical | open |  |  |  | Closed | 24-Sep-25: Artfcats to be uploaded 11-Sep-25: Feature Available, Shall be demonstrated |  |  | Siva Kumar |  |  | COMPLETED & APPROVED | [9 empty] | MOMHelpdesk | Helpdesk (Contact Center) | CLOSED |  |  |  | 2025-09-24 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\M119,733 |  | 1
685 | M1190 | MOM | 2024-12-09 | P3 |  |  | NOC Operationalization |  | Share NOC Dec24 roaster |  | Critical | Closed |  |  |  |  | Roaster shared |  |  | Ahmad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  | Daily oprational task | 2025-09-24 | "\\172.28.9.23\TNOC_Roaster Plan |  | 1
686 | M1191 | MOM | 2024-12-09 |  |  |  | NOC Operationalization |  | OSS to be discussed on 10Dec24 or today |  | Critical | Closed |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1
687 | M1192 | MOM | 2024-12-09 |  |  |  | NOC Operationalization |  | Send all presentations to Principal Consultant |  | Critical | Closed |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1
688 | M1193 | MOM | 2024-12-09 |  | OSS | OSS | OSS | NOC Operationalization | Change Mgmt. system to be made up, currently its manual on mails/excel |  | Critical | Open | [7 empty] | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMOSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  | #N/A |  | 1
689 | M1194 | MOM | 2024-12-09 |  |  |  | BSS |  | Aravindham have personal challenges, can come on MS Team. Request him to come for 2 day for physical meeting |  | Critical | Closed | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN | [6 empty] | 1
690 | M1195 | MOM | 2024-12-09 |  |  |  | NSO | Service provisioning | IP Schema to discussed |  | Critical | Closed | [7 empty] | Jayant Madavi |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMNSO | Applications/Tools | OPEN |  |  |  |  | Artefacts to be uploaded |  | 1
691 | M1196 | MOM | 2024-12-09 |  |  |  | NOC Operationalization |  | Current PRIORITY discussion to be done for : NOC Review, OSS, DC-Infra, Call Centre HLD/LLD, IP MPLS. Balance to be communicated during the sessions |  | NON-Critical | Closed |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1
692 | M1197 | MOM | 2024-12-09 | P3 |  |  | NOC Operationalization |  | Different kinds of reports to be discussed : Daily reports/dashboards, Capacity reports for all nodes/links (like ISP Util, Capacities utilization, licenses , availability reports for PCK-A/B/C technology wise, etc.) |  | Critical | Closed |  |  |  |  | Discussed and reports sent to Principal COnsultant |  |  | Ahmad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  | Covered in OSS | 2025-09-19 | Artefacts not Required |  | 1
693 | M1198 | MOM | 2024-12-09 |  | OSS | OSS | OSS | BBNL | CDOT integration with NMS is highest priority. The team should be actively engaged with teams and visit sites. |  | Critical | Closed | [7 empty] | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMOSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1
694 | M1199 | MOM | 2024-12-09 | P3 |  |  | NOC Operationalization |  | Principal Consultant meeting with NOC L3s |  | Critical | Closed |  |  |  |  | Meeting was done |  |  | Ahmad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  | Not related to delivery | 2025-09-19 | Artefacts not Required |  | 1
695 | M12 | MOM | 2023-04-03 |  |  |  | T&D Environment | T&D Environment | Test Lab Setup Equipments and Plan |  | NON-Critical | Open |  |  |  |  | 11-Oct-25: T Fiber requested to submit reference document Historically the L&T submitted proposal was not approved. Need to work for the final setup |  |  | Ravi Kishore |  | Open | Open | [9 empty] | MOMT&D Environment | Applications | OPEN | [6 empty] | 1
696 | M120 | MOM | 2023-08-01 |  |  |  | Helpdesk | Handbook & SOPs | Duration of Call Measurement |  | Critical | open |  |  |  | Closed | 24-Sep-25: Artfcats to be uploaded 11-Sep-25: Feature Available, Shall be demonstrated |  |  | Siva Kumar |  |  | COMPLETED & APPROVED | [9 empty] | MOMHelpdesk | Helpdesk (Contact Center) | CLOSED |  |  |  | 2025-09-24 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\M120,129 |  | 1
697 | M1200 | MOM | 2024-12-09 |  |  |  | NOC Operationalization |  | NOC 2.0 Mission : 30th April - All systems should be live. BSS KNOT(phase1) should be ready by 15th March OSS should be ready by Jan end NSO should be ready by mid-March |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMNOC Operationalization | Network | OPEN | [6 empty] | 1
698 | M1201 | MOM | 2024-12-09 |  |  |  | NOC Operationalization |  | L&T should recommend systems that should be procured for better efficiencies. A tendering process may be taken up as suitable by TFIBER. |  | Critical | Closed |  |  |  | Siva prasad to getback on same | 23-Sep-25: NON Critical to be reviewd later | L&T | Sivaprasad | Sivaprasad |  | Open | Open | [9 empty] | MOMNOC Operationalization | Network | OPEN | [6 empty] | 1
699 | M1202 | MOM | 2024-12-09 |  |  |  | NOC Operationalization |  | Map of technology vis-à-vis OEM vis-à-vis issues |  | Critical | Closed |  |  |  | Closed, Artefacts to be uploaded | 23-Sep-25: Approved Artefacts to be Submitted | L&T | Sivaprasad | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  |  | Artefacts Need to upload |  | 1
700 | M1203 | MOM | 2024-12-09 | P3 |  |  | NOC Operationalization |  | Passive Infra-Additional capacity needed in the NOC |  | Critical | Closed |  |  |  |  | TFiber team had to share this as per future plan. DC Passive deployed capacity is already as per RFP and AT completed |  |  | Ahmad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  | No clarity on requirment | 2025-09-19 | Artefacts not Required |  | 1
701 | M1204 | MOM | 2024-12-09 | P3 |  |  | NOC Operationalization |  | CCTV to be configured on Principal Consultant office and laptop. L&T to come up with solution |  | Critical | Closed |  |  |  |  | Discussed with TFiber later on, not needed |  |  | Ahmad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  | Not related to delivery | 2025-09-19 | Artefacts not Required |  | 1
702 | M1205 | MOM | 2024-12-09 |  |  |  | NOC Operationalization |  | Test labs and staging environment, currently project equipment's (routers, GPON, etc.) are being used |  | Critical | Closed |  |  |  | TO be reviewed | 23-Sep-25: NON Critical to be reviewd later | L&T | Sivaprasad | Sivaprasad |  | Open | Open | [9 empty] | MOMNOC Operationalization | Network | OPEN | [6 empty] | 1
703 | M1206 | MOM | 2024-12-09 |  |  |  | DC-IT | NOC Operationalization | HLD and LLD documents to be revised for DC Infra |  | NON-Critical | Open |  |  |  |  | Work in progress |  |  | Ravi Kishore |  | Open | Open | [9 empty] | MOMDC-IT | Network | OPEN | [6 empty] | 1
704 | M1207 | MOM | 2024-12-10 |  |  |  | BSS |  | One call with BSS and NSO SME to be done tomorrow morning |  | Critical | Closed | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN | [6 empty] | 1
705 | M1208 | MOM | 2024-12-10 |  |  |  | OEM Related |  | Tejas : TR069 feature to be enabled for TFIBER network |  | NON-Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMOEM Related | OEM Related Issues | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1
706 | M1209 | MOM | 2024-12-10 |  |  |  | OEM Related |  | One resource from Tejas to be placed at TNOC for sorting out Tejas related issues |  | Critical | Closed |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMOEM Related | OEM Related Issues | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1
707 | M121 | MOM | 2023-08-01 |  |  |  | Helpdesk | Handbook & SOPs | Exceptions in IVR User Response |  | Critical | open |  |  |  | Closed | 24-Sep-25: Approved and shall be closed |  |  | Siva Kumar |  |  | COMPLETED & APPROVED | [9 empty] | MOMHelpdesk | Helpdesk (Contact Center) | CLOSED |  |  |  | 2025-09-24 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\M121,170,99,726 |  | 1
708 | M1210 | MOM | 2024-12-10 |  |  |  | NOC Operationalization |  | Tejas: Pending API to be given on priority |  | Critical | Closed | [7 empty] | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API | [6 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API |  | 1
709 | M1211 | MOM | 2024-12-10 |  |  |  | NOC Operationalization |  | Make one WhatsApp group for Tejas only (LTTS, TFIBER, Tejas) |  | Critical | Closed |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1
710 | M1212 | MOM | 2024-12-10 |  |  |  | NOC Operationalization |  | Suggested one format for SME tasks tracking Each SME to update that tracker putting all critical/major/minor tasks/issues listed in this. To be updated on daily basis with dates |  | Critical | Closed |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1
711 | M1213 | MOM | 2024-12-10 |  |  |  | NSO | Service provisioning | 27 services NSO licenses details to be shared with Principal Consultant |  | Critical | Closed | [7 empty] | Jayant Madavi |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMNSO | Applications/Tools | OPEN |  |  |  |  | Artefacts to be uploaded |  | 1
712 | M1214 | MOM | 2024-12-10 |  |  |  | NSO | Service provisioning | NSO VMs details for T&D to be shared with Principal Consultant along with issue details (what support needed from Cisco) |  | Critical | Closed | [7 empty] | Jayant Madavi |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMNSO | Applications/Tools | OPEN |  |  |  |  | Artefacts to be uploaded |  | 1
713 | M1215 | MOM | 2024-12-10 |  |  |  | NSO | Service provisioning | Trial licenses will be given as stop gap arrangement for NSO T&D setup. VM details to be shared with Ravindra (MAC id , etc.) by LTTS |  | Critical | Closed | [7 empty] | Jayant Madavi |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMNSO | Applications/Tools | OPEN |  |  |  |  | Artefacts to be uploaded |  | 1
714 | M1216 | MOM | 2024-12-10 |  |  |  | OEM Related | Cisco EPNM | License issue for EPNM and ISE to be resolved |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMOEM Related | OEM Related Issues | OPEN | [6 empty] | 1
715 | M1217 | MOM | 2024-12-10 |  |  |  | NOC Operationalization |  | One resource from Tejas to be placed at TNOC for sorting out Tejas related issues |  | Critical | Closed |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1
716 | M1218 | MOM | 2024-12-10 |  |  |  | NSO | Service provisioning | Agreed SOW for NSO to be shared |  | Critical | Closed | [7 empty] | Jayant Madavi |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMNSO | Applications/Tools | OPEN |  |  |  |  | Artefacts to be uploaded |  | 1
717 | M1219 | MOM | 2024-12-10 |  |  |  | NSO | Service provisioning | SOW for Cisco NSO - by when quotation will be closed by Cisco? Cisco to revert back with quotation timelines, probably tomorrow, also with TAT for implementation |  | Critical | Open | [7 empty] | Jayant Madavi |  | Open | Open | [9 empty] | MOMNSO | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
718 | M122 | MOM | 2023-08-01 |  |  |  | Helpdesk | Handbook & SOPs | The unit of measurement is required for all Key Performance Indicator (KPI) parameters. |  | Critical | open |  |  |  | Closed | 24-Sep-25: Updated Document Shared 23-Aug-23 |  |  | Siva Kumar |  |  | COMPLETED & APPROVED | [9 empty] | MOMHelpdesk | Helpdesk (Contact Center) | CLOSED |  |  |  | 2025-09-24 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\M104,105,109,111,113,115,122,123,127,128,130,132,162 |  | 1
719 | M1220 | MOM | 2024-12-10 |  |  |  | NOC Operationalization |  | Make one WhatsApp group for NSO only (LTTS, TFIBER, OEM) |  | Critical | Closed |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1
720 | M1221 | MOM | 2024-12-10 |  |  |  | NSO | Service provisioning | Dark Fiber as a service |  | Critical | Closed | [7 empty] | Jayant Madavi |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMNSO | Applications/Tools | OPEN |  |  |  |  | Artefacts to be uploaded |  | 1
721 | M1222 | MOM | 2024-12-10 |  |  |  | NSO | Service provisioning | List down all services which are needed for launch (As per LTTS understanding). During 2PM workshop tomorrow KNOT, Aravindham, Ashish, Ravindra Cisco, TFIBER will be there on call |  | Critical | Closed | [7 empty] | Jayant Madavi |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMNSO | Applications/Tools | OPEN |  |  |  |  | Artefacts to be uploaded |  | 1
722 | M1223 | MOM | 2024-12-10 |  |  |  | OEM Related |  | SG350 switch EOS/EOL: GP all OK. Mandal/Zonal level have some discrepancy like less ports compared to current version or at least match to RFP |  | NON-Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMOEM Related | OEM Related Issues | OPEN | [6 empty] | 1
723 | M1224 | MOM | 2024-12-10 |  |  |  | NOC Operationalization |  | Make other WhatsApp group for Cisco other domains (apart from NSO). Make Ravindar Admin to add other Cisco team members. (LTTS except NSO, TF, Cisco) |  | Critical | Closed |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1
724 | M1225 | MOM | 2024-12-10 |  |  |  | OEM Related | Cisco | SG350 switch: EOSale/EOL/LDOHWS (Last date of HW support which is Oct2026. Till LDOHWS that RMA will be given with new CBS model. Post that support will stop. Mail request to be send to Cisco to extend support. |  | NON-Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMOEM Related | OEM Related Issues | OPEN | [6 empty] | 1
725 | M1226 | MOM | 2024-12-10 |  |  |  | OEM Related |  | EPNM license upgraded, in smart account licenses are not working. Its issue with PKG-A only (PKG-B/C had procured separately 5.x so they don’t have this issue, while LTTS procured 2.x as per Ravindra) |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMOEM Related | OEM Related Issues | OPEN | [6 empty] | 1
726 | M1227 | MOM | 2024-12-10 |  |  |  | BSS |  | Is our network integrated with Aadhar servers, GST? LTTS confirmed it is not integrated |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
727 | M1228 | MOM | 2024-12-10 |  |  |  | NOC Operationalization |  | Agreement status for all OEM to be shared |  | Critical | Closed |  |  |  | Closed, Artefacts to be uploaded | 23-Sep-25: Approved Artefacts to be Submitted | L&T | Sivaprasad | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  |  | Artefacts Need to upload |  | 1
728 | M1229 | MOM | 2024-12-10 |  | OSS | OSS | OSS | BBNL | BBNL - API : is top priority. Each day update to be sent to Principal Consultant |  | Critical | Closed | [7 empty] | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMOSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1
729 | M123 | MOM | 2023-08-01 |  |  |  | Helpdesk | Handbook & SOPs | Sample Methods for KPI Calculations |  | Critical | open |  |  |  | Closed | 24-Sep-25: Updated Document Shared 23-Aug-23 |  |  | Siva Kumar |  |  | COMPLETED & APPROVED | [9 empty] | MOMHelpdesk | Helpdesk (Contact Center) | CLOSED |  |  |  | 2025-09-24 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\M104,105,109,111,113,115,122,123,127,128,130,132,162 |  | 1
730 | M1230 | MOM | 2024-12-10 |  | OSS | OSS | OSS | BBNL | Tomorrow 3 PM. will call Rupa Maan and Akhilesh Gupta Sir for BBNL API |  | Critical | Closed | [7 empty] | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMOSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1
731 | M1231 | MOM | 2024-12-10 |  |  |  | OEM Related |  | Principal Consultant Room Dashboard - Excel sheet sent, to discuss and finetune. Discussed. Need this report through OSS, to be added in HPE/OT scope once they are onboarded - discuss jointly with TFIBER along with OEM |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMOEM Related | OEM Related Issues | OPEN | [6 empty] | 1
732 | M1232 | MOM | 2024-12-10 |  |  |  | NOC Operationalization |  | All inhouse automation : LLD to be made by SME and handover to Ops & TFIBER team |  | NON-Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMNOC Operationalization | Network | OPEN | [6 empty] | 1
733 | M1233 | MOM | 2024-12-10 |  |  |  | OEM Related |  | OSS out of Scope: 1. Service Topology 2. Retail Services (5Mn), 3. Services & Service KPI Monitoring. As per SOR this is not there. This is for Principal Consultant information |  | Critical | Closed |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMOEM Related | OEM Related Issues | OPEN | [6 empty] | 1
734 | M1234 | MOM | 2024-12-10 |  |  |  | OEM Related |  | Share all OSS documents (RFP points, LLD, FRS, etc.) |  | Critical | Closed |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMOEM Related | OEM Related Issues | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1
735 | M1235 | MOM | 2024-12-10 |  |  |  | NOC Operationalization |  | Make P1/P2/P3 list for all pending tasks for all domain P1: 25% P2 : 30% P3 : 45% And then list of some additional ask if needed like new HW or software required. |  | Critical | Closed |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1
736 | M1236 | MOM | 2024-12-10 |  | OSS | OSS | OSS | BBNL | Manoj: Complete BBNL ask tasks will be completed by 12 Dec24 (only GP and Block Node status API pending). Sanjay: Uptime gap ~7% to be addressed. For this, HPE support needed. Then only we can go to BBNL for closure. Alarm re-synchronization issue - need HPE support. Interim solution implemented (1 Hr). Same for Inventory. |  | Critical | Open | [7 empty] | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMOSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1
737 | M1237 | MOM | 2024-12-10 |  |  |  | OEM Related |  | Bottomline for OSS: Engagement with HPE and OT to start to get all OSS open/pending tasks done |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMOEM Related | OEM Related Issues | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1
738 | M1238 | MOM | 2024-12-10 |  |  |  | OEM Related | All OEM's | Priority engagement with HPE/OT/Cisco/Aleppo needed to meet Apr25 target. Current payment/cash flow issues hindering this right now |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMOEM Related | OEM Related Issues | OPEN | [6 empty] | 1
739 | M1239 | MOM | 2024-12-10 |  |  |  | NOC Operationalization |  | Pending AT for all Application and DC systems to be shared by tomorrow |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMNOC Operationalization | Network | OPEN | [6 empty] | 1
740 | M124 | MOM | 2023-08-01 |  |  |  | Helpdesk | Handbook & SOPs | Inquiry into how Customer Satisfaction (CSAT) is measured and whether there is a mechanism for transactional feedback. |  | Critical | Open |  |  |  | WIP |  |  |  | Siva Kumar |  | Open | WIP | [9 empty] | MOMHelpdesk | Helpdesk (Contact Center) | OPEN | [6 empty] | 1
741 | M1240 | MOM | 2024-12-10 | P3 |  |  | NOC Operationalization |  | Major nodes/links utilization report to be shared (Deployed V/s Utilized) by tomorrow |  | Critical | Closed |  |  |  |  | Report shared |  |  | Ahmad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  | Covered in OSS | 2025-09-19 | Artefacts not Required |  | 1
742 | M1241 | MOM | 2024-12-10 |  |  |  | NOC Operationalization |  | Did anyone visited DR Ctrl-S location at Mumbai? No, except of earlier L&T Delivery Head Principal Consultant: Will plan visit to this location in future |  | Critical | Open |  |  |  | Will be discussed later | 23-Sep-25: NON Critical to be reviewd later | L&T | Sivaprasad | Sivaprasad |  | Open | Open | [9 empty] | MOMNOC Operationalization | Network | OPEN | [6 empty] | 1
743 | M1242 | MOM | 2024-12-10 | P3 |  |  | NOC Operationalization |  | Send Cluster wise utilization report for DC infra |  | Critical | Closed |  |  |  |  | Report shared |  |  | Ahmad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  | Daily oprational task | 2025-09-19 | Artefacts not Required |  | 1
744 | M1243 | MOM | 2024-12-10 | P3 |  |  | NOC Operationalization |  | Login in OSS, BSS, ticketing, NSO and to share all links with Principal Consultant |  | Critical | Closed |  |  |  |  | Login ID made and link shared |  |  | Ahmad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  | Not related to delivery | 2025-09-19 | Artefacts not Required |  | 1
745 | M1244 | MOM | 2024-12-10 |  |  |  | OEM Related | Neox | Neox team to be called for meeting |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMOEM Related | OEM Related Issues | OPEN | [6 empty] | 1
746 | M1245 | MOM | 2024-12-10 | P3 |  |  | NOC Operationalization |  | Access to NAS server to be provided to Principal Consultant to get access to HLD / LLD / reports. |  | NON-Critical | Closed |  |  |  |  | Access given |  |  | Ahmad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  | Not related to delivery | 2025-09-19 | Artefacts not Required |  | 1
747 | M1246 | MOM | 2024-12-10 | P3 |  |  | NOC Operationalization |  | Dashboards samples were shared by the Principal Consultant, a brief discussions carried on how critical data to be presented |  | Critical | Closed |  |  |  |  | Report shared as per Principal Consultant review |  |  | Ahmad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  | Covered in OSS | 2025-09-19 | Artefacts not Required |  | 1
748 | M1247 | MOM | 2024-12-11 |  |  |  | IP/MPLS | NOC Operationalization | Actual implemented IP MPLS ring details needed. |  | Critical | Closed |  |  |  |  | RIng details shared | L&T |  | RS Rao |  |  | COMPLETED & APPROVED | [9 empty] | MOMIP/MPLS | IPMPLS | CLOSED |  |  |  | After Jun-25 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\Link topology of PKG A B C updated as on 05082025.xlsx |  | 1
749 | M1248 | MOM | 2024-12-11 |  |  |  | NOC Operationalization |  | Share Test Setup proposal which was sent to TFIBER by LTTS. |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1
750 | M1249 | MOM | 2024-12-11 | P3 |  |  | NOC Operationalization |  | What is total scope of the project V/S implementation. And then total equipment procured Vs installed Vs Available in field and at DC |  | Critical | Closed |  |  |  |  | Report shared |  |  | Ahmad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  | Covered in OSS | 2025-09-19 | Artefacts not Required |  | 1
751 | M125 | MOM | 2023-08-01 |  |  |  | Helpdesk | Handbook & SOPs | Expression of First Call Resolution (FCR) as a percentage |  | Critical | Open |  |  |  | WIP |  |  |  | Siva Kumar |  | Open | WIP | [9 empty] | MOMHelpdesk | Helpdesk (Contact Center) | OPEN | [6 empty] | 1
752 | M1250 | MOM | 2024-12-11 |  |  |  | OEM Related | HPSM | In Asset Manager deployed inventory status is available. WH equipment data also available for PKG-B & C. |  | Critical | Closed |  |  |  | to be discussed later | 23-Sep-25: NON Critical to be reviewd later | L&T | Sivaprasad | Sivaprasad |  | Open | Open | [9 empty] | MOMOEM Related | OEM Related Issues | OPEN | [6 empty] | 1
753 | M1251 | MOM | 2024-12-11 | P3 |  |  | NOC Operationalization |  | Tomorrow Field Project team discussion is scheduled (Different Packages , Different Slots, Need OSS and NOC team) |  | Critical | Closed |  |  |  |  | Meetin conducted |  |  | Ahmad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  | Not related to delivery | 2025-09-19 | Artefacts not Required |  | 1
754 | M1252 | MOM | 2024-12-11 | P3 |  |  | NOC Operationalization |  | Inventory, down, nodes/links with aging, team deployed in field to be shown to them |  | Critical | Closed |  |  |  |  | Data shown especially DWDM, Mandal, GP and UPS |  |  | Ahmad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  | Covered in OSS | 2025-09-19 | Artefacts not Required |  | 1
755 | M1253 | MOM | 2024-12-11 |  | OSS | OSS | OSS | BBNL | Make a Focused WhatsApp group for BBNL |  | Critical | Closed | [7 empty] | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMOSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1
756 | M1254 | MOM | 2024-12-11 |  |  |  | IP/MPLS | NOC Operationalization | Holistic IP planning for all service type to be done based on discussion in near future |  | Critical | Closed | [5 empty] | L&T |  | RS Rao |  |  | COMPLETED & APPROVED | [9 empty] | MOMIP/MPLS | IPMPLS | CLOSED |  |  |  | After Jun-25 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\TFiber IP Plan Details.zip |  | 1
757 | M1255 | MOM | 2024-12-11 |  |  |  | NOC Operationalization |  | Official mail to IPNIC from TFIBER MD office for additional IPs to be sent |  | Critical | Open | [7 empty] | TFiber |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMNOC Operationalization | Network | OPEN |  |  |  |  | Artefacts to be uploaded |  | 1
758 | M1256 | MOM | 2024-12-11 |  |  |  | NOC Operationalization |  | For all equipment's, need confirmation mail/letter from all OEMs for IPv4 and IPv6 dual stack implementation compliance |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMNOC Operationalization | Network | OPEN | [6 empty] | 1
759 | M1257 | MOM | 2024-12-11 |  |  |  | NOC Operationalization |  | A consistent process of design review to acceptance of artefact is missing. Requested Principal Consultant to agree process to set a design authority |  | Critical | Closed | [7 empty] | TFiber |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMNOC Operationalization | Network | OPEN |  |  |  |  | Artefacts to be uploaded |  | 1
760 | M1258 | MOM | 2024-12-11 |  |  |  | BSS |  | Capture Aadhar integration need in our requirement doc / soln/SOW for BSS/NSO. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
761 | M1259 | MOM | 2024-12-11 |  |  |  | NOC Operationalization |  | What BSS & NSO does? Can you make flow of processes/data/provisioning/delivery etc. across BSS, NSO, OSS, EMS, Billing, Helpdesk |  | Critical | Closed |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMNOC Operationalization | Network | OPEN | [6 empty] | 1
762 | M126 | MOM | 2023-08-01 |  |  |  | Helpdesk | Handbook & SOPs | Review of Agent Utilization Formula |  | Critical | open |  |  |  | Closed | 25-Sep-25: Artefacts to be uploaded |  |  | Siva Kumar |  |  | COMPLETED & APPROVED | [9 empty] | MOMHelpdesk | Helpdesk (Contact Center) | CLOSED |  |  |  | 2025-09-24 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\M117,126,728 |  | 1
763 | M1260 | MOM | 2024-12-11 |  |  |  | NOC Operationalization |  | What all services are automated and what is not automated list to be provided |  | Critical | Closed |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMNOC Operationalization | Network | OPEN | [6 empty] | 1
764 | M1261 | MOM | 2024-12-11 |  |  |  | BSS |  | Business flow discussed like existing telecom operator customer mgmt. case study . BSS Workout sheet made by Principal Consultant will be sent to you, and will discuss in detailed along with KNOT, TFIBER, TFIBER business/finance team when Aravindhan comes over to HYD at TFIBER office |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN | [6 empty] | 1
765 | M1262 | MOM | 2024-12-13 | P3 |  |  | NOC Operationalization |  | Make Node Availability as per today's format as suggested by Principal Consultant |  | Critical | Closed |  |  |  |  | Report shared as per Principal Consultant review |  |  | Ahmad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  | Covered in OSS | 2025-09-19 | Artefacts not Required |  | 1
766 | M1263 | MOM | 2024-12-13 | P3 |  |  | NOC Operationalization |  | All nodes/applications AMC details to be shared |  | Critical | Closed |  |  |  |  | AMC status shared |  |  | Ahmad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  | Infrastructure | 2025-09-24 | \\172.28.9.23\tnocreports\AMC |  | 1
767 | M1264 | MOM | 2024-12-31 | P3 |  |  | NOC Operationalization |  | Network alarms to be reduced, currently 90K alarms |  | Critical | Closed |  |  |  |  | Report shared. Field related alarms exists as per field anamolies |  |  | Ahmad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  | Covered in OSS | 2025-09-19 | Artefacts not Required |  | 1
768 | M1265 | MOM | 2025-02-14 |  |  |  | NOC Operationalization |  | Go-live plan discussion and action items to be tracked and closed |  | Critical | Closed |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMNOC Operationalization | Network | OPEN | [6 empty] | 1
769 | M1266 | MOM | 2025-02-14 | P3 |  |  | NOC Operationalization |  | One-to-one meeting with complete TNOC resources to be completed |  | Critical | Open |  |  |  |  | Scheduled as per Principal Consultant availability |  |  | Ahmad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  | Not related to delivery | 2025-09-19 | Artefacts not Required |  | 1
770 | M1267 | MOM | 2025-02-14 |  |  |  | OEM Related | Nokia | All APIs to be taken from Nokia |  | Critical | Open |  |  |  | Closed, Artefacts to be uploaded | 23-Sep-25: Approved Artefacts to be Submitted | L&T | Sivaprasad | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMOEM Related | OEM Related Issues | CLOSED |  |  |  |  | Artefacts Need to upload |  | 1
771 | M1268 | MOM | 2025-02-14 |  |  |  | NOC Operationalization |  | Undertaking from L&T is needed for all In-House software |  | Critical | Open |  |  |  | Closed, Artefacts to be uploaded | 23-Sep-25: Approved Artefacts to be Submitted | L&T | Sivaprasad | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  |  | Artefacts Need to upload |  | 1
772 | M1269 | MOM | 2025-02-14 | P3 |  |  | NOC Operationalization |  | PKG-A WH inventory data to be uploaded in Asset Manager |  | Critical | Open |  |  |  |  | Done |  |  | Ahmad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  | Covered in OSS | 2025-09-19 | Artefacts not Required |  | 1
773 | M127 | MOM | 2023-08-01 |  |  |  | Helpdesk | Handbook & SOPs | Customer-Specific SLA Flows |  | Critical | open |  |  |  | Closed | 24-Sep-25: Updated Document Shared 23-Aug-23 |  |  | Siva Kumar |  |  | COMPLETED & APPROVED | [9 empty] | MOMHelpdesk | Helpdesk (Contact Center) | CLOSED |  |  |  | 2025-09-24 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\M104,105,109,111,113,115,122,123,127,128,130,132,162 |  | 1
774 | M1270 | MOM | 2025-02-14 |  |  |  | Helpdesk | Handbook & SOPs | Helpdesk IVR: after selecting any number (apart from configured 1/2/3), call is getting disconnected. This need to be corrected |  | Critical | open |  |  |  | Closed | 24-Sep-25: Artefacts to be uploaded |  |  | Siva Kumar |  |  | COMPLETED & APPROVED | [9 empty] | MOMHelpdesk | Helpdesk (Contact Center) | CLOSED |  |  |  | 2025-09-24 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\M1270 |  | 1
775 | M1271 | MOM | 2025-04-03 |  |  |  | NOC Operationalization |  | One slide to be presented showing status of work capturing: a. Status (last week actions), b) Issues, c) Achievements d) Plan for Next week. Only major points to be mentioned |  | Critical | Closed |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1
776 | M1272 | MOM | 2025-04-03 |  |  |  | NOC Operationalization |  | Review slides to capture: 1. Tech/SME/OEM wise update 2. Domain Status - one slide for each domain 3. HLD/LLD/FAT update 4. Detailed HLD/LLD/FAT open points list: 20-30 points 5. Other important points (NOC also like DWDM losses, infra issues at ZOnal/mandal, etc.) 6. 742 Tracker, MoM update |  | NON-Critical | Closed |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1
777 | M1273 | MOM | 2025-04-03 |  |  |  | NOC Operationalization |  | Aggressive followups with TPA to be done by L&T SMEs. Post 2-3 followups, then come to Principal Consultant for support alongwith TPA |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1
778 | M1274 | MOM | 2025-04-03 |  |  |  | GIS | User Experience | GIS: Make a PPT for operationalisation of GIS Ops & updation. This will be shared to PKG-B & C |  | Critical | Open | Conflict | Gtech | [5 empty] | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMGIS | Applications/Tools | OPEN | [6 empty] | 1
779 | M1275 | MOM | 2025-04-03 |  |  |  | NOC Operationalization |  | Incorporate MoM points in HLD/LLD documents |  | NON-Critical | Closed |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMNOC Operationalization | Network | OPEN | [6 empty] | 1
780 | M1276 | MOM | 2025-04-03 |  |  |  | NOC Operationalization |  | Make proper justification for A&O for Tfiber MD approval. Shpw project plan. Show previous delivered systems like IPDR, BBNL solution which his made solely by L&T inhouse team. Include Support system/mechanism to Tfiber during 7 years and post L&T exit project |  | Critical | Closed |  |  |  | Closed, Artefacts to be uploaded | 23-Sep-25: Approved Artefacts to be Submitted | L&T | Sivaprasad | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  |  | Artefacts Need to upload |  | 1
781 | M1277 | MOM | 2025-04-03 |  |  |  | NSO | Service provisioning | GI-BB Demo to be shown to Principal Consultant on 15th April2025 |  | Critical | Closed | [7 empty] | Jayant Madavi |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMNSO | Applications/Tools | OPEN |  |  |  |  | Artefacts to be uploaded |  | 1
782 | M1278 | MOM | 2025-04-03 |  |  |  | NOC Operationalization |  | Every Thursday 11 AM review meeting to be planned with Principal Consultant on NOC project |  | Critical | Closed |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1
783 | M128 | MOM | 2023-08-01 |  |  |  | Helpdesk | Handbook & SOPs | Exhaustive List of General Enquiries |  | Critical | open |  |  |  | Closed | 24-Sep-25: Updated Document Shared 23-Aug-23 |  |  | Siva Kumar |  |  | COMPLETED & APPROVED | [9 empty] | MOMHelpdesk | Helpdesk (Contact Center) | CLOSED |  |  |  | 2025-09-24 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\M104,105,109,111,113,115,122,123,127,128,130,132,162 |  | 1
784 | M129 | MOM | 2023-08-01 |  |  |  | Helpdesk | Handbook & SOPs | DoT KPIs Coverage in KPI Section |  | Critical | open |  |  |  | Closed | 24-Sep-25: Artfcats to be uploaded 11-Sep-25: Feature Available, Shall be demonstrated |  |  | Siva Kumar |  |  | COMPLETED & APPROVED | [9 empty] | MOMHelpdesk | Helpdesk (Contact Center) | CLOSED |  |  |  | 2025-09-24 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\M120,129 |  | 1
785 | M13 | MOM | 2023-04-03 |  | OSS | OSS | OSS | Functional AT Plan | Quality test report submission for DWDM & IPMPLS each zonal path. |  | Critical | Open |  | OSS Dashboards | [5 empty] | Suresh Pawar |  | Open | Open | [9 empty] | MOMOSS | Applications/Tools | OPEN | OPEN | 0 |  |  | #N/A |  | 1
786 | M130 | MOM | 2023-08-01 |  |  |  | Helpdesk | Handbook & SOPs | FAQs Based on Case Studies |  | Critical | open |  |  |  | Closed | 24-Sep-25: Updated Document Shared 23-Aug-23 |  |  | Siva Kumar |  |  | COMPLETED & APPROVED | [9 empty] | MOMHelpdesk | Helpdesk (Contact Center) | CLOSED |  |  |  | 2025-09-24 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\M104,105,109,111,113,115,122,123,127,128,130,132,162 |  | 1
787 | M131 | MOM | 2023-08-01 |  |  |  | Helpdesk | Handbook & SOPs | Request to differentiate between registered users and registered numbers using examples. |  | Critical | Open |  |  |  | WIP | 11-Sep-25: BSS Integration to be completed |  |  | Siva Kumar |  | Open | WIP | [9 empty] | MOMHelpdesk | Helpdesk (Contact Center) | OPEN | [6 empty] | 1
788 | M132 | MOM | 2023-08-01 |  |  |  | Helpdesk | Handbook & SOPs | the roles and responsibilities of NOC and Field Personnel be separate according to the RASCI matrix |  | Critical | open |  |  |  | Closed | 24-Sep-25: Updated Document Shared 23-Aug-23 |  |  | Siva Kumar |  |  | COMPLETED & APPROVED | [9 empty] | MOMHelpdesk | Helpdesk (Contact Center) | CLOSED |  |  |  | 2025-09-24 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\M104,105,109,111,113,115,122,123,127,128,130,132,162 |  | 1
789 | M133 | MOM | 2023-08-01 |  |  |  | Helpdesk | Handbook & SOPs | Inclusion of Master and Child Service Level Agreement (SLA) monitoring; if any SLA is breached, a proper escalation matrix should be available for speedy escalation and resolution of the issue. |  | Critical | open |  |  |  | WIP |  |  |  | Siva Kumar |  | Open | WIP | [9 empty] | MOMHelpdesk | Helpdesk (Contact Center) | OPEN | [6 empty] | 1
790 | M134 | MOM | 2023-08-01 |  |  |  | Helpdesk | Training | Training for Call Transferring |  | Critical | open |  |  |  | Closed | 24-Sep-25: Trianing completed, Artefacts to be uploaded |  |  | Siva Kumar |  |  | COMPLETED & APPROVED | [9 empty] | MOMHelpdesk | Helpdesk (Contact Center) | CLOSED |  |  |  | 2025-09-24 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\M114,722,134 |  | 1
791 | M135 | MOM | 2023-08-01 |  |  |  | Helpdesk | User Experience | Proactive Intimation of Planned Downtime |  | Critical | open |  |  |  | WIP | 24-Sep-25: Part of Neox integration with BSS/OSS | L&T | Manoj & Shiva kumar | Siva Kumar |  | Open | WIP | [9 empty] | MOMHelpdesk | Helpdesk (Contact Center) | OPEN | [6 empty] | 1
792 | M136 | MOM | 2023-08-23 |  |  |  | BSS | Notification Template | comprehensive list of event notification scenarios and implementation plan. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
793 | M137 | MOM | 2023-08-23 |  |  |  | BSS | Improvement | Complete User Group creation |  | Critical | Closed | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN | [6 empty] | 1
794 | M138 | MOM | 2023-08-23 |  |  |  | BSS | Improvement | customizable columns |  | Critical | Closed | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN | [6 empty] | 1
795 | M139 | MOM | 2023-08-23 |  |  |  | BSS | Dashboards | Summary of Leads |  | NON-Critical | Closed | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN | [6 empty] | 1
796 | M14 | MOM | 2023-04-16 |  | OSS | OSS | OSS | Full NOC Readiness | Secretary, DoT enquired to show the MTTR through against individual TT in the OSS |  | Critical | Open |  | OSS Dashboards | [5 empty] | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMOSS | Applications/Tools | OPEN | CLOSURE REVIEW PENDING | 0 |  |  |  |  | 1
797 | M140 | MOM | 2023-08-23 |  |  |  | BSS | Improvement | Advance Search options |  | NON-Critical | Open |  |  |  |  | It is available OOB |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN | [6 empty] | 1
798 | M141 | MOM | 2023-08-23 |  |  |  | BSS | Resource Related | Structure & Composition of Service Delivery group |  | NON-Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
799 | M142 | MOM | 2023-08-23 |  |  |  | BSS | Resource Related | Roles & Responsibility of Service Delivery group |  | NON-Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
800 | M143 | MOM | 2023-08-23 |  |  |  | BSS | User Experience | Notification with status changes from Opportunity - RFO - RFS – Order |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
801 | M144 | MOM | 2023-08-23 |  |  |  | BSS | Handbook & SOPs | Process for Data Integrity of Bulk upload |  | NON-Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
802 | M145 | MOM | 2023-08-23 |  | OSS | OSS | OSS | Manual Feasibility Plan | Plan for manual feasibility in the OSS |  | NON-Critical | Open | [7 empty] | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMOSS | Applications/Tools | OPEN | CLOSURE REVIEW PENDING | 0 |  |  |  |  | 1
803 | M146 | MOM | 2023-08-23 |  |  |  | BSS | Dashboards | Summary before Feasibility Result |  | NON-Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
804 | M147 | MOM | 2023-08-23 |  |  |  | BSS | Manual Feasibility Plan | Order Fulfilment - Exception Scenarios |  | NON-Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
805 | M148 | MOM | 2023-08-23 |  |  |  | BSS | Action points | Ensure that site editing is restricted |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
806 | M149 | MOM | 2023-08-23 |  |  |  | BSS | Data Upload | Entire network POI/ PoP status, including 12751 GPs, 1 NOC, all zones, districts & Mandal nodes, is available in the CRM database |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
807 | M15 | MOM | 2023-04-16 |  | OSS | OSS | OSS | Full NOC Readiness | Secretary, DoT advised to show more KPIs, Video wall extension is required |  | Critical | Open |  | OSS Dashboards | [5 empty] | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMOSS | Applications/Tools | OPEN | COMPLETED | All power BI dashboards, SM MTTR Dashboards |  |  | #N/A |  | 1
808 | M150 | MOM | 2023-08-23 |  |  |  | BSS | CSP User Experience | Telugu Subtitles in CSP |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
809 | M151 | MOM | 2023-08-23 |  |  |  | BSS | CSP User Experience | Google Location Pickup |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
810 | M152 | MOM | 2023-08-23 |  |  |  | BSS | CSP User Experience | Lat/Long coordinates and LGD codes should be removed from the search bar. |  | Critical | Closed | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN | [6 empty] | 1
811 | M153 | MOM | 2023-08-23 |  |  |  | BSS | CSP User Experience | Check Residential" should be changed with a more appropriate term. |  | NON-Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
812 | M154 | MOM | 2023-08-23 |  |  |  | BSS | CSP User Experience | Introduce a "Thank You" page after a lead is submitted, displaying the lead number. This lead number could be useful for Helpdesk also. |  | NON-Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
813 | M155 | MOM | 2023-08-23 |  |  |  | BSS | CSP User Experience | The term "External" should be replaced with "Internal." |  | NON-Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
814 | M156 | MOM | 2023-08-23 |  |  |  | BSS | CSP User Experience | "Value-Add Partners" Tab |  | NON-Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
815 | M157 | MOM | 2023-08-23 |  |  |  | BSS | CSP User Experience | Landing Page Content |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
816 | M158 | MOM | 2023-08-23 |  |  |  | BSS | CSP User Experience | The term "Last Miles" should be changed to "Partners. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
817 | M159 | MOM | 2023-08-23 |  |  |  | BSS | CSP User Experience | The "Government/Cell Tower/Enterprise" tab should have a dropdown for various services & information. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
818 | M16 | MOM | 2023-04-19 |  |  |  | GIS | Functional AT Plan | Loading Sample Data and Internal Quality Test Report Submission |  | NON-Critical | Open |  | OSS Dashboards | [5 empty] | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMGIS | Applications/Tools | OPEN | [6 empty] | 1
819 | M160 | MOM | 2023-08-23 |  |  |  | BSS | CSP User Experience | Chatbot Feature |  | NON-Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
820 | M161 | MOM | 2023-08-23 |  |  |  | BSS | CSP User Experience | Leads Summary for B2B Partner |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
821 | M162 | MOM | 2023-08-31 |  |  |  | BSS | User Experience | CRM should be in IST Times |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
822 | M163 | MOM | 2023-08-31 |  |  |  | BSS | User Experience | User Group training for administrator to Add/Modify the user access in CSP and CRM |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
823 | M164 | MOM | 2023-08-31 |  |  |  | BSS | Billing Related | SSL Certificate implementation |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
824 | M165 | MOM | 2023-08-31 |  |  |  | BSS | User Experience | Corporate Number for WhatsApp |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
825 | M166 | MOM | 2023-09-08 |  |  |  | BSS | Handbook & SOPs | Order Fulfilment Process |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
826 | M167 | MOM | 2023-09-08 |  |  |  | BSS | Handbook & SOPs | Service Delivery Process |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
827 | M168 | MOM | 2023-09-08 |  |  |  | BSS | Handbook & SOPs | Service Delivery Team Resource and responsibilities & relationship with other packages |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
828 | M169 | MOM | 2023-09-08 |  |  |  | BSS | Handbook & SOPs | Clearly define user system mapping with specific process steps with documentation for clarity |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
829 | M17 | MOM | 2023-05-18 |  |  |  | GIS | Functional AT Plan | Basic GIS Tool UAT for TPA |  | Critical | Open |  | OSS Dashboards |  |  | The ATP was submitted, discussed with the TPA, and all feedback was incorporated. The revised ATP has also been sent |  |  | Kaushalendra Kumar |  | Open | Open | [9 empty] | MOMGIS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
830 | M170 | MOM | 2023-09-08 |  |  |  | Helpdesk | User Experience | Change in IVRS Welcome Message |  | Critical | open |  |  |  | Closed | 24-Sep-25: Approved and shall be closed 11-Sep-25: Changed and operational Now |  |  | Siva Kumar |  |  | COMPLETED & APPROVED | [9 empty] | MOMHelpdesk | Helpdesk (Contact Center) | CLOSED |  |  |  | 2025-09-24 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\M121,170,99,726 |  | 1
831 | M171 | MOM | 2023-09-08 |  |  |  | Helpdesk | Resource Related | Other package involvement |  | Critical | open |  |  |  | Closed | 24-Sep-25: Artefacts to be submitted 11-Sep-25: Clarified as its only L&T Manpower |  |  | Siva Kumar |  |  | COMPLETED & APPROVED | [9 empty] | MOMHelpdesk | Helpdesk (Contact Center) | CLOSED |  |  |  | 2025-09-24 | Artefacts Need to upload |  | 1
832 | M172 | MOM | 2023-09-12 | P3 |  |  | NOC Operationalization | Handbook & SOPs | SOPs Submission |  | Critical | Closed |  |  |  |  | Agreed SOPs are submitted and agreed with TFiber |  |  | Ahmad | 2025-09-20 |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  | Documentation | 2025-09-24 | \\172.28.9.23\tnocreports\Approved Process and SOP_ T Fiber\SOP |  | 1
833 | M173 | MOM | 2023-09-12 |  |  |  | NOC Operationalization | OEM's Details | Submit details on OEM alignment, warranty, AMC, and engagement status for go-live and post-go-live phases, location-wise & application-wise, to Director-Contracts, T-Fiber |  | Critical | Open | [7 empty] | Ahmad |  | Open | Open | [9 empty] | MOMNOC Operationalization | Network | OPEN |  |  |  |  | #N/A |  | 1
834 | M174 | MOM | 2023-09-12 |  |  |  | Helpdesk | Improvement | Streamlining of Helpdesk and Ticketing system |  | Critical | open |  |  |  | WIP | 11-Sep-25: Same has been Submitted |  |  | Siva Kumar |  | Open | WIP | [9 empty] | MOMHelpdesk | Helpdesk (Contact Center) | OPEN | [6 empty] | 1
835 | M175 | MOM | 2023-09-12 | P3 |  |  | NOC Operationalization | Dashboards | Dashboards for each element of the Video Wall, specifying manual or automatic clarity |  | Critical | Completed |  |  |  |  | Curently Video wall is displaying dashboards as per agreement with TFiber |  |  | Ahmad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  | Covered in OSS | 2025-09-19 | Artefacts not Required |  | 1
836 | M176 | MOM | 2023-09-12 | P3 |  |  | NOC Operationalization | Resource Related | T-NOC Resource details and deployment with Roles and Responsibilities |  | Critical | Completed |  |  |  |  | TNOC resource is deployed as per RFP. Manpower report is shared on weekly basis. |  |  | Ahmad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  | Not related to delivery | 2025-09-24 | \\172.28.9.23\tnocreports\TNOC Manpower_CVs\NOC Resources Details & Roles |  | 1
837 | M177 | MOM | 2023-09-12 |  |  |  | Security & Regulatory Compliance | Patch update | Engagements with vendors for Patch Delivery and Testing |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1
838 | M178 | MOM | 2023-09-12 |  |  |  | NOC Operationalization | Dashboards | SLA Monitoring and Network Performance Statistics |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMNOC Operationalization | Network | OPEN | [6 empty] | 1
839 | M179 | MOM | 2023-09-12 |  |  |  | NOC Operationalization | O&M Strategy | Spares Management |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMNOC Operationalization | Network | OPEN | [6 empty] | 1
840 | M18 | MOM | 2023-05-18 |  | OSS | OSS | OSS | Integration | IP MPLS auto trouble tickets |  | Critical | Open |  | OSS Dashboards |  |  | 09-09-2025: Stabilization needed |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMOSS | Applications/Tools | OPEN | COMPLETED | 09-09-2025: Stabilization needed |  |  |  |  | 1
841 | M180 | MOM | 2023-09-12 |  |  |  | NOC Operationalization | O&M Strategy | Repair and Replacement process |  | Critical | Completed |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1
842 | M181 | MOM | 2023-09-12 |  |  |  | BSS | Dynamic Feature | Overall capability to support the creation of innovative new products and seamless customer experience |  | NON-Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
843 | M182 | MOM | 2023-09-22 |  |  |  | NSO | Service provisioning | NSO provisioning is happening through EMS and asked for the list of provisioning/monitoring features being limited or constrained due to any interoperability issues in a multi-vendor eco-system. |  | Critical | Open | [7 empty] | Jayant Madavi |  | Open | Open | [9 empty] | MOMNSO | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
844 | M183 | MOM | 2023-09-22 |  | OSS | OSS | OSS | Service provisioning | Role of OSS in Service Provisioning |  | Critical | Open | [7 empty] | Suresh Pawar |  | Open | WIP | [9 empty] | MOMOSS | Applications/Tools | OPEN | OPEN | 0 |  |  | #N/A |  | 1
845 | M184 | MOM | 2023-09-22 |  |  |  | NOC Operationalization | O&M Strategy | Redundancy Plan for NSO and OSS |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMNOC Operationalization | Network | OPEN | [6 empty] | 1
846 | M185 | MOM | 2023-09-22 |  |  |  | NOC Operationalization | O&M Strategy | Limitations in OSS and NSO Scalability for post go live |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMNOC Operationalization | Network | OPEN | [6 empty] | 1
847 | M186 | MOM | 2023-09-22 |  |  |  | BSS | Dynamic Feature | Enhance BSS to allow flexibility in creating, modifying, adding, and deleting product categories |  | NON-Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
848 | M187 | MOM | 2023-09-22 |  |  |  | NSO | Handbook & SOPs | Train in-house L&T resources in NSO and NEDs for reduced dependency on Cisco. |  | Critical | Open | [7 empty] | Jayant Madavi |  | Open | Open | [9 empty] | MOMNSO | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
849 | M188 | MOM | 2023-09-22 |  |  |  | BSS | Notification Template | Notification Template Flexibility |  | NON-Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
850 | M189 | MOM | 2023-09-22 |  |  |  | BSS | Notification Template | CP to be changed to CP-TFGCLT |  | NON-Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
851 | M19 | MOM | 2023-05-18 |  |  |  | BSS | Resource Related | Inter-Dependence Matrix and Resource Identification |  | Critical | Open |  | OSS Dashboards | [5 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
852 | M190 | MOM | 2023-09-22 |  |  |  | BSS | CSP User Experience | Ensure that only the logos of the Government of Telangana and T-Fiber are used in the CSP. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
853 | M191 | MOM | 2023-09-22 |  |  |  | BSS | Billing Related | CAF detailed analysis related to TRAI |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
854 | M192 | MOM | 2023-09-22 |  |  |  | BSS | CSP User Experience | Clearly mention on the Landing Page that services are currently extended only for Rural Telangana; Capture and store leads for requests from Urban Telangana. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
855 | M193 | MOM | 2023-09-22 |  |  |  | BSS | CSP User Experience | User guides such as "May I help you", Chatbots, Videos |  | NON-Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
856 | M194 | MOM | 2023-09-22 |  |  |  | BSS | CSP User Experience | Definitions of terminologies to be available on mouseover |  | NON-Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
857 | M195 | MOM | 2023-09-22 |  |  |  | DR | O&M Strategy | a brief note on what is required to be delivered by CtrlS for DR |  | NON-Critical | Open |  |  |  |  | Work in progress |  |  | Ravi Kishore |  | Open | Open | [9 empty] | MOMDR | DR | OPEN | [6 empty] | 1
858 | M196 | MOM | 2023-09-22 |  |  |  | DR | Functional AT Plan | Share the test results of DR systems with T-Fiber. |  | NON-Critical | Open |  |  |  |  | Work in progress |  |  | Ravi Kishore |  | Open | Open | [9 empty] | MOMDR | DR | OPEN | [6 empty] | 1
859 | M197 | MOM | 2023-09-22 |  |  |  | BSS | Integration | WFM-SMS Gateway integration |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
860 | M198 | MOM | 2023-09-22 |  |  |  | BSS | CSP User Experience | L&T, to update the Landing Page to cater to all specified segments such as Pin code, Address, Lat-Long, or address pulling from Google API is required |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
861 | M199 | MOM | 2023-09-22 |  |  |  | BSS | Notification Template | Replace "Re-confirm" with "View" in the notification template. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
862 | M2 | MOM | 2023-02-06 | P3 |  |  | NOC Operationalization | Handbook & SOPs | T-Fiber requested the inclusion of Protocol Manager and Regulatory roles in the TNOC organization chart. Also, emphasized clear demarcation and mapping of resources with names, roles, and responsibilities |  | Critical | Completed |  | OSS Dashboards |  |  | NOC resources details is shared on weekly basis. Roles of NOC is as per RFP. |  |  | Ahmad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  | Not related to delivery | 2025-09-19 | Artefacts not Required |  | 1
863 | M20 | MOM | 2023-05-18 |  |  |  | BSS | Full NOC Readiness | Roadmap for Network Service Order Fulfilment and Service Assurance |  | Critical | Open |  | OSS Dashboards | [5 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
864 | M200 | MOM | 2023-09-22 |  |  |  | BSS | Notification Template | Ensure that SMS includes a link to the CSP. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
865 | M201 | MOM | 2023-09-22 |  |  |  | BSS | Functional AT Plan | Perform testing of negative scenarios to identify and address any issues or vulnerabilities |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
866 | M202 | MOM | 2023-09-22 |  |  |  | BSS | CSP User Experience | Validate all mandatory fields and associated asterisks to ensure completeness and accuracy of data entry |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
867 | M203 | MOM | 2023-09-22 |  |  |  | BSS | Billing Related | Establish a mechanism to confirm the synchronization between the current account and the payment portal. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
868 | M204 | MOM | 2023-09-22 |  |  |  | BSS | CSP User Experience | Display Progress in CSP Post-Order |  | NON-Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
869 | M205 | MOM | 2023-09-22 |  |  |  | BSS | CSP User Experience | User-Friendly Product Naming |  | NON-Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
870 | M206 | MOM | 2023-09-22 |  |  |  | BSS | Action points | Address and resolve issues related to using the backspace key on the webpage, ensuring smooth navigation to the previous page. |  | NON-Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
871 | M207 | MOM | 2023-09-22 |  |  |  | BSS | Billing Related | Payments and policies : BSS billing module should have various frameworks of full payment, part payment, advance payment, based on customer credit worthiness , based on discount policy etc. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
872 | M208 | MOM | 2023-09-22 |  |  |  | BSS | CSP User Experience | Time Duration of OTP need to be fixed with timer |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
873 | M209 | MOM | 2023-09-22 |  |  |  | BSS | CSP User Experience | Implement 'Request to Re-send OTP' |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
874 | M21 | MOM | 2023-06-01 |  |  |  | GIS | User Experience | Google Map availability in Geo Media Tool with real time navigation |  | Critical | Open |  | OSS Dashboards |  |  | Google Map availability in Geo Media Tool, Hexagon clarified that Google Map feature is not available in Geo Media as it is a client based independent tool which can be installed in client PCs; however, end users can use OSM and/or Bing maps along with Geo media |  |  | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMGIS | Applications/Tools | OPEN | [6 empty] | 1
875 | M210 | MOM | 2023-09-22 |  |  |  | BSS | Billing Related | Implement a system to generate a revised Proforma Invoice with the latest date if the ordering process is stopped and resumed. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
876 | M211 | MOM | 2023-09-22 |  |  |  | BSS | CSP User Experience | Configure the CSP portal to display only orders relevant to the specific customer, enhancing user experience and clarity. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
877 | M212 | MOM | 2023-09-22 |  |  |  | BSS | Service provisioning | Reservation of Bandwidth at Provisioning |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
878 | M213 | MOM | 2023-09-22 |  |  |  | BSS | CSP User Experience | Customer Care should in bold |  | NON-Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
879 | M214 | MOM | 2023-09-22 |  |  |  | BSS | Billing Related | Align Order Confirmation with Payment Receipt |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
880 | M215 | MOM | 2023-09-22 |  |  |  | BSS | Improvement | Improve 'Pick Order' Button and Placeholder |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
881 | M216 | MOM | 2023-09-22 |  |  |  | BSS | Billing Related | Implement Alerts for CAF Approval and Payment |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
882 | M217 | MOM | 2023-09-22 |  |  |  | BSS | Improvement | Customer Dashboards with visible website name for branding |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
883 | M218 | MOM | 2023-09-22 |  |  |  | BSS | User Experience | Make Site ID More Relevant for Order Selection |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
884 | M219 | MOM | 2023-09-22 |  |  |  | BSS | Improvement | Display Opportunity ID and Order ID Differently columns |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
885 | M22 | MOM | 2023-06-01 |  |  |  | GIS | User Experience | Fixed Topology Nomenclature |  | Critical | Open |  | OSS Dashboards | [5 empty] | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMGIS | Applications/Tools | OPEN | [6 empty] | 1
886 | M220 | MOM | 2023-09-22 |  |  |  | BSS | Action points | Address Missing Scroll Bar in Some Pages |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
887 | M221 | MOM | 2023-09-22 |  |  |  | BSS | Billing Related | Incorporate a partial payment option for larger or priority accounts, allowing T-Fiber to decide on a case-by-case basis, along with an approval matrix. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
888 | M222 | MOM | 2023-09-22 |  |  |  | BSS | Action points | Rectify the issue with the 'Show Password' option to ensure its proper functionality |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
889 | M223 | MOM | 2023-09-22 |  |  |  | BSS | Billing Related | Mandate the selection of the payment window (half-yearly or annually) during the ordering process, making it clear to the customer, rather than defaulting to monthly. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
890 | M224 | MOM | 2023-09-22 |  |  |  | BSS | Improvement | Modify the order submission process to collect secondary phone numbers and email IDs, as required. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
891 | M225 | MOM | 2023-09-22 |  |  |  | BSS | Billing Related | Implement a restriction to prevent order placement without the completion of payment, ensuring a secure and controlled ordering process. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
892 | M226 | MOM | 2023-09-22 |  |  |  | BSS | Improvement | Standardize colour coding across all UX/UI elements for consistency and a unified visual experience. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
893 | M227 | MOM | 2023-09-22 |  |  |  | BSS | Improvement | Allow users to refresh and continue after prolonged inactivity, enhancing the user experience and preventing disruptions |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
894 | M228 | MOM | 2023-09-22 |  |  |  | BSS | Improvement | Welcome Message Placement |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
895 | M229 | MOM | 2023-09-22 |  |  |  | BSS | Improvement | Introduce a flashing indicator for orders to attract attention and improve visibility. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
896 | M23 | MOM | 2023-06-01 |  |  |  | GIS | User Experience | Character size in G-Tech |  | Critical | Open |  | OSS Dashboards | [5 empty] | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMGIS | Applications/Tools | OPEN | [6 empty] | 1
897 | M230 | MOM | 2023-09-22 |  |  |  | BSS | User Experience | Add a visual indication for users to select the service under the Create Order page. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
898 | M231 | MOM | 2023-09-22 |  |  |  | BSS | Action points | Investigate and address the issue where no details are displayed upon clicking on "Customer Premises Equipment." |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
899 | M232 | MOM | 2023-09-22 |  |  |  | BSS | Improvement | Rephrase the error message that appears when clicking on the Remove button under Create Order Step 3 for better clarity. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
900 | M233 | MOM | 2023-09-22 |  |  |  | BSS | Improvement | Display Recurring Charge Frequency in Order Summary |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
901 | M234 | MOM | 2023-09-22 |  |  |  | BSS | User Experience | Display Instructions for CAF Download |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
902 | M235 | MOM | 2023-09-22 |  |  |  | BSS | User Experience | Indicate File Type and Size at Confirmation Stage |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
903 | M236 | MOM | 2023-09-22 |  |  |  | BSS | User Experience | Implement Preview Option for Uploaded Documents |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
904 | M237 | MOM | 2023-09-22 |  |  |  | BSS | Improvement | Emphasize the purpose of the "Edit Proceed" button for user understanding and clarity. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
905 | M238 | MOM | 2023-09-22 |  |  |  | BSS | Action points | Resolve Issues with "Edit Proceed" Button |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
906 | M239 | MOM | 2023-09-22 |  |  |  | BSS | Improvement | Digitally Sign Proforma Invoice |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
907 | M24 | MOM | 2023-06-01 |  |  |  | GIS | User Experience | Searching for location accuracy in G-Tech with pinpoint accuracy |  | Critical | Open |  | OSS Dashboards | [5 empty] | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMGIS | Applications/Tools | OPEN | [6 empty] | 1
908 | M240 | MOM | 2023-09-26 |  |  |  | NOC Operationalization | Handbook & SOPs | Provide clarification on the status of HOTO (Handover to Operations) and Knowledge Transfer. |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1
909 | M241 | MOM | 2023-09-26 |  |  |  | NOC Operationalization | Functional AT Plan | Systems functional Acceptance Tests Plan yet |  | Critical | Completed |  |  |  | WIP | FAT documents shared, Tracker & updates are sent on periodic basis | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMNOC Operationalization | Network | OPEN | [6 empty] | 1
910 | M242 | MOM | 2023-09-26 |  |  |  | NOC Operationalization | Full NOC Readiness | Launch Road Map |  | Critical | Completed |  |  |  | WIP | 12 NOC points, 472 Tracker is being tracked with timelines and updates / reiew happening on regular basis | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMNOC Operationalization | Network | OPEN | [6 empty] | 1
911 | M243 | MOM | 2023-09-26 |  |  |  | T&D Environment | T&D Environment | Provide details on the completion status of test and development of systems. |  | NON-Critical | Open |  |  |  |  | [15/09/25] Test Environment is actively used for T&D by Delivery and OEM teams. NOC submission provided in Tfiber has the T&D application from Oct-Mar2025 |  |  | Ravi Kishore |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMT&D Environment | Applications | OPEN |  |  |  |  | #N/A |  | 1
912 | M244 | MOM | 2023-09-26 |  |  |  | NOC Operationalization | Full NOC Readiness | Provide assurance that comprehensive solutions and designs will be within the specified list, considering anything beyond as a change request. |  | Critical | Open |  |  |  | Will be discussed later | 23-Sep-25: NON Critical to be reviewd later | L&T | Sivaprasad | Sivaprasad |  | Open | Open | [9 empty] | MOMNOC Operationalization | Network | OPEN | [6 empty] | 1
913 | M245 | MOM | 2023-09-26 |  |  |  | WFM | WFM Application | Clarify the distinction between smart app and WFM. |  | Critical | Open | [7 empty] | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMWFM | Applications/Tools | OPEN | [6 empty] | 1
914 | M246 | MOM | 2023-09-26 |  |  |  | NSO | Service provisioning | IP Pool analysis with clearly define the ownership structure of IPs, specifying whether it's co-ownership or complete ownership by the OEM. |  | NON-Critical | Open | [7 empty] | Jayant Madavi |  | Open | Open | [9 empty] | MOMNSO | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
915 | M247 | MOM | 2023-09-26 |  |  |  | T&D Environment | T&D Environment | Clarify constraints related to infra upgradation for testing & development. |  | NON-Critical | Open |  |  |  |  | 11-Oct-25: Need to list out requirement of T&D for all Domains. [15/09/25] It was decided to setup T&D using existing infra in DC in the interim |  |  | Ravi Kishore |  | Open | WIP | [9 empty] | MOMT&D Environment | Applications | OPEN | [6 empty] | 1
916 | M248 | MOM | 2023-09-26 |  |  |  | NOC Operationalization | Full NOC Readiness | Consider RFP, technical bid, and solutions for understanding the requirements of a staging system after go-live. |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMNOC Operationalization | Network | OPEN | [6 empty] | 1
917 | M249 | MOM | 2023-09-26 |  |  |  | NOC Operationalization | OEM's Details | Provide all OEMs' test cases & certificates for T-Fiber network testing |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMNOC Operationalization | Network | OPEN | [6 empty] | 1
918 | M25 | MOM | 2023-06-01 |  |  |  | GIS | User Experience | Self-address auto-population in G-Tech |  | Critical | Open |  | OSS Dashboards |  |  | Duplicate with Point- 80 |  |  | Kaushalendra Kumar |  | Open | Duplicate | [9 empty] | MOMGIS | Applications/Tools | #N/A |  |  |  |  | #N/A |  | 1
919 | M250 | MOM | 2023-10-11 |  |  |  | NOC Operationalization | Full NOC Readiness | Full NOC to be ready by 10th Nov'23 |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1
920 | M251 | MOM | 2023-10-11 |  |  |  | BSS | Resource Related | BSS Expert onboarding |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
921 | M252 | MOM | 2023-10-11 |  |  |  | Security & Regulatory Compliance | Functional AT Plan | Share scope and test plans of the External Audit. |  | Critical | Open |  |  |  |  | External audit is done by 3rd party broughtin by TFiber |  |  | Sarmendra |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | Artefacts to be Submitted |  | 1
922 | M253 | MOM | 2023-10-11 |  |  |  | Security & Regulatory Compliance | Physical Execution | Physical User access : Button is used for exit and still L&T have to finalise vendor |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1
923 | M254 | MOM | 2023-10-11 |  |  |  | Security & Regulatory Compliance | Dashboards | QoS reporting- Breakdown between automated and manual aspects |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1
924 | M255 | MOM | 2023-10-18 |  |  |  | BSS | CSP User Experience | Back Button to be available in the Payment Screen. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
925 | M256 | MOM | 2023-10-18 |  |  |  | BSS | CSP User Experience | Guidelines to be available to the user in the CAF upload stage, what to upload in CAF upload stage is not clear. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
926 | M257 | MOM | 2023-10-18 |  |  |  | BSS | CSP User Experience | Add a disclaimer for “Subject to Verification of CAF”, with notification trigger |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
927 | M258 | MOM | 2023-10-18 |  |  |  | BSS | CSP User Experience | Unable to view offline payment transactions uploaded |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
928 | M259 | MOM | 2023-10-18 |  |  |  | BSS | CSP User Experience | Mandatory sections of the CAF to be highlighted. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
929 | M26 | MOM | 2023-06-01 |  |  |  | GIS | User Experience | GPON Fiber Termination plan adherence |  | Critical | Open |  | Gtech | [5 empty] | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMGIS | Applications/Tools | OPEN | [6 empty] | 1
930 | M260 | MOM | 2023-10-18 |  |  |  | BSS | CSP User Experience | Notifications for ticket via SMS and Email not received. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
931 | M261 | MOM | 2023-10-18 |  |  |  | BSS | CSP User Experience | Received a Pop-up for incorrect entry of OTP despite entering the correct OTP |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
932 | M262 | MOM | 2023-10-18 |  |  |  | BSS | CSP User Experience | Raised single ticket in CSP, however 3 distinct tickets are visible in CSP with same narration of issue, notification or alerts not received for any of these tickets. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
933 | M263 | MOM | 2023-10-18 |  |  |  | BSS | CSP User Experience | tickets raised are visible at the department level only, is this possible to be made available Departmental user wise? |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
934 | M264 | MOM | 2023-10-18 |  |  |  | BSS | CSP User Experience | Searching by Order ID is case sensitive. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
935 | M265 | MOM | 2023-10-18 |  |  |  | BSS | CSP User Experience | Receiving the “Pending Feasibility” confirmation message, then receiving result as “Feasible” |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
936 | M266 | MOM | 2023-10-18 |  |  |  | BSS | CSP User Experience | How does BSS handle dismantled GPs if there is no real-time sync between GIS-OSS |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
937 | M267 | MOM | 2023-10-18 |  |  |  | BSS | CSP User Experience | Cygnet product name showing in the top of the tab, to be removed. |  | NON-Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
938 | M268 | MOM | 2023-10-18 |  |  |  | BSS | CSP User Experience | GP names are not aligned to government list |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
939 | M269 | MOM | 2023-10-18 |  |  |  | BSS | CSP User Experience | Plot number to be renamed as Plot / House no |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
940 | M27 | MOM | 2023-06-07 |  |  |  | GIS | Handbook & SOPs | Approval mechanism for object changes/deletion |  | Critical | Open |  | Gtech |  |  | Duplicate with Point- 81 |  |  | Kaushalendra Kumar |  | Open | Duplicate | [9 empty] | MOMGIS | Applications/Tools | #N/A |  |  |  |  | #N/A |  | 1
941 | M270 | MOM | 2023-10-18 |  |  |  | BSS | CSP User Experience | In case of Manual Provisioning, is there a stage for Validation? |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
942 | M271 | MOM | 2023-10-18 |  |  |  | BSS | CSP User Experience | Unable to enter the OTP, Unable to close the Pop-up window for OTP, require either a “Close” button OR closing the Pop-up should be allowed by clicking outside the Pop-up. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
943 | M272 | MOM | 2023-10-18 |  |  |  | BSS | CSP User Experience | Unable to go back to Home Screen |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
944 | M273 | MOM | 2023-10-18 |  |  |  | BSS | CSP User Experience | In Landing Page, number of GPs is mentioned as 12,751, this number to be validated. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
945 | M274 | MOM | 2023-10-18 |  |  |  | BSS | CSP User Experience | Back Button required in Create Order and Order Summary screens |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
946 | M275 | MOM | 2023-10-18 |  |  |  | BSS | CSP User Experience | What is the purpose of displaying segment as G2G in CAF ? |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
947 | M276 | MOM | 2023-10-18 |  |  |  | BSS | CSP User Experience | How does a GI customer know the Site ID to be entered. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
948 | M277 | MOM | 2023-10-18 |  |  |  | BSS | CSP User Experience | Payment is showing as Net banking for all transactions, including offline transactions. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
949 | M278 | MOM | 2023-10-18 |  |  |  | BSS | CSP User Experience | Unable to see Order Summary just before Payment. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
950 | M279 | MOM | 2023-10-18 |  |  |  | BSS | CSP User Experience | Notification of Success / Failure to be available on Order Submission. |  | NON-Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
951 | M28 | MOM | 2023-06-07 |  |  |  | GIS | Handbook & SOPs | Change Management Log/User Log history |  | Critical | Open |  | Gtech |  |  | Duplicate with Point- 82 |  |  | Kaushalendra Kumar |  | Open | Duplicate | [9 empty] | MOMGIS | Applications/Tools | #N/A |  |  |  |  | #N/A |  | 1
952 | M280 | MOM | 2023-10-18 |  |  |  | BSS | CSP User Experience | In Payment Screen, add a disclaimer that “Payment details are subject to verification for offline payments” to cover for the scenario of wrong / incorrect Payment ID provided by the user. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
953 | M281 | MOM | 2023-10-18 |  |  |  | BSS | CSP User Experience | Is a location added in CSP visible in the CRM as a lead? |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
954 | M282 | MOM | 2023-10-18 |  |  |  | BSS | CSP User Experience | While adding a new location using the map, searching by name is working (example- Jagtial), however searching by Lat-Long is not working. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
955 | M283 | MOM | 2023-10-18 |  |  |  | BSS | CSP User Experience | Added a location, but GP name is not getting populated, how is this address added in the CRM, received a pop-up alert for location confirmation, but this location is not added to the list. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
956 | M284 | MOM | 2023-10-18 |  |  |  | BSS | CSP User Experience | Product Selection screen did not display “Last Mile Connectivity” with no view to scroll right, either restrict the size of the location name or display all columns in a single page. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
957 | M285 | MOM | 2023-10-18 |  |  |  | BSS | CSP User Experience | Email notifications not being triggered for a few actions where events are not configured |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
958 | M286 | MOM | 2023-10-18 |  |  |  | BSS | CSP User Experience | Received order confirmation, but no notifications received for payment, no notification on save order. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
959 | M287 | MOM | 2023-10-18 |  |  |  | BSS | CSP User Experience | What is the Transaction number? |  | NON-Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
960 | M288 | MOM | 2023-10-18 |  |  |  | BSS | CSP User Experience | While adding a new address, selected a gram panchayat, changed Lat-Long, provided address details, successfully added these details, but the address for GP name is not seen, to be shown. |  | NON-Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
961 | M289 | MOM | 2023-10-19 |  |  |  | NOC Operationalization | Interim NOC | Provide a list of points that need to be available for the Network Launch targeted for November 30th, 2023. Identify the points that will be included in the roadmap and specify the timelines for their implementation |  | Critical | Completed |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1
962 | M29 | MOM | 2023-06-07 |  |  |  | GIS | Handbook & SOPs | Data Validation Rules document |  | Critical | Open |  | Gtech | [5 empty] | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMGIS | Applications/Tools | OPEN | [6 empty] | 1
963 | M290 | MOM | 2023-10-19 |  |  |  | NOC Operationalization | Interim NOC | explain their approach for handling Operations and Maintenance (O&M) to meet the SLAs (Service Level Agreements) and provide process documents for features that are currently unavailable. |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1
964 | M291 | MOM | 2023-10-19 |  |  |  | NOC Operationalization | Interim NOC | To clarify how they plan to transition the O&M responsibilities and data once the currently unavailable features are made available. |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1
965 | M292 | MOM | 2023-10-19 |  |  |  | NOC Operationalization | Interim NOC | Evidence from L&T on the timelines for fulfilling the feature gaps |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1
966 | M293 | MOM | 2023-10-19 |  |  |  | BSS | GeM Integration | GeM integration with BSS: the point may be deferred for 6 months, with timeline to be added by L&T for next review, L&T to issue a Note (Note 1) recording this statement. |  | NON-Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
967 | M294 | MOM | 2023-10-19 |  |  |  | GPON | Interim NOC | Request a Note (Note 2) from L&T addressing the impact of the unavailability of NBI API availability for BW query Dependent on new OLT build for GI deployment and how NOC operations will be managed in the interim period until the required features are developed and integrated with seamless transition. |  | Critical | Open |  | Nokia OEM | AMS |  | Duplicate point of 472 - T175 | Duplicate |  | Sayyad Pasha |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | MOMGPON | GPON | OPEN |  |  | Duplicate |  | #VALUE! |  | 1
968 | M295 | MOM | 2023-10-19 |  |  |  | GPON | Integration | Point No. 175: CR for Nokia API integration to resolve BW query and PMS-related issues. 1. Note 2 should also cover Point No. 175. 2. Set a target completion date of November 20th '23 for this activity. |  | Critical | Open |  | Nokia OEM | AMS |  | Duplicate point of 472 - T175 | Duplicate |  | Sayyad Pasha |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | MOMGPON | GPON | OPEN |  |  | Duplicate |  | #N/A |  | 1
969 | M296 | MOM | 2023-10-19 |  |  |  | GPON | Upgradation | Point No. 179: Troubleshooting required with Tejas and Nokia for Tejas ONT firmware upgrade issue. 1. Technical Head from L&T to seek support from L&T-Contracts team and aim for implementation within 15-20 days from the resolution of the issue. 2. L&T to submit the agreed Scope between L&T and NOC OEMs (primarily OSS, BSS, NSO) by October 24th '23. 3.Request a Note (Note 3) outlining the interim/final solution and an undertaking co-signed by Package Owners to be submitted by October 26th '23. 4.Target completion of Point No. 179 by November 20th '23. |  | Critical | Open | [7 empty] | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T179 | [6 empty] | MOMGPON | GPON | CLOSED |  |  |  | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T179 |  | 1
970 | M297 | MOM | 2023-10-19 |  |  |  | GPON | Upgradation | Point No. 180: Nokia ONT to support NAT, DHCP in both Router and Bridge modes. 1. Instruct L&T to identify the number of ONTs in the warehouse and send them to the Nokia Warehouse immediately for upgrade. 2. Coordinate with Package B&C for similar actions. 3.Note 4 on the mitigation and deployment plan for remediation, along with the timelines, testing to be part of the method of deployment. |  | Critical | Open |  | Nokia OEM | ONT |  | Duplicate point of 472 - T180 | Duplicate |  | Sayyad Pasha |  | Open | Duplicate | [9 empty] | MOMGPON | GPON | CLOSED |  |  | Duplicate |  | Artefacts not Required |  | 1
971 | M298 | MOM | 2023-10-19 |  |  |  | IP/MPLS | Service Solution | Point No. 186: IPTV to Household ,Point No. 190: CCTV Multicast ,Point No. 193: SDC content to Household and GI ,Point No. 194: Incremental Product/ Services finalization in T-Fiber network,Point No. 197: Service Provisioning PoC for SCCM/NSO - MVPN (all scenarios) ,Point No. 198: Simulation and testing network for parameters like network convergence etc & Point No. 344: CCTV Solution - solution to start PoC with DC connectivity at Cyberabad location as receiver and Sircilla NVR as source. To respond with relevant evidence on how the scope is contracted between L&T and its NOC OEMs, how L&T will implement the Network AT given the Launch date of 30th November ’23. |  | Critical | Open |  |  |  |  | 25-Sep-25: Aretfacts to be uploaded for closure All updated in 472 tracker 186, 190 - Closed 344 - CCTV PoC completed. 193 - Plan re-submitted on 12-Sep-25 198 - Pending, OEM dependancy 197 - NSO point | L&T | RS Rao | RS Rao |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-05-05 | T186 - \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\House Hold VoIP Services Design LLD V1.2 - t187.pdf T190 - \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\CCTV Multicast Solution LLD V1.2 - T190.pdf T344 - | [6 empty] | MOMIP/MPLS | IPMPLS | CLOSED |  |  |  | 2025-05-05 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\House Hold VoIP Services Design LLD V1.2 - t187.pdf |  | 1
972 | M299 | MOM | 2023-10-19 |  |  |  | NSO | Design features | Point No. 221: MAG/GAC ports reservation feasibility for services booked in BSS with payments made. - BSS-SME, L&T to seek clarity on port reservation as a business requirement and the time period required for reservation. - Head Telecom Networks, L&T to record the statement that the port reservation is not a blocker for Network Launch. - Request a Note (Note 5) documenting the statement made by Head Telecom Networks. - L&T to make a decision on the period of port reservation considering the scope of NOC O&M for 7 years. |  | Critical | Open | [7 empty] | Jayant Madavi |  | Open | Open | [9 empty] | MOMNSO | Applications/Tools | OPEN |  |  |  |  | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\CCTV Multicast Solution LLD V1.2 - T190.pdf |  | 1
973 | M3 | MOM | 2023-03-27 |  |  |  | NOC Operationalization | Full NOC Readiness | Present a plan on how digital processes and tools will be used for GI connectivity provisioning, customer acceptance, and O&M functions |  | Critical | Open |  | OSS Dashboards |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMNOC Operationalization | Network | OPEN |  |  |  |  | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\CCTV Multicast Solution LLD V1.2 - T190.pdf |  | 1
974 | M30 | MOM | 2023-06-07 |  |  |  | GIS | User Experience | Show duct length, Cable length, chambers, and joint closures in a Mandal |  | NON-Critical | Open |  | Gtech | [5 empty] | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMGIS | Applications/Tools | OPEN | [6 empty] | 1
975 | M300 | MOM | 2023-10-19 |  |  |  | NSO | Development & Unit Testing | Point No. 223: IPTV tested needs to be finalised for additional configuration for multicast and tested as per lab availability and final sign off Technical Head, L&T to get the solution sign-off from T-Fiber for additional IPTV configuration and testing. - Target implementation date set for November 15th '23. - Request a Note (Note 6) recording the statement that this point is not a blocker for Network Launch. |  | Critical | Open | [7 empty] | Jayant Madavi |  | Open | Open | [9 empty] | MOMNSO | Applications/Tools | OPEN |  |  |  |  | #VALUE! |  | 1
976 | M301 | MOM | 2023-10-19 |  | OSS | OSS | New BSS | Integration | Point No. 251: Fetch SLA violation by BSS billing & Point No. 252 Circuit performance data to BSS CRM L&T to provide an outline of the interim solution before the Service Inventory solution from HP is in place. - Ensure no impact on operations during the interim period. - L&T proposes interim measures such as manual computation of downtime, manual SLA performance management, etc. - Request an Undertaking (Note 7) confirming that the interim solution will have no cost impact to T-Fiber. - Timelines for interim milestones and emphasize the need to plan for the final deliverables and a seamless transition. - Segment Head, L&T to provide clear confirmation by the 1st week of November '23. |  | Critical | Open | [7 empty] | Suresh Pawar |  | Open | WIP | [9 empty] | MOMNew BSS | #N/A | OPEN | Not Relevant to OSS | 0 |  |  | #VALUE! |  | 1
977 | M302 | MOM | 2023-10-19 |  | OSS | OSS | New BSS | Integration | Point No. 264: Network Downtime, fault reported to be mapped with BSS to consider during billing process & Point No. 265: Feasibility Engine & Point No. 266: Commercial engine to be designed along with rules to Budgetary calculation for network and customer feasibilities L&T to submit the SOW agreed between L&T and HP by EoD 19th October ’23. |  | Critical | Open | [7 empty] | Suresh Pawar |  | Open | WIP | [9 empty] | MOMNew BSS | #N/A | OPEN | Not Relevant to OSS | 0 |  |  | #VALUE! |  | 1
978 | M303 | MOM | 2023-10-19 |  | OSS | OSS | OSS | Development & Unit Testing | Point No. 267: Port Block against Service ID ( Note 5) |  | Critical | Open |  |  |  |  | Additional Scope (This is not give to HPE/OT) |  |  | Suresh Pawar |  | Open | Open | [9 empty] | MOMOSS | Applications/Tools | OPEN | Additional scope | 0 |  |  |  |  | 1
979 | M304 | MOM | 2023-10-19 |  | OSS | OSS | OSS | Design & Documentation | Point No. 272: Infra team to maintain the SSH connectivity • Security-SME, L&T to submit the design document for SSH. |  | Critical | Open | [7 empty] | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMOSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1
980 | M305 | MOM | 2023-10-19 |  | OSS | OSS | OSS | Dashboards | Point No. 280: Cross domain Corelation and exact reason for any outage in Network till ONT Port with E2E topology is targeted for closure by November 15th '23. |  | Critical | Open | [7 empty] | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMOSS | Applications/Tools | OPEN | COMPLETED | Pending |  |  | #N/A |  | 1
981 | M306 | MOM | 2023-10-19 |  | OSS | OSS | OSS | Dashboards | Point No. 282: For ONT Down cases, Some of the Alarms and cause code given by OEM is not matching with RFO provided by field engineer with target date as 25th October ’23. |  | Critical | Open |  |  |  |  | 15-09-2025: Demostrated in the Demo/UAT call |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMOSS | Applications/Tools | OPEN | COMPLETED | 15-09-2025: Demostrated in the Demo/UAT call |  |  |  |  | 1
982 | M307 | MOM | 2023-10-19 |  | OSS | OSS | OSS | Dashboards | Point No. 283: Alert Mechanism (event rule) when power supply is through UPS which is running on Battery backup mode then there should be alert in the form of SMS sent to field team so outages can be avoided or minimized proactively. target date is 15th November ’23. |  | Critical | Open |  |  |  |  | 09-09-2025: It can be enabled based on customer confirmation |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMOSS | Applications/Tools | OPEN | COMPLETED | Pending |  |  |  |  | 1
983 | M308 | MOM | 2023-10-19 |  | OSS | OSS | OSS | Dashboards | Point No. 290: IP MPLS node status report to be automated (Zonal / Mandal/GP) along with Alias Name (Like Actual Mandal /GP names) -Feasibility check required if Alias can be updated & fetched by OSS tool will be informed |  | Critical | Open | [7 empty] | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMOSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1
984 | M309 | MOM | 2023-10-19 |  | OSS | OSS | OSS | Dashboards | Point No. 292: Customised dashboard template with available set of fields for different set of user views by 20th Oct'23 |  | Critical | Open | [7 empty] | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMOSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1
985 | M31 | MOM | 2023-06-07 |  |  |  | GIS | User Experience | Correct Actual Measure Length and Loop length in BOQ |  | NON-Critical | Open |  | Gtech | [5 empty] | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMGIS | Applications/Tools | OPEN | [6 empty] | 1
986 | M310 | MOM | 2023-10-19 |  | OSS | OSS | OSS | Dashboards | Point No. 294: OSS MTTR report to include additional columns like RFO, Sub RFO, Resolution etc. By 20th Oct'23 |  | Critical | Open | [7 empty] | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMOSS | Applications/Tools | OPEN | CLOSURE REVIEW PENDING | 0 |  |  |  |  | 1
987 | M311 | MOM | 2023-10-19 |  | OSS | OSS | OSS | Dashboards | Point No. 296: Service Management dashboard should list planned outages and corelate TT if that is on same device or NW component by 20th Oct'23 |  | Critical | Open | [7 empty] | Suresh Pawar |  | Open | WIP | [9 empty] | MOMOSS | Applications/Tools | OPEN | OPEN | 0 |  |  | #N/A |  | 1
988 | M312 | MOM | 2023-10-19 |  |  |  | Security & Regulatory Compliance | Regulatory Compliance | Point No. 308: IPDR - Developing in-house solution, also exploring with external vendors. to obtain clarity from the Regulator on the requirements, along with the industry best practices. • VP-Program, T-Fiber asked L&T to revert on the next steps by 26th October ’23. |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #VALUE! |  | 1
989 | M313 | MOM | 2023-10-19 |  |  |  | Security & Regulatory Compliance | Regulatory Compliance | Point No. 312: SLA Reporting for Cell Tower and GIs • Head Telecom Networks, L&T mentioned that two approaches are under consideration, solution approach to be finalised, target for completion is 30th November ’23. |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1
990 | M314 | MOM | 2023-10-19 |  | OSS | OSS | OSS | Resource Related | SVP, T-Fiber emphasized the importance of L&T establishing its own resources for the HPE related tasks and they should not rely solely on one individual. |  | Critical | Open |  |  |  |  | 09-09-2025: Taken support from vigility Team |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMOSS | Applications/Tools | OPEN | COMPLETED | 09-09-2025: Taken support from vigility Team |  |  |  |  | 1
991 | M315 | MOM | 2023-10-19 |  |  |  | Security & Regulatory Compliance | User Traceability | Point No. 316: User Traceability,targeted for closure by 15th November ’23. this point to be included in the SOPs for NOC. |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1
992 | M316 | MOM | 2023-10-19 |  |  |  | Security & Regulatory Compliance | Policy Implementation | Point No. 318: Policy Implementation – Network Forensics the process for tracing all incidents including security incidents is yet to be put in place, targeted for 15th November ’23. |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1
993 | M317 | MOM | 2023-10-19 |  |  |  | Security & Regulatory Compliance | Report | Point no. 326: IPDR static IP report SVP, T-Fiber asked for the Regulatory aspects to be discovered by 26th October ’23. |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1
994 | M318 | MOM | 2023-10-19 |  |  |  | Security & Regulatory Compliance | Design features | Point No. 333: Alepo AAA to be integrated with AD SVP, T-Fiber asked for an SOP to be defined for this. • SVP, T-Fiber asked for a note (Note 8) recording this statement. |  | Critical | Open |  |  |  |  | This is Security point |  |  | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1
995 | M319 | MOM | 2023-10-19 |  |  |  | NSO | Design & Documentation | Point No. 343: SDC content to GI – Design document required. Head Telecom Networks, L&T to update on the next steps by 26th October ’23. |  | NON-Critical | Open | [7 empty] | Jayant Madavi |  | Open | Open | [9 empty] | MOMNSO | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
996 | M32 | MOM | 2023-06-07 |  |  |  | GIS | Handbook & SOPs | Detailed validation document |  | NON-Critical | Open |  | Gtech | [5 empty] | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMGIS | Applications/Tools | OPEN | [6 empty] | 1
997 | M320 | MOM | 2023-10-19 |  |  |  | Helpdesk | Demo | Assistant Director-P&E, T-Fiber asked L&T to submit the Helpdesk Compliance report along with a summary with respect to RFP by 23rd October’23 and the Demonstration on Helpdesk NEOX to be scheduled after the compliance report submission. |  | Critical | open |  |  |  | WIP | 11-Sep-25: Same has been Submitted | L&T | Shiva kumar | Siva Kumar |  | Open | WIP | [9 empty] | MOMHelpdesk | Helpdesk (Contact Center) | OPEN | [6 empty] | 1
998 | M321 | MOM | 2023-10-19 |  |  |  | BSS | Development & Unit Testing | Point No. 16: Development and Unit Testing - Service Assurance and trouble tickets To be linked with the points in follow-up with HP for completion by March ’24, with clarity on next steps by 1st week of November. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
999 | M322 | MOM | 2023-10-19 |  |  |  | DR | DNS Switchover | Point No. 79: to confirm that DNS switchover between DC and DR locations should be automatic • Chief Delivery Officer, LTTS updated that this in follow-up with Cisco and CtrlS, next update by 26th October ’23. |  | NON-Critical | Closed |  |  |  |  | [15/09/25] Completed |  |  | Ravi Kishore |  |  | COMPLETED & APPROVED | AD-UT-Tfiber |  | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\DR\Artifact for - T79 | [6 empty] | MOMDR | DR | CLOSED |  |  |  |  | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\DR\Artifact for - T79 |  | 1
1000 | M323 | MOM | 2023-10-19 |  |  |  | DWDM | Integration with OSS | Point No. 103: DWDM-OSS integration - Service Inventory Data Availability in HPE OSS & Point No. 237: DWDM-OSS integration - Service inventory data availability in HPE OSS • Technical Head, L&T updated that this is targeted for closure by 15th November ’23. |  | Critical | Open |  |  |  |  | Duplicate Already covered in 472-points, Ref Point No. 103 & 237 |  |  | Suresh Kumar |  | Open | Duplicate | [9 empty] | MOMDWDM | DWDM | #N/A |  |  | Duplicate |  |  |  | 1
1001 | M324 | MOM | 2023-10-19 |  |  |  | DWDM | Integration with OSS | Point No. 104 – DWDM-OSS integration: Planned Event Service Impact analysis report & Point No. 238: DWDM-OSS integration: For planned event service impact analysis data / report SVP, T-Fiber asked for the SOP that shall be put in place by L&T until the Service Inventory solution from HP is in place |  | Critical | Open |  |  |  |  | Duplicate Already covered in 472-points, Ref Point No. 104& 238 |  |  | Suresh Kumar |  | Open | Duplicate | [9 empty] | MOMDWDM | DWDM | #N/A |  |  | Duplicate |  |  |  | 1
1002 | M325 | MOM | 2023-10-19 |  | OSS | OSS | OSS | Integration | Point No. 231: Ciena DWDM Network Topology has been created in HPE OSS topology MAP along with neighbour NE details. SVP, T-Fiber suggested that this requirement may be revisited later. |  | Critical | Open | [7 empty] | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMOSS | Applications/Tools | OPEN | CLOSURE REVIEW PENDING | 0 |  |  |  |  | 1
1003 | M326 | MOM | 2023-10-19 |  | OSS | OSS | OSS | Design Features | Point No. 259: OSS E2E Topology it will be completed by 30th December’23 |  | Critical | Open |  |  |  |  | This point is already covered under point no. 584. and Point no. 633 under 472 tracker column |  |  | Suresh Pawar |  | Open | Duplicate | [9 empty] | MOMOSS | Applications/Tools | OPEN | DUPLICATE | This point is already covered under point no. 584. and Point no. 633 under 472 tracker column |  |  | #N/A |  | 1
1004 | M327 | MOM | 2023-10-19 |  | OSS | OSS | OSS | Dashboards | Point No. 275: In OSS management dashboard, Block count should count only Mandal OLTs and not GP OLTs target date as 30th December ’23. |  | Critical | Open | [7 empty] | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMOSS | Applications/Tools | OPEN | CLOSURE REVIEW PENDING | 0 |  |  |  |  | 1
1005 | M328 | MOM | 2023-10-19 |  | OSS | OSS | OSS | Design Features | Point No. 281: Problem Management report for various recurring outages for the given period target date as 30th December ’23 |  | Critical | Open | [7 empty] | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMOSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1
1006 | M329 | MOM | 2023-10-19 |  | OSS | OSS | OSS | Design Features | Point No. 287: Exact SPAN/Link details must be taken from GIS (Including Lat, Long) for Fiber cut/outage scenario to understand fix is permanent or temporary in nature and impact on Multiple Nodes/GP’s. |  | Critical | Open | [7 empty] | Suresh Pawar |  | Open | Not Feasible | [9 empty] | MOMOSS | Applications/Tools | #N/A | OPEN | 0 |  |  | #N/A |  | 1
1007 | M33 | MOM | 2023-06-07 |  |  |  | GIS | User Experience | Hyperlink real images to GPs and Mandals |  | Critical | Open |  | Gtech | [5 empty] | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMGIS | Applications/Tools | OPEN | [6 empty] | 1
1008 | M330 | MOM | 2023-10-19 |  | OSS | OSS | OSS | Dashboards | Point No. 288: Report for Backup Status (success/failure) of all VM (source it from Vcenter Report) L&T to conclude discussions with HP to obtain the target date. |  | Critical | Open |  |  |  |  | 09-09-2025: managed at vmware(comvault) by DCInfra Team |  |  | Suresh Pawar |  | Open | Not Feasible | [9 empty] | MOMOSS | Applications/Tools | #N/A | NOT-FEASIBLE | 09-09-2025: managed at vmware(comvault) by DCInfra Team |  |  | #N/A |  | 1
1009 | M331 | MOM | 2023-10-19 |  | OSS | OSS | OSS | Dashboards | Point No. 289: DC Active infra-Health check-up /Utilization and Resource Availability report L&T to conclude discussions with HP to obtain the target date. |  | Critical | Open | [7 empty] | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMOSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1
1010 | M332 | MOM | 2023-10-19 |  | OSS | OSS | OSS | Dashboards | Point No. 293: Service VLAN status report from EMS (Nokia and Tejas) Technical Head, L&T to conclude discussions to obtain the target date. |  | Critical | Open |  |  |  |  | It will be available from intranet portal |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMOSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  | #N/A |  | 1
1011 | M333 | MOM | 2023-11-03 |  |  |  | BSS | Service provisioning | UD,SD Peramaters to be captured. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1012 | M334 | MOM | 2023-11-03 |  |  |  | NSO | Service provisioning | NSo inventory manager funtionality to check. |  | Critical | Open | [7 empty] | Jayant Madavi |  | Open | Open | [9 empty] | MOMNSO | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1013 | M335 | MOM | 2023-11-03 |  |  |  | BSS | Service provisioning | UD perameters for product based to be prepared. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1014 | M336 | MOM | 2023-11-03 |  |  |  | BSS | Service provisioning | Ashish to comeback with Design plan for Inventory Manager at NSO |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1015 | M337 | MOM | 2023-11-03 |  |  |  | BSS | Service provisioning | Arvindam to comeback with product wise UD perameters |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1016 | M338 | MOM | 2023-11-03 |  |  |  | BSS | Service provisioning | Additional information for VRF, VLAN , Inner vlan etc to capture in Master DB |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1017 | M339 | MOM | 2023-11-03 |  |  |  | BSS | Service provisioning | As per Cisco LLD All 28 types of L2, L3 models to be mapped aginest products |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1018 | M34 | MOM | 2023-06-07 |  |  |  | GIS | Installation | 100TB storage for LIDAR survey data |  | Critical | Open | Conflict | Gtech | [5 empty] | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMGIS | Applications/Tools | OPEN | [6 empty] | 1
1019 | M340 | MOM | 2023-11-03 |  |  |  | BSS | Service Codes | GL code to be mapped based on subtype GI under sub type Central & State |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1020 | M341 | MOM | 2023-11-03 |  |  |  | BSS | Service Codes | Define the Code for Circuit type , Customer type , customer service type etc in single format |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1021 | M342 | MOM | 2023-11-03 |  |  |  | BSS | Service Codes | Define design plan for House hold services in GPON Level |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1022 | M343 | MOM | 2023-11-03 |  |  |  | BSS | Service Codes | Define Household plan for provisioning as per the GPON plan design |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1023 | M344 | MOM | 2023-11-03 |  |  |  | BSS | Service Codes | OSS Method of distance from GIS need to comeback with plan |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1024 | M345 | MOM | 2023-11-03 |  |  |  | BSS | Service Codes | Aravindam to update on previous meetings updates to be updated in next in continuous meetings |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1025 | M346 | MOM | 2023-11-17 |  |  |  | Helpdesk | Demo | Neox helpdesk Demo : |  | Critical | Open |  |  |  | WIP |  |  |  | Siva Kumar |  | Open | WIP | [9 empty] | MOMHelpdesk | Helpdesk (Contact Center) | OPEN | [6 empty] | 1
1026 | M347 | MOM | 2023-11-17 |  |  |  | Helpdesk | Compliance | Neox Compliance confirmation : |  | Critical | open |  |  |  | WIP | 11-Sep-25: Same has been Submitted | L&T | Shiva kumar | Siva Kumar |  | Open | WIP | [9 empty] | MOMHelpdesk | Helpdesk (Contact Center) | OPEN | [6 empty] | 1
1027 | M348 | MOM | 2023-11-17 |  |  |  | NOC Operationalization | Action Points | 370 points out of which 24 points which are already covered in 370 : Praveen to share indicating the reference of 24 points by |  | Critical | Closed |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1
1028 | M349 | MOM | 2023-11-17 |  |  |  | NOC Operationalization | Action Points | 196 points closure along with artefacts : |  | Critical | Closed |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1
1029 | M35 | MOM | 2023-06-07 |  |  |  | GIS | Training | Hands-on Training on GIS tool |  | NON-Critical | Open |  | Gtech | [5 empty] | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMGIS | Applications/Tools | OPEN | [6 empty] | 1
1030 | M350 | MOM | 2023-11-17 | P3 |  |  | NOC Operationalization | Documentation | Revised Organization structure : |  | Critical | Completed |  |  |  |  | NOC structure and manpower details shared |  |  | Ahmad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  | Not related to delivery | 2025-09-19 | Artefacts not Required |  | 1
1031 | M351 | MOM | 2023-11-17 |  |  |  | BSS | Demo | Second Dry Run (details to be shared later) : week starting |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1032 | M352 | MOM | 2023-11-17 |  |  |  | NOC Operationalization | Documentation | Artefacts storage link : |  | Critical | Completed |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1
1033 | M353 | MOM | 2023-11-17 |  |  |  | Security & Regulatory Compliance | Regulatory Compliance | Security Assessment Review Meeting : week starting |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1
1034 | M354 | MOM | 2023-11-17 |  |  |  | NOC Operationalization | Resource Related | HP & Cisco OEM teams onboarding from 20th November'23. |  | Critical | Closed |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1
1035 | M355 | MOM | 2023-11-17 |  |  |  | NOC Operationalization | Documentation | Letter from all OEMs apart from Cisco & HP to be submitted by 22nd November'23 |  | Critical | Open |  |  |  | Closed, Artefacts to be uploaded | 23-Sep-25: Approved Artefacts to be Submitted | L&T | Sivaprasad | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  |  | Artefacts Need to upload |  | 1
1036 | M356 | MOM | 2023-11-17 |  |  |  | NOC Operationalization | Documentation | Letter from from Cisco & HP to be submitted by 24th November'23 |  | Critical | Open |  |  |  | Closed, Artefacts to be uploaded | 23-Sep-25: Approved Artefacts to be Submitted | L&T | Sivaprasad | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  |  | Artefacts Need to upload |  | 1
1037 | M357 | MOM | 2023-11-17 |  |  |  | NOC Operationalization | Documentation | Letter of confirmation for closure of issues with Tejas & Nokia on or before 30th November’23 |  | Critical | Open |  |  |  | Closed, Artefacts to be uploaded | 23-Sep-25: Approved Artefacts to be Submitted | L&T | Sivaprasad | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  |  | Artefacts Need to upload |  | 1
1038 | M358 | MOM | 2023-11-17 |  |  |  | NOC Operationalization | Meeting | Date for All OEMs Meeting |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1
1039 | M359 | MOM | 2023-11-17 |  |  |  | BSS | Resource Related | BSS-SME visit & extended stay for backlog clearance and sharing agenda prior to visit |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1040 | M36 | MOM | 2023-06-07 |  |  |  | GIS | Dashboards | Discuss and Develop Dashboard for GIS tool |  | NON-Critical | Open |  | Gtech | [5 empty] | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMGIS | Applications/Tools | OPEN | [6 empty] | 1
1041 | M360 | MOM | 2023-11-17 |  |  |  | NOC Operationalization | Documentation | Revert pending on 8 Notes(Undertaking) |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1
1042 | M361 | MOM | 2023-11-17 |  |  |  | Helpdesk | Resource Related | Dimensioning of Helpdesk calls |  | Critical | open |  |  |  | Closed | 24-Sep-25: Approved and shall be closed 11-Sep-25: Changed and operational Now |  |  | Siva Kumar |  |  | COMPLETED & APPROVED | [9 empty] | MOMHelpdesk | Helpdesk (Contact Center) | CLOSED |  |  |  | 2025-09-24 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\M117,126,728 |  | 1
1043 | M362 | MOM | 2023-11-17 | P3 |  |  | NOC Operationalization | Documentation | Revert on 26 SOPS & O&M Handbook |  | Critical | Open |  |  |  |  | SOP agreed and signed off. O&M Handbook WIP |  |  | Ahmad | 2025-10-07 | Open | Open | [9 empty] | MOMNOC Operationalization | Network | OPEN |  |  | Documentation |  | #N/A |  | 1
1044 | M363 | MOM | 2023-11-17 | P3 |  |  | NOC Operationalization | Documentation | Measurable KPI for individual TNOC team |  | Critical | Completed |  |  |  |  | NOC role KRA and KPI submitted to TFiber |  |  | Ahmad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  | Not related to delivery | 2025-09-24 | \\172.28.9.23\tnocreports\TNOC Manpower_CVs\NOC Resources Details & Roles |  | 1
1045 | M364 | MOM | 2023-11-17 | P3 |  |  | NOC Operationalization | Resource Related | Service delivery & Service assurance Manager |  | Critical | Completed |  |  |  |  | Not part of RFP. Service Provisioning is being done by NOC team |  |  | Ahmad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  | Not related to delivery | 2025-09-19 | Artefacts not Required |  | 1
1046 | M365 | MOM | 2023-11-17 | P3 |  |  | NOC Operationalization | Resource Related | Plan for Manpower augmentation to handle Infra Alarm in TNOC & field to finalize O&M |  | Critical | Completed |  |  |  |  | NOC manpower is deputed as per RFP and manpower report is shared with TFiber on weekly basis |  |  | Ahmad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  | Not related to delivery | 2025-09-19 | Artefacts not Required |  | 1
1047 | M366 | MOM | 2023-11-17 |  |  |  | BSS | Dry Run | BSS product system readiness for usage |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1048 | M367 | MOM | 2023-11-17 |  |  |  | NOC Operationalization | Resource Related | Additional resources for fast tracking of project |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1
1049 | M368 | MOM | 2023-11-28 |  |  |  | NOC Operationalization | Meeting | L&T to communicate with OEMs and arrange a meeting on behalf of T-Fiber. 1. To seek evidence from L&T on the commitment from respective OEMs of BSS, OSS, NSO, GIS, GPON on closure of gaps identified so far, related to the operationalization of various systems along with firm dates for delivery from respective OEMs for the same. 2. L&T to provide a plan on how the NOC O&M will be handled with SOPs where relevant in the interim period. 3. How L&T transitions the systems from the interim to the final state without any business impact while ensuring data integrity. |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1
1050 | M369 | MOM | 2023-11-28 |  |  |  | Security & Regulatory Compliance | Regulatory Compliance | Fast-track track closure of Regulatory and security requirements along with SLA monitoring for the immediate start of Business related to Cell Tower, GI BB, GI ILL & VPN service delivery. |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1
1051 | M37 | MOM | 2023-06-07 |  |  |  | GIS | User Experience | New validation Logic to be incorporated in DI tool - if Depth is zero and construction method is HDD/OT, Protection is required |  | NON-Critical | Open |  | Gtech | [5 empty] | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMGIS | Applications/Tools | OPEN | [6 empty] | 1
1052 | M370 | MOM | 2023-11-28 |  |  |  | NOC Operationalization | Demo | L&T to prepare and execute the next DRY run effectively. |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1
1053 | M371 | MOM | 2023-11-28 |  |  |  | NOC Operationalization | Documentation | L&T to develop a comprehensive presentation on product readiness and NOC operationalization schedule. |  | Critical | Completed |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1
1054 | M372 | MOM | 2023-12-12 |  |  |  | Security & Regulatory Compliance | RMC meeting | Submit Acceptable Usage Policy document with suggested changes |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1
1055 | M373 | MOM | 2023-12-12 |  |  |  | Security & Regulatory Compliance | RMC meeting | Complete the configuration of CA signed SSL certificate |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1
1056 | M374 | MOM | 2023-12-12 |  |  |  | Security & Regulatory Compliance | RMC meeting | Concur with T-Fiber for annual external VAPT testing |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1
1057 | M375 | MOM | 2023-12-12 |  |  |  | Security & Regulatory Compliance | RMC meeting | Submit Vulnerability Management Policy |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1
1058 | M376 | MOM | 2023-12-12 |  |  |  | Security & Regulatory Compliance | RMC meeting | List and share the Security Policy documents and SOPS |  | Critical | Open |  |  |  |  | Docs List is shared |  |  | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1
1059 | M377 | MOM | 2023-12-12 |  |  |  | Security & Regulatory Compliance | RMC meeting | Upload all RMC MoMs to the shared folder and share access |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1
1060 | M378 | MOM | 2023-12-12 |  |  |  | Security & Regulatory Compliance | RMC meeting | Submit Asset Management policy |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1
1061 | M379 | MOM | 2023-12-12 |  |  |  | Security & Regulatory Compliance | RMC meeting | Submit onboarding/offboarding policy |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1
1062 | M38 | MOM | 2023-06-15 |  |  |  | BSS | Resource Related | Billing Expert onboarding |  | Critical | Open |  | Billing | [5 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1063 | M380 | MOM | 2023-12-12 |  |  |  | Security & Regulatory Compliance | RMC meeting | Submit scope of work for External VAPT |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1
1064 | M381 | MOM | 2023-12-12 |  |  |  | Security & Regulatory Compliance | RMC meeting | Collect Cryptography encryption model document from all OEMs |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1
1065 | M382 | MOM | 2023-12-12 |  |  |  | Security & Regulatory Compliance | RMC meeting | Submit the revised undertaking for Tejas - Alepo and Nokia |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1
1066 | M383 | MOM | 2023-12-12 |  |  |  | Security & Regulatory Compliance | RMC meeting | Provide compliance documents for all applications and devices |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1
1067 | M384 | MOM | 2023-12-12 |  |  |  | Security & Regulatory Compliance | RMC meeting | Submit document on Privilege management |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1
1068 | M385 | MOM | 2023-12-12 |  |  |  | Security & Regulatory Compliance | RMC meeting | Submit password management policy |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1
1069 | M386 | MOM | 2023-12-12 |  |  |  | Security & Regulatory Compliance | RMC meeting | Submit artefacts for all banners |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1
1070 | M387 | MOM | 2023-12-12 |  |  |  | Security & Regulatory Compliance | RMC meeting | Submit internal/external, Trusted, untrusted zone checklist |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1
1071 | M388 | MOM | 2023-12-12 |  |  |  | Security & Regulatory Compliance | RMC meeting | Submit internal network policies details |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1
1072 | M389 | MOM | 2023-12-12 |  |  |  | Security & Regulatory Compliance | RMC meeting | Submit SSL implementation report for all APIs |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1
1073 | M39 | MOM | 2023-06-15 |  |  |  | BSS | Handbook & SOPs | State of maturity of all Business process flows mentioned in the HLD |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1074 | M390 | MOM | 2023-12-12 |  |  |  | Security & Regulatory Compliance | RMC meeting | Submit Acceptable Usage Policy |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1
1075 | M391 | MOM | 2023-12-12 |  |  |  | Security & Regulatory Compliance | RMC meeting | Submit Security endpoints list of Infra, workstations |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1
1076 | M392 | MOM | 2023-12-12 |  |  |  | Security & Regulatory Compliance | RMC meeting | Submit SOP for security policies |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1
1077 | M393 | MOM | 2023-12-12 |  |  |  | Security & Regulatory Compliance | RMC meeting | Submit DR reports for all Applications |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1
1078 | M394 | MOM | 2023-12-12 |  |  |  | Security & Regulatory Compliance | RMC meeting | Submit attendance list for security awareness trainings |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1
1079 | M395 | MOM | 2023-12-12 |  |  |  | Security & Regulatory Compliance | RMC meeting | Finalize backup duration and frequency, and provide utilization report |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1
1080 | M396 | MOM | 2023-12-12 |  |  |  | Security & Regulatory Compliance | RMC meeting | Submit a report capturing online and offline storage status |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1
1081 | M397 | MOM | 2023-12-12 |  |  |  | Security & Regulatory Compliance | RMC meeting | Finalize Technology Risk Management checklist |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1
1082 | M398 | MOM | 2023-12-12 |  |  |  | Security & Regulatory Compliance | RMC meeting | Further audit and VAPT by Allied Boston |  | Critical | Open |  |  |  |  | Audit done by Allied Boston |  |  | Sarmendra |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | Artefacts to be Submitted |  | 1
1083 | M399 | MOM | 2023-12-15 |  |  |  | WFM | Mobile Application | Arrange a demonstration of WFM Tool for field operations |  | Critical | Open |  |  |  |  | Duplicate with Point- 235 |  |  | Kaushalendra Kumar |  | Open | Duplicate | [9 empty] | MOMWFM | Applications/Tools | #N/A |  |  |  |  | #N/A |  | 1
1084 | M4 | MOM | 2023-03-27 |  |  |  | BSS | Service provisioning | BSS-based provisioning for regularizing 3000 GI through NOC BSS, with scalability to 30,000 GIs. |  | Critical | Open |  | OSS Dashboards | [5 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1085 | M40 | MOM | 2023-06-19 |  |  |  | GIS | User Experience | Download active port connectivity details |  | Critical | Open | Conflict | Gtech |  |  | Link Trace Report Download |  |  | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMGIS | Applications/Tools | OPEN | [6 empty] | 1
1086 | M400 | MOM | 2023-12-15 |  |  |  | WFM | Mobile Application | Clarity on GPS tracking availability and battery consumption |  | Critical | Open | [7 empty] | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMWFM | Applications/Tools | OPEN | [6 empty] | 1
1087 | M401 | MOM | 2023-12-15 |  |  |  | WFM | Mobile Application | WFM Mobile App Features: L&T to provide clarity on GPS tracking availability, polling frequency, photo upload feature, file size limitations, and supported Android and iOS versions. |  | Critical | Open | [7 empty] | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMWFM | Applications/Tools | OPEN | [6 empty] | 1
1088 | M402 | MOM | 2023-12-15 |  |  |  | WFM | Mobile Application | Clarify on photo upload feature and impact on mobile phone memory |  | NON-Critical | Open | [7 empty] | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMWFM | Applications/Tools | OPEN | [6 empty] | 1
1089 | M403 | MOM | 2023-12-15 |  |  |  | WFM | Mobile Application | Clarity on offline data storage feature availability |  | NON-Critical | Open |  |  |  |  | 11-7-2025:- Offline data, such as images and documents, can be uploaded either from the mobile gallery or directly using the camera. To support the storage of LIDAR survey data and GIS images, an 80 TB NAS storage system has already been deployed at the NOC Data Center |  |  | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMWFM | Applications/Tools | OPEN | [6 empty] | 1
1090 | M404 | MOM | 2023-12-15 |  |  |  | WFM | Mobile Application | Clarity on file size limitations during upload |  | NON-Critical | Open | [7 empty] | Kaushalendra Kumar |  | Open | Open | [9 empty] | MOMWFM | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1091 | M405 | MOM | 2023-12-15 |  |  |  | WFM | Mobile Application | The urgency for L&T to demonstrate the WFM tool for field operations and to provide detailed information on its features and capabilities. |  | NON-Critical | Open | [7 empty] | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMWFM | Applications/Tools | OPEN | [6 empty] | 1
1092 | M406 | MOM | 2023-12-15 |  |  |  | WFM | Mobile Application | Clarify the usage differences between GIS and WFM mobile apps |  | NON-Critical | Open | [7 empty] | Kaushalendra Kumar |  | Open | Open | [9 empty] | MOMWFM | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1093 | M407 | MOM | 2023-12-15 |  |  |  | WFM | Mobile Application | Security Assurance: L&T to provide the NDA signed with M/S Lepton, assure API security, and share the contract copy. |  | NON-Critical | Open | [7 empty] | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMWFM | Applications/Tools | OPEN | [6 empty] | 1
1094 | M408 | MOM | 2023-12-15 |  |  |  | WFM | Mobile Application | Geo-fencing: L&T to explain how geo-fencing shall work for a fiber route and how it will be assigned for Mandal and GP locations. |  | Critical | Open | [7 empty] | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMWFM | Applications/Tools | OPEN | [6 empty] | 1
1095 | M409 | MOM | 2023-12-15 |  |  |  | WFM | Mobile Application | Ticket Allocation: L&T to start manual ticket allocation and freeze the process for node and link ticket allocation. |  | Critical | Open | [7 empty] | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMWFM | Applications/Tools | OPEN | [6 empty] | 1
1096 | M41 | MOM | 2023-06-19 |  |  |  | GIS | User Experience | Real-time sync of topology details from OSS |  | Critical | Open |  | Gtech | [5 empty] | Kaushalendra Kumar |  | Open | WIP | [9 empty] | MOMGIS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1097 | M410 | MOM | 2023-12-15 |  |  |  | WFM | Mobile Application | Ticket Allocation: L&T to start manual ticket allocation and freeze the process for node and link ticket allocation. |  | NON-Critical | Open | [7 empty] | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMWFM | Applications/Tools | OPEN | [6 empty] | 1
1098 | M411 | MOM | 2023-12-15 |  |  |  | WFM | Mobile Application | Use of document forms from the Operations Handbook by the WFM app |  | Critical | Open | [7 empty] | Kaushalendra Kumar |  | Open | Open | [9 empty] | MOMWFM | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1099 | M412 | MOM | 2023-12-15 |  |  |  | WFM | Mobile Application | Summary Dashboards/Management Reports: L&T to provide inputs based on Operations best practices for weekly/monthly management reports from the WFM package. |  | Critical | Open | [7 empty] | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMWFM | Applications/Tools | OPEN | [6 empty] | 1
1100 | M413 | MOM | 2023-12-19 |  |  |  | WFM | Mobile Application | WFM Tool Demonstration: L&T to arrange a demonstration of the WFM tool usage for field operations soon. |  | Critical | Open | [7 empty] | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMWFM | Applications/Tools | OPEN | [6 empty] | 1
1101 | M414 | MOM | 2023-12-19 |  |  |  | BSS | Improvement | Investigate and expedite the issue on slowness of BSS Test Environment |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1102 | M415 | MOM | 2023-12-19 |  |  |  | BSS | Dashboards | Explore web-based Analytic tools for performance benchmarking |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1103 | M416 | MOM | 2023-12-19 |  |  |  | BSS | Compliance | Review the status of points with "No Change" status and obtain T-Fiber's consensus before rendering items as "Closed". |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1104 | M417 | MOM | 2023-12-19 |  |  |  | BSS | Improvement | Verify the feature allowing multiple locations per customer |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1105 | M418 | MOM | 2023-12-19 |  |  |  | BSS | Improvement | Cross-reference user experience feedback with related points |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1106 | M419 | MOM | 2023-12-19 |  |  |  | BSS | SMS Integration | Implement notification of SMS dispatch in the CSP and provision of a link in SMS to the CSP page allowing T-Fiber user to Approve or Reject |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1107 | M42 | MOM | 2023-06-19 |  |  |  | GIS | User Experience | automate active connectivity within site with logical link name populated from OSS |  | Critical | Open |  | Gtech |  |  | Based on discussions with the OSS and GIS teams, integration is not feasible, and automation of connectivity cannot be implemented, 11th July 2025, a discussion is needed with Siva Sir to explore in-house solution possibilities. |  |  | Kaushalendra Kumar |  | Open | Not Feasible | [9 empty] | MOMGIS | Applications/Tools | #N/A |  |  |  |  | #N/A |  | 1
1108 | M420 | MOM | 2023-12-19 |  |  |  | BSS | Product Demo | Provide a demo to showcase product catalogue configurability |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1109 | M421 | MOM | 2023-12-19 |  |  |  | BSS | Product Demo | Provide a demo of Backend Validation and share a document with the steps for validation |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1110 | M422 | MOM | 2023-12-19 |  |  |  | BSS | Product Demo | Address the delay in data load due to system limitation in the production instance |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1111 | M423 | MOM | 2023-12-19 |  |  |  | BSS | Product Demo | Define a benchmark for page loading, login, browsing, and payment scenarios |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1112 | M424 | MOM | 2023-12-19 |  |  |  | BSS | Product Demo | Review the status of Point no. 52 from Dry Run 1 with a demo |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1113 | M425 | MOM | 2023-12-19 |  |  |  | BSS | Product Demo | Ensure uniform colour coding across the website |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1114 | M426 | MOM | 2023-12-19 |  |  |  | BSS | Product Demo | Address the change of website heading for customer dashboards prior to moving into production |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1115 | M427 | MOM | 2023-12-19 |  |  |  | BSS | Product Demo | Arrange for a demo of current products since significant time has passed since the Dry Run |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1116 | M428 | MOM | 2023-12-19 |  |  |  | BSS | Product Demo | Show the flows of Dark Fiber with BSS and WFM |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1117 | M429 | MOM | 2023-12-19 |  |  |  | BSS | Product Demo | Hold discussions for T-Cell product integration with respective OEMs |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1118 | M43 | MOM | 2023-06-19 |  |  |  | GIS | Functional AT Plan | TPA to validate active-active connectivity |  | Critical | Open | Conflict | Gtech | [5 empty] | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMGIS | Applications/Tools | OPEN | [6 empty] | 1
1119 | M430 | MOM | 2023-12-19 |  |  |  | BSS | Product Demo | Complete T-Cell, T-VPN, and GI-ILL |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1120 | M431 | MOM | 2023-12-19 |  |  |  | BSS | Product Demo | Address delay in support for enabling newer products |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1121 | M432 | MOM | 2023-12-19 |  |  |  | BSS | Product Demo | Complete T-Cell, T-VPN and GI-ILL on priority before impending visit to NOC by Hon’ Minister |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1122 | M433 | MOM | 2023-12-19 |  |  |  | BSS | Product Demo | Include headers and check across pages in the CSP |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1123 | M434 | MOM | 2023-12-19 |  |  |  | BSS | Product Demo | Start working on the CSP for listed schools |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1124 | M435 | MOM | 2023-12-19 |  |  |  | BSS | Product Demo | Clarify scenario where GP location is feasible, whereas the feasibility of end customer location is yet to be ascertained |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1125 | M436 | MOM | 2023-12-19 |  |  |  | BSS | Product Demo | Include feasibility logic for S1, and S2 splitters |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1126 | M437 | MOM | 2023-12-19 |  |  |  | BSS | Product Demo | Present the logic for Bandwidth feasibility in the backhaul, network capacity planning to be progressively provisioned, and operationalised |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1127 | M438 | MOM | 2023-12-19 |  |  |  | BSS | Improvement | Address immediate need for NSO inventory to be part of the final solution for feasibility |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1128 | M439 | MOM | 2023-12-19 |  |  |  | BSS | Resource Related | Ask Segment Head, L&T to discuss with EVP, T-Fiber on the adequacy of NMS works resources |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN | [6 empty] | 1
1129 | M44 | MOM | 2023-06-19 |  |  |  | GIS | User Experience | Add card/module/slot level details |  | Critical | Open |  | Gtech |  |  | Duplicate with Point- 90 |  |  | Kaushalendra Kumar |  | Open | Duplicate | [9 empty] | MOMGIS | Applications/Tools | #N/A |  |  |  |  | #N/A |  | 1
1130 | M440 | MOM | 2023-12-19 |  |  |  | BSS | Improvement | Clarify that Repository Module for Uploading of MSA, CAF form and other documents of a particular customer is in CRM, not in CSP |  | NON-Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1131 | M441 | MOM | 2023-12-19 |  |  |  | BSS | Integration | Incorporate advanced features in the CSP's WhatsApp Integration |  | NON-Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1132 | M442 | MOM | 2023-12-19 |  |  |  | BSS | User Experience | On-board an internal UI/UX resource and engage them with T-Fiber |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1133 | M443 | MOM | 2023-12-28 |  |  |  | BSS | Product Demo | Complete T-VPN and T-DILL |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1134 | M444 | MOM | 2023-12-28 |  |  |  | BSS | Product Demo | Complete basic products by |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1135 | M445 | MOM | 2023-12-28 |  |  |  | BSS | Product Demo | Complete GI-BB, T-Cell, Dark Fiber |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1136 | M446 | MOM | 2023-12-28 |  | OSS | OSS | OSS | HPSM | Remove duplicate TroubleTicket issue |  | Critical | Open | [7 empty] | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMOSS | Applications/Tools | OPEN | CLOSURE REVIEW PENDING | 0 |  |  |  |  | 1
1137 | M447 | MOM | 2023-12-28 |  |  |  | Security & Regulatory Compliance | Regulatory Compliance | Finalize scope of external audit in consultation with T-Fiber |  | Critical | Open |  |  |  |  | Audit done by Allied Boston |  |  | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1
1138 | M448 | MOM | 2023-12-28 |  |  |  | Security & Regulatory Compliance | Regulatory Compliance | Conduct external audit |  | Critical | Open |  |  |  |  | Audit done by Allied Boston |  |  | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1
1139 | M449 | MOM | 2023-12-28 |  |  |  | Helpdesk | Training | Improve maturity of Helpdesk to handle incoming calls |  | Critical | Open |  |  |  | Closed | 24-Sep-25: Approved and shall be closed |  |  | Siva Kumar |  |  | COMPLETED & APPROVED | [9 empty] | MOMHelpdesk | Helpdesk (Contact Center) | CLOSED |  |  |  | 2025-09-24 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\M114,722,134 |  | 1
1140 | M45 | MOM | 2023-06-19 |  |  |  | GIS | User Experience | Ensure Topology name uniqueness |  | Critical | Open | Conflict | Gtech |  |  | Duplicate with Point- 128 |  |  | Kaushalendra Kumar |  | Open | Duplicate | [9 empty] | MOMGIS | Applications/Tools | #N/A |  |  |  |  | #N/A |  | 1
1141 | M450 | MOM | 2023-12-28 |  | OSS | OSS | OSS | HPSM | Freeze the process for node ticket allocation |  | Critical | Open | [7 empty] | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMOSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1
1142 | M451 | MOM | 2023-12-28 |  |  |  | NOC Operationalization | Action Points | Cover all requirements from workshops, RFP, and discussions in the roadmap |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1
1143 | M452 | MOM | 2023-12-28 |  | OSS | OSS | OSS | Action Points | Generate SLA reports automatically from NOC |  | Critical | Open | [7 empty] | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMOSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  | #N/A |  | 1
1144 | M453 | MOM | 2023-12-28 |  |  |  | NOC Operationalization | Action Points | Submit a Roadmap covering all requirements raised in all Workshops, the RFP requirements, the 396-point Worksheet maintained by L&T, and all the discussions |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1
1145 | M454 | MOM | 2023-12-28 |  |  |  | NOC Operationalization | Action Points | Explore templates from BBNL NOC for invoice settlement |  | Critical | Open |  |  |  | Will be discussed later | 23-Sep-25: NON Critical to be reviewd later | L&T | Sivaprasad | Sivaprasad |  | Open | Open | [9 empty] | MOMNOC Operationalization | Network | OPEN | [6 empty] | 1
1146 | M455 | MOM | 2023-12-28 |  | OSS | OSS | OSS | HPSM | Ensure cross-domain RCA, SIA, Helpdesk and Network Service Topology are in place |  | Critical | Open |  |  |  |  | Inhouse solution |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMOSS | Applications/Tools | OPEN | COMPLETED | Pending |  |  | #N/A |  | 1
1147 | M456 | MOM | 2023-12-28 |  |  |  | NOC Operationalization | Action Points | Deliver NOC before the end of T3 |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMNOC Operationalization | Network | OPEN | [6 empty] | 1
1148 | M457 | MOM | 2024-01-04 |  | OSS | OSS | OSS | HPSM | Implement ticket tracking with OSS Service Manager |  | Critical | Open | [7 empty] | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMOSS | Applications/Tools | OPEN | CLOSURE REVIEW PENDING | 0 |  |  |  |  | 1
1149 | M458 | MOM | 2024-01-04 |  |  |  | BSS | Product category | Complete T-DILL & T-VPN |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1150 | M459 | MOM | 2024-01-04 |  |  |  | BSS | Product category | Discuss network design for T-DILL with AD-P&E, T-Fiber & IPMPLS-SME |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1151 | M46 | MOM | 2023-06-19 |  |  |  | GIS | User Experience | BoQ feature to download passive/active devices separately |  | Critical | Open | Conflict | Gtech | [5 empty] | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMGIS | Applications/Tools | OPEN | [6 empty] | 1
1152 | M460 | MOM | 2024-01-04 |  |  |  | NSO | Service Solution | Submit a plan for the completion of the 28 services, along with dependencies |  | Critical | Open | [7 empty] | Jayant Madavi |  | Open | Open | [9 empty] | MOMNSO | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1153 | M461 | MOM | 2024-01-04 |  |  |  | BSS | Product category | Conduct a product discussion audit |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1154 | M462 | MOM | 2024-01-04 |  |  |  | BSS | Product category | Submit evidence on commitment from OEMs for integration of various systems with BSS |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1155 | M463 | MOM | 2024-01-04 |  |  |  | NSO | Service Solution | Submit a road map for the completion of the 28 services and all variants |  | Critical | Open | [7 empty] | Jayant Madavi |  | Open | Open | [9 empty] | MOMNSO | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1156 | M464 | MOM | 2024-01-04 |  |  |  | NSO | Service Solution | Initiate daily meetings and share progress updates |  | Critical | Open | [7 empty] | Jayant Madavi |  | Open | Open | [9 empty] | MOMNSO | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1157 | M465 | MOM | 2024-01-04 |  |  |  | BSS | Product category | Finalize network design and initiate the implementation of Mandal-to-Mandal and Mandal-to-GP dark fiber process |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1158 | M466 | MOM | 2024-01-04 |  |  |  | BSS | Product category | Prepare for mock audit regarding bill desk integration and prepare a road map for the dry run of T-DILL & T-VPN |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1159 | M467 | MOM | 2024-01-04 |  |  |  | BSS | Product category | Finalize details of services of T3 & T4 |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1160 | M468 | MOM | 2024-01-04 |  | OSS | OSS | OSS | Service Solution | Resolve discrepancies in readiness status of Fault Management, Network Performance Management Security Management, Regulatory Compliances, Service Delivery- Feasibility, DR readiness, and Technical Helpdesk |  | Critical | Open | [7 empty] | Suresh Pawar |  | Open | WIP | [9 empty] | MOMOSS | Applications/Tools | OPEN | OPEN | 0 |  |  | #N/A |  | 1
1161 | M469 | MOM | 2024-01-04 |  |  |  | NOC Operationalization | O&M Strategy | Achieve readiness of all 'T0' NOC functions |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1
1162 | M47 | MOM | 2023-06-19 |  |  |  | GIS | User Experience | Bulk Feasibility closure case reports from GIS |  | Critical | Open |  | Gtech |  |  | To fulfill this requirement, an external feasibility application or tool is needed, as it cannot be achieved within the GIS application, 11 July 2025:- TFIBER is not agreed, asked to take with L&T upper management |  |  | Kaushalendra Kumar |  | Open | Open | [9 empty] | MOMGIS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1163 | M470 | MOM | 2024-01-04 |  |  |  | NOC Operationalization | O&M Strategy | Submit details of remaining services of T3 & T4 |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMNOC Operationalization | Network | OPEN | [6 empty] | 1
1164 | M471 | MOM | 2024-01-04 |  |  |  | NOC Operationalization | O&M Strategy | Start daily meetings and share progress updates |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1
1165 | M472 | MOM | 2024-01-04 |  |  |  | BSS | Product category | Ensure all 29 BSNL locations are loaded for lead to order presentation |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1166 | M473 | MOM | 2024-01-04 |  |  |  | BSS | Product category | Submit confirmation responses along with product notes on all raised points |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1167 | M474 | MOM | 2024-01-05 |  |  |  | BSS | Product category | Review and finalize the Unique ID code convention for various attributes |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1168 | M475 | MOM | 2024-01-05 |  |  |  | BSS | Product category | Provide demo on Circuit ID generation process and integrate it in BSS |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1169 | M476 | MOM | 2024-01-05 |  |  |  | NSO | Service provisioning | Revisit current Circuit ID logic in NSO and define new naming convention |  | Critical | Open | [7 empty] | Jayant Madavi |  | Open | Open | [9 empty] | MOMNSO | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1170 | M477 | MOM | 2024-01-05 |  |  |  | NSO | Service provisioning | Ensure GUI interface to initiate the order from NSO directly |  | Critical | Open | [7 empty] | Jayant Madavi |  | Open | Open | [9 empty] | MOMNSO | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1171 | M478 | MOM | 2024-01-05 |  |  |  | NSO | Service provisioning | Make A&O independent of BSS for generating Circuit ID |  | Critical | Open | [7 empty] | Jayant Madavi |  | Open | Open | [9 empty] | MOMNSO | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1172 | M479 | MOM | 2024-01-05 |  |  |  | NSO | Service provisioning | Circuit ID should distinguish origin system if a new front-end system is introduced |  | Critical | Open | [7 empty] | Jayant Madavi |  | Open | Open | [9 empty] | MOMNSO | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1173 | M48 | MOM | 2023-06-19 |  |  |  | GIS | User Experience | Route path identification through Google |  | Critical | Open | Conflict | Gtech | [5 empty] | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMGIS | Applications/Tools | OPEN | [6 empty] | 1
1174 | M480 | MOM | 2024-01-05 |  |  |  | NSO | Service provisioning | Ensure Circuit ID isn't limited to 6/8 digits; it should follow the industry-recommended approach |  | Critical | Open | [7 empty] | Jayant Madavi |  | Open | Open | [9 empty] | MOMNSO | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1175 | M481 | MOM | 2024-01-05 |  |  |  | BSS | Product category | Provide option to add new Customer ID during onboarding a new customer |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1176 | M482 | MOM | 2024-01-05 |  |  |  | BSS | Product category | Proceed with Payment approach Option 3 including one-time and recurring invoice generation |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1177 | M483 | MOM | 2024-01-05 |  |  |  | BSS | Product category | If purchase order and CAF are already loaded in the CRM and mapped with customer account, the CAF generation and approval process should be skipped |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1178 | M484 | MOM | 2024-01-05 |  |  |  | BSS | Billing Related | L&T and NMSworks to conduct a detailed training session on operational activities of the Billing module post invoice generation |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN | [6 empty] | 1
1179 | M485 | MOM | 2024-01-05 |  |  |  | BSS | Integration | Offer option to perform manual assignment and auto-assignment of Task Tickets |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1180 | M486 | MOM | 2024-01-05 |  |  |  | BSS | Dry Run | Demonstrate the complete Buyer and Seller journey |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1181 | M487 | MOM | 2024-01-05 |  |  |  | BSS | Design & Documentation | Ensure workflows/activities carried outside the BSS system are captured and mapped in BSS process flows |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1182 | M488 | MOM | 2024-01-05 |  |  |  | BSS | Billing Related | Introduce new column in the invoice template to distinguish billing items as ONE TIME or RECURRING |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1183 | M489 | MOM | 2024-01-05 |  |  |  | BSS | Billing Related | Review the solution of automatic QR code generation integration with Clear Tax or any other third party portal |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1184 | M49 | MOM | 2023-06-19 |  |  |  | GIS | User Experience | Network portal search functionality for objects |  | Critical | Open |  | Gtech | [5 empty] | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMGIS | Applications/Tools | OPEN | [6 empty] | 1
1185 | M490 | MOM | 2024-01-05 |  |  |  | BSS | Billing Related | Pending changes suggested by the Finance Director should be incorporated into the invoice template |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1186 | M491 | MOM | 2024-01-05 |  |  |  | BSS | Billing Related | Onboard Pioneer and start generating bills |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1187 | M492 | MOM | 2024-01-05 |  |  |  | BSS | Billing Related | Provide a detailed approach on how BSS is integrated with Bill Desk |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1188 | M493 | MOM | 2024-01-05 |  |  |  | BSS | Billing Related | Finalize bill desk integration-related final solution documents covering aspects suggested by Assistant Director-P&E, T-Fiber |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1189 | M494 | MOM | 2024-01-05 |  |  |  | BSS | Billing Related | Pending discussions from October’23 regarding bill desk integration should be completed |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1190 | M495 | MOM | 2024-01-05 |  |  |  | BSS | Design Features | Schedule a separate session with OEMs regarding Ticketing process through OSS/BSS referring to the current design template |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1191 | M496 | MOM | 2024-01-18 |  |  |  | BSS | Design Features | Finalize the Unique ID code convention for various attributes |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1192 | M497 | MOM | 2024-01-18 |  |  |  | BSS | Design Features | Integrate Circuit ID generation process in BSS |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1193 | M498 | MOM | 2024-01-18 |  |  |  | BSS | Design Features | Discuss and define a new naming convention for Circuit ID |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1194 | M499 | MOM | 2024-01-18 |  |  |  | BSS | Design Features | Review direct order through GUI interface |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1195 | M5 | MOM | 2023-03-27 |  |  |  | NSO | Full NOC Readiness | variance in L2 & L3, requiring time to understand along with NSO & OSS SMEs |  | Critical | Open |  | OSS Dashboards | [5 empty] | Jayant Madavi |  | Open | Open | [9 empty] | MOMNSO | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1196 | M50 | MOM | 2023-06-19 |  |  |  | GIS | User Experience | GIS function for bulk feasibility report |  | Critical | Open |  | Gtech |  |  | To fulfill this requirement, an external feasibility application or tool is needed, as it cannot be achieved within the GIS application,11 July 2025:- TFIBER is not agreed, asked to take with L&T upper management |  |  | Kaushalendra Kumar |  | Open | Open | [9 empty] | MOMGIS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1197 | M500 | MOM | 2024-01-18 |  |  |  | BSS | Design Features | Make dependency of A&O for generating Circuit ID independent of BSS |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1198 | M501 | MOM | 2024-01-18 |  |  |  | BSS | Design Features | Circuit ID should distinguish the origin if a new front-end system is introduced |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1199 | M502 | MOM | 2024-01-18 |  |  |  | BSS | Design Features | Include option to introduce new Customer ID when onboarding a new customer |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1200 | M503 | MOM | 2024-01-18 |  |  |  | BSS | Design Features | Transition from Excel-based format to live data for Lit-up and other relevant data |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1201 | M504 | MOM | 2024-01-18 |  |  |  | BSS | Design Features | Capture whether the network is linear or ring based |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1202 | M505 | MOM | 2024-01-18 |  |  |  | BSS | Design Features | Review and finalize the definition of 'Ready for Service' |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1203 | M506 | MOM | 2024-01-18 |  |  |  | BSS | Design Features | Implement user access control for converting from RFO to RFS in BSS |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1204 | M507 | MOM | 2024-01-18 |  |  |  | BSS | Design Features | Use terms from the industry library for representing 'Ready for Service', etc. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1205 | M508 | MOM | 2024-01-18 |  |  |  | BSS | Design Features | Retry the implementation of the Mandal-to-Mandal and Mandal-to-GP dark fiber process |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1206 | M509 | MOM | 2024-01-18 |  |  |  | BSS | Design Features | Integrate with GIS for live data capturing for feasibility check |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1207 | M51 | MOM | 2023-06-19 |  |  |  | GIS | User Experience | building logic / intelligence to populate the relevant information in the BoQ, presently available as a dump. |  | Critical | Open | Conflict | Gtech | [5 empty] | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMGIS | Applications/Tools | OPEN | [6 empty] | 1
1208 | M510 | MOM | 2024-01-18 |  |  |  | BSS | Design Features | Correct and finalize the changes suggested in the Lead page |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1209 | M511 | MOM | 2024-01-18 |  |  |  | BSS | Design Features | Enable communication to customers via Quote Tab in system |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1210 | M512 | MOM | 2024-01-18 |  |  |  | BSS | Design Features | Review Service order Form and related attributes |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1211 | M513 | MOM | 2024-01-18 |  |  |  | BSS | Design Features | Implement immediate Dark Fiber service for Mandal to GP and Mandal to Mandal |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1212 | M514 | MOM | 2024-01-18 |  |  |  | BSS | Design Features | Bring the approach for Bulk Feasibility into use |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1213 | M515 | MOM | 2024-01-18 |  |  |  | BSS | Design Features | Confirm the list of personnel who will be part of BSS operations |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1214 | M516 | MOM | 2024-01-18 |  |  |  | BSS | Design Features | Solve the issue of Document repository not being tagged with the order number |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1215 | M517 | MOM | 2024-01-18 |  |  |  | BSS | Design Features | Present a lead to order and GIS integration way forward for BSNL locations |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1216 | M518 | MOM | 2024-01-18 |  |  |  | BSS | Design Features | Confirm the timeline for GI-BB |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1217 | M519 | MOM | 2024-01-18 |  |  |  | BSS | Design Features | Confirm the timeline for T-Cell |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1218 | M52 | MOM | 2023-06-19 |  |  |  | GIS | Integration | GIS integration with WFM tool |  | Critical | Open |  | Gtech | [5 empty] | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMGIS | Applications/Tools | OPEN | [6 empty] | 1
1219 | M520 | MOM | 2024-01-18 |  |  |  | BSS | Design Features | Discuss with T-Fiber regarding Route Mode and Bridge Mode for Internet Leased Line product |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1220 | M521 | MOM | 2024-01-24 |  |  |  | NSO | O&M Strategy | Complete basic six products and field O&M |  | Critical | Open | [7 empty] | Jayant Madavi |  | Open | Open | [9 empty] | MOMNSO | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1221 | M522 | MOM | 2024-01-24 |  |  |  | BSS | Design & Documentation | Complete delivery of 24 variant products |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1222 | M523 | MOM | 2024-01-24 |  |  |  | BSS | Design & Documentation | Submit documentation for each of 6 products with respect to flow, regulatory, connectivity to other elements signed off with T-Fiber |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1223 | M524 | MOM | 2024-01-24 |  |  |  | NOC Operationalization | Design & Documentation | Provide final timeline for all conditional approvals & workshop tracker and detailed scope document |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1
1224 | M525 | MOM | 2024-01-24 |  | OSS | OSS | OSS | Design Features | Present the readiness of service inventory module |  | Critical | Open |  |  |  |  | Inhouse solution |  |  | Suresh Pawar |  | Open | WIP | [9 empty] | MOMOSS | Applications/Tools | OPEN | OPEN | 0 |  |  | #N/A |  | 1
1225 | M526 | MOM | 2024-01-24 |  |  |  | NOC Operationalization | Design & Documentation | Share detailed scope document and conditional approvals & workshops tracker |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1
1226 | M527 | MOM | 2024-01-24 |  |  |  | Helpdesk | Helpdesk | Obtain T-Fiber's review in the next two days and submit revised Helpdesk SOPs |  | Critical | open |  |  |  | Closed | 24-Sep-25: Artefcts to be submiited for closure 11-Sep-25: Same has been Submitted |  |  | Siva Kumar |  |  | COMPLETED & APPROVED | [9 empty] | MOMHelpdesk | Helpdesk (Contact Center) | CLOSED |  |  |  | 2025-09-24 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\M1076 |  | 1
1227 | M528 | MOM | 2024-01-24 |  |  |  | NOC Operationalization | O&M Strategy | Discuss and revert all pending points with MD(I/C), T-Fiber, and T-Fiber Operations Team |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1
1228 | M529 | MOM | 2024-01-24 |  |  |  | NSO | Design Features | Provide road map detailing how the 6 products will move from manual process to automation |  | Critical | Open | [7 empty] | Jayant Madavi |  | Open | Open | [9 empty] | MOMNSO | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1229 | M53 | MOM | 2023-06-19 |  |  |  | GIS | User Experience | Automation of active connectivity |  | Critical | Open |  | Gtech |  |  | Duplicate with Point- 145 |  |  | Kaushalendra Kumar |  | Open | Duplicate | [9 empty] | MOMGIS | Applications/Tools | #N/A |  |  |  |  | #N/A |  | 1
1230 | M530 | MOM | 2024-01-24 |  |  |  | NSO | Design Features | Share a plan about how 6 products Dark Fiber, GI-BB, T-Cell, T-VPN, T-Dill will move from manual process to automation |  | Critical | Open | [7 empty] | Jayant Madavi |  | Open | Open | [9 empty] | MOMNSO | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1231 | M531 | MOM | 2024-01-24 |  |  |  | BSS | Design Features | Finalize the readiness of all modules, including ticketing, Helpdesk, full automation, and WFM |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1232 | M532 | MOM | 2024-01-24 |  |  |  | GIS | Design Features | Discuss internally and provide a feasible response about leading the GIS data update process |  | Critical | Open | [7 empty] | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMGIS | Applications/Tools | OPEN | [6 empty] | 1
1233 | M533 | MOM | 2024-01-24 |  |  |  | Helpdesk | Design Features | Arrange Helpdesk toll-free (1800-XXX-XX) number |  | Critical | Open |  |  |  |  | 11-09-2025: Same as T366(472) Closed |  |  | Siva Kumar |  |  | COMPLETED & APPROVED | Yes | 2025-07-19 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\T366 | [6 empty] | MOMHelpdesk | Helpdesk (Contact Center) | CLOSED |  |  |  | 2025-07-19 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\T366 |  | 1
1234 | M534 | MOM | 2024-01-24 |  |  |  | Helpdesk | Design Features | Share finalized notification readiness of SMS, WhatsApp & Email formats for T-Fiber customers |  | Critical | Open |  |  |  | WIP |  |  |  | Siva Kumar |  | Open | WIP | [9 empty] | MOMHelpdesk | Helpdesk (Contact Center) | OPEN | [6 empty] | 1
1235 | M535 | MOM | 2024-01-24 |  |  |  | Helpdesk | Helpdesk | Arrange a demonstration of Helpdesk and IVR functions flow |  | Critical | open |  |  |  | Closed | 23-Sep-25: Demo completed shall be closed 11-Sep-25: Complied, Part of Interim NOC KPI |  |  | Siva Kumar |  |  | COMPLETED & APPROVED | [9 empty] | MOMHelpdesk | Helpdesk (Contact Center) | CLOSED |  |  |  | 2025-09-24 | Artefacts not Required |  | 1
1236 | M536 | MOM | 2024-01-24 |  |  |  | Security & Regulatory Compliance | Compliance | Ensure L&T meets all regulatory compliance for poducts and provide NOC operationalisation |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1
1237 | M537 | MOM | 2024-01-25 |  |  |  | WFM | WFM Application | Complete the WFM-OSS integration |  | Critical | Open | [7 empty] | Kaushalendra Kumar |  | Open | WIP | [9 empty] | MOMWFM | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1238 | M538 | MOM | 2024-01-25 |  |  |  | WFM | WFM Application | Understand use cases of WFM integration with BSS |  | Critical | Open | [7 empty] | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMWFM | Applications/Tools | OPEN | [6 empty] | 1
1239 | M539 | MOM | 2024-01-25 |  |  |  | OSS | WFM Application | Define authorization of PoP RFS criteria for approval |  | Critical | Open |  |  |  |  | Not a WFM Point 11th July 2025:-this point needs to be discussed with Siva Sir to explore the possibility of accommodating the feature in the respective application, as it is not related to WFM |  |  | Suresh Pawar |  | Open | Shifted to OSS | [9 empty] | MOMOSS | Applications/Tools | #N/A | #N/A | #N/A |  |  | #N/A |  | 1
1240 | M54 | MOM | 2023-06-19 |  |  |  | GIS | Integration | Sync issue error alerts in OSS and GIS |  | Critical | Open |  | Gtech | [5 empty] | Kaushalendra Kumar |  | Open | WIP | [9 empty] | MOMGIS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1241 | M540 | MOM | 2024-01-25 |  |  |  | WFM | WFM Application | Complete Fault Management and Trouble Ticketing assignment (OSS to WFM) |  | Critical | Open |  |  |  |  | DWDM Completed |  |  | Kaushalendra Kumar |  | Open | WIP | [9 empty] | MOMWFM | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1242 | M541 | MOM | 2024-01-25 |  |  |  | WFM | WFM Application | Distinguish between the use of GIS mobile app and WFM mobile app |  | Critical | Open | [7 empty] | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMWFM | Applications/Tools | OPEN | [6 empty] | 1
1243 | M542 | MOM | 2024-01-25 |  |  |  | WFM | WFM Application | Submit the NDA signed between L&T and M/S Lepton |  | Critical | Open | [7 empty] | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMWFM | Applications/Tools | OPEN | [6 empty] | 1
1244 | M543 | MOM | 2024-01-25 |  |  |  | WFM | WFM Application | Submit sample reports and dashboards of WFM package |  | Critical | Open | [7 empty] | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMWFM | Applications/Tools | OPEN | [6 empty] | 1
1245 | M544 | MOM | 2024-01-25 |  |  |  | WFM | WFM Application | Verify proposed solution for WFM |  | Critical | Open | [7 empty] | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMWFM | Applications/Tools | OPEN | [6 empty] | 1
1246 | M545 | MOM | 2024-01-25 |  |  |  | WFM | WFM Application | Dry run and operationalize three routes for testing WFM with actual data |  | Critical | Open | [7 empty] | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMWFM | Applications/Tools | OPEN | [6 empty] | 1
1247 | M546 | MOM | 2024-01-25 |  |  |  | WFM | WFM Application | Conduct weekly training sessions for patrollers on WFM app |  | Critical | Open |  |  |  |  | Completed on 100 Licenced Users, three months weekly training provide to PKG-A, Training given to PKG-B & C also |  |  | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMWFM | Applications/Tools | OPEN | [6 empty] | 1
1248 | M547 | MOM | 2024-01-25 |  |  |  | WFM | WFM Application | Check and confirm the watermarking feature on photos taken by field users |  | Critical | Open | [7 empty] | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMWFM | Applications/Tools | OPEN | [6 empty] | 1
1249 | M548 | MOM | 2024-02-13 |  |  |  | Security & Regulatory Compliance | RMC meeting | Implement IP-MAC binding to prevent IP spoofing |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1
1250 | M549 | MOM | 2024-02-13 |  |  |  | Security & Regulatory Compliance | RMC meeting | Ensure the standardization of usernames across applications |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1
1251 | M55 | MOM | 2023-06-22 |  |  |  | Security & Regulatory Compliance | Audit | Scope submission for external audit |  | Critical | Open |  |  |  |  | Audit done by Allied Boston. And further external audit to be done by TFiber vendor |  |  | Sarmendra |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | Artefacts to be Submitted |  | 1
1252 | M550 | MOM | 2024-02-13 |  |  |  | Security & Regulatory Compliance | RMC meeting | Obtain T-Fiber's review and approval for policy documents |  | Critical | Open |  |  |  |  | As process this is being followed. Mails being sent for approvals. This point is adhered |  |  | Sarmendra |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | Artefacts to be Submitted |  | 1
1253 | M551 | MOM | 2024-02-13 |  |  |  | BSS | Product | Work on implementing the guidelines for Dark Fiber from T-Fiber and GIS team |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1254 | M552 | MOM | 2024-02-13 |  |  |  | BSS | Product | Get clarity on integration rules and timeline for activating 'Ready for Order' and 'Ready for Service' statuses |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1255 | M553 | MOM | 2024-02-13 |  |  |  | BSS | Product | Implement user access control for converting from RFO to RFS |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1256 | M554 | MOM | 2024-02-13 |  |  |  | BSS | Product | Populate data fields automatically while feeding site information |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1257 | M555 | MOM | 2024-02-13 |  |  |  | BSS | Product | Submit a document explaining reformatted guidelines for service |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1258 | M556 | MOM | 2024-02-13 |  |  |  | Security & Regulatory Compliance | RMC meeting | Initiate the implementation of Mandal-to-Mandal and Mandal-to-GP dark fiber process |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1
1259 | M557 | MOM | 2024-02-13 |  |  |  | GIS | Feasibility | Introduce the approach for Bulk Feasibility |  | Critical | Open |  |  |  |  | To fulfill this requirement, an external feasibility application or tool is needed, as it cannot be achieved within the GIS application, 11 July 2025:- TFIBER is not agreed, asked to take with L&T upper management |  |  | Kaushalendra Kumar |  | Open | Open | [9 empty] | MOMGIS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1260 | M558 | MOM | 2024-02-13 |  |  |  | BSS |  | Capture and demonstrate BSS integration with Bill Desk |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1261 | M559 | MOM | 2024-02-13 |  |  |  | BSS |  | Ensure all 29 BSNL locations are loaded for lead to order presentation |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1262 | M56 | MOM | 2023-06-22 |  |  |  | Security & Regulatory Compliance | Audit | External agency Audit with certification |  | Critical | Open |  |  |  |  | Audit done by Allied Boston. And further external audit to be done by TFiber vendor |  |  | Sarmendra |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | Artefacts to be Submitted |  | 1
1263 | M560 | MOM | 2024-02-13 |  |  |  | Security & Regulatory Compliance | RMC meeting | Finalize GI-BB timeline |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1
1264 | M561 | MOM | 2024-02-13 |  |  |  | Security & Regulatory Compliance | RMC meeting | Finalize T-Cell timeline |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1
1265 | M562 | MOM | 2024-02-13 |  |  |  | Security & Regulatory Compliance | RMC meeting | Make user access control to convert from RFO to RFS |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1
1266 | M563 | MOM | 2024-02-13 |  |  |  | Security & Regulatory Compliance | RMC meeting | Revisit the actual requirements of SSL certifications and implementation policies |  | Critical | Open |  |  |  |  | Duplicate point. Hence clsoing this point |  |  | Sarmendra |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | Artefacts to be Submitted |  | 1
1267 | M564 | MOM | 2024-02-13 |  |  |  | Security & Regulatory Compliance | RMC meeting | Submit a document with details on implementing the suggested process changes |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1
1268 | M565 | MOM | 2024-02-13 |  |  |  | Security & Regulatory Compliance | RMC meeting | Develop a standard training program followed by quizzes for improving security |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1
1269 | M566 | MOM | 2024-02-13 |  |  |  | Security & Regulatory Compliance | RMC meeting | Start a weekly security bulletin |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1
1270 | M567 | MOM | 2024-02-13 |  |  |  | Security & Regulatory Compliance | RMC meeting | Study the best practices of the State Security Operations Center and implement them |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1
1271 | M568 | MOM | 2024-02-14 |  |  |  | NSO | Service provisioning | Resolve issues with the NSO features |  | Critical | Open | [7 empty] | Jayant Madavi |  | Open | Open | [9 empty] | MOMNSO | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1272 | M569 | MOM | 2024-02-14 |  |  |  | NSO | Service provisioning | Fast track the making of the pre-production environment |  | Critical | Open | [7 empty] | Jayant Madavi |  | Open | Open | [9 empty] | MOMNSO | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1273 | M57 | MOM | 2023-06-22 |  |  |  | Security & Regulatory Compliance | Audit | external auditor to be government empanelled (MeitY / STQC). |  | Critical | Open |  |  |  |  | Audit done by Allied Boston. And further external audit to be done by TFiber vendor |  |  | Sarmendra |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | Artefacts to be Submitted |  | 1
1274 | M570 | MOM | 2024-02-14 |  |  |  | NSO | Service provisioning | Upload government orders in the BSS |  | Critical | Open | [7 empty] | Jayant Madavi |  | Open | Open | [9 empty] | MOMNSO | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1275 | M571 | MOM | 2024-02-14 |  |  |  | NSO | Service provisioning | Re-initiate the daily cadence calls |  | Critical | Open | [7 empty] | Jayant Madavi |  | Open | Open | [9 empty] | MOMNSO | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1276 | M572 | MOM | 2024-02-14 |  |  |  | NSO | Service provisioning | Make all products for the government and cellular business segments ready by |  | Critical | Open | [7 empty] | Jayant Madavi |  | Open | Open | [9 empty] | MOMNSO | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1277 | M573 | MOM | 2024-02-14 |  |  |  | BSS | Dry Run | Finish all Dry runs |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1278 | M574 | MOM | 2024-02-14 |  |  |  | NSO | Service provisioning | Work parallelly on household business products |  | Critical | Open | [7 empty] | Jayant Madavi |  | Open | Open | [9 empty] | MOMNSO | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1279 | M575 | MOM | 2024-02-14 |  |  |  | NSO | Service provisioning | Onboard all L&T SMEs and involve OEMs for 15th March'24 target |  | Critical | Open | [7 empty] | Jayant Madavi |  | Open | Open | [9 empty] | MOMNSO | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1280 | M576 | MOM | 2024-02-14 |  |  |  | Helpdesk | Helpdesk | Ensure helpdesk is ready by |  | Critical | Open |  |  |  | WIP |  |  |  | Siva Kumar |  | Open | WIP | [9 empty] | MOMHelpdesk | Helpdesk (Contact Center) | OPEN | [6 empty] | 1
1281 | M577 | MOM | 2024-02-14 |  |  |  | NOC Operationalization | O&M Strategy | Provide daily updates on the progress made in NOC by |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1
1282 | M578 | MOM | 2024-02-14 |  |  |  | NOC Operationalization | O&M Strategy | Resolve all issues |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1
1283 | M579 | MOM | 2024-02-14 |  |  |  | NOC Operationalization | O&M Strategy | Establish two distinct setup—one for live operations, another for pre-production |  | Critical | Completed |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1
1284 | M58 | MOM | 2023-06-22 |  |  |  | Security & Regulatory Compliance | Audit | simulation of attacks on the network and hardening of applications in the NOC |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1
1285 | M580 | MOM | 2024-02-14 |  |  |  | NOC Operationalization | O&M Strategy | Share all related details for pre-production setup to Director-NOC, T-Fiber |  | Critical | Completed |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1
1286 | M581 | MOM | 2024-02-16 |  |  |  | BSS | O&M Strategy | Implement ticket tracking with OSS Service Manager |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1287 | M582 | MOM | 2024-02-16 |  |  |  | BSS | GIS | Address challenge in BSS-GIS integration |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1288 | M583 | MOM | 2024-02-16 |  |  |  | BSS | GIS | Ensure collection of required / optional parameters at each step |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1289 | M584 | MOM | 2024-02-16 |  |  |  | BSS | CRM | Reconsider requirement for document collection in CAF approval stage |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1290 | M585 | MOM | 2024-02-16 |  |  |  | BSS | CRM | Introduce 'Manual reference ID' attribute in service order form |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1291 | M586 | MOM | 2024-02-16 |  |  |  | BSS | CRM | Enable option to close or update work order status manually |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1292 | M587 | MOM | 2024-02-16 |  |  |  | BSS | CRM | Alter selections or drop-down options in Lead, Opportunity, and Service Order page |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1293 | M588 | MOM | 2024-02-16 |  |  |  | BSS | CRM | Renaming certain attributes in the Opportunity Screen |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1294 | M589 | MOM | 2024-02-16 |  |  |  | BSS | CRM | Rename 'Normal Loss' attribute to 'Optical Loss' in service order form |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1295 | M59 | MOM | 2023-06-22 |  |  |  | WFM | Mobile Application | Mobile App supported in Android & IOS |  | Critical | Open | [7 empty] | Kaushalendra Kumar |  | Open | Open | [9 empty] | MOMWFM | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1296 | M590 | MOM | 2024-02-16 |  |  |  | BSS | CRM | Add multiple reference documents received from customer in service order |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1297 | M591 | MOM | 2024-02-16 |  |  |  | BSS | BSS | Display order count bar chart in the Dashboard |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1298 | M592 | MOM | 2024-02-16 |  |  |  | BSS | BSS | Issues observed in the generated CAF to be resolved |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1299 | M593 | MOM | 2024-02-16 |  |  |  | BSS | GIS | Automatically populate Site FDMS name post-GIS integration |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1300 | M594 | MOM | 2024-02-16 |  |  |  | BSS | BSS | Limit 'retry' options in BSS until process failure |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1301 | M595 | MOM | 2024-02-16 |  |  |  | BSS | WFM Application | Ensure multiple tasks tied to single work order are visible in WFM |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1302 | M596 | MOM | 2024-02-16 |  |  |  | BSS | WFM Application | Make manual acceptance function available in BSS for WFM |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1303 | M597 | MOM | 2024-02-16 |  |  |  | BSS | NSO | Resolve configuration issues to operationalize Product Catalogue module |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1304 | M598 | MOM | 2024-02-16 |  |  |  | BSS | BSS | Physical survey and customer signoff to be included in the next step |  | NON-Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1305 | M599 | MOM | 2024-02-16 |  |  |  | BSS | WFM Application | Feedback on WFM stages to be given in the next meeting |  | NON-Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1306 | M6 | MOM | 2023-03-27 |  |  |  | NOC Operationalization | Handbook & SOPs | Clear accountability and responsibility of SMEs, along with an presented RASCI matrix |  | Critical | Completed |  | NSO |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1
1307 | M60 | MOM | 2023-06-28 |  |  |  | NOC Operationalization | Handbook & SOPs | Classification of Procedures and processes from ITIL and eTOM |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1
1308 | M600 | MOM | 2024-02-16 |  |  |  | BSS | WFM Application | Generate customer signoff through WFM and create separate tabs for storing OTDR traces and customer signoff |  | NON-Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1309 | M601 | MOM | 2023-07-03 |  |  |  | Security & Regulatory Compliance | Internal Audit | Security Audit |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1
1310 | M602 | MOM | 2023-07-03 |  |  |  | Security & Regulatory Compliance | Internal Security | Acceptable Usage of information |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1
1311 | M603 | MOM | 2023-07-03 |  |  |  | Security & Regulatory Compliance | Safety | ERT and mock drills |  | Critical | Open |  |  |  |  | Mock drills, safety briefing and training is done |  |  | Srinivas Kommreddy |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | Artefacts to be uploaded |  | 1
1312 | M604 | MOM | 2023-07-03 |  |  |  | Security & Regulatory Compliance | Internal Security | Gate pass for materials |  | Critical | Open |  |  |  |  | Gate pass process in place at TNOC |  |  | Srinivas Kommreddy |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | Artefacts to be uploaded |  | 1
1313 | M605 | MOM | 2023-07-03 |  |  |  | Security & Regulatory Compliance | Internal Security | VAPT |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1
1314 | M606 | MOM | 2023-07-03 |  |  |  | Security & Regulatory Compliance | Internal Security | Security Incident management |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1
1315 | M607 | MOM | 2023-07-03 |  |  |  | Security & Regulatory Compliance | Safety | Training |  | Critical | Open |  |  |  |  | Mock drills, safety briefing and training is done |  |  | Srinivas Kommreddy |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | Artefacts to be uploaded |  | 1
1316 | M608 | MOM | 2023-07-03 |  |  |  | Security & Regulatory Compliance | Internal Security | Assest Management |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1
1317 | M609 | MOM | 2023-07-03 |  |  |  | Security & Regulatory Compliance | Internal Security | Crytography |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1
1318 | M61 | MOM | 2023-06-28 |  |  |  | NOC Operationalization | Resource Related | L&T with ITIL or eTOM certifications |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMNOC Operationalization | Network | OPEN | [6 empty] | 1
1319 | M610 | MOM | 2023-07-03 |  |  |  | Security & Regulatory Compliance | Internal Security | Access control |  | Critical | Open |  |  |  |  | Physical access control in place at TNOC. FOr system Access control, this is duplicate point |  |  | Sarmendra |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | Artefacts to be Submitted |  | 1
1320 | M611 | MOM | 2023-07-04 | P3 |  |  | NOC Operationalization | Operational Handbook | Incorporate changes into the proposed operational framework as per T-Fiber's review, including adding a Vision and Mission statement, identifying additional relevant processes, updating the organisation structure, and correcting inconsistencies in the documentation of processes. |  | Critical | Open |  |  |  |  | SOPs approved, have flow diagrams |  |  | Ahmad | 2025-09-20 |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  | Documentation | 2025-09-24 | \\172.28.9.23\tnocreports\Approved Process and SOP_ T Fiber\SOP |  | 1
1321 | M612 | MOM | 2023-07-04 |  |  |  | NOC Operationalization | Operational Handbook | Detail flow charts of the processes into SOPs. |  | Critical | Open |  |  |  | Artefacts to be submitted | 24-Sep-25: Updated Document Shared 23-Aug-23 |  |  | Siva Kumar |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-24 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\M104,105,109,111,113,115,122,123,127,128,130,132,162 |  | 1
1322 | M613 | MOM | 2023-07-04 |  | OSS | OSS | OSS | O&M Strategy | Justify the use of the implemented HPSM tool as best suited to ITIL compliant processes. |  | Critical | Open | [7 empty] | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | AD-UT-Tfiber | 2025-09-12 | \\172.28.9.34\SHARE DRIVE\Artefacts_T-Fiber TNOC Tracker\OSS | [6 empty] | MOMOSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1
1323 | M614 | MOM | 2023-07-04 |  |  |  | NOC Operationalization | O&M Strategy | Revert on the segregation of current, interim, and final organisation structure along with the timelines in which these should be applicable. |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1
1324 | M615 | MOM | 2023-07-04 |  |  |  | NOC Operationalization | Hiddencove suggestions | Include the processes recommended by the external auditor (Hiddencove) such as Handover deployment to Operation process, Service Request Process, Configuration Management, Asset Management, Critical Event Management, Site Access Management, Handover Deployment to Operations Process (Transition Process). |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMNOC Operationalization | Network | OPEN | [6 empty] | 1
1325 | M616 | MOM | 2023-07-04 |  |  |  | NOC Operationalization | O&M Strategy | Include a Continuous Improvement framework covering the process of identification/initiation of the areas for continuous improvement on a regular basis. Standard frameworks like KAIZEN Or PDCA are suggested. |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1
1326 | M617 | MOM | 2023-07-04 | P3 |  |  | NOC Operationalization | Escalation Matrix | Include aspects like document processes, RASCI & Escalation Matrix in NOC Operational Framework. |  | Critical | Open | [7 empty] | Ahmad | 2025-10-07 | Open | Open | [9 empty] | MOMNOC Operationalization | Network | OPEN |  |  | Documentation |  | #N/A |  | 1
1327 | M618 | MOM | 2023-07-04 |  |  |  | NOC Operationalization | O&M Strategy | Highlight the processes that will be implemented and ready by 15th August ’23 and provide a roadmap of which module will be ready by when. |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1
1328 | M619 | MOM | 2023-07-04 | P3 |  |  | NOC Operationalization | Escalation Matrix | Define clear roles and responsibilities related to L1, L2 & L3 with an appropriate number of resources which should be according to the fault rates. |  | Critical | Open |  |  |  |  | 24-Sep-25: Updated Document Shared 23-Aug-23 |  |  | Ahmad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  | Not related to delivery | 2025-09-24 | \\172.28.9.23\tnocreports\TNOC Manpower_CVs\NOC Resources Details & Roles |  | 1
1329 | M62 | MOM | 2023-06-28 | P3 |  |  | NOC Operationalization | Handbook & SOPs | All KPIs details submission |  | Critical | Completed |  |  |  |  | NOC KPI report for submitted and signed for Oct24 to Dec24. Jan to March25 KPI submitted but sign-off pending with TFiber |  |  | Ahmad | 2025-09-20 |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  | Documentation | 2025-09-24 | \\172.28.9.23\tnocreports\Monthly KPI Reports\FY 24-25\NOV-24\Interim NOC KPI for Signoff_ NOV-24 |  | 1
1330 | M620 | MOM | 2023-07-04 |  |  |  | NOC Operationalization | GIS | Ensure the coverage of GIS operations as part of a single integrated picture of NOC, Field including handovers to/from Field and NOC. |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1
1331 | M621 | MOM | 2023-07-04 |  |  |  | Helpdesk | Helpdesk | Evaluate the readiness of the current Helpdesk to start taking calls for GI and validate the sufficiency of the Helpdesk based on the fault rate, waiting time for each agent etc. by 15th July'23 |  | Critical | open |  |  |  | Closed | 24-Sep-25: Approved and shall be closed 11-Sep-25: Changed and operational Now |  |  | Siva Kumar |  |  | COMPLETED & APPROVED | [9 empty] | MOMHelpdesk | Helpdesk (Contact Center) | CLOSED |  |  |  | 2025-09-24 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\M117,126,728 |  | 1
1332 | M622 | MOM | 2023-07-04 | P3 |  |  | NOC Operationalization | O&M Strategy | Submission of the proposed TNOC Operational Framework document on 9th July ’23 for review. |  | Critical | Open |  |  |  |  | 223-Sep-25: Artefacts uploded |  |  | Ahmad | 2025-10-07 |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  | Documentation | 2025-09-22 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\TNOC\M622 |  | 1
1333 | M623 | MOM | 2023-07-04 |  |  |  | NOC Operationalization | O&M Strategy | Next review on Operational Framework by 11th July ’23. |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1
1334 | M624 | MOM | 2023-07-04 |  |  |  | NOC Operationalization | O&M Strategy | Develop a process and framework for order fulfillment, ensuring that all applications and tools are ready for production. |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMNOC Operationalization | Network | OPEN | [6 empty] | 1
1335 | M625 | MOM | 2023-07-04 |  |  |  | NOC Operationalization | O&M Strategy | Prepare a more comprehensive plan for product catalog and infrastructure management and maintenance. |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMNOC Operationalization | Network | OPEN | [6 empty] | 1
1336 | M626 | MOM | 2023-07-04 |  |  |  | NOC Operationalization | O&M Strategy | Develop a comprehensive plan for improving network service management and address any issues related to MPLS-related resources. |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMNOC Operationalization | Network | OPEN | [6 empty] | 1
1337 | M627 | MOM | 2023-07-04 |  |  |  | NOC Operationalization | Dry Run | Schedule the first dry run for the NOC Operationalization for 24th July '23. |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1
1338 | M628 | MOM | 2023-07-04 |  |  |  | WFM | Mobile Application | Develop and present mobile applications that are functional and meet the needs and preferences of users by 15th August '23. |  | Critical | Open | [7 empty] | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMWFM | Applications/Tools | OPEN | [6 empty] | 1
1339 | M629 | MOM | 2023-07-04 |  |  |  | NOC Operationalization |  | The Tools Assigned the Operation to be ready and deployed by 9th July '23. |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMNOC Operationalization | Network | OPEN | [6 empty] | 1
1340 | M63 | MOM | 2023-06-28 |  |  |  | NOC Operationalization | Handbook & SOPs | The difference between problem and issue management. |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1
1341 | M630 | MOM | 2023-07-04 |  |  |  | NOC Operationalization |  | HLD & LLD Approval: L&T to expedite closure of pending points with daily discussions, aiming for 6th April '23. |  | NON-Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMNOC Operationalization | Network | OPEN | [6 empty] | 1
1342 | M631 | MOM | 2023-07-04 |  |  |  | BSS | T-Cell Launch | Cell Tower Launch: CRM-based demo by L&T with manual NSO loop and GIS by 27th March '23. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1343 | M632 | MOM | 2023-07-04 |  |  |  | BSS | T-Cell Launch | Dependencies for Cell Tower Launch: L&T to address payment gateway integration, product catalog sign-off, and E2E flows with T-Fiber approval. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1344 | M633 | MOM | 2023-07-04 |  |  |  | BSS | T-Cell Launch | GIS Feasibility for Cell Tower: L&T to present an alternative solution within 2 to 3 days and document risks and mitigation for seamless migration. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1345 | M634 | MOM | 2023-07-04 |  |  |  | GIS | GIS Completion | GIS OEM - Hexagon: L&T to ensure GIS readiness within 2 to 4 weeks for service provisioning automation. |  | Critical | Open | [7 empty] | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMGIS | Applications/Tools | OPEN | [6 empty] | 1
1346 | M635 | MOM | 2023-07-04 |  |  |  | OEM Related | Security | Cisco Firewall Limitation: L&T to demonstrate GI Internet workflow by 5th April '23 and confirm support for full capacity of 30 thousand institutions. |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMOEM Related | OEM Related Issues | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1
1347 | M636 | MOM | 2023-07-04 |  |  |  | PM Tool Issue | PM Tool Issue | Digital Process for GI Connectivity: L&T to present a plan for digital process and tools usage by 5th April '23, with the possibility of presenting earlier in Cadence calls. |  | NON-Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMPM Tool Issue | Applications | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1
1348 | M637 | MOM | 2023-07-04 |  |  |  | BSS | BSS | BSS Cadence Calls: L&T to initiate and lead the required Cadence calls to meet project timelines. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1349 | M638 | MOM | 2023-07-04 |  |  |  | NOC Operationalization | Resource Augmentation | IPMPLS SME Resignation: L&T to address the resignation and retention of the IPMPLS SME. |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1
1350 | M639 | MOM | 2023-07-04 |  |  |  | NOC Operationalization | Communication Matrix | Project SPOC: Mr. Anthony from L&T to coordinate across all domains to deliver the project. |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1
1351 | M64 | MOM | 2023-06-28 |  |  |  | NOC Operationalization | Handbook & SOPs | Establish a configuration management system to monitor all changes in NOC operations |  | Critical | Completed |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMNOC Operationalization | Network | OPEN | [6 empty] | 1
1352 | M640 | MOM | 2023-07-04 |  |  |  | NOC Operationalization | Service Solution | T-NOC Operationalisation Plan: L&T to present a phased plan on 27th March '23 for minimal readiness by 5th April, stage 2 by 20th April, and stage 3 by 30th April, with the entire T-NOC operational by 30th April and launch by 15th May '23. |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMNOC Operationalization | Network | OPEN | [6 empty] | 1
1353 | M641 | MOM | 2023-07-04 |  |  |  | Field Related | Resource Augmentation | Resource Deployment for District Delivery: L&T to ramp up resources to meet the delivery target of five and a half districts by 7th April '23. |  | Critical | Open | [7 empty] | S Kodali |  | Open | Open | [9 empty] | MOMField Related | Field Related issues | OPEN |  |  | Project Team |  | Artefacts to be uploaded |  | 1
1354 | M642 | MOM | 2023-07-04 |  |  |  | Field Related | Zonal Path connectivity | Zonal Path Completion: L&T to complete Medak to Mahbubnagar Zonal path by 31st March and AT by 15th April '23; AT of other completed zonal paths by 31st March '23. |  | Critical | Open | [7 empty] | S Kodali |  | Open | Open | [9 empty] | MOMField Related | Field Related issues | OPEN |  |  | Project Team |  | #N/A |  | 1
1355 | M643 | MOM | 2023-07-05 |  |  |  | GIS | GIS Completion | Evaluate the current readiness status of the GIS tool and address the pending issues. |  | Critical | Open | [7 empty] | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMGIS | Applications/Tools | OPEN | [6 empty] | 1
1356 | M644 | MOM | 2023-07-05 |  |  |  | BSS | BSS | Ensure that the product being developed meets all the discussed and agreed-upon requirements and features. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1357 | M645 | MOM | 2023-07-05 |  |  |  | BSS | Dry Run | Complete the BSS Demo according to the feedback points received and demonstrate progress on the same by the first week of May. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1358 | M646 | MOM | 2023-07-05 |  |  |  | NOC Operationalization | NOC Operationalization | Develop and present a comprehensive proposal for improving the appearance of T-NOC. |  | Critical | Open |  |  |  |  | TNOC passive infra delivered, AT done |  |  | Ahmad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  | Need clarity | 2025-09-19 | Artefacts not Required |  | 1
1359 | M647 | MOM | 2023-07-05 |  |  |  | GIS | GIS Completion | Submit revise plan for Complete GIS Tool (Basic) Readiness by 30th April’23, GIS Tool (Advanced) Readiness by 31st May’23, and GIS Tool (Integration) Readiness by 30th June’23. |  | Critical | Open | [7 empty] | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMGIS | Applications/Tools | OPEN | [6 empty] | 1
1360 | M648 | MOM | 2023-07-05 |  |  |  | GIS | GIS Completion | Submit responses on concerns of the number of GIS licences for data upload and readiness of current helpdesk to start taking calls for GI. |  | Critical | Open |  |  |  |  | TFIBER is a critical dependency for closing the GIS licenses |  |  | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMGIS | Applications/Tools | OPEN | [6 empty] | 1
1361 | M649 | MOM | 2023-07-05 | P3 |  |  | NOC Operationalization | Operational Framework | Identify and rectify inconsistencies in the document processes presented in the NOC's Operational Framework. |  | Critical | Open | [7 empty] | Ahmad | 2025-10-07 | Open | Open | [9 empty] | MOMNOC Operationalization | Network | OPEN |  |  | Documentation |  | #N/A |  | 1
1362 | M65 | MOM | 2023-06-28 | P3 |  |  | NOC Operationalization | Handbook & SOPs | Create an archival policy for documentation storage, including retrieval systems, access matrix, and policies |  | Critical | Open | [7 empty] | Ahmad | 2025-10-07 | Open | Open | [9 empty] | MOMNOC Operationalization | Network | OPEN |  |  | Documentation |  | #N/A |  | 1
1363 | M650 | MOM | 2023-07-05 |  |  |  | BSS | Dry Run | Provide BSS Demo with actual auto-feasibility check by 6th April. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1364 | M651 | MOM | 2023-07-05 |  |  |  | BSS | Dry Run | Present a clear day-wise plan for BSS readiness by 30th September 2023 for full-fledged production with automated GIS. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1365 | M652 | MOM | 2023-07-05 |  |  |  | Field Related | Full NOC Readiness | Complete the connection of 589 Mandals by 1st week of June, with an expectation of minimum 3 hours and maximum of 5 hours for each Mandal. |  | Critical | Open | [7 empty] | S Kodali |  | Open | Open | [9 empty] | MOMField Related | Field Related issues | OPEN |  |  | Project Team |  | #N/A |  | 1
1366 | M653 | MOM | 2023-07-05 |  |  |  | NOC Operationalization | Full NOC Readiness | Highlight the processes that will be implemented and ready by 15th August ’23 and provide a roadmap of which module will be ready by when during the meeting on 4th July'23. |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMNOC Operationalization | Network | OPEN | [6 empty] | 1
1367 | M654 | MOM | 2023-07-05 |  |  |  | Security & Regulatory Compliance | Full NOC Readiness | Still update on the perceived firewall limitation issue is pending , asked on 3rd April'24 |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1
1368 | M655 | MOM | 2023-07-05 |  |  |  | BSS | WFM Application | Submit internal E2E Project Plan on 31st March’23 as committed for review. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1369 | M656 | MOM | 2023-07-05 |  |  |  | BSS | Dry Run | BSS Demo on 6th April’23 must provide order feasibility. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1370 | M657 | MOM | 2023-07-05 |  |  |  | NOC Operationalization | Operational Framework | Ensure that all references to processes from ITIL and eTOM are clearly explained and utilized in the operational framework. |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1
1371 | M658 | MOM | 2023-07-05 | P3 |  |  | NOC Operationalization | Escalation Matrix | Implement a robust RASCI & Escalation Matrix in the NOC Operational Framework. |  | Critical | Open | [7 empty] | Ahmad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  | Not related to delivery | 2025-09-19 | Artefacts not Required |  | 1
1372 | M659 | MOM | 2023-07-05 |  |  |  | GIS | GIS Completion | Integrate the processes recommended by the external auditor into the process flow of GIS readiness. |  | Critical | Open |  |  |  |  | GIS SOP |  |  | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMGIS | Applications/Tools | OPEN | [6 empty] | 1
1373 | M66 | MOM | 2023-06-28 | P3 |  |  | NOC Operationalization | Handbook & SOPs | Define categories of problems along with a resolution approach plan |  | Critical | Open | [7 empty] | Ahmad | 2025-10-07 | Open | Open | [9 empty] | MOMNOC Operationalization | Network | OPEN |  |  | Documentation |  | #N/A |  | 1
1374 | M660 | MOM | 2023-07-05 |  |  |  | BSS | GIS | Perform manual feasibility checking until the GIS tool is ready and data is uploaded into the tool. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1375 | M661 | MOM | 2023-07-05 |  |  |  | BSS | GI Demo | Showcase the GI demo by the end of May. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1376 | M662 | MOM | 2023-07-05 |  |  |  | GIS | GIS Completion | Improve coordination with GIS, OEMs, and explore the possibility of developing a new GIS OEM to deliver the requirements of T-Fiber. |  | Critical | Open | [7 empty] | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMGIS | Applications/Tools | OPEN | [6 empty] | 1
1377 | M663 | MOM | 2023-07-05 |  |  |  | Helpdesk | Helpdesk | Take the performance measurement processes into consideration for measuring the performance of the identified Helpdesk resources. |  | Critical | Open |  |  |  | Closed | 24-Sep-25: Approved and shall be closed |  |  | Siva Kumar |  |  | COMPLETED & APPROVED | [9 empty] | MOMHelpdesk | Helpdesk (Contact Center) | CLOSED |  |  |  | 2025-09-24 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\M114,722,134 |  | 1
1378 | M664 | MOM | 2023-07-05 |  |  |  | BSS | CRM | Handle more professionally the field activity portion of the CRM flow. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1379 | M665 | MOM | 2023-07-05 |  |  |  | NSO | NSO | Arrive at feasible alternatives to handle situations such as NSO provisioning timeouts, submit alternative approaches in such scenarios and revert with exact steps taken to achieve this. |  | Critical | Open | [7 empty] | Jayant Madavi |  | Open | Open | [9 empty] | MOMNSO | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1380 | M666 | MOM | 2023-07-05 |  |  |  | NOC Operationalization | Daily Meetings | Officially commence up the daily stand-up call on 16th June ’23, with the call to be held routinely from this date. |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1
1381 | M667 | MOM | 2023-07-05 |  |  |  | BSS | Dry Run | BSS Demo on 6th April ’23 to provide order feasibility. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1382 | M668 | MOM | 2023-07-05 |  |  |  | NOC Operationalization | Operational Framework | Review of the Operational Framework by 11th July ’23. |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1
1383 | M669 | MOM | 2023-07-05 |  |  |  | BSS | T-Cell Launch | Showcase the demo for T-Cell on 6th April ’23. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1384 | M67 | MOM | 2023-06-28 |  |  |  | NOC Operationalization | Handbook & SOPs | Adopt a continuous improvement framework such as DMAIC and Kaizen for process improvement |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1
1385 | M670 | MOM | 2023-07-05 |  |  |  | BSS | Billing Related | Auto-approval of the Invoice by Finance users. |  | NON-Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1386 | M671 | MOM | 2023-07-05 |  |  |  | Helpdesk | Helpdesk | Make Helpdesk operational by 15th July ’23. |  | Critical | Open |  |  |  | WIP |  |  |  | Siva Kumar |  | Open | WIP | [9 empty] | MOMHelpdesk | Helpdesk (Contact Center) | OPEN | [6 empty] | 1
1387 | M672 | MOM | 2023-07-21 |  |  |  | BSS | BSS | BSS Readiness Confirmation: L&T to review and update overall readiness for E2E NOC by EOD 8th September '23, including confirmation on launch deliverables and interim launch processes . |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1388 | M673 | MOM | 2023-07-21 |  |  |  | BSS | Dry Run | BSS Demo Observations: L&T to address observations from the BSS Demo on 24th July '23 and action items from the meeting with Director-Finance, T-Fiber . |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1389 | M674 | MOM | 2023-07-21 |  |  |  | WFM |  | WFM Integration: L&T commenced WFM integration and will arrange a demonstration for field operations . |  | Critical | Open | [7 empty] | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMWFM | Applications/Tools | OPEN | [6 empty] | 1
1390 | M675 | MOM | 2023-07-21 |  |  |  | BSS | NSO | Static IP and UI/UX Changes: Ready for demonstration by L&T . |  | NON-Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1391 | M676 | MOM | 2023-07-21 |  |  |  | Security & Regulatory Compliance | Compliance | Security and Compliance: L&T to address critical security-related activities for launch and regulatory compliances with specific target dates . |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1
1392 | M677 | MOM | 2023-07-21 |  |  |  | BSS | Billing Related | Payment Gateway Completion: If SSL Certificate is provided by 11th September '23, L&T to complete the payment gateway by 30th September '23 . |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1393 | M678 | MOM | 2023-07-21 |  |  |  | BSS | Dry Run | BSS E2E Demo: Chief Delivery Officer, L&T proposed to have the E2E BSS Demo on 4th July '23, with features to be confirmed by 1st July '23 . |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1394 | M679 | MOM | 2023-07-21 |  |  |  | WFM |  | Mobile App & WFM: SVP, T-Fiber requested clarity on the number of mobile apps and urged L&T to freeze the scope in consultation with MSI B and C. Demo with M/S Lepton scheduled for 21st June '23 . |  | Critical | Open | [7 empty] | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMWFM | Applications/Tools | OPEN | [6 empty] | 1
1395 | M68 | MOM | 2023-07-04 | P3 |  |  | NOC Operationalization | Handbook & SOPs | RASCI & Escalation Matrix in NOC Operational Framework |  | Critical | Closed |  |  |  |  | OEM, vendor , Field/NOC escalation matrix available. This is a point in 472 tracker as well and this point is approved by TFiber |  |  | Ahmad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  | Not related to delivery | 2025-09-19 | Artefacts not Required |  | 1
1396 | M680 | MOM | 2023-07-21 |  |  |  | NSO | NSO related | NSO Competency Plan: L&T to put in place an NSO competency plan . |  | Critical | Open | [7 empty] | Jayant Madavi |  | Open | Open | [9 empty] | MOMNSO | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1397 | M681 | MOM | 2023-07-21 |  |  |  | T&D Environment | Testing Environment | Separation of T&D and Production Environments: L&T to provide a plan addressing the requirement for separate environments . |  | NON-Critical | Open |  |  |  |  | [15/09/2025] Clusters are segregated for Production vis-à-vis pre-production |  |  | Ravi Kishore |  |  | COMPLETED & APPROVED | [9 empty] | MOMT&D Environment | Applications | CLOSED |  |  |  |  | Artefacts Need to upload |  | 1
1398 | M682 | MOM | 2023-07-21 |  |  |  | BSS | Testing Environment | Onboarding of Billing Specialist: L&T to update on the onboarding process for a long-term Billing Specialist . |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1399 | M683 | MOM | 2023-07-21 |  |  |  | BSS | Billing Related | Closure of CRM Billing Process and Invoice Format: L&T to close action items regarding CRM Billing Process and Invoice format . |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1400 | M684 | MOM | 2023-07-21 |  |  |  | BSS | Action Points | BSS Roadmap Progress: L&T to demonstrate completed points for closure and include related test cases . |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1401 | M685 | MOM | 2023-07-21 |  |  |  | BSS | Dry Run | Next BSS Demo for Cell Tower: L&T to confirm the date of the next BSS Demo for Cell Tower by 21st August '23 . |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1402 | M686 | MOM | 2023-07-21 |  |  |  | BSS | Action Points | User Groups Demonstration: L&T to showcase the demonstration on user groups along with the demo for Cell Tower . |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1403 | M687 | MOM | 2023-07-21 |  |  |  | BSS | Action Points | Next BSS Demo Schedule: Scheduled for 23rd August '23, to include RFS/RFO status, notification templates, UI/UX validation, and exception scenarios . |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1404 | M688 | MOM | 2023-07-21 |  |  |  | BSS | Regulatory Compliance | Regulatory Reports Review: L&T to identify available reports in BSS as Ready/WIP by 21st August '23 and review with T-Fiber for approval . |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1405 | M689 | MOM | 2023-07-26 |  |  |  | WFM |  | Finalise and share the scope of work (SOW) for Work Force Management solution implementation with M/S Lepton. |  | Critical | Open | [7 empty] | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMWFM | Applications/Tools | OPEN | [6 empty] | 1
1406 | M69 | MOM | 2023-07-04 | P3 |  |  | NOC Operationalization | Handbook & SOPs | clear definition of roles and responsibilities related to L1, L2 & L3 with number of resources which should be according to the fault rates. |  | Critical | Completed |  |  |  |  | NOC manpower report is shared on weekly basis. Manpower is as per RFP count. KRA is also submitted for L1/L2/L3 roles |  |  | Ahmad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  | Not related to delivery | 2025-09-24 | \\172.28.9.23\tnocreports\TNOC Manpower_CVs\NOC Resources Details & Roles |  | 1
1407 | M690 | MOM | 2023-07-26 |  |  |  | WFM |  | Support for translation to Telugu to be checked with M/S Lepton. |  | Critical | Open |  |  |  |  | Duplicate with Point- 177 |  |  | Kaushalendra Kumar |  | Open | Duplicate | [9 empty] | MOMWFM | Applications/Tools | #N/A |  |  |  |  | #N/A |  | 1
1408 | M691 | MOM | 2023-07-26 |  |  |  | WFM |  | Clarity on the term “As-is solution to be deployed” under Order Management is to be provided. |  | Critical | Open | [7 empty] | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMWFM | Applications/Tools | OPEN | [6 empty] | 1
1409 | M692 | MOM | 2023-07-26 |  |  |  | WFM |  | Support for Barcode scanning as well as QR code scanning to be checked with M/S Lepton. |  | Critical | Open | [7 empty] | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMWFM | Applications/Tools | OPEN | [6 empty] | 1
1410 | M693 | MOM | 2023-07-26 |  |  |  | BSS | Dry Run | Preparation for a dry run of BSS to include WFM. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1411 | M694 | MOM | 2023-07-26 |  |  |  | WFM |  | Receive clarification on the support for re-assignment of workflow in case a Field Technician is on leave. |  | Critical | Open |  |  |  |  | Manager has to reassign TT to different FE |  |  | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMWFM | Applications/Tools | OPEN | [6 empty] | 1
1412 | M695 | MOM | 2023-07-26 |  |  |  | WFM |  | Verify processes for recording of timelocks of patrol routes. |  | Critical | Open | [7 empty] | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMWFM | Applications/Tools | OPEN | [6 empty] | 1
1413 | M696 | MOM | 2023-07-26 |  |  |  | WFM |  | Improve the clarity, definition, and availability of existing filters in WFM dashboards. |  | Critical | Open |  |  |  |  | Duplicate with Point- 186 |  |  | Kaushalendra Kumar |  | Open | Duplicate | [9 empty] | MOMWFM | Applications/Tools | #N/A |  |  |  |  | #N/A |  | 1
1414 | M697 | MOM | 2023-07-26 |  |  |  | WFM |  | Video upload support. |  | Critical | Open |  |  |  |  | Duplicate with Point- 187 |  |  | Kaushalendra Kumar |  | Open | Duplicate | [9 empty] | MOMWFM | Applications/Tools | #N/A |  |  |  |  | #N/A |  | 1
1415 | M698 | MOM | 2023-07-26 |  |  |  | WFM |  | Support for Workforce Management productivity statistics mentioned that this shall fall under the customisation scope. |  | Critical | Open |  |  |  |  | Duplicate with Point- 188 |  |  | Kaushalendra Kumar |  | Open | Duplicate | [9 empty] | MOMWFM | Applications/Tools | #N/A |  |  |  |  | #N/A |  | 1
1416 | M699 | MOM | 2023-07-26 |  |  |  | WFM |  | Coordination required with NOC, Operations, and Projects team of 3 MSIs for the WFM Demo of 3 Packages including BSS-SME- L&T. |  | Critical | Open | [7 empty] | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMWFM | Applications/Tools | OPEN | [6 empty] | 1
1417 | M7 | MOM | 2023-04-03 |  |  |  | NOC Operationalization | Full NOC Readiness | Request for submission of Test Reports, outcomes, and documentation on a common server for continuous testing and monitoring. (Shared Folder) |  | Critical | Completed |  | OSS Dashboards |  | Artefacts to be submitted | 24-Sep-25: All Field and Interim NOC KPIs, reports, forms are available in shared folder.Artefacts will be uploaded today in NAS |  |  | Siva Kumar |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-24 | \\172.28.9.23\tnocreports |  | 1
1418 | M70 | MOM | 2023-07-04 | P3 |  |  | NOC Operationalization | Audit | Checklist for issue handling and first level troubleshooting |  | Critical | Completed |  |  |  |  | Checklist available with Helpdesk |  |  | Ahmad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  | Daily oprational task | 2025-09-19 | Artefacts not Required |  | 1
1419 | M700 | MOM | 2023-07-26 |  |  |  | WFM |  | Asses if NOC Work Force Management is handled by the proposed WFM tool |  | Critical | Open |  |  |  |  | Duplicate with Point- 189 |  |  | Kaushalendra Kumar |  | Open | Duplicate | [9 empty] | MOMWFM | Applications/Tools | #N/A |  |  |  |  | #N/A |  | 1
1420 | M701 | MOM | 2023-07-26 |  |  |  | WFM |  | Samples or actual reports and dashboards based on operational processes to be presented by 28th July’23. |  | Critical | Open |  |  |  |  | Duplicate with Point- 207 |  |  | Kaushalendra Kumar |  | Open | Duplicate | [9 empty] | MOMWFM | Applications/Tools | #N/A |  |  |  |  | #N/A |  | 1
1421 | M702 | MOM | 2023-07-26 |  |  |  | WFM |  | Assessment to ensure that planned Event Manpower assignment is covered by the WFM solution. |  | Critical | Open |  |  |  |  | Duplicate with Point- 190 |  |  | Kaushalendra Kumar |  | Open | Duplicate | [9 empty] | MOMWFM | Applications/Tools | #N/A |  |  |  |  | #N/A |  | 1
1422 | M703 | MOM | 2023-07-26 |  |  |  | WFM |  | Assessment about whether the proposed WFM solution supports field personnel to schedule appointments with end customers. |  | Critical | Open |  |  |  |  | Duplicate with Point- 194 |  |  | Kaushalendra Kumar |  | Open | Duplicate | [9 empty] | MOMWFM | Applications/Tools | #N/A |  |  |  |  | #N/A |  | 1
1423 | M704 | MOM | 2023-07-26 |  |  |  | WFM |  | Ensure the licenses for WFM are perpetual. |  | Critical | Open |  |  |  |  | Duplicate with Point- 196 |  |  | Kaushalendra Kumar |  | Open | Duplicate | [9 empty] | MOMWFM | Applications/Tools | #N/A |  |  |  |  | #N/A |  | 1
1424 | M705 | MOM | 2023-07-26 |  |  |  | NOC Operationalization | Launch Readiness | Assessment and redistribution of support because of the launch date approaching on 15th August. |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1
1425 | M706 | MOM | 2023-08-01 |  |  |  | GIS | Launch Readiness | Each MSI needs to commit to the target for Mandal upload in the GIS tool for business readiness. |  | Critical | Open | [7 empty] | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMGIS | Applications/Tools | OPEN | [6 empty] | 1
1426 | M707 | MOM | 2023-08-01 |  |  |  | GIS | Launch Readiness | Commit target dates for GIS Data Upload for each package. |  | Critical | Open | [7 empty] | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMGIS | Applications/Tools | OPEN | [6 empty] | 1
1427 | M708 | MOM | 2023-08-01 |  |  |  | GIS | Launch Readiness | Package A needs to provide a day by day Mandal upload action plan to meet the committed target dates. |  | Critical | Open | [7 empty] | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMGIS | Applications/Tools | OPEN | [6 empty] | 1
1428 | M709 | MOM | 2023-08-01 |  |  |  | GIS | Launch Readiness | Packages B and C are expected to submit a proposal to hasten data upload in consultation with GIS-SME, Pkg-A. |  | Critical | Open | [7 empty] | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMGIS | Applications/Tools | OPEN | [6 empty] | 1
1429 | M71 | MOM | 2023-07-04 |  |  |  | NOC Operationalization | Audit | Latency/Jitter & Backbone packet loss SLAs |  | Critical | Completed |  |  |  | WIP | Report & SLA compliance is shared on monhtly basis | L&T | Manoj | Siva Kumar |  | Open | WIP | [9 empty] | MOMNOC Operationalization | Network | OPEN | [6 empty] | 1
1430 | M710 | MOM | 2023-08-01 |  |  |  | Field Related | Launch Readiness | MSIs to prioritise a district-wise approach over a scattered approach. |  | Critical | Open | [7 empty] | S Kodali |  | Open | Open | [9 empty] | MOMField Related | Field Related issues | OPEN |  |  | Project Team |  | #N/A |  | 1
1431 | M711 | MOM | 2023-08-01 |  |  |  | Field Related | Mandal Rings | The status of Mandal Rings completion i.e. GIS uploading done, splicing pending, attribute updating is pending. |  | NON-Critical | Open |  |  |  |  | completed for 110 Mandals and balance in progress with mandal readiness by acitive & passive |  |  | S Kodali |  | Open | Open | [9 empty] | MOMField Related | Field Related issues | OPEN |  |  | Project Team |  | #N/A |  | 1
1432 | M712 | MOM | 2023-08-01 |  |  |  | GIS | Launch Readiness | The current committed dates for GIS Data Upload are not meeting the expectations of T-Fiber. |  | Critical | Open | [7 empty] | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMGIS | Applications/Tools | OPEN | [6 empty] | 1
1433 | M713 | MOM | 2023-08-01 |  |  |  | Helpdesk | Launch Readiness | Complete Helpdesk integration with OSS and BSS. |  | Critical | Open |  |  |  | WIP |  |  |  | Siva Kumar |  | Open | WIP | [9 empty] | MOMHelpdesk | Helpdesk (Contact Center) | OPEN | [6 empty] | 1
1434 | M714 | MOM | 2023-08-01 |  |  |  | BSS | Launch Readiness | Set up SMS based alerting. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1435 | M715 | MOM | 2023-08-01 |  |  |  | Helpdesk | Launch Readiness | Handle 150-160 calls per day in Helpdesk. |  | Critical | open |  |  |  | Closed | 24-Sep-25: Approved and shall be closed 11-Sep-25: Changed and operational Now |  |  | Siva Kumar |  |  | COMPLETED & APPROVED | [9 empty] | MOMHelpdesk | Helpdesk (Contact Center) | CLOSED |  |  |  | 2025-09-24 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\M117,126,728 |  | 1
1436 | M716 | MOM | 2023-08-01 |  |  |  | Helpdesk | Launch Readiness | Ensure that Helpdesk SLAs from the RFP are met. |  | Critical | open |  |  |  | WIP |  |  |  | Siva Kumar |  | Open | WIP | [9 empty] | MOMHelpdesk | Helpdesk (Contact Center) | OPEN | [6 empty] | 1
1437 | M717 | MOM | 2023-08-01 |  | OSS | OSS | OSS | Launch Readiness | Deploy the Knowledge Management module in HPSM. |  | Critical | Open | [7 empty] | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMOSS | Applications/Tools | OPEN | CLOSURE REVIEW PENDING | 0 |  |  |  |  | 1
1438 | M718 | MOM | 2023-08-01 |  |  |  | Helpdesk | Launch Readiness | Make the number for reaching Helpdesk toll-free. |  | Critical | Open |  |  |  |  | 11-09-2025: Same as T366(472) Closed |  |  | Siva Kumar |  |  | COMPLETED & APPROVED | Yes | 2025-07-19 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\T366 | [6 empty] | MOMHelpdesk | Helpdesk (Contact Center) | CLOSED |  |  |  | 2025-07-19 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\T366 |  | 1
1439 | M719 | MOM | 2023-08-01 |  |  |  | BSS | Launch Readiness | Create and finalize multiple channels of communication to the Helpdesk such as SMS, WhatsApp, and email. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1440 | M72 | MOM | 2023-07-04 | P3 |  |  | NOC Operationalization | Handbook & SOPs | service management of configuration |  | Critical | Open | [7 empty] | Ahmad | 2025-10-07 | Open | Open | [9 empty] | MOMNOC Operationalization | Network | OPEN |  |  | Documentation |  | #N/A |  | 1
1441 | M720 | MOM | 2023-08-01 |  | OSS | OSS | OSS | Launch Readiness | Define incident categorisation. |  | Critical | Open | [7 empty] | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMOSS | Applications/Tools | OPEN | CLOSURE REVIEW PENDING | 0 |  |  |  |  | 1
1442 | M721 | MOM | 2023-08-01 |  |  |  | Helpdesk | Launch Readiness | Specify features of Helpdesk not presently available for future deployment. |  | Critical | Open |  |  |  | WIP |  |  |  | Siva Kumar |  | Open | WIP | [9 empty] | MOMHelpdesk | Helpdesk (Contact Center) | OPEN | [6 empty] | 1
1443 | M722 | MOM | 2023-08-01 |  |  |  | Helpdesk | Launch Readiness | Training for Helpdesk users and managers for call center response and management. |  | Critical | open |  |  |  | Closed | 24-Sep:25: Artefacts to sbumitted |  |  | Siva Kumar |  |  | COMPLETED & APPROVED | [9 empty] | MOMHelpdesk | Helpdesk (Contact Center) | CLOSED |  |  |  | 2025-09-24 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\M114,722,134 |  | 1
1444 | M723 | MOM | 2023-08-01 |  |  |  | Helpdesk | Launch Readiness | Set up a mechanism for non-technical call handling improvement. |  | Critical | open |  |  |  | Closed | 25-Sep-25: aretfacts to be sumitted for closure 11-Sep-25: Established Business Helpdesk Setup at T Fiber office |  |  | Siva Kumar |  |  | COMPLETED & APPROVED | [9 empty] | MOMHelpdesk | Helpdesk (Contact Center) | CLOSED |  |  |  | 2025-09-24 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\M116,723,1026 |  | 1
1445 | M724 | MOM | 2023-08-01 |  |  |  | Helpdesk | Launch Readiness | Get readiness of Helpdesk and Business to accept issues with order login. |  | Critical | open |  |  |  | Closed | 25-Sep-25: aretfacts to be sumitted for closure 11-Sep-25: Established Business Helpdesk Setup at T Fiber office |  |  | Siva Kumar |  |  | COMPLETED & APPROVED | [9 empty] | MOMHelpdesk | Helpdesk (Contact Center) | CLOSED |  |  |  | 2025-09-24 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\M724 |  | 1
1446 | M725 | MOM | 2023-08-01 |  |  |  | Helpdesk | Launch Readiness | Determine how to handle calls originating from different packages given the shared Helpdesk agents. |  | Critical | open |  |  |  | Closed | 24-Sep-25: IVR Flows made ready Accordingly |  |  | Siva Kumar |  |  | COMPLETED & APPROVED | [9 empty] | MOMHelpdesk | Helpdesk (Contact Center) | CLOSED |  |  |  | 2025-09-24 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\M725,735 |  | 1
1447 | M726 | MOM | 2023-08-01 |  |  |  | Helpdesk | Launch Readiness | Problems with not supporting Telugu language in IVR and Helpdesk. |  | Critical | open |  |  |  | Closed | 24-Sep-25: Now its in 3 Languages |  |  | Siva Kumar |  |  | COMPLETED & APPROVED | [9 empty] | MOMHelpdesk | Helpdesk (Contact Center) | CLOSED |  |  |  | 2025-09-24 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\M121,170,99,726 |  | 1
1448 | M727 | MOM | 2023-08-01 |  |  |  | Helpdesk | Launch Readiness | Unclear about support for integration with WhatsApp. |  | Critical | open |  |  |  | WIP | 11-Se-25:This Prouct Not Support |  |  | Siva Kumar |  | Open | WIP | [9 empty] | MOMHelpdesk | Helpdesk (Contact Center) | OPEN | [6 empty] | 1
1449 | M728 | MOM | 2023-08-01 |  |  |  | Helpdesk | Resource Augmentation | Confirm if the current load handled by Helpdesk is sufficient. |  | Critical | open |  |  |  | Closed | 24-Sep-25: Artefcats to be submitted 11-Sep-25: Data Shared |  |  | Siva Kumar |  |  | COMPLETED & APPROVED | [9 empty] | MOMHelpdesk | Helpdesk (Contact Center) | CLOSED |  |  |  | 2025-09-24 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\M117,126,728 |  | 1
1450 | M729 | MOM | 2023-08-01 |  |  |  | Helpdesk | Launch Readiness | Concern over non-availability of Helpdesk Manager between 10 PM – 6 AM and how emergencies are handled during this time. |  | Critical | open |  |  |  | Closed | 24-Sep-25: Existing Lead available during Business Hours, Remaining duration Shift Lead will Manage |  |  | Siva Kumar |  |  | COMPLETED & APPROVED | [9 empty] | MOMHelpdesk | Helpdesk (Contact Center) | CLOSED |  |  |  | 2025-09-24 | Artefacts not Required |  | 1
1451 | M73 | MOM | 2023-07-26 |  |  |  | WFM | User Experience | Support for translation to Telugu |  | Critical | Open |  |  |  |  | As per OEM this point is not feasible 11 July 2025:- A follow-up discussion with the OEM is required to assess feasibility. If it is found to be unfeasible, a call should be arranged with Sanjay Sir along with the OEM team & artefacts needs to submit |  |  | Kaushalendra Kumar |  | Open | Not Feasible | [9 empty] | MOMWFM | Applications/Tools | #N/A |  |  |  |  | #N/A |  | 1
1452 | M730 | MOM | 2023-08-01 |  |  |  | NOC Operationalization | Launch Readiness | The relationship between people and functions as realised by RASCI matrix needs improvement. |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1
1453 | M731 | MOM | 2023-08-01 |  |  |  | Helpdesk | Launch Readiness | Differentiate between registered users and registered numbers. |  | Critical | Open |  |  |  | WIP | 11-Sep-25: BSS Integration to be completed |  |  | Siva Kumar |  | Open | WIP | [9 empty] | MOMHelpdesk | Helpdesk (Contact Center) | OPEN | [6 empty] | 1
1454 | M732 | MOM | 2023-08-01 |  |  |  | Helpdesk | Launch Readiness | Resolve confusion over the categorisation of incoming queries. |  | Critical | open |  |  |  | WIP |  |  |  | Siva Kumar |  | Open | WIP | [9 empty] | MOMHelpdesk | Helpdesk (Contact Center) | OPEN | [6 empty] | 1
1455 | M733 | MOM | 2023-08-01 |  |  |  | Helpdesk |  | Check how the Call management system can support live intrusion of calls for instant feedback. |  | Critical | open |  |  |  | Artefacts to be submitted | 24-Sep-25:Artefacts to be submitted 11-Sep-25: Feature is available, Shall be demonstrated |  |  | Siva Kumar |  |  | COMPLETED & APPROVED | [9 empty] | MOMHelpdesk | Helpdesk (Contact Center) | CLOSED |  |  |  | 2025-09-24 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\M119,733 |  | 1
1456 | M734 | MOM | 2023-08-01 |  |  |  | Helpdesk |  | Define how readiness of Helpdesk to report on compliances and responsiveness and penalties calculation. |  | Critical | open |  |  |  | WIP |  |  |  | Siva Kumar |  | Open | WIP | [9 empty] | MOMHelpdesk | Helpdesk (Contact Center) | OPEN | [6 empty] | 1
1457 | M735 | MOM | 2023-08-04 |  |  |  | Helpdesk |  | Determine how the Helpdesk to NOC and Field is going to be integrated with the operational framework when they currently lack synergy. |  | Critical | open |  |  |  | WIP | 11-Sep-25: IVR Flows are aligned accordingly, Post Approval and Implementation we can meet expectations |  |  | Siva Kumar |  |  | COMPLETED & APPROVED | [9 empty] | MOMHelpdesk | Helpdesk (Contact Center) | CLOSED |  |  |  | 2025-09-24 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\M725,735 |  | 1
1458 | M736 | MOM | 2023-08-04 |  |  |  | Helpdesk |  | Concern over Toll-free levels availability for the Helpdesk. |  | Critical | Open |  |  |  | WIP |  |  |  | Siva Kumar |  | Open | WIP | [9 empty] | MOMHelpdesk | Helpdesk (Contact Center) | OPEN | [6 empty] | 1
1459 | M737 | MOM | 2023-08-18 |  |  |  | BSS | NSO | BSS Readiness and Demo: L&T to demonstrate Static IP and UI/UX changes, with WFM integration not part of the demonstration. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1460 | M738 | MOM | 2023-08-18 |  |  |  | WFM | WFM Application | WFM Tool Usage Demonstration: L&T to arrange a demonstration of WFM tool usage for field operations soon. |  | Critical | Open |  |  |  |  | Duplicate with Point- 235 |  |  | Kaushalendra Kumar |  | Open | Duplicate | [9 empty] | MOMWFM | Applications/Tools | #N/A |  |  |  |  | #N/A |  | 1
1461 | M739 | MOM | 2023-08-18 |  |  |  | BSS | Billing Related | Payment Gateway Completion: L&T to complete the payment gateway by 30th September '23 if SSL Certificate is provided by 11th September '23. |  | Critical | Open |  |  |  |  | DUPLICATE POINT (M739) |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1462 | M74 | MOM | 2023-07-26 |  |  |  | WFM | Handbook & SOPs | Scope of Order Processing and Service Ticket Management |  | Critical | Open | [7 empty] | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMWFM | Applications/Tools | OPEN | [6 empty] | 1
1463 | M740 | MOM | 2023-08-18 |  |  |  | Security & Regulatory Compliance | Compliance | Security Related Activities: L&T to address various security and compliance sub-activities with specific target dates. |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1
1464 | M741 | MOM | 2023-08-18 |  |  |  | BSS | BSS | BSS Integration with Lepton WFM: L&T to complete the demo of BSS Integration with Lepton WFM by 25th August '23. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1465 | M742 | MOM | 2023-08-18 |  |  |  | BSS | NSO | NSO Competency Plan: L&T to put in place an NSO competency plan. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1466 | M743 | MOM | 2023-08-18 |  |  |  | BSS | T&D Environment | Separation of T&D and Production Environments: L&T to provide a plan addressing the requirement for separate environments. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1467 | M744 | MOM | 2023-08-18 |  |  |  | BSS | Resource Augmentation | Onboarding of Billing Specialist: L&T to update on the onboarding process for a long-term Billing Specialist. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1468 | M745 | MOM | 2023-08-18 |  |  |  | BSS | Billing Related | Closure of CRM Billing Process and Invoice Format: L&T to close action items regarding CRM Billing Process and Invoice format. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1469 | M746 | MOM | 2023-08-18 |  |  |  | BSS | T&D Environment | BSS Roadmap Progress: L&T to demonstrate completed points for closure and include related test cases. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1470 | M747 | MOM | 2023-08-18 |  |  |  | BSS | Dry Run | Next BSS Demo for Cell Tower: L&T to confirm the date of the next BSS Demo for Cell Tower by 21st August '23. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1471 | M748 | MOM | 2023-08-18 |  |  |  | BSS | Dry Run | User Groups Demonstration: L&T to showcase the demonstration on user groups along with the demo for Cell Tower. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1472 | M749 | MOM | 2023-08-18 |  |  |  | BSS | Dry Run | Next BSS Demo Schedule: Scheduled for 23rd August '23, to include RFS/RFO status, notification templates, UI/UX validation, and exception scenarios. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1473 | M75 | MOM | 2023-07-26 |  |  |  | WFM | Handbook & SOPs | Document references in SOW to be shared |  | Critical | Open | [7 empty] | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMWFM | Applications/Tools | OPEN | [6 empty] | 1
1474 | M750 | MOM | 2023-08-18 |  |  |  | BSS | Regulatory Compliance | Regulatory Reports Review: L&T to identify available reports in BSS as Ready/WIP by 21st August '23 and review with T-Fiber for approval. |  | Critical | Open |  |  |  |  | DUPLICATE POINT (M688) |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1475 | M751 | MOM | 2023-08-18 |  |  |  | BSS |  | Dedication of Time to T-Fiber Project: Chief Delivery Officer, L&T to confirm dedicating 2 days a week to the T-Fiber Project in Hyderabad leading up to the Network Launch. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1476 | M752 | MOM | 2023-08-23 |  |  |  | BSS |  | Review of alert and notification templates and implementation. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1477 | M753 | MOM | 2023-08-23 |  |  |  | BSS |  | Lead data presentation for Airtel and GI_BB customers. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1478 | M754 | MOM | 2023-08-23 |  |  |  | BSS |  | Walkthrough of Ready for Service (RFS) Process. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1479 | M755 | MOM | 2023-08-23 |  |  |  | BSS |  | Identifying and addressing challenges for user experience in CRM. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1480 | M756 | MOM | 2023-08-23 |  |  |  | BSS |  | Development of BSS demo of CSP. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1481 | M757 | MOM | 2023-08-23 |  |  |  | BSS |  | Analysis of the issue impacting BSS demo. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1482 | M758 | MOM | 2023-08-23 |  |  |  | NOC Operationalization |  | Fixing issues with OSS - BSS integration. |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMNOC Operationalization | Network | OPEN | [6 empty] | 1
1483 | M759 | MOM | 2023-08-23 |  |  |  | BSS |  | Establish a comprehensive list of event notification scenarios and implementation plan. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1484 | M76 | MOM | 2023-07-26 |  |  |  | WFM | User Experience | WFM tool's own Google Map |  | Critical | Open | [7 empty] | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMWFM | Applications/Tools | OPEN | [6 empty] | 1
1485 | M760 | MOM | 2023-08-23 |  |  |  | BSS |  | Identify and create more user groups according to the business and workflow requirements. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1486 | M761 | MOM | 2023-08-23 |  |  |  | BSS |  | Resolve discrepancies with manual updates for RFO and RFS status. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1487 | M762 | MOM | 2023-08-23 |  |  |  | WFM |  | Respond to the query of WFM integration. |  | Critical | Open | [7 empty] | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMWFM | Applications/Tools | OPEN | [6 empty] | 1
1488 | M763 | MOM | 2023-08-23 |  |  |  | BSS |  | Improve user experience for better data accuracy. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1489 | M764 | MOM | 2023-08-23 |  |  |  | BSS |  | Ensure the BSS-Lead, L&T and Head Telecom Practice, L&T to discuss and create more user groups according to the business and workflow requirements. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1490 | M765 | MOM | 2023-08-23 |  |  |  | BSS |  | Introduce a status/bucket "Renewal" for orders that need further work / rectification. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1491 | M766 | MOM | 2023-08-23 |  |  |  | BSS |  | Ensure that the entire network POI/ PoP status including 12751 GPs, 1 NOC, all zones, districts & Mandal nodes should be available in CRM database. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1492 | M767 | MOM | 2023-08-23 |  |  |  | BSS |  | Address observations made in the CSP by L&T and implement changes. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1493 | M768 | MOM | 2023-08-23 |  |  |  | BSS | T-Cell Launch | Propose the next date for T-Cell Demo. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1494 | M769 | MOM | 2023-08-31 |  |  |  | NOC Operationalization |  | L&T to review NOC readiness and demonstrate service excellence for launch; separate meeting for 360 View presentation on 31st August '23. |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMNOC Operationalization | Network | OPEN | [6 empty] | 1
1495 | M77 | MOM | 2023-07-26 |  |  |  | WFM | Improvement | Support for Re-assignment of workflow in case of leave |  | Critical | Open | [7 empty] | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMWFM | Applications/Tools | OPEN | [6 empty] | 1
1496 | M770 | MOM | 2023-08-31 |  |  |  | NOC Operationalization | Launch Readiness | Implement IST in SCCM and confirm BSS readiness for live customers like Airtel by 31st August '23. |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMNOC Operationalization | Network | OPEN | [6 empty] | 1
1497 | M771 | MOM | 2023-08-31 |  |  |  | NOC Operationalization | NOC Operationalization | Data cleanup before Airtel onboarding and present GI migration approach from trial to production. |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1
1498 | M772 | MOM | 2023-08-31 |  | OSS | Security & OSS | All Domain | WhatsApp | List pending action items from T-Fiber; SSL certificate and WhatsApp Integration expected closure in 2-3 days. |  | NON-Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMAll Domain | Applications/Tools | OPEN | [6 empty] | 1
1499 | M773 | MOM | 2023-08-31 |  |  |  | BSS |  | Share status updates on BSS action items by 1st September '23. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1500 | M774 | MOM | 2023-08-31 |  |  |  | WFM |  | Schedule WFM integration with BSS demo for 15th September '23. |  | Critical | Open | [7 empty] | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMWFM | Applications/Tools | OPEN | [6 empty] | 1
1501 | M775 | MOM | 2023-09-08 |  |  |  | Field Related | GI Connectivity | Rectification and progress of GI Connectivity. |  | NON-Critical | Open |  |  |  |  | Maintainance in progress for go Live districts |  |  | S Kodali |  | Open | Open | [9 empty] | MOMField Related | Field Related issues | OPEN |  |  | O&M Team |  | #N/A |  | 1
1502 | M776 | MOM | 2023-09-08 |  |  |  | NOC Operationalization | Launch Readiness | Completion of Pause-Mechanism and QOS Visibility part of the committed deliverables. |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMNOC Operationalization | Network | OPEN | [6 empty] | 1
1503 | M777 | MOM | 2023-09-08 |  |  |  | NOC Operationalization | Launch Readiness | Reviewing readiness for launch, readiness of O&M Approach, and readiness of NOC from a multiple perspectives. |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMNOC Operationalization | Network | OPEN | [6 empty] | 1
1504 | M778 | MOM | 2023-09-08 |  |  |  | NOC Operationalization |  | Submissio of module wise Functional Acceptance Test Plan. |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMNOC Operationalization | Network | OPEN | [6 empty] | 1
1505 | M779 | MOM | 2023-09-08 |  |  |  | NOC Operationalization | Launch Readiness | Implementation and readiness in order for Interim Launch from NOC to field level. |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1
1506 | M78 | MOM | 2023-07-26 |  |  |  | WFM | Improvement | Support for pre-defined routes |  | Critical | Open | [7 empty] | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMWFM | Applications/Tools | OPEN | [6 empty] | 1
1507 | M780 | MOM | 2023-09-08 |  |  |  | Security & Regulatory Compliance | NOC Operationalization | Establishing a security system including hardware, IT Infra, and Applications security certifications. |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1
1508 | M781 | MOM | 2023-09-08 |  |  |  | NOC Operationalization |  | Submit report capturing the number of test cases and their status. |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMNOC Operationalization | Network | OPEN | [6 empty] | 1
1509 | M782 | MOM | 2023-09-08 |  |  |  | NOC Operationalization | Launch Readiness | Include more sample sites in the 2nd Dry Run by the end of September' 23. |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1
1510 | M783 | MOM | 2023-09-08 |  |  |  | NOC Operationalization | Launch Readiness | Review and finalize the process design related to Service Delivery linked to manpower. |  | Critical | Open |  |  |  | Closed, Artefacts to be uploaded | 23-Sep-25: Approved Artefacts to be Submitted | L&T | Sivaprasad | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  |  | Artefacts Need to upload |  | 1
1511 | M784 | MOM | 2023-09-08 |  |  |  | NOC Operationalization |  | LLD (Revised) with OADM Solution (Ciena) |  | NON-Critical | Open | [7 empty] | Suresh Kumar |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  |  | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\DWDM\Artefact - T90 |  | 1
1512 | M785 | MOM | 2023-09-08 |  |  |  | T&D Environment | Testing Environment | BSS T&D license to be accessible by 30/6/23. It will be moved to a production environment afterward. |  | NON-Critical | Open |  |  |  |  | [15/09/2025] KNOT BSS T&D is setup |  |  | Ravi Kishore |  |  | COMPLETED & APPROVED | [9 empty] | MOMT&D Environment | Applications | CLOSED |  |  |  |  | Artefacts Need to upload |  | 1
1513 | M786 | MOM | 2023-09-08 |  |  |  | NOC Operationalization | Launch Readiness | The readiness of E2E NOC will be reviewed and updated by 8th Sep ‘23. |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1
1514 | M787 | MOM | 2023-09-08 |  |  |  | NOC Operationalization | Launch Readiness | The status of pending deliverables that were committed for delivery by 15th August ’23 has not been mentioned to have been met by specific dates. |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1
1515 | M788 | MOM | 2023-09-08 |  |  |  | NOC Operationalization | Launch Readiness | T-NOC Readiness Confirmation: EVP, T-Fiber requested confirmation on launch deliverables and interim launch processes by EOD 8th September '23. |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1
1516 | M789 | MOM | 2023-09-08 |  |  |  | NOC Operationalization |  | Review of Pending Activities: Director-P&E, T-Fiber to review and update the status of 92 pending activities related to the 15th August '23 deliverables. |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1
1517 | M79 | MOM | 2023-07-26 |  |  |  | WFM | User Experience | Support for recording timeclocks of patrol routes |  | Critical | Open | [7 empty] | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMWFM | Applications/Tools | OPEN | [6 empty] | 1
1518 | M790 | MOM | 2023-09-08 |  |  |  | NOC Operationalization |  | Revised LLD for DWDM: Technical Head, L&T submitted the revised LLD for approval. |  | NON-Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1
1519 | M791 | MOM | 2023-09-08 |  |  |  | Security & Regulatory Compliance | Compliance | Risk Assessment: VP-Program emphasized the need for a Risk register with a responsible SPOC and response plan. |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1
1520 | M792 | MOM | 2023-09-08 |  |  |  | BSS |  | Payment Gateway Completion: L&T to complete the payment gateway by 30th September '23 if SSL Certificate is provided by 11th September '23. |  | Critical | Open |  |  |  |  | DUPLICATE POINT (M739) |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1521 | M793 | MOM | 2023-09-08 |  |  |  | Security & Regulatory Compliance | Compliance | Security Related Activities: Director-P&E, T-Fiber stressed the importance of security activities for launch and regulatory compliances. |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1
1522 | M794 | MOM | 2023-09-08 |  |  |  | Security & Regulatory Compliance | Compliance | Security and Compliance Sub-Activities: L&T to address various security and compliance sub-activities with specific target dates ranging from 31st August to 15th September '23. |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1
1523 | M795 | MOM | 2023-09-08 |  |  |  | Security & Regulatory Compliance | Compliance | Alepo AAA and TACACS Integration: Alepo to test integration with Nokia and Ciena nodes on TACACS with supporting artefacts of testing. |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1
1524 | M796 | MOM | 2023-09-08 |  |  |  | Security & Regulatory Compliance | Compliance | OSS Firewall Ports: L&T to address OSS firewall ports required for security compliance. |  | Critical | Open | [7 empty] | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN | COMPLETED | 0 |  |  | #N/A |  | 1
1525 | M797 | MOM | 2023-09-08 |  |  |  | Security & Regulatory Compliance | Compliance | Security LLD: Customer requested a complete Security LLD that outlines the security architecture and interactions between security products. |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1
1526 | M798 | MOM | 2023-09-08 |  |  |  | Security & Regulatory Compliance | Compliance | External Audit and VAPT: L&T to conduct external audits and vulnerability assessments for applications and network elements. |  | Critical | Open |  |  |  |  | Audit done by Allied Boston. And further external audit to be done by TFiber vendor |  |  | Sarmendra |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | Artefacts to be Submitted |  | 1
1527 | M799 | MOM | 2023-09-12 |  |  |  | WFM |  | L&T is to submit a proposal to T-Fiber on the scope to be showcased in the proposed WFM-BSS demonstration. |  | Critical | Open | [7 empty] | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMWFM | Applications/Tools | OPEN | [6 empty] | 1
1528 | M8 | MOM | 2023-04-03 |  |  |  | NOC Operationalization | Full NOC Readiness | All Test Plans to be submitted to TPA in coordination with Package B&C; reviewed by Assistant Director Technical, T-Fiber. |  | Critical | Open |  | OSS Dashboards |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1
1529 | M80 | MOM | 2023-07-26 |  |  |  | WFM | User Experience | Support for Barcode and QR code scanning |  | Critical | Open | [7 empty] | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMWFM | Applications/Tools | OPEN | [6 empty] | 1
1530 | M800 | MOM | 2023-09-12 |  |  |  | WFM |  | L&T is to identify a product owner for WFM. |  | Critical | Open | [7 empty] | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMWFM | Applications/Tools | OPEN | [6 empty] | 1
1531 | M801 | MOM | 2023-09-22 |  |  |  | NOC Operationalization | Launch Readiness | Overcoming technical issues hampering the setup for the 1st Dry Run. |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1
1532 | M802 | MOM | 2023-09-22 |  |  |  | NOC Operationalization | Launch Readiness | Reviewing the setup for 1st Dry Run observed by the EVP, T-Fiber. |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1
1533 | M803 | MOM | 2023-09-22 |  |  |  | NOC Operationalization | Launch Readiness | Gaining clarity on roles and functionalities of NSO and OSS. |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMNOC Operationalization | Network | OPEN | [6 empty] | 1
1534 | M804 | MOM | 2023-09-22 |  |  |  | BSS |  | Overcoming technical issues observed in CSP and CRM. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1535 | M805 | MOM | 2023-09-22 |  |  |  | BSS |  | Reviewing processes of order booking to be communicated more simply and effectively to the end users. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1536 | M806 | MOM | 2023-09-22 |  |  |  | NOC Operationalization |  | L&T to identify provisioning/monitoring features limited because of interoperability issues in a multi-vendor eco-system. |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMNOC Operationalization | Network | OPEN | [6 empty] | 1
1537 | M807 | MOM | 2023-09-22 |  |  |  | NOC Operationalization |  | L&T to articulate how NSO and OSS are complementing each other and their roles in service provisioning. |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMNOC Operationalization | Network | OPEN | [6 empty] | 1
1538 | M808 | MOM | 2023-09-22 |  |  |  | NOC Operationalization |  | L&T to provide the redundancy plan if entire DC were to go down and the backup measures if NSO were to fail. |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMNOC Operationalization | Network | OPEN | [6 empty] | 1
1539 | M809 | MOM | 2023-09-22 |  |  |  | NOC Operationalization |  | L&T to work towards a system that is foolproof, automated, futuristic, and provides seamless service experience for end users. |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMNOC Operationalization | Network | OPEN | [6 empty] | 1
1540 | M81 | MOM | 2023-07-26 |  |  |  | WFM | Handbook & SOPs | Confirmation of SOW addressing Packages B and C |  | Critical | Open | [7 empty] | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMWFM | Applications/Tools | OPEN | [6 empty] | 1
1541 | M810 | MOM | 2023-09-22 |  |  |  | NOC Operationalization | Dry Run | L&T to propose the date for the 2nd Dry Run inclusive of Internet Leased Line, P2P, and P2MP flavors of service. |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1
1542 | M811 | MOM | 2023-09-22 |  |  |  | NOC Operationalization | Dry Run | L&T to confirm target date for E2E BSS Demo. |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMNOC Operationalization | Network | OPEN | [6 empty] | 1
1543 | M812 | MOM | 2023-09-22 |  |  |  | NOC Operationalization | Dry Run | L&T to consider the creation of a template for tracking observations. |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1
1544 | M813 | MOM | 2023-09-22 |  |  |  | NOC Operationalization | NSO | Provision of training for L&T pool of resources in NSO and development of NEDs. |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMNOC Operationalization | Network | OPEN | [6 empty] | 1
1545 | M814 | MOM | 2023-09-22 |  |  |  | NOC Operationalization |  | L&T to create a timetable displaying the percentage of progress on activities week-wise and fortnight-wise. |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1
1546 | M815 | MOM | 2023-09-22 |  |  |  | NOC Operationalization |  | L&T to confirm the features ready for showcase in the E2E Demo by 25th September’23. |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1
1547 | M816 | MOM | 2023-09-22 |  |  |  | NOC Operationalization |  | Target the 2nd Dry Run on 30th September ’23 with more ONTs, covering GI BB, Point to point, dedicated ILL & Dark fiber by end of L&T. |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1
1548 | M817 | MOM | 2024-09-26 |  |  |  | T&D Environment | AT Process | Defining and aligning with the acceptance criteria for each system in the NOC. |  | NON-Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMT&D Environment | Applications | OPEN | [6 empty] | 1
1549 | M818 | MOM | 2023-09-26 |  |  |  | Helpdesk |  | Inclusion of Helpdesk and other missing items as per the RFP and solution in the Build. |  | Critical | Open |  |  |  | Closed | 24-Sep-25: Approved and shall be closed, Accordingly Helpdesk LLD Aligning |  |  | Siva Kumar |  |  | COMPLETED & APPROVED | [9 empty] | MOMHelpdesk | Helpdesk (Contact Center) | CLOSED |  |  |  | 2025-09-24 | Artefacts not Required |  | 1
1550 | M819 | MOM | 2023-09-26 |  |  |  | T&D Environment | T&D Environment | Implementation of Test and Development environment. |  | NON-Critical | Open |  |  |  |  | [15/09/2025] Clusters are segregated for Production vis-à-vis pre-production |  |  | Ravi Kishore |  |  | COMPLETED & APPROVED | [9 empty] | MOMT&D Environment | Applications | CLOSED |  |  |  |  | Artefacts Need to upload |  | 1
1551 | M82 | MOM | 2023-07-26 |  |  |  | WFM | User Experience | Clear definition and availability of existing filters in WFM dashboards |  | Critical | Open |  |  |  |  | 11-7-2025:- The dashboard and report filter options should be showcased during the WFM application demonstration. |  |  | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMWFM | Applications/Tools | OPEN | [6 empty] | 1
1552 | M820 | MOM | 2023-09-26 |  |  |  | T&D Environment | T&D Environment | Discussion on the requirements for Test Lab/Staging environment. |  | NON-Critical | Open |  |  |  |  | [15/09/2025] Interim T&D is setup, finalised option detailing pending |  |  | Ravi Kishore |  |  | COMPLETED & APPROVED | [9 empty] | MOMT&D Environment | Applications | CLOSED |  |  |  |  | Artefacts Need to upload |  | 1
1553 | M821 | MOM | 2023-10-18 |  |  |  | BSS | CSP Testing | Adding a back button on the payment screen. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1554 | M822 | MOM | 2023-10-18 |  |  |  | BSS | CSP Testing | Providing guidelines for the CAF upload stage and adding a disclaimer for "Subject to Verification of CAF." |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1555 | M823 | MOM | 2023-10-18 |  |  |  | BSS | CSP Testing | Ensuring offline payment transactions are viewable and mandatory sections of the CAF are highlighted. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1556 | M824 | MOM | 2023-10-18 |  |  |  | BSS | CSP Testing | Addressing issues with ticket creation, notification, and enquiry handling in the CSP. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1557 | M825 | MOM | 2023-10-18 |  |  |  | BSS | CSP Testing | Clarifying the bulk upload of leads and the feasibility of integrating such a feature in the CSP. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1558 | M826 | MOM | 2023-10-18 |  |  |  | BSS | CSP Testing | Resolving user interface issues such as incorrect OTP entry pop-ups, case sensitivity in order ID searches, and real-time synchronization between GIS-OSS for feasibility checks. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1559 | M827 | MOM | 2023-10-18 |  |  |  | BSS | CSP Testing | Removing unnecessary elements from the UI, aligning GP names with government lists, and modifying the sequence of address fields. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1560 | M828 | MOM | 2023-10-18 |  |  |  | BSS | CSP Testing | Integrating Google API for auto-populating details based on service location selection. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1561 | M829 | MOM | 2023-10-18 |  |  |  | BSS | CSP Testing | Ensuring proper display and functionality of various screens within the CSP, including payment and order summary screens. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1562 | M83 | MOM | 2023-07-26 |  |  |  | WFM | User Experience | Upload of video |  | Critical | Open |  |  |  |  | As per OEM this point is not feasible 11 July 2025:- A follow-up discussion with the OEM is required to assess feasibility. If it is found to be unfeasible, a call should be arranged with Sanjay Sir along with the OEM team & artefacts needs to submit |  |  | Kaushalendra Kumar |  | Open | Not Feasible | [9 empty] | MOMWFM | Applications/Tools | #N/A |  |  |  |  | #N/A |  | 1
1563 | M830 | MOM | 2023-10-18 |  |  |  | BSS | CSP Testing | Configuring event-based email notifications for actions within the CSP. |  | NON-Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1564 | M831 | MOM | 2023-10-19 |  |  |  | IPDR | Regulatory Compliance | Clarity from the Regulator on IPDR requirements to be obtained by L&T: Discussion on industry best practices and regulatory aspects to be concluded by 26th October '23. |  | Critical | Open | [7 empty] | Jayant Madavi |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMIPDR | Applications/Tools | OPEN |  |  |  |  | Artefacts to be uploaded |  | 1
1565 | M832 | MOM | 2023-11-03 |  |  |  | NSO | Service Delivery | UD,SD Peramaters to be captured. |  | Critical | Open | [7 empty] | Jayant Madavi |  | Open | Open | [9 empty] | MOMNSO | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1566 | M833 | MOM | 2023-11-03 |  |  |  | NSO | Service Delivery | NSo inventory manager funtionality to check. |  | Critical | Open | [7 empty] | Jayant Madavi |  | Open | Open | [9 empty] | MOMNSO | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1567 | M834 | MOM | 2023-11-03 |  |  |  | NSO | Service Delivery | UD perameters for product based to be prepared. |  | Critical | Open | [7 empty] | Jayant Madavi |  | Open | Open | [9 empty] | MOMNSO | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1568 | M835 | MOM | 2023-11-03 |  |  |  | NSO | Service Delivery | Ashish to comeback with Design plan for Inventory Manager at NSO |  | Critical | Open | [7 empty] | Jayant Madavi |  | Open | Open | [9 empty] | MOMNSO | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1569 | M836 | MOM | 2023-11-03 |  |  |  | NSO | Service Delivery | Arvindam to comeback with product wise UD perameters |  | Critical | Open | [7 empty] | Jayant Madavi |  | Open | Open | [9 empty] | MOMNSO | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1570 | M837 | MOM | 2023-11-03 |  |  |  | NSO | Service Delivery | Additional information for VRF, VLAN , Inner vlan etc to capture in Master DB |  | Critical | Open | [7 empty] | Jayant Madavi |  | Open | Open | [9 empty] | MOMNSO | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1571 | M838 | MOM | 2023-11-03 |  |  |  | NSO | Service Delivery | As per Cisco LLD All 28 types of L2, L3 models to be mapped aginest products |  | Critical | Open | [7 empty] | Jayant Madavi |  | Open | Open | [9 empty] | MOMNSO | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1572 | M839 | MOM | 2023-11-03 |  |  |  | NSO | Service Delivery | GL code to be mapped based on subtype GI under sub type Central & State |  | Critical | Open | [7 empty] | Jayant Madavi |  | Open | Open | [9 empty] | MOMNSO | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1573 | M84 | MOM | 2023-07-26 |  |  |  | WFM | Dashboards | Support for Workforce Management productivity statistics |  | Critical | Open |  |  |  |  | 11-7-2025:- Various reports should be demonstrated during the WFM application demo to showcase its capabilities. |  |  | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMWFM | Applications/Tools | OPEN | [6 empty] | 1
1574 | M840 | MOM | 2023-11-03 |  |  |  | NSO | Service Delivery | Definbe the Code for Circuit type , Customer type , customer service type etc in single format |  | Critical | Open | [7 empty] | Jayant Madavi |  | Open | Open | [9 empty] | MOMNSO | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1575 | M841 | MOM | 2023-11-03 |  |  |  | NSO | Service Delivery | Define design plan for House hold services in GPON Level |  | Critical | Open | [7 empty] | Jayant Madavi |  | Open | Open | [9 empty] | MOMNSO | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1576 | M842 | MOM | 2023-11-03 |  |  |  | NSO | Service Delivery | Define Household plan for provisioning as per the GPON plan design |  | Critical | Open | [7 empty] | Jayant Madavi |  | Open | Open | [9 empty] | MOMNSO | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1577 | M843 | MOM | 2023-11-03 |  |  |  | NSO | Service Delivery | OSS Method of distance from GIS need to comeback with plan |  | Critical | Open | [7 empty] | Jayant Madavi |  | Open | Open | [9 empty] | MOMNSO | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1578 | M844 | MOM | 2023-11-03 |  |  |  | NSO | Service Delivery | Aravindam to update on previous meetings updates to be updated in next in continuous meetings |  | Critical | Open | [7 empty] | Jayant Madavi |  | Open | Open | [9 empty] | MOMNSO | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1579 | M845 | MOM | 2023-11-17 |  |  |  | Helpdesk |  | Neox Helpdesk Demo: Scheduled for either 23rd or 24th November. |  | Critical | Open |  |  |  | WIP |  |  |  | Siva Kumar |  | Open | WIP | [9 empty] | MOMHelpdesk | Helpdesk (Contact Center) | OPEN | [6 empty] | 1
1580 | M846 | MOM | 2023-11-17 |  |  |  | Helpdesk |  | Neox Compliance Confirmation: Closed on 17th November. |  | Critical | open |  |  |  | WIP | 11-Sep-25 Same has been Submitted |  |  | Siva Kumar |  | Open | WIP | [9 empty] | MOMHelpdesk | Helpdesk (Contact Center) | OPEN | [6 empty] | 1
1581 | M847 | MOM | 2023-11-17 |  |  |  | Helpdesk |  | Reference for 24 Points: Praveen to share the reference of 24 points by 20th November. |  | Critical | open |  |  |  | WIP |  |  |  | Siva Kumar |  | Open | WIP | [9 empty] | MOMHelpdesk | Helpdesk (Contact Center) | OPEN | [6 empty] | 1
1582 | M848 | MOM | 2023-11-17 |  |  |  | OEM Related | GPON | Closure of Issues with Tejas & Nokia: Letter of confirmation for closure to be submitted on or before 30th November ’23. |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMOEM Related | OEM Related Issues | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1
1583 | M849 | MOM | 2023-11-17 |  |  |  | OEM Related | GPON | OEM Teams Onboarding: HP & Cisco OEM teams to be onboarded from 20th November '23. |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMOEM Related | OEM Related Issues | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1
1584 | M85 | MOM | 2023-07-26 |  |  |  | WFM | Improvement | Check if NOC Workforce Management is handled by the proposed WFM tool |  | Critical | Open |  |  |  |  | The WFM application is designed to manage field force operations, task assignments, and service delivery. Separate licenses & functionally & user role will be required for managing NOC resources. 11 July 2025:- A note needs to be sent to Sanjay Sir outlining the benefits, potential duplication of work, and any associated drawbacks. |  |  | Kaushalendra Kumar |  | Open | Open | [9 empty] | MOMWFM | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1585 | M850 | MOM | 2023-11-17 |  |  |  | OEM Related |  | Letters from OEMs: Letters from all OEMs, excluding Cisco & HP, to be submitted by 22nd November '23. Letters from Cisco & HP to be submitted by 24th November '23. |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMOEM Related | OEM Related Issues | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1
1586 | M851 | MOM | 2023-11-28 |  |  |  | Security & Regulatory Compliance | Compliance | Regulatory and Security Requirements: L&T to fast-track the closure of regulatory and security requirements, along with SLA monitoring for the immediate start of business services. |  | Critical | Open |  |  |  |  | Duplicate point. Hence clsoing this point |  |  | Sarmendra |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | Artefacts to be Submitted |  | 1
1587 | M852 | MOM | 2023-12-12 |  |  |  | NOC Operationalization |  | Submit updated Acceptable Usage Policy |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMNOC Operationalization | Network | OPEN | [6 empty] | 1
1588 | M853 | MOM | 2023-12-12 |  |  |  | Security & Regulatory Compliance | Compliance | Complete configuration of CA signed SSL certificate for all web-based applications |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1
1589 | M854 | MOM | 2023-12-12 |  |  |  | Security & Regulatory Compliance | Compliance | Obtain T-Fiber’s approval for annual external VAPT testing |  | Critical | Open |  |  |  |  | Audit done by Allied Boston. And further external audit to be done by TFiber vendor |  |  | Sarmendra |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | Artefacts to be Submitted |  | 1
1590 | M855 | MOM | 2023-12-12 |  |  |  | Security & Regulatory Compliance | Compliance | Submit Vulnerability Management Policy as part of Patch Management Policy |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1
1591 | M856 | MOM | 2023-12-12 |  |  |  | Security & Regulatory Compliance | Compliance | Submit a list of Security Policy documents and all SOPs, Checklist |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1
1592 | M857 | MOM | 2023-12-12 |  |  |  | Security & Regulatory Compliance | Compliance | Deliver security policy documents and SOPs for launch |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1
1593 | M858 | MOM | 2023-12-12 |  |  |  | Security & Regulatory Compliance | Compliance | Upload RMC MoMs to shared folder and grant access to T-Fiber |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1
1594 | M859 | MOM | 2023-12-12 |  |  |  | Security & Regulatory Compliance | Compliance | Provide comments against each sub-point in Internal Audit Report |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1
1595 | M86 | MOM | 2023-07-26 |  |  |  | WFM | Improvement | Coverage of Planned Event Manpower assignment by WFM solution |  | Critical | Open |  |  |  |  | OT System Dependency |  |  | Kaushalendra Kumar |  | Open | Open | [9 empty] | MOMWFM | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1596 | M860 | MOM | 2023-12-12 |  |  |  | Security & Regulatory Compliance | Compliance | Submit Asset Management policy |  | Critical | Open |  |  |  |  | Duplicate point. Hence clsoing this point |  |  | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1
1597 | M861 | MOM | 2023-12-12 |  |  |  | Security & Regulatory Compliance | Compliance | Submit onboarding/offboarding policy |  | Critical | Open |  |  |  |  | Duplicate point. Hence clsoing this point |  |  | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1
1598 | M862 | MOM | 2023-12-12 |  |  |  | Security & Regulatory Compliance | Compliance | Report on the management of physical and environmental security |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1
1599 | M863 | MOM | 2023-12-12 |  |  |  | Security & Regulatory Compliance | Compliance | Provide review of work scope for External VAPT prior |  | Critical | Open | [7 empty] | Sarmendra |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | Artefacts to be Submitted |  | 1
1600 | M864 | MOM | 2023-12-12 |  |  |  | Security & Regulatory Compliance | Compliance | Close Vulnerability & patch management after audit document is finalized |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1
1601 | M865 | MOM | 2023-12-12 |  |  |  | Security & Regulatory Compliance | Compliance | Submit Cryptography encryption model document |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1
1602 | M866 | MOM | 2023-12-12 |  |  |  | OEM Related | Tejas Related | Submit updated undertakings for Tejas - Alepo and Nokia |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMOEM Related | OEM Related Issues | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1
1603 | M867 | MOM | 2023-12-12 |  |  |  | Security & Regulatory Compliance | Compliance | Provide compliance with supporting documents for all applications & devices |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1
1604 | M868 | MOM | 2023-12-12 |  |  |  | Security & Regulatory Compliance | Compliance | Submit document on Privilege management |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1
1605 | M869 | MOM | 2023-12-12 |  |  |  | Security & Regulatory Compliance | Compliance | Submit a password management policy for the entire Network |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1
1606 | M87 | MOM | 2023-07-26 |  |  |  | WFM | Handbook & SOPs | Overall fitment of WFM in E2E applications architecture with integration touchpoints highlighted, along with the WFM flows |  | Critical | Open | [7 empty] | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMWFM | Applications/Tools | OPEN | [6 empty] | 1
1607 | M870 | MOM | 2023-12-12 |  |  |  | Security & Regulatory Compliance | Compliance | Disable all Remote access |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1
1608 | M871 | MOM | 2023-12-12 |  |  |  | Security & Regulatory Compliance | Compliance | Submit artefacts for all banners |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1
1609 | M872 | MOM | 2023-12-12 |  |  |  | Security & Regulatory Compliance | Compliance | Submit checklist of internal/external, Trusted, untrusted zones |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1
1610 | M873 | MOM | 2023-12-12 |  |  |  | Security & Regulatory Compliance | Compliance | Submit details of the policies for DMZ and internet-facing interfaces |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1
1611 | M874 | MOM | 2023-12-12 |  |  |  | Security & Regulatory Compliance | Compliance | Re-audit of Section 4.8 with the response captured in 4 sub-points |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1
1612 | M875 | MOM | 2023-12-12 |  |  |  | Security & Regulatory Compliance | Compliance | Submit list of APIs for all applications with risk information & conduct detailed audit on API security |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1
1613 | M876 | MOM | 2023-12-12 |  |  |  | Security & Regulatory Compliance | Compliance | Submit Security Endpoints List of Infrastructure, Workstations, etc. |  | Critical | Open |  |  |  |  | Completed . Also Screenshot has been taken during security audit . |  |  | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1
1614 | M877 | MOM | 2023-12-12 |  |  |  | Security & Regulatory Compliance | Compliance | Provide a list of applications generating Syslog, not generating syslog |  | Critical | Open |  |  |  |  | integration of application with syslog is still undergoing will; be submitted soon. |  |  | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1
1615 | M878 | MOM | 2023-12-12 |  |  |  | Security & Regulatory Compliance | Compliance | Submit DR reports for all Applications that have been tested for DC-DR switchover |  | Critical | Open |  |  |  |  | DC-dr failover will be shown during FATS for Application |  |  | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1
1616 | M879 | MOM | 2023-12-12 |  |  |  | Security & Regulatory Compliance | Compliance | Submit attendance list for security awareness trainings, ensure all NOC resources attend |  | Critical | Open |  |  |  |  | Last training conducted on 23 May25, and mail sent |  |  | Sarmendra |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | Artefacts to be Submitted |  | 1
1617 | M88 | MOM | 2023-07-26 |  |  |  | WFM | Handbook & SOPs | Clarity required on the scope of WFM under Phase-2 and sharing of Phase-1 & 2 scope with T-Fiber |  | Critical | Open |  |  |  |  | BSS Integration was on phase-II however it has integrated in phase-I |  |  | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMWFM | Applications/Tools | OPEN | [6 empty] | 1
1618 | M880 | MOM | 2023-12-12 |  |  |  | Security & Regulatory Compliance | Compliance | Finalise the duration and frequency of backup, provide storage utilisation report weekly, provide config backup details of all routers/switches/devices, submit weekly report capturing online & offline storage status |  | Critical | Open |  |  |  |  | The point is already under discussion and duration of back up has been already mentioned as per ISO 27001 Data retention policy. Custoimer mat tailor it as per their requirement |  |  | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1
1619 | M881 | MOM | 2023-12-15 |  |  |  | WFM |  | WFM Tool Demonstration: L&T to arrange a demonstration of the WFM tool usage for field operations soon. |  | Critical | Open | [7 empty] | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMWFM | Applications/Tools | OPEN | [6 empty] | 1
1620 | M882 | MOM | 2023-12-15 |  |  |  | WFM |  | WFM Mobile App Features: L&T to provide clarity on GPS tracking availability, polling frequency, photo upload feature, file size limitations, and supported Android and iOS versions. |  | Critical | Open | [7 empty] | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMWFM | Applications/Tools | OPEN | [6 empty] | 1
1621 | M883 | MOM | 2023-12-15 |  |  |  | WFM |  | Offline Data Storage: L&T to address the lack of offline data storage feature in the mobile application. |  | Critical | Open |  |  |  |  | 11-7-2025:- Offline data, such as images and documents, can be uploaded either from the mobile gallery or directly using the camera. To support the storage of LIDAR survey data and GIS images, an 80 TB NAS storage system has already been deployed at the NOC Data Center |  |  | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMWFM | Applications/Tools | OPEN | [6 empty] | 1
1622 | M884 | MOM | 2023-12-15 |  |  |  | WFM |  | Workflow Simulation: L&T to simulate a fiber cut and explain the workflow for clearing the fault and updating GIS. |  | Critical | Open | [7 empty] | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMWFM | Applications/Tools | OPEN | [6 empty] | 1
1623 | M885 | MOM | 2023-12-15 |  |  |  | WFM |  | Security Assurance: L&T to provide the NDA signed with M/S Lepton, assure API security, and share the contract copy. |  | Critical | Open | [7 empty] | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMWFM | Applications/Tools | OPEN | [6 empty] | 1
1624 | M886 | MOM | 2023-12-15 |  |  |  | GIS | GIS Related | Geo-fencing: L&T to explain how geo-fencing shall work for a fiber route and how it will be assigned for Mandal and GP locations. |  | Critical | Open | [7 empty] | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMGIS | Applications/Tools | OPEN | [6 empty] | 1
1625 | M887 | MOM | 2023-12-15 |  |  |  | WFM | GIS Completion | Ticket Allocation: L&T to start manual ticket allocation and freeze the process for node and link ticket allocation. |  | Critical | Open | [7 empty] | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMWFM | Applications/Tools | OPEN | [6 empty] | 1
1626 | M888 | MOM | 2023-12-15 | P3 |  |  | NOC Operationalization | Operational Handbook | Operations Handbook: L&T to share document forms from the Operations Handbook to be used by the WFM app. |  | Critical | Open | [7 empty] | Ahmad | 2025-10-07 | Open | Open | [9 empty] | MOMNOC Operationalization | Network | OPEN |  |  | Documentation |  | #N/A |  | 1
1627 | M889 | MOM | 2023-12-15 |  |  |  | WFM |  | Summary Dashboards/Management Reports: L&T to provide inputs based on Operations best practices for weekly/monthly management reports from the WFM package. |  | Critical | Open | [7 empty] | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMWFM | Applications/Tools | OPEN | [6 empty] | 1
1628 | M89 | MOM | 2023-07-26 |  |  |  | WFM | Integration | Integration with Material Management systems, ERP systems, and On-Demand dashboards to be covered in Phase-2 |  | Critical | Open |  |  |  |  | For GI service delivery, the ONT inventory management feature has been given into the WFM application & integration completed between web & mobile also with BSS . application supports ONT authentication and inventory tracking. Additionally, various dashboards have been provided within the WFM application to enhance monitoring and management capabilities |  |  | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMWFM | Applications/Tools | OPEN | [6 empty] | 1
1629 | M890 | MOM | 2023-12-15 |  |  |  | WFM |  | The urgency for L&T to demonstrate the WFM tool for field operations and to provide detailed information on its features and capabilities. |  | Critical | Open | [7 empty] | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMWFM | Applications/Tools | OPEN | [6 empty] | 1
1630 | M891 | MOM | 2023-12-15 |  |  |  | WFM |  | The necessity for L&T to address the absence of offline data storage in the mobile application and to simulate a fiber cut workflow. |  | Critical | Open |  |  |  |  | Duplicate with Point- 237 |  |  | Kaushalendra Kumar |  | Open | Duplicate | [9 empty] | MOMWFM | Applications/Tools | #N/A |  |  |  |  | #N/A |  | 1
1631 | M892 | MOM | 2023-12-15 |  |  |  | WFM |  | The requirement for L&T to assure security in the WFM package, including API security and geo-fencing capabilities. |  | Critical | Open | [7 empty] | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMWFM | Applications/Tools | OPEN | [6 empty] | 1
1632 | M893 | MOM | 2023-12-15 |  |  |  | WFM |  | The expectation for L&T to provide comprehensive management reports and dashboards to support process improvements and operational efficiency. |  | Critical | Open | [7 empty] | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMWFM | Applications/Tools | OPEN | [6 empty] | 1
1633 | M894 | MOM | 2023-12-19 |  |  |  | BSS |  | BSS Test Environment: VP-Program, T-Fiber requested BSS-SME, L&T to investigate and expedite the resolution of the slowness in the BSS Test Environment. |  | NON-Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1634 | M895 | MOM | 2023-12-19 |  |  |  | BSS |  | Performance Benchmarking Tools: BSS-SME, L&T to explore web-based analytic tools for performance benchmarking. |  | NON-Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1635 | M896 | MOM | 2023-12-19 |  |  |  | BSS |  | Status of Action Items: VP-Program, T-Fiber emphasized that action items marked as "Completed" should only be rendered "Closed" upon concurrence from T-Fiber. |  | NON-Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1636 | M897 | MOM | 2023-12-19 |  |  |  | BSS |  | SMS and CSP Integration: BSS-SME, L&T to implement SMS dispatch notification in CSP and include a link to the CSP page for T-Fiber USER to Approve or Reject. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1637 | M898 | MOM | 2023-12-19 |  |  |  | BSS |  | Product Catalogue Demo: SVP, T-Fiber requested a demo to showcase the configurable product catalogue feature. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1638 | M899 | MOM | 2023-12-19 |  |  |  | BSS |  | Backend Validation Demo: Director-P&E, T-Fiber asked for a demo of Backend Validation and a document with validation steps. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1639 | M9 | MOM | 2023-04-03 |  |  |  | NOC Operationalization | Full NOC Readiness | Demonstration of Repository Module |  | Critical | Open |  | Helpdesk |  | Closed | 24-Sep-25: Approved and shall be closed, its NAS Created in NOC for all Domains documentaton |  |  | Siva Kumar |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-24 | \\172.28.9.23\tnocreports |  | 1
1640 | M90 | MOM | 2023-07-26 |  |  |  | WFM | Improvement | Proposed WFM solution support field personnel to schedule appointments with end customers |  | Critical | Open |  |  |  |  | Customer appointment is being handled by BSS and FE appointment by WFM |  |  | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMWFM | Applications/Tools | OPEN | [6 empty] | 1
1641 | M900 | MOM | 2023-12-19 |  |  |  | BSS |  | Page Load Benchmark: Director-P&E, T-Fiber requested a benchmark for page loading to be defined. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1642 | M901 | MOM | 2023-12-19 |  |  |  | BSS |  | Payment Gateway Integration: BSS-SME, L&T confirmed integration is completed with a test account. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1643 | M902 | MOM | 2023-12-19 |  |  |  | BSS |  | BSS E2E Demo: Chief Delivery Officer, L&T proposed to have the E2E BSS Demo on 4th July '23, with features to be confirmed by 1st July '23. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1644 | M903 | MOM | 2023-12-19 |  |  |  | WFM |  | Mobile App & WFM: SVP, T-Fiber requested clarity on the number of mobile apps and urged L&T to freeze the scope in consultation with MSI B and C. Demo with M/S Lepton scheduled for 21st June '23. |  | Critical | Open |  |  |  |  | Duplicate with Point- 214 |  |  | Kaushalendra Kumar |  | Open | Duplicate | [9 empty] | MOMWFM | Applications/Tools | #N/A |  |  |  |  | #N/A |  | 1
1645 | M904 | MOM | 2023-12-19 |  |  |  | GIS | GIS Completion | BSS-SME, L&T to ensure Dark Fiber with BSS and WFM flows can be shown by 30th December '23. |  | Critical | Open |  |  |  |  | Pending with BSS Team |  |  | Kaushalendra Kumar |  | Open | Open | [9 empty] | MOMGIS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1646 | M905 | MOM | 2023-12-19 |  |  |  | NOC Operationalization | Launch Readiness | T-Cell, T-VPN, and GI-ILL Completion: SVP, T-Fiber called for these to be completed on priority before the visit by Hon’ Minister. |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMNOC Operationalization | Network | OPEN | [6 empty] | 1
1647 | M906 | MOM | 2023-12-19 |  |  |  | GIS | Feasibility Logic | Feasibility Logic: SVP, T-Fiber asked for the feasibility logic to include S1, S2 splitters and to be demonstrated in the next demo. |  | Critical | Open |  |  |  |  | Dependency On OSS Splitter View has been given to OSS team |  |  | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMGIS | Applications/Tools | OPEN | [6 empty] | 1
1648 | M907 | MOM | 2023-12-19 |  |  |  | OSS | Feasibility Logic | Bandwidth Feasibility Logic: Director-P&E, T-Fiber requested the logic for Bandwidth feasibility in the backhaul to be provisioned and operationalised immediately. |  | Critical | Open |  |  |  |  | This point not related to GIS,11th July 2025:- As discussed with Sanjay Sir, this points need to be move to the OSS team. |  |  | Suresh Pawar |  | Open | Shifted to OSS | [9 empty] | MOMOSS | Applications/Tools | #N/A | #N/A | #N/A |  |  | #N/A |  | 1
1649 | M908 | MOM | 2023-12-19 |  |  |  | BSS | Resource Augmentation | NMS Works Resources: SVP, T-Fiber requested a discussion with EVP, T-Fiber on the adequacy of NMS works resources. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN | [6 empty] | 1
1650 | M909 | MOM | 2023-12-19 |  |  |  | BSS | BSS | Repository Module for Document Upload: BSS-SME, L&T to ensure the module is available in CRM and discussed with OEM. |  | NON-Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN | [6 empty] | 1
1651 | M91 | MOM | 2023-07-26 |  |  |  | WFM | Handbook & SOPs | Finalization of Operational Processes linked to WFM workflows |  | Critical | Open | [7 empty] | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMWFM | Applications/Tools | OPEN | [6 empty] | 1
1652 | M910 | MOM | 2023-12-19 |  |  |  | BSS | WhatsApp | WhatsApp Integration: BSS-SME, L&T to incorporate advanced features into WhatsApp Integration with CSP. |  | NON-Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN | [6 empty] | 1
1653 | M911 | MOM | 2023-12-19 |  |  |  | BSS |  | UI/UX Resource: BSS-SME, L&T updated that an internal UI/UX resource has been onboarded. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1654 | M912 | MOM | 2023-12-19 |  |  |  | BSS |  | Discussions on the BSS roadmap, including the status of action items from the dry run and CSP testing exercise. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1655 | M913 | MOM | 2023-12-19 |  |  |  | Field Related | District Completion Target | The urgency for STL to complete E2E for additional districts by 07th April '23 and the need to resolve issues impacting project progress. |  | NON-Critical | Open | [7 empty] | S Kodali |  | Open | Open | [9 empty] | MOMField Related | Field Related issues | OPEN |  |  | Project Team |  | #N/A |  | 1
1656 | M914 | MOM | 2023-12-19 |  |  |  | NOC Operationalization |  | The necessity for STL to complete T-NOC Operationalization by 6th April 2023 to begin commercialization. |  | Critical | Open | [7 empty] | Ahmad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  | Not related to delivery | 2025-09-22 | Artefacts not Required |  | 1
1657 | M915 | MOM | 2023-12-19 |  |  |  | Field Related | Resource Augmentation | The requirement for STL to address resource productivity issues and ensure sufficient resources for project completion. |  | NON-Critical | Open | [7 empty] | S Kodali |  | Open | Open | [9 empty] | MOMField Related | Field Related issues | OPEN |  |  | Project Team |  | #N/A |  | 1
1658 | M916 | MOM | 2023-12-19 |  |  |  | Field Related | Payment Related | The need for T-Fiber to expedite payment processes and for STL to provide a senior resource to orchestrate project completion efforts. |  | NON-Critical | Open | [7 empty] | S Kodali |  | Open | Open | [9 empty] | MOMField Related | Field Related issues | OPEN |  |  | Project Team |  | #N/A |  | 1
1659 | M917 | MOM | 2023-12-19 |  |  |  | NOC Operationalization |  | The presentation of a comprehensive T-NOC operationalisation plan by STL, with clear phases and readiness stages. |  | Critical | Open | [7 empty] | Ahmad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  | Not related to delivery | 2025-09-22 | Artefacts not Required |  | 1
1660 | M918 | MOM | 2023-12-19 |  |  |  | Field Related | Zonal Path connectivity | The completion of zonal paths and the delivery of districts within the committed timelines. |  | NON-Critical | Open | [7 empty] | S Kodali |  | Open | Open | [9 empty] | MOMField Related | Field Related issues | OPEN |  |  | Project Team |  | #N/A |  | 1
1661 | M919 | MOM | 2023-12-28 |  |  |  | NOC Operationalization | Launch Readiness | Achieve T-VPN and T-DILL completion by 31st Jan '24; confirm Dark Fiber P2P link target date later. |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMNOC Operationalization | Network | OPEN | [6 empty] | 1
1662 | M92 | MOM | 2023-07-26 |  |  |  | WFM | Resource Related | Perpetual licenses for WFM |  | Critical | Open |  |  |  |  | TFIBER is a critical dependency for closing the WFM license |  |  | Kaushalendra Kumar |  | Open | Open | [9 empty] | MOMWFM | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1663 | M920 | MOM | 2023-12-28 |  |  |  | NOC Operationalization | Launch Readiness | Ensure basic products are available by end of April '24; complete all 28 products within 2 months beyond April '24. |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMNOC Operationalization | Network | OPEN | [6 empty] | 1
1664 | M921 | MOM | 2023-12-28 |  |  |  | NSO | Service Delivery | Develop Service Delivery – Provisioning through OSS module; address potential failures and industry best practices. |  | Critical | Open | [7 empty] | Jayant Madavi |  | Open | Open | [9 empty] | MOMNSO | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1665 | M922 | MOM | 2023-12-28 |  |  |  | OEM Related | Service Delivery | Manual KPI for service assurance due to lack of OEM confirmation; address concerns about NSO and OSS use. |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMOEM Related | OEM Related Issues | OPEN | [6 empty] | 1
1666 | M923 | MOM | 2023-12-28 |  |  |  | OEM Related |  | Align L&T and OEM with product vision and delivery cadence; consider product development strategy. |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMOEM Related | OEM Related Issues | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1
1667 | M924 | MOM | 2023-12-28 |  |  |  | NSO | Resource Augmentation | NSO resource available from 3rd January '24; ensure readiness to operate remotely and train L&T resources. |  | Critical | Open | [7 empty] | Jayant Madavi |  | Open | Open | [9 empty] | MOMNSO | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1668 | M925 | MOM | 2023-12-28 |  |  |  | NOC Operationalization | Launch Readiness | Conduct Dry Run for 3 Products (GI-BB, T-CELL, Dark Fiber) on 5th January '24 with BSS & WFM; share date soon. |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMNOC Operationalization | Network | OPEN | [6 empty] | 1
1669 | M926 | MOM | 2023-12-28 |  |  |  | NOC Operationalization | Communication Matrix | Initiate daily meetings with T-Fiber; share progress updates daily. |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1
1670 | M927 | MOM | 2023-12-28 |  |  |  | NOC Operationalization | O&M Related | Start daily uptime report immediately; resolve duplicate TroubleTicket issue within the week. |  | Critical | Open |  |  |  | Closed | 24-Sep-25: Approved and shall be closed |  |  | Siva Kumar |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-24 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\M927 |  | 1
1671 | M928 | MOM | 2023-12-28 |  |  |  | Security & Regulatory Compliance | Compliance | Clarify NOC resource roles and seating; discuss and fix scope for external audit by 3rd Jan '24; conduct External Audit by 31st January '24. |  | Critical | Open |  |  |  |  | Audit done by Allied Boston. And further external audit to be done by TFiber vendor. Scope has been submitted to customer for external Audit. NOC teams role and KRA shared with TFiber |  |  | Sarmendra |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | Artefacts to be Submitted |  | 1
1672 | M929 | MOM | 2023-12-28 |  |  |  | Helpdesk |  | Address maturity of the Helpdesk; clarify integration aspects and ensure Helpdesk is ready to handle calls. |  | Critical | Open |  |  |  | WIP |  |  |  | Siva Kumar |  | Open | WIP | [9 empty] | MOMHelpdesk | Helpdesk (Contact Center) | OPEN | [6 empty] | 1
1673 | M93 | MOM | 2023-07-26 |  |  |  | WFM | Handbook & SOPs | To check for potential overlapping functions between proposed WFM app and GIS O&M app, and accordingly streamline the Operational process |  | Critical | Open | [7 empty] | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMWFM | Applications/Tools | OPEN | [6 empty] | 1
1674 | M930 | MOM | 2023-12-28 |  |  |  | NOC Operationalization | Launch Readiness | Cover all requirements in the roadmap with completion dates; explore standard templates for SLA reports to settle invoices with BBNL. |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1
1675 | M931 | MOM | 2023-12-28 |  |  |  | NOC Operationalization | O&M Related | Provide clarity on Alarm Correlation, cross-domain RCA, SIA, Helpdesk design, Network and Service Topology. |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMNOC Operationalization | Network | OPEN | [6 empty] | 1
1676 | M932 | MOM | 2023-12-28 |  |  |  | NOC Operationalization | Launch Readiness | Deliver NOC before the end of T3 as mandated by EVP, T-Fiber. |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1
1677 | M933 | MOM | 2024-01-05 |  |  |  | BSS | BSS | BSS readiness |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1678 | M934 | MOM | 2024-01-05 |  |  |  | BSS | Product category | Unique ID – Naming Convention |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1679 | M935 | MOM | 2024-01-05 |  |  |  | NSO | Service provisioning | GUI Interface for NSO |  | Critical | Open | [7 empty] | Jayant Madavi |  | Open | Open | [9 empty] | MOMNSO | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1680 | M936 | MOM | 2024-01-05 |  |  |  | BSS | Billing Related | Payment Approach & Integration |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1681 | M937 | MOM | 2024-01-05 |  |  |  | BSS | Billing Related | Invoice Template |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1682 | M938 | MOM | 2024-01-05 |  |  |  | BSS | Billing Related | Integration of Bill Desk & Other Points |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1683 | M939 | MOM | 2024-01-18 |  |  |  | BSS | Product category | BSS progress session for Dark Fiber |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1684 | M94 | MOM | 2023-07-26 |  |  |  | WFM | Improvement | Manual overwrite of data |  | Critical | Open |  |  |  |  | 11-7-2025:-WFM does not allow any manual data overwrite scenarios |  |  | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMWFM | Applications/Tools | OPEN | [6 empty] | 1
1685 | M940 | MOM | 2024-01-18 |  |  |  | OSS | Integration | Integrate live data for location feasibility |  | Critical | Open |  | Gtech |  |  | This point not related to GIS,External Feasibility Tool is required ,11th July 2025:- As discussed with Sanjay Sir, this points need to be move to the OSS team. |  |  | Suresh Pawar |  | Open | Shifted to OSS | [9 empty] | MOMOSS | Applications/Tools | #N/A | #N/A | #N/A |  |  | #N/A |  | 1
1686 | M941 | MOM | 2024-01-18 |  |  |  | OSS | Integration | Review and align ‘Ready for Service’ nomenclature |  | Critical | Open |  | Gtech |  |  | This point not related to GIS, 11th July 2025:-this point needs to be discussed with Siva Sir to explore the possibility of accommodating the feature in the respective application, as it is not related to GIS |  |  | Suresh Pawar |  | Open | Shifted to OSS | [9 empty] | MOMOSS | Applications/Tools | #N/A | #N/A | #N/A |  |  | #N/A |  | 1
1687 | M942 | MOM | 2024-01-18 |  |  |  | BSS | CRM | Implement auto-population of fields in CRM |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1688 | M943 | MOM | 2024-01-18 |  |  |  | BSS |  | Implement user access control for RFO to RFS conversion |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1689 | M944 | MOM | 2024-01-18 |  |  |  | BSS | GIS | Integrate BSS with GIS for distance calculation |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1690 | M945 | MOM | 2024-01-18 |  |  |  | BSS |  | Provide updates and roadmap for Lead/Opportunity/Order conversion process |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1691 | M946 | MOM | 2024-01-18 |  |  |  | BSS |  | Implement Mandal to GP and Mandal to Mandal Dark fiber service |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1692 | M947 | MOM | 2024-01-18 |  |  |  | BSS |  | Clarify the list of individuals involved in BSS operations |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1693 | M948 | MOM | 2024-01-18 |  |  |  | BSS |  | Resolve document upload feature with order tagging |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1694 | M949 | MOM | 2024-01-18 |  |  |  | BSS |  | Prepare for soft launch in accordance with management's direction |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1695 | M95 | MOM | 2023-07-26 |  |  |  | WFM | User Experience | Verification process for checking whether the field technician has gone to the required location or not. |  | Critical | Open | [7 empty] | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMWFM | Applications/Tools | OPEN | [6 empty] | 1
1696 | M950 | MOM | 2024-01-18 |  |  |  | BSS |  | Upload BSNL locations for demonstration and discuss GIS integration and document repository issues |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1697 | M951 | MOM | 2024-01-18 |  |  |  | BSS |  | Confirm timeline for GI-BB and T-Cell |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1698 | M952 | MOM | 2024-01-18 |  |  |  | BSS |  | Discuss Route and Bridge Mode for Internet Leased Line product |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1699 | M953 | MOM | 2024-01-24 |  |  |  | NOC Operationalization |  | NOC Readiness Review |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1
1700 | M954 | MOM | 2024-01-24 |  |  |  | NOC Operationalization |  | Ensure full delivery of NOC including field O&M and basic six products |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1
1701 | M955 | MOM | 2024-01-24 |  |  |  | NOC Operationalization |  | Confirm readiness of all NOC modules including ticketing, Helpdesk and WFM |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMNOC Operationalization | Network | OPEN | [6 empty] | 1
1702 | M956 | MOM | 2024-01-24 |  |  |  | NOC Operationalization |  | Deliver service inventory module |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMNOC Operationalization | Network | OPEN | [6 empty] | 1
1703 | M957 | MOM | 2024-01-24 |  |  |  | NOC Operationalization |  | Create a tracker sheet for conditional approvals and workshop points |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMNOC Operationalization | Network | OPEN | [6 empty] | 1
1704 | M958 | MOM | 2024-01-24 |  |  |  | NOC Operationalization |  | Submit detailed plan for module-wise readiness |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1
1705 | M959 | MOM | 2024-01-24 |  |  |  | NOC Operationalization |  | Present documentation for automation of 6 products |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMNOC Operationalization | Network | OPEN | [6 empty] | 1
1706 | M96 | MOM | 2023-08-01 |  |  |  | Helpdesk | User Experience | Toll Free-Number |  | NON-Critical | Open |  |  |  |  | 11-09-2025: Same as T366(472) Closed |  |  | Siva Kumar |  |  | COMPLETED & APPROVED | Yes | 2025-07-19 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\T366 | [6 empty] | MOMHelpdesk | Helpdesk (Contact Center) | CLOSED |  |  |  | 2025-07-19 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\T366 |  | 1
1707 | M960 | MOM | 2024-01-24 |  |  |  | NOC Operationalization |  | Submit package for NOC readiness, roadmaps, and sheets |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1
1708 | M961 | MOM | 2024-01-24 |  |  |  | NOC Operationalization |  | Engage OEMs till end-to-end stabilization of services |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1
1709 | M962 | MOM | 2024-01-24 |  |  |  | NOC Operationalization |  | Discuss pending points and close the final scope with T-Fiber |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1
1710 | M963 | MOM | 2024-01-24 |  |  |  | NOC Operationalization |  | Share a business continuity plan for 6 manual to automated product transitions |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMNOC Operationalization | Network | OPEN | [6 empty] | 1
1711 | M964 | MOM | 2024-01-24 |  |  |  | NOC Operationalization |  | Present NOC pre-production testing and environment plan |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1
1712 | M965 | MOM | 2024-01-24 |  |  |  | NOC Operationalization |  | Confirm list of BSS operation team members |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1
1713 | M966 | MOM | 2024-01-24 |  |  |  | WFM | NOC Operationalization | Update the GIS data and confirm its operation SOP |  | Critical | Open | [7 empty] | Kaushalendra Kumar |  | Open | Open | [9 empty] | MOMWFM | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1714 | M967 | MOM | 2024-01-24 |  |  |  | NOC Operationalization |  | Deploy senior resource for managing T-Fiber helpdesk |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMNOC Operationalization | Network | OPEN | [6 empty] | 1
1715 | M968 | MOM | 2024-01-24 |  |  |  | NOC Operationalization |  | Separate helpdesk and call center desk with transition plan |  | Critical | Open |  |  |  | WIP | Only technical helpdesk in scope which is operational | T Fiber | Sanjay | Siva Kumar |  | Open | WIP | [9 empty] | MOMNOC Operationalization | Network | OPEN | [6 empty] | 1
1716 | M969 | MOM | 2024-01-24 |  |  |  | NOC Operationalization |  | Arrange toll-free number and update on notification formats readiness |  | Critical | Open |  |  |  | WIP |  |  |  | Siva Kumar |  | Open | WIP | [9 empty] | MOMNOC Operationalization | Network | OPEN | [6 empty] | 1
1717 | M97 | MOM | 2023-08-01 |  |  |  | Helpdesk | User Experience | Different communication channels such as SMS, WhatsApp, Email |  | Critical | open |  |  |  | WIP | 11- Sep-25: SMS and E-mail Integrated and Whatsapp existing Product will not support |  |  | Siva Kumar |  | Open | WIP | [9 empty] | MOMHelpdesk | Helpdesk (Contact Center) | OPEN | [6 empty] | 1
1718 | M970 | MOM | 2024-01-24 |  |  |  | NOC Operationalization |  | Integrate WhatsApp for customer communication through calls with IVR |  | Critical | Open |  |  |  | WIP |  |  |  | Siva Kumar |  | Open | WIP | [9 empty] | MOMNOC Operationalization | Network | OPEN | [6 empty] | 1
1719 | M971 | MOM | 2024-01-24 |  |  |  | NOC Operationalization |  | Provide updates on NOC progress and ensure commitment dates are met |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1
1720 | M972 | MOM | 2024-01-24 |  |  |  | NOC Operationalization |  | Deploy stable standard product for IPDR |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1
1721 | M973 | MOM | 2024-01-24 |  |  |  | NOC Operationalization |  | Ensure pre-scheduled meetings occur without SMEs absence |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1
1722 | M974 | MOM | 2024-01-24 |  |  |  | NOC Operationalization |  | Prepare NOC for review by the State IT&EC Minister and PS-ITE&C |  | Critical | Open |  |  |  | Closed | 24-Sep-25: Closed, Meeting completed |  |  | Siva Kumar |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-24 | Artefacts not Required |  | 1
1723 | M975 | MOM | 2024-01-24 |  |  |  | NOC Operationalization |  | Project Review with 3 MSIs |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1
1724 | M976 | MOM | 2024-01-24 | P3 |  |  | NOC Operationalization |  | Resource mobilization and network availability |  | Critical | Open |  |  |  |  | NOC resources available, availability report being shared |  |  | Ahmad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  | Not related to delivery | 2025-09-19 | Artefacts not Required |  | 1
1725 | M977 | MOM | 2024-01-24 |  |  |  | NOC Operationalization |  | Adoption of WFM by packages B & C |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMNOC Operationalization | Network | OPEN | [6 empty] | 1
1726 | M978 | MOM | 2024-01-24 |  |  |  | Field Related |  | Implementation of Mandal rings of NoFN PH-1 |  | NON-Critical | Open | [7 empty] | S Kodali |  | Open | Open | [9 empty] | MOMField Related | Field Related issues | OPEN |  |  | Project Team |  | #N/A |  | 1
1727 | M979 | MOM | 2024-01-24 |  |  |  | NOC Operationalization |  | Restoration of social welfare and tribal welfare schools to service |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1
1728 | M98 | MOM | 2023-08-01 |  |  |  | Helpdesk | Dashboards | Categorization of Incoming Queries |  | Critical | open |  |  |  | WIP | 11- Sep-25: Available in Neox Application |  |  | Siva Kumar |  | Open | WIP | [9 empty] | MOMHelpdesk | Helpdesk (Contact Center) | OPEN | [6 empty] | 1
1729 | M980 | MOM | 2024-01-24 |  |  |  | Field Related |  | Complete all GI connectivity before March '24 |  | Critical | Open | [7 empty] | S Kodali |  | Open | Open | [9 empty] | MOMField Related | Field Related issues | OPEN |  |  | Project Team |  | Artefacts to be uploaded |  | 1
1730 | M981 | MOM | 2024-01-24 |  |  |  | NOC Operationalization |  | Focus on top 4 network readiness priorities |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1
1731 | M982 | MOM | 2024-01-25 |  |  |  | WFM | NOC Operationalization | WFM Patrolling App Demo |  | Critical | Open | [7 empty] | Kaushalendra Kumar |  | Open | Open | [9 empty] | MOMWFM | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1732 | M983 | MOM | 2024-01-25 |  |  |  | WFM | NOC Operationalization | Complete WFM-OSS integration |  | Critical | Open | [7 empty] | Kaushalendra Kumar |  | Open | Open | [9 empty] | MOMWFM | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1733 | M984 | MOM | 2024-01-25 |  |  |  | NOC Operationalization |  | Submit solution document for PoP RFS |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1
1734 | M985 | MOM | 2024-01-25 |  |  |  | WFM | NOC Operationalization | Understand use cases of WFM integration with BSS |  | Critical | Open | [7 empty] | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMWFM | Applications/Tools | OPEN | [6 empty] | 1
1735 | M986 | MOM | 2024-01-25 |  | OSS | OSS | OSS |  | Complete Fault Management and Trouble Ticketing |  | Critical | Open | [7 empty] | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMOSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1
1736 | M987 | MOM | 2024-01-25 |  |  |  | WFM | NOC Operationalization | Clarify GIS vs WFM mobile app usage |  | Critical | Open | [7 empty] | Kaushalendra Kumar |  | Open | Open | [9 empty] | MOMWFM | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1737 | M988 | MOM | 2024-01-25 |  |  |  | WFM | NOC Operationalization | Submit the NDA signed between L&T and M/S Lepton |  | Critical | Open | [7 empty] | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMWFM | Applications/Tools | OPEN | [6 empty] | 1
1738 | M989 | MOM | 2024-01-25 |  |  |  | Security & Regulatory Compliance | NOC Operationalization | Ensure API security measures |  | Critical | Open |  |  |  |  | Applicationer has been asked to collect from Developers |  |  | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1
1739 | M99 | MOM | 2023-08-01 |  |  |  | Helpdesk | User Experience | Bilingual IVR |  | Critical | open |  |  |  | CLosed | 24-Sep-25: Now its in 3 Languages |  |  | Siva Kumar |  |  | COMPLETED & APPROVED | [9 empty] | MOMHelpdesk | Helpdesk (Contact Center) | CLOSED |  |  |  | 2025-09-24 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\M121,170,99,726 |  | 1
1740 | M990 | MOM | 2024-01-25 |  | OSS | OSS | OSS |  | Submit sample dashboards/reports |  | Critical | Open | [7 empty] | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMOSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1
1741 | M991 | MOM | 2024-01-25 | P3 |  |  | NOC Operationalization |  | Provide Operations Handbook document forms |  | Critical | Open | [7 empty] | Ahmad | 2025-10-07 | Open | Open | [9 empty] | MOMNOC Operationalization | Network | OPEN |  |  | Documentation |  | #N/A |  | 1
1742 | M992 | MOM | 2024-01-25 |  |  |  | NOC Operationalization |  | Clarify attendance watermarking feature |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1
1743 | M993 | MOM | 2024-01-25 |  |  |  | NOC Operationalization |  | Schedule weekly training for patrollers |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1
1744 | M994 | MOM | 2024-01-25 |  |  |  | NOC Operationalization |  | Update on previous MoM action items |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1
1745 | M995 | MOM | 2024-01-25 |  |  |  | BSS |  | Continue defining logic for Dark Fiber and GI-BB products |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1746 | M996 | MOM | 2024-01-25 |  |  |  | WFM | NOC Operationalization | Dry run and operationalize three routes for testing WFM with actual data |  | Critical | Open | [7 empty] | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMWFM | Applications/Tools | OPEN | [6 empty] | 1
1747 | M997 | MOM | 2024-01-25 |  |  |  | Field Related |  | Improve resource mobilization & achieve 65% network availability |  | NON-Critical | Open | [7 empty] | S Kodali |  | Open | Open | [9 empty] | MOMField Related | Field Related issues | OPEN |  |  | Project Team |  | #N/A |  | 1
1748 | M998 | MOM | 2024-01-25 |  |  |  | Field Related |  | Engage partners for O&M resources augmentation and ensure active spares availability |  | NON-Critical | Open | [7 empty] | S Kodali |  | Open | Open | [9 empty] | MOMField Related | Field Related issues | OPEN |  |  | O&M Team |  | #N/A |  | 1
1749 | M999 | MOM | 2024-01-25 |  |  |  | Field Related |  | Deploy committed resources and achieve network availability |  | NON-Critical | Open | [7 empty] | S Kodali |  | Open | Open | [9 empty] | MOMField Related | Field Related issues | OPEN |  |  | O&M Team |  | #N/A |  | 1
1750 | NOC1 | NOC | NA |  | OSS | OSS | OSS | DC | DC Active Infra uptime & SLA Daily |  | Critical |  |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCOSS | Applications/Tools | OPEN | OPEN | 0 |  |  | #N/A |  | 1
1751 | NOC10 | NOC | NA |  | OSS | OSS | OSS | DC | DC Passive infra uptime & SLA Weekly |  | Critical |  |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCOSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  | #N/A |  | 1
1752 | NOC100 | NOC | NA |  |  |  | GPON | OSS | Governenmnet Institutions ( GI ) links delivery. Preparation and publishing of KPI Daily |  | Critical | OPEN |  | NNMI | NPS |  | OPEN-DEPENDENT |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCGPON | Applications/Tools | OPEN | OPEN-DEPENDENT | 0 |  |  | #N/A |  | 1
1753 | NOC101 | NOC | NA |  |  |  | GPON | OSS | Governenmnet Institutions ( GI ) links delivery. Preparation and publishing of KPI Weekly |  | Critical | OPEN |  | NNMI | NPS |  | OPEN-DEPENDENT |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCGPON | Applications/Tools | OPEN | OPEN-DEPENDENT | 0 |  |  | #N/A |  | 1
1754 | NOC102 | NOC | NA |  |  |  | GPON | OSS | Governenmnet Institutions ( GI ) links delivery. Preparation and publishing of KPI Monthly |  | Critical | OPEN |  | NNMI | NPS |  | OPEN-DEPENDENT |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCGPON | Applications/Tools | OPEN | OPEN-DEPENDENT | 0 |  |  | #N/A |  | 1
1755 | NOC103 | NOC | NA |  |  |  | GPON | OSS | Governenmnet Institutions ( GI ) links delivery. Preparation and publishing of KPI (Selective from and to dates) |  | Critical | OPEN |  | NNMI | NPS |  | OPEN-DEPENDENT |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCGPON | Applications/Tools | OPEN | OPEN-DEPENDENT | 0 |  |  | #N/A |  | 1
1756 | NOC104 | NOC | NA |  |  |  | GPON | OSS | Published GP Network uptime (like, total scope, litup count and availability according to the category) Daily |  | Critical | COMPLETED |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCGPON | Applications/Tools | OPEN | CLOSURE REVIEW PENDING | 0 |  |  |  |  | 1
1757 | NOC105 | NOC | NA |  |  |  | GPON | OSS | Published GP Network uptime (like, total scope, litup count and availability according to the category) Weekly |  | Critical | OPEN |  | HPSM | Incident Management |  | 26-Sep-2025: GPON , DWDM, Routers, switches and UPS we can take monthly and Daily reports from UOC. For UPS, Routers and switches we can take hourly, weekly, monthly on demand and any selective period basis from NNMI. L&T conveyed that, As per the agreed scope of work between L&T, TFiber, HP and OT this hourly and weekly granuality not given in the scope, also availability based on alarm. As per the confirmation from Manoj L&T, The existing tool can only give daily and monthly reports only. Apart from that the system doesn't have capabilities to generate other reports. Vigility need to co-ordinate with OEM and confirm the feasibility. |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCGPON | Applications/Tools | OPEN | NOT-FEASIBLE | 26-Sep-2025: GPON , DWDM, Routers, switches and UPS we can take monthly and Daily reports from UOC. For UPS, Routers and switches we can take hourly, weekly, monthly on demand and any selective period basis from NNMI. L&T conveyed that, As per the agreed scope of work between L&T, TFiber, HP and OT this hourly and weekly granuality not given in the scope, also availability based on alarm. As per the confirmation from Manoj L&T, The existing tool can only give daily and monthly reports only. Apart from that the system doesn't have capabilities to generate other reports. Vigility need to co-ordinate with OEM and confirm the feasibility. |  |  |  |  | 1
1758 | NOC106 | NOC | NA |  |  |  | GPON | OSS | Published GP Network uptime (like, total scope, litup count and availability according to the category) Monthly |  | Critical | COMPLETED |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCGPON | Applications/Tools | OPEN | CLOSURE REVIEW PENDING | 0 |  |  |  |  | 1
1759 | NOC107 | NOC | NA |  |  |  | GPON | OSS | Published GP Network uptime (like, total scope, litup count and availability according to the category) (Selective from and to dates) |  | Critical | COMPLETED |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCGPON | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1
1760 | NOC108 | NOC | NA |  |  |  | GPON | OSS | Publishing Package wise and District wise GP Network uptime and GP TT resolution MTTR dashboard Daily |  | Critical | COMPLETED |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCGPON | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1
1761 | NOC109 | NOC | NA |  |  |  | GPON | OSS | Publishing Package wise and District wise GP Network uptime and GP TT resolution MTTR dashboard Weekly |  | Critical | COMPLETED |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCGPON | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1
1762 | NOC11 | NOC | NA |  | OSS | OSS | OSS | DC | DC Passive infra uptime & SLA Monthly |  | Critical |  |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCOSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  | #N/A |  | 1
1763 | NOC110 | NOC | NA |  |  |  | GPON | OSS | Publishing Package wise and District wise GP Network uptime and GP TT resolution MTTR dashboard Monthly |  | Critical | COMPLETED |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCGPON | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1
1764 | NOC111 | NOC | NA |  |  |  | GPON | OSS | Publishing Package wise and District wise GP Network uptime and GP TT resolution MTTR dashboard (Selective from and to dates) |  | Critical | OPEN |  | HPSM | Incident Management |  | Availability is available in UOC for Daily and monthly only. MTTR Report is available from SM on Daily , Weekly, monthly and customized period. Dashboards made available as per requirements against MTTR |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCGPON | Applications/Tools | OPEN | WIP | Availability is available in UOC for Daily and monthly only. MTTR Report is available from SM on Daily , Weekly, monthly and customized period. Dashboards made available as per requirements against MTTR |  |  | #N/A |  | 1
1765 | NOC112 | NOC | NA |  |  |  | GPON | OSS | Published Mandal Network uptime (like, total scope, litup count and availability according to the category) Hourly |  | Critical | OPEN |  | HPSM | Incident Management |  | Availability is available in UOC for Daily and monthly only. |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCGPON | Applications/Tools | OPEN | NOT-FEASIBLE | Availability is available in UOC for Daily and monthly only. |  |  | #N/A |  | 1
1766 | NOC113 | NOC | NA |  |  |  | GPON | OSS | Published Mandal Network uptime (like, total scope, litup count and availability according to the category) Daily |  | Critical | COMPLETED |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCGPON | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1
1767 | NOC114 | NOC | NA |  |  |  | GPON | OSS | Published Mandal Network uptime (like, total scope, litup count and availability according to the category) Weekly |  | Critical | OPEN |  | HPSM | Incident Management |  | Additional Scope (Total scope value is not possible to display in HPSM) |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCGPON | Applications/Tools | OPEN | NOT-FEASIBLE | 0 |  |  | #N/A |  | 1
1768 | NOC115 | NOC | NA |  |  |  | GPON | OSS | Published Mandal Network uptime (like, total scope, litup count and availability according to the category) Monthly |  | Critical | COMPLETED |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCGPON | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1
1769 | NOC116 | NOC | NA |  |  |  | GPON | OSS | Published Mandal Network uptime (like, total scope, litup count and availability according to the category) (Selective from and to dates) |  | Critical | COMPLETED |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCGPON | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1
1770 | NOC117 | NOC | NA |  |  |  | GPON | OSS | Publishing Package wise and district wise Mandal Network uptime and Mandal TT resolution MTTR dashboard Daily |  | Critical | COMPLETED |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCGPON | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1
1771 | NOC118 | NOC | NA |  |  |  | GPON | OSS | Publishing Package wise and district wise Mandal Network uptime and Mandal TT resolution MTTR dashboard Weekly |  | Critical | COMPLETED |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCGPON | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1
1772 | NOC119 | NOC | NA |  |  |  | GPON | OSS | Publishing Package wise and district wise Mandal Network uptime and Mandal TT resolution MTTR dashboard Monthly |  | Critical | COMPLETED |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCGPON | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1
1773 | NOC12 | NOC | NA |  | OSS | OSS | OSS | DC | DC Passive infra uptime & SLA (Selective from and to dates) |  | Critical |  |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCOSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  | #N/A |  | 1
1774 | NOC120 | NOC | NA |  |  |  | GPON | OSS | Publishing Package wise and district wise Mandal Network uptime and Mandal TT resolution MTTR dashboard (Selective from and to dates) |  | Critical | OPEN |  | HPSM | Incident Management |  | Uptime and MMTR are two separate reports. |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCGPON | Applications/Tools | OPEN | WIP | 0 |  |  | #N/A |  | 1
1775 | NOC121 | NOC | NA |  | OSS | OSS | All Domain | OSS | Based on DFR, prepare and publishing domain wise Ticketing dashboard Hourly |  | Critical | COMPLETED |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCAll Domain | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1
1776 | NOC122 | NOC | NA |  | OSS | OSS | All Domain | OSS | Based on DFR, prepare and publishing domain wise Ticketing dashboard Daily |  | Critical | COMPLETED |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCAll Domain | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1
1777 | NOC123 | NOC | NA |  | OSS | OSS | All Domain | OSS | Based on DFR, prepare and publishing domain wise Ticketing dashboard Weekly |  | Critical | COMPLETED |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCAll Domain | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1
1778 | NOC124 | NOC | NA |  | OSS | OSS | All Domain | OSS | Based on DFR, prepare and publishing domain wise Ticketing dashboard Monthly |  | Critical | COMPLETED |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCAll Domain | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1
1779 | NOC125 | NOC | NA |  | OSS | OSS | All Domain | OSS | Based on DFR, prepare and publishing domain wise Ticketing dashboard (Selective from and to dates) |  | Critical | COMPLETED |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCAll Domain | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1
1780 | NOC126 | NOC | NA |  | OSS | OSS | All Domain | OSS | Publishing of total field network devices dashboard Daily |  | Critical | COMPLETED |  | OSS Dashboards | UTM |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCAll Domain | Applications/Tools | OPEN | COMPLETED | Power BI DB - Device status will be live in the dashboard |  |  |  |  | 1
1781 | NOC127 | NOC | NA |  | OSS | OSS | All Domain | OSS | Publishing of total field network devices dashboard Weekly |  | Critical | NOT_FEASIBLE |  | OSS Dashboards | UTM |  |  |  |  | Suresh Pawar |  | Open | Not Feasible | [9 empty] | NOCAll Domain | Applications/Tools | #N/A | NOT-FEASIBLE | 0 |  |  | #N/A |  | 1
1782 | NOC128 | NOC | NA |  | OSS | OSS | All Domain | OSS | Publishing of total field network devices dashboard Monthly |  | Critical | COMPLETED |  | OSS Dashboards | UTM |  | Device status will be live in the dashboard |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCAll Domain | Applications/Tools | OPEN | COMPLETED | Device status will be live in the dashboard |  |  |  |  | 1
1783 | NOC129 | NOC | NA |  | OSS | OSS | All Domain | OSS | Publishing of total field network devices dashboard (Selective from and to dates) |  | Critical | NOT_FEASIBLE |  | OSS Dashboards | UTM |  |  |  |  | Suresh Pawar |  | Open | Not Feasible | [9 empty] | NOCAll Domain | Applications/Tools | #N/A | NOT-FEASIBLE | 0 |  |  | #N/A |  | 1
1784 | NOC13 | NOC | NA |  | OSS | OSS | OSS | DC | DC Network link uptime & SLA Daily |  | Critical |  |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCOSS | Applications/Tools | OPEN | OPEN | 0 |  |  | #N/A |  | 1
1785 | NOC130 | NOC | NA |  | OSS | OSS | OSS | Field Passive Infra | Preparion and publishing Field Passive Infra Devices Uptime dashboard (Zone,Mandal,GP wise) Daily |  | Critical | COMPLETED |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCOSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1
1786 | NOC131 | NOC | NA |  | OSS | OSS | OSS | Field Passive Infra | Preparion and publishing Field Passive Infra Devices Uptime dashboard (Zone,Mandal,GP wise) Weekly |  | Critical | NOT_FEASIBLE |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  | Open | Not Feasible | [9 empty] | NOCOSS | Applications/Tools | #N/A | NOT-FEASIBLE | 0 |  |  | #N/A |  | 1
1787 | NOC132 | NOC | NA |  | OSS | OSS | OSS | Field Passive Infra | Preparion and publishing Field Passive Infra Devices Uptime dashboard (Zone,Mandal,GP wise) Monthly |  | Critical | COMPLETED |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCOSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1
1788 | NOC133 | NOC | NA |  | OSS | OSS | OSS | Field Passive Infra | Preparion and publishing Field Passive Infra Devices Uptime dashboard (Zone,Mandal,GP wise) (Selective from and to dates) |  | Critical | COMPLETED |  | NNMI | NPS |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCOSS | Applications/Tools | OPEN | COMPLETED | available-weekly in NPS not in UOC |  |  |  |  | 1
1789 | NOC134 | NOC | NA |  | OSS | OSS | OSS | Planned Events | Publishing Planned Events dashboard of all the packages(like , PE applied,Success,cancelation etc) Daily |  | Critical | COMPLETED |  | NNMI | NPS |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCOSS | Applications/Tools | OPEN | COMPLETED | there is no dashboard |  |  |  |  | 1
1790 | NOC135 | NOC | NA |  | OSS | OSS | OSS | Planned Events | Publishing Planned Events dashboard of all the packages(like , PE applied,Success,cancelation etc) Weekly |  | Critical | COMPLETED |  | NNMI | NPS |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCOSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1
1791 | NOC136 | NOC | NA |  | OSS | OSS | OSS | Planned Events | Publishing Planned Events dashboard of all the packages(like , PE applied,Success,cancelation etc) Monthly |  | Critical | COMPLETED |  | NNMI | NPS |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCOSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1
1792 | NOC137 | NOC | NA |  | OSS | OSS | OSS | Planned Events | Publishing Planned Events dashboard of all the packages(like , PE applied,Success,cancelation etc) (Selective from and to dates) |  | Critical | COMPLETED |  | NNMI | NPS |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCOSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1
1793 | NOC138 | NOC | NA |  | OSS | OSS | OSS | DC IT Active Infra | Preparation and publishing of all DC IT devices availability dashboard Daily |  | NON-Critical |  |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCOSS | Applications/Tools | OPEN | OPEN | 0 |  |  | #N/A |  | 1
1794 | NOC139 | NOC | NA |  | OSS | OSS | OSS | DC IT Active Infra | Preparation and publishing of all DC IT devices availability dashboard Weekly |  | NON-Critical |  |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCOSS | Applications/Tools | OPEN | OPEN | 0 |  |  | #N/A |  | 1
1795 | NOC14 | NOC | NA |  | OSS | OSS | OSS | DC | DC Network link uptime & SLA Weekly |  | Critical |  |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCOSS | Applications/Tools | OPEN | OPEN | 0 |  |  | #N/A |  | 1
1796 | NOC140 | NOC | NA |  | OSS | OSS | OSS | DC IT Active Infra | Preparation and publishing of all DC IT devices availability dashboard Monthly |  | NON-Critical |  |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCOSS | Applications/Tools | OPEN | OPEN | 0 |  |  | #N/A |  | 1
1797 | NOC141 | NOC | NA |  | OSS | OSS | OSS | DC IT Active Infra | Preparation and publishing of all DC IT devices availability dashboard (Selective from and to dates) |  | NON-Critical |  |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCOSS | Applications/Tools | OPEN | OPEN | 0 |  |  | #N/A |  | 1
1798 | NOC142 | NOC | NA |  |  |  | DC Passive Infra | OSS | Preparation and publishing of all DC Non IT devices availability dashboard Daily |  | NON-Critical |  |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCDC Passive Infra | Applications/Tools | OPEN | OPEN | 0 |  |  | #N/A |  | 1
1799 | NOC143 | NOC | NA |  |  |  | DC Passive Infra | OSS | Preparation and publishing of all DC Non IT devices availability dashboard Weekly |  | NON-Critical |  |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCDC Passive Infra | Applications/Tools | OPEN | OPEN | 0 |  |  | #N/A |  | 1
1800 | NOC144 | NOC | NA |  |  |  | DC Passive Infra | OSS | Preparation and publishing of all DC Non IT devices availability dashboard Monthly |  | NON-Critical |  |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCDC Passive Infra | Applications/Tools | OPEN | OPEN | 0 |  |  | #N/A |  | 1
1801 | NOC145 | NOC | NA |  |  |  | DC Passive Infra | OSS | Preparation and publishing of all DC Non IT devices availability dashboard (Selective from and to dates) |  | NON-Critical |  |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCDC Passive Infra | Applications/Tools | OPEN | OPEN | 0 |  |  | #N/A |  | 1
1802 | NOC146 | NOC | NA |  | OSS | OSS | OSS | OSS | Preparation and publishing of all application availability dashboard Daily |  | Critical | COMPLETED |  | OSS Dashboards | UOC |  | 09-09-2025: Sitescope based application URL monitoring |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCOSS | Applications/Tools | OPEN | COMPLETED | 09-09-2025: Sitescope based application URL monitoring |  |  |  |  | 1
1803 | NOC147 | NOC | NA |  | OSS | OSS | OSS | OSS | Preparation and publishing of all application availability dashboard Weekly |  | Critical | COMPLETED |  | OSS Dashboards | UOC |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCOSS | Applications/Tools | OPEN | COMPLETED | sitescope |  |  |  |  | 1
1804 | NOC148 | NOC | NA |  | OSS | OSS | OSS | OSS | Preparation and publishing of all application availability dashboard Monthly |  | Critical | COMPLETED |  | OSS Dashboards | UOC |  | 09-09-2025: Sitescope based application URL monitoring |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCOSS | Applications/Tools | OPEN | COMPLETED | 09-09-2025: Sitescope based application URL monitoring |  |  |  |  | 1
1805 | NOC149 | NOC | NA |  | OSS | OSS | OSS | OSS | Preparation and publishing of all application availability dashboard (Selective from and to dates) |  | Critical | COMPLETED |  | OSS Dashboards | UOC |  | 09-09-2025: Sitescope based application URL availability monitoring |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCOSS | Applications/Tools | OPEN | COMPLETED | 09-09-2025: Sitescope based application URL availability monitoring |  |  |  |  | 1
1806 | NOC15 | NOC | NA |  | OSS | OSS | OSS | DC | DC Network link uptime & SLA Monthly |  | Critical |  |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCOSS | Applications/Tools | OPEN | OPEN | 0 |  |  | #N/A |  | 1
1807 | NOC150 | NOC | NA |  | OSS | OSS | OSS | OSS | Service assurance & Dashboards |  | Critical |  |  | OSS Dashboards | HPE Telco Unified OSS Console |  | Power Bi |  |  | Suresh Pawar |  | Open | WIP | [9 empty] | NOCOSS | Applications/Tools | OPEN | OPEN | 0 |  |  | #N/A |  | 1
1808 | NOC151 | NOC | NA |  | OSS | OSS | OSS | OSS | Network Service Assurance Dashboards |  | Critical |  |  | OSS Dashboards | HPE Telco Unified OSS Console |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCOSS | Applications/Tools | OPEN | COMPLETED | dashboard is not there |  |  |  |  | 1
1809 | NOC152 | NOC | NA |  | OSS | OSS | OSS | OSS | Business Service Assurance Dashboards |  | Critical |  |  | OSS Dashboards | HPE Telco Unified OSS Console |  |  |  |  | Suresh Pawar |  | Open | WIP | [9 empty] | NOCOSS | Applications/Tools | OPEN | OPEN | 0 |  |  | #N/A |  | 1
1810 | NOC153 | NOC | NA |  | OSS | OSS | OSS | OSS | Customer Service Dashboards |  | Critical |  |  | OSS Dashboards | HPE Telco Unified OSS Console |  | It will be available in BSS |  |  | Suresh Pawar |  | Open | WIP | [9 empty] | NOCOSS | Applications/Tools | OPEN | OPEN | 0 |  |  | #N/A |  | 1
1811 | NOC154 | NOC | NA |  | OSS | OSS | OSS | OSS | Security Assurance Dashboard |  | Critical |  |  | OSS Dashboards | HPE Telco Unified OSS Console |  | It will be available in BSS |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCOSS | Applications/Tools | OPEN | COMPLETED | MTTR Reports for all domain including customer tickets |  |  | #N/A |  | 1
1812 | NOC155 | NOC | NA |  | OSS | OSS | OSS | OSS | Service Inventory |  | Critical |  |  | OSS Dashboards | HPE Telco Unified OSS Console |  | Inhouse solution |  |  | Suresh Pawar |  | Open | WIP | [9 empty] | NOCOSS | Applications/Tools | OPEN | OPEN | 0 |  |  | #N/A |  | 1
1813 | NOC156 | NOC | NA |  | OSS | OSS | OSS | OSS | Service Monitoring |  | Critical |  |  | OSS Dashboards | HPE Telco Unified OSS Console |  |  |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCOSS | Applications/Tools | OPEN | OPEN | 0 |  |  | #N/A |  | 1
1814 | NOC157 | NOC | NA |  | OSS | OSS | New BSS | OSS | OSS Intigration for POC Locations LCO,RMSO & MSO |  | Critical | OPEN |  | HPSM | Incident Management |  | Aditional Scope for OT/HPE |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCNew BSS | #N/A | OPEN | Not Relevant to OSS | 0 |  |  | #N/A |  | 1
1815 | NOC158 | NOC | NA |  | OSS | OSS | New BSS | OSS | OSS Intigration for Live LCO , RMSO & MSO |  | Critical | OPEN |  | HPSM | Incident Management |  | Aditional Scope for OT/HPE |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCNew BSS | #N/A | OPEN | Not Relevant to OSS | 0 |  |  | #N/A |  | 1
1816 | NOC159 | NOC | NA |  | OSS | OSS | OSS | OSS | Video customer inventory , Internet customer inventory , Bandwidth allocation inventory count etc., |  | Critical | OPEN |  | HPSM | Incident Management |  | Aditional Scope for OT/HPE |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCOSS | Applications/Tools | OPEN | OPEN | 0 |  |  | #N/A |  | 1
1817 | NOC16 | NOC | NA |  | OSS | OSS | OSS | DC | DC Network link uptime & SLA (Selective from and to dates) |  | Critical |  |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCOSS | Applications/Tools | OPEN | OPEN | 0 |  |  | #N/A |  | 1
1818 | NOC160 | NOC | NA |  |  |  | DC Passive Infra | OSS | Preparation and publishing of all DC passive infra(Internal, OEM) PM dashboard Daily |  | NON-Critical |  |  | OSS Dashboards | UOC |  |  |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCDC Passive Infra | Applications/Tools | OPEN | OPEN | 0 |  |  | #N/A |  | 1
1819 | NOC161 | NOC | NA |  |  |  | DC Passive Infra | OSS | Preparation and publishing of all DC passive infra(Internal, OEM) PM dashboard Weekly |  | NON-Critical |  |  | OSS Dashboards | UOC |  |  |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCDC Passive Infra | Applications/Tools | OPEN | OPEN | 0 |  |  | #N/A |  | 1
1820 | NOC162 | NOC | NA |  |  |  | DC Passive Infra | OSS | Preparation and publishing of all DC passive infra(Internal, OEM) PM dashboard Monthly |  | NON-Critical |  |  | OSS Dashboards | UOC |  |  |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCDC Passive Infra | Applications/Tools | OPEN | OPEN | 0 |  |  | #N/A |  | 1
1821 | NOC163 | NOC | NA |  |  |  | DC Passive Infra | OSS | Preparation and publishing of all DC passive infra(Internal, OEM) PM dashboard (Selective from and to dates) |  | NON-Critical |  |  | OSS Dashboards | UOC |  |  |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCDC Passive Infra | Applications/Tools | OPEN | OPEN | 0 |  |  | #N/A |  | 1
1822 | NOC164 | NOC | NA |  | OSS | OSS | OSS | NOC | Preparation and publishing of all devices, application, software AMC dashboard Daily |  | Critical |  |  | OSS Dashboards | Asset Manager |  | Report is available in Asset manager |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCOSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1
1823 | NOC165 | NOC | NA |  | OSS | OSS | OSS | NOC | Preparation and publishing of all devices, application, software AMC dashboard Weekly |  | Critical |  |  | OSS Dashboards | Asset Manager |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCOSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  | #N/A |  | 1
1824 | NOC166 | NOC | NA |  | OSS | OSS | OSS | NOC | Preparation and publishing of all devices, application, software AMC dashboard Monthly |  | Critical |  |  | OSS Dashboards | Asset Manager |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCOSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  | #N/A |  | 1
1825 | NOC167 | NOC | NA |  | OSS | OSS | OSS | NOC | Preparation and publishing of all devices, application, software AMC dashboard (Selective from and to dates) |  | Critical |  |  | OSS Dashboards | Asset Manager |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCOSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  | #N/A |  | 1
1826 | NOC168 | NOC | NA |  | OSS | OSS | OSS | NOC | Publishing of all major events in Tnoc dashboard Daily |  | Critical |  |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCOSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  | #N/A |  | 1
1827 | NOC169 | NOC | NA |  | OSS | OSS | OSS | NOC | Publishing of all major events in Tnoc dashboard Weekly |  | Critical |  |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCOSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  | #N/A |  | 1
1828 | NOC17 | NOC | NA |  |  |  | BSS | Service Provisioning | configure of GI services and tracking and publishing data Daily |  | Critical | OPEN |  | BSS | CRM |  | It will be available in NSO and BSS |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1829 | NOC170 | NOC | NA |  | OSS | OSS | OSS | NOC | Publishing of all major events in Tnoc dashboard Monthly |  | Critical |  |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCOSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  | #N/A |  | 1
1830 | NOC171 | NOC | NA |  | OSS | OSS | OSS | NOC | Publishing of all major events in Tnoc dashboard (Selective from and to dates) |  | Critical |  |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCOSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  | #N/A |  | 1
1831 | NOC172 | NOC | NA |  | OSS | OSS | OSS | BBNL Reports | Publishing of BBNL dashboard Daily |  | Critical | COMPLETED |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCOSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1
1832 | NOC173 | NOC | NA |  | OSS | OSS | OSS | BBNL Reports | Publishing of BBNL dashboard Weekly |  | Critical | NOT_FEASIBLE |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  | Open | Not Feasible | [9 empty] | NOCOSS | Applications/Tools | #N/A | Not Required to BBNL | 11-Oct-25: BBNL do not ask weekly hence it is not delivered |  |  | #N/A |  | 1
1833 | NOC174 | NOC | NA |  | OSS | OSS | OSS | BBNL Reports | Publishing of BBNL dashboard Monthly |  | Critical | COMPLETED |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCOSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1
1834 | NOC175 | NOC | NA |  | OSS | OSS | OSS | BBNL Reports | Publishing of BBNL dashboard (Selective from and to dates) |  | Critical | NOT_FEASIBLE |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  | Open | Not Feasible | [9 empty] | NOCOSS | Applications/Tools | #N/A | Not Required to BBNL | 11-Oct-25: BBNL do not ask Selective from and to dates hence it is not delivered |  |  | #N/A |  | 1
1835 | NOC176 | NOC | NA |  | OSS | OSS | OSS | Field Passive Infra | Publishing of Field Passive infra total devices dashboard Daily |  | Critical | COMPLETED |  | NNMI | NNMI |  | 09-09-2025: Inventory Dashboard visible for live data which is refreshing 6 times a day. |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCOSS | Applications/Tools | OPEN | COMPLETED | 09-09-2025: Inventory Dashboard visible for live data which is refreshing 6 times a day. |  |  |  |  | 1
1836 | NOC177 | NOC | NA |  | OSS | OSS | OSS | Field Passive Infra | Publishing of Field Passive infra total devices dashboard Weekly |  | Critical | NOT_FEASIBLE |  | NNMI | NNMI |  |  |  |  | Suresh Pawar |  | Open | Not Feasible | [9 empty] | NOCOSS | Applications/Tools | #N/A | NOT-FEASIBLE | 0 |  |  | #N/A |  | 1
1837 | NOC178 | NOC | NA |  | OSS | OSS | OSS | Field Passive Infra | Publishing of Field Passive infra total devices dashboard Monthly |  | Critical | COMPLETED |  | NNMI | NNMI |  | Live report is available in UOC |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCOSS | Applications/Tools | OPEN | COMPLETED | Live report is available in UOC |  |  |  |  | 1
1838 | NOC179 | NOC | NA |  | OSS | OSS | OSS | Field Passive Infra | Publishing of Field Passive infra total devices dashboard (Selective from and to dates) |  | Critical | COMPLETED |  | NNMI | NNMI |  | Live report is available in UOC |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCOSS | Applications/Tools | OPEN | COMPLETED | Live report is available in UOC |  |  |  |  | 1
1839 | NOC18 | NOC | NA |  |  |  | BSS | Service Provisioning | configure of GI services and tracking and publishing data Weekly |  | Critical | OPEN |  | BSS | CRM |  | It will be available in NSO and BSS |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1840 | NOC180 | NOC | NA |  |  |  | DWDM | OSS | Published Zonal Network uptime (like, total scope, litup count and availability according to the category) Daily |  | Critical | COMPLETED |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCDWDM | Applications/Tools | OPEN | CLOSURE REVIEW PENDING | 0 |  |  |  |  | 1
1841 | NOC181 | NOC | NA |  |  |  | DWDM | OSS | Published Zonal Network uptime (like, total scope, litup count and availability according to the category) Weekly |  | Critical | OPEN |  | HPSM | Incident Management |  | Uptime and MMTR are two separate reports. |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCDWDM | Applications/Tools | OPEN | OPEN | 0 |  |  | #N/A |  | 1
1842 | NOC182 | NOC | NA |  |  |  | DWDM | OSS | Published Zonal Network uptime (like, total scope, litup count and availability according to the category) Monthly |  | Critical | COMPLETED |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCDWDM | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1
1843 | NOC183 | NOC | NA |  |  |  | DWDM | OSS | Published Zonal Network uptime (like, total scope, litup count and availability according to the category) (Selective from and to dates) |  | Critical | COMPLETED |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCDWDM | Applications/Tools | OPEN | CLOSURE REVIEW PENDING | 0 |  |  |  |  | 1
1844 | NOC184 | NOC | NA |  |  |  | DWDM | OSS | Publishing Package wise , district wise and node wise (like DWDM,OADM) Zonal Network uptime and Mandal TT resolution MTTR dashboard Daily |  | Critical | COMPLETED |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCDWDM | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1
1845 | NOC185 | NOC | NA |  |  |  | DWDM | OSS | Publishing Package wise , district wise and node wise (like DWDM,OADM) Zonal Network uptime and Mandal TT resolution MTTR dashboard Weekly |  | Critical | COMPLETED |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCDWDM | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1
1846 | NOC186 | NOC | NA |  |  |  | DWDM | OSS | Publishing Package wise , district wise and node wise (like DWDM,OADM) Zonal Network uptime and Mandal TT resolution MTTR dashboard Monthly |  | Critical | COMPLETED |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCDWDM | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1
1847 | NOC187 | NOC | NA |  |  |  | DWDM | OSS | Publishing Package wise , district wise and node wise (like DWDM,OADM) Zonal Network uptime and Mandal TT resolution MTTR dashboard (Selective from and to dates) |  | Critical | OPEN |  | HPSM | Incident Management |  | Uptime and MMTR are two separate reports. |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCDWDM | Applications/Tools | OPEN | WIP | 0 |  |  | #N/A |  | 1
1848 | NOC188 | NOC | NA |  |  |  | DWDM | OSS | Preparation and publishing of Zonal link summary , uptime and MTTR dashboard Daily |  | Critical | COMPLETED |  | HPSM | Incident Management |  | 11-09-2025: Uptime/Availability and MTTR is available for daily and monthly |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCDWDM | Applications/Tools | OPEN | COMPLETED | 11-09-2025: Uptime/Availability and MTTR is available for daily and monthly |  |  |  |  | 1
1849 | NOC189 | NOC | NA |  |  |  | DWDM | OSS | Preparation and publishing of Zonal link summary , uptime and MTTR dashboard Weekly |  | Critical | OPEN |  | HPSM | Incident Management |  | 11-09-2025: Uptime/Availability and MTTR is available for daily and monthly |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCDWDM | Applications/Tools | OPEN | WIP | 11-09-2025: Uptime/Availability and MTTR is available for daily and monthly |  |  | #N/A |  | 1
1850 | NOC19 | NOC | NA |  |  |  | BSS | Service Provisioning | configure of GI services and tracking and publishing data Monthly |  | Critical | OPEN |  | BSS | CRM |  | It will be available in NSO and BSS |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1851 | NOC190 | NOC | NA |  |  |  | DWDM | OSS | Preparation and publishing of Zonal link summary , uptime and MTTR dashboard Monthly |  | Critical | OPEN |  | HPSM | Incident Management |  | 11-09-2025: Uptime/Availability and MTTR is available for daily and monthly |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCDWDM | Applications/Tools | OPEN | WIP | 11-09-2025: Uptime/Availability and MTTR is available for daily and monthly |  |  | #N/A |  | 1
1852 | NOC191 | NOC | NA |  |  |  | DWDM | OSS | Preparation and publishing of Zonal link summary , uptime and MTTR dashboard (Selective from and to dates) |  | Critical | OPEN |  | HPSM | Incident Management |  | Uptime and MMTR are two separate reports. |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCDWDM | Applications/Tools | OPEN | WIP | 0 |  |  | #N/A |  | 1
1853 | NOC192 | NOC | NA |  |  |  | DWDM | OSS | Preparing and publishing Zonal Link Fiber MTTR dashboard Daily |  | Critical | OPEN |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCDWDM | Applications/Tools | OPEN | WIP | 0 |  |  | #N/A |  | 1
1854 | NOC193 | NOC | NA |  |  |  | DWDM | OSS | Preparing and publishing Zonal Link Fiber MTTR dashboard Weekly |  | Critical | OPEN |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCDWDM | Applications/Tools | OPEN | WIP | 0 |  |  | #N/A |  | 1
1855 | NOC194 | NOC | NA |  |  |  | DWDM | OSS | Preparing and publishing Zonal Link Fiber MTTR dashboard Monthly |  | Critical | OPEN |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCDWDM | Applications/Tools | OPEN | WIP | 0 |  |  | #N/A |  | 1
1856 | NOC195 | NOC | NA |  |  |  | DWDM | OSS | Preparing and publishing Zonal Link Fiber MTTR dashboard (Selective from and to dates) |  | Critical | OPEN |  | HPSM | Incident Management |  | Uptime and MMTR are two separate reports. |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCDWDM | Applications/Tools | OPEN | WIP | 0 |  |  | #N/A |  | 1
1857 | NOC196 | NOC | NA |  |  |  | DWDM | OSS | Preparation and publishing dashboard for major events happened in network Hourly |  | Critical | OPEN |  | HPSM | Incident Management |  | Option is Availale in UOC (FAS) to check major alarms |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCDWDM | Applications/Tools | OPEN | COMPLETED | Option is Availale in UOC (FAS) to check major alarms |  |  | #N/A |  | 1
1858 | NOC197 | NOC | NA |  |  |  | DWDM | OSS | Preparation and publishing dashboard for major events happened in network Daily |  | Critical | COMPLETED |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCDWDM | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1
1859 | NOC198 | NOC | NA |  |  |  | DWDM | OSS | Preparation and publishing dashboard for major events happened in network Weekly |  | Critical | COMPLETED |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCDWDM | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1
1860 | NOC199 | NOC | NA |  |  |  | DWDM | OSS | Preparation and publishing dashboard for major events happened in network Monthly |  | Critical | COMPLETED |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCDWDM | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1
1861 | NOC2 | NOC | NA |  | OSS | OSS | OSS | DC | DC Active Infra uptime & SLA Weekly |  | Critical |  |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCOSS | Applications/Tools | OPEN | OPEN | 0 |  |  | #N/A |  | 1
1862 | NOC20 | NOC | NA |  |  |  | BSS | Service Provisioning | configure of GI services and tracking and publishing data (Selective from and to dates) |  | Critical | OPEN |  | BSS | CRM |  | It will be available in NSO and BSS |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
1863 | NOC200 | NOC | NA |  |  |  | DWDM | OSS | Preparation and publishing dashboard for major events happened in network (Selective from and to dates) |  | Critical | COMPLETED |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCDWDM | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1
1864 | NOC201 | NOC | NA |  |  |  | DWDM | OSS | Preparation and publishing of all DC DWDM devices availability dashboard Daily |  | Critical | COMPLETED |  | OSS Dashboards | UOC |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCDWDM | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1
1865 | NOC202 | NOC | NA |  |  |  | DWDM | OSS | Preparation and publishing of all DC DWDM devices availability dashboard Weekly |  | Critical | NOT_FEASIBLE |  | OSS Dashboards | UOC |  |  |  |  | Suresh Pawar |  | Open | Not Feasible | [9 empty] | NOCDWDM | Applications/Tools | #N/A | NOT-FEASIBLE | 0 |  |  | #N/A |  | 1
1866 | NOC203 | NOC | NA |  |  |  | DWDM | OSS | Preparation and publishing of all DC DWDM devices availability dashboard Monthly |  | Critical | COMPLETED |  | OSS Dashboards | UOC |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCDWDM | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1
1867 | NOC204 | NOC | NA |  |  |  | DWDM | OSS | Preparation and publishing of all DC DWDM devices availability dashboard (Selective from and to dates) |  | Critical | COMPLETED |  | OSS Dashboards | UOC |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCDWDM | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1
1868 | NOC205 | NOC | NA |  |  |  | DWDM | OSS | T-NOC Report : Zonal Links DWDM DFR Status as on 15-May-2025 Action to be taken on Top Most Priority Daily |  | Critical | COMPLETED |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCDWDM | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1
1869 | NOC206 | NOC | NA |  |  |  | DWDM | OSS | T-NOC Report : Zonal Links DWDM DFR Status as on 15-May-2025 Action to be taken on Top Most Priority Weekly |  | Critical | COMPLETED |  | HPSM | Incident Management |  | 09-09-2025: Ticket data based on Service Manager |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCDWDM | Applications/Tools | OPEN | COMPLETED | 09-09-2025: Ticket data based on Service Manager |  |  |  |  | 1
1870 | NOC207 | NOC | NA |  |  |  | DWDM | OSS | T-NOC Report : Zonal Links DWDM DFR Status as on 15-May-2025 Action to be taken on Top Most Priority Monthly |  | Critical | COMPLETED |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCDWDM | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1
1871 | NOC208 | NOC | NA |  |  |  | DWDM | OSS | T-NOC Report : Zonal Links DWDM DFR Status as on 15-May-2025 Action to be taken on Top Most Priority (Selective from and to dates) |  | Critical | COMPLETED |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCDWDM | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1
1872 | NOC209 | NOC | NA |  |  |  | DWDM | OSS | Zonal High Received Span Losses with TT for PKG_A Daily |  | Critical | OPEN |  | OSS Dashboards | UOC |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCDWDM | Applications/Tools | OPEN | COMPLETED | 0 |  |  | #N/A |  | 1
1873 | NOC21 | NOC | NA |  | OSS | OSS | OSS | Service Assurance | Monitoring,tracking of field details, Tracking of GI services form and prepare Service assurance dashboard Hourly |  | NON-Critical | OPEN |  | HPSM | Incident Management |  | OPEN-DEPENDENT |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCOSS | Applications/Tools | OPEN | OPEN-DEPENDENT | 0 |  |  | #N/A |  | 1
1874 | NOC210 | NOC | NA |  |  |  | DWDM | OSS | Zonal High Received Span Losses with TT for PKG_A Weekly |  | Critical | OPEN |  | OSS Dashboards | UOC |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCDWDM | Applications/Tools | OPEN | COMPLETED | 0 |  |  | #N/A |  | 1
1875 | NOC211 | NOC | NA |  |  |  | DWDM | OSS | Zonal High Received Span Losses with TT for PKG_A Monthly |  | Critical | OPEN |  | OSS Dashboards | UOC |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCDWDM | Applications/Tools | OPEN | COMPLETED | 0 |  |  | #N/A |  | 1
1876 | NOC212 | NOC | NA |  |  |  | DWDM | OSS | Zonal High Received Span Losses with TT for PKG_A (Selective from and to dates) |  | Critical | OPEN |  | OSS Dashboards | UOC |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCDWDM | Applications/Tools | OPEN | COMPLETED | 0 |  |  | #N/A |  | 1
1877 | NOC213 | NOC | NA |  |  |  | DWDM | OSS | Zonal High Received Span Losses with TT for PKG_B Daily |  | Critical | OPEN |  | OSS Dashboards | UOC |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCDWDM | Applications/Tools | OPEN | COMPLETED | 0 |  |  | #N/A |  | 1
1878 | NOC214 | NOC | NA |  |  |  | DWDM | OSS | Zonal High Received Span Losses with TT for PKG_B Weekly |  | Critical | OPEN |  | OSS Dashboards | UOC |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCDWDM | Applications/Tools | OPEN | COMPLETED | 0 |  |  | #N/A |  | 1
1879 | NOC215 | NOC | NA |  |  |  | DWDM | OSS | Zonal High Received Span Losses with TT for PKG_B Monthly |  | Critical | OPEN |  | OSS Dashboards | UOC |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCDWDM | Applications/Tools | OPEN | COMPLETED | 0 |  |  | #N/A |  | 1
1880 | NOC216 | NOC | NA |  |  |  | DWDM | OSS | Zonal High Received Span Losses with TT for PKG_B (Selective from and to dates) |  | Critical | OPEN |  | OSS Dashboards | UOC |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCDWDM | Applications/Tools | OPEN | COMPLETED | 0 |  |  | #N/A |  | 1
1881 | NOC217 | NOC | NA |  |  |  | DWDM | OSS | Zonal High Received Span Losses with TT for PKG_C Daily |  | Critical | OPEN |  | OSS Dashboards | UOC |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCDWDM | Applications/Tools | OPEN | COMPLETED | 0 |  |  | #N/A |  | 1
1882 | NOC218 | NOC | NA |  |  |  | DWDM | OSS | Zonal High Received Span Losses with TT for PKG_C Weekly |  | Critical | OPEN |  | OSS Dashboards | UOC |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCDWDM | Applications/Tools | OPEN | COMPLETED | 0 |  |  | #N/A |  | 1
1883 | NOC219 | NOC | NA |  |  |  | DWDM | OSS | Zonal High Received Span Losses with TT for PKG_C Monthly |  | Critical | OPEN |  | OSS Dashboards | UOC |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCDWDM | Applications/Tools | OPEN | COMPLETED | 0 |  |  | #N/A |  | 1
1884 | NOC22 | NOC | NA |  | OSS | OSS | OSS | Service Assurance | Monitoring,tracking of field details, Tracking of GI services form and prepare Service assurance dashboard Daily |  | NON-Critical | OPEN |  | HPSM | Incident Management |  | OPEN-DEPENDENT |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCOSS | Applications/Tools | OPEN | OPEN-DEPENDENT | 0 |  |  | #N/A |  | 1
1885 | NOC220 | NOC | NA |  |  |  | DWDM | OSS | Zonal High Received Span Losses with TT for PKG_C (Selective from and to dates) |  | Critical | OPEN |  | OSS Dashboards | UOC |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCDWDM | Applications/Tools | OPEN | COMPLETED | 0 |  |  | #N/A |  | 1
1886 | NOC221 | NOC | NA |  | OSS | OSS | OSS | GPON/IPMPLS | Monitoring and published of Dark Fiber and TSWAN KPI Daily |  | Critical | OPEN |  | HPSM | Incident Management |  | OPEN-DEPENDENT |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCOSS | Applications/Tools | OPEN | OPEN-DEPENDENT | 0 |  |  | #N/A |  | 1
1887 | NOC222 | NOC | NA |  | OSS | OSS | OSS | GPON/IPMPLS | Monitoring and published of Dark Fiber and TSWAN KPI Weekly |  | Critical | OPEN |  | HPSM | Incident Management |  | OPEN-DEPENDENT |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCOSS | Applications/Tools | OPEN | OPEN-DEPENDENT | 0 |  |  | #N/A |  | 1
1888 | NOC223 | NOC | NA |  | OSS | OSS | OSS | GPON/IPMPLS | Monitoring and published of Dark Fiber and TSWAN KPI Monthly |  | Critical | OPEN |  | HPSM | Incident Management |  | OPEN-DEPENDENT |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCOSS | Applications/Tools | OPEN | OPEN-DEPENDENT | 0 |  |  | #N/A |  | 1
1889 | NOC224 | NOC | NA |  | OSS | OSS | OSS | GPON/IPMPLS | Monitoring and published of Dark Fiber and TSWAN KPI (Selective from and to dates) |  | Critical | OPEN |  | HPSM | Incident Management |  | OPEN-DEPENDENT |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCOSS | Applications/Tools | OPEN | OPEN-DEPENDENT | 0 |  |  | #N/A |  | 1
1890 | NOC225 | NOC | NA |  |  |  | IP/MPLS | OSS | Preparation and publishing of GP to GP and GP to Mandal link summary , uptime and MTTR dashboard Hourly |  | Critical | OPEN |  | HPSM | Incident Management |  | 11-09-2025: Uptime/Availability and MTTR is available for daily and monthly |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCIP/MPLS | Applications/Tools | OPEN | WIP | 11-09-2025: Uptime/Availability and MTTR is available for daily and monthly |  |  | #N/A |  | 1
1891 | NOC226 | NOC | NA |  |  |  | IP/MPLS | OSS | Preparation and publishing of GP to GP and GP to Mandal link summary , uptime and MTTR dashboard Daily |  | Critical | COMPLETED |  | HPSM | Incident Management |  | 11-09-2025: Uptime/Availability and MTTR is available for daily and monthly |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCIP/MPLS | Applications/Tools | OPEN | COMPLETED | 11-09-2025: Uptime/Availability and MTTR is available for daily and monthly |  |  |  |  | 1
1892 | NOC227 | NOC | NA |  |  |  | IP/MPLS | OSS | Preparation and publishing of GP to GP and GP to Mandal link summary , uptime and MTTR dashboard Weekly |  | Critical | COMPLETED |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCIP/MPLS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1
1893 | NOC228 | NOC | NA |  |  |  | IP/MPLS | OSS | Preparation and publishing of GP to GP and GP to Mandal link summary , uptime and MTTR dashboard Monthly |  | Critical | OPEN |  | HPSM | Incident Management |  | 11-09-2025: Uptime/Availability and MTTR is available for daily and monthly |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCIP/MPLS | Applications/Tools | OPEN | WIP | 11-09-2025: Uptime/Availability and MTTR is available for daily and monthly |  |  | #N/A |  | 1
1894 | NOC229 | NOC | NA |  |  |  | IP/MPLS | OSS | Preparation and publishing of GP to GP and GP to Mandal link summary , uptime and MTTR dashboard (Selective from and to dates) |  | Critical | OPEN |  | HPSM | Incident Management |  | 11-09-2025: Uptime/Availability and MTTR is available for daily and monthly |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCIP/MPLS | Applications/Tools | OPEN | WIP | 11-09-2025: Uptime/Availability and MTTR is available for daily and monthly |  |  | #N/A |  | 1
1895 | NOC23 | NOC | NA |  | OSS | OSS | OSS | Service Assurance | Monitoring,tracking of field details, Tracking of GI services form and prepare Service assurance dashboard Weekly |  | NON-Critical | OPEN |  | HPSM | Incident Management |  | OPEN-DEPENDENT |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCOSS | Applications/Tools | OPEN | OPEN-DEPENDENT | 0 |  |  | #N/A |  | 1
1896 | NOC230 | NOC | NA |  |  |  | IP/MPLS | OSS | Preparation and publishing of Mandal to Mandal and Mandal to Zonal link summary , uptime and MTTR dashboard Daily |  | Critical | COMPLETED |  | HPSM | Incident Management |  | 11-09-2025: Uptime/Availability and MTTR is available for daily and monthly |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCIP/MPLS | Applications/Tools | OPEN | COMPLETED | 11-09-2025: Uptime/Availability and MTTR is available for daily and monthly |  |  |  |  | 1
1897 | NOC231 | NOC | NA |  |  |  | IP/MPLS | OSS | Preparation and publishing of Mandal to Mandal and Mandal to Zonal link summary , uptime and MTTR dashboard Weekly |  | Critical | OPEN |  | HPSM | Incident Management |  | 11-09-2025: Uptime/Availability and MTTR is available for daily and monthly |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCIP/MPLS | Applications/Tools | OPEN | WIP | 11-09-2025: Uptime/Availability and MTTR is available for daily and monthly |  |  | #N/A |  | 1
1898 | NOC232 | NOC | NA |  |  |  | IP/MPLS | OSS | Preparation and publishing of Mandal to Mandal and Mandal to Zonal link summary , uptime and MTTR dashboard Monthly |  | Critical | OPEN |  | HPSM | Incident Management |  | 11-09-2025: Uptime/Availability and MTTR is available for daily and monthly |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCIP/MPLS | Applications/Tools | OPEN | WIP | 11-09-2025: Uptime/Availability and MTTR is available for daily and monthly |  |  | #N/A |  | 1
1899 | NOC233 | NOC | NA |  |  |  | IP/MPLS | OSS | Preparation and publishing of Mandal to Mandal and Mandal to Zonal link summary , uptime and MTTR dashboard (Selective from and to dates) |  | Critical | OPEN |  | HPSM | Incident Management |  | 11-09-2025: Uptime/Availability and MTTR is available for daily and monthly |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCIP/MPLS | Applications/Tools | OPEN | WIP | 11-09-2025: Uptime/Availability and MTTR is available for daily and monthly |  |  | #N/A |  | 1
1900 | NOC234 | NOC | NA |  |  |  | IP/MPLS | OSS | High priority link like Tfiber ring monitoring and publishing KPI Hourly |  | Critical | OPEN |  | HPSM | Incident Management |  | Manually group needs to form in the NNMi and from that group it can be monitored. Venkatesh is giving KT to Operation team |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCIP/MPLS | Applications/Tools | OPEN | COMPLETED | Manually group needs to form in the NNMi and from that group it can be monitored. Venkatesh is giving KT to Operation team |  |  | #N/A |  | 1
1901 | NOC235 | NOC | NA |  |  |  | IP/MPLS | OSS | High priority link like Tfiber ring monitoring and publishing KPI Daily |  | Critical | COMPLETED |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCIP/MPLS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1
1902 | NOC236 | NOC | NA |  |  |  | IP/MPLS | OSS | High priority link like Tfiber ring monitoring and publishing KPI Weekly |  | Critical | OPEN |  | HPSM | Incident Management |  | Manually group needs to form in the NNMi and from that group it can be monitored. Venkatesh is giving KT to Operation team |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCIP/MPLS | Applications/Tools | OPEN | COMPLETED | Manually group needs to form in the NNMi and from that group it can be monitored. Venkatesh is giving KT to Operation team |  |  | #N/A |  | 1
1903 | NOC237 | NOC | NA |  |  |  | IP/MPLS | OSS | High priority link like Tfiber ring monitoring and publishing KPI Monthly |  | Critical | COMPLETED |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCIP/MPLS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1
1904 | NOC238 | NOC | NA |  |  |  | IP/MPLS | OSS | High priority link like Tfiber ring monitoring and publishing KPI (Selective from and to dates) |  | Critical | COMPLETED |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCIP/MPLS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1
1905 | NOC239 | NOC | NA |  |  |  | IP/MPLS | OSS | Enteprise Services Delivery ( Aitel Towers, Airtel LWEsite, pioneer etc ) Monitoring, preparation KPI like Service Up reports Hourly |  | Critical | OPEN |  | HPSM | Incident Management |  | OPEN-DEPENDENT |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCIP/MPLS | Applications/Tools | OPEN | OPEN-DEPENDENT | 0 |  |  | #N/A |  | 1
1906 | NOC24 | NOC | NA |  | OSS | OSS | OSS | Service Assurance | Monitoring,tracking of field details, Tracking of GI services form and prepare Service assurance dashboard Monthly |  | NON-Critical | OPEN |  | HPSM | Incident Management |  | OPEN-DEPENDENT |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCOSS | Applications/Tools | OPEN | OPEN-DEPENDENT | 0 |  |  | #N/A |  | 1
1907 | NOC240 | NOC | NA |  |  |  | IP/MPLS | OSS | Enteprise Services Delivery ( Aitel Towers, Airtel LWEsite, pioneer etc ) Monitoring, preparation KPI like Service Up reports Daily |  | Critical | OPEN |  | HPSM | Incident Management |  | OPEN-DEPENDENT |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCIP/MPLS | Applications/Tools | OPEN | OPEN-DEPENDENT | 0 |  |  | #N/A |  | 1
1908 | NOC241 | NOC | NA |  |  |  | IP/MPLS | OSS | Enteprise Services Delivery ( Aitel Towers, Airtel LWEsite, pioneer etc ) Monitoring, preparation KPI like Service Up reports Weekly |  | Critical | OPEN |  | HPSM | Incident Management |  | OPEN-DEPENDENT |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCIP/MPLS | Applications/Tools | OPEN | OPEN-DEPENDENT | 0 |  |  | #N/A |  | 1
1909 | NOC242 | NOC | NA |  |  |  | IP/MPLS | OSS | Enteprise Services Delivery ( Aitel Towers, Airtel LWEsite, pioneer etc ) Monitoring, preparation KPI like Service Up reports Monthly |  | Critical | OPEN |  | HPSM | Incident Management |  | OPEN-DEPENDENT |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCIP/MPLS | Applications/Tools | OPEN | OPEN-DEPENDENT | 0 |  |  | #N/A |  | 1
1910 | NOC243 | NOC | NA |  |  |  | IP/MPLS | OSS | Enteprise Services Delivery ( Aitel Towers, Airtel LWEsite, pioneer etc ) Monitoring, preparation KPI like Service Up reports (Selective from and to dates) |  | Critical | OPEN |  | HPSM | Incident Management |  | OPEN-DEPENDENT |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCIP/MPLS | Applications/Tools | OPEN | OPEN-DEPENDENT | 0 |  |  | #N/A |  | 1
1911 | NOC244 | NOC | NA |  |  |  | IP/MPLS | OSS | Preparation and publishing of Enterprise Customer Service KPIs like availability, packet drops, latency, jitter & bandwidth utilization Daily |  | Critical | COMPLETED |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCIP/MPLS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1
1912 | NOC245 | NOC | NA |  |  |  | IP/MPLS | OSS | Preparation and publishing of Enterprise Customer Service KPIs like availability, packet drops, latency, jitter & bandwidth utilization Weekly |  | Critical | COMPLETED |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCIP/MPLS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1
1913 | NOC246 | NOC | NA |  |  |  | IP/MPLS | OSS | Preparation and publishing of Enterprise Customer Service KPIs like availability, packet drops, latency, jitter & bandwidth utilization Monthly |  | Critical | COMPLETED |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCIP/MPLS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1
1914 | NOC247 | NOC | NA |  |  |  | IP/MPLS | OSS | Preparation and publishing of Enterprise Customer Service KPIs like availability, packet drops, latency, jitter & bandwidth utilization (Selective from and to dates) |  | Critical | COMPLETED |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCIP/MPLS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1
1915 | NOC248 | NOC | NA |  |  |  | IP/MPLS | OSS | Preparation and publishing of all DC MPLS Network devices availability dashboard Daily |  | Critical | COMPLETED |  | NNMI | NPS |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCIP/MPLS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1
1916 | NOC249 | NOC | NA |  |  |  | IP/MPLS | OSS | Preparation and publishing of all DC MPLS Network devices availability dashboard Weekly |  | Critical | NOT_FEASIBLE |  | NNMI | NPS |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCIP/MPLS | Applications/Tools | #N/A | COMPLETED | available- hourly & weekly in NPS |  |  | #N/A |  | 1
1917 | NOC25 | NOC | NA |  | OSS | OSS | OSS | Service Assurance | Monitoring,tracking of field details, Tracking of GI services form and prepare Service assurance dashboard(Selective from and to dates) |  | NON-Critical | OPEN |  | HPSM | Incident Management |  | OPEN-DEPENDENT |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCOSS | Applications/Tools | OPEN | OPEN-DEPENDENT | 0 |  |  | #N/A |  | 1
1918 | NOC250 | NOC | NA |  |  |  | IP/MPLS | OSS | Preparation and publishing of all DC MPLS Network devices availability dashboard Monthly |  | Critical | COMPLETED |  | NNMI | NPS |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCIP/MPLS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1
1919 | NOC251 | NOC | NA |  |  |  | IP/MPLS | OSS | Preparation and publishing of all DC MPLS Network devices availability dashboard (Selective from and to dates) |  | Critical | COMPLETED |  | NNMI | NPS |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCIP/MPLS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1
1920 | NOC252 | NOC | NA |  |  |  | IP/MPLS | OSS | Prepartion and publishing of Core link availability and utilization dashboard Hourly |  | Critical | COMPLETED |  | HPSM | Incident Management |  | Link Group can be created in NNMi and monitor for only IPMPLS links |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCIP/MPLS | Applications/Tools | OPEN | COMPLETED | Link Group can be created in NNMi and monitor for only IPMPLS links |  |  |  |  | 1
1921 | NOC253 | NOC | NA |  |  |  | IP/MPLS | OSS | Prepartion and publishing of Core link availability and utilization dashboard Daily |  | Critical | COMPLETED |  | NNMI | NPS |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCIP/MPLS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1
1922 | NOC254 | NOC | NA |  |  |  | IP/MPLS | OSS | Prepartion and publishing of Core link availability and utilization dashboard Weekly |  | Critical | COMPLETED |  | NNMI | NPS |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCIP/MPLS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1
1923 | NOC255 | NOC | NA |  |  |  | IP/MPLS | OSS | Prepartion and publishing of Core link availability and utilization dashboard Monthly |  | Critical | COMPLETED |  | NNMI | NPS |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCIP/MPLS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1
1924 | NOC256 | NOC | NA |  |  |  | IP/MPLS | OSS | Prepartion and publishing of Core link availability and utilization dashboard (Selective from and to dates) |  | Critical | COMPLETED |  | NNMI | NPS |  | Link Group can be created in NNMi and monitor for only IPMPLS links |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCIP/MPLS | Applications/Tools | OPEN | COMPLETED | Link Group can be created in NNMi and monitor for only IPMPLS links |  |  |  |  | 1
1925 | NOC257 | NOC | NA |  |  |  | IP/MPLS | OSS | Package A Low RX Optical Power Levels in IPMPLS Network Daily |  | Critical | OPEN |  | NNMI | NNMI |  | 09-09-2025: Need confirmation from OT for "Low RX Optical Power Levels" KPI |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCIP/MPLS | Applications/Tools | OPEN | OPEN | 09-09-2025: Need confirmation from OT for "Low RX Optical Power Levels" KPI |  |  | #N/A |  | 1
1926 | NOC258 | NOC | NA |  |  |  | IP/MPLS | OSS | Package A Low RX Optical Power Levels in IPMPLS Network Weekly |  | Critical | OPEN |  | NNMI | NNMI |  |  |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCIP/MPLS | Applications/Tools | OPEN | OPEN | 0 |  |  | #N/A |  | 1
1927 | NOC259 | NOC | NA |  |  |  | IP/MPLS | OSS | Package A Low RX Optical Power Levels in IPMPLS Network Monthly |  | Critical | OPEN |  | NNMI | NNMI |  | 09-09-2025: Need confirmation from OT for "Low RX Optical Power Levels" KPI |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCIP/MPLS | Applications/Tools | OPEN | OPEN | 09-09-2025: Need confirmation from OT for "Low RX Optical Power Levels" KPI |  |  | #N/A |  | 1
1928 | NOC26 | NOC | NA |  | OSS | OSS | OSS | Service Monitoring | Monitoring,tracking service details, Tracking of GI services uptime Service assurance dashboard Daily |  | Critical | OPEN |  | HPSM | Incident Management |  | OPEN-DEPENDENT |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCOSS | Applications/Tools | OPEN | OPEN-DEPENDENT | 0 |  |  | #N/A |  | 1
1929 | NOC260 | NOC | NA |  |  |  | IP/MPLS | OSS | Package A Low RX Optical Power Levels in IPMPLS Network (Selective from and to dates) |  | Critical | OPEN |  | NNMI | NNMI |  | 09-09-2025: Need confirmation from OT for "Low RX Optical Power Levels" KPI |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCIP/MPLS | Applications/Tools | OPEN | OPEN | 09-09-2025: Need confirmation from OT for "Low RX Optical Power Levels" KPI |  |  | #N/A |  | 1
1930 | NOC261 | NOC | NA |  |  |  | IP/MPLS | OSS | Package B Low RX Optical Power Levels in IPMPLS Network Daily |  | Critical | OPEN |  | NNMI | NNMI |  | 09-09-2025: Need confirmation from OT for "Low RX Optical Power Levels" KPI |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCIP/MPLS | Applications/Tools | OPEN | OPEN | 09-09-2025: Need confirmation from OT for "Low RX Optical Power Levels" KPI |  |  | #N/A |  | 1
1931 | NOC262 | NOC | NA |  |  |  | IP/MPLS | OSS | Package B Low RX Optical Power Levels in IPMPLS Network Weekly |  | Critical | OPEN |  | NNMI | NNMI |  |  |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCIP/MPLS | Applications/Tools | OPEN | OPEN | 0 |  |  | #N/A |  | 1
1932 | NOC263 | NOC | NA |  |  |  | IP/MPLS | OSS | Package B Low RX Optical Power Levels in IPMPLS Network Monthly |  | Critical | OPEN |  | NNMI | NNMI |  | 09-09-2025: Need confirmation from OT for "Low RX Optical Power Levels" KPI |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCIP/MPLS | Applications/Tools | OPEN | OPEN | 09-09-2025: Need confirmation from OT for "Low RX Optical Power Levels" KPI |  |  | #N/A |  | 1
1933 | NOC264 | NOC | NA |  |  |  | IP/MPLS | OSS | Package B Low RX Optical Power Levels in IPMPLS Network (Selective from and to dates) |  | Critical | OPEN |  | NNMI | NNMI |  | 09-09-2025: Need confirmation from OT for "Low RX Optical Power Levels" KPI |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCIP/MPLS | Applications/Tools | OPEN | OPEN | 09-09-2025: Need confirmation from OT for "Low RX Optical Power Levels" KPI |  |  | #N/A |  | 1
1934 | NOC265 | NOC | NA |  |  |  | IP/MPLS | OSS | Package C Low RX Optical Power Levels in IPMPLS Network Daily |  | Critical | OPEN |  | NNMI | NNMI |  | 09-09-2025: Need confirmation from OT for "Low RX Optical Power Levels" KPI |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCIP/MPLS | Applications/Tools | OPEN | OPEN | 09-09-2025: Need confirmation from OT for "Low RX Optical Power Levels" KPI |  |  | #N/A |  | 1
1935 | NOC266 | NOC | NA |  |  |  | IP/MPLS | OSS | Package C Low RX Optical Power Levels in IPMPLS Network Weekly |  | Critical | OPEN |  | NNMI | NNMI |  |  |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCIP/MPLS | Applications/Tools | OPEN | OPEN | 0 |  |  | #N/A |  | 1
1936 | NOC267 | NOC | NA |  |  |  | IP/MPLS | OSS | Package C Low RX Optical Power Levels in IPMPLS Network Monthly |  | Critical | OPEN |  | NNMI | NNMI |  | 09-09-2025: Need confirmation from OT for "Low RX Optical Power Levels" KPI |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCIP/MPLS | Applications/Tools | OPEN | OPEN | 09-09-2025: Need confirmation from OT for "Low RX Optical Power Levels" KPI |  |  | #N/A |  | 1
1937 | NOC268 | NOC | NA |  |  |  | IP/MPLS | OSS | Package C Low RX Optical Power Levels in IPMPLS Network (Selective from and to dates) |  | Critical | OPEN |  | NNMI | NNMI |  | 09-09-2025: Need confirmation from OT for "Low RX Optical Power Levels" KPI |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCIP/MPLS | Applications/Tools | OPEN | OPEN | 09-09-2025: Need confirmation from OT for "Low RX Optical Power Levels" KPI |  |  | #N/A |  | 1
1938 | NOC269 | NOC | NA |  |  |  | IP/MPLS | OSS | Mandal Link Down + GP Link Down DFR Daily |  | Critical | COMPLETED |  | HPSM | Incident Management |  | 09-09-2025: Need confirmation from OT for "Low RX Optical Power Levels" KPI |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCIP/MPLS | Applications/Tools | OPEN | COMPLETED | 09-09-2025: Need confirmation from OT for "Low RX Optical Power Levels" KPI |  |  |  |  | 1
1939 | NOC27 | NOC | NA |  | OSS | OSS | OSS | Service Monitoring | Monitoring,tracking service details, Tracking of GI services uptime Service assurance dashboard Weekly |  | Critical | OPEN |  | HPSM | Incident Management |  | OPEN-DEPENDENT |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCOSS | Applications/Tools | OPEN | OPEN-DEPENDENT | 0 |  |  | #N/A |  | 1
1940 | NOC270 | NOC | NA |  |  |  | IP/MPLS | OSS | Mandal Link Down + GP Link Down DFR Weekly |  | Critical | COMPLETED |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCIP/MPLS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1
1941 | NOC271 | NOC | NA |  |  |  | IP/MPLS | OSS | Mandal Link Down + GP Link Down DFR Monthly |  | Critical | COMPLETED |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCIP/MPLS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1
1942 | NOC272 | NOC | NA |  |  |  | IP/MPLS | OSS | Mandal Link Down + GP Link Down DFR (Selective from and to dates) |  | Critical | COMPLETED |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCIP/MPLS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1
1943 | NOC273 | NOC | NA |  | OSS | OSS | All Domain | OSS | All Domain RMA Tracker //Daily Daily//Domain And package wise Filtering |  | Critical | COMPLETED |  | HPSM | Incident Management |  | Direct integration with OEM portal is not in scope, however manual ticket can be created in service manager using 'RMA_TAC' category and monitor the status and progress |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCAll Domain | Applications/Tools | OPEN | COMPLETED | Direct integration with OEM portal is not in scope, however manual ticket can be created in service manager using 'RMA_TAC' category and monitor the status and progress |  |  |  |  | 1
1944 | NOC274 | NOC | NA |  | OSS | OSS | All Domain | OSS | All Domain RMA Tracker //Daily Weekly Domain and package Wise Filtering |  | Critical | COMPLETED |  | HPSM | Incident Management |  | Direct integration with OEM portal is not in scope, however manual ticket can be created in service manager using 'RMA_TAC' category and monitor the status and progress |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCAll Domain | Applications/Tools | OPEN | COMPLETED | Direct integration with OEM portal is not in scope, however manual ticket can be created in service manager using 'RMA_TAC' category and monitor the status and progress |  |  |  |  | 1
1945 | NOC275 | NOC | NA |  | OSS | OSS | All Domain | OSS | All Domain RMA Tracker //Daily Monthly Domain and package Wise Filtering |  | Critical | COMPLETED |  | HPSM | Incident Management |  | Direct integration with OEM portal is not in scope, however manual ticket can be created in service manager using 'RMA_TAC' category and monitor the status and progress |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCAll Domain | Applications/Tools | OPEN | COMPLETED | Direct integration with OEM portal is not in scope, however manual ticket can be created in service manager using 'RMA_TAC' category and monitor the status and progress |  |  |  |  | 1
1946 | NOC276 | NOC | NA |  | OSS | OSS | All Domain | OSS | All OEM_TAC Cases Tracker Daily Domain and package Wise Filtering |  | Critical | COMPLETED |  | HPSM | Incident Management |  | Direct integration with OEM portal is not in scope, however manual ticket can be created in service manager using 'RMA_TAC' category and monitor the status and progress |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCAll Domain | Applications/Tools | OPEN | COMPLETED | Direct integration with OEM portal is not in scope, however manual ticket can be created in service manager using 'RMA_TAC' category and monitor the status and progress |  |  |  |  | 1
1947 | NOC277 | NOC | NA |  | OSS | OSS | All Domain | OSS | All OEM_TAC Cases Tracker Weekly Domain and package Wise Filtering |  | Critical | COMPLETED |  | HPSM | Incident Management |  | Direct integration with OEM portal is not in scope, however manual ticket can be created in service manager using 'RMA_TAC' category and monitor the status and progress |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCAll Domain | Applications/Tools | OPEN | COMPLETED | Direct integration with OEM portal is not in scope, however manual ticket can be created in service manager using 'RMA_TAC' category and monitor the status and progress |  |  |  |  | 1
1948 | NOC278 | NOC | NA |  | OSS | OSS | All Domain | OSS | All OEM_TAC Cases Tracker Monthly Domain and package Wise Filtering |  | Critical | COMPLETED |  | HPSM | Incident Management |  | Direct integration with OEM portal is not in scope, however manual ticket can be created in service manager using 'RMA_TAC' category and monitor the status and progress |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCAll Domain | Applications/Tools | OPEN | COMPLETED | Direct integration with OEM portal is not in scope, however manual ticket can be created in service manager using 'RMA_TAC' category and monitor the status and progress |  |  |  |  | 1
1949 | NOC279 | NOC | NA |  | OSS | OSS | All Domain | OSS | All OEM_TAC Cases Tracker (Selective from and to dates) Domain and package Wise Filtering |  | Critical | COMPLETED |  | HPSM | Incident Management |  | Direct integration with OEM portal is not in scope, however manual ticket can be created in service manager using 'RMA_TAC' category and monitor the status and progress |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCAll Domain | Applications/Tools | OPEN | COMPLETED | Direct integration with OEM portal is not in scope, however manual ticket can be created in service manager using 'RMA_TAC' category and monitor the status and progress |  |  |  |  | 1
1950 | NOC28 | NOC | NA |  | OSS | OSS | OSS | Service Monitoring | Monitoring,tracking service details, Tracking of GI services uptime Service assurance dashboard Monthly |  | Critical | OPEN |  | HPSM | Incident Management |  | OPEN-DEPENDENT |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCOSS | Applications/Tools | OPEN | OPEN-DEPENDENT | 0 |  |  | #N/A |  | 1
1951 | NOC280 | NOC | NA |  | OSS | OSS | All Domain | OSS | All Sites Infra OPEN TTs details for HRT(High Temparature) Alarm Daily |  | Critical | COMPLETED |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCAll Domain | Applications/Tools | OPEN | COMPLETED | need to check |  |  |  |  | 1
1952 | NOC281 | NOC | NA |  | OSS | OSS | All Domain | OSS | All Sites Infra OPEN TTs details for HRT(High Temparature) Alarm Weekly |  | Critical | COMPLETED |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCAll Domain | Applications/Tools | OPEN | COMPLETED | need to check |  |  |  |  | 1
1953 | NOC282 | NOC | NA |  | OSS | OSS | All Domain | OSS | All Sites Infra OPEN TTs details for HRT(High Temparature) Alarm Monthly |  | Critical | COMPLETED |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCAll Domain | Applications/Tools | OPEN | COMPLETED | need to check |  |  |  |  | 1
1954 | NOC283 | NOC | NA |  | OSS | OSS | All Domain | OSS | All Sites Infra OPEN TTs details for HRT(High Tempararure) Alarm (Selective from and to dates) |  | Critical | COMPLETED |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCAll Domain | Applications/Tools | OPEN | COMPLETED | need to check |  |  |  |  | 1
1955 | NOC284 | NOC | NA |  | OSS | OSS | OSS | Field Passive Infra | Field Passive Infra :: Package Wise District Level Visibility Status Daily |  | Critical | COMPLETED |  | NNMI | NNMI |  | 09-09-2025: live status will be available |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCOSS | Applications/Tools | OPEN | COMPLETED | 09-09-2025: live status will be available |  |  |  |  | 1
1956 | NOC285 | NOC | NA |  | OSS | OSS | OSS | Field Passive Infra | Field Passive Infra :: Package Wise District Level Visibility Status Weekly |  | Critical | NOT_FEASIBLE |  | NNMI | NNMI |  |  |  |  | Suresh Pawar |  | Open | Not Feasible | [9 empty] | NOCOSS | Applications/Tools | #N/A | NOT-FEASIBLE | 0 |  |  | #N/A |  | 1
1957 | NOC286 | NOC | NA |  | OSS | OSS | OSS | Field Passive Infra | Field Passive Infra :: Package Wise District Level Visibility Status Monthly |  | Critical | NOT_FEASIBLE |  | NNMI | NNMI |  |  |  |  | Suresh Pawar |  | Open | Not Feasible | [9 empty] | NOCOSS | Applications/Tools | #N/A | NOT-FEASIBLE | 0 |  |  | #N/A |  | 1
1958 | NOC287 | NOC | NA |  | OSS | OSS | OSS | Field Passive Infra | Field Passive Infra :: Package Wise District Level Visibility Status (Selective from and to dates) |  | Critical | NOT_FEASIBLE |  | NNMI | NNMI |  |  |  |  | Suresh Pawar |  | Open | Not Feasible | [9 empty] | NOCOSS | Applications/Tools | #N/A | NOT-FEASIBLE | avaiable in NNMI , assign to someone from oSSteam |  |  | #N/A |  | 1
1959 | NOC288 | NOC | NA |  | OSS | OSS | OSS | Field Passive Infra | NNMI :: Integration Status with Reachability Daily |  | Critical | COMPLETED |  | NNMI | NNMI |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCOSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1
1960 | NOC289 | NOC | NA |  | OSS | OSS | OSS | Field Passive Infra | NNMI :: Integration Status with Reachability Weekly |  | Critical | COMPLETED |  | NNMI | NNMI |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCOSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1
1961 | NOC29 | NOC | NA |  | OSS | OSS | OSS | Service Monitoring | Monitoring,tracking service details, Tracking of GI services uptime Service assurance dashboard (Selective from and to dates) |  | Critical | OPEN |  | HPSM | Incident Management |  | OPEN-DEPENDENT |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCOSS | Applications/Tools | OPEN | OPEN-DEPENDENT | 0 |  |  | #N/A |  | 1
1962 | NOC290 | NOC | NA |  | OSS | OSS | OSS | Field Passive Infra | NNMI :: Integration Status with Reachability Monthly |  | Critical | COMPLETED |  | NNMI | NNMI |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCOSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1
1963 | NOC291 | NOC | NA |  | OSS | OSS | OSS | Field Passive Infra | NNMI :: Integration Status with Reachability (Selective from and to dates) |  | Critical | COMPLETED |  | NNMI | NNMI |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCOSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1
1964 | NOC292 | NOC | NA |  | OSS | OSS | OSS | Field Passive Infra | PKG -A :: Open TTs for O&M GP for UPS Daily |  | Critical | COMPLETED |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCOSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1
1965 | NOC293 | NOC | NA |  | OSS | OSS | OSS | Field Passive Infra | PKG -A :: Open TTs for O&M GP for UPS Weekly |  | Critical | COMPLETED |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCOSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1
1966 | NOC294 | NOC | NA |  | OSS | OSS | OSS | Field Passive Infra | PKG -A :: Open TTs for O&M GP for UPS Monthly |  | Critical | COMPLETED |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCOSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1
1967 | NOC295 | NOC | NA |  | OSS | OSS | OSS | Field Passive Infra | PKG -A :: Open TTs for O&M GP for UPS (Selective from and to dates) |  | Critical | COMPLETED |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCOSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1
1968 | NOC296 | NOC | NA |  | OSS | OSS | OSS | Field Passive Infra | PKG -B :: Open TTs for O&M GP for UPS Daily |  | Critical | COMPLETED |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCOSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1
1969 | NOC297 | NOC | NA |  | OSS | OSS | OSS | Field Passive Infra | PKG -B :: Open TTs for O&M GP for UPS Weekly |  | Critical | COMPLETED |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCOSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1
1970 | NOC298 | NOC | NA |  | OSS | OSS | OSS | Field Passive Infra | PKG -B :: Open TTs for O&M GP for UPS Monthly |  | Critical | COMPLETED |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCOSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1
1971 | NOC299 | NOC | NA |  | OSS | OSS | OSS | Field Passive Infra | PKG -B :: Open TTs for O&M GP for UPS (Selective from and to dates) |  | Critical | COMPLETED |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCOSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1
1972 | NOC3 | NOC | NA |  | OSS | OSS | OSS | DC | DC Active Infra uptime & SLA Monthly |  | Critical |  |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCOSS | Applications/Tools | OPEN | OPEN | 0 |  |  | #N/A |  | 1
1973 | NOC30 | NOC | NA |  |  |  | Helpdesk | OSS | Service Delivery & Service Assurance Dash Board Daily |  | Critical | COMPLETED |  | HPSM | Incident Management |  | 11-09-2025: BSS will display all delivery data as well as service ticket informations in the CRM portal. OSS will maintain only technical information. |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCHelpdesk | Applications/Tools | OPEN | COMPLETED | 11-09-2025: BSS will display all delivery data as well as service ticket informations in the CRM portal. OSS will maintain only technical information. |  |  |  |  | 1
1974 | NOC300 | NOC | NA |  | OSS | OSS | OSS | Field Passive Infra | PKG -C :: Open TTs for O&M GP for UPS Daily |  | Critical | COMPLETED |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCOSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1
1975 | NOC301 | NOC | NA |  | OSS | OSS | OSS | Field Passive Infra | PKG -C :: Open TTs for O&M GP for UPS Weekly |  | Critical | COMPLETED |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCOSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1
1976 | NOC302 | NOC | NA |  | OSS | OSS | OSS | Field Passive Infra | PKG -C :: Open TTs for O&M GP for UPS Monthly |  | Critical | COMPLETED |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCOSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1
1977 | NOC303 | NOC | NA |  | OSS | OSS | OSS | Field Passive Infra | PKG -C :: Open TTs for O&M GP for UPS (Selective from and to dates) |  | Critical | COMPLETED |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCOSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1
1978 | NOC304 | NOC | NA |  | OSS | OSS | OSS | Field Passive Infra | SNMP issues _ Report Daily |  | Critical | COMPLETED |  | NNMI | NNMI |  | 09-09-2025: Live status will be available |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCOSS | Applications/Tools | OPEN | COMPLETED | 09-09-2025: Live status will be available |  |  |  |  | 1
1979 | NOC305 | NOC | NA |  | OSS | OSS | OSS | Field Passive Infra | SNMP issues _ Report Weekly |  | Critical | NOT_FEASIBLE |  | NNMI | NNMI |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCOSS | Applications/Tools | #N/A | COMPLETED | 0 |  |  | #N/A |  | 1
1980 | NOC306 | NOC | NA |  | OSS | OSS | OSS | Field Passive Infra | SNMP issues _ Report Monthly |  | Critical | NOT_FEASIBLE |  | NNMI | NNMI |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCOSS | Applications/Tools | #N/A | COMPLETED | 0 |  |  | #N/A |  | 1
1981 | NOC307 | NOC | NA |  | OSS | OSS | OSS | Field Passive Infra | SNMP issues _ Report (Selective from and to dates) |  | Critical | NOT_FEASIBLE |  | NNMI | NNMI |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCOSS | Applications/Tools | #N/A | COMPLETED | 0 |  |  | #N/A |  | 1
1982 | NOC308 | NOC | NA |  | OSS | OSS | OSS | Field Passive Infra | Mandal EB & Zonal DG Running report Daily |  | Critical | OPEN |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCOSS | Applications/Tools | OPEN | NOT-FEASIBLE | 0 |  |  | #N/A |  | 1
1983 | NOC309 | NOC | NA |  | OSS | OSS | OSS | Field Passive Infra | Mandal EB & Zonal DG Running report Weekly |  | Critical | OPEN |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCOSS | Applications/Tools | OPEN | NOT-FEASIBLE | 0 |  |  | #N/A |  | 1
1984 | NOC31 | NOC | NA |  |  |  | Helpdesk | OSS | Service Delivery & Service Assurance Dash Board Weekly |  | Critical | COMPLETED |  | HPSM | Incident Management |  | 11-09-2025: BSS will display all delivery data as well as service ticket informations in the CRM portal. OSS will maintain only technical information. |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCHelpdesk | Applications/Tools | OPEN | COMPLETED | 11-09-2025: BSS will display all delivery data as well as service ticket informations in the CRM portal. OSS will maintain only technical information. |  |  |  |  | 1
1985 | NOC310 | NOC | NA |  | OSS | OSS | OSS | Field Passive Infra | Mandal EB & Zonal DG Running report Monthly |  | Critical | OPEN |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCOSS | Applications/Tools | OPEN | NOT-FEASIBLE | 0 |  |  | #N/A |  | 1
1986 | NOC311 | NOC | NA |  | OSS | OSS | OSS | Field Passive Infra | Mandal EB & Zonal DG Running report (Selective from and to dates) |  | Critical | OPEN |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCOSS | Applications/Tools | OPEN | OPEN | 0 |  |  | #N/A |  | 1
1987 | NOC312 | NOC | NA |  | OSS | OSS | OSS | Field Passive Infra | DG Running status NNMi Logs Daily |  | Critical | COMPLETED |  | NNMI | NNMI |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCOSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1
1988 | NOC313 | NOC | NA |  | OSS | OSS | OSS | Field Passive Infra | DG Running status NNMi Logs Weekly |  | Critical | COMPLETED |  | NNMI | NNMI |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCOSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1
1989 | NOC314 | NOC | NA |  | OSS | OSS | OSS | Field Passive Infra | DG Running status NNMi Logs Monthly |  | Critical | COMPLETED |  | NNMI | NNMI |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCOSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1
1990 | NOC315 | NOC | NA |  | OSS | OSS | OSS | Field Passive Infra | DG Running status NNMi Logs (Selective from and to dates) |  | Critical | COMPLETED |  | NNMI | NNMI |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCOSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1
1991 | NOC316 | NOC | NA |  | OSS | OSS | OSS | Service Monitoring | Customised Dashboard as per Department/Service/Locations, etc.. Daily |  | Critical | COMPLETED |  | HPSM | Incident Management |  | 09-09-2025: Only Availability |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCOSS | Applications/Tools | OPEN | COMPLETED | 09-09-2025: Only Availability |  |  |  |  | 1
1992 | NOC317 | NOC | NA |  | OSS | OSS | OSS | Service Monitoring | Customised Dashboard as per Department/Service/Locations, etc..Weekly |  | Critical | NOT_FEASIBLE |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  | Open | Not Feasible | [9 empty] | NOCOSS | Applications/Tools | #N/A | NOT-FEASIBLE | 0 |  |  | #N/A |  | 1
1993 | NOC318 | NOC | NA |  | OSS | OSS | OSS | Service Monitoring | Customised Dashboard as per Department/Service/Locations, etc..Monthly |  | Critical | NOT_FEASIBLE |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  | Open | Not Feasible | [9 empty] | NOCOSS | Applications/Tools | #N/A | NOT-FEASIBLE | 0 |  |  | #N/A |  | 1
1994 | NOC319 | NOC | NA |  | OSS | OSS | OSS | Service Monitoring | Customised Dashboard as per Department/Service/Locations, etc..Selective Dates |  | Critical | NOT_FEASIBLE |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  | Open | Not Feasible | [9 empty] | NOCOSS | Applications/Tools | #N/A | NOT-FEASIBLE | 0 |  |  | #N/A |  | 1
1995 | NOC32 | NOC | NA |  |  |  | Helpdesk | OSS | Service Delivery & Service Assurance Dash Board Monthly |  | Critical | COMPLETED |  | HPSM | Incident Management |  | 11-09-2025: BSS will display all delivery data as well as service ticket informations in the CRM portal. OSS will maintain only technical information. |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCHelpdesk | Applications/Tools | OPEN | COMPLETED | 11-09-2025: BSS will display all delivery data as well as service ticket informations in the CRM portal. OSS will maintain only technical information. |  |  |  |  | 1
1996 | NOC320 | NOC | NA |  | OSS | OSS | OSS | Service Monitoring | T-NOC Report :: GI Sites SD SA Report Daily |  | Critical | COMPLETED |  | HPSM | Incident Management |  | 09-09-2025: SD report to be collected from BSS. Ticketing & utilization report is available in OSS. |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCOSS | Applications/Tools | OPEN | COMPLETED | 09-09-2025: SD report to be collected from BSS. Ticketing & utilization report is available in OSS. |  |  |  |  | 1
1997 | NOC321 | NOC | NA |  | OSS | OSS | OSS | Service Monitoring | T-NOC Report :: GI Sites SD SA Report Weekly |  | Critical | NOT_FEASIBLE |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  | Open | Not Feasible | [9 empty] | NOCOSS | Applications/Tools | #N/A | NOT-FEASIBLE | 0 |  |  | #N/A |  | 1
1998 | NOC322 | NOC | NA |  | OSS | OSS | OSS | Service Monitoring | T-NOC Report :: GI Sites SD SA Report Monthly |  | Critical | COMPLETED |  | HPSM | Incident Management |  | 09-09-2025: SD report to be collected from BSS. Ticketing & utilization report is available in OSS. |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCOSS | Applications/Tools | OPEN | COMPLETED | 09-09-2025: SD report to be collected from BSS. Ticketing & utilization report is available in OSS. |  |  |  |  | 1
1999 | NOC323 | NOC | NA |  | OSS | OSS | OSS | Service Monitoring | T-NOC Report :: GI Sites SD SA Report (Selective from and to dates) |  | Critical | COMPLETED |  | HPSM | Incident Management |  | 09-09-2025: SD report to be collected from BSS. Ticketing & utilization report is available in OSS. |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCOSS | Applications/Tools | OPEN | COMPLETED | 09-09-2025: SD report to be collected from BSS. Ticketing & utilization report is available in OSS. |  |  |  |  | 1
2000 | NOC324 | NOC | NA |  | OSS | OSS | OSS | Service Monitoring | List of GI with bandwidth Utilization Details Daily |  | Critical | COMPLETED |  | OSS Dashboards | PMS(UOC) |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCOSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1
2001 | NOC325 | NOC | NA |  | OSS | OSS | OSS | Service Monitoring | List of GI with bandwidth Utilization Details Weekly |  | Critical | NOT_FEASIBLE |  | OSS Dashboards | PMS(UOC) |  |  |  |  | Suresh Pawar |  | Open | Not Feasible | [9 empty] | NOCOSS | Applications/Tools | #N/A | NOT-FEASIBLE | 0 |  |  | #N/A |  | 1
2002 | NOC326 | NOC | NA |  | OSS | OSS | OSS | Service Monitoring | List of GI with bandwidth Utilization Details Monthly |  | Critical | COMPLETED |  | OSS Dashboards | PMS(UOC) |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCOSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1
2003 | NOC327 | NOC | NA |  | OSS | OSS | OSS | Service Monitoring | List of GI with bandwidth Utilization Details (Selective from and to dates) |  | Critical | NOT_FEASIBLE |  | OSS Dashboards | PMS(UOC) |  |  |  |  | Suresh Pawar |  | Open | Not Feasible | [9 empty] | NOCOSS | Applications/Tools | #N/A | NOT-FEASIBLE | 0 |  |  | #N/A |  | 1
2004 | NOC328 | NOC | NA |  | OSS | OSS | OSS | Service Monitoring | T-NOC :: Status Summary of Bandwidth Utilization & Non Utilization of WIFI Routers in GB & ONTs Status Daily |  | Critical | COMPLETED |  | OSS Dashboards | PMS(UOC) |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCOSS | Applications/Tools | OPEN | COMPLETED | ont bw |  |  |  |  | 1
2005 | NOC329 | NOC | NA |  | OSS | OSS | OSS | Service Monitoring | T-NOC :: Status Summary of Bandwidth Utilization & Non Utilization of WIFI Routers in GB & ONTs Status Weekly |  | Critical | NOT_FEASIBLE |  | OSS Dashboards | PMS(UOC) |  |  |  |  | Suresh Pawar |  | Open | Not Feasible | [9 empty] | NOCOSS | Applications/Tools | #N/A | NOT-FEASIBLE | 0 |  |  | #N/A |  | 1
2006 | NOC33 | NOC | NA |  |  |  | Helpdesk | OSS | Service Delivery & Service Assurance Dash Board (Selective from and to dates) |  | Critical | COMPLETED |  | HPSM | Incident Management |  | 11-09-2025: BSS will display all delivery data as well as service ticket informations in the CRM portal. OSS will maintain only technical information. |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCHelpdesk | Applications/Tools | OPEN | COMPLETED | 11-09-2025: BSS will display all delivery data as well as service ticket informations in the CRM portal. OSS will maintain only technical information. |  |  |  |  | 1
2007 | NOC330 | NOC | NA |  | OSS | OSS | OSS | Service Monitoring | T-NOC :: Status Summary of Bandwidth Utilization & Non Utilization of WIFI Routers in GB & ONTs Status Monthly |  | Critical | COMPLETED |  | OSS Dashboards | PMS(UOC) |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCOSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1
2008 | NOC331 | NOC | NA |  | OSS | OSS | OSS | Service Monitoring | T-NOC :: Status Summary of Bandwidth Utilization & Non Utilization of WIFI Routers in GB & ONTs Status (Selective from and to dates) |  | Critical | NOT_FEASIBLE |  | OSS Dashboards | PMS(UOC) |  |  |  |  | Suresh Pawar |  | Open | Not Feasible | [9 empty] | NOCOSS | Applications/Tools | #N/A | NOT-FEASIBLE | 0 |  |  | #N/A |  | 1
2009 | NOC332 | NOC | NA |  | OSS | OSS | New BSS | Service Monitoring | Request for FTTH Connection Details Sheet for T-Fiber Daily |  | Critical | OPEN |  | OSS Dashboards | PMS(UOC) |  | Not Relevent to OSS, It should come from BSS |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCNew BSS | #N/A | OPEN | Not Relevant to OSS | 0 |  |  | #N/A |  | 1
2010 | NOC333 | NOC | NA |  | OSS | OSS | New BSS | Service Monitoring | Request for FTTH Connection Details Sheet for T-Fiber Weekly |  | Critical | OPEN |  | OSS Dashboards | PMS(UOC) |  | Not Relevent to OSS, It should come from BSS |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCNew BSS | #N/A | OPEN | Not Relevant to OSS | 0 |  |  | #N/A |  | 1
2011 | NOC334 | NOC | NA |  | OSS | OSS | New BSS | Service Monitoring | Request for FTTH Connection Details Sheet for T-Fiber Monthly |  | Critical | OPEN |  | OSS Dashboards | PMS(UOC) |  | Not Relevent to OSS, It should come from BSS |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCNew BSS | #N/A | OPEN | Not Relevant to OSS | 0 |  |  | #N/A |  | 1
2012 | NOC335 | NOC | NA |  | OSS | OSS | New BSS | Service Monitoring | Request for FTTH Connection Details Sheet for T-Fiber (Selective from and to dates) |  | Critical | OPEN |  | OSS Dashboards | PMS(UOC) |  | Not Relevent to OSS, It should come from BSS |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCNew BSS | #N/A | OPEN | Not Relevant to OSS | 0 |  |  | #N/A |  | 1
2013 | NOC336 | NOC | NA |  | OSS | OSS | New BSS | Service Monitoring | Service Delivery & Service Assurance Dash Board (Signed Forms) Daily |  | Critical | OPEN |  | HPSM | Incident Management |  | Aditional Scope for OT/HPE |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCNew BSS | #N/A | OPEN | Not Relevant to OSS | 0 |  |  | #N/A |  | 1
2014 | NOC337 | NOC | NA |  | OSS | OSS | New BSS | Service Monitoring | Service Delivery & Service Assurance Dash Board (Signed Forms) Weekly |  | Critical | OPEN |  | HPSM | Incident Management |  | Aditional Scope for OT/HPE |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCNew BSS | #N/A | OPEN | Not Relevant to OSS | 0 |  |  | #N/A |  | 1
2015 | NOC338 | NOC | NA |  | OSS | OSS | New BSS | Service Monitoring | Service Delivery & Service Assurance Dash Board (Signed Forms) Monthly |  | Critical | OPEN |  | HPSM | Incident Management |  | Aditional Scope for OT/HPE |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCNew BSS | #N/A | OPEN | Not Relevant to OSS | 0 |  |  | #N/A |  | 1
2016 | NOC339 | NOC | NA |  | OSS | OSS | New BSS | Service Monitoring | Service Delivery & Service Assurance Dash Board (Signed Forms) (Selective from and to dates) |  | Critical | OPEN |  | HPSM | Incident Management |  | Aditional Scope for OT/HPE |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCNew BSS | #N/A | OPEN | Not Relevant to OSS | 0 |  |  | #N/A |  | 1
2017 | NOC34 | NOC | NA |  |  |  | Helpdesk | OSS | Incident Reporting and Field Assignment(Any failure/incident on any part of the network infrastructure or its facilities shall be communicated immediately to Helpdesk by Network Monitoring team/ field representative / end user giving details of the incident/fault/problem.) Daily |  | Critical |  |  | HPSM | Incident Management |  | 09-09-2025: Integration with WFM is in place to give live trigger to FE and SMS/email integration also in place to give notification to configured escallation matrix |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCHelpdesk | Applications/Tools | OPEN | NOT-FEASIBLE | 09-09-2025: Integration with WFM is in place to give live trigger to FE and SMS/email integration also in place to give notification to configured escallation matrix |  |  | #VALUE! |  | 1
2018 | NOC340 | NOC | NA |  | OSS | OSS | All Domain | OSS | PE Mapping with MTTR report Daily |  | Critical | OPEN |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCAll Domain | Applications/Tools | OPEN | WIP | 0 |  |  | #N/A |  | 1
2019 | NOC341 | NOC | NA |  | OSS | OSS | All Domain | OSS | PE Mapping with MTTR report Weekly |  | Critical | OPEN |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCAll Domain | Applications/Tools | OPEN | WIP | 0 |  |  | #N/A |  | 1
2020 | NOC342 | NOC | NA |  | OSS | OSS | All Domain | OSS | PE Mapping with MTTR report Monthly |  | Critical | OPEN |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCAll Domain | Applications/Tools | OPEN | WIP | 0 |  |  | #N/A |  | 1
2021 | NOC343 | NOC | NA |  | OSS | OSS | All Domain | OSS | PE Mapping with MTTR report (Selective from and to dates) |  | Critical | NOT_FEASIBLE |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCAll Domain | Applications/Tools | #N/A | COMPLETED | 0 |  |  | #N/A |  | 1
2022 | NOC344 | NOC | NA |  |  |  | BSS | Service Delivery | GI GP Wifi HH Delivery Status Daily |  | Critical | OPEN |  | BSS | CRM |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
2023 | NOC345 | NOC | NA |  |  |  | BSS | Service Delivery | GI GP Wifi HH Delivery Status Weekly |  | Critical | OPEN |  | BSS | CRM |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
2024 | NOC346 | NOC | NA |  |  |  | BSS | Service Delivery | GI GP Wifi HH Delivery Status Monthly |  | Critical | OPEN |  | BSS | CRM |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
2025 | NOC347 | NOC | NA |  |  |  | BSS | Service Delivery | GI GP Wifi HH Delivery Status (Selective from and to dates) |  | Critical | OPEN |  | BSS | CRM |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
2026 | NOC348 | NOC | NA |  |  |  | BSS | Service Delivery | Service IDs for all GI Locatinos Daily |  | Critical | OPEN |  | BSS | CRM |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
2027 | NOC349 | NOC | NA |  |  |  | BSS | Service Delivery | Service IDs for all GI Locatinos Weekly |  | Critical | OPEN |  | BSS | CRM |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
2028 | NOC35 | NOC | NA |  |  |  | Helpdesk | OSS | Incident Reporting and Field Assignment(Any failure/incident on any part of the network infrastructure or its facilities shall be communicated immediately to Helpdesk by Network Monitoring team/ field representative / end user giving details of the incident/fault/problem.) Weekly |  | Critical |  |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCHelpdesk | Applications/Tools | OPEN | COMPLETED | 0 |  |  | #VALUE! |  | 1
2029 | NOC350 | NOC | NA |  |  |  | BSS | Service Delivery | Service IDs for all GI Locatinos Monthly |  | Critical | OPEN |  | BSS | CRM |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
2030 | NOC351 | NOC | NA |  |  |  | BSS | Service Delivery | Service IDs for all GI Locatinos (Selective from and to dates) |  | Critical | OPEN |  | BSS | CRM |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
2031 | NOC352 | NOC | NA |  |  |  | BSS | Service Delivery | Household Delivery Status Report Daily |  | Critical | OPEN |  | BSS | CRM |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
2032 | NOC353 | NOC | NA |  |  |  | BSS | Service Delivery | Household Delivery Status Report Weekly |  | Critical | OPEN |  | BSS | CRM |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
2033 | NOC354 | NOC | NA |  |  |  | BSS | Service Delivery | Household Delivery Status Report Monthly |  | Critical | OPEN |  | BSS | CRM |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
2034 | NOC355 | NOC | NA |  |  |  | BSS | Service Delivery | Household Delivery Status Report (Selective from and to dates) |  | Critical | OPEN |  | BSS | CRM |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
2035 | NOC356 | NOC | NA |  | OSS | OSS | All Domain | OSS | Alarm seviority(Critical/major/Minor)(Domain wise Filter) Daily |  | Critical | COMPLETED |  | OSS Dashboards | VTemip |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCAll Domain | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1
2036 | NOC357 | NOC | NA |  | OSS | OSS | All Domain | OSS | Alarm seviority(Critical/major/Minor)(Domain wise Filter) Weekly |  | Critical | COMPLETED |  | OSS Dashboards | VTemip |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCAll Domain | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1
2037 | NOC358 | NOC | NA |  | OSS | OSS | All Domain | OSS | Alarm seviority(Critical/major/Minor)(Domain wise Filter) Monthly |  | Critical | COMPLETED |  | OSS Dashboards | VTemip |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCAll Domain | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1
2038 | NOC359 | NOC | NA |  | OSS | OSS | All Domain | OSS | Alarm seviority(Critical/major/Minor)(Domain wise Filter) (Selective from and to dates) |  | Critical | COMPLETED |  | OSS Dashboards | VTemip |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCAll Domain | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1
2039 | NOC36 | NOC | NA |  |  |  | Helpdesk | OSS | Incident Reporting and Field Assignment(Any failure/incident on any part of the network infrastructure or its facilities shall be communicated immediately to Helpdesk by Network Monitoring team/ field representative / end user giving details of the incident/fault/problem.) Monthly |  | Critical |  |  | HPSM | Incident Management |  | 09-09-2025: Integration with WFM is in place to give live trigger to FE and SMS/email integration also in place to give notification to configured escallation matrix |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCHelpdesk | Applications/Tools | OPEN | NOT-FEASIBLE | 09-09-2025: Integration with WFM is in place to give live trigger to FE and SMS/email integration also in place to give notification to configured escallation matrix |  |  | #VALUE! |  | 1
2040 | NOC360 | NOC | NA |  | OSS | OSS | All Domain | OSS | Inventory Dashboard and Report(Domain wise Filter) Daily |  | Critical | COMPLETED |  | OSS Dashboards | UTM |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCAll Domain | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1
2041 | NOC361 | NOC | NA |  | OSS | OSS | All Domain | OSS | Inventory Dashboard and Report(Domain wise Filter) Weekly |  | Critical | NOT_FEASIBLE |  | OSS Dashboards | UTM |  |  |  |  | Suresh Pawar |  | Open | Not Feasible | [9 empty] | NOCAll Domain | Applications/Tools | #N/A | NOT-FEASIBLE | 0 |  |  | #N/A |  | 1
2042 | NOC362 | NOC | NA |  | OSS | OSS | All Domain | OSS | Inventory Dashboard and Report(Domain wise Filter) Monthly |  | Critical | NOT_FEASIBLE |  | OSS Dashboards | UTM |  |  |  |  | Suresh Pawar |  | Open | Not Feasible | [9 empty] | NOCAll Domain | Applications/Tools | #N/A | NOT-FEASIBLE | 0 |  |  | #N/A |  | 1
2043 | NOC363 | NOC | NA |  | OSS | OSS | All Domain | OSS | Inventory Dashboard and Report(Domain wise Filter) (Selective from and to dates) |  | Critical | NOT_FEASIBLE |  | OSS Dashboards | UTM |  |  |  |  | Suresh Pawar |  | Open | Not Feasible | [9 empty] | NOCAll Domain | Applications/Tools | #N/A | NOT-FEASIBLE | 0 |  |  | #N/A |  | 1
2044 | NOC364 | NOC | NA |  | OSS | OSS | All Domain | OSS | Correlation within Domain and cross domain Daily |  | Critical |  |  | OSS Dashboards | UCA |  |  |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCAll Domain | Applications/Tools | OPEN | OPEN | 0 |  |  | #N/A |  | 1
2045 | NOC365 | NOC | NA |  | OSS | OSS | All Domain | OSS | Correlation within Domain and cross domain Weekly |  | Critical | DUPLICATE POINT |  | OSS Dashboards | UCA |  | DUPLICATE POINT |  |  | Suresh Pawar |  | Open | WIP | [9 empty] | NOCAll Domain | Applications/Tools | OPEN | OPEN | 0 |  |  | #N/A |  | 1
2046 | NOC366 | NOC | NA |  | OSS | OSS | All Domain | OSS | Correlation within Domain and cross domain Monthly |  | Critical |  |  | OSS Dashboards | UCA |  |  |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCAll Domain | Applications/Tools | OPEN | OPEN | 0 |  |  | #N/A |  | 1
2047 | NOC367 | NOC | NA |  | OSS | OSS | All Domain | OSS | Correlation within Domain and cross domain (Selective from and to dates) |  | Critical |  |  | OSS Dashboards | UCA |  |  |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCAll Domain | Applications/Tools | OPEN | OPEN | 0 |  |  | #N/A |  | 1
2048 | NOC368 | NOC | NA |  | OSS | OSS | OSS | DC IT Active Infra | Service Monitoring of All DC Elements(DC WAN, Leaf, Spine and Service riding on these Network and Servers) Daily |  | Critical |  |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCOSS | Applications/Tools | OPEN | OPEN | 0 |  |  | #N/A |  | 1
2049 | NOC369 | NOC | NA |  | OSS | OSS | OSS | DC IT Active Infra | Service Monitoring of All DC Elements(DC WAN, Leaf, Spine and Service riding on these Network and Servers) Weekly |  | Critical |  |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCOSS | Applications/Tools | OPEN | OPEN | 0 |  |  | #N/A |  | 1
2050 | NOC37 | NOC | NA |  |  |  | Helpdesk | OSS | Incident Reporting and Field Assignment(Any failure/incident on any part of the network infrastructure or its facilities shall be communicated immediately to Helpdesk by Network Monitoring team/ field representative / end user giving details of the incident/fault/problem.) (Selective from and to dates) |  | Critical |  |  | HPSM | Incident Management |  | 09-09-2025: Integration with WFM is in place to give live trigger to FE and SMS/email integration also in place to give notification to configured escallation matrix |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCHelpdesk | Applications/Tools | OPEN | NOT-FEASIBLE | 09-09-2025: Integration with WFM is in place to give live trigger to FE and SMS/email integration also in place to give notification to configured escallation matrix |  |  | #VALUE! |  | 1
2051 | NOC370 | NOC | NA |  | OSS | OSS | OSS | DC IT Active Infra | Service Monitoring of All DC Elements(DC WAN, Leaf, Spine and Service riding on these Network and Servers) Monthly |  | Critical |  |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCOSS | Applications/Tools | OPEN | OPEN | 0 |  |  | #N/A |  | 1
2052 | NOC371 | NOC | NA |  | OSS | OSS | OSS | DC IT Active Infra | Service Monitoring of All DC Elements(DC WAN, Leaf, Spine and Service riding on these Network and Servers) (Selective from and to dates) |  | Critical |  |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCOSS | Applications/Tools | OPEN | OPEN | 0 |  |  | #N/A |  | 1
2053 | NOC372 | NOC | NA |  | OSS | OSS | All Domain | OSS | Interface Utilisation(>80%) Hourly |  | Critical | COMPLETED |  | NNMI | NPS |  | 09-09-2025: Threshold limits needs tobe enabled and on that threshold limit the alarms to be generated and that alarm should qualify for ticket generation as per requirement |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCAll Domain | Applications/Tools | OPEN | COMPLETED | 09-09-2025: Threshold limits needs tobe enabled and on that threshold limit the alarms to be generated and that alarm should qualify for ticket generation as per requirement-need to check with govind |  |  |  |  | 1
2054 | NOC373 | NOC | NA |  | OSS | OSS | All Domain | OSS | Interface Utilisation(>80%) Daily |  | Critical | COMPLETED |  | NNMI | NPS |  | 09-09-2025: Threshold limits needs tobe enabled and on that threshold limit the alarms to be generated and that alarm should qualify for ticket generation as per requirement |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCAll Domain | Applications/Tools | OPEN | COMPLETED | 09-09-2025: Threshold limits needs tobe enabled and on that threshold limit the alarms to be generated and that alarm should qualify for ticket generation as per requirement |  |  |  |  | 1
2055 | NOC374 | NOC | NA |  | OSS | OSS | All Domain | OSS | Interface Utilisation(>80%) Weekly |  | Critical | COMPLETED |  | NNMI | NPS |  | 09-09-2025: Threshold limits needs tobe enabled and on that threshold limit the alarms to be generated and that alarm should qualify for ticket generation as per requirement |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCAll Domain | Applications/Tools | OPEN | COMPLETED | 09-09-2025: Threshold limits needs tobe enabled and on that threshold limit the alarms to be generated and that alarm should qualify for ticket generation as per requirement |  |  |  |  | 1
2056 | NOC375 | NOC | NA |  | OSS | OSS | All Domain | OSS | Interface Utilisation(>80%) Monthly |  | Critical | COMPLETED |  | NNMI | NPS |  | 09-09-2025: Threshold limits needs tobe enabled and on that threshold limit the alarms to be generated and that alarm should qualify for ticket generation as per requirement |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCAll Domain | Applications/Tools | OPEN | COMPLETED | 09-09-2025: Threshold limits needs tobe enabled and on that threshold limit the alarms to be generated and that alarm should qualify for ticket generation as per requirement |  |  |  |  | 1
2057 | NOC376 | NOC | NA |  | OSS | OSS | All Domain | OSS | Interface Utilisation(% of Utilisation configurable) |  | Critical | COMPLETED |  | NNMI | NPS |  | 09-09-2025: Threshold limits needs tobe enabled and on that threshold limit the alarms to be generated and that alarm should qualify for ticket generation as per requirement |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCAll Domain | Applications/Tools | OPEN | COMPLETED | 09-09-2025: Threshold limits needs tobe enabled and on that threshold limit the alarms to be generated and that alarm should qualify for ticket generation as per requirement |  |  |  |  | 1
2058 | NOC377 | NOC | NA |  | OSS | OSS | All Domain | OSS | Interface Utilisation(Polling Duration configurable) |  | Critical | COMPLETED |  | NNMI | NPS |  | 09-09-2025: Threshold limits needs tobe enabled and on that threshold limit the alarms to be generated and that alarm should qualify for ticket generation as per requirement |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCAll Domain | Applications/Tools | OPEN | COMPLETED | 09-09-2025: Threshold limits needs tobe enabled and on that threshold limit the alarms to be generated and that alarm should qualify for ticket generation as per requirement |  |  |  |  | 1
2059 | NOC378 | NOC | NA |  | OSS | OSS | All Domain | OSS | Interface Utilisation(>80%) (Selective from and to dates) |  | Critical | COMPLETED |  | NNMI | NPS |  | 09-09-2025: Threshold limits needs tobe enabled and on that threshold limit the alarms to be generated and that alarm should qualify for ticket generation as per requirement |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCAll Domain | Applications/Tools | OPEN | COMPLETED | 09-09-2025: Threshold limits needs tobe enabled and on that threshold limit the alarms to be generated and that alarm should qualify for ticket generation as per requirement |  |  |  |  | 1
2060 | NOC379 | NOC | NA |  | OSS | OSS | All Domain | OSS | CPU/RAM(>80%) Daily |  | Critical | COMPLETED |  | NNMI | NPS |  | 09-09-2025: Threshold limits needs tobe enabled and on that threshold limit the alarms to be generated and that alarm should qualify for ticket generation as per requirement |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCAll Domain | Applications/Tools | OPEN | COMPLETED | 09-09-2025: Threshold limits needs tobe enabled and on that threshold limit the alarms to be generated and that alarm should qualify for ticket generation as per requirement |  |  |  |  | 1
2061 | NOC38 | NOC | NA |  |  |  | Helpdesk | Help Desk | Help Desk managing and publishing KPI like Total I/O call, answereed call withing time frame etc. Hourly |  | NON-Critical |  |  | Helpdesk | Dial center | CLosed | 24-Sep-25: Option available to Choose Dates, daily, Weekly and Monthly But not Direct as Daily, Weekly, Monthly |  |  | Siva Kumar |  |  | COMPLETED & APPROVED | [9 empty] | NOCHelpdesk | Applications/Tools | CLOSED |  |  |  | 2025-09-24 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\NOC38,39,40,41,42 |  | 1
2062 | NOC380 | NOC | NA |  | OSS | OSS | All Domain | OSS | CPU/RAM(>80%) Weekly |  | Critical | COMPLETED |  | NNMI | NPS |  | 09-09-2025: Threshold limits needs tobe enabled and on that threshold limit the alarms to be generated and that alarm should qualify for ticket generation as per requirement |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCAll Domain | Applications/Tools | OPEN | COMPLETED | 09-09-2025: Threshold limits needs tobe enabled and on that threshold limit the alarms to be generated and that alarm should qualify for ticket generation as per requirement |  |  |  |  | 1
2063 | NOC381 | NOC | NA |  | OSS | OSS | All Domain | OSS | CPU/RAM(>80%) Monthly |  | Critical | COMPLETED |  | NNMI | NPS |  | 09-09-2025: Threshold limits needs tobe enabled and on that threshold limit the alarms to be generated and that alarm should qualify for ticket generation as per requirement |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCAll Domain | Applications/Tools | OPEN | COMPLETED | 09-09-2025: Threshold limits needs tobe enabled and on that threshold limit the alarms to be generated and that alarm should qualify for ticket generation as per requirement |  |  |  |  | 1
2064 | NOC382 | NOC | NA |  | OSS | OSS | All Domain | OSS | CPU/RAM(% of Utilisation configurable) |  | Critical | COMPLETED |  | NNMI | NPS |  | 09-09-2025: Threshold limits needs tobe enabled and on that threshold limit the alarms to be generated and that alarm should qualify for ticket generation as per requirement |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCAll Domain | Applications/Tools | OPEN | COMPLETED | 09-09-2025: Threshold limits needs tobe enabled and on that threshold limit the alarms to be generated and that alarm should qualify for ticket generation as per requirement |  |  |  |  | 1
2065 | NOC383 | NOC | NA |  | OSS | OSS | All Domain | OSS | CPU/RAM(Polling Duration configurable) |  | Critical | COMPLETED |  | NNMI | NPS |  | 09-09-2025: Threshold limits needs tobe enabled and on that threshold limit the alarms to be generated and that alarm should qualify for ticket generation as per requirement |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCAll Domain | Applications/Tools | OPEN | COMPLETED | 09-09-2025: Threshold limits needs tobe enabled and on that threshold limit the alarms to be generated and that alarm should qualify for ticket generation as per requirement |  |  |  |  | 1
2066 | NOC384 | NOC | NA |  | OSS | OSS | All Domain | OSS | CPU/RAM(>80%) (Selective from and to dates) |  | Critical | COMPLETED |  | NNMI | NPS |  | 09-09-2025: Threshold limits needs tobe enabled and on that threshold limit the alarms to be generated and that alarm should qualify for ticket generation as per requirement |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCAll Domain | Applications/Tools | OPEN | COMPLETED | 09-09-2025: Threshold limits needs tobe enabled and on that threshold limit the alarms to be generated and that alarm should qualify for ticket generation as per requirement |  |  |  |  | 1
2067 | NOC385 | NOC | NA |  | OSS | OSS | All Domain | OSS | Incident/Alarm Notifciation via SMS, E-mail and Call, Whatsapp as per escalation Matrix (Selective from and to dates) |  | Critical | COMPLETED |  | HPSM | Incident Management |  | 09-09-2025: SMS & EMAIL is integrated. Whatsapp & Call not feasible |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCAll Domain | Applications/Tools | OPEN | COMPLETED | 09-09-2025: SMS & EMAIL is integrated. Whatsapp & Call not feasible-earlier it was present as there was no credit it was stopped |  |  |  |  | 1
2068 | NOC386 | NOC | NA |  | OSS | OSS | All Domain | OSS | Node(POP) wise Availability Daily |  | Critical | COMPLETED |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCAll Domain | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1
2069 | NOC387 | NOC | NA |  | OSS | OSS | All Domain | OSS | Node(POP) wise Availability Weekly |  | Critical | NOT_FEASIBLE |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  | Open | Not Feasible | [9 empty] | NOCAll Domain | Applications/Tools | #N/A | NOT-FEASIBLE | 0 |  |  | #N/A |  | 1
2070 | NOC388 | NOC | NA |  | OSS | OSS | All Domain | OSS | Node(POP) wise Availability Monthly |  | Critical | COMPLETED |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCAll Domain | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1
2071 | NOC389 | NOC | NA |  | OSS | OSS | All Domain | OSS | Node(POP) wise Availability (Selective from and to dates) |  | Critical | NOT_FEASIBLE |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  | Open | Not Feasible | [9 empty] | NOCAll Domain | Applications/Tools | #N/A | NOT-FEASIBLE | 0 |  |  | #N/A |  | 1
2072 | NOC39 | NOC | NA |  |  |  | Helpdesk | Help Desk | Help Desk managing and publishing KPI like Total I/O call, answereed call withing time frame etc. Daily |  | NON-Critical |  |  | Helpdesk | Dial center | CLosed | 24-Sep-25: Option available to Choose Dates, daily, Weekly and Monthly But not Direct as Daily, Weekly, Monthly |  |  | Siva Kumar |  |  | COMPLETED & APPROVED | [9 empty] | NOCHelpdesk | Applications/Tools | CLOSED |  |  |  | 2025-09-24 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\NOC38,39,40,41,42 |  | 1
2073 | NOC390 | NOC | NA |  | OSS | OSS | All Domain | OSS | Equipment wise Availability Daily |  | Critical | COMPLETED |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCAll Domain | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1
2074 | NOC391 | NOC | NA |  | OSS | OSS | All Domain | OSS | Equipment wise Availability Weekly |  | Critical | NOT_FEASIBLE |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  | Open | Not Feasible | [9 empty] | NOCAll Domain | Applications/Tools | #N/A | NOT-FEASIBLE | 0 |  |  | #N/A |  | 1
2075 | NOC392 | NOC | NA |  | OSS | OSS | All Domain | OSS | Equipment wise Availability Monthly |  | Critical | COMPLETED |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCAll Domain | Applications/Tools | OPEN | COMPLETED | for DWDN no monthly report inUOC |  |  |  |  | 1
2076 | NOC393 | NOC | NA |  | OSS | OSS | All Domain | OSS | Equipment wise Availability (Selective from and to dates) |  | Critical | NOT_FEASIBLE |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  | Open | Not Feasible | [9 empty] | NOCAll Domain | Applications/Tools | #N/A | NOT-FEASIBLE | 0 |  |  | #N/A |  | 1
2077 | NOC394 | NOC | NA |  | OSS | OSS | All Domain | OSS | Link wise Uptime Daily |  | Critical | COMPLETED |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCAll Domain | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1
2078 | NOC395 | NOC | NA |  | OSS | OSS | All Domain | OSS | Link wise Uptime Weekly |  | Critical | NOT_FEASIBLE |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  | Open | Not Feasible | [9 empty] | NOCAll Domain | Applications/Tools | #N/A | NOT-FEASIBLE | 0 |  |  | #N/A |  | 1
2079 | NOC396 | NOC | NA |  | OSS | OSS | All Domain | OSS | Link wise Uptime Monthly |  | Critical | COMPLETED |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCAll Domain | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1
2080 | NOC397 | NOC | NA |  | OSS | OSS | All Domain | OSS | Link wise Uptime (Selective from and to dates) |  | Critical | NOT_FEASIBLE |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  | Open | Not Feasible | [9 empty] | NOCAll Domain | Applications/Tools | #N/A | NOT-FEASIBLE | 0 |  |  | #N/A |  | 1
2081 | NOC398 | NOC | NA |  | OSS | OSS | All Domain | OSS | Link wise MTTR Daily |  | Critical | OPEN |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCAll Domain | Applications/Tools | OPEN | WIP | 0 |  |  | #N/A |  | 1
2082 | NOC399 | NOC | NA |  | OSS | OSS | All Domain | OSS | Link wise MTTR Weekly |  | Critical | OPEN |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCAll Domain | Applications/Tools | OPEN | WIP | 0 |  |  | #N/A |  | 1
2083 | NOC4 | NOC | NA |  | OSS | OSS | OSS | DC | DC Active Infra uptime & SLA Custom(Selective from and to dates) |  | Critical |  |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCOSS | Applications/Tools | OPEN | OPEN | 0 |  |  | #N/A |  | 1
2084 | NOC40 | NOC | NA |  |  |  | Helpdesk | Help Desk | Help Desk managing and publishing KPI like Total I/O call, answereed call withing time frame etc. Weekly |  | NON-Critical |  |  | Helpdesk | Dial center | CLosed | 24-Sep-25: Option available to Choose Dates, daily, Weekly and Monthly But not Direct as Daily, Weekly, Monthly |  |  | Siva Kumar |  |  | COMPLETED & APPROVED | [9 empty] | NOCHelpdesk | Applications/Tools | CLOSED |  |  |  | 2025-09-24 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\NOC38,39,40,41,42 |  | 1
2085 | NOC400 | NOC | NA |  | OSS | OSS | All Domain | OSS | Link wise MTTR Monthly |  | Critical | OPEN |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCAll Domain | Applications/Tools | OPEN | WIP | 0 |  |  | #N/A |  | 1
2086 | NOC401 | NOC | NA |  | OSS | OSS | All Domain | OSS | Link wise MTTR (Selective from and to dates) |  | Critical | NOT_FEASIBLE |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCAll Domain | Applications/Tools | #N/A | COMPLETED | 0 |  |  | #N/A |  | 1
2087 | NOC402 | NOC | NA |  | OSS | OSS | OSS | DC and Field IPMPLS | IPSLA Daily(Packet Drops, Latency, Jitter, ect..) |  | Critical | COMPLETED |  | NNMI | NPS |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCOSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1
2088 | NOC403 | NOC | NA |  | OSS | OSS | OSS | DC and Field IPMPLS | IPSLA Weekly(Packet drops, latency, jitter, etc..) |  | Critical | COMPLETED |  | NNMI | NPS |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCOSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1
2089 | NOC404 | NOC | NA |  | OSS | OSS | OSS | DC and Field IPMPLS | IPSLA Monthly (Packet drops, latency, jitter, etc..) |  | Critical | COMPLETED |  | NNMI | NPS |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCOSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1
2090 | NOC405 | NOC | NA |  | OSS | OSS | OSS | DC and Field IPMPLS | IPSLA (Selective from and to dates)(Packet drops, latency, jitter, etc..) |  | Critical | COMPLETED |  | NNMI | NPS |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCOSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1
2091 | NOC406 | NOC | NA |  | OSS | OSS | OSS | DC and Field IPMPLS | IPSLA (Packet drops to be configurable and existing >1% to be reported in Dashboard |  | Critical | COMPLETED |  | NNMI | NPS |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCOSS | Applications/Tools | OPEN | COMPLETED | To be checked |  |  |  |  | 1
2092 | NOC407 | NOC | NA |  | OSS | OSS | OSS | DC and Field IPMPLS | IPSLA (Latency to be configurable and existing >10ms to be reported in Dashboard |  | Critical | COMPLETED |  | NNMI | NPS |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCOSS | Applications/Tools | OPEN | COMPLETED | To be checked |  |  |  |  | 1
2093 | NOC408 | NOC | NA |  | OSS | OSS | OSS | DC and Field IPMPLS | IPSLA (Jitter to be configurable and existing >30ms to be reported in Dashboard |  | Critical | COMPLETED |  | NNMI | NPS |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCOSS | Applications/Tools | OPEN | COMPLETED | To be checked |  |  |  |  | 1
2094 | NOC409 | NOC | NA |  | OSS | OSS | OSS | DC and Field IPMPLS | Traffic Utilisation covering All QoS Partameters Daily |  | Critical | OPEN |  | NNMI | NPS |  | 09-09-2025: Need to discuss with OT |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCOSS | Applications/Tools | OPEN | OPEN | 09-09-2025: Need to discuss with OT |  |  | #N/A |  | 1
2095 | NOC41 | NOC | NA |  |  |  | Helpdesk | Help Desk | Help Desk managing and publishing KPI like Total I/O call, answereed call withing time frame etc. Monthly |  | NON-Critical |  |  | Helpdesk | Dial center | CLosed | 24-Sep-25: Option available to Choose Dates, daily, Weekly and Monthly But not Direct as Daily, Weekly, Monthly |  |  | Siva Kumar |  |  | COMPLETED & APPROVED | [9 empty] | NOCHelpdesk | Applications/Tools | CLOSED |  |  |  | 2025-09-24 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\NOC38,39,40,41,42 |  | 1
2096 | NOC410 | NOC | NA |  | OSS | OSS | OSS | DC and Field IPMPLS | Traffic Utilisation covering All QoS Partameters Weekly |  | Critical | OPEN |  | NNMI | NPS |  | 09-09-2025: Need to discuss with OT |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCOSS | Applications/Tools | OPEN | OPEN | 09-09-2025: Need to discuss with OT |  |  | #N/A |  | 1
2097 | NOC411 | NOC | NA |  | OSS | OSS | OSS | DC and Field IPMPLS | Traffic Utilisation covering All QoS Partameters Monthly |  | Critical | OPEN |  | NNMI | NPS |  | 09-09-2025: Need to discuss with OT |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCOSS | Applications/Tools | OPEN | OPEN | 09-09-2025: Need to discuss with OT |  |  | #N/A |  | 1
2098 | NOC412 | NOC | NA |  | OSS | OSS | OSS | DC and Field IPMPLS | Traffic Utilisation covering All QoS Partameters (Selective from and to dates) |  | Critical | OPEN |  | NNMI | NPS |  | 09-09-2025: Need to discuss with OT |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCOSS | Applications/Tools | OPEN | OPEN | 09-09-2025: Need to discuss with OT |  |  | #N/A |  | 1
2099 | NOC413 | NOC | NA |  | OSS | OSS | OSS | BBNL Reports | Block and GP Status Daily |  | Critical | COMPLETED |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCOSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1
2100 | NOC414 | NOC | NA |  | OSS | OSS | OSS | BBNL Reports | Block and GP Status Weekly |  | Critical | NOT_FEASIBLE |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  | Open | Not Feasible | [9 empty] | NOCOSS | Applications/Tools | #N/A | Not Required to BBNL | 11-Oct-25: BBNL do not ask weekly hence it is not delivered |  |  | #N/A |  | 1
2101 | NOC415 | NOC | NA |  | OSS | OSS | OSS | BBNL Reports | Block and GP Status Monthly |  | Critical | COMPLETED |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCOSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1
2102 | NOC416 | NOC | NA |  | OSS | OSS | OSS | BBNL Reports | Block and GP Status (Selective from and to dates) |  | Critical | NOT_FEASIBLE |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  | Open | Not Feasible | [9 empty] | NOCOSS | Applications/Tools | #N/A | Not Required to BBNL | 11-Oct-25: BBNL do not ask Selective from and to dates hence it is not delivered |  |  | #N/A |  | 1
2103 | NOC417 | NOC | NA |  | OSS | OSS | OSS | BBNL Reports | Block and GP Availability Daily |  | Critical | COMPLETED |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCOSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1
2104 | NOC418 | NOC | NA |  | OSS | OSS | OSS | BBNL Reports | Block and GP Availability Weekly |  | Critical | NOT_FEASIBLE |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  | Open | Not Feasible | [9 empty] | NOCOSS | Applications/Tools | #N/A | Not Required to BBNL | 11-Oct-25: BBNL do not ask weekly hence it is not delivered |  |  | #N/A |  | 1
2105 | NOC419 | NOC | NA |  | OSS | OSS | OSS | BBNL Reports | Block and GP Availability Monthly |  | Critical | COMPLETED |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCOSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1
2106 | NOC42 | NOC | NA |  |  |  | Helpdesk | Help Desk | Help Desk managing and publishing KPI like Total I/O call, answereed call withing time frame etc. (Selective from and to dates) |  | NON-Critical |  |  | Helpdesk | Dial center | CLosed | 24-Sep-25: Option available to Choose Dates, daily, Weekly and Monthly But not Direct as Daily, Weekly, Monthly |  |  | Siva Kumar |  |  | COMPLETED & APPROVED | [9 empty] | NOCHelpdesk | Applications/Tools | CLOSED |  |  |  | 2025-09-24 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\NOC38,39,40,41,42 |  | 1
2107 | NOC420 | NOC | NA |  | OSS | OSS | OSS | BBNL Reports | Block and GP Availability (Selective from and to dates) |  | Critical | NOT_FEASIBLE |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  | Open | Not Feasible | [9 empty] | NOCOSS | Applications/Tools | #N/A | Not Required to BBNL | 11-Oct-25: BBNL do not ask Selective from and to dates hence it is not delivered |  |  | #N/A |  | 1
2108 | NOC421 | NOC | NA |  |  |  | New BSS | BBNL Reports | FTTH Connections and their utilisation(Including Household) Daily |  | Critical | OPEN |  | BSS | CRM |  |  |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCNew BSS | #N/A | OPEN | Not Relevant to OSS | 0 |  |  | #N/A |  | 1
2109 | NOC422 | NOC | NA |  |  |  | New BSS | BBNL Reports | FTTH Connections and their utilisation(Including Household) Weekly |  | Critical | OPEN |  | BSS | CRM |  |  |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCNew BSS | #N/A | OPEN | Not Relevant to OSS | 0 |  |  | #N/A |  | 1
2110 | NOC423 | NOC | NA |  |  |  | New BSS | BBNL Reports | FTTH Connections and their utilisation(Including Household) Monthly |  | Critical | OPEN |  | BSS | CRM |  |  |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCNew BSS | #N/A | OPEN | Not Relevant to OSS | 0 |  |  | #N/A |  | 1
2111 | NOC424 | NOC | NA |  |  |  | New BSS | BBNL Reports | FTTH Connections and their utilisation(Including Household) (Selective from and to dates) |  | Critical | OPEN |  | BSS | CRM |  |  |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCNew BSS | #N/A | OPEN | Not Relevant to OSS | 0 |  |  | #N/A |  | 1
2112 | NOC425 | NOC | NA |  |  |  | BSS | Regulatory Compliance | Customer connections Daily |  | Critical | OPEN |  | BSS | CRM |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
2113 | NOC426 | NOC | NA |  |  |  | BSS | Regulatory Compliance | Customer connections Weekly |  | Critical | OPEN |  | BSS | CRM |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
2114 | NOC427 | NOC | NA |  |  |  | BSS | Regulatory Compliance | Customer connections Monthly |  | Critical | OPEN |  | BSS | CRM |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
2115 | NOC428 | NOC | NA |  |  |  | BSS | Regulatory Compliance | Customer connections (Selective from and to dates) |  | Critical | OPEN |  | BSS | CRM |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
2116 | NOC429 | NOC | NA |  |  |  | BSS | Regulatory Compliance | Billing Daily |  | Critical | OPEN |  | BSS | Billing |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
2117 | NOC43 | NOC | NA |  | OSS | OSS | OSS | Service Assurance | Raised Proactive and reactive TT for all service deliverable sites and troubleshoot, escalation to field, follow up with field and resolve the issue Hourly |  | Critical | COMPLETED |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCOSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1
2118 | NOC430 | NOC | NA |  |  |  | BSS | Regulatory Compliance | Billing Weekly |  | Critical | OPEN |  | BSS | Billing |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
2119 | NOC431 | NOC | NA |  |  |  | BSS | Regulatory Compliance | Billing Monthly |  | Critical | OPEN |  | BSS | Billing |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
2120 | NOC432 | NOC | NA |  |  |  | BSS | Regulatory Compliance | Billing (Selective from and to dates) |  | Critical | OPEN |  | BSS | Billing |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
2121 | NOC433 | NOC | NA |  |  |  | BSS | Regulatory Compliance | Waiver Daily |  | Critical | OPEN |  | BSS | Billing |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
2122 | NOC434 | NOC | NA |  |  |  | BSS | Regulatory Compliance | Waiver Weekly |  | Critical | OPEN |  | BSS | Billing |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
2123 | NOC435 | NOC | NA |  |  |  | BSS | Regulatory Compliance | Waiver Monthly |  | Critical | OPEN |  | BSS | Billing |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
2124 | NOC436 | NOC | NA |  |  |  | BSS | Regulatory Compliance | Waiver (Selective from and to dates) |  | Critical | OPEN |  | BSS | Billing |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
2125 | NOC437 | NOC | NA |  |  |  | IPDR | Regulatory | Customer data logs(Session with MAC) Daily |  | Critical |  |  | IPDR | IPDR |  |  |  |  | Jayant Madavi |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCIPDR | Applications/Tools | OPEN |  |  |  |  | Artefacts to be uploaded |  | 1
2126 | NOC438 | NOC | NA |  |  |  | IPDR | Regulatory | Customer data logs(Session with MAC) Weekly |  | Critical |  |  | IPDR | IPDR |  |  |  |  | Jayant Madavi |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCIPDR | Applications/Tools | OPEN |  |  |  |  | Artefacts to be uploaded |  | 1
2127 | NOC439 | NOC | NA |  |  |  | IPDR | Regulatory | Customer data logs(Session with MAC) Monthly |  | Critical |  |  | IPDR | IPDR |  |  |  |  | Jayant Madavi |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCIPDR | Applications/Tools | OPEN |  |  |  |  | Artefacts to be uploaded |  | 1
2128 | NOC44 | NOC | NA |  | OSS | OSS | OSS | Service Assurance | Raised Proactive and reactive TT for all service deliverable sites and troubleshoot, escalation to field, follow up with field and resolve the issue Daily |  | Critical | COMPLETED |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCOSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1
2129 | NOC440 | NOC | NA |  |  |  | IPDR | Regulatory | Customer data logs(Session with MAC) (Selective from and to dates) |  | Critical |  |  | IPDR | IPDR |  |  |  |  | Jayant Madavi |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCIPDR | Applications/Tools | OPEN |  |  |  |  | Artefacts to be uploaded |  | 1
2130 | NOC441 | NOC | NA |  |  |  | BSS | Regulatory Compliance | Service Delivery TAT Dashboard and Reporting Daily |  | Critical | OPEN |  | BSS | CRM |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
2131 | NOC442 | NOC | NA |  |  |  | BSS | Regulatory Compliance | Service Delivery TAT Dashboard and Reporting Weekly |  | Critical | OPEN |  | BSS | CRM |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
2132 | NOC443 | NOC | NA |  |  |  | BSS | Regulatory Compliance | Service Delivery TAT Dashboard and Reporting Monthly |  | Critical | OPEN |  | BSS | CRM |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
2133 | NOC444 | NOC | NA |  |  |  | BSS | Regulatory Compliance | Service Delivery TAT Dashboard and Reporting (Selective from and to dates) |  | Critical | OPEN |  | BSS | CRM |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
2134 | NOC445 | NOC | NA |  | OSS | OSS | OSS | Service Monitoring | VLAN |  | Critical | OPEN |  | HPSM | Service Inventory |  | OPEN-DEPENDENT |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCOSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  | #N/A |  | 1
2135 | NOC446 | NOC | NA |  | OSS | OSS | OSS | Service Monitoring | ONT Downlink Port(Service segregation 4- UPS, 1-4 for Services) |  | Critical | NOT_FEASIBLE |  | HPSM | Service Inventory |  |  |  |  | Suresh Pawar |  | Open | Not Feasible | [9 empty] | NOCOSS | Applications/Tools | #N/A | NOT-FEASIBLE | 0 |  |  | #N/A |  | 1
2136 | NOC447 | NOC | NA |  | OSS | OSS | OSS | Service Monitoring | Service ID Mapping for UPS and Customer services |  | Critical | OPEN |  | HPSM | Service Inventory |  | OPEN-DEPENDENT |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCOSS | Applications/Tools | OPEN | OPEN-DEPENDENT | 0 |  |  | #N/A |  | 1
2137 | NOC448 | NOC | NA |  |  |  | NSO | Service Provisioning | Service Provision using NSO Daily |  | Critical |  |  | NSO | SCCM |  |  |  |  | Jayant Madavi |  | Open | Open | [9 empty] | NOCNSO | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
2138 | NOC449 | NOC | NA |  |  |  | NSO | Service Provisioning | Service template configuration |  | Critical |  |  | NSO | SCCM |  |  |  |  | Jayant Madavi |  | Open | Open | [9 empty] | NOCNSO | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
2139 | NOC45 | NOC | NA |  | OSS | OSS | OSS | Service Assurance | Raised Proactive and reactive TT for all service deliverable sites and troubleshoot, escalation to field, follow up with field and resolve the issue Weekly |  | Critical | COMPLETED |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCOSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1
2140 | NOC450 | NOC | NA |  |  |  | BSS | Service Provisioning | ILL(G2G) Daily |  | Critical | OPEN |  | BSS | CRM |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
2141 | NOC451 | NOC | NA |  |  |  | BSS | Service Provisioning | ILL(G2G) with QoS Daily |  | Critical | OPEN |  | BSS | CRM |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
2142 | NOC452 | NOC | NA |  |  |  | BSS | Service Provisioning | ILL(G2G) with QoS Weekly |  | Critical | COMPLETED |  | BSS | CRM |  | 09-09-2025: If IPMPLS Node interface for customer link then possible |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN | [6 empty] | 1
2143 | NOC453 | NOC | NA |  |  |  | BSS | Service Provisioning | ILL(G2G) with QoS Monthly |  | Critical | OPEN |  | BSS | CRM |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
2144 | NOC454 | NOC | NA |  |  |  | BSS | Service Provisioning | ILL(G2G) with QoS (Selective from and to dates) |  | Critical | OPEN |  | BSS | CRM |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
2145 | NOC455 | NOC | NA |  |  |  | BSS | Service Provisioning | GI BB(G2G) Direct Bandwidth Daily |  | Critical | OPEN |  | BSS | CRM |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
2146 | NOC456 | NOC | NA |  |  |  | BSS | Service Provisioning | GI BB(G2G) Direct Bandwidth Weekly |  | Critical | COMPLETED |  | BSS | CRM |  | 09-09-2025: If IPMPLS Node interface for customer link then possible |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN | [6 empty] | 1
2147 | NOC457 | NOC | NA |  |  |  | BSS | Service Provisioning | GI BB(G2G) Direct Bandwidth Monthly |  | Critical | OPEN |  | BSS | CRM |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
2148 | NOC458 | NOC | NA |  |  |  | BSS | Service Provisioning | GI BB(G2G) Direct Bandwidth (Selective from and to dates) |  | Critical | OPEN |  | BSS | CRM |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
2149 | NOC459 | NOC | NA |  |  |  | BSS | Service Provisioning | GI BB(G2G) Bandidth with QoS filtered Daily |  | Critical | OPEN |  | BSS | CRM |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
2150 | NOC46 | NOC | NA |  | OSS | OSS | OSS | Service Assurance | Raised Proactive and reactive TT for all service deliverable sites and troubleshoot, escalation to field, follow up with field and resolve the issue Monthly |  | Critical | COMPLETED |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCOSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1
2151 | NOC460 | NOC | NA |  |  |  | BSS | Service Provisioning | GI BB(G2G) Bandidth with QoS filtered Weekly |  | Critical | COMPLETED |  | BSS | CRM |  | 09-09-2025: If IPMPLS Node interface for customer link then possible |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN | [6 empty] | 1
2152 | NOC461 | NOC | NA |  |  |  | BSS | Service Provisioning | GI BB(G2G) Bandidth with QoS filtered Monthly |  | Critical | OPEN |  | BSS | CRM |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
2153 | NOC462 | NOC | NA |  |  |  | BSS | Service Provisioning | GI BB(G2G) Bandidth with QoS filtered (Selective from and to dates) |  | Critical | OPEN |  | BSS | CRM |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
2154 | NOC463 | NOC | NA |  |  |  | BSS | Service Provisioning | Dark Fiber Daily |  | Critical | OPEN |  | BSS | CRM |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
2155 | NOC464 | NOC | NA |  |  |  | BSS | Service Provisioning | Dark Fiber Weekly |  | Critical | OPEN |  | BSS | CRM |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
2156 | NOC465 | NOC | NA |  |  |  | BSS | Service Provisioning | Dark Fiber Monthly |  | Critical | OPEN |  | BSS | CRM |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
2157 | NOC466 | NOC | NA |  |  |  | BSS | Service Provisioning | Dark Fiber (Selective from and to dates) |  | Critical | OPEN |  | BSS | CRM |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
2158 | NOC467 | NOC | NA |  |  |  | BSS | Service Provisioning | Household(G2C) Daily |  | Critical | OPEN |  | BSS | CRM |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
2159 | NOC468 | NOC | NA |  |  |  | BSS | Service Provisioning | Household(G2C) Weekly |  | Critical | OPEN |  | BSS | CRM |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
2160 | NOC469 | NOC | NA |  |  |  | BSS | Service Provisioning | Household(G2C) Monthly |  | Critical | OPEN |  | BSS | CRM |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
2161 | NOC47 | NOC | NA |  | OSS | OSS | OSS | Service Assurance | Raised Proactive and reactive TT for all service deliverable sites and troubleshoot, escalation to field, follow up with field and resolve the issue (Selective from and to dates) |  | Critical | COMPLETED |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCOSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1
2162 | NOC470 | NOC | NA |  |  |  | BSS | Service Provisioning | Household(G2C) (Selective from and to dates) |  | Critical | OPEN |  | BSS | CRM |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
2163 | NOC471 | NOC | NA |  |  |  | BSS | Service Provisioning | VPN(B2B) Daily |  | Critical | OPEN |  | BSS | CRM |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
2164 | NOC472 | NOC | NA |  |  |  | BSS | Service Provisioning | VPN(B2B) Weekly |  | Critical | OPEN |  | BSS | CRM |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
2165 | NOC473 | NOC | NA |  |  |  | BSS | Service Provisioning | VPN(B2B) Monthly |  | Critical | OPEN |  | BSS | CRM |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
2166 | NOC474 | NOC | NA |  |  |  | BSS | Service Provisioning | VPN(B2B) (Selective from and to dates) |  | Critical | OPEN |  | BSS | CRM |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
2167 | NOC475 | NOC | NA |  |  |  | BSS | Service Provisioning | VPN(B2B)with filtered QoS Daily |  | Critical | OPEN |  | BSS | CRM |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
2168 | NOC476 | NOC | NA |  |  |  | BSS | Service Provisioning | VPN(B2B)with filtered QoS Weekly |  | Critical | OPEN |  | BSS | CRM |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
2169 | NOC477 | NOC | NA |  |  |  | BSS | Service Provisioning | VPN(B2B)with filtered QoS Monthly |  | Critical | OPEN |  | BSS | CRM |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
2170 | NOC478 | NOC | NA |  |  |  | BSS | Service Provisioning | VPN(B2B)with filtered QoS (Selective from and to dates) |  | Critical | OPEN |  | BSS | CRM |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
2171 | NOC479 | NOC | NA |  |  |  | BSS | Service Provisioning | Enterprise(B2B) Daily |  | Critical | OPEN |  | BSS | CRM |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
2172 | NOC48 | NOC | NA |  |  |  | GPON | OSS | Summary Status of complete 424 Mandal OLTs ( Blocks ) of PKG-ABC Daily |  | Critical | COMPLETED |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCGPON | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1
2173 | NOC480 | NOC | NA |  |  |  | BSS | Service Provisioning | Enterprise(B2B) Weekly |  | Critical | OPEN |  | BSS | CRM |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
2174 | NOC481 | NOC | NA |  |  |  | BSS | Service Provisioning | Enterprise(B2B) Monthly |  | Critical | OPEN |  | BSS | CRM |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
2175 | NOC482 | NOC | NA |  |  |  | BSS | Service Provisioning | Enterprise(B2B) (Selective from and to dates) |  | Critical | OPEN |  | BSS | CRM |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
2176 | NOC483 | NOC | NA |  |  |  | BSS | Service Provisioning | Enterprise(B2B) with filtered QoS Daily |  | Critical | OPEN |  | BSS | CRM |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
2177 | NOC484 | NOC | NA |  |  |  | BSS | Service Provisioning | Enterprise(B2B) with filtered QoS Weekly |  | Critical | OPEN |  | BSS | CRM |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
2178 | NOC485 | NOC | NA |  |  |  | BSS | Service Provisioning | Enterprise(B2B) with filtered QoS Monthly |  | Critical | OPEN |  | BSS | CRM |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
2179 | NOC486 | NOC | NA |  |  |  | BSS | Service Provisioning | Enterprise(B2B) with filtered QoS (Selective from and to dates) |  | Critical | OPEN |  | BSS | CRM |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
2180 | NOC487 | NOC | NA |  |  |  | BSS | Service Provisioning | Partner(B2B2C) Daily |  | Critical | COMPLETED |  | BSS | CRM |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN | [6 empty] | 1
2181 | NOC488 | NOC | NA |  |  |  | BSS | Service Provisioning | Partner(B2B2C) Weekly |  | Critical | COMPLETED |  | BSS | CRM |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN | [6 empty] | 1
2182 | NOC489 | NOC | NA |  |  |  | BSS | Service Provisioning | Partner(B2B2C) Monthly |  | Critical | COMPLETED |  | BSS | CRM |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN | [6 empty] | 1
2183 | NOC49 | NOC | NA |  |  |  | GPON | OSS | Summary Status of complete 424 Mandal OLTs ( Blocks ) of PKG-ABC Weekly |  | Critical | NOT_FEASIBLE |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  | Open | Not Feasible | [9 empty] | NOCGPON | Applications/Tools | #N/A | NOT-FEASIBLE | Live data -bothUOC and POWErbi |  |  | #N/A |  | 1
2184 | NOC490 | NOC | NA |  |  |  | BSS | Service Provisioning | Partner(B2B2C) (Selective from and to dates) |  | Critical | COMPLETED |  | BSS | CRM |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN | [6 empty] | 1
2185 | NOC491 | NOC | NA |  |  |  | BSS | Service Provisioning | Partner(B2B2C) with Filtered QoS Daily |  | Critical | OPEN |  | BSS | CRM |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
2186 | NOC492 | NOC | NA |  |  |  | BSS | Service Provisioning | Partner(B2B2C) with Filtered QoS Weekly |  | Critical | OPEN |  | BSS | CRM |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
2187 | NOC493 | NOC | NA |  |  |  | BSS | Service Provisioning | Partner(B2B2C) with Filtered QoS Monthly |  | Critical | OPEN |  | BSS | CRM |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
2188 | NOC494 | NOC | NA |  |  |  | BSS | Service Provisioning | Partner(B2B2C) with Filtered QoS (Selective from and to dates) |  | Critical | OPEN |  | BSS | CRM |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
2189 | NOC495 | NOC | NA |  |  |  | BSS | Service Provisioning | T-cell (P2MP) Daily |  | Critical | OPEN |  | BSS | CRM |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
2190 | NOC496 | NOC | NA |  |  |  | BSS | Service Provisioning | T-cell (P2MP) Weekly |  | Critical | OPEN |  | BSS | CRM |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
2191 | NOC497 | NOC | NA |  |  |  | BSS | Service Provisioning | T-cell (P2MP) Monthly |  | Critical | OPEN |  | BSS | CRM |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
2192 | NOC498 | NOC | NA |  |  |  | BSS | Service Provisioning | T-cell (P2MP) (Selective from and to dates) |  | Critical | OPEN |  | BSS | CRM |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
2193 | NOC499 | NOC | NA |  |  |  | BSS | Service Provisioning | T-cell P2MP with Filtered QoS Daily |  | Critical | OPEN |  | BSS | CRM |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
2194 | NOC5 | NOC | NA |  | OSS | OSS | OSS | DC | DC Applications uptime & SLA Daily |  | Critical |  |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCOSS | Applications/Tools | OPEN | OPEN | 0 |  |  | #N/A |  | 1
2195 | NOC50 | NOC | NA |  |  |  | GPON | OSS | Summary Status of complete 424 Mandal OLTs ( Blocks ) of PKG-ABC Monthly |  | Critical | COMPLETED |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCGPON | Applications/Tools | OPEN | COMPLETED | only Live data |  |  |  |  | 1
2196 | NOC500 | NOC | NA |  |  |  | BSS | Service Provisioning | T-cell P2MP with Filtered QoS Weekly |  | Critical | OPEN |  | BSS | CRM |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
2197 | NOC501 | NOC | NA |  |  |  | BSS | Service Provisioning | T-cell P2MP with Filtered QoS Monthly |  | Critical | OPEN |  | BSS | CRM |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
2198 | NOC502 | NOC | NA |  |  |  | BSS | Service Provisioning | T-cell P2MP with Filtered QoS (Selective from and to dates) |  | Critical | OPEN |  | BSS | CRM |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
2199 | NOC503 | NOC | NA |  |  |  | BSS | Service Provisioning | T-cell (P2P) Daily |  | Critical | OPEN |  | BSS | CRM |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
2200 | NOC504 | NOC | NA |  |  |  | BSS | Service Provisioning | T-cell (P2P) Weekly |  | Critical | OPEN |  | BSS | CRM |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
2201 | NOC505 | NOC | NA |  |  |  | BSS | Service Provisioning | T-cell (P2P) Monthly |  | Critical | OPEN |  | BSS | CRM |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
2202 | NOC506 | NOC | NA |  |  |  | BSS | Service Provisioning | T-cell (P2P) (Selective from and to dates) |  | Critical | OPEN |  | BSS | CRM |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
2203 | NOC507 | NOC | NA |  |  |  | BSS | Service Provisioning | T-cell P2P with Filtered QoS Daily |  | Critical | OPEN |  | BSS | CRM |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
2204 | NOC508 | NOC | NA |  |  |  | BSS | Service Provisioning | T-cell P2P with Filtered QoS Weekly |  | Critical | OPEN |  | BSS | CRM |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
2205 | NOC509 | NOC | NA |  |  |  | BSS | Service Provisioning | T-cell P2P with Filtered QoS Monthly |  | Critical | OPEN |  | BSS | CRM |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
2206 | NOC51 | NOC | NA |  |  |  | GPON | OSS | Summary Status of complete 424 Mandal OLTs ( Blocks ) of PKG-ABC (Selective from and to dates) |  | Critical | COMPLETED |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCGPON | Applications/Tools | OPEN | COMPLETED | Live data |  |  |  |  | 1
2207 | NOC510 | NOC | NA |  |  |  | BSS | Service Provisioning | T-cell P2P with Filtered QoS (Selective from and to dates) |  | Critical | OPEN |  | BSS | CRM |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
2208 | NOC511 | NOC | NA |  | OSS | OSS | OSS and NSO | Service Provisioning | Bandwidth Feasibility for New Provisioning, Exising configured bandwidth to be made available at OSS Daily |  | Critical | OPEN |  | OSS and NSO | Service Inventory, SCCM |  | 14-09-2025: We can get this report from BSS by downloading services provisioned for the perticular week |  |  | Jayant Madavi |  | Open | WIP | [9 empty] | NOCOSS and NSO | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
2209 | NOC512 | NOC | NA |  | OSS | OSS | OSS and NSO | Service Provisioning | Bandwidth Feasibility for New Provisioning, Exising configured bandwidth to be made available at OSS Weekly |  | Critical | OPEN |  | OSS and NSO | Service Inventory, SCCM |  | 14-09-2025: We can get this report from BSS by downloading services provisioned for the perticular week |  |  | Jayant Madavi |  | Open | WIP | [9 empty] | NOCOSS and NSO | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
2210 | NOC513 | NOC | NA |  | OSS | OSS | OSS and NSO | Service Provisioning | Bandwidth Feasibility for New Provisioning, Exising configured bandwidth to be made available at OSS Monthly |  | Critical | OPEN |  | OSS and NSO | Service Inventory, SCCM |  | 14-09-2025: We can get this report from BSS by downloading services provisioned for the perticular month |  |  | Jayant Madavi |  | Open | WIP | [9 empty] | NOCOSS and NSO | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
2211 | NOC514 | NOC | NA |  | OSS | OSS | OSS and NSO | Service Provisioning | Bandwidth Feasibility for New Provisioning, Exising configured bandwidth to be made available at OSS (Selective from and to dates) |  | Critical | OPEN |  | OSS and NSO | Service Inventory, SCCM |  | 14-09-2025: We can get this report from BSS by downloading services provisioned for the selected period |  |  | Jayant Madavi |  | Open | WIP | [9 empty] | NOCOSS and NSO | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
2212 | NOC515 | NOC | NA |  | OSS | OSS | OSS | Service Provisioning | Capacity augmentationn based on Feasible/NON- Feasible status count and required bandwidth Daily |  | Critical | COMPLETED |  | OSS | Service Inventory, UTM |  | 09-09-2025: Desired output will be shown through BSS but actual data is fetching from the OSS (UTM +GIS). |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCOSS | Applications/Tools | OPEN | COMPLETED | 09-09-2025: Desired output will be shown through BSS but actual data is fetching from the OSS (UTM +GIS). |  |  |  |  | 1
2213 | NOC516 | NOC | NA |  | OSS | OSS | OSS | Service Provisioning | Capacity augmentationn based on Feasible/NON- Feasible status count and required bandwidth Weekly |  | Critical | NOT_FEASIBLE |  | OSS | Service Inventory, UTM |  |  |  |  | Suresh Pawar |  | Open | Not Feasible | [9 empty] | NOCOSS | Applications/Tools | #N/A | NOT-FEASIBLE | 0 |  |  | #N/A |  | 1
2214 | NOC517 | NOC | NA |  | OSS | OSS | OSS | Service Provisioning | Capacity augmentationn based on Feasible/NON- Feasible status count and required bandwidth Monthly |  | Critical | COMPLETED |  | OSS | Service Inventory, UTM |  | 09-09-2025: Desired output will be shown through BSS but actual data is fetching from the OSS (UTM +GIS). |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCOSS | Applications/Tools | OPEN | COMPLETED | 09-09-2025: Desired output will be shown through BSS but actual data is fetching from the OSS (UTM +GIS). |  |  |  |  | 1
2215 | NOC518 | NOC | NA |  | OSS | OSS | OSS | Service Provisioning | Capacity augmentationn based on Feasible/NON- Feasible status count and required bandwidth (Selective from and to dates) |  | Critical | COMPLETED |  | OSS | Service Inventory, UTM |  | 09-09-2025: Desired output will be shown through BSS but actual data is fetching from the OSS (UTM +GIS). |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCOSS | Applications/Tools | OPEN | COMPLETED | 09-09-2025: Desired output will be shown through BSS but actual data is fetching from the OSS (UTM +GIS). |  |  |  |  | 1
2216 | NOC519 | NOC | NA |  |  |  | WFM | WFM | User level view for Number of tasks assigned/resolved/closed Daily |  | Critical |  |  | WFM | Corrective |  | Development Completed & Reports are available |  |  | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCWFM | Applications/Tools | OPEN | [6 empty] | 1
2217 | NOC52 | NOC | NA |  |  |  | GPON | OSS | Summary of Lit-up GPs Status_8894 as on 14-05-2025_4PM(Revised) Daily |  | Critical | COMPLETED |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCGPON | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1
2218 | NOC520 | NOC | NA |  |  |  | WFM | WFM | User level view for Number of tasks assigned/resolved/closed Weekly |  | Critical |  |  | WFM | Incident Management |  | Development Completed & Reports are available |  |  | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCWFM | Applications/Tools | OPEN | [6 empty] | 1
2219 | NOC521 | NOC | NA |  |  |  | WFM | WFM | User level view for Number of tasks assigned/resolved/closed Monthly |  | Critical |  |  | WFM | Incident Management |  | Development Completed & Reports are available |  |  | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCWFM | Applications/Tools | OPEN | [6 empty] | 1
2220 | NOC522 | NOC | NA |  |  |  | WFM | WFM | User level view for Number of tasks assigned/resolved/closed (Selective from and to dates) |  | Critical |  |  | WFM | Smart track |  | Development Completed & Reports are available |  |  | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCWFM | Applications/Tools | OPEN | [6 empty] | 1
2221 | NOC523 | NOC | NA |  |  |  | WFM | WFM | Management Dashboard Patroller Daily |  | Critical |  |  | WFM | Smart track |  | The development is complete and can be demonstrated through three methods: reports, dashboards, and single-click interaction on the map |  |  | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCWFM | Applications/Tools | OPEN | [6 empty] | 1
2222 | NOC524 | NOC | NA |  |  |  | WFM | WFM | Management Dashboard Patroller Weekly |  | Critical |  |  | WFM | Smart track |  | The development is complete and can be demonstrated through three methods: reports, dashboards, and single-click interaction on the map |  |  | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCWFM | Applications/Tools | OPEN | [6 empty] | 1
2223 | NOC525 | NOC | NA |  |  |  | WFM | WFM | Management Dashboard Patroller Monthly |  | Critical |  |  | WFM | Smart track |  | The development is complete and can be demonstrated through three methods: reports, dashboards, and single-click interaction on the map |  |  | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCWFM | Applications/Tools | OPEN | [6 empty] | 1
2224 | NOC526 | NOC | NA |  |  |  | WFM | WFM | Management Dashboard Patroller (Selective from and to dates) |  | Critical |  |  | WFM | Smart track |  | The development is complete and can be demonstrated through three methods: reports, dashboards, and single-click interaction on the map |  |  | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCWFM | Applications/Tools | OPEN | [6 empty] | 1
2225 | NOC527 | NOC | NA |  |  |  | WFM | WFM | Management Dashboard FRT Daily |  | Critical |  |  | WFM | Smart track |  | The development is complete and can be demonstrated through three methods: reports, dashboards, and single-click interaction on the map |  |  | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCWFM | Applications/Tools | OPEN | [6 empty] | 1
2226 | NOC528 | NOC | NA |  |  |  | WFM | WFM | Management Dashboard FRT Weekly |  | Critical |  |  | WFM | Smart track |  | The development is complete and can be demonstrated through three methods: reports, dashboards, and single-click interaction on the map |  |  | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCWFM | Applications/Tools | OPEN | [6 empty] | 1
2227 | NOC529 | NOC | NA |  |  |  | WFM | WFM | Management Dashboard FRT Monthly |  | Critical |  |  | WFM | Smart track |  | The development is complete and can be demonstrated through three methods: reports, dashboards, and single-click interaction on the map |  |  | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCWFM | Applications/Tools | OPEN | [6 empty] | 1
2228 | NOC53 | NOC | NA |  |  |  | GPON | OSS | Summary of Lit-up GPs Status_8894 as on 14-05-2025_4PM(Revised) Weekly |  | Critical | NOT_FEASIBLE |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  | Open | Not Feasible | [9 empty] | NOCGPON | Applications/Tools | #N/A | NOT-FEASIBLE | 0 |  |  | #N/A |  | 1
2229 | NOC530 | NOC | NA |  |  |  | WFM | WFM | Management Dashboard FRT (Selective from and to dates) |  | Critical |  |  | WFM | Smart track |  | The development is complete and can be demonstrated through three methods: reports, dashboards, and single-click interaction on the map |  |  | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCWFM | Applications/Tools | OPEN | [6 empty] | 1
2230 | NOC531 | NOC | NA |  |  |  | WFM | WFM | Management Dashboard Engineers Daily |  | Critical |  |  | WFM | Smart track |  | The development is complete and can be demonstrated through three methods: reports, dashboards, and single-click interaction on the map |  |  | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCWFM | Applications/Tools | OPEN | [6 empty] | 1
2231 | NOC532 | NOC | NA |  |  |  | WFM | WFM | Management Dashboard Engineers Weekly |  | Critical |  |  | WFM | Smart track |  | The development is complete and can be demonstrated through three methods: reports, dashboards, and single-click interaction on the map |  |  | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCWFM | Applications/Tools | OPEN | [6 empty] | 1
2232 | NOC533 | NOC | NA |  |  |  | WFM | WFM | Management Dashboard Engineers Monthly |  | Critical |  |  | WFM | Smart track |  | The development is complete and can be demonstrated through three methods: reports, dashboards, and single-click interaction on the map |  |  | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCWFM | Applications/Tools | OPEN | [6 empty] | 1
2233 | NOC534 | NOC | NA |  |  |  | WFM | WFM | Management Dashboard Engineers (Selective from and to dates) |  | Critical |  |  | WFM | Smart track |  | The development is complete and can be demonstrated through three methods: reports, dashboards, and single-click interaction on the map |  |  | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCWFM | Applications/Tools | OPEN | [6 empty] | 1
2234 | NOC535 | NOC | NA |  |  |  | Helpdesk | BSS | Integration to be Aligned with Approved IVR flow(All Customers) Daily |  | NON-Critical |  |  | BSS | CRM | WIP | IVR Flows Submitted for Approval |  |  | Siva Kumar |  | Open | WIP | [9 empty] | NOCHelpdesk | Applications/Tools | OPEN | [6 empty] | 1
2235 | NOC536 | NOC | NA |  |  |  | Helpdesk | BSS | Integration to be Aligned with Approved IVR flow(All Customers) Weekly |  | NON-Critical |  |  | BSS | CRM | WIP | IVR Flows Submitted for Approval |  |  | Siva Kumar |  | Open | WIP | [9 empty] | NOCHelpdesk | Applications/Tools | OPEN | [6 empty] | 1
2236 | NOC537 | NOC | NA |  |  |  | Helpdesk | BSS | Integration to be Aligned with Approved IVR flow(All Customers) Monthly |  | NON-Critical |  |  | BSS | CRM | WIP | IVR Flows Submitted for Approval |  |  | Siva Kumar |  | Open | WIP | [9 empty] | NOCHelpdesk | Applications/Tools | OPEN | [6 empty] | 1
2237 | NOC538 | NOC | NA |  |  |  | Helpdesk | BSS | Integration to be Aligned with Approved IVR flow(All Customers) (Selective from and to dates) |  | NON-Critical |  |  | BSS | CRM | WIP | IVR Flows Submitted for Approval |  |  | Siva Kumar |  | Open | WIP | [9 empty] | NOCHelpdesk | Applications/Tools | OPEN | [6 empty] | 1
2238 | NOC539 | NOC | NA |  |  |  | Helpdesk | BSS | Integration to be Aligned with Approved IVR flow(All Enterprise) Daily |  | NON-Critical |  |  | BSS | CRM | WIP | IVR Flows Submitted for Approval |  |  | Siva Kumar |  | Open | WIP | [9 empty] | NOCHelpdesk | Applications/Tools | OPEN | [6 empty] | 1
2239 | NOC54 | NOC | NA |  |  |  | GPON | OSS | Summary of Lit-up GPs Status_8894 as on 14-05-2025_4PM(Revised) Monthly |  | Critical | NOT_FEASIBLE |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  | Open | Not Feasible | [9 empty] | NOCGPON | Applications/Tools | #N/A | NOT-FEASIBLE | 0 |  |  | #N/A |  | 1
2240 | NOC540 | NOC | NA |  |  |  | Helpdesk | BSS | Integration to be Aligned with Approved IVR flow(All Enterprise) Weekly |  | NON-Critical |  |  | BSS | CRM | WIP | IVR Flows Submitted for Approval |  |  | Siva Kumar |  | Open | WIP | [9 empty] | NOCHelpdesk | Applications/Tools | OPEN | [6 empty] | 1
2241 | NOC541 | NOC | NA |  |  |  | Helpdesk | BSS | Integration to be Aligned with Approved IVR flow(All Enterprise) Monthly |  | NON-Critical |  |  | BSS | CRM | WIP | IVR Flows Submitted for Approval |  |  | Siva Kumar |  | Open | WIP | [9 empty] | NOCHelpdesk | Applications/Tools | OPEN | [6 empty] | 1
2242 | NOC542 | NOC | NA |  |  |  | Helpdesk | BSS | Integration to be Aligned with Approved IVR flow(All Enterprise) (Selective from and to dates) |  | NON-Critical |  |  | BSS | CRM | WIP | IVR Flows Submitted for Approval |  |  | Siva Kumar |  | Open | WIP | [9 empty] | NOCHelpdesk | Applications/Tools | OPEN | [6 empty] | 1
2243 | NOC543 | NOC | NA |  |  |  | Helpdesk | BSS | Integration to be Aligned with Approved IVR flow(All Partners) Daily |  | NON-Critical |  |  | BSS | CRM | WIP | IVR Flows Submitted for Approval |  |  | Siva Kumar |  | Open | WIP | [9 empty] | NOCHelpdesk | Applications/Tools | OPEN | [6 empty] | 1
2244 | NOC544 | NOC | NA |  |  |  | Helpdesk | BSS | Integration to be Aligned with Approved IVR flow(All Partners) Weekly |  | NON-Critical |  |  | BSS | CRM | WIP | IVR Flows Submitted for Approval |  |  | Siva Kumar |  | Open | WIP | [9 empty] | NOCHelpdesk | Applications/Tools | OPEN | [6 empty] | 1
2245 | NOC545 | NOC | NA |  |  |  | Helpdesk | BSS | Integration to be Aligned with Approved IVR flow(All Partners) Monthly |  | NON-Critical |  |  | BSS | CRM | WIP | IVR Flows Submitted for Approval |  |  | Siva Kumar |  | Open | WIP | [9 empty] | NOCHelpdesk | Applications/Tools | OPEN | [6 empty] | 1
2246 | NOC546 | NOC | NA |  |  |  | Helpdesk | BSS | Integration to be Aligned with Approved IVR flow(All Partners) (Selective from and to dates) |  | NON-Critical |  |  | BSS | CRM | WIP | IVR Flows Submitted for Approval |  |  | Siva Kumar |  | Open | WIP | [9 empty] | NOCHelpdesk | Applications/Tools | OPEN | [6 empty] | 1
2247 | NOC547 | NOC | NA |  |  |  | Helpdesk | OSS | Integration to be Aligned with Approved IVR flow(MSI) Daily |  | NON-Critical |  |  | HPSM | Incident Management | WIP | IVR Flows Submitted for Approval |  |  | Siva Kumar |  | Open | WIP | [9 empty] | NOCHelpdesk | Applications/Tools | OPEN | [6 empty] | 1
2248 | NOC548 | NOC | NA |  |  |  | Helpdesk | OSS | Integration to be Aligned with Approved IVR flow(MSI) Weekly |  | NON-Critical |  |  | HPSM | Incident Management | WIP | IVR Flows Submitted for Approval |  |  | Siva Kumar |  | Open | WIP | [9 empty] | NOCHelpdesk | Applications/Tools | OPEN | [6 empty] | 1
2249 | NOC549 | NOC | NA |  |  |  | Helpdesk | OSS | Integration to be Aligned with Approved IVR flow(MSI) Monthly |  | NON-Critical |  |  | HPSM | Incident Management | WIP | IVR Flows Submitted for Approval |  |  | Siva Kumar |  | Open | WIP | [9 empty] | NOCHelpdesk | Applications/Tools | OPEN | [6 empty] | 1
2250 | NOC55 | NOC | NA |  |  |  | GPON | OSS | Summary of Lit-up GPs Status_8894 as on 14-05-2025_4PM(Revised) (Selective from and to dates) |  | Critical | NOT_FEASIBLE |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  | Open | Not Feasible | [9 empty] | NOCGPON | Applications/Tools | #N/A | NOT-FEASIBLE | 0 |  |  | #N/A |  | 1
2251 | NOC550 | NOC | NA |  |  |  | Helpdesk | OSS | Integration to be Aligned with Approved IVR flow(MSI) (Selective from and to dates) |  | NON-Critical |  |  | HPSM | Incident Management | WIP | IVR Flows Submitted for Approval |  |  | Siva Kumar |  | Open | WIP | [9 empty] | NOCHelpdesk | Applications/Tools | OPEN | [6 empty] | 1
2252 | NOC551 | NOC | NA |  |  |  | Helpdesk | OSS | Integration to be Aligned with Approved IVR flow(NOC) Daily |  | NON-Critical |  |  | HPSM | Incident Management | WIP | IVR Flows Submitted for Approval |  |  | Siva Kumar |  | Open | WIP | [9 empty] | NOCHelpdesk | Applications/Tools | OPEN | [6 empty] | 1
2253 | NOC552 | NOC | NA |  |  |  | Helpdesk | OSS | Integration to be Aligned with Approved IVR flow(NOC) Weekly |  | NON-Critical |  |  | HPSM | Incident Management | WIP | IVR Flows Submitted for Approval |  |  | Siva Kumar |  | Open | WIP | [9 empty] | NOCHelpdesk | Applications/Tools | OPEN | [6 empty] | 1
2254 | NOC553 | NOC | NA |  |  |  | Helpdesk | OSS | Integration to be Aligned with Approved IVR flow(NOC) Monthly |  | NON-Critical |  |  | HPSM | Incident Management | WIP | IVR Flows Submitted for Approval |  |  | Siva Kumar |  | Open | WIP | [9 empty] | NOCHelpdesk | Applications/Tools | OPEN | [6 empty] | 1
2255 | NOC554 | NOC | NA |  |  |  | Helpdesk | OSS | Integration to be Aligned with Approved IVR flow(NOC) (Selective from and to dates) |  | NON-Critical |  |  | HPSM | Incident Management | WIP | IVR Flows Submitted for Approval |  |  | Siva Kumar |  | Open | WIP | [9 empty] | NOCHelpdesk | Applications/Tools | OPEN | [6 empty] | 1
2256 | NOC555 | NOC | NA |  |  |  | NSO | Service Provisioning | VLAN Planning |  | Critical | OPEN |  | NSO | SCCM/Playbook |  |  |  |  | Jayant Madavi |  | Open | Open | [9 empty] | NOCNSO | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
2257 | NOC556 | NOC | NA |  |  |  | NSO | Service Provisioning | IPV4 and IPV6 Planning |  | Critical | OPEN |  | NSO | SCCM/Playbook |  |  |  |  | Jayant Madavi |  | Open | Open | [9 empty] | NOCNSO | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
2258 | NOC557 | NOC | NA |  |  |  | BSS | Service Provisioning | Migration of Existing customers provision via BSS-NSO |  | Critical | OPEN |  | BSS, NSO | CRM, SCCM |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
2259 | NOC558 | NOC | NA |  | OSS | OSS | All Domain | OSS | TT should not be generated for planned event window and Affected CI |  | Critical | OPEN |  | HPSM | Change Management |  |  |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCAll Domain | Applications/Tools | OPEN | OPEN | 0 |  |  | #N/A |  | 1
2260 | NOC559 | NOC | NA |  | OSS | OSS | All Domain | OSS | Planned event to be rejected/Postponed incase another side Ring is open |  | Critical | COMPLETED |  | HPSM | Change Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCAll Domain | Applications/Tools | OPEN | COMPLETED | consider SS from mail |  |  |  |  | 1
2261 | NOC56 | NOC | NA |  |  |  | GPON | OSS | T-NOC Report :: Summary of O&M Cluster OLTs status Daily |  | Critical | COMPLETED |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCGPON | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1
2262 | NOC560 | NOC | NA |  |  |  | WFM | WFM | Field Remarks like ETR, RFO updation pending against Open Task |  | Critical |  |  | WFM | Smart track |  |  |  |  | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCWFM | Applications/Tools | OPEN | [6 empty] | 1
2263 | NOC561 | NOC | NA |  |  |  | WFM | WFM | Field team working without events and as a part of corrective actions at Passive |  | Critical |  |  | WFM | Smart track |  | 11-7-2025:- SM & WFM Intigration is WIP |  |  | Kaushalendra Kumar |  | Open | WIP | [9 empty] | NOCWFM | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
2264 | NOC562 | NOC | NA |  | OSS | OSS&WFM | OSS | OSS | Auto Escalation Matrix |  | Critical |  |  | HPSM | Incident Management |  | 09-09-2025: its configurable item and can be modified on demand |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCOSS | Applications/Tools | OPEN | COMPLETED | 09-09-2025: its configurable item and can be modified on demand |  |  | Artefacts to be uploaded |  | 1
2265 | NOC563 | NOC | NA |  | OSS | OSS | All Domain | OSS | Configutable paramters for SLA |  | Critical | COMPLETED |  | NNMI | NPS |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCAll Domain | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1
2266 | NOC564 | NOC | NA |  |  |  | GPON | GPON | Requested Tejas to enable the TR-069 for T-Fiber deployed elements |  | Critical |  |  | Tejas OEM | ONT |  | Duplicate point of 472 - 399 | Duplicate |  | Sayyad Pasha |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | NOCGPON | Applications/Tools | OPEN |  |  | Duplicate |  |  |  | 1
2267 | NOC565 | NOC | NA |  |  |  | GPON | GPON | CIR/PIR in OLT/EMS |  | Critical |  |  | Tejas OEM | EMS/OLT |  | Duplicate point of 472 - 407 | Duplicate |  | Sayyad Pasha |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | NOCGPON | Applications/Tools | OPEN |  |  | Duplicate |  |  |  | 1
2268 | NOC566 | NOC | NA |  |  |  | GPON | GPON | Unable to modify the Service Name |  | Critical |  |  | Tejas OEM | EMS |  |  |  |  | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-07-03 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\409 | [6 empty] | NOCGPON | Applications/Tools | CLOSED |  |  |  | 2025-07-03 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\409 |  | 1
2269 | NOC567 | NOC | NA |  |  |  | GPON | GPON | Live PM monitoring per UNI in EMS service Window |  | Critical |  |  | Tejas OEM | EMS |  |  |  |  | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-07-10 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\416 | [6 empty] | NOCGPON | Applications/Tools | CLOSED |  |  |  | 2025-07-10 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\416 |  | 1
2270 | NOC568 | NOC | NA |  |  |  | GPON | GPON | Unable to Enable PM from EMS |  | Critical |  |  | Tejas OEM | EMS |  |  |  |  | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-07-07 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\414 | [6 empty] | NOCGPON | Applications/Tools | CLOSED |  |  |  | 2025-07-07 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\414 |  | 1
2271 | NOC569 | NOC | NA |  |  |  | GPON | GPON | While creating service profile, maximum bandwidth is not taking 1024000 only considering 1000000 |  | Critical |  |  | Tejas OEM | EMS |  |  |  |  | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-07-31 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\417 | [6 empty] | NOCGPON | Applications/Tools | CLOSED |  |  |  | 2025-07-31 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\417 |  | 1
2272 | NOC57 | NOC | NA |  |  |  | GPON | OSS | T-NOC Report :: Summary of O&M Cluster OLTs status Weekly |  | Critical | NOT_FEASIBLE |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  | Open | Not Feasible | [9 empty] | NOCGPON | Applications/Tools | #N/A | NOT-FEASIBLE | 0 |  |  | #N/A |  | 1
2273 | NOC570 | NOC | NA |  |  |  | GPON | GPON | OLT Node not reachable alarm clearance and regeneration |  | Critical |  |  | Tejas OEM | EMS |  |  |  |  | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-07-05 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\425 | [6 empty] | NOCGPON | Applications/Tools | CLOSED |  |  |  | 2025-07-05 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\425 |  | 1
2274 | NOC571 | NOC | NA |  |  |  | GPON | GPON | while adding uni in EMS, list of downstream profiles are highlighting in the bottom |  | Critical |  |  | Tejas OEM | EMS |  |  |  |  | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-07-05 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\430 | [6 empty] | NOCGPON | Applications/Tools | CLOSED |  |  |  | 2025-07-05 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\430 |  | 1
2275 | NOC572 | NOC | NA |  |  |  | GPON | GPON | Nokia ONT ethernet port status is not updating |  | Critical |  |  | Tejas OEM | ONT |  | Duplicate point of 472 - 432 | Duplicate |  | Sayyad Pasha |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | NOCGPON | Applications/Tools | OPEN |  |  | Duplicate |  |  |  | 1
2276 | NOC573 | NOC | NA |  |  |  | GPON | GPON | Tejas ONT Software Upgrade which are connected under Nokia OLT |  | Critical |  |  | Tejas OEM | ONT |  | Duplicate point of 472 - 433 | Duplicate |  | Sayyad Pasha |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | NOCGPON | Applications/Tools | OPEN |  |  | Duplicate |  |  |  | 1
2277 | NOC574 | NOC | NA |  |  |  | GPON | GPON | API for GI-BB Service, combo port, mixed service - Route Mode with/without translation, including uplink port configuration |  | Critical |  |  | Tejas OEM | EMS |  |  |  |  | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-08-06 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\442 | [6 empty] | NOCGPON | Applications/Tools | CLOSED |  |  |  | 2025-08-06 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\442 |  | 1
2278 | NOC575 | NOC | NA |  |  |  | GPON | GPON | API for TDIA Service, combo port, mixed service - Route Mode with/without translation, including uplink port configuration |  | Critical |  |  | Tejas OEM | EMS |  |  |  |  | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API | [6 empty] | NOCGPON | Applications/Tools | CLOSED |  |  |  | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API |  | 1
2279 | NOC576 | NOC | NA |  |  |  | GPON | GPON | API to restirct/block the PON port to a specific customer |  | Critical |  |  | Tejas OEM | EMS |  | OEM confirmed API will be made availble in next release of EMS on March-2026 | Tejas & Nokia | Deepak and Sivakasi | Sayyad Pasha |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | NOCGPON | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
2280 | NOC577 | NOC | NA |  |  |  | GPON | GPON | API to modify the service- ONT, UNI Port, bandwidth, vlan, description, unatgged to tag or vice versa., |  | Critical |  |  | Tejas OEM | EMS |  | Duplicate point of 472 - 463 | Duplicate |  | Sayyad Pasha |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | NOCGPON | Applications/Tools | OPEN |  |  | Duplicate |  |  |  | 1
2281 | NOC578 | NOC | NA |  |  |  | GPON | GPON | PIR not working in route mode |  | Critical |  |  | Tejas OEM | OLT |  | Duplicate point of 472 - 407 | Duplicate |  | Sayyad Pasha |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | NOCGPON | Applications/Tools | OPEN |  |  | Duplicate |  | #N/A |  | 1
2282 | NOC579 | NOC | NA |  |  |  | GPON | GPON | Nokia ONT/3rd party ONT under Tejas OLT Remote access for WAN port |  | Critical |  |  | Tejas OEM | OLT/ONT |  | OEM confirmed this feature is not available 20-Sep-25: T Fiber team asked to arrange meeting with Tejas, Nokia OEM | Tejas & Nokia | Deepak and Sivakasi | Sayyad Pasha |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | NOCGPON | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
2283 | NOC58 | NOC | NA |  |  |  | GPON | OSS | T-NOC Report :: Summary of O&M Cluster OLTs status Monthly |  | Critical | NOT_FEASIBLE |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  | Open | Not Feasible | [9 empty] | NOCGPON | Applications/Tools | #N/A | NOT-FEASIBLE | 0 |  |  | #N/A |  | 1
2284 | NOC580 | NOC | NA |  |  |  | GPON | GPON | Unable to browse Internet when IPV6 configured in wifi ONT |  | Critical |  |  | Nokia OEM | AMS |  |  |  |  | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-07-31 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\472 | [6 empty] | NOCGPON | Applications/Tools | CLOSED |  |  |  | 2025-07-31 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\472 |  | 1
2285 | NOC581 | NOC | NA |  |  |  | GPON | GPON | Hybrid Mode of the G-240G-E ONT |  | Critical |  |  | Nokia OEM | ONT |  | Duplicate point of 472 - T180 | Duplicate |  | Sayyad Pasha |  | Open | Duplicate | [9 empty] | NOCGPON | Applications/Tools | CLOSED |  |  | Duplicate |  | Artefacts not Required |  | 1
2286 | NOC582 | NOC | NA |  |  |  | GPON | GPON | Nokia ONT under Nokia OLT Remote access for WAN port |  | Critical |  |  | Nokia OEM | OLT/ONT |  | OEM confirmed this feature is not available 20-Sep-25: T Fiber team asked to arrange meeting with Tejas, Nokia OEM | Tejas & Nokia | Deepak and Sivakasi | Sayyad Pasha |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | NOCGPON | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
2287 | NOC583 | NOC | NA |  |  |  | GPON | GPON | Tejas ONT/3rd party ONT under Nokia OLT Remote access for WAN port |  | Critical |  |  | Nokia OEM | OLT/ONT |  | OEM confirmed this feature is not available 20-Sep-25: T Fiber team asked to arrange meeting with Tejas, Nokia OEM | Tejas & Nokia | Deepak and Sivakasi | Sayyad Pasha |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | NOCGPON | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
2288 | NOC584 | NOC | NA |  |  |  | GPON | GPON | Nokia ONT under Tejas OLT Remote access for WAN port |  | Critical |  |  | Nokia OEM | OLT/ONT |  | OEM confirmed this feature is not available 20-Sep-25: T Fiber team asked to arrange meeting with Tejas, Nokia OEM | Tejas & Nokia | Deepak and Sivakasi | Sayyad Pasha |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | NOCGPON | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
2289 | NOC585 | NOC | NA |  |  |  | GPON | GPON | ONT cosumed count is showing wrong in license page |  | Critical |  |  | Nokia OEM | AMS |  | To resolve this issue, AMS to be upgraded and plan of action is awaited from OEM 20-Sep-25: Licensing conumption quantity not showing in Nokia AMS for discovered ONTs.Nokia OEM informed to address this issue Nokia AMS software need to be upgraded. As requested by Nokia team required pre-requsuits shared with Nokia OEM.yet to receive upgradation plan from Nokia Team. | Tejas & Nokia | Deepak and Sivakasi | Sayyad Pasha |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | NOCGPON | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
2290 | NOC586 | NOC | NA |  |  |  | GPON | GPON | API and Template for ILL Service - Bridge Mode, including uplink port configuration |  | Critical |  |  | Nokia OEM | AMS |  | OEM confirmed API/Template is not available for uplink port configuration | Nokia & NSO | Sivakasi & Jayath | Sayyad Pasha |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | NOCGPON | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
2291 | NOC587 | NOC | NA |  |  |  | GPON | GPON | API and Template for ILL Service - Route Mode, including uplink port configuration |  | Critical |  |  | Nokia OEM | AMS |  | OEM confirmed API/Template is not available for uplink port configuration | Nokia & NSO | Sivakasi & Jayath | Sayyad Pasha |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | NOCGPON | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
2292 | NOC588 | NOC | NA |  |  |  | GPON | GPON | API and Template for Household Services, including uplink port configuration |  | Critical |  |  | Nokia OEM | AMS |  | OEM confirmed API/Template is not available for uplink port configuration | Nokia & NSO | Sivakasi & Jayath | Sayyad Pasha |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | NOCGPON | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
2293 | NOC589 | NOC | NA |  |  |  | GPON | GPON | API and Template for IPTV services, including uplink port configuration |  | Critical |  |  | Nokia OEM | AMS |  | OEM confirmed API/Template is not available for uplink port configuration | Nokia & NSO | Sivakasi & Jayath | Sayyad Pasha |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | NOCGPON | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
2294 | NOC59 | NOC | NA |  |  |  | GPON | OSS | T-NOC Report :: Summary of O&M Cluster OLTs status (Selective from and to dates) |  | Critical | NOT_FEASIBLE |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  | Open | Not Feasible | [9 empty] | NOCGPON | Applications/Tools | #N/A | NOT-FEASIBLE | 0 |  |  | #N/A |  | 1
2295 | NOC590 | NOC | NA |  |  |  | GPON | GPON | API, Template and configuration for VOIP services, including uplink port configuration |  | Critical |  |  | Nokia OEM | AMS |  | OEM confirmed API/Template is not available for uplink port configuration | Nokia & NSO | Sivakasi & Jayath | Sayyad Pasha |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | NOCGPON | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
2296 | NOC591 | NOC | NA |  |  |  | GPON | GPON | API and Template for GI-BB Service - Bridge Mode, including uplink port configuration |  | Critical |  |  | Nokia OEM | AMS |  | OEM confirmed API/Template is not available for uplink port configuration | Nokia & NSO | Sivakasi & Jayath | Sayyad Pasha |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | NOCGPON | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
2297 | NOC592 | NOC | NA |  |  |  | GPON | GPON | API and Template for GI-BB Service - Route Mode, including uplink port configuration |  | Critical |  |  | Nokia OEM | AMS |  | OEM confirmed API/Template is not available for uplink port configuration | Nokia & NSO | Sivakasi & Jayath | Sayyad Pasha |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | NOCGPON | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
2298 | NOC593 | NOC | NA |  |  |  | GPON | GPON | API to fetch the configured services in AMS, including uplink port configuration |  | Critical |  |  | Nokia OEM | AMS |  | OEM confirmed API/Template is not available for uplink port configuration | Nokia & NSO | Sivakasi & Jayath | Sayyad Pasha |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | NOCGPON | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
2299 | NOC594 | NOC | NA |  |  |  | GPON | GPON | Configuration, API and Template for applying QOS for the different types of services |  | Critical |  |  | Nokia OEM | AMS |  | API has to share by OEM | Nokia & NSO | Sivakasi & Jayath | Sayyad Pasha |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | NOCGPON | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
2300 | NOC595 | NOC | NA |  |  |  | GPON | GPON | API and Template required to provision ONT along with selecting specific UNI port in ONT |  | Critical |  |  | Nokia OEM | AMS |  | API has to share by OEM | Nokia & NSO | Sivakasi & Jayath | Sayyad Pasha |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | NOCGPON | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
2301 | NOC596 | NOC | NA |  |  |  | GPON | GPON | API and Template required to provision ONT with multiple services along with selecting specific UNI port in ONT |  | Critical |  |  | Nokia OEM | AMS |  | API has to share by OEM | Nokia & NSO | Sivakasi & Jayath | Sayyad Pasha |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | NOCGPON | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
2302 | NOC597 | NOC | NA |  |  |  | GPON | GPON | API and Template required to provision ONT with same service on all ports |  | Critical |  |  | Nokia OEM | AMS |  | API has to share by OEM | Nokia & NSO | Sivakasi & Jayath | Sayyad Pasha |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | NOCGPON | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
2303 | NOC598 | NOC | NA |  |  |  | GPON | GPON | API and Template to configure multiple vlans on single ONT UNI Port |  | Critical |  |  | Nokia OEM | AMS |  | API has to share by OEM | Nokia & NSO | Sivakasi & Jayath | Sayyad Pasha |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | NOCGPON | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
2304 | NOC599 | NOC | NA |  |  |  | GPON | GPON | Configuration, API and Template for extedning services to enterprise customers |  | Critical |  |  | Nokia OEM | AMS |  | API has to share by OEM | Nokia & NSO | Sivakasi & Jayath | Sayyad Pasha |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | NOCGPON | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
2305 | NOC6 | NOC | NA |  | OSS | OSS | OSS | DC | DC Applications uptime & SLA Weekly |  | Critical |  |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCOSS | Applications/Tools | OPEN | OPEN | 0 |  |  | #N/A |  | 1
2306 | NOC60 | NOC | NA |  |  |  | GPON | OSS | Router UP - OLT Down cases Daily |  | Critical | COMPLETED |  | NNMI | NNMI |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCGPON | Applications/Tools | OPEN | COMPLETED | To be updated by Manoj |  |  |  |  | 1
2307 | NOC600 | NOC | NA |  |  |  | GPON | GPON | API and Template to verify and enable the PM |  | Critical |  |  | Nokia OEM | AMS |  | API has to share by OEM | Nokia & NSO | Sivakasi & Jayath | Sayyad Pasha |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | NOCGPON | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
2308 | NOC601 | NOC | NA |  |  |  | GPON | GPON | API and Template to configure Vlan and Profiles in OLT |  | Critical |  |  | Nokia OEM | AMS |  | API has to share by OEM | Nokia & NSO | Sivakasi & Jayath | Sayyad Pasha |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | NOCGPON | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
2309 | NOC602 | NOC | NA |  |  |  | GPON | GPON | Required complete API and Template developer document |  | Critical |  |  | Nokia OEM | AMS |  | OEM shared the document of APC template creation but required document for the API attributes | Nokia & NSO | Sivakasi & Jayath | Sayyad Pasha |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | NOCGPON | Applications/Tools | OPEN |  |  |  |  | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API Document |  | 1
2310 | NOC603 | NOC | NA |  |  |  | GPON | GPON | API and Template to validate the profiles, vlans available in OLT,ONT |  | Critical |  |  | Nokia OEM | AMS |  | API has to share by OEM | Nokia & NSO | Sivakasi & Jayath | Sayyad Pasha |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | NOCGPON | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
2311 | NOC604 | NOC | NA |  |  |  | GPON | GPON | API and Template to restirct/block the PON port to a specific customer |  | Critical |  |  | Nokia OEM | AMS |  | API has to share by OEM | Nokia & NSO | Sivakasi & Jayath | Sayyad Pasha |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | NOCGPON | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
2312 | NOC605 | NOC | NA |  |  |  | GPON | GPON | API and Template to modify the service- ONT, UNI Port, bandwidth, vlan, description, unatgged to tag or vice versa., |  | Critical |  |  | Nokia OEM | AMS |  | API has to share by OEM | Nokia & NSO | Sivakasi & Jayath | Sayyad Pasha |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | NOCGPON | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
2313 | NOC606 | NOC | NA |  |  |  | GPON | GPON | API and Template to configure,modify,suspend,delete the WAN profiles in WiFi ONT |  | Critical |  |  | Nokia OEM | AMS |  | OEM confirmed API/Template is not available | Nokia & NSO | Sivakasi & Jayath | Sayyad Pasha |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | NOCGPON | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
2314 | NOC607 | NOC | NA |  |  |  | GPON | GPON | Verification of the service provisioning templates which are prepared for the different types of services |  | Critical |  |  | Nokia OEM | AMS |  | API has to share by OEM | Nokia & NSO | Sivakasi & Jayath | Sayyad Pasha |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | NOCGPON | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
2315 | NOC608 | NOC | NA |  |  |  | GPON | GPON | Verification of the services configured by NSO through Playbook(Cisco Tool) |  | Critical |  |  | Nokia OEM | AMS |  | API has to share by OEM | Nokia & NSO | Sivakasi & Jayath | Sayyad Pasha |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | NOCGPON | Applications/Tools | OPEN |  |  |  |  | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API to validate the configured Services |  | 1
2316 | NOC609 | NOC | NA |  |  |  | GPON | GPON | Mapping bandiwdth profiles per vlan in a ONT UNI | 20-Sep-25: As per Nokia OEM, Mapping BW profiles per service BW on ONT Interface.Meeting to be arranged with Nokia OEM | Critical |  |  | Nokia OEM | OLT/ONT |  | Update awaited from OEM | Nokia & NSO | Sivakasi & Jayath | Sayyad Pasha |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | NOCGPON | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
2317 | NOC61 | NOC | NA |  |  |  | GPON | OSS | Router UP - OLT Down cases Weekly |  | Critical | COMPLETED |  | NNMI | NNMI |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCGPON | Applications/Tools | OPEN | COMPLETED | To be updated by Manoj |  |  |  |  | 1
2318 | NOC610 | NOC | NA |  |  |  | GPON | GPON | NOKIA ONT is not supporting for bandwidth Rate Limit configuration On ONT LAN Ethernet port (UNI) when connected under Tejas OLT | 20-Sep-25:Guidelines have to share with all 3 packages to deploy balance scope as Tejas OLT- Tejas ONT and Nokia OLT-Nokia ONT | Critical |  |  | Nokia OEM | ONT |  | OEM confirmed Rate Limit is not supported by Nokia ONTs | Nokia & NSO | Sivakasi & Jayath | Sayyad Pasha |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | NOCGPON | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
2319 | NOC611 | NOC | NA |  |  |  | GPON | GPON | PM Report for 24hrs of OLT,ONT,ONT Eth Port(Bridge/Route), Wifi |  | Critical |  |  | Nokia OEM | AMS |  |  |  |  | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-07-31 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\470 | [6 empty] | NOCGPON | Applications/Tools | CLOSED |  |  |  | 2025-07-31 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\470 |  | 1
2320 | NOC612 | NOC | NA |  |  |  | GPON | GPON | Nokia ONT ethernet port status is not updating |  | Critical | DUPLICATE POINT (NOC572) |  | Nokia OEM | OLT/ONT |  | Duplicate point of 472 - 432 | Duplicate |  | Sayyad Pasha |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | NOCGPON | Applications/Tools | OPEN |  |  | Duplicate |  |  |  | 1
2321 | NOC613 | NOC | NA |  |  |  | GPON | GPON | Unable to provide available download bandwidth of PON Port for Nokia devices (Nokia BW Query) |  | Critical |  |  | Nokia OEM | AMS |  | Duplicate point of 472 - T175 | Duplicate |  | Sayyad Pasha |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | NOCGPON | Applications/Tools | OPEN |  |  | Duplicate |  | #N/A |  | 1
2322 | NOC614 | NOC | NA |  | OSS | OSS | All Domain | OSS | EOL and EOS Through inventory Dashboard-Weekly |  | Critical | COMPLETED |  | HPSM | Asset Manager |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCAll Domain | Applications/Tools | OPEN | COMPLETED | we dont have dashboard only report is available |  |  |  |  | 1
2323 | NOC615 | NOC | NA |  | OSS | OSS | All Domain | OSS | EOL and EOS Through inventory Dashboard-Monthly |  | Critical | COMPLETED |  | HPSM | Asset Manager |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCAll Domain | Applications/Tools | OPEN | COMPLETED | we dont have dashboard only report is available |  |  |  |  | 1
2324 | NOC616 | NOC | NA |  | OSS | OSS | All Domain | OSS | Infra Server Url Services Intigration |  | Critical | COMPLETED |  | HPSM | Site scope |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCAll Domain | Applications/Tools | OPEN | CLOSURE REVIEW PENDING | 0 |  |  |  |  | 1
2325 | NOC617 | NOC | NA |  | OSS | OSS | All Domain | OSS | Infra Server Url Services Monitoring |  | Critical | COMPLETED |  | HPSM | Site scope |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCAll Domain | Applications/Tools | OPEN | CLOSURE REVIEW PENDING | 0 |  |  |  |  | 1
2326 | NOC618 | NOC | NA |  | OSS | OSS | All Domain | OSS | Infra Server Url Services Reporting |  | Critical | COMPLETED |  | HPSM | Site scope |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCAll Domain | Applications/Tools | OPEN | CLOSURE REVIEW PENDING | 0 |  |  |  |  | 1
2327 | NOC619 | NOC | NA |  | OSS | OSS | All Domain | OSS | real-time information |  | Critical | COMPLETED |  | HPSM | Site scope |  | 09-09-2025: Ticket, status, Inventory, Alarms, etc are available in real time |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCAll Domain | Applications/Tools | OPEN | COMPLETED | 09-09-2025: Ticket, status, Inventory, Alarms, etc are available in real time |  |  |  |  | 1
2328 | NOC62 | NOC | NA |  |  |  | GPON | OSS | Router UP - OLT Down cases Monthly |  | Critical | COMPLETED |  | NNMI | NNMI |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCGPON | Applications/Tools | OPEN | COMPLETED | To be updated by Manoj |  |  |  |  | 1
2329 | NOC620 | NOC | NA |  | OSS | OSS | All Domain | OSS | Health of the Performance for Traffic |  | Critical | COMPLETED |  | HPSM | NNM iSPI |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCAll Domain | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1
2330 | NOC621 | NOC | NA |  | OSS | OSS | All Domain | OSS | Analyze Flow Packets |  | Critical | COMPLETED |  | HPSM | NNM iSPI |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCAll Domain | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1
2331 | NOC622 | NOC | NA |  | OSS | OSS | All Domain | OSS | Performance for Traffic Maps |  | Critical | COMPLETED |  | HPSM | NNM iSPI |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCAll Domain | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1
2332 | NOC623 | NOC | NA |  |  |  | NSO | NSO | NSO Intigration for POC Locations LCO,RMSO & MSO |  | Critical |  |  | NSO | SCCM/Playbook |  |  |  |  | Jayant Madavi |  | Open | Open | [9 empty] | NOCNSO | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
2333 | NOC624 | NOC | NA |  |  |  | NSO | NSO | Video customer inventory , Internet customer inventory , Bandwidth allocation inventory count etc., |  | Critical |  |  | NSO | SCCM/Playbook |  |  |  |  | Jayant Madavi |  | Open | Open | [9 empty] | NOCNSO | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
2334 | NOC625 | NOC | NA |  |  |  | NSO | NSO | NSO Intigration for Live Locations LCO,RMSO & MSO |  | Critical |  |  | NSO | SCCM/Playbook |  |  |  |  | Jayant Madavi |  | Open | Open | [9 empty] | NOCNSO | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
2335 | NOC626 | NOC | NA |  |  |  | NSO | NSO | Video customer inventory , Internet customer inventory , Bandwidth allocation inventory count etc., |  | Critical | DUPLICATE POINT (NOC624) |  | NSO | SCCM/Playbook |  |  |  |  | Jayant Madavi |  | Open | Open | [9 empty] | NOCNSO | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
2336 | NOC627 | NOC | NA |  |  |  | BSS | BSS | TFiber BSS to be integrated with Partners SMS & BSS (LCO, RMSO & MSO etc..) for POC Locations |  | Critical | OPEN |  | KNOT | CRM |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
2337 | NOC628 | NOC | NA |  |  |  | BSS | BSS | After completion of POC Same solution shall be implemented for All Household of Telangana (TFiber BSS to be integrated with all other Partners SMS & BSS for Live (LCO , RMSO & MSO etc..)) |  | Critical | OPEN |  | KNOT | CRM |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
2338 | NOC629 | NOC | NA |  |  |  | BSS | BSS | New Customer order HouseHolds |  | Critical | OPEN |  | KNOT | CRM |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
2339 | NOC63 | NOC | NA |  |  |  | GPON | OSS | Router UP - OLT Down cases (Selective from and to dates) |  | Critical | COMPLETED |  | NNMI | NNMI |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCGPON | Applications/Tools | OPEN | COMPLETED | To be updated by Manoj |  |  |  |  | 1
2340 | NOC630 | NOC | NA |  |  |  | BSS | BSS | Existing customer alignment for order |  | Critical | OPEN |  | KNOT | CRM |  | DUPLICATE POINT (NOC630) |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
2341 | NOC631 | NOC | NA |  |  |  | BSS | BSS | Customer service ID allocation |  | Critical | OPEN |  | KNOT | CRM |  | DUPLICATE POINT (NOC631) |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
2342 | NOC632 | NOC | NA |  |  |  | BSS | BSS | Activation & Deactivation update to BSS |  | Critical | OPEN |  | KNOT | CRM |  | DUPLICATE POINT (NOC632) |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
2343 | NOC633 | NOC | NA |  |  |  | BSS | BSS | New customer package & billing |  | Critical | OPEN |  | KNOT | Billing |  | DUPLICATE POINT (NOC633) |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
2344 | NOC634 | NOC | NA |  |  |  | BSS | BSS | Existing customer renewal & package modification update |  | Critical | OPEN |  | KNOT | Billing |  | DUPLICATE POINT (NOC634) |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
2345 | NOC635 | NOC | NA |  |  |  | BSS | BSS | Customer address change intigration |  | Critical | OPEN |  | KNOT | Billing |  | DUPLICATE POINT (NOC635) |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
2346 | NOC636 | NOC | NA |  |  |  | BSS | BSS | Customer Discount update to BSS |  | Critical | OPEN |  | KNOT | Billing |  | DUPLICATE POINT (NOC636) |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
2347 | NOC637 | NOC | NA |  |  |  | BSS | BSS | Partner Dashboard Number of customers through TFiber |  | Critical | OPEN |  | BSS | CRM |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
2348 | NOC638 | NOC | NA |  |  |  | BSS | BSS | Partner Dashboard Uptime SLA customers through TFiber |  | Critical | OPEN |  | HPSM | Incident Management |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
2349 | NOC639 | NOC | NA |  |  |  | BSS | BSS | Partner Dashboard Access |  | Critical | OPEN |  | BSS | CRM |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
2350 | NOC64 | NOC | NA |  |  |  | GPON | OSS | ONTs down more than 8 hrs. list Daily |  | Critical | COMPLETED |  | OSS Dashboards | UOC |  | 09-09-2025: Aging Report available, Stabilization Required |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCGPON | Applications/Tools | OPEN | COMPLETED | 09-09-2025: Aging Report available, Stabilization Required |  |  |  |  | 1
2351 | NOC640 | NOC | NA |  |  |  | BSS | BSS | TFiber BSS to be Implemented for all GI of Telangana |  | Critical | OPEN |  | KNOT | CRM |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
2352 | NOC641 | NOC | NA |  |  |  | BSS | BSS | After completion of POC Same solution shall be implemented for All Government Institutions of Telangana (TFiber BSS to be Utilized for go Live ) |  | Critical | OPEN |  | KNOT | CRM |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
2353 | NOC642 | NOC | NA |  |  |  | BSS | BSS | New Customer order GI |  | Critical | OPEN |  | KNOT | CRM |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
2354 | NOC643 | NOC | NA |  |  |  | BSS | BSS | Existing customer alignment for order |  | Critical | DUPLICATE POINT (NOC630) |  | KNOT | CRM |  | DUPLICATE POINT (NOC630) |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
2355 | NOC644 | NOC | NA |  |  |  | BSS | BSS | Customer service ID allocation |  | Critical | DUPLICATE POINT (NOC631) |  | KNOT | CRM |  | DUPLICATE POINT (NOC631) |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
2356 | NOC645 | NOC | NA |  |  |  | BSS | BSS | Activation & Deactivation update to BSS |  | Critical | DUPLICATE POINT (NOC632) |  | KNOT | CRM |  | DUPLICATE POINT (NOC632) |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
2357 | NOC646 | NOC | NA |  |  |  | BSS | BSS | New customer package & billing |  | Critical | DUPLICATE POINT (NOC633) |  | KNOT | Billing |  | DUPLICATE POINT (NOC633) |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
2358 | NOC647 | NOC | NA |  |  |  | BSS | BSS | Existing customer renewal & package modification update |  | Critical | DUPLICATE POINT (NOC634) |  | KNOT | Billing |  | DUPLICATE POINT (NOC634) |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
2359 | NOC648 | NOC | NA |  |  |  | BSS | BSS | Customer address change intigration |  | Critical | DUPLICATE POINT (NOC635) |  | KNOT | Billing |  | DUPLICATE POINT (NOC635) |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
2360 | NOC649 | NOC | NA |  |  |  | BSS | BSS | Customer Discount update to BSS |  | Critical | DUPLICATE POINT (NOC636) |  | KNOT | Billing |  | DUPLICATE POINT (NOC636) |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
2361 | NOC65 | NOC | NA |  |  |  | GPON | OSS | ONTs down more than 8 hrs. list Weekly |  | Critical | COMPLETED |  | OSS Dashboards | UOC |  | 09-09-2025: Aging Report available, Stabilization Required |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCGPON | Applications/Tools | OPEN | COMPLETED | 09-09-2025: Aging Report available, Stabilization Required |  |  |  |  | 1
2362 | NOC650 | NOC | NA |  |  |  | BSS | BSS | Customer Dashboard Number of customers through TFiber |  | Critical | OPEN |  | BSS | CRM |  | DUPLICATE POINT (NOC650) |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
2363 | NOC651 | NOC | NA |  |  |  | BSS | BSS | Customer Dashboard Uptime SLA customers through TFiber |  | Critical | OPEN |  | HPSM | Incident Management |  | DUPLICATE POINT (NOC651) |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
2364 | NOC652 | NOC | NA |  |  |  | BSS | BSS | Customer Dashboard Access |  | Critical | OPEN |  | BSS | CRM |  | DUPLICATE POINT (NOC652) |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
2365 | NOC653 | NOC | NA |  |  |  | BSS | BSS | TFiber BSS to be Implemented for all Enterprice P2p & P2MP services in Telangana |  | Critical | OPEN |  | KNOT | CRM |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
2366 | NOC654 | NOC | NA |  |  |  | BSS | BSS | After completion of POC Same solution shall be implemented for All Enterprice P2p & P2MP services in Telangana (TFiber BSS to be Utilized for go Live ) |  | Critical | OPEN |  | KNOT | CRM |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
2367 | NOC655 | NOC | NA |  |  |  | BSS | BSS | New Customer order Enterprice |  | Critical | OPEN |  | KNOT | CRM |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
2368 | NOC656 | NOC | NA |  |  |  | BSS | BSS | Existing customer alignment for order |  | Critical | DUPLICATE POINT (NOC630) |  | KNOT | CRM |  | DUPLICATE POINT (NOC630) |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
2369 | NOC657 | NOC | NA |  |  |  | BSS | BSS | Customer service ID allocation |  | Critical | DUPLICATE POINT (NOC631) |  | KNOT | CRM |  | DUPLICATE POINT (NOC631) |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
2370 | NOC658 | NOC | NA |  |  |  | BSS | BSS | Activation & Deactivation update to BSS |  | Critical | DUPLICATE POINT (NOC632) |  | KNOT | CRM |  | DUPLICATE POINT (NOC632) |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
2371 | NOC659 | NOC | NA |  |  |  | BSS | BSS | New customer package & billing |  | Critical | DUPLICATE POINT (NOC633) |  | KNOT | Billing |  | DUPLICATE POINT (NOC633) |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
2372 | NOC66 | NOC | NA |  |  |  | GPON | OSS | ONTs down more than 8 hrs. list Monthly |  | Critical | COMPLETED |  | OSS Dashboards | UOC |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCGPON | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1
2373 | NOC660 | NOC | NA |  |  |  | BSS | BSS | Existing customer renewal & package modification update |  | Critical | DUPLICATE POINT (NOC634) |  | KNOT | Billing |  | DUPLICATE POINT (NOC634) |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
2374 | NOC661 | NOC | NA |  |  |  | BSS | BSS | Customer address change intigration |  | Critical | DUPLICATE POINT (NOC635) |  | KNOT | Billing |  | DUPLICATE POINT (NOC635) |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
2375 | NOC662 | NOC | NA |  |  |  | BSS | BSS | Customer Discount update to BSS |  | Critical | DUPLICATE POINT (NOC636) |  | KNOT | Billing |  | DUPLICATE POINT (NOC636) |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
2376 | NOC663 | NOC | NA |  |  |  | BSS | BSS | Customer Dashboard Number of customers through TFiber |  | NON-Critical | DUPLICATE POINT (NOC650) |  | BSS | CRM |  | DUPLICATE POINT (NOC650) |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
2377 | NOC664 | NOC | NA |  |  |  | BSS | BSS | Customer Dashboard Uptime SLA customers through TFiber |  | NON-Critical | DUPLICATE POINT (NOC651) |  | HPSM | Incident Management |  | DUPLICATE POINT (NOC651) |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
2378 | NOC665 | NOC | NA |  |  |  | BSS | BSS | Customer Dashboard Access |  | NON-Critical | DUPLICATE POINT (NOC652) |  | BSS | CRM |  | DUPLICATE POINT (NOC652) |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
2379 | NOC666 | NOC | NA |  |  |  | NSO | Service Solutions | GI-BB |  | Critical |  |  | NSO | SCCM/Playbook |  |  |  |  | Jayant Madavi |  | Open | Open | [9 empty] | NOCNSO | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
2380 | NOC667 | NOC | NA |  |  |  | NSO | Service Solutions | T-CELL |  | Critical |  |  | NSO | SCCM/Playbook |  |  |  |  | Jayant Madavi |  | Open | Open | [9 empty] | NOCNSO | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
2381 | NOC668 | NOC | NA |  |  |  | NSO | Service Solutions | HH Triple Play (Internet, IPTV, VoIP) |  | Critical |  |  | NSO | SCCM/Playbook |  |  |  |  | Jayant Madavi |  | Open | Open | [9 empty] | NOCNSO | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
2382 | NOC669 | NOC | NA |  |  |  | NSO | Service Solutions | CCTV Unicast |  | Critical |  |  | NSO | SCCM/Playbook |  |  |  |  | Jayant Madavi |  | Open | Open | [9 empty] | NOCNSO | Applications/Tools | OPEN |  |  |  |  | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\Centrailzed CCTV Surveillance Monitoring over T-Fiber Network-Solution Doucment_Initial Draft V1.0 - T189.pdf |  | 1
2383 | NOC67 | NOC | NA |  |  |  | GPON | OSS | ONTs down more than 8 hrs. list (Selective from and to dates) |  | Critical | COMPLETED |  | OSS Dashboards | UOC |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCGPON | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1
2384 | NOC670 | NOC | NA |  |  |  | NSO | Service Solutions | CCTV Multicast |  | Critical |  |  | NSO | SCCM/Playbook |  |  |  |  | Jayant Madavi |  | Open | Open | [9 empty] | NOCNSO | Applications/Tools | OPEN |  |  |  |  | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\CCTV Multicast Solution LLD V1.2 - T190.pdf |  | 1
2385 | NOC671 | NOC | NA |  |  |  | NSO | Service Solutions | T-DIA (ILL) |  | Critical |  |  | NSO | SCCM/Playbook |  |  |  |  | Jayant Madavi |  | Open | Open | [9 empty] | NOCNSO | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
2386 | NOC672 | NOC | NA |  |  |  | NSO | Service Solutions | L2VPN |  | Critical |  |  | NSO | SCCM/Playbook |  |  |  |  | Jayant Madavi |  | Open | Open | [9 empty] | NOCNSO | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
2387 | NOC673 | NOC | NA |  |  |  | NSO | Service Solutions | L3VPN |  | Critical |  |  | NSO | SCCM/Playbook |  |  |  |  | Jayant Madavi |  | Open | Open | [9 empty] | NOCNSO | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
2388 | NOC674 | NOC | NA |  |  |  | NSO | Service Solutions | TVPN - Rythu Vedika |  | Critical |  |  | NSO | SCCM/Playbook |  |  |  |  | Jayant Madavi |  | Open | Open | [9 empty] | NOCNSO | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
2389 | NOC675 | NOC | NA |  |  |  | NSO | Service Solutions | TVPN - DHQ to SHQ Connectivity |  | Critical |  |  | NSO | SCCM/Playbook |  |  |  |  | Jayant Madavi |  | Open | Open | [9 empty] | NOCNSO | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
2390 | NOC676 | NOC | NA |  |  |  | NSO | Service Solutions | TVPN - MRO Office Connectivity |  | Critical |  |  | NSO | SCCM/Playbook |  |  |  |  | Jayant Madavi |  | Open | Open | [9 empty] | NOCNSO | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
2391 | NOC677 | NOC | NA |  |  |  | NSO | Service Solutions | SDC/TSWAN integration |  | Critical |  |  | NSO | SCCM/Playbook |  |  |  |  | Jayant Madavi |  | Open | Open | [9 empty] | NOCNSO | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
2392 | NOC678 | NOC | NA |  |  |  | NSO | Service Solutions | TSP NNI |  | Critical |  |  | NSO | SCCM/Playbook |  |  |  |  | Jayant Madavi |  | Open | Open | [9 empty] | NOCNSO | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1
2393 | NOC68 | NOC | NA |  |  |  | GPON | OSS | Mandal OLT down more than 6 hrs. list Daily |  | Critical | COMPLETED |  | OSS Dashboards | UOC |  | 09-09-2025: Aging Report available, Stabilization Required |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCGPON | Applications/Tools | OPEN | COMPLETED | 09-09-2025: Aging Report available, Stabilization Required -real time data |  |  |  |  | 1
2394 | NOC69 | NOC | NA |  |  |  | GPON | OSS | Mandal OLT down more than 6 hrs. list Weekly |  | Critical | COMPLETED |  | OSS Dashboards | UOC |  | 09-09-2025: Aging Report available, Stabilization Required |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCGPON | Applications/Tools | OPEN | COMPLETED | 09-09-2025: Aging Report available, Stabilization Required |  |  |  |  | 1
2395 | NOC7 | NOC | NA |  | OSS | OSS | OSS | DC | DC Applications uptime & SLA Monthly |  | Critical |  |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCOSS | Applications/Tools | OPEN | OPEN | 0 |  |  | #N/A |  | 1
2396 | NOC70 | NOC | NA |  |  |  | GPON | OSS | Mandal OLT down more than 6 hrs. list Monthly |  | Critical | COMPLETED |  | OSS Dashboards | UOC |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCGPON | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1
2397 | NOC71 | NOC | NA |  |  |  | GPON | OSS | Mandal OLT down more than 6 hrs. list (Selective from and to dates) |  | Critical | COMPLETED |  | OSS Dashboards | UOC |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCGPON | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1
2398 | NOC72 | NOC | NA |  |  |  | GPON | OSS | HH_PM Utilization Dump _PKGA_PKGC Daily |  | NON-Critical | COMPLETED |  | NNMI | NPS |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCGPON | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1
2399 | NOC73 | NOC | NA |  |  |  | GPON | OSS | HH_PM Utilization Dump _PKGA_PKGC Weekly |  | NON-Critical | NOT_FEASIBLE |  | NNMI | NPS |  |  |  |  | Suresh Pawar |  | Open | Not Feasible | [9 empty] | NOCGPON | Applications/Tools | #N/A | NOT-FEASIBLE | 0 |  |  | #N/A |  | 1
2400 | NOC74 | NOC | NA |  |  |  | GPON | OSS | HH_PM Utilization Dump _PKGA_PKGC Monthly |  | NON-Critical | COMPLETED |  | NNMI | NPS |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCGPON | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1
2401 | NOC75 | NOC | NA |  |  |  | GPON | OSS | HH_PM Utilization Dump _PKGA_PKGC (Selective from and to dates) |  | NON-Critical | NOT_FEASIBLE |  | NNMI | NPS |  |  |  |  | Suresh Pawar |  | Open | Not Feasible | [9 empty] | NOCGPON | Applications/Tools | #N/A | NOT-FEASIBLE | 0 |  |  | #N/A |  | 1
2402 | NOC76 | NOC | NA |  |  |  | GPON | OSS | Summary of Lit-up GPs Status_8895 Daily |  | NON-Critical | DUPLICATE POINT |  | HPSM | Incident Management |  | DUPLICATE POINT |  |  | Suresh Pawar |  | Open | Duplicate | [9 empty] | NOCGPON | Applications/Tools | OPEN | DUPLICATE | 0 |  |  | Artefacts to be uploaded |  | 1
2403 | NOC77 | NOC | NA |  |  |  | GPON | OSS | Summary of Lit-up GPs Status_8895 Weekly |  | NON-Critical | DUPLICATE POINT |  | HPSM | Incident Management |  | DUPLICATE POINT |  |  | Suresh Pawar |  | Open | Duplicate | [9 empty] | NOCGPON | Applications/Tools | OPEN | DUPLICATE | 0 |  |  | Artefacts to be uploaded |  | 1
2404 | NOC78 | NOC | NA |  |  |  | GPON | OSS | Summary of Lit-up GPs Status_8895 Monthly |  | NON-Critical | DUPLICATE POINT |  | HPSM | Incident Management |  | DUPLICATE POINT |  |  | Suresh Pawar |  | Open | Duplicate | [9 empty] | NOCGPON | Applications/Tools | OPEN | DUPLICATE | 0 |  |  | Artefacts to be uploaded |  | 1
2405 | NOC79 | NOC | NA |  |  |  | GPON | OSS | Summary of Lit-up GPs Status_8895 (Selective from and to dates) |  | Critical | DUPLICATE POINT |  | HPSM | Incident Management |  | DUPLICATE POINT |  |  | Suresh Pawar |  | Open | Duplicate | [9 empty] | NOCGPON | Applications/Tools | OPEN | DUPLICATE | 0 |  |  | Artefacts to be uploaded |  | 1
2406 | NOC8 | NOC | NA |  | OSS | OSS | OSS | DC | DC Applications uptime & SLA (Selective from and to dates) |  | Critical |  |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCOSS | Applications/Tools | OPEN | OPEN | 0 |  |  | #N/A |  | 1
2407 | NOC80 | NOC | NA |  |  |  | GPON | OSS | GPON OLT TT trend dashboard Daily |  | Critical | COMPLETED |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCGPON | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1
2408 | NOC81 | NOC | NA |  |  |  | GPON | OSS | GPON OLT TT trend dashboard Weekly |  | Critical | COMPLETED |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCGPON | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1
2409 | NOC82 | NOC | NA |  |  |  | GPON | OSS | GPON OLT TT trend dashboard Monthly |  | Critical | COMPLETED |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCGPON | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1
2410 | NOC83 | NOC | NA |  |  |  | GPON | OSS | GPON OLT TT trend dashboard (Selective from and to dates) |  | Critical | COMPLETED |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCGPON | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1
2411 | NOC84 | NOC | NA |  |  |  | GPON | OSS | GPON ONT TT trend dashboard Daily |  | Critical | COMPLETED |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCGPON | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1
2412 | NOC85 | NOC | NA |  |  |  | GPON | OSS | GPON ONT TT trend dashboard Weekly |  | Critical | COMPLETED |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCGPON | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1
2413 | NOC86 | NOC | NA |  |  |  | GPON | OSS | GPON ONT TT trend dashboard Monthly |  | Critical | COMPLETED |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCGPON | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1
2414 | NOC87 | NOC | NA |  |  |  | GPON | OSS | GPON ONT TT trend dashboard (Selective from and to dates) |  | Critical | COMPLETED |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCGPON | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1
2415 | NOC88 | NOC | NA |  |  |  | GPON | OSS | POP uptime_ GP Mandal and Zonal Daily |  | Critical | COMPLETED |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCGPON | Applications/Tools | OPEN | COMPLETED | availablity |  |  |  |  | 1
2416 | NOC89 | NOC | NA |  |  |  | GPON | OSS | POP uptime_ GP Mandal and Zonal Weekly |  | Critical | NOT_FEASIBLE |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  | Open | Not Feasible | [9 empty] | NOCGPON | Applications/Tools | #N/A | NOT-FEASIBLE | 0 |  |  | #N/A |  | 1
2417 | NOC9 | NOC | NA |  | OSS | OSS | OSS | DC | DC Passive infra uptime & SLA Daily |  | Critical |  |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCOSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  | #N/A |  | 1
2418 | NOC90 | NOC | NA |  |  |  | GPON | OSS | POP uptime_ GP Mandal and Zonal Monthly |  | Critical | COMPLETED |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCGPON | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1
2419 | NOC91 | NOC | NA |  |  |  | GPON | OSS | POP uptime_ GP Mandal and Zonal (Selective from and to dates) |  | Critical | NOT_FEASIBLE |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  | Open | Not Feasible | [9 empty] | NOCGPON | Applications/Tools | #N/A | NOT-FEASIBLE | 0 |  |  | #N/A |  | 1
2420 | NOC92 | NOC | NA |  |  |  | GPON | OSS | Weekly BW utilization Supporting data Daily |  | NON-Critical | COMPLETED |  | OSS Dashboards | PMS(UOC) |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCGPON | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1
2421 | NOC93 | NOC | NA |  |  |  | GPON | OSS | Weekly BW utilization Supporting data Weekly |  | NON-Critical | NOT_FEASIBLE |  | OSS Dashboards | PMS(UOC) |  |  |  |  | Suresh Pawar |  | Open | Not Feasible | [9 empty] | NOCGPON | Applications/Tools | #N/A | NOT-FEASIBLE | 0 |  |  | #N/A |  | 1
2422 | NOC94 | NOC | NA |  |  |  | GPON | OSS | Weekly BW utilization Supporting data Monthly |  | NON-Critical | COMPLETED |  | OSS Dashboards | PMS(UOC) |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCGPON | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1
2423 | NOC95 | NOC | NA |  |  |  | GPON | OSS | Weekly BW utilization Supporting data (Selective from and to dates) |  | NON-Critical | NOT_FEASIBLE |  | OSS Dashboards | PMS(UOC) |  |  |  |  | Suresh Pawar |  | Open | Not Feasible | [9 empty] | NOCGPON | Applications/Tools | #N/A | NOT-FEASIBLE | 0 |  |  | #N/A |  | 1
2424 | NOC96 | NOC | NA |  |  |  | GPON | OSS | T-NOC Report :: Migrated & Duplicated GPs still available both Tejas EMS & Nokia AMS Daily |  | NON-Critical | COMPLETED |  | HPSM | Incident Management |  | 09-09-2025: It has to handle manuaaly by downloading report |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCGPON | Applications/Tools | OPEN | COMPLETED | 09-09-2025: It has to handle manuaaly by downloading report |  |  |  |  | 1
2425 | NOC97 | NOC | NA |  |  |  | GPON | OSS | T-NOC Report :: Migrated & Duplicated GPs still available both Tejas EMS & Nokia AMS Weekly |  | NON-Critical | NOT_FEASIBLE |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCGPON | Applications/Tools | #N/A | COMPLETED | 0 |  |  | #N/A |  | 1
2426 | NOC98 | NOC | NA |  |  |  | GPON | OSS | T-NOC Report :: Migrated & Duplicated GPs still available both Tejas EMS & Nokia AMS Monthly |  | NON-Critical | COMPLETED |  | HPSM | Incident Management |  | 09-09-2025: It has to handle manuaaly by downloading report |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCGPON | Applications/Tools | OPEN | COMPLETED | 09-09-2025: It has to handle manuaaly by downloading report |  |  |  |  | 1
2427 | NOC99 | NOC | NA |  |  |  | GPON | OSS | T-NOC Report :: Migrated & Duplicated GPs still available both Tejas EMS & Nokia AMS (Selective from and to dates) |  | NON-Critical | COMPLETED |  | HPSM | Incident Management |  | 09-09-2025: It has to handle manuaaly by downloading report |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCGPON | Applications/Tools | OPEN | COMPLETED | 09-09-2025: It has to handle manuaaly by downloading report |  |  |  |  | 1
2428 | T2A | 472 | NA |  |  |  | Security & Regulatory Compliance | Security | Ciena to comply the password policy for MCP and field nodes, though Alepo AAA. |  |  | Open |  |  |  |  | Password managment policy for ciena need to be finalised and to be approved by authority prior implentations |  |  | Sarmendra |  | Open | WIP | [9 empty] | 472Security & Regulatory Compliance | Security | OPEN | [6 empty] | 1
`

## Sheet7 (hidden)
Sum of Qty | Column Labels
Row Labels | 472 | MOM | NOC | Grand Total
Completed & Approved | 255 | 271 | 15 | 541
Completed but Verification undrer Process | 45 | 174 | 269 | 488
Open | 172 | 833 | 394 | 1399
Grand Total | 472 | 1278 | 678 | 2428

## Summary-1 (hidden)
Sum of Qty | Column Labels
Row Labels | 472 | MOM | NOC | Grand Total
Closed after June | 54 | 227 | 15 | 296
Closed before june-2025 | 201 | 44 |  | 245
Completed but Verification undrer Process | 45 | 174 | 269 | 488
Open | 172 | 833 | 394 | 1399
Grand Total | 472 | 1278 | 678 | 2428

## Ramana-Master Tracker 2428
Slno | UniqueID | Category | Meeting Date | Priority | Ramana | Ramana-Domain | Domain | Sub-Domain | Action Point | Impact | Priority | Baseline Status | Application | Module | Remarks |  |  |  | LTTS REMARKS | NSO SD | NSO ED | Created By | NSO Status | Owner | Final Approval Status |  |  | Tfiber-Cat | Derived Status (L&T) | OSS | OSS DetailedRemarks | T/F | Ramana Remarks as on 19-Sep-2025 | NSO Comments | Review Status | Review Comments dated on | Tentative Completion Date | T Fiber Appoved Date | Artifacts | Ramana-Remarks | Updated on 01-Dec-2025 | 2025-10-13 | Remarks(1399)
1 | T1 | 472 | NA |  |  |  | Security & Regulatory Compliance | Configuration | Integration testing of All supported devices is complete and adding all the devices is underway. |  |  | Open |  |  | what ever request has come all are integrated with ISE , any new device request comes same will be added . Also Aleppo PO get relaesed for ADintegration , it will also get integrated with AD. | [12 empty] | Security | Closed |  |  |  |  | Organization structure |  |  |  | 2025-11-12 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\NW-Security\T1_01-Nov-25.pdf | Completed & Approved | Closed after 07-Nov-25 | Open
2 | T2 | 472 | NA |  |  |  | DWDM | Integration with Alepo | RADIUS Configuration Testing on Ciena Node & EMS (MCP) |  |  | Colosed | [15 empty] | DWDM | Closed |  |  |  |  | Received sample doc from Manoj |  |  |  | 2025-05-06 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\DWDM\Artefact - T106 | Completed & Approved | Closed before june-2025 | Closed before june-2025
3 | T3 | 472 | NA |  |  |  | Security & Regulatory Compliance | Integration | Accouting data from Ciena MCP and field nodes to be captured in Alepo AAA |  | Critical | Open |  |  | 28-Nov-25: The Alepo team is integrating AD Once done these points will be closed. MCP upgradation is in pipeline . same will be completed by 25 Sep 2025 | [12 empty] | Security | OPEN |  |  |  |  | Is this IPv4 and IPv6 | [5 empty] | Open | Open | Open
4 | T3 | 472 | NA |  |  |  | DWDM | Integration with Alepo | TACACS+/Radius testing for AAA on ciena node |  |  | Open |  |  | 28-Nov-25: The Alepo team is integrating AD Once done these points will be closed. 20-09-2025: 8.1 MCP software Patch upgradation will be completed by 27-Sep-25, After completetion of upgrdation AAA functi | ona | litie | s wi | ll be tes | for ciena d |  | evi | ces |  |  | by | using radius 13-09-25:MCP upgradation is in progress, will be able to check the logs by next week 28-08-2025: Activity is in progress, target to complete by 25th Sep'25 Authentication and Authorization tested and found OK for Node and MCP. 19-08-2025: Due to issue in disk partition and file type of storage, activity is not started 10-08-2025: OEM confirmation recieved and activity is planned from 18th August'25. 05-July-2025: DC OSS to DR MCP communication is through now, need to integrate and test before activity 12-July-2025: DC OSS to DR MCP integration testing done. Alarms and Autoticketing functioning as expected. Upgradation activity will be scheduled as per OEM confirmation, Target date - 30-07-25 26-July-2025: Schedule awaited from OEM 30-June-2025: DC OSS to DR MCP connectivity to be extended for PE approval, WIP. Target date - 30-07-25 15-06-25: Targeting to close the upgradation by month end, 30-06-25 30-05-2025: Accounting issue resolved in latest MCP version, verified in 8.2 Ver (Node logs are now capturing in MCP). Upgradation schedule awaited from Teleindia for our MCP from 7.1-P02 5/21/2025: Correlation to identified to find the user logged in at the specific time 28APR'25: As discussed with Sanjay sir, if user id not avaialble pls. try for correlation with IP. Some how Correlation to be done. In Accounting, Node and MCP logs are successfully reporting in Alepo with below limitation. Node Logs - Active profile name (ADMIN/RADIUS) is displayed against User ID (Ciena confirmed it is as per design no changes are possible) | DWDM | OPEN |  |  |  |  | what are these services | [5 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
5 | T4 | 472 | NA |  |  |  | Security & Regulatory Compliance | Security | Alepo confirmed that Alepo AAA supports TACACS, Alepo to test Nokia and Ciena nodes integration on TACACS , with supporting artefacts of testing. 1.TACACS Testing with Tejas, Nokia, Ciena 2. Alepo Testing with Tejas, Nokia and Ciena |  |  | Open |  |  | 28-Nov-25: The Alepo team is integrating AD Once done these points will be closed. 1.TACACS Testing with Tejas, Nokia, Ciena completed 2. Alepo Testing with Tejas, Nokia and Ciena | [12 empty] | Security | OPEN |  |  |  |  | We have development VM's but not testing kindly clarity | [5 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
6 | T5 | 472 | NA |  |  |  | Security & Regulatory Compliance | Functional AT | Had a meeting with Ashwani from Alepo and sent him updated test cases. He is working on data gathering and will send us back by Tuesday. |  |  | Open |  |  | FAT were submitted to customer, Customer observation in being work out. Target to resubmission.- 23.07.25 | [12 empty] | Security | Closed | [8 empty] | 2025-10-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\NW-Security\T5_29-Oct-25.pdf | Closed | Closed After 14-Oct | Completed but Verification undrer Process
7 | T6 | 472 | NA |  |  |  | BSS | Installation | Installation of BSS Application |  |  | Open |  |  | 29-08-2025: Design and Solution document to be shared with GM NOC and Physical instllation of BSS need to validate according to solution from L&T Side before submitting for for review with T Fiber 26-06- | 202 | 5: We | hav | e offered | stallation A |  | T. | TFI |  |  | BER | has asked DC architecture review including license validity | Applications/Tools | OPEN | [10 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
8 | T7 | 472 | NA |  |  |  | BSS | Integration | Initial Integration with Third Party Applications (OSS & NSO) |  |  | Open |  |  | 26-06-2025: OSS Integration is done. NSO integration is pending. Awaiting NSO Team. | [12 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
9 | T8 | 472 | NA |  |  |  | BSS | Integration | OSS interfaces |  |  | Open |  |  | 26-06-2025: Feasibility API & Ticket API integration is completed. | [12 empty] | Applications/Tools | OPEN |  |  |  |  | Ask Ritik | [5 empty] | Open | Open | Open
10 | T9 | 472 | NA |  |  |  | BSS | Integration | NSO interfaces |  |  | Open |  |  | 26-06-2025: Awaiting NSO Team | [12 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
11 | T10 | 472 | NA |  |  |  | BSS | Integration | GeM Portal |  |  | Open | [15 empty] | Applications/Tools | CLOSED | [8 empty] | 2025-07-16 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\BSS\Artifact_T10 | Open | Open | Open
12 | T11 | 472 | NA |  |  |  | BSS | Development and unit testing | Import Sub-Departments, Import Leads, Campaign Management, Opportunity/Quote/order Management, order booking and Service Order workflow for tested services |  |  | Open |  |  | 29-08-2025: All points are completed Import Sub-Departments, Import Leads, Opportunity/Quote/order Management, order booking and Service Order workflow for tested services Demo to be conducted to TFIBER. | "Ca | mpaig | n Ma | nagement" | Pending whe |  | re | inp |  |  | uts | are required from TFIBER Business team 26-06-2025: Awaiting few inputs from TFIBER | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
13 | T12 | 472 | NA |  |  |  | BSS | Development and unit testing | Product/Service Catalogue integration |  |  | Open |  |  | 29-08-2025: Feature is available to admin User(Product Team) to configure new product based on requirement. BSS Team will provide Demo to the TFIBER (business team([Uday]/Solution Team[Sanjay]) for their | acc | eptan | ce. | 26-06-202 | Artifacts su |  | bmi | tte |  |  | d. C | losure review is pending with TFIBER | Applications/Tools | OPEN |  |  |  |  | Jayant Sir | [5 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
14 | T13 | 472 | NA |  |  |  | BSS | Development and unit testing | Billing, Discounts & Adjustments, Invoice generation, Bill Formatting |  |  | Open |  |  | 29-08-2025: Feature is made available in the BSS application, BSS Team will provide demo to TFIBER Team (Business [Uday] & Finance[Bhaskar]) 26-06-2025: Artifacts submitted. Closure review is pending with | TFI | BER | [10 empty] | Applications/Tools | OPEN | [10 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
15 | T14 | 472 | NA |  |  |  | BSS | Development and unit testing | Feasibility API response from OSS for service provisioning request |  |  | Open |  |  | 29-08-2025: Feaibility API is already integrated with BSS and demonstrated in GIBB demo and it is applicable for all products. 26-06-2025: Artifacts submitted. Closure review is pending with TFIBER | [12 empty] | Applications/Tools | OPEN | [10 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
16 | T15 | 472 | NA |  |  |  | BSS | Development and unit testing | SMS notification, email gateway, Field engineer mobile app readiness |  |  | Open |  |  | 29-08-2025: Integration is already completed and applicable for all product same has demonstrated to TFIBER during GIBB demo session. 26-06-2025: Artifacts submitted. Closure review is pending with TFIBER | [12 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
17 | T16 | 472 | NA |  |  |  | BSS | Development and unit testing | Service Assurance and trouble tickets |  |  | Open |  |  | 29-08-2025: Integration with Service Manager is done for technical ticket and BSS have functionality to handle the non-technical ticket in BSS itself. BSS team will demonstrate this functionality to TFIBER | . S | anjay | Sir | needs to | nfirm demo d |  | ate | . 2 |  |  | 2025-06-06 | -2025: Artifacts submitted. Closure review is pending with TFIBER | Applications/Tools | OPEN | [10 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
18 | T17 | 472 | NA |  |  |  | BSS | Development and unit testing | Customer Self care portal development for T-CELL, T-NET, L0 |  |  | Open |  |  | 29-08-2025: Webportal is available. BSS team needs to demonstrate to TFIBER team. Sanjay Sir needs to confirm demo date. 26-06-2025: Artifacts submitted. Closure review is pending with TFIBER | [12 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
19 | T18 | 472 | NA |  |  |  | BSS | Integration | Integration modules Like on board Un-Assist & dependent module to be completed for all products from system to be initiated a workshop and to be closed in next 2 Weeks |  |  | Open |  |  | 29-08-2025: Seek input from Business team (Uday) and deploy post assisted completion. 26-06-2025: Input awaited from TFIBER | [12 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
20 | T19 | 472 | NA |  |  |  | BSS | MoM Action | T-Cell service definition for workflow implementation in BSS for creating Spoke primary and secondary |  |  | Open |  |  | 29-08-2025:Update product concept note similar to GIBB and share with TFIBER for review 26-06-2025: We can deliver this post getting product concept note from TFIBER | [12 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
21 | T20 | 472 | NA |  |  |  | BSS | Development and unit testing | Rules for primary and secondary spoke implementation in BSS- - GP with shortest distance will be primary - To display dropdown and concerned user group to select and confirm |  |  | Open |  |  | #N/A | [12 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
22 | T21 | 472 | NA |  |  |  | BSS | MoM Action | BSS firewall ports required for Security compliance |  |  | Open |  |  | BSS has to forward list of Port as per deiffrent modules of application | [12 empty] | Applications/Tools | Closed | [8 empty] | 2025-11-01 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\NW-Security\T21_31-Oct-25.pdf | Closed | Closed After 14-Oct | Open
23 | T22 | 472 | NA |  |  |  | BSS | Security | Roadmap for password policy implementation in CSP |  |  | Open |  |  | Ciriteria for Paswword policy hase been Shared wioth BSS team . BSS team has to implement and submit report for verifications. 30-Oct-25: Ciriteria for Paswword policy hase been Shared wioth BSS team . BSS | te | am ha | s to | implemen | nd submit re |  | por | t f |  |  | or v | erifications. Point to be moved to BSS | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
24 | T23 | 472 | NA |  |  |  | BSS | Security | DMZ requirements for CSP |  |  | Open |  |  | IP amd URL required by BSS foir NAT through DMZ has been Completed | [12 empty] | Applications/Tools | Closed | [8 empty] | 2025-11-01 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\NW-Security\T23_31-Oct-25.pdf | Closed | Closed After 14-Oct | Open
25 | T24 | 472 | NA |  |  |  | BSS | MoM Action | PoP location confirmation usergroup for connectivity to O&M |  |  | Open |  |  | 29-08-2025: Seek input from O&M team (Umesh) 26-06-2025: Input awaited from TFIBER | [12 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
26 | T25 | 472 | NA |  |  |  | BSS | MoM Action | Product concept note configuration in BSS queries to be shared |  |  | Open |  |  | 29-08-2025: Queries to be prepared and share with TFIBER for discussion. 17-07-2025: Business Team of TFIBER needs to finalize and confirm all product. 26-06-2025: Need Product concept note from TFIBER | [12 empty] | Applications/Tools | OPEN |  |  |  |  | BSS | [5 empty] | Open | Open | Open
27 | T26 | 472 | NA |  |  |  | BSS | MoM Action | Location id logic for NSO provisioning |  |  | Open |  |  | 29-08-2025: Ciruit ID logic PPT shared by Sivakumar, needs to use and implement in BSS. 26-06-2025: Timeline 30th July is considering NSO support is available in 2-3 days | [12 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
28 | T27 | 472 | NA |  |  |  | BSS | Integration | Tariff plan parameters viz. 5G, 4G finalisation. (BSS should capture QOS parameter & Requirements) |  |  | Open |  |  | 29-08-2025: Product Can be configured in BSS product catalogue Demo to be given to TFIBER 26-06-2025: Input awaited from TFIBER | [12 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
29 | T28 | 472 | NA |  |  |  | IP/MPLS | Functional AT | Internal AT 83% complete. Waiting Cisco to update data sent by Vikram and then we will submit to TPA ( for pending cases, we just need a maintanence window to test as it is impacting activity) This is for ISE |  |  | Open |  |  | 28-Nov-25: Document preparation in progress once done points will be closed. FAT documents were submitted to TPA , However it has some common observation which will be discussed with TPA team by Mr Sharma. | Su | bsequ | entl | y , corre | on will be m |  | ade | in |  |  | FAT | doc | IPMPLS | OPEN | [10 empty] | Open | Open | Open
30 | T29 | 472 | NA |  |  |  | IP/MPLS | Functional AT | CSM is having memory issues. Need to sort it out before we do AT. Working on settling that with Cisco. Memory will be allocated and tested in the first week of July |  |  | Open |  |  | CSM has been replaced by ASDM | [12 empty] | IPMPLS | Closed |  |  |  |  | Jayant Sir |  |  |  | 2025-10-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\NW-Security\M1145_29-Oct-25.pdf | Closed | Closed After 14-Oct | Open
31 | T30 | 472 | NA |  |  |  | IP/MPLS | Functional AT | Internal AT 72% complete. Waiting on Cisco to update data sent by Vikram and then we will submit to TPA. ( for pending cases, we just need a maintanence window to test as it is impacting activity) |  |  | Open |  |  | 28-Nov-25: Document preparation in progress once done points will be closed. FAT documents were submitted to TPA , However it has some common observation which will be discussed with TPA team by Mr Sharma. | Su | bsequ | entl | y , corre | on will be m |  | ade | in |  |  | FAT | doc | IPMPLS | OPEN | [10 empty] | Open | Open | Open
32 | T31 | 472 | NA |  |  |  | Security & Regulatory Compliance | Security | Internal Audit for all applications |  |  | Open |  |  | 28-Nov-25: VAPT is going on, once VAPT is done points will be closed. Application audited partally , howver PT audit couldnot be done due to lack of necessary tools. Same has been requested with LTTS team | , b | ut it | cou | ld not be | terialised. | [7 empty] | Security | OPEN | [10 empty] | Open | Open | Open
33 | T32 | 472 | NA |  |  |  | Security & Regulatory Compliance | Security | Internal audit for network elements |  |  | Open |  |  | 28-Nov-25: VAPT is going on, once VAPT is done points will be closed. Network elemants auditted including NOC end points , However PT for same is pending. | [12 empty] | Security | OPEN |  |  |  |  | Venkatesh | [5 empty] | Open | Open | Open
34 | T33 | 472 | NA |  |  |  | BSS | Security | Security policies to evolve related to DOT/CDOT etc |  |  | Open |  |  | 29-08-2025: Collect data from Sivakumar and read user to access the data by DOT. 26-06-2025: Waiting for inputs for multiple deliverables | [12 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
35 | T34 | 472 | NA |  |  |  | IP/MPLS | Security | external Audit for all applications (Tfiber will be arranging a partner for third party audit) |  |  | Open |  |  | 28-Nov-25: VAPT is going on, once VAPT is done points will be closed. Awaited TSTG Audit party to engage. | [12 empty] | IPMPLS | OPEN | [8 empty] | 2025-12-19 |  | Completed &Approved | Closed after 14-Dec-25 | Completed &Approved
36 | T35 | 472 | NA |  |  |  | IP/MPLS | Security | external audit for network elements(Tfiber will be arranging a partner for third party audit) |  |  | Open |  |  | 28-Nov-25: VAPT is going on, once VAPT is done points will be closed. Awaited TSTG Audit party to engage | [12 empty] | IPMPLS | OPEN | [8 empty] | 2025-12-19 |  | Completed &Approved | Closed after 14-Dec-25 | Completed &Approved
37 | T36 | 472 | NA |  |  |  | Security & Regulatory Compliance | Security | Physical user access |  |  | Open |  |  | Has completed , Artefacts will be resubmitted. | [12 empty] | Security | Closed | [8 empty] | 2025-10-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\NW-Security\T36_28-Oct-25.pdf | Closed | Closed After 14-Oct | Open
38 | T37 | 472 | NA |  |  |  | Security & Regulatory Compliance | Security | Virtual user access-VPN |  |  | Open |  |  | Has completed , Artefacts will be resubmitted. | [12 empty] | Security | Closed |  |  |  |  | Jyothi |  |  |  | 2025-10-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\NW-Security\T37_28-Oct-25.pdf | Closed | Closed After 14-Oct | Open
39 | T38 | 472 | NA |  |  |  | Security & Regulatory Compliance | Security | Role based severity access |  |  | Open |  |  | 28-Nov-25: Work in Progress. Completed and Review pending. Artfacts submitted | [12 empty] | Security | OPEN |  |  |  |  | Jayant Sir | [5 empty] | Open | Open | Open
40 | T39 | 472 | NA |  |  |  | Security & Regulatory Compliance | Security | ISE integration with Cisco elements |  |  | Open |  |  | 28-Nov-25: Work in Progress. Artefacts will be submitted. | [12 empty] | Security | OPEN | [10 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
41 | T40 | 472 | NA |  |  |  | Security & Regulatory Compliance | Regulatory | Regulatory Compliance with respect DoT policies 1. Security Policy-Complied 2. Security Architecture of Telecom Network-Complied 3. Information Security Risk Assessment and Risk Treatment processes and their implementation plan-WIP, Target: Dec 2024 reviewed with customer. 4. Recruitment processes and employee's record-WIP, Target:12-10-2025 5. Controls for effectiveness of security management-WIP, Target: 28 -02-2025 6. Evidence of monitoring, measurement results and management reviews of security management-WIP, Target: 28-02-2025 7. Security Audit programs and audit results-Complied 8. Inventory management and classification of information assets and their handling Completed 9. Procedure for responding to information and network security incidents-WIP, Target: 28-02-2025 - SIRT reviewed 10. Main S/W updation and changes-WIP, Target: 28-02-2025 11. Supply chain of products (HW/SW). To be taken from manufacturer/supplier-Communicated to Sekhar. WIP, Target: 14-02-2025 12. SW details and documentation obtained from manufacturers/supplier-Communicated to Sekhar WIP, Target: 14-02-2025 13. O&M procedures in the form of manual-O&M manual and OEM wise manuals WIP, Target: 14-02-2025 14. Processes for internal and external communication relevant to the security management-WIP, Target: 07-3-2025 |  |  | Open |  |  | 28-Nov-25: Document preparation in progress once done points will be closed. Confirmation of purchase of ISE. License needed to upgrade for HA | [12 empty] | Security | OPEN | [10 empty] | Open | Open | Open
42 | T41 | 472 | NA |  |  |  | DC-IT | Servers and Strorage (Deployment and Installations) | 1. Compute & Storage |  |  | Open |  |  | 11-Oct-25: As per the OEM's/SME's request, storage is allocated as per requirements. Artifacts are Captured. OEM Confirmation Emails to be captured as a Reference. | [12 empty] | Network | OPEN | [10 empty] | Open | Open | Open
43 | T42 | 472 | NA |  |  |  | DC-IT | Servers and Strorage (Deployment and Installations) | 2. Virtulization |  |  | Colosed | [15 empty] | Network | Closed | [8 empty] | 2025-05-14 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\DC IT-Infra\Artifact for -T42 | Completed & Approved | Closed before june-2025 | Closed before june-2025
44 | T43 | 472 | NA |  |  |  | DC-IT | Servers and Strorage (Deployment and Installations) | 3. Anti-virus |  |  | Colosed | [15 empty] | Network | Closed | [8 empty] | 2025-05-14 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\DC IT-Infra\Artifact for -T43 | Completed & Approved | Closed before june-2025 | Closed before june-2025
45 | T44 | 472 | NA |  |  |  | DC-IT | Servers and Strorage (Deployment and Installations) | 4. VM's Deployment Application Installations |  |  | Colosed | [15 empty] | Network | Closed | [8 empty] | 2025-05-14 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\DC IT-Infra\Artifact for -T44 | Completed & Approved | Closed before june-2025 | Closed before june-2025
46 | T45 | 472 | NA |  |  |  | DC-IT | Commvault Backup | Application Installation |  |  | Colosed | [15 empty] | Network | Closed | [8 empty] | 2025-05-14 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\DC IT-Infra\Artifact for - T45 | Completed & Approved | Closed before june-2025 | Closed before june-2025
47 | T46 | 472 | NA |  |  |  | DC-IT | Commvault Backup | Application Configuration |  |  | Colosed | [15 empty] | Network | Closed | [8 empty] | 2025-05-14 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\DC IT-Infra\Artifact for - T46 | Completed & Approved | Closed before june-2025 | Closed before june-2025
48 | T47 | 472 | NA |  |  |  | DC-IT | Commvault Backup | Application Installation AT |  |  | Colosed | [15 empty] | Network | Closed | [8 empty] | 2025-05-14 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\DC IT-Infra\Artifact for - T47 | Completed & Approved | Closed before june-2025 | Closed before june-2025
49 | T48 | 472 | NA |  |  |  | DC-IT | Commvault Backup | Application Functional AT |  |  | Open |  |  | Working on the Extra Test cases which are received from the TPA & T-Fiber. | [12 empty] | Network | OPEN |  |  |  |  | Jyothi | [5 empty] | Open | Open | Open
50 | T49 | 472 | NA |  |  |  | DC-IT | LLD | LLD Approved conditionally with few punch points. Updated LLD to be submitted |  |  | Open |  |  | Working on DC IT-Infra Server and storage-MoM Points received from the T-Fiber. | [12 empty] | Network | OPEN |  |  |  |  | Jyothi | [5 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
51 | T50 | 472 | NA |  |  |  | DC-IT | MoM Action | Radware , A10 Configuration file needed to be shared to RaviKishore |  |  | Open |  |  | Artfacts submitted . point Closure on 10 Jul 25 | [12 empty] | Network | Closed | [9 empty] | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\NW-Security\T50 | Completed & Approved | Closed before june-2025 | Closed after June
52 | T51 | 472 | NA |  |  |  | DC-IT | Commvault Backup | Backup retention and Backup activity (such as when incremental backup,full backup are scheduled and time duration required to complete such backup). Application Wise Backup Retention should be as per DOT Guidelines |  |  | Colosed | [15 empty] | Network | Closed | [8 empty] | 2025-05-14 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\DC IT-Infra\Artifact for - T51 | Completed & Approved | Closed before june-2025 | Closed before june-2025
53 | T52 | 472 | NA |  |  |  | DC-IT | Commvault Backup | Backup solution should have hot , cold and archieve storage inorder to decrease the backup size/capacity in long run. |  |  | Colosed | [15 empty] | Network | Closed | [8 empty] | 2025-05-14 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\DC IT-Infra\Artifact for - T52 | Completed & Approved | Closed before june-2025 | Closed before june-2025
54 | T53 | 472 | NA |  |  |  | DC-IT | SSD storage migration – EPNM/PI | EPNM/PI VMs migration to SSD Storage |  |  | Colosed | [15 empty] | Network | Closed | [8 empty] | 2025-05-14 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\DC IT-Infra\Artifact for - T53 | Completed & Approved | Closed before june-2025 | Closed before june-2025
55 | T54 | 472 | NA |  |  |  | DC-IT | SSD storage migration – ISE/FMC | ISE & FMC VMs migration to SSD Storage |  |  | Colosed | [15 empty] | Network | Closed |  |  |  |  | kartheek |  |  |  | 2025-05-14 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\DC IT-Infra\Artifact for - T54 | Completed & Approved | Closed before june-2025 | Closed before june-2025
56 | T55 | 472 | NA |  |  |  | DC-IT | MoM Action | VM Placing should be verified & rectified, Same service VM needs to be placed in different Physical Server/host. |  |  | Colosed | [15 empty] | Network | Closed | [8 empty] | 2025-05-14 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\DC IT-Infra\Artifact for - T55 | Completed & Approved | Closed before june-2025 | Closed before june-2025
57 | T56 | 472 | NA |  |  |  | DC-IT | MoM Action | SOP documents needs to be provided |  |  | Open |  |  | SOP documents submitted to Operations team. Remaining pending documents to be prepared periodically. | [12 empty] | Network | OPEN | [10 empty] | Open | Open | Open
58 | T57 | 472 | NA |  |  |  | DC-IT | LLD | Approved conditionally with few punch points. Updated LLD to be submitted |  |  | Open |  |  | 14-Aug-25 : Discussion was done with TPA and Tfiber and submitted updated LLD document. 18-Jun-25 : Updated DC Network LLD submitted on 18-Jun-25 for TFiber review | [12 empty] | Network | Closed | [8 empty] | 2025-08-14 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\DC Network LLD V1.7 14-Aug-2025.pdf | Completed & Approved | Closed before june-2025 | Closed after June
59 | T58 | 472 | NA |  |  |  | DC-IT | Cisco EPNM | Cisco EPNM infrastructure AT |  |  | Open |  |  | 22-Sep-25: IPMPLS Domain team to submit detailed remarks on raised queries. 08-Jul-2025 - Sandeep will come back by EoD today on extension of Cisco support renewal 01-Jul-25 : Revised FAT documents submiss | ion | pend | ing | (TPA obs | ations to be |  | in | clu |  |  | ded) | OEM(Cisco) suport is required to show the new test cases, Inputs provided to OEM on 14th May & 30th Jun. OEM onboarding is in progress & LnT Contracts team coordinating | Network | OPEN |  |  |  |  | erv | [5 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
60 | T59 | 472 | NA |  |  |  | DC-IT | Cisco PI | Cisco prime infrastructure AT |  |  | Open |  |  | 22-Sep-25: IPMPLS Domain team to submit detailed remarks on raised queries. 08-Jul-2025 - Sandeep will come back by EoD today on extension of Cisco support renewal 01-Jul-25 : Revised FAT documents submiss | ion | pend | ing | (TPA obs | ations to be |  | in | clu |  |  | ded) | OEM(Cisco) suport is required to show the new test cases, Inputs provided to OEM on 14th May & 30th Jun. OEM onboarding is in progress & LnT Contracts team is coordinating | Network | OPEN |  |  |  |  | erv | [5 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
61 | T60 | 472 | NA |  |  |  | DC-IT | NTP | Installation |  |  | Colosed | [15 empty] | Network | Closed | [8 empty] | 2025-05-05 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\Primary NTP - T60,T61,T62.pdf \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\Secondary NTP - T60,T61,T62.pdf | Completed & Approved | Closed before june-2025 | Closed before june-2025
62 | T61 | 472 | NA |  |  |  | DC-IT | NTP | Configuration |  |  | Colosed | [15 empty] | Network | Closed | [8 empty] | 2025-05-05 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\Primary NTP - T60,T61,T62.pdf \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\Secondary NTP - T60,T61,T62.pdf | Completed & Approved | Closed before june-2025 | Closed before june-2025
63 | T62 | 472 | NA |  |  |  | DC-IT | NTP | NTP Installation AT |  |  | Colosed | [15 empty] | Network | Closed | [8 empty] | 2025-05-05 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\Primary NTP - T60,T61,T62.pdf \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\Secondary NTP - T60,T61,T62.pdf | Completed & Approved | Closed before june-2025 | Closed before june-2025
64 | T63 | 472 | NA |  |  |  | DC-IT | NTP | NTP Functional AT |  |  | Open | [15 empty] | Network | Closed | [8 empty] | 2025-07-03 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\NTP FAT & Acceptance - T63.pdf | Completed & Approved | Closed before june-2025 | Closed after June
65 | T64 | 472 | NA |  |  |  | DC-IT | Functional AT | DC Network Infra AT |  |  | Open |  |  | 22-Sep-25: IPMPLS Domain team to submit detailed remarks on raised queries. 08-Jul-2025 - Sandeep will come back by EoD today on extension of Cisco support renewal 01-Jul-25 : Revised FAT documents submiss | ion | pend | ing | (TPA obs | ations to be |  | in | clu |  |  | ded) | OEM(Cisco) suport is required to show the new test cases, Inputs provided to OEM on 14th May & 30th Jun. OEM onboarding is in progress & LnT Contracts team is coordinating | Network | OPEN |  |  |  |  | erv | [5 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
66 | T65 | 472 | NA |  |  |  | DR | Servers and Strorage (Deployment and Installations) | Virtulization |  |  | Colosed | [15 empty] | DR | Closed | [8 empty] | 2025-05-14 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\DR\Artifact for - T65 | Completed & Approved | Closed before june-2025 | Closed before june-2025
67 | T66 | 472 | NA |  |  |  | DR | DC (TNOC-DR) | Network Readiness |  |  | Colosed | [15 empty] | DR | Closed | [8 empty] | 2025-05-14 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\DR\Artifact for - T66 | Completed & Approved | Closed before june-2025 | Closed before june-2025
68 | T67 | 472 | NA |  |  |  | DR | Mahbubnagar-DR | Network Readiness |  |  | Colosed | [15 empty] | DR | Closed | [8 empty] | 2025-05-14 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\DR\Artifact for - T66 | Completed & Approved | Closed before june-2025 | Closed before june-2025
69 | T68 | 472 | NA |  |  |  | DR | Design & Documentation | LLD: Approved conditionally with few punch points. Updated LLD to be submitted |  |  | Open |  |  | Working on additional points shared by Tfiber. | [12 empty] | DR | OPEN | [10 empty] | Open | Open | Open
70 | T69 | 472 | NA |  |  |  | DR | Design & Documentation | HLD: Revised solution to submitted |  |  | Open |  |  | Working on additional points shared by Tfiber. | [12 empty] | DR | OPEN | [10 empty] | Open | Open | Open
71 | T70 | 472 | NA |  |  |  | DR | Design & Documentation | DC-DR redunancy Test |  |  | Colosed | [15 empty] | DR | Closed | [8 empty] | 2025-05-14 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\DR\Artifact for - T70 | Completed & Approved | Closed before june-2025 | Closed before june-2025
72 | T71 | 472 | NA |  |  |  | DR | MoM Action | UTM Features (DR FW) |  |  | Open |  |  | Meeting scheduled with CTRL S to verify the UTM features 30-Oct-25: Duplicate to Point T71. DR does not have a public-facing application, and DR and DC firewalls are different | [12 empty] | DR | Closed | [8 empty] | 2025-11-01 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\NW-Security\T71_31-Oct-25.pdf | Completed & Approved | Closed After 14-Oct | Open
73 | T72 | 472 | NA |  |  |  | DR | MoM Action | To configure LACP between L3 Switch and Core Router |  |  | Open |  |  | 11-Oct-25: CtrlS has to give proposal for procurement for addtional BoQ. IT infra SME need to Re-intiate a mail to get BoQ 22-Sep-25: The existing switch which was placed at DR by CtrlS doesnt have feature | on | LACP | Bun | dling. Ct | is planning |  | to | re |  |  | lpla | ce the exising switch with LACP supported switch. DC Infra admin need to provide tentative timelines for replacement. 08-Jul-2025 Sandeep will ensure on CTRL-S support and update by EoD 01-Jul-25 : Ticket (SR01301726) raised with CtrlS on 27-Jun, Config & testing to be carried out. This is additional task as per CtrlS and commercials may be involved. LnT Contracts team also talking to CtrlS account team to complete the task. 24-Dec-25 : SR01036770 opened with CtrlS for LACP configuration and it is not O&M activity as per CtrlS ops. team. escalated to LnT Contracts team for supoort. | DR | OPEN |  |  |  |  | rlS | [5 empty] | Open | Open | Open
74 | T73 | 472 | NA |  |  |  | DR | MoM Action | To configure LACP between Core Router and Firewall |  |  | Open |  |  | 11-Oct-25: CtrlS has to give proposal for procurement for addtional BoQ. IT infra SME need to Re-intiate a mail to get BoQ 22-Sep-25: The existing switch which was placed at DR by CtrlS doesnt have feature | on | LACP | Bun | dling. Ct | is planning |  | to | re |  |  | lpla | ce the exising switch with LACP supported switch. DC Infra admin need to provide tentative timelines for replacement. 01-Jul-25 : Ticket (SR01301726) raised with CtrlS on 27-Jun, Config & testing to be carried out. This is additional task as per CtrlS and commercials may be involved. LnT Contracts team also talking to CtrlS account team to complete the task. 24-Dec-25 : SR01036770 opened with CtrlS for LACP configuration and it is not O&M activity as per CtrlS ops. team. escalated to LnT Contracts team for supoort. | DR | OPEN |  |  |  |  | rlS | [5 empty] | Open | Open | Open
75 | T74 | 472 | NA |  |  |  | DR | MoM Action | To configure LACP between Firewall and L2 Switch |  |  | Open |  |  | 11-Oct-25: CtrlS has to give proposal for procurement for addtional BoQ. IT infra SME need to Re-intiate a mail to get BoQ 22-Sep-25: The existing switch which was placed at DR by CtrlS doesnt have feature | on | LACP | Bun | dling. Ct | is planning |  | to | re |  |  | lpla | ce the exising switch with LACP supported switch. DC Infra admin need to provide tentative timelines for replacement. 01-Jul-25 : Ticket (SR01301726) raised with CtrlS on 27-Jun, Config & testing to be carried out. This is additional task as per CtrlS and commercials may be involved. LnT Contracts team also talking to CtrlS account team to complete the task. 24-Dec-25 : SR01036770 opened with CtrlS for LACP configuration and it is not O&M activity as per CtrlS ops. team. escalated to LnT Contracts team for supoort. | DR | OPEN |  |  |  |  | rlS | [5 empty] | Open | Open | Open
76 | T75 | 472 | NA |  |  |  | DR | MoM Action | To confirm on backups for DR Virtual machines |  |  | Colosed | [15 empty] | DR | Closed | [8 empty] | 2025-05-14 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\DR\Artifact for - T75 | Completed & Approved | Closed before june-2025 | Closed before june-2025
77 | T76 | 472 | NA |  |  |  | DR | MoM Action | Backup storage to 25 TB |  |  | Colosed | [15 empty] | DR | Closed | [8 empty] | 2025-05-14 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\DR\Artifact for - T76 | Completed & Approved | Closed before june-2025 | Closed before june-2025
78 | T77 | 472 | NA |  |  |  | DR | MoM Action | To submit the SOPs for DC-DR switchover, DC-DR failover and failback |  |  | Open |  |  | Tejas, Nokia, GIS & Ciena MCP documnets are received. Remaining all Applications domains SOP's to be updated. | [12 empty] | DR | OPEN | [10 empty] | Open | Open | Open
79 | T78 | 472 | NA |  |  |  | DR | MoM Action | to monitor the DR Servers |  |  | Open |  |  | DR servers monitoring through DR vCentre happening. DR is maintained by CtrlS team as per contract. Feasibility to be checked to integrated through OSS OBM. | [12 empty] | DR | OPEN | [10 empty] | Open | Open | Open
80 | T79 | 472 | NA |  |  |  | DR | MoM Action | To confirm that DNS switchover between DC and DR locations should be automatic |  |  | Colosed | [15 empty] | DR | Closed | [8 empty] | 2025-05-14 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\DR\Artifact for - T79 | Completed & Approved | Closed before june-2025 | Closed before june-2025
81 | T80 | 472 | NA |  |  |  | DR | MoM Action | Mahubnagar as NTP |  |  | Colosed | [15 empty] | DR | Closed | [8 empty] | 2025-05-05 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\Primary NTP - T60,T61,T62.pdf \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\Secondary NTP - T60,T61,T62.pdf | Completed & Approved | Closed before june-2025 | Closed before june-2025
82 | T81 | 472 | NA |  |  |  | DR | Configuration | All application to be migrated to implement DR LB configuration |  |  | Open |  |  | 11-Oct-25: Approved DR HLD document to be shared with T Fiber for further discussion. Noikia app is integrated with DR LB . Balance application migration on DR LB is in Pipeline | [12 empty] | DR | OPEN | [10 empty] | Open | Open | Open
83 | T82 | 472 | NA |  |  |  | DR | MoM Action | To confirm the applications which support Veem Replication for Reconfiguration |  |  | Colosed | [15 empty] | DR | Closed | [8 empty] | 2025-05-14 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\DR\Artifact for - T82 | Completed & Approved | Closed before june-2025 | Closed before june-2025
84 | T83 | 472 | NA |  |  |  | DWDM | Network Deployment & integration | Zonal Links Integration (12/15) |  |  | Open |  |  | 20-Sep-25: Nirmal, Jainoor, Gudihatnoor & Bhimni RFE pending due to forest permission 31-July-2025:As per discussion with Ramanaiah sir, need to discuss these points with T Fiber Project team for furthe | r a | ction | , ti | ll that t | this point |  | kep | t o |  |  | n ho | ld Depend on 04 Facilities RFE in Pkg-C Asifabad - Warangal & Karimnagar - Asifabad - Links integrated as per interim plan, actual integration pending Nizamabad - Asifabad - E2E link integration pending 28th-Apr'25: As per Sandeep Sanmani - Forest permission still pending 6/25/2025: Status is same no visibility on forest permission, Target date would be D+21 05-July-25: No progress on the forest permission | DWDM | OPEN |  |  |  |  | ime | [5 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
85 | T84 | 472 | NA |  |  |  | DWDM | Network Deployment & integration | Nodes Live & Operational (67/71) |  |  | Open |  |  | 31-July-2025:As per discussion with Ramanaiah sir, need to discuss these points with T Fiber Project team for further action, till that time this point kept on hold Nirmal, Jainoor, Gudihatnoor & Bhimni RF | E p | endin | g du | e to fore | permission |  | 28 | th- |  |  | Apr' | 25: As per Sandeep Sanmani - Forest permission still pending 15-06-25: No progress on the permission, target - D+15 05-July-25: No progress on the forest permission | DWDM | OPEN |  |  |  |  | st | [5 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
86 | T85 | 472 | NA |  |  |  | DWDM | Network Deployment & integration | Zonal Rings readiness with 1+R protection (5/7) |  |  | Open |  |  | 31-July-2025:As per discussion with Ramanaiah sir, need to discuss these points with T Fiber Project team for further action, till that time this point kept on hold 02 rings depend on 04 Facilities RFE re | adi | ness | in P | kg-C, whi | is pending d |  | ue | to |  |  | fore | st permission 28th-Apr'25: As per Sandeep Sanmani - Forest permission still pending 6/25/2025: No visibility on forest permission, target date would be D+30 05-July-25: No progress on the forest permission | DWDM | OPEN |  |  |  |  | ch | [5 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
87 | T86 | 472 | NA |  |  |  | DWDM | Network Deployment & AT Status | Nodal AT (67/71) |  |  | Open |  |  | 31-July-2025:As per discussion with Ramanaiah sir, need to discuss these points with T Fiber Project team for further action, till that time this point kept on hold Nirmal, Jainoor, Gudihatnoor & Bhimni RF | E p | endin | g du | e to fore | permission |  | 28 | th- |  |  | Apr' | 25: As per Sandeep Sanmani - Forest permission still pending 15-06-25: No progress on the permission, target - D+15 05-July-25: No progress on the forest permission | DWDM | OPEN |  |  |  |  | st | [5 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
88 | T87 | 472 | NA |  |  |  | DWDM | Network Deployment & integration | Mandal Ring Integration through OADM |  |  | Open |  |  | 31-July-2025:As per discussion with Ramanaiah sir, need to discuss these points with T Fiber Project team for further action, till that time this point kept on hold Mandal services are provisioned (10G) as | pe | r int | egra | tion plan | all package |  | s 6 | /25 |  |  | /202 | 5: 203 services provisioned out of 270 planned. Remaining can be provisioned as per the requirement | DWDM | OPEN |  |  |  |  | by | [5 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
89 | T88 | 472 | NA |  |  |  | DWDM | Network Deployment & AT Status | Zonal Link AT (7/15) |  |  | Open |  |  | 31-July-2025:As per discussion with Ramanaiah sir, need to discuss these points with T Fiber Project team for further action, till that time this point kept on hold 04 Link AT's approved by T Fiber and 03 | Lin | k AT' | s pe | nding due | letter from |  | Ci | ena |  |  | awa | ited (No impact due to ILA to OADM upgradation) 05 Link AT pending due to high losses in the spans, depend on all packages 02 Links integrated as per interim plan, so not considered for Link AT 20May'25: Declaration letter submitted to T Fiber for 03 links AT approval 25-06-2025: Dependancy on field, no progress. 30-June-2025: As discussed in the meeting, need to arrange meeting with all stakeholders | DWDM | OPEN |  |  |  | 20-Sep-25: Mr.Suresh will update the status | to | [5 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
90 | T89 | 472 | NA |  |  |  | DWDM | Design & Documentation | HLD (Revised) with OADM Solution |  |  | Colosed | [15 empty] | DWDM | Closed | [8 empty] | 2025-05-06 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\DWDM\Artefact - T89 | Completed & Approved | Closed before june-2025 | Closed before june-2025
91 | T90 | 472 | NA |  |  |  | DWDM | Design & Documentation | LLD (Revised) with OADM Solution (Ciena) |  |  | Colosed | [15 empty] | DWDM | Closed | [8 empty] | 2025-05-06 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\DWDM\Artefact - T90 | Completed & Approved | Closed before june-2025 | Closed before june-2025
92 | T91 | 472 | NA |  |  |  | DWDM | Design & Documentation | Nodal ATP |  |  | Colosed | [15 empty] | DWDM | Closed | [8 empty] | 2025-05-06 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\DWDM\Artefact - T91 & T92 | Completed & Approved | Closed before june-2025 | Closed before june-2025
93 | T92 | 472 | NA |  |  |  | DWDM | Design & Documentation | Link ATP |  |  | Colosed | [15 empty] | DWDM | Closed | [8 empty] | 2025-05-06 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\DWDM\Artefact - T91 & T92 | Completed & Approved | Closed before june-2025 | Closed before june-2025
94 | T93 | 472 | NA |  |  |  | DWDM | Design & Documentation | Ring ATP |  |  | Colosed | [15 empty] | DWDM | Closed | [8 empty] | 2025-05-06 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\DWDM\Artefact - T93 | Completed & Approved | Closed before june-2025 | Closed before june-2025
95 | T94 | 472 | NA |  |  |  | DWDM | Design & Documentation | DWDM EMS (MCP) Functional ATP |  |  | Open |  |  | 20-Sep-25: MCP FAT document submitted to TPA on XX-XX-XXXX. Meeting need to be scheduled on 22-Sep-25 with TPA to get the clarifications on delay. 13-Sep-25: Response awaited from TPA team 29-August-2025: | Sp | oken | with | Mr. Bijj | response awa |  | ite | d 2 |  |  | 6-Ju | ly-25: FAT document approval pending 08-July-2025: 1. MCP FAT document prepared as per RFP requirements and TPA remarks 2. 100G traffic throughput will be shown during Ring ATP 07-July-2025: 1. SME not aware of MCP FAT Check list, but prepared FAT document and sent to TPA for validation 05-July-2025: Submitted AT document to T Fiber TPA 30-June-2025: target to submit by 2nd July'25, based on OEM reply Revised version to be submitted as per T Fiber remarks on 29th Apr'25 | DWDM | OPEN |  |  |  | Pending from TPA | u, | [5 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
96 | T95 | 472 | NA |  |  |  | DWDM | Integration with OSS | DWDM Network Alarms Integration |  |  | Colosed | [15 empty] | DWDM | Closed | [8 empty] | 2025-05-06 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\DWDM\Artefact - T95 | Completed & Approved | Closed before june-2025 | Closed before june-2025
97 | T96 | 472 | NA |  |  |  | DWDM | Integration with OSS | Hardware Inventory Integration in HPE OSS |  |  | Colosed | [15 empty] | DWDM | Closed | [8 empty] | 2025-05-06 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\DWDM\Artefact - T96 | Completed & Approved | Closed before june-2025 | Closed before june-2025
98 | T97 | 472 | NA |  |  |  | DWDM | Integration with OSS | DWDM Network Topology |  |  | Open |  |  | 11-Nov-25: 26-July-2025: HPE conveyed that Topology border unable to make bold or hilight 12-July-2025: Update awaited from HPE 07-July-2025: Topology is visible but border is not highlighted. HP checking | fo | r the | pos | sibility | impose of bo |  | rde | r m |  |  | ap o | n topology. Required 02 weeks post confirmation 05-July-2025: In discussion with HPE, required 02 weeks post confirmation, 21st July 30-June-2025: As discussed with Suresh P checking with HPE. Tentative date: 16th July. As discussed in the meeting, call to be arranged along with OSS SME and HP team | DWDM | OPEN |  |  |  |  | to | [5 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
99 | T98 | 472 | NA |  |  |  | DWDM | Integration with OSS | Auto Ticket & RCA for Fiber Cuts |  |  | Colosed | [15 empty] | DWDM | Closed | [8 empty] | 2025-05-06 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\DWDM\Artefact - T98 | Completed & Approved | Closed before june-2025 | Closed before june-2025
100 | T99 | 472 | NA |  |  |  | DWDM | Integration with OSS | Auto Ticket & RCA for Hardware Failures |  |  | Open | [15 empty] | DWDM | Closed | [9 empty] | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\DWDM\Artefact - T99 | Completed & Approved | Closed before june-2025 | Closed after June
101 | T100 | 472 | NA |  |  |  | DWDM | Integration with OSS | Auto Ticket & RCA for Infra Failures |  |  | Open |  |  | 20-Sep-25: Required configuration changes was done by HPE team. DWDM team will validate and confirm by 23-Sep-25 13-09-25: Few issues observed, corrected by HP. Validation is in progress 10-08-2025: HP t | eam | conf | irme | d cause o | ailure updat |  | ed, | va |  |  | lida | tion is in progress 26-July-2025: Raised the concerns to HP team, cause of failure yet to update by them, Target date awaited9 12-July-2025: Configuration updated in production and RCA TT's for node down are generating. But having issue in cause of failure, same informed to HP team. Target date - 18-07-25 05-July-2025: Cofiguration in production planned on 8th July'25 30-June-25: WIP with HPE, target date 09-07-25 As discussed in the meeting, call to be arranged along with OSS SME and HP team 15-06-2025: WIP with HPE, target date 30-06-2025 21-05-2025: RCA Yet to be started by HPE, date: 30th June 2025 30APR'25: Node down Auto TT is ok but RCA pending | DWDM | Closed |  |  |  |  | f f |  |  |  | 2025-09-23 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\DWDM\Artefact 100 | Completed & Approved | Closed before june-2025 | Closed after June
102 | T101 | 472 | NA |  |  |  | DWDM | Integration with OSS | Network and service performance monitoring KPIs report in HPE OSS |  |  | Colosed | [15 empty] | DWDM | Closed | [8 empty] | 2025-05-06 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\DWDM\Artefact - T101 | Completed & Approved | Closed before june-2025 | Closed before june-2025
103 | T102 | 472 | NA |  |  |  | DWDM | Integration with OSS | Bandwidth Utilization Data in HPE OSS |  |  | Colosed | [15 empty] | DWDM | Closed | [8 empty] | 2025-05-06 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\DWDM\Artefact - T102 | Completed & Approved | Closed before june-2025 | Closed before june-2025
104 | T103 | 472 | NA |  |  |  | DWDM | Integration with OSS | Service Inventory Data Availibilty in HPE OSS |  |  | Open |  |  | 11-Nov-25: As per OSS SME Mr. manoj this task would be completed by 13-Nov-25 in TND based on test result shall move to production. Post 24.06.25 review and direction, working for a alternate options for N | SO. | will | com | e back as | rliest with |  | clo | sur |  |  | e pl | an. | DWDM | OPEN |  |  |  |  | ea | [5 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
105 | T104 | 472 | NA |  |  |  | DWDM | Integration with OSS | Planned Event Service Impact analysis report |  |  | Open |  |  | 11-Nov-25: Once Service inventory(Unique ID: T103) is ready, same can be used for impact Analysis Post 24.06.25 review and direction, working for a alternate options for NSO. will come back as earliest wit | h c | losur | e pl | an. | [8 empty] | DWDM | OPEN | [10 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
106 | T105 | 472 | NA |  |  |  | DWDM | Integration with NSO | 1+1 , 1+0 and 1+R service provisioning testing through NSO |  |  | Open |  |  | Post 24.06.25 review and direction, working for a alternate options for NSO. will come back as earliest with closure plan. | [12 empty] | DWDM | OPEN | [10 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
107 | T108 | 472 | NA |  |  |  | GIS | Data gathering | Data Gathering for RFS Mandals |  |  | Open |  |  | 15-Nov-25: 256 Mandal uploaded and AT Completed for 250 Mandals,Ongoing & Approved | [12 empty] | Applications/Tools | Closed | [8 empty] | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T108 | Closed | Closed After 14-Oct | Open
108 | T109 | 472 | NA |  |  |  | GIS | Data gathering | Data Upload of RFS Mandals |  |  | Open |  |  | 15-Nov-25: 256 Mandal uploaded and AT Completed for 250 Mandals,Ongoing & Approved | [12 empty] | Applications/Tools | Closed | [8 empty] | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T109 | Closed | Closed After 14-Oct | Open
109 | T110 | 472 | NA |  |  |  | GIS | Basic Readiness | Each Package 5 Mandal (Total-15 Mandal) Upload |  |  | Colosed | 1 |  | As a PoC, 15 Mandals data uploaded for testing purpose | [12 empty] | Applications/Tools | Closed | [8 empty] | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T110 | Completed & Approved | Closed before june-2025 | Closed before june-2025
110 | T111 | 472 | NA |  |  |  | GIS | Deployment | GIS Hardware & Software deployment at DC |  |  | Colosed | 1 |  | HA Re-Testing Planned with TPA & TFIBER on 2nd June 2025 | [12 empty] | Applications/Tools | Closed | [8 empty] | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T111 | Completed & Approved | Closed before june-2025 | Closed before june-2025
111 | T112 | 472 | NA |  |  |  | GIS | Deployment | High Availability & Load Balancer Testing |  |  | Open |  |  | Awaiting for approval from TFIBER & TPA | [12 empty] | Applications/Tools | Closed | [8 empty] | 2025-07-07 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T112 | Completed & Approved | Closed before june-2025 | Closed after June
112 | T113 | 472 | NA |  |  |  | GIS | Deployment | PCs & Licences (G-tech, DI, Geo Media) |  |  | Open |  |  | Tool & PCs has been installed in NOC GIS room. for Licesnes dependecy on T FIber. During the meeting, the Managing Director of T-Fiber directed that only the minimum number of additional licenses will be p | roc | ured, | and | T-Fiber | l handle the |  | pr | ocu |  |  | reme | nt | Applications/Tools | Closed |  |  |  |  | wil |  |  |  | After Jun-25 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T113 | Completed & Approved | Closed before june-2025 | Closed after June
113 | T114 | 472 | NA |  |  |  | GIS | Deployment | G-Tech |  |  | Colosed | 1 | [14 empty] | Applications/Tools | Closed | [8 empty] | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T114 | Completed & Approved | Closed before june-2025 | Closed before june-2025
114 | T115 | 472 | NA |  |  |  | GIS | Deployment | Network Portal |  |  | Colosed | 1 |  | Network Portal in Production and provided by the approval NoC team but need to demonstarte for Core team | [12 empty] | Applications/Tools | Closed | [8 empty] | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T115 | Completed & Approved | Closed before june-2025 | Closed before june-2025
115 | T116 | 472 | NA |  |  |  | GIS | Deployment | Mobile App |  |  | Colosed | 1 |  | Mobile App in Production and provided by the approval NoC team but need to demonstarte for Core team | [12 empty] | Applications/Tools | Closed | [8 empty] | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T116 | Completed & Approved | Closed before june-2025 | Closed before june-2025
116 | T117 | 472 | NA |  |  |  | GIS | DC-DR | Requirement Vs Solution |  |  | Open |  |  | #N/A | [12 empty] | Applications/Tools | Closed | [8 empty] | 2025-07-09 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T117 | Completed & Approved | Closed before june-2025 | Closed after June
117 | T118 | 472 | NA |  |  |  | GIS | DC-DR | DC-DR Testing |  |  | Open |  |  | DC-DR Testing completed & Document has been kept on share drive,Awaiting TFIBER Approval | [12 empty] | Applications/Tools | Closed | [8 empty] | 2025-07-09 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T118 | Completed & Approved | Closed before june-2025 | Closed after June
118 | T119 | 472 | NA |  |  |  | GIS | Basic Readiness | Google Map API configuration |  |  | Colosed | 1 | [14 empty] | Applications/Tools | Closed | [8 empty] | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T119 | Completed & Approved | Closed before june-2025 | Closed before june-2025
119 | T120 | 472 | NA |  |  |  | GIS | Basic Readiness | Fixing of telco Boundaries in GIS |  |  | Colosed | 1 | [14 empty] | Applications/Tools | Closed | [8 empty] | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T120 | Completed & Approved | Closed before june-2025 | Closed before june-2025
120 | T121 | 472 | NA |  |  |  | GIS | Basic Readiness | Data Model Optimization |  |  | Colosed | 1 | [14 empty] | Applications/Tools | Closed | [8 empty] | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\ | Completed & Approved | Closed before june-2025 | Closed before june-2025
121 | T122 | 472 | NA |  |  |  | GIS | Basic Readiness | ISP/OSP object modelling in tool as per T-Fibre |  |  | Colosed | 1 | [14 empty] | Applications/Tools | Closed | [8 empty] | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T122 | Completed & Approved | Closed before june-2025 | Closed before june-2025
122 | T123 | 472 | NA |  |  |  | GIS | Basic Readiness | Make & Model deployment against all object as per T-Fibre Project |  |  | Colosed | 1 | [14 empty] | Applications/Tools | Closed | [8 empty] | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T123 | Completed & Approved | Closed before june-2025 | Closed before june-2025
123 | T124 | 472 | NA |  |  |  | GIS | Basic Readiness | Device (Active/Passive) ( All Type as per T-Fibre Project) & Port Modelling In Tool |  |  | Colosed | 1 | [14 empty] | Applications/Tools | Closed | [8 empty] | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\ | Completed & Approved | Closed before june-2025 | Closed before june-2025
124 | T125 | 472 | NA |  |  |  | GIS | Basic Readiness | Correction In Fttx Network placement rules (GP To GI) |  |  | Colosed | 1 | [14 empty] | Applications/Tools | Closed | [8 empty] | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\ | Completed & Approved | Closed before june-2025 | Closed before june-2025
125 | T126 | 472 | NA |  |  |  | GIS | Basic Readiness | Fine tuning or Enable of Cart feature. ( Pan, Zoom, Vertex, Selection method, ruler Etc.) |  |  | Colosed | 1 | [14 empty] | Applications/Tools | Closed | [8 empty] | 2025-06-02 | D:\T-Fiber Project\Hexagon GIS\Artefacts Of T-NOC Tracker\T126 | Completed & Approved | Closed before june-2025 | Closed before june-2025
126 | T127 | 472 | NA |  |  |  | GIS | Basic Readiness | Trace Feature ( Link/Spare/Topology) |  |  | Colosed | 1 | [14 empty] | Applications/Tools | Closed | [8 empty] | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T127 | Completed & Approved | Closed before june-2025 | Closed before june-2025
127 | T128 | 472 | NA |  |  |  | GIS | Basic Readiness | Reports (Fibre Utilisation, BOQ, Area selection, ISP/OSP Quantify) |  |  | Colosed | 1 | [14 empty] | Applications/Tools | Closed | [8 empty] | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T128 | Completed & Approved | Closed before june-2025 | Closed before june-2025
128 | T129 | 472 | NA |  |  |  | GIS | Basic Readiness | Document/Image Upload feature |  |  | Colosed | 1 | [14 empty] | Applications/Tools | Closed | [8 empty] | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\ | Completed & Approved | Closed before june-2025 | Closed before june-2025
129 | T130 | 472 | NA |  |  |  | GIS | Basic Readiness | Port level & Fibre stand lever attribute |  |  | Colosed | 1 | [14 empty] | Applications/Tools | Closed | [8 empty] | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T130 | Completed & Approved | Closed before june-2025 | Closed before june-2025
130 | T131 | 472 | NA |  |  |  | GIS | Basic Readiness | Topology Highlight feature |  |  | Colosed | 1 | [14 empty] | Applications/Tools | Closed | [8 empty] | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T131 | Completed & Approved | Closed before june-2025 | Closed before june-2025
131 | T132 | 472 | NA |  |  |  | GIS | Basic Readiness | Data Model G-TECH Alignment |  |  | Colosed | 1 | [14 empty] | Applications/Tools | Closed | [8 empty] | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T132 | Completed & Approved | Closed before june-2025 | Closed before june-2025
132 | T133 | 472 | NA |  |  |  | GIS | Basic Readiness | DI alignment as per new 35 Layer data model |  |  | Colosed | 1 | [14 empty] | Applications/Tools | Closed | [8 empty] | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\ | Completed & Approved | Closed before june-2025 | Closed before june-2025
133 | T134 | 472 | NA |  |  |  | GIS | Basic Readiness | Active to Passive, Active to active connectivity correction |  |  | Colosed | 1 | [14 empty] | Applications/Tools | Closed | [8 empty] | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T134 | Completed & Approved | Closed before june-2025 | Closed before june-2025
134 | T135 | 472 | NA |  |  |  | GIS | Basic Readiness | DI processing timing optimisation |  |  | Colosed | 1 | [14 empty] | Applications/Tools | Closed | [8 empty] | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\ | Completed & Approved | Closed before june-2025 | Closed before june-2025
135 | T136 | 472 | NA |  |  |  | GIS | Basic Readiness | Rack to Rack Connectivity |  |  | Colosed | 1 | [14 empty] | Applications/Tools | Closed | [8 empty] | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T136 | Completed & Approved | Closed before june-2025 | Closed before june-2025
136 | T137 | 472 | NA |  |  |  | GIS | Advance Readiness | Graphical Symbology deployment against all object |  |  | Colosed | 1 | [14 empty] | Applications/Tools | Closed | [8 empty] | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T137 | Completed & Approved | Closed before june-2025 | Closed before june-2025
137 | T138 | 472 | NA |  |  |  | GIS | Advance Readiness | Fixing Of Labelling (Sequencing & Attributes) |  |  | Colosed | 1 | [14 empty] | Applications/Tools | Closed | [8 empty] | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T138 | Completed & Approved | Closed before june-2025 | Closed before june-2025
138 | T139 | 472 | NA |  |  |  | GIS | Advance Readiness | Object search options to user |  |  | Colosed | 1 | [14 empty] | Applications/Tools | Closed | [8 empty] | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T139 | Completed & Approved | Closed before june-2025 | Closed before june-2025
139 | T140 | 472 | NA |  |  |  | GIS | Advance Readiness | G-tech to .shp & Kml conversion |  |  | Colosed | 1 | [14 empty] | Applications/Tools | Closed | [8 empty] | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T140 | Completed & Approved | Closed before june-2025 | Closed before june-2025
140 | T141 | 472 | NA |  |  |  | GIS | Advance Readiness | Plotting & Print Feature |  |  | Colosed | 1 | [14 empty] | Applications/Tools | Closed | [8 empty] | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T141 | Completed & Approved | Closed before june-2025 | Closed before june-2025
141 | T142 | 472 | NA |  |  |  | GIS | Advance Readiness | 4 More API from Google Map |  |  | Colosed | 1 | [14 empty] | Applications/Tools | Closed | [8 empty] | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T142 | Completed & Approved | Closed before june-2025 | Closed before june-2025
142 | T143 | 472 | NA |  |  |  | GIS | Advance Readiness | Fibre Utilisation Reports |  |  | Colosed | 1 | [14 empty] | Applications/Tools | Closed | [8 empty] | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T143 | Completed & Approved | Closed before june-2025 | Closed before june-2025
143 | T144 | 472 | NA |  |  |  | GIS | Advance Readiness | Consolidated reports from GIS |  |  | Colosed | 1 | [14 empty] | Applications/Tools | Closed | [8 empty] | 2025-06-02 | D:\T-Fiber Project\Hexagon GIS\Artefacts Of T-NOC Tracker\T144 | Completed & Approved | Closed before june-2025 | Closed before june-2025
144 | T145 | 472 | NA |  |  |  | GIS | Advance Readiness | Link trace Reports |  |  | Colosed | 1 | [14 empty] | Applications/Tools | Closed | [8 empty] | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T145 | Completed & Approved | Closed before june-2025 | Closed before june-2025
145 | T146 | 472 | NA |  |  |  | GIS | Advance Readiness | Consolidation/Customization of Dashboard feature in G-tech, Network Portal |  |  | Colosed | 1 | [14 empty] | Applications/Tools | Closed | [8 empty] | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T146 | Completed & Approved | Closed before june-2025 | Closed before june-2025
146 | T147 | 472 | NA |  |  |  | GIS | Advance Readiness | Network data availability in G-Tech & Network portal & Geo media |  |  | Colosed | 1 | [14 empty] | Applications/Tools | Closed | [8 empty] | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T147 | Completed & Approved | Closed before june-2025 | Closed before june-2025
147 | T148 | 472 | NA |  |  |  | GIS | Advance Readiness | Final Demo to customer |  |  | Colosed | 1 | [14 empty] | Applications/Tools | Closed | [8 empty] | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T148 | Completed & Approved | Closed before june-2025 | Closed before june-2025
148 | T149 | 472 | NA |  |  |  | GIS | Mobile Applications | Network availability in Mobile application with G-MAP |  |  | Colosed | 1 | [14 empty] | Applications/Tools | Closed | [8 empty] | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T149 | Completed & Approved | Closed before june-2025 | Closed before june-2025
149 | T150 | 472 | NA |  |  |  | GIS | Mobile Applications | Red line, Red Point Feature deployment in Mobile application |  |  | Colosed | 1 | [14 empty] | Applications/Tools | Closed | [8 empty] | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T150 | Completed & Approved | Closed before june-2025 | Closed before june-2025
150 | T151 | 472 | NA |  |  |  | GIS | Mobile Applications | JOB creation testing in GIS tool from GIS Mobile app |  |  | Colosed | 1 | [14 empty] | Applications/Tools | Closed | [8 empty] | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T151 | Completed & Approved | Closed before june-2025 | Closed before june-2025
151 | T152 | 472 | NA |  |  |  | GIS | Design & Documentation | Feasible Points closure of workshop |  |  | Colosed | 1 | [14 empty] | Applications/Tools | Closed | [8 empty] | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T152 | Completed & Approved | Closed before june-2025 | Closed before june-2025
152 | T153 | 472 | NA |  |  |  | GIS | Resources | Resources onboarding, Licences arrangement, Workstation plan |  |  | Open |  |  | Resource & PCs has been deployed in NOC GIS room. for Licesnes dependecy on T FIber. | [12 empty] | Applications/Tools | Closed | [8 empty] | After Jun-25 | Artefacts not Required | Completed & Approved | Closed before june-2025 | Closed after June
153 | T154 | 472 | NA |  |  |  | GIS | Data gathering | T-NOC Creation in GIS Tool with connectivity |  |  | Colosed | 1 | [14 empty] | Applications/Tools | Closed | [8 empty] | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T154 | Completed & Approved | Closed before june-2025 | Closed before june-2025
154 | T155 | 472 | NA |  |  |  | GIS | Design & Documentation | SOP Creation |  |  | Colosed | 1 | [14 empty] | Applications/Tools | Closed | [8 empty] | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T155 | Completed & Approved | Closed before june-2025 | Closed before june-2025
155 | T156 | 472 | NA |  |  |  | GIS | MoM Action | MB kilometers vs UG and arial to path and over all route length to be added in webapplication |  |  | Colosed | 1 | [14 empty] | Applications/Tools | Closed | [8 empty] | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T156 | Completed & Approved | Closed before june-2025 | Closed before june-2025
156 | T157 | 472 | NA |  |  |  | GIS | MoM Action | 3 Formats of Lat long (DMS, DMM & Mtr) required in Hexagon tool |  |  | Colosed | 1 | [14 empty] | Applications/Tools | Closed | [8 empty] | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T157 | Completed & Approved | Closed before june-2025 | Closed before june-2025
157 | T158 | 472 | NA |  |  |  | GIS | MoM Action | GIS LLD submitted to T-Fiber on 02.03.2025, to be discussed with T-Fiber |  |  | Open |  |  | 15-Nov-25: Resubmission done after discussion. Date-19.03.25. queries on LLD with mail dated 25.03.25 | [12 empty] | Applications/Tools | Closed | [8 empty] | After Jun-25 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T158 | Completed & Approved | Closed before june-2025 | Closed after June
158 | T159 | 472 | NA |  |  |  | GIS | Integration | Physical Device sync-up with OSS System |  |  | Open |  |  | 15-Nov-25:Integration with OSS Is WIP | [12 empty] | Applications/Tools | OPEN | [9 empty] | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T159 | Open | Open | Open
159 | T160 | 472 | NA |  |  |  | GIS | Integration | Common Span Path |  |  | Open |  |  | 15-Nov-25: Integration with OSS Is WIP | [12 empty] | Applications/Tools | OPEN | [9 empty] | Dependency On Physical Device Syn-up (Integration) & alarm corelation | Open | Open | Open
160 | T161 | 472 | NA |  |  |  | GIS | Integration | Auto feasibility |  |  | Open |  |  | 15-Nov-25: BSS(knot) has demonstrated the Auto Feasibility feature for single location business cases. If, Customer is expecting Bulk feasibility capabilities, which is not a feature of GIS, required exter | nal | tool | . | [9 empty] | Applications/Tools | OPEN | [10 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
161 | T162 | 472 | NA |  |  |  | GPON | Tejas-Design & Documentation | Customer Requirement Document |  |  | Colosed | [15 empty] | GPON | Closed | [8 empty] | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T162 | Completed & Approved | Closed before june-2025 | Closed before june-2025
162 | T163 | 472 | NA |  |  |  | GPON | Tejas-Design & Documentation | HLD |  |  | Colosed | [15 empty] | GPON | Closed | [8 empty] | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T163 Please refer Section-3 in E2E Network HLD | Completed & Approved | Closed before june-2025 | Closed before june-2025
163 | T164 | 472 | NA |  |  |  | GPON | Nokkia-Design & Documentation | LLD for 152 Mandals |  |  | Colosed | [15 empty] | GPON | Closed | [8 empty] | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T164 | Completed & Approved | Closed before june-2025 | Closed before june-2025
164 | T165 | 472 | NA |  |  |  | GPON | Tejas | Latest EMS Integration with OSS (Hold due to CR) |  |  | Colosed | [15 empty] | GPON | Closed | [8 empty] | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T165 | Completed & Approved | Closed before june-2025 | Closed before june-2025
165 | T166 | 472 | NA |  |  |  | GPON | Tejas | * Testing done for new build in T-Fiber test lab . * Plan event for OLTs new SW upgradation in production environment. |  |  | Open | Tejas OEM | OLT | 15-Nov-25: Below is the breakup of pending OLT status PKG-A : 430/462 PKG-B : 228/322 PKG-C : 94/165 13-Oct-25: GPON SME has to provide the breakup for all Pending OLT upgradation activities, need to send | a m | ail t | o co | ncern pac | es with resp |  | ect | ive |  |  | pen | ding OLT upgradation. 20-Sep-25: All the reachable OLT to EMS are upgraded successfully. And Not reachbale OLTs need to be upgraded, There is a dependecny on All 3 Packages field teams to make reachability to EMS. GPON SME need to submit detailed report on Scope vs upgraded and Pending devices breakup(Package wise). | GPON | OPEN |  |  |  |  | kag | [5 empty] | Open | Open | Open
166 | T167 | 472 | NA |  |  |  | GPON | Tejas | TACACS Feature |  |  | Colosed | [15 empty] | GPON | Closed | [8 empty] | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T372 | Completed & Approved | Closed before june-2025 | Closed before june-2025
167 | T168 | 472 | NA |  |  |  | GPON | Tejas | Authentication & Authorization with RAIDUS |  |  | Colosed | [15 empty] | GPON | Closed | [8 empty] | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T168 | Completed & Approved | Closed before june-2025 | Closed before june-2025
168 | T169 | 472 | NA |  |  |  | GPON | Tejas | EMS authentication & Authorization with Alepo |  |  | Colosed | [15 empty] | GPON | Closed | [8 empty] | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T169 | Completed & Approved | Closed before june-2025 | Closed before june-2025
169 | T170 | 472 | NA |  |  |  | GPON | Nokia | Accounting Feature with New build & Logs filteration |  |  | Colosed | [15 empty] | GPON | Closed | [8 empty] | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T170 | Completed & Approved | Closed before june-2025 | Closed before june-2025
170 | T171 | 472 | NA |  |  |  | GPON | Tejas | Accounting Feature with New build & Logs filteration |  |  | Colosed | [15 empty] | GPON | Closed | [8 empty] | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T170 | Completed & Approved | Closed before june-2025 | Closed before june-2025
171 | T172 | 472 | NA |  |  |  | GPON | Tejas | Tejas EMS ATP |  |  | Colosed | [15 empty] | GPON | Closed | [8 empty] | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T172 | Completed & Approved | Closed before june-2025 | Closed before june-2025
172 | T173 | 472 | NA |  |  |  | GPON | Tejas | DC-DR Switchover Activity |  |  | Colosed | [15 empty] | GPON | Closed | [8 empty] | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T173 | Completed & Approved | Closed before june-2025 | Closed before june-2025
173 | T174 | 472 | NA |  |  |  | GPON | Tejas | NBI API availability for BW query Dependent on new OLT build, which supposed to released on 31- March23. |  |  | Colosed | [15 empty] | GPON | Closed | [8 empty] | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T174 | Completed & Approved | Closed before june-2025 | Closed before june-2025
174 | T175 | 472 | NA |  |  |  | GPON | Nokia | CR for Nokia API integration to close BW query and PMS related issues |  |  | Open | Nokia OEM | AMS | 15-Nov-25: Having dependency on Service Inventory and NSO | [12 empty] | GPON | OPEN | [10 empty] | Open | Open | Open
175 | T176 | 472 | NA |  |  |  | GPON | Nokia | OLT devices status in OSS is not as per AMS. |  |  | Colosed | [15 empty] | GPON | Closed | [8 empty] | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T176 | Completed & Approved | Closed before june-2025 | Closed before june-2025
176 | T177 | 472 | NA |  |  |  | GPON | Nokia | ONT devices have been recovered and validated as per AMS count. |  |  | Colosed | [15 empty] | GPON | Closed | [8 empty] | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T177 | Completed & Approved | Closed before june-2025 | Closed before june-2025
177 | T178 | 472 | NA |  |  |  | GPON | Nokia | Authentication and authorization have been tested with Nokia devices except CB OLT. |  |  | Colosed | [15 empty] | GPON | Closed | [8 empty] | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T178 | Completed & Approved | Closed before june-2025 | Closed before june-2025
178 | T179 | 472 | NA |  |  |  | GPON | Nokia | Tejas ONT firmware upgradation not happing through Nokia OLT. Joint troubleshooting is required with Tejas and Nokia. |  |  | Colosed | [15 empty] | GPON | Closed | [8 empty] | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T179 | Completed & Approved | Closed before june-2025 | Closed before june-2025
179 | T180 | 472 | NA |  |  |  | GPON | Nokia | Nokia ONT to support NAT, DHCP, both Router and Bridge mode |  |  | Open | Nokia OEM | ONT | Nokia has provided the SOP, which has been tested and is working as expected. However, Nokia ONTs connected to Tejas OLTs cannot be enabled directly through the Tejas OLT. As discussed with TFiber, we have | pr | epare | d an | SOP for | field team |  | and | ar |  |  | e cu | rrently working on mapping the Nokia ONTs under Tejas OLTs to nearby Nokia OLTs | GPON | Closed |  |  |  |  | the |  |  |  | 2025-09-20 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T180 | Completed & Approved | Closed before june-2025 | Closed after June
180 | T181 | 472 | NA |  |  |  | GPON | Nokia | Accounting logs are forwarded to Alepo server, same was reflecting in Alepo server but it was forwarding towards syslog server. |  |  | Colosed | [15 empty] | GPON | Closed | [8 empty] | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T181 | Completed & Approved | Closed before june-2025 | Closed before june-2025
181 | T182 | 472 | NA |  |  |  | GPON | Nokia | Nokia EMS functional ATP to be closed with customer |  |  | Open | Nokia OEM | AMS | 15-Nov-25: Working with OEM 20-Sep-25: ATP document submitted to TPA, And TPA Shared 12 observations related to RFP compliance.Same has been given to OEM for closure. Nokia team provided clarifications for | 10 | poin | ts a | nd 2 poin | are WIP. GPO |  | N t | eam |  |  | has | to share clarifications of 10 points to TPA and need to confirm timelines for remaining 2 points on 23-Sep-25. | GPON | OPEN |  |  |  |  | ts | [5 empty] | Open | Open | Open
182 | T183 | 472 | NA |  |  |  | GPON | Nokia | DC-DR Switchover activity need to plan. |  |  | Colosed | [15 empty] | GPON | Closed | [8 empty] | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T183 | Completed & Approved | Closed before june-2025 | Closed before june-2025
183 | T184 | 472 | NA |  |  |  | GPON | Nokia | Nokia OLTs reachability is pending for DR Servers. |  |  | Colosed | [15 empty] | GPON | Closed | [8 empty] | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T184 | Completed & Approved | Closed before june-2025 | Closed before june-2025
184 | T185 | 472 | NA |  |  |  | IP/MPLS | Service Solution | HSI (High Speed Internet to Household) |  |  | Colosed | [15 empty] | IPMPLS | Closed | [8 empty] | 2025-05-05 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\House Hold HSI Services Design LLD V1.2 - T185.pdf | Completed & Approved | Closed before june-2025 | Closed before june-2025
185 | T186 | 472 | NA |  |  |  | IP/MPLS | Service Solution | IPTV to Household |  |  | Colosed | [15 empty] | IPMPLS | Closed | [8 empty] | 2025-05-05 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\House Hold IPTV Services Design LLD V1.2 - T186.pdf | Completed & Approved | Closed before june-2025 | Closed before june-2025
186 | T187 | 472 | NA |  |  |  | IP/MPLS | Service Solution | VOIP to Household |  |  | Colosed | [15 empty] | IPMPLS | Closed | [8 empty] | 2025-05-05 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\House Hold VoIP Services Design LLD V1.2 - t187.pdf | Completed & Approved | Closed before june-2025 | Closed before june-2025
187 | T188 | 472 | NA |  |  |  | IP/MPLS | Service Solution | Internet to GI (Govt. Institution) |  |  | Colosed | [15 empty] | IPMPLS | Closed | [8 empty] | 2025-05-05 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\T-FIBER T-Net for GI Broadband Service Design LLD V1.1 - T188.pdf | Completed & Approved | Closed before june-2025 | Closed before june-2025
188 | T189 | 472 | NA |  |  |  | IP/MPLS | Service Solution | CCTV Unicast |  |  | Colosed | [15 empty] | IPMPLS | Closed | [8 empty] | 2025-05-05 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\Centrailzed CCTV Surveillance Monitoring over T-Fiber Network-Solution Doucment_Initial Draft V1.0 - T189.pdf | Completed & Approved | Closed before june-2025 | Closed before june-2025
189 | T190 | 472 | NA |  |  |  | IP/MPLS | Service Solution | CCTV Multicast |  |  | Colosed | [15 empty] | IPMPLS | Closed | [8 empty] | 2025-05-05 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\CCTV Multicast Solution LLD V1.2 - T190.pdf | Completed & Approved | Closed before june-2025 | Closed before june-2025
190 | T191 | 472 | NA |  |  |  | IP/MPLS | Service Solution | Cell Tower L2VPN |  |  | Colosed | [15 empty] | IPMPLS | Closed | [8 empty] | 2025-05-05 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\TFIBER T-CELL Service Design & Solution V4.3 T197, T336, T337, T338.pdf | Completed & Approved | Closed before june-2025 | Closed before june-2025
191 | T192 | 472 | NA |  |  |  | IP/MPLS | Service Solution | Dhanush Telemedicine Application |  |  | Colosed | [15 empty] | IPMPLS | Closed | [8 empty] | 2025-05-05 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\T-FIBER DHANUSH TELEMEDICINE SOLUTION LLD V1.0 - T192.pdf | Completed & Approved | Closed before june-2025 | Closed before june-2025
192 | T193 | 472 | NA |  |  |  | IP/MPLS | Service Solution | SDC content to Household and GI |  |  | Open |  |  | 22-Sep-25: Need to review plan and approve 12-Sep-25 : Peering plan submitted as per discussion on 11-Sep-25 01-Jul-25 : Design document submitted with suggested approaches. Require inputs from TFiber to | co | nduct | PoC | and fina | e service de |  | sig | n. |  |  |  |  | IPMPLS | Closed |  |  |  |  | liz |  |  |  | 2025-10-31 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\T-Fiber & SDC Peering Plan V1.1 - T193 T343.pdf | Closed | Closed After 14-Oct | Open
193 | T194 | 472 | NA |  |  |  | BSS | Service Catalogue | Incremental Product/ Services finalization in T-Fiber network |  |  | Open |  |  | 01-Jul-25 : Dependecy on Tfiber in PCN (Product Concept Note) finalisation. Tracked in BSS action item T12 (part of 472 tracker) | [12 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
194 | T195 | 472 | NA |  |  |  | IP/MPLS | Service Provisioning | Service Provisioning PoC for SCCM/NSO - L2, L3 VPN |  |  | Open |  |  | Post 24.06.25 review and direction, working for a alternate options for NSO. will come back as earliest with closure plan. | [12 empty] | IPMPLS | OPEN | [10 empty] | Open | Open | Open
195 | T196 | 472 | NA |  |  |  | IP/MPLS | Service Provisioning | Service Provisioning PoC for SCCM/NSO - QoS (all scenarios) |  |  | Open |  |  | Post 24.06.25 review and direction, working for a alternate options for NSO. will come back as earliest with closure plan. | [12 empty] | IPMPLS | OPEN | [10 empty] | Open | Open | Open
196 | T197 | 472 | NA |  |  |  | IP/MPLS | Service Provisioning | Service Provisioning PoC for SCCM/NSO - MVPN (all scenarios) |  |  | Open |  |  | Post 24.06.25 review and direction, working for a alternate options for NSO. will come back as earliest with closure plan. | [12 empty] | IPMPLS | OPEN | [10 empty] | Open | Open | Open
197 | T198 | 472 | NA |  |  |  | IP/MPLS | Network AT | Simulation and testing network for parameters like network convergence etc |  |  | Open |  |  | 22-Sep-2025: Need to have discussion on Network AT parameters 8-Jul-2025 - Sandeep will come back by EoD today on extension of Cisco support renewal 01-Jul-25 : OEM(Cisco) suport is required to perform net | wor | k AT, | Inp | uts provi | to OEM. OEM |  | to | pr |  |  | ovid | e Network AT procedure including all tests and test procedures. OEM onboarding is in progress & LnT Contracts team is coordinating | IPMPLS | OPEN |  |  |  |  | ded | [5 empty] | Open | Open | Open
198 | T199 | 472 | NA |  |  |  | IP/MPLS | Design & Documentation | HLD |  |  | Colosed | [15 empty] | IPMPLS | Closed | [8 empty] | 2025-05-05 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\E2E_Network HLD_Part1_V2.0_ 29.10.2020(Approved) - T199.pdf | Completed & Approved | Closed before june-2025 | Closed before june-2025
199 | T200 | 472 | NA |  |  |  | IP/MPLS | Design & Documentation | Approved conditionally with few punch points. Updated LLD to be submitted |  |  | Open | [15 empty] | IPMPLS | Closed |  |  |  | Duplicate |  |  |  |  | 2025-08-21 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\IP MPLS Network LLD V1.7 14-Aug-2025.pdf | Completed & Approved | Closed before june-2025 | Closed after June
200 | T201 | 472 | NA |  |  |  | IP/MPLS | OSS | FMS Fault Management System (Device, Link ticketing etc) |  |  | Open |  |  | 22-Sep-25: Auto ticketing verification is depending on OSS, reqiured configguration or changes done in OSS. Now auto ticket is working atrefatcs to be submitted for Node and Link. 08-Jul-25 : Requirement g | ive | n to | OSS | for imple | tation. FMS |  | par | ame |  |  | ters | given 1. Node down (Router, Switch, DC Network Switches, DWDM, OTN, OADM, OLT, UPS) : Field alarm should be received in NNMi. NNMi has to forward the alarm to OBM, NPS and to TeMiP. UCA has to carryout correlation and accordingly pass the root cause to SM to generate TT. once TT is generated it is assigned to respective District Engineer along with mail. After Fault resolution, TT should be resolved in system with alarm clearance and NoC has to close the TT with RFO. Link down, Protocol down, RSP/Card/PSU down, High Temperature, Latency, Packet Loss, Jitter. End-to-end implementation and demonstration pending in OSS | IPMPLS | OPEN |  | Closed/Approved | FALSE |  | men | [5 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
201 | T202 | 472 | NA |  |  |  | IP/MPLS | OSS | PMS Performance Management System (Utilization, Errors etc) |  |  | Open |  |  | 25-Sep-25: Implementation completed, Need to validate and cofirm 07-Jul-25 : Requirement given to OSS for implementation. PMS parameters given - CPU, Memory, Backplane and Link utilization, CRC errors, Opt | ica | l pow | er, | QoS param | rs . End-to |  | #NAME? | d i |  |  | mple | mentation and demonstration pending in OSS | IPMPLS | OPEN |  | Completed With Artifacts | FALSE |  | ete | [5 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
202 | T203 | 472 | NA |  |  |  | IP/MPLS | OSS | Dashboard (Network Parameter Dash Boards) |  |  | Open |  |  | 25-Sep-25: Implementation completed, Need to validate and cofirm 07-Jul-25 : Requirement given to OSS for implementation. Dash Board required - Top CPU, Memory, Link utilization, Temperature, All Critical | ala | rms | . D | emonstrat | pending in |  | OSS | [5 empty] | IPMPLS | OPEN |  | OPEN | FALSE |  | ion | [5 empty] | Open | Open | Open
203 | T204 | 472 | NA |  |  |  | IP/MPLS | OSS | Reports (Invetory, Device avability, Link Availability) |  |  | Open |  |  | 25-Sep-25: Reports are available in UOC, Artefacts to be submitted for clsore 07-Jul-25 : Requirement given to OSS for implementation. Reports required - Node availability, Link availability, Link utilizat | ion | , Inv | ento | ry, CPU u | ization, Mem |  | ory | Ut |  |  | iliz | ation, Latecy. Demonstration pending in OSS | IPMPLS | Closed |  | Completed With Artifacts | FALSE |  | til |  |  |  | 2025-11-18 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\OSS\52 Artefcats_18112025 | Closed after 14-Nov-25 | Closed after 14-Nov-25 | Completed but Verification undrer Process
204 | T205 | 472 | NA |  |  |  | NSO | Installation | Installation of NSO Applications |  |  | Open |  |  | 29-12-2025:- production installation is completed . E2E demo was provided. |  |  | Installation is done. Upgradation in pending version for completion | is NSO version screenshot fine or any other req doc similar to BSS appliction (26/2/2026: updated document images in order) | 17/2/2026 | 25/02/2026 | Jyothi & Mahesh | Completed | Jayanth Madhavi | Not Approved |  |  | Applications/Tools | OPEN |  |  |  |  | Added Below Attachments - SCCM Application Login and SCCM VM Source Code - NSO Application Login and NSO VM Connectivity - NSO VM Source Code - Attached File: VM/Server Specification and Storage Utilization Report | Review Done | 27/02/2026:Need to check the status of NSO Installation if its done action point is closed or Need to check the status of NSO Upgradation status(Provide the timeline for upgradation) | 20/04/2026 |  |  | Open | Open | Open
205 | T206 | 472 | NA |  |  |  | NSO | Integration | Integration with Third Party Applications/Nodes |  |  | Open |  |  | 29-12-2025:- Completed available.E2E demo for GiBB completed.BSS/OSS completed. |  |  | master depends on 5 below points | need clarity Other than NSO remaning are 3rd party -Tejas nokia-need to provide by BSS Team |  |  |  |  | Jayanth Madhavi |  |  |  | Applications/Tools | OPEN |  |  |  |  | This task depends on the completion of 208, 209, 210, 211, and 212. | [5 empty] | Open | Open | Open
206 | T207 | 472 | NA |  |  |  | NSO | Integration | OSS |  |  | Open |  |  | 29-12-2025:- Service information is being fetched by OSS. . URL:/sccm/sccm_api/web/api/v1/commited_service_orders (hpeadmin). E2E demo for GiBB completed |  |  |  | OSS Screenshot yet to receive (23/02/2026) | 2026-12-02 | 26/02/2026 | Jyothi & Aditya | Completed | Sivaprasad | Approved |  |  | Applications/Tools | OPEN |  |  |  |  | - 20/01/2026: OSS screenshot of the service to be attached (to be provided by Jakky Venkatesh) - 26/01/2026: Screenshots received - 04/03/2026: Follow‑up with Jakky - 06/03/2026: Mail sent to Jakky - 16/03/2026: Jakky to loop in vendor -Jakky Venkatesh needs to check the CSV part with the OEM and will provide an update after confirmation. | Review Done | 27/02/2026:Need clarification on the CSV file – confirm if it is an API response converted into CSV and whether this CSV is used for database insertion. Action: Check with Jakky Venkatesh. 18/03/2026:Artifact Approved. | 2026-09-03 |  |  | Open | Open | Open
207 | T208 | 472 | NA |  |  |  | NSO | Integration | BSS |  |  | Open |  |  | 12-12-2025:- Integration framework is working fine. E2E demo for GiBB completed |  |  |  |  | 17/02/2026 |  |  | Completed | Sandeep | Not Approved |  |  | Applications/Tools | OPEN |  |  |  |  | API's - Login Sequence: Step 1, Step 2, Step 3 (sequence diagram) 20/02/2026 : BSS screenshot of that service to be attached 04/03/2026 : Need to check with BSS Vendors(KNOT solutions) 06/03/2026 : Vendor did not agree to share proof 10/03/2026 : If proof not shared, send mail to Sandeep for approval 10/3/2026 2:30 PM : Mail sent to sandeep 11/3/2026: Screenshots received from Venkatesh Kanna 18/03/2026:After review, the following details are missing and need to be obtained from BSS: OLT IP, Router IP, and Hostname details. | Review Pending | 18/03/2026:OLT IP, Router IP, and Hostname details Needed Gi-BB to Close add Bridge mode Screenshots | 2026-05-03 |  |  | Open | Open | Open
208 | T209 | 472 | NA |  |  |  | NSO | Integration | Nodes |  |  | Open |  |  | 29-12-2025 :All the nodes are working fine. |  |  | OLT/Router/NE's | Need Clarification InProgress jyothi (23/02/2026) 26/02/2026(need clarity) |  |  |  | Not Completed | Jayanth Madhavi | Not Approved |  |  | Applications/Tools | OPEN |  |  |  |  | Able to connect cisco router screenshot of working router and switches (Screenshot of Neds, Nokia working OLTs,Tejas not required ) (API logs- In SCCM -screenshot of cisco devices & OLT (which are commited state(green))) 04/03/2026 : Unitl Tejas fixed we can't close this | Review Pending |  | Depends On NSO Upgradation |  |  | Open | Open | Open
209 | T210 | 472 | NA |  |  |  | NSO | Integration | EMS-GPON |  |  | Open |  |  | 13-12-2025: Tejas& Nokia NEDs were working fine. Sept-25 Tejas NED stopped working |  |  |  | BSS Screenshot yet to receive(23/02/2026) | 2026-12-02 |  |  | Completed | Sayyed | Not Approved |  |  | Applications/Tools | OPEN |  |  |  |  | 04/03/2026 : Unitl Tejas fixed we can't close this 10/03/2026 : If proof not shared send mail to sandeep for approval 10/03/2026 : If proof not shared send mail to sandeeo for approval 10/3/2026 2:30 PM : Mail sent to sandeep | Review Pending |  | BSS Screenshot & Depends On NSO Upgradation |  |  | Open | Open | Open
210 | T211 | 472 | NA |  |  |  | NSO | Integration | EMS-DWDM |  |  | Open |  |  | Integration demonstrated in the past. |  |  |  | Need Clarification (26/02/2026:New 2 Screenshot added) | 19/2/2026 | 23/2/2026 | Jyothi & Mahesh | Completed |  | Not Approved |  |  | Applications/Tools | OPEN |  |  |  |  | 18/03/2026: ASK UMA | Review Pending | 17/03/2026 – (Sanjay Ji Review): NSO Attach MPLS‑related artifact. 18/03/2026:()EMS- Completed with screenshots 1,2,3 | Review not done |  |  | Open | Open | Open
211 | T212 | 472 | NA |  |  |  | NSO | Development and unit testing | Service verification and provisioning - IP MPLS |  |  | Open |  |  | 02-dec-2025: E2E demo of gibb shown. First part of GIBB service is MPLS, which is working as expected. |  |  | direct 1+1 protection | BSS Team didn’t test GIBB router | 2026-12-02 | 23/2/2026 | Jyothi & Mahesh | Completed |  | Not Approved |  |  | Applications/Tools | OPEN |  |  |  |  | 04/03/2026 - First check SCCM - Second check GIBB - Third check with RS team | Review Done | 27/02/2026: MPLS configuration identified as wrong. Need to check with the Network Team. 18/03/2026: Remove Nokia attachments and add Router screenshots. Gill is correct screenshot(previously attached) but configuration wrong | 12/3/2026 (Completed) |  |  | Open | Open | Open
212 | T213 | 472 | NA |  |  |  | NSO | Development and unit testing | Service verification and activation - GPON Nokia and Tejas |  |  | Open |  |  | 05-12-2025: Integration with Nokia EMS, GIBB service demonstrated.29-12-2025:- Tejas NED not working |  |  | E2E test UAT GIBB logs | Pending (23/02/2026) InProgress with Jyothi DONE:(26/02/2026 same as T210) | 19/02/2026 | 25/02/2026 | Jyothi & Aditya | Completed |  | Not Approved |  |  | Applications/Tools | OPEN |  |  |  |  | (API logs- In SCCM -screenshot of cisco devices & OLT (which are commited state(green))) 04/03/2026 : Unitl Tejas fixed we can't close this | Review Done | 27/02/2026:Teja's NED are not working so we can't close this | Depends On NSO Upgradation |  |  | Open | Open | Open
213 | T214 | 472 | NA |  |  |  | NSO | Development and unit testing | SCCM provisioning request for HSI, IPTV, T-Wire,T-VPN,VoIP,CCTV SDD |  |  | Open |  |  | 19-12-2025:- Plan,scope and schedule for remaining services finalized. |  |  | artifact from sccm. | Pending | [8 empty] | Applications/Tools | OPEN |  |  |  |  | Development still in progress. | [5 empty] | Open | Open | Open
214 | T215 | 472 | NA |  |  |  | NSO | Development and unit testing | NSO module final implementation |  |  | Open |  |  | 19-12-2025:- Plan,scope and schedule for remaining services finalized. |  |  | Link with NSO upgradation. | Pending | 19/2/2026 | 24/2/2026 | Jyothi & Aditya | Completed |  | Not Approved |  |  | Applications/Tools | OPEN |  |  |  |  | service catelog picture,NSO upgrade pending | Review Pending |  | Depends On NSO Upgradation |  |  | Open | Open | Open
215 | T216 | 472 | NA |  |  |  | NSO | Integration | NSO integration with SCCM |  |  | Open |  |  | 29-dec-2025 : Integration is working fine. E2E service was demonstrated. |  |  | backend screenshot |  | 19/2/2026 | 24/2/2026 | Jyothi & Aditya | Completed |  | Not Approved |  |  | Applications/Tools | OPEN |  |  |  |  | SCCM Service name or order id (same service will be there in NSO UI) 04/03/2026 : Need backend logic of SCCM Application NSO | Review Done | 27/02/2026:Backend Integration logic is also required(DB or any) | 6/3/2026(Completed) |  |  | Open | Open | Open
216 | T217 | 472 | NA |  |  |  | NSO | MoM Action | Cisco NSO to test all the cisco elements including SG350 Horizontal switch to deliver service |  |  | Open |  |  | 19-dec-2025: this Device is included in plan, Network team to share template and design document. 19-12-2025:- Plan,scope and schedule for remaining services finalized. |  |  |  | Pending (26/02/2026 Not Developed -Switch) | [8 empty] | Applications/Tools | OPEN |  |  |  |  | similiar to cisco 920, 907 , 9k, (SG350 under progress (cisco suport)) | [5 empty] | Open | Open | Open
217 | T218 | 472 | NA |  |  |  | NSO | MoM Action | NSO LLD |  |  | Open |  |  | 12-12-2025 : Need to implement review comments |  |  |  | Pending |  |  |  | In-Progress |  | Not Approved |  |  | Applications/Tools | OPEN |  |  |  |  | LLD Document 04/03/2026 : Need clarity some points | Review Pending |  |  |  |  | Open | Open | Open
218 | T219 | 472 | NA |  |  |  | NSO | MoM Action | Service catalog with product concept note for all services with target requirement date. |  |  | Open |  |  | 19-12-2025:- Plan for remaining services identified.. GIBB and TDIA-ILL is except with Tejas is completed. |  |  | screenshot of SCCM Scatalog | 26-02-2026-removed 2 images only catelog image required. | 19/2/2026 | 19/2/2026 | Jyothi & Aditya | Completed |  | Not Approved |  |  | Applications/Tools | OPEN |  |  |  |  | service catelog picture 04/03/2026 : Unitl Tejas fixed we can't close this | Review Done | 27/02/2026: Teja's NED are not working so we can't close this | Depends On NSO Upgradation |  |  | Open | Open | Open
219 | T220 | 472 | NA |  |  |  | NSO | MoM Action | T-Cell Service definition sign off |  |  | Open |  |  | 29-dec-2025: Need to check with Network team |  |  | p2p/p2mp | Pending(TCELL is airtel) (26/02/2026:created) | 2026-02-24 | 2026-02-26 | Jyothi & Aditya | Completed |  | Not Approved |  |  | Applications/Tools | OPEN |  |  |  |  | 04/03/2026 : The point is also closed | Review Done | 27/02/2026: Point is already closed kindly check with the Network Team. | 10/3/2026 (Completed) |  |  | Open | Open | Open
220 | T221 | 472 | NA |  |  |  | NSO | MoM Action | MAG/GAC ports reservation feasibility for services booked in BSS with payments made |  |  | Open | [5 empty] | Check with BSS/OSS. | [5 empty] | Ravibhushan/Siva |  |  |  | Applications/Tools | OPEN |  |  |  |  | 16/3/2026-BSS screenshot venkatesh+SCCM Screenshot can be closed after discussion with Customer Reservation of ports is not feasible - the solution and viability not agreed | [5 empty] | Open | Open | Open
221 | T222 | 472 | NA |  |  |  | NSO | MoM Action | Tejas NED readiness |  |  | Open |  |  | 29-12-2025: Tejas NED stopped working. Since the NSO version is not supported. Upgrade is required. | [8 empty] | Sayyed |  |  |  | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
222 | T223 | 472 | NA |  |  |  | NSO | MoM Action | IPTV tested needs to be finalised for additional configuration for multicast and tested as per lab availability and final sign off |  |  | Open |  |  | 19-12-2025:- Plan,scope and schedule for remaining services finalized. | [8 empty] | Sayyed |  |  |  | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
223 | T224 | 472 | NA |  |  |  | NSO | MoM Action | BSS to provide actual feasibility parameters e.g PE port number(s) from OSS . Right now values are hard-coded . In turn OSS to get these details from GIS. We havent seen an e2e workign scenario on this yet. |  |  | Open |  |  | 19-12-2025:- NOT a NSO action. |  |  | check with BSS/OSS | check with BSS/OSS |  |  |  |  | Sanddep |  |  |  | Applications/Tools | OPEN |  |  |  |  | 16/3/2026-BSS screenshot venkatesh+ OSS screenshot(Harshini) | [5 empty] | Open | Open | Open
224 | T225 | 472 | NA |  |  |  | NSO | MoM Action | VLAN logic : Vlan logic for HSI-SVLAN has beed provided per zone information. But most of deployments are coming with vlan 256 of PIONEER for any service . This needs to be looked at. VLAN ID should be changed to as per plan shared by Aravindhan. |  |  | Open |  |  | 19-12-2025:- For each service vlan plan is documented in the solution document which is analysed by NSO and implemented. Completed for GIBB & TDIA |  |  | implmented by NSO for GIBB | Need Clarification |  |  |  |  | RS sir |  |  |  | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
225 | T226 | 472 | NA |  | OSS | OSS | OSS | IPMPLS | Alarm & Auto TT |  |  | Open |  |  | 1. OT Stack upgrade is under discussion 2. Resync stabilization is WIP : Action Plan to submitted by 9th Sept 2025 | [12 empty] | Applications/Tools | OPEN | 1. OT Stack upgrade is under discussion 2. Resync stabilization is WIP : Action Plan to submitted by 9th Sept 2025 | Completed With Artifacts | TRUE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
226 | T227 | 472 | NA |  | OSS | OSS | OSS | Other Applications Integrations with OSS | Create trouble ticket by BSS CRM |  |  | Colosed | [15 empty] | Applications/Tools | Closed | 0 | Closed/Approved | TRUE | [5 empty] | 2025-05-26 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\OSS\T227 | Completed & Approved | Closed before june-2025 | Closed before june-2025
227 | T228 | 472 | NA |  | OSS | OSS | OSS | Other Applications Integrations with OSS | Creation of technical incident by Helpdesk |  |  | Open |  |  | 17-05-2025: Under observation. Seek approval from Sivakumar 26-06-2025: closed from OSS end, help desk to start using | [12 empty] | Applications/Tools | OPEN |  | Completed With Artifacts | FALSE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
228 | T229 | 472 | NA |  | OSS | OSS | OSS | DWDM Integration with OSS | DWDM Network Alarms integration has been completed in HPE OSS. However, all alarm counts are not in sync with Ciena MCP to HPE vTeMIP. |  |  | Colosed | [15 empty] | Applications/Tools | Closed | 0 | Closed/Approved | TRUE | [5 empty] | 2025-05-29 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\OSS\T229 | Completed & Approved | Closed before june-2025 | Closed before june-2025
229 | T230 | 472 | NA |  | OSS | OSS | OSS | DWDM Integration with OSS | Hardware inventory integration has been completed in HPE OSS. |  |  | Colosed | [15 empty] | Applications/Tools | Closed | 0 | Closed/Approved | TRUE | [5 empty] | 2025-05-26 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\OSS\T230 | Completed & Approved | Closed before june-2025 | Closed before june-2025
230 | T231 | 472 | NA |  | OSS | OSS | OSS | DWDM Integration with OSS | Ciena DWDM Network Topology has been created in HPE OSS topology MAP along with neighbour NE details. Adding the geographical map in the background of HPE OSS is possible with openstreet map.. Not posisble to integarted with GIS map |  |  | Open |  |  | 09-09-2025: topology available but bordering not feasible | [12 empty] | Applications/Tools | OPEN | 09-09-2025: topology available but bordering not feasible | Completed With Artifacts | TRUE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
231 | T232 | 472 | NA |  | OSS | OSS | OSS | DWDM Integration with OSS | Auto Ticket Generation- Fiber Cut |  |  | Colosed |  |  | 15-09-2025: Demonstrated in the Demo/UAT call | [12 empty] | Applications/Tools | Closed | 15-09-2025: Demonstrated in the Demo/UAT call | Closed/Approved | TRUE | [5 empty] | 2025-05-26 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\OSS\T232 | Completed & Approved | Closed before june-2025 | Closed before june-2025
232 | T233 | 472 | NA |  | OSS | OSS | OSS | DWDM Integration with OSS | Auto Ticket Generation- Hardwares Failures |  |  | Open | [15 empty] | Applications/Tools | Closed | 0 | Closed/Approved | TRUE | [6 empty] | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\OSS\T233 | Completed & Approved | Closed before june-2025 | Closed after June
233 | T234 | 472 | NA |  | OSS | OSS | OSS | DWDM Integration with OSS | Auto Ticket Generation- Infra Failure |  |  | Colosed | [15 empty] | Applications/Tools | Closed | 0 | Closed/Approved | TRUE | [5 empty] | 2025-05-26 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\OSS\T234 | Completed & Approved | Closed before june-2025 | Closed before june-2025
234 | T235 | 472 | NA |  | OSS | OSS | OSS | DWDM Integration with OSS | Network and service performance monitoring KPIs report in HPE OSS |  |  | Colosed | [15 empty] | Applications/Tools | Closed | 0 | Closed/Approved | TRUE | [5 empty] | 2025-05-26 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\DWDM\Artefact - T101 | Completed & Approved | Closed before june-2025 | Closed before june-2025
235 | T236 | 472 | NA |  | OSS | OSS | OSS | DWDM Integration with OSS | Bandwidth utilization data in HPE OSS is available and under validation. |  |  | Colosed | [15 empty] | Applications/Tools | Closed | 0 | Closed/Approved | TRUE | [5 empty] | 2025-05-26 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\OSS\T236 | Completed & Approved | Closed before june-2025 | Closed before june-2025
236 | T237 | 472 | NA |  | OSS | OSS | OSS | DWDM Integration with OSS | Service inventory data availability in HPE OSS |  |  | Open |  |  | 17-05-2025: Dependancy on NSO 26-06-2025: Cisco to be onboarded then it will take ~30 days to complete(timeline is given concidering NSO support available on 1st July) | [12 empty] | Applications/Tools | OPEN |  | OPEN | FALSE | [7 empty] | Open | Open | Open
237 | T238 | 472 | NA |  | OSS | OSS | OSS | DWDM Integration with OSS | For planned event service impact analysis data / report |  |  | Open |  |  | 17-05-2025: Dependancy on NSO 26-06-2025: Cisco to be onboarded then it will take ~30 days to complete(timeline is given concidering NSO support available on 1st July) | [12 empty] | Applications/Tools | OPEN |  | Completed with artifacts | FALSE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
238 | T239 | 472 | NA |  | OSS | OSS | OSS | IPMPLS Integration with OSS | FMS (Inventory, Alarm, Auto TT) Ref 226 |  |  | Open |  |  | 24-05-2025:Working with some operational challenges like frequent NNMi and OBM hung issue, queue increase. | [12 empty] | Applications/Tools | OPEN |  | Completed With Artifacts | FALSE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
239 | T240 | 472 | NA |  | OSS | OSS | OSS | IPMPLS Integration with OSS | PMS reports for IPMPLS domain network elements |  |  | Open |  |  | 17-05-2025: Data collection rom internal (SME & NOC team) and then OT support is required for NPS to enable all permormance parameters. 24-06-2025: NPS reports available and NOC came back with some observa | tio | n of | wron | g data, f | which OT has |  | as | ked |  |  | evi | dences which are awaited from NOC | Applications/Tools | OPEN |  | Completed With Artifacts | FALSE |  | or | [5 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
240 | T241 | 472 | NA |  | OSS | OSS | OSS | IPMPLS Integration with OSS | Dashboards for IPMPLS Domain |  |  | Open |  |  | 17-05-2025: OOB dashboards are already available in NNMi, L&T NOC team needs to review and confirm if any descripancy observed. | [12 empty] | Applications/Tools | OPEN |  | Completed With Artifacts | FALSE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
241 | T242 | 472 | NA |  | OSS | OSS | OSS | IPMPLS Integration with OSS | Reports |  |  | Open |  |  | 24-05-2025: Operational Challenges 26-06-2025: Multiple reports are already available, need clarity if anything is missing from IPMPLS | [12 empty] | Applications/Tools | OPEN |  | Completed With Artifacts | FALSE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
242 | T243 | 472 | NA |  | OSS | OSS | OSS | GPON-NOKIA Integration with OSS | CR for Nokia API integration to close BW query and PMS related issues |  |  | Open |  |  | 13-Sep-2025: Having dependency on A&O/NSO and service inventory deployment. 29-Aug-2025: Having dependency on A&O/NSO and service inventory deployment. 07-July-2025: L&T Remarks: As per the Tfiber suggesti | on, | this | is | feasible | will be con |  | sid | ere |  |  | d du | ring A&O OEM solution deployemenet. 05-July-2025 : TFiber Comments: Available bandwidth has to be calculated before provisioning service to a customer. Available bandwidth can be achieved either from OSS or from Service Inventory systems- which already have the services provisioned data Internal discussion planned on 07-July-2025 30-June-2025 : To arrange a call with Tfiber for the discussion and conclusion Nokia provided the available upload bandwidth on PON Port but Nokia claiming that devices/AMS does not support to provide the available download bandwidth of a PON Port. This feature is not available with Nokia | Applications/Tools | OPEN |  | Completed With Artifacts | FALSE |  | and | [5 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
243 | T244 | 472 | NA |  | OSS | OSS | OSS | Other Applications Integrations with OSS | Fetch trouble ticket status for ticket(s) by BSS CRM |  |  | Colosed | [15 empty] | Applications/Tools | Closed | 0 | Closed/Approved | TRUE | [5 empty] | 2025-05-26 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\OSS\T244 | Completed & Approved | Closed before june-2025 | Closed before june-2025
244 | T245 | 472 | NA |  | OSS | OSS | OSS | Passive Infra Integration with OSS | Integration with DG - HPE |  |  | Colosed | [15 empty] | Applications/Tools | Closed | 0 | Closed/Approved | TRUE | [5 empty] | 2025-05-26 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\OSS\T245 | Completed & Approved | Closed before june-2025 | Closed before june-2025
245 | T246 | 472 | NA |  | OSS | OSS | OSS | Passive Infra Integration with OSS | Integration with UPS - HPE |  |  | Colosed | [15 empty] | Applications/Tools | Closed | 0 | Closed/Approved | TRUE | [5 empty] | 2025-05-26 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\OSS\T246 | Completed & Approved | Closed before june-2025 | Closed before june-2025
246 | T247 | 472 | NA |  | OSS | OSS | OSS | Other Applications Integrations with OSS | Inventory Synch - Physical devices with GIS |  |  | Open |  |  | 24-05-2025:WIP with HPE 26-06-2025: To be tested post GIS integration | [12 empty] | Applications/Tools | OPEN |  | OPEN | FALSE | [7 empty] | Open | Open | Open
247 | T248 | 472 | NA |  | OSS | OSS | OSS | GPON | Nokia API integration - . PMS ( Chassi OLT ), Inventory, Device Status (ONT ) |  |  | Open |  |  | 17-05-2025: HPE team will deliver post application upgradation 23-06-2025: for Device status, HPE said the the Nokia alarm format is wrong; post having calls with Nokia HPE reviewing the NBI documentation. | 17 | -9 | 025: | Solution | plyed for on |  | e p | ack |  |  | age, | for other 2 package need to raise PE on 22nd July | Applications/Tools | OPEN |  | Completed With Artifacts | FALSE |  | de | [5 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
248 | T249 | 472 | NA |  | OSS | OSS | OSS | GPON-NOKIA Integration with OSS | OLT & ONT devices status in OSS is not as per AMS |  |  | Open |  |  | 06-06-2025: HPE requested a call with Nokia 11-06-2025: Nokia call happened and inputs were shared with HPE 23-06-2025: Post having calls with Nokia one more time last week they have share NBI documents w | ith | HPE | toda | y which t | are reviewi |  | ng. | 22 |  |  | -07- | 2025: count matching, confirmation awaited from NOC | Applications/Tools | OPEN |  | Completed With Artifacts | FALSE |  | hey | [5 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
249 | T250 | 472 | NA |  | OSS | OSS | OSS | GPON-NOKIA Integration with OSS | ONT devices have been recovered and validated as per AMS count |  |  | Open |  |  | 15-06-2025: validation pending from NOC | [12 empty] | Applications/Tools | OPEN |  | Completed With Artifacts | FALSE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
250 | T251 | 472 | NA |  | OSS | OSS | OSS | Other Applications Integrations with OSS | Fetch SLA violation by BSS billing |  |  | Open |  |  | 26-06-2025: table to exposed with BSS, awating sevice ID from BSS and same needs to implemented in Network | [12 empty] | Applications/Tools | OPEN |  | Not Relevant To OSS | FALSE | [7 empty] | Open | Open | Open
251 | T252 | 472 | NA |  | OSS | OSS | OSS | Other Applications Integrations with OSS | Circuit performance data to BSS CRM |  |  | Open |  |  | 26-06-2025: table to exposed with BSS, awating sevice ID from BSS and same needs to implemented in Network | [12 empty] | Applications/Tools | OPEN |  | Not Relevant To OSS | FALSE | [7 empty] | Open | Open | Open
252 | T253 | 472 | NA |  | OSS | OSS | OSS | DWDM | Alarm Sync issue with MCP |  |  | Colosed | [15 empty] | Applications/Tools | Closed | 0 | Closed/Approved | TRUE | [5 empty] | 2025-05-29 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\OSS\T253 | Completed & Approved | Closed before june-2025 | Closed before june-2025
253 | T254 | 472 | NA |  | OSS | OSS | OSS | GPON | Co-located OLT topology view |  |  | Open |  |  | 17-05-2025: As per previous joint discussion with TFIBER and HPE team, this is not required.(to be discuss and remove/close) 26-06-2025: Completed, need confirmation from NOC | [12 empty] | Applications/Tools | Closed |  | Completed With Artifacts | FALSE | [5 empty] | 2025-11-18 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\OSS\52 Artefcats_18112025 | Closed after 14-Nov-25 | Closed after 14-Nov-25 | Completed but Verification undrer Process
254 | T255 | 472 | NA |  | OSS | OSS | OSS | Other Applications Integrations with OSS | Send SMS communication to SMS gateway |  |  | Open | [15 empty] | Applications/Tools | Closed | 0 | Closed/Approved | TRUE | [6 empty] | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\OSS\T255 | Completed & Approved | Closed before june-2025 | Closed after June
255 | T256 | 472 | NA |  | OSS | OSS | OSS | IPMPLS | EPNM & PI Inventory |  |  | Open |  |  | 09-09-2025: to show only integrated devices, need take up with HPE to change select query to excluse non SNMP device | [12 empty] | Applications/Tools | OPEN | 09-09-2025: to show only integrated devices, need take up with HPE to change select query to excluse non SNMP device | Completed With Artifacts | TRUE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
256 | T257 | 472 | NA |  | OSS | OSS | OSS | Other Applications Integrations with OSS | Syslog Sync to Syslog Server |  |  | Open |  |  | 17-06-2025: Support required from Sys-log team/Sarmendra & Ravikishore | [12 empty] | Applications/Tools | OPEN |  | OPEN | FALSE | [7 empty] | Open | Open | Open
257 | T258 | 472 | NA |  | OSS | OSS | OSS | GIS | GIS integration |  |  | Open |  |  | 17-05-2025: WIP with HPE team | [12 empty] | Applications/Tools | OPEN |  | OPEN | FALSE | [7 empty] | Open | Open | Open
258 | T259 | 472 | NA |  | OSS | OSS | OSS | E2E | TOPOLOGY |  |  | Open |  |  | 17-05-2025: WIP with HPE team | [12 empty] | Applications/Tools | OPEN |  | OPEN | FALSE | [7 empty] | Open | Open | Open
259 | T260 | 472 | NA |  | OSS | OSS | OSS | E2E | Cross domain RCA corelation |  |  | Open |  |  | 17-05-2025: WIP with HPE team | [12 empty] | Applications/Tools | OPEN |  | Duplicate | FALSE | [7 empty] | Open | Open | Open
260 | T261 | 472 | NA |  | OSS | OSS | OSS | Infra | Data enrichment - Location information PKG A B C, etc |  |  | Open |  |  | 17-05-2025: GIS Integration with UTM is WIP(OT dependancy) 24-06-2025: OT has shared the API for attributes required by HPE | [12 empty] | Applications/Tools | Closed |  | Completed With Artifacts | FALSE | [5 empty] | 2025-11-18 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\OSS\52 Artefcats_18112025 | Closed after 14-Nov-25 | Closed after 14-Nov-25 | Completed but Verification undrer Process
261 | T262 | 472 | NA |  | OSS | OSS | OSS | DC - Active infra Alarm and Auto TT | DC-Active infra Alarm, RCA and Auto TT |  |  | Open |  |  | 17-05-2025: URL unreachable alarms are there but tickets are not getting generated. OT support required. 26-06-2025: Functionality is delivered,under stabilization. | [12 empty] | Applications/Tools | OPEN |  | Completed With Artifacts | FALSE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
262 | T263 | 472 | NA |  | OSS | OSS | OSS | Documentation - LLD, FAT, HA Testing | OSS Documentation - LLD, FAT, HA Testing |  |  | Open |  |  | 17-05-2025: OT support is required. 26-06-2025: OT & HPE working on preparing the document concidering the BSOW | [12 empty] | Applications/Tools | OPEN |  | Completed | FALSE | [7 empty] | Open | Open | Open
263 | T264 | 472 | NA |  | OSS | OSS | OSS | MoM Action | Network Downtime, fault reported to be mapped with BSS to consider during billing process |  |  | Open |  |  | 26-06-2025: Post NSO integration | [12 empty] | Applications/Tools | OPEN |  | Not Relevant To OSS | FALSE | [7 empty] | Open | Open | Open
264 | T265 | 472 | NA |  | OSS | OSS | OSS | MoM Action | Feasibility Engine |  |  | Open |  |  | 18-Nov-25: To be discussed further- BSS Dependancy 24-05-2025: WIP with HPE, OT dendancy for data. 26-06-2025: OT has provided necessary data to HPE, HPE to complete remaining development | [12 empty] | Applications/Tools | OPEN | API | Completed With Artifacts | FALSE | [7 empty] | Reopened | Reopened | Completed but Verification undrer Process
265 | T266 | 472 | NA |  | OSS | OSS | OSS | MoM Action | Commercial engine to be designed along with rules to Budgetory calculation for network and customer feasibilies |  |  | Open |  |  | 26-06-2025: this needs to be taken care by BSS side | [12 empty] | Applications/Tools | OPEN |  | Not Relevant To OSS | FALSE | [7 empty] | Open | Open | Open
266 | T267 | 472 | NA |  | OSS | OSS | OSS | MoM Action | Port Block (reservation) against Service ID |  |  | Open |  |  | DUPLICATE POINT | [12 empty] | Applications/Tools | OPEN |  | Duplicate | FALSE | [7 empty] | Open | Open | Open
267 | T268 | 472 | NA |  | OSS | OSS | OSS | Design & Documentation | LLD |  |  | Open |  |  | DUPLICATE POINT | [12 empty] | Applications/Tools | OPEN |  | Duplicate | FALSE | [7 empty] | Open | Open | Open
268 | T269 | 472 | NA |  | OSS | OSS | OSS | MoM Action | Change management process (eg. planned /Unplanned ) activities to be demonstrated |  |  | Open |  |  | 17-05-2025: OT Team has to work and deliver 26-06-2025: change managemnt is delivered, NOC team has to confirm | [12 empty] | Applications/Tools | OPEN |  | Completed With Artifacts | FALSE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
269 | T270 | 472 | NA |  | OSS | OSS | OSS | MoM Action | Device status in OSS ciena inventory, details received from Ciena |  |  | Colosed | [15 empty] | Applications/Tools | Closed | 0 | Closed/Approved | TRUE | [5 empty] | 2025-05-26 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\OSS\T270 | Completed & Approved | Closed before june-2025 | Closed before june-2025
270 | T271 | 472 | NA |  | OSS | OSS | OSS | GPON | ONT & OLT vendor name should be mapped to OSS Inventory & PMS Inventory. |  |  | Open | [15 empty] | Applications/Tools | Closed | 0 | Closed/Approved | TRUE | [6 empty] | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\OSS\T271 | Completed & Approved | Closed before june-2025 | Closed after June
271 | T272 | 472 | NA |  | OSS | OSS | OSS | Design & Documentation | Infra team to maintain the SSL connectivity |  |  | Open |  |  | 17-05-2025: Dependancy on HPE upgrade and OT PS Team support 23-06-2025: New VM was requested by OT and same is provided. OT will to the testing in TND and confirm for production by 27th June 2025 | [12 empty] | Applications/Tools | Closed | SSL configuartion completed in Service Manager | Completed With Artifacts | FALSE | [5 empty] | 2025-11-18 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\OSS\52 Artefcats_18112025 | Closed after 14-Nov-25 | Closed after 14-Nov-25 | Completed but Verification undrer Process
272 | T273 | 472 | NA |  | OSS | OSS | OSS | Deployment and Installations | Deployment process - Process of building network & passive device connectivity to T-NOC through SG350, ONT (One port Voice, 2nd - Data, 3rd - Video & 4th port to T-NOC for SNMP traps) . Along with , and also all other Services to be test and provision in SG350 |  |  | Open |  |  | 09-09-2025: Needs to be closed along with IPMPLS(RS Rao) & GPON(Sayyad) | [12 empty] | Applications/Tools | OPEN | 09-09-2025: Needs to be closed along with IPMPLS(RS Rao) & GPON(Sayyad) | Completed | TRUE | [7 empty] | Open | Open | Open
273 | T274 | 472 | NA |  | OSS | OSS | OSS | Development and unit testing | In OSS Script File, both Nokia Primary and Secondary IPs are mentioned, however OSS is considering only the first mentioned IP even if Secondary IP is master. Due to this alarms are not reflecting in OSS. Infra team has to setup Virtual IP. |  |  | Colosed | [15 empty] | Applications/Tools | Closed | 0 | Closed/Approved | TRUE | [5 empty] | 2025-05-26 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\OSS\T274 | Completed & Approved | Closed before june-2025 | Closed before june-2025
274 | T275 | 472 | NA |  | OSS | OSS | OSS | MoM Action | In OSS management dashboard, Block count should count only Mandal OLTs and not GP OLTs. |  |  | Open | [15 empty] | Applications/Tools | Closed | 0 | Closed/Approved | TRUE | [6 empty] | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\OSS\T275 | Completed & Approved | Closed before june-2025 | Closed after June
275 | T276 | 472 | NA |  | OSS | OSS | OSS | MoM Action | DG Set integration with OSS is in progress for Package A, details for DG set integration with OSS awaited from Package B and C. |  |  | Open |  |  | 26-06-2025: Functionality is delivered, but system is not stable; same issue is escalated to HPE and OT. 22-07-2025: genset alarms are working now, confirmation required from NOC | [12 empty] | Applications/Tools | Closed |  | Completed With Artifacts | FALSE | [5 empty] | 2025-11-18 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\OSS\52 Artefcats_18112025 | Closed after 14-Nov-25 | Closed after 14-Nov-25 | Completed but Verification undrer Process
276 | T277 | 472 | NA |  | OSS | OSS | OSS | MoM Action | UPS and DG Device status, GP Name and LGD code & Block Name and LGD code are not available in the Passive Infra (Non-IT) inventory |  |  | Open |  |  | 09-09-2025: Status available in NNMi & PowerBI. All other atributes available in UOC | [12 empty] | Applications/Tools | OPEN | 09-09-2025: Status available in NNMi & PowerBI. All other atributes available in UOC | Completed With Artifacts | TRUE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
277 | T278 | 472 | NA |  | OSS | OSS | OSS | Firewall | OSS firewall ports required for Security compliance |  |  | Open |  |  | 09-09-2025: Security team is already taking care with help of MTR sharma | [12 empty] | Applications/Tools | OPEN | 09-09-2025: Security team is already taking care with help of MTR sharma | Completed | TRUE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
278 | T279 | 472 | NA |  | OSS | OSS | OSS | Security | Security policies to evolve related to DOT/CDOT etc.. from internal and intigration |  |  | Open |  |  | 26-06-2025: Dependacy on Cross domain delivery | [12 empty] | Applications/Tools | OPEN | Security SME can share artefacts | Completed | FALSE | [7 empty] | Open | Open | Open
279 | T280 | 472 | NA |  | OSS | OSS | OSS | Correlations | Cross domain Corelation and exact reason for any outage in Network till ONT Port with E2E topology |  |  | Open |  |  | 17-05-2025: WIP with HPE team | [12 empty] | Applications/Tools | OPEN |  | OPEN | FALSE | [7 empty] | Open | Open | Open
280 | T281 | 472 | NA |  | OSS | OSS | OSS | MoM Action | Problem Management report for various recurring outages for the given period like i) one Unique LGD code >5 times in a Month ii) Fiber cut SPAN/Link >2 times in a month iii) Unique LGD code Down for >2 times with Same RFO iv) etc. |  |  | Open |  |  | 18-Nov-25: Latest Records shoule be shown as a test results | [12 empty] | Applications/Tools | OPEN | 0 | Completed With Artifacts | TRUE | [7 empty] | Reopened | Reopened | Open
281 | T282 | 472 | NA |  | OSS | OSS | OSS | MoM Action | For ONT Down cases, Some of the Alarms and cause code given by OEM is not matching with RFO provided by field engg., for example incase of Particular ONT goes down at GP level then exact RFO should be available for NOC to correlate with outages due to UPS power or other issue? |  |  | Open |  |  | 15-09-2025: Demostrated in the Demo/UAT call | [12 empty] | Applications/Tools | OPEN | 15-09-2025: Demostrated in the Demo/UAT call | Completed With Artifacts | TRUE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
282 | T283 | 472 | NA |  | OSS | OSS | OSS | Dashboards | Alert Mechanism (event rule) when power supply is through UPS which is running on Battery backup mode then there should be alert in the form of SMS sent to field team so outages can be avoided or minimized proactively. threshold can be configured (TBD) )for given range for Battery backup status i) <50%- - Minor ii) <40%-Major iii) <30% -Critical) |  |  | Open | [15 empty] | Applications/Tools | OPEN | pending | OPEN | FALSE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
283 | T284 | 472 | NA |  | OSS | OSS | OSS | Dashboards | Weekly, Monthly E2E Network Availability Trend for each Packages and over all per District, Zone level. |  |  | Open |  |  | Weekly Availability is not getting calculated hence it is not-feasible | [12 empty] | Applications/Tools | OPEN |  | Not-Feasible | FALSE | [7 empty] | Open | Open | Open
284 | T285 | 472 | NA |  | OSS | OSS | OSS | Dashboards | District wise Performance report for period of infra, fiber, ISP, config issues etc. |  |  | Open |  |  | 09-09-2025: user can download reports as on his requirement | [12 empty] | Applications/Tools | OPEN | 09-09-2025: user can download reports as on his requirement - TT report | Completed With Artifacts | FALSE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
285 | T286 | 472 | NA |  | OSS | OSS | OSS | Dashboards | Individual NOC Engineer and shift Lead Performance Measurement for handling the TT's |  |  | Open |  |  | 17-05-2025: Artefacts needs to be collected from Sivakumar and seek approval. 26-06-2025: Waiting for Sivakumar's approval | [12 empty] | Applications/Tools | OPEN | closure | Completed With Artifacts | FALSE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
286 | T287 | 472 | NA |  | OSS | OSS | OSS | MoM Action | Exact SPAN/Link details must be taken from GIS(Including Lat,Long) for Fiber cut/outage scenario to undserstand fix is permanent or temporarary in nature and impact on Multiple Nodes/GP’s . |  |  | Open |  |  | 16-Oct-25: We don’t have Fiber monitoring system hence we can not achieve it 17-05-2025: Common span scenarios solution needs to be finalization pending with L&T and will be finalized based on data coming | fro | m GIS | int | egration. | -06-2025: De |  | pen | dan |  |  | cy o | n GIS integration. Expected to be completed by 16th July and then ~30 days needed for Common span | Applications/Tools | OPEN | We don’t have Fiber monitoring system hence we can not achieve it | Not-Feasible | FALSE |  | 26 | [5 empty] | Open | Open | Open
287 | T288 | 472 | NA |  |  | DC-Infrastructure | OSS | MoM Action | Report for Backup Status (success/failure) of all VM (source it from Vcenter Report) |  |  | Open | [15 empty] | Applications/Tools | Closed | [8 empty] | 2025-07-05 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\OSS\Artifact-T288 | Completed & Approved | Closed before june-2025 | Closed after June
288 | T289 | 472 | NA |  | OSS | OSS | OSS | MoM Action | DC Active infra-Health check-up /Utilization and Resource Availability report.—Hardware and Servers. (Source it from Vcenter to OSS tool) |  |  | Open |  |  | 26-06-2025: data available in OBM, need confirmation from DC team | [12 empty] | Applications/Tools | OPEN |  | Completed With Artifacts | FALSE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
289 | T290 | 472 | NA |  | OSS | OSS | OSS | MoM Action | IP MPLS node status report to be automated(Zonal / Mandal/GP) along with Alias Name(Like Actual Mandal /GP names) -Feasibility check required if Alias can be updated & fetched by OSS tool |  |  | Open |  |  | 26-06-2025: IPMPLS node status available in NNMi, need confirmation from NOC | [12 empty] | Applications/Tools | OPEN | pending | OPEN | FALSE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
290 | T291 | 472 | NA |  | OSS | OSS | OSS | Dashboards | IP MPLS Node/Link/Port availability & Utilization |  |  | Open |  |  | 17-05-2025: Utilization is already available. Node and Link availability is WIP. OT Support not available to check port availability, it needs to resume. 26-06-2025: all data available now except Link avai | lab | ility | , ne | ed confir | ion from NOC | [7 empty] | Applications/Tools | OPEN |  | Completed With Artifacts | FALSE |  | mat | [5 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
291 | T292 | 472 | NA |  | OSS | OSS | OSS | MoM Action | Customised dashboard template with available set of fields for different set of users views |  |  | Open |  |  | 17-05-2025: OOB is available, to be reviewed with NOC | [12 empty] | Applications/Tools | OPEN |  | Completed With Artifacts | FALSE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
292 | T293 | 472 | NA |  | OSS | OSS | OSS | Dashboards | Service VLAN status report from EMS (Nokia and Tejas) |  |  | Open |  |  | 24-05-2025: Inhouse solution being built by rishik | [12 empty] | Applications/Tools | OPEN |  | Duplicate | FALSE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
293 | T294 | 472 | NA |  | OSS | OSS | OSS | MoM Action | OSS MTTR report to include additional columns like RFO, Sub RFO, Resolution etc. |  |  | Open | [15 empty] | Applications/Tools | Closed | 0 | Closed/Approved | TRUE | [6 empty] | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\OSS\T294 | Completed & Approved | Closed before june-2025 | Closed after June
294 | T295 | 472 | NA |  | OSS | OSS | OSS | MoM Action | Service Management tool has having duplicate tickets for same node which is impacting availability, outage reports. Issue needs to be fixed. |  |  | Open |  |  | 12-06-2025: duplicate ticket booking needs to be handle by HPE, HPE working on a script to handle it. 26-06-2025: Script deplyed by HPE, need confirmation from NOC | [12 empty] | Applications/Tools | OPEN |  | Completed with artifacts | FALSE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
295 | T296 | 472 | NA |  | OSS | OSS | OSS | MoM Action | Service Management dashboard should list planned outages and corelate TT if that is on same device or NW component. |  |  | Open |  |  | 17-05-2025: OT & NSO support required | [12 empty] | Applications/Tools | OPEN |  | OPEN | FALSE | [7 empty] | Open | Open | Open
296 | T297 | 472 | NA |  |  |  | DC-IT | Servers and Strorage (Deployment and Installations) | VM's Deployment Application Installations |  |  | Open |  |  | Applications installation completed in the given VM's. Storage/resource Allocation details captured in the TNOC IT Infra Server & Storage-LLD_v_1.5 & DC Inventory master sheet. Artifacts are captured. | [12 empty] | Network | Closed | [9 empty] | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\DC IT-Infra\Artifact for - T297 | Completed & Approved | Closed before june-2025 | Closed after June
297 | T298 | 472 | NA |  |  |  | GPON | Tejas-MoM Action | Deployment process - Process of building network & passive device connectivity to T-NOC through SG350, ONT (One port Voice, 2nd - Data, 3rd - Video & 4 th port to T-NOC for SNMP traps) . Along with , and also all other Services to be test and provision in SG350 |  |  | Colosed | [15 empty] | GPON | Closed | [8 empty] | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T298 | Completed & Approved | Closed before june-2025 | Closed before june-2025
298 | T299 | 472 | NA |  | OSS | Security | OSS | Integrating AD so that there is single user ID for all apps and they can integrate better in future if there is a need | Integration testing done for all apps that are ready currently except Alepo. Apps like HP OSS, Cisco ISE and other such applications are already integrated. We can switch IDs to AD anytime |  |  | Open |  |  | 28-Nov-25: The Alepo team is integrating AD Once done these points will be closed. Once AD integration happen for Aleppo this point also will be closed along with T333. | [12 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
299 | T300 | 472 | NA |  | OSS | Security | OSS | Configuration and best practices | User IDs created. Need to work with users for testing for NOC desktops |  |  | Open |  |  | Artifacts will be created and submitted on 03 Jul 25 | [12 empty] | Applications/Tools | Closed | [9 empty] | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\NW-Security\T300 | Completed & Approved | Closed before june-2025 | Closed after June
300 | T301 | 472 | NA |  |  |  | Security & Regulatory Compliance | Configuration | On A-10 -Configuration done on LB side. WAF will be configure with License |  |  | Open |  |  | 28-Nov-25: Gathering artifacts from other teams. A10 AMC not renewed , Awaiting AMC renewal with WAF features | [12 empty] | Security | OPEN | [10 empty] | Open | Open | Open
301 | T302 | 472 | NA |  |  |  | Security & Regulatory Compliance | Functional AT | Will start next week as KT happened this week for all the new resources |  |  | Open |  |  | 28-Nov-25: Document preparation in progress once done points will be closed. KT has been done. | [12 empty] | Security | OPEN | [10 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
302 | T303 | 472 | NA |  | OSS | Security | OSS | Configuration | OSS- Redware LB-There were configuration issues and have been sorted our by having multiple sessions over the past few weeks |  |  | Open |  |  | Artifact created and will be submitted to customer on 03 Jul 25. | [12 empty] | Applications/Tools | Closed | [8 empty] | 2025-10-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\NW-Security\T303_28-Oct-25.pdf | Closed | Closed After 14-Oct | Completed but Verification undrer Process
303 | T304 | 472 | NA |  |  |  | Security & Regulatory Compliance | Functional AT | Radware LB - Will start next week as KT happened this week for all the new resources |  |  | Open |  |  | 28-Nov-25: Document preparation in progress once done points will be closed. KT has been done. | [12 empty] | Security | OPEN | [10 empty] | Open | Open | Open
304 | T305 | 472 | NA |  | OSS | DC-Infrastructure | OSS | Configuration | We have identified memory needed. Need help with space allocation for VM and also need license for a syslog server. ( we can also use Default Linux daemon) Syslog |  |  | Open |  |  | [17/09/2025] Syslog integration with both Redhat and Windows servers Completed. | [12 empty] | Applications/Tools | Closed | [8 empty] | 2025-09-19 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\OSS\T305 | Completed & Approved | Closed before june-2025 | Closed after June
305 | T306 | 472 | NA |  |  |  | Security & Regulatory Compliance | Documentation | Customer has requested a complete Security LLD that states how our security architechture is and how different security products talk to each other |  |  | Open |  |  | 28-Nov-25: Document preparation in progress once done points will be closed. Completed and Review pending. New changes will be incorporated as an addendum to design. | [12 empty] | Security | OPEN | [10 empty] | Open | Open | Open
306 | T307 | 472 | NA |  |  |  | Security & Regulatory Compliance | User Access Rights | Cisco: PKGA-testing in WIP, PKGB&C-will be replicated after PKGA completion GPON: Segregation is done, implementation is WIP DWDM: Segregation is done, implementation is WIP HPE OSS: User to access mapping is done, implementation WIP by hp team Other Apps: Will have meetings this week and sort it out. |  |  | Open |  |  | #VALUE! | [12 empty] | Security | Closed | [8 empty] | 2025-11-01 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\NW-Security\M1133.pdf | Completed & Approved | Closed After 14-Oct | Open
307 | T308 | 472 | NA |  |  |  | Security & Regulatory Compliance | IPDR | Developing in-house solution, also exploring with external vendors. 3 vendors declined. |  |  | Open |  |  | 27.06.25 , IPDR solution operational , pending document will be submitted by 1st week of Jul'25 | [12 empty] | Security | Closed | [8 empty] | 2025-10-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\NW-Security\T303_28-Oct-25.pdf | Closed | Closed After 14-Oct | Open
308 | T309 | 472 | NA |  |  |  | Security & Regulatory Compliance | Storage | Storage requirement worked out and given to contract team. PO to be issued(Syslog) |  |  | Open |  |  | 25-Sep-2025: Artefacts to be uploaded, Need to provide current consumption of storage, incremental log will be added to existing storage after adding 18 TB additional storage . | [12 empty] | Security | Closed | [9 empty] | Artefacts Need to upload | Completed & Approved | Closed before june-2025 | Closed after June
309 | T310 | 472 | NA |  |  |  | Security & Regulatory Compliance | NAT | Developed in-house solution, also exploring with external vendors. 3 vendors declined. In-house solution is ready for demo, tested with the sample data.( |  |  | Open |  |  | 25-Sep-2025: Detailed discussion will be taken up later(Sanjay will brief background against this point) | [12 empty] | Security | Closed | [8 empty] | 2025-10-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\NW-Security\T303_28-Oct-25.pdf | Completed & Approved | Closed before june-2025 | Closed after June
310 | T311 | 472 | NA |  |  |  | Security & Regulatory Compliance | QoS Reporting | QoS Reporting related to all parameters |  |  | Open |  |  | Completed and Review pending.FAT documents were submitted to TPA , However it has some common observation which will be discussed with TPA team by Mr Sharma. | [12 empty] | Security | Closed | [8 empty] | 2025-10-30 | \\172.28.9.23\tnocreports\Approved Process and SOP_ T Fiber\SOP | Closed | Closed After 14-Oct | Open
311 | T312 | 472 | NA |  |  |  | Security & Regulatory Compliance | Regulatory compliance | SLA Reporting for Cell Tower and GIs |  |  | Colosed | [15 empty] | Security | Closed | [8 empty] | 2025-05-13 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\T312 | Completed & Approved | Closed before june-2025 | Closed before june-2025
312 | T313 | 472 | NA |  |  |  | Security & Regulatory Compliance | Regulatory compliance | Communication made to T-Fiber. Procedure need to be finalized for remote access |  |  | Open |  |  | 28-Nov-25: Gathering artifacts from other teams | [12 empty] | Security | OPEN | [10 empty] | Open | Open | Open
313 | T314 | 472 | NA |  |  |  | Security & Regulatory Compliance | External Audit and VAPT | External Audit and VAPT (Tfiber will be arranging a partner for third party audit) |  |  | Open |  |  | 28-Nov-25: VAPT is going on, once VAPT is done points will be closed. T Fiber to conduct the Audit and VAPT | [12 empty] | Security | OPEN | [8 empty] | 2025-12-19 |  | Completed &Approved | Closed after 14-Dec-25 | Completed &Approved
314 | T315 | 472 | NA |  |  | BMS | BMS | Fire and Safety Drill | Certificate and artefacts of last fire & safety drill submitted |  |  | Open | [15 empty] | #N/A | Closed | [9 empty] | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\NW-Security\T315 | Completed & Approved | Closed before june-2025 | Closed after June
315 | T316 | 472 | NA |  |  |  | Security & Regulatory Compliance | User Traceability | User access traceability |  |  | Open | [15 empty] | Security | Closed | [8 empty] | 2025-05-19 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\NW-Security\T316 | Completed & Approved | Closed before june-2025 | Closed after June
316 | T317 | 472 | NA |  | OSS | OSS | OSS | Certifications | ITIL Product certification |  |  | Open | [15 empty] | Applications/Tools | Closed | 0 | Closed/Approved | TRUE | [5 empty] | 2025-09-12 | \\172.28.9.34\SHARE DRIVE\Artefacts_T-Fiber TNOC Tracker\OSS | Completed & Approved | Closed before june-2025 | Closed after June
317 | T318 | 472 | NA |  |  |  | Security & Regulatory Compliance | Policy Implementation | Network Forensic |  |  | Colosed | [15 empty] | Security | Closed | [8 empty] | 2025-05-19 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\NW-Security\T318 | Completed & Approved | Closed before june-2025 | Closed before june-2025
318 | T319 | 472 | NA |  |  |  | Security & Regulatory Compliance | Policy Implementation | Network Hardening |  |  | Open |  |  | All unauthorised access has been blocked at firwall level. All USB is disables at NOC . All unysed port has been hardened | [12 empty] | Security | Closed | [8 empty] | 2025-10-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\NW-Security\T36_28-Oct-25.pdf | Closed | Closed After 14-Oct | Open
319 | T320 | 472 | NA |  |  |  | Security & Regulatory Compliance | Policy Implementation | Network Penetration Test |  |  | Open |  |  | 28-Nov-25: VAPT is going on, once VAPT is done points will be closed. PT will conducted once Ext audit team arrives | [12 empty] | Security | OPEN | [10 empty] | Open | Open | Open
320 | T321 | 472 | NA |  |  |  | Security & Regulatory Compliance | MoM Action | Firewall policy compare from DC to DR validation check for redundancy |  |  | Open |  |  | May be clubed with point T 71 all Policy will be compared with current configuration of firewall and be submitted . 30-Oct-25: Duplicate to Point T71. DR does not have a public-facing application, and DR a | nd | DC fi | rewa | lls are d | erent | [7 empty] | Security | Closed |  |  |  |  | iff |  |  |  | 2025-11-01 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\NW-Security\T71_31-Oct-25.pdf | Completed & Approved | Closed After 14-Oct | Open
321 | T322 | 472 | NA |  |  |  | Security & Regulatory Compliance | MoM Action | Day 0 attacks for any government departments lifecycle (GIBB to be protected from the day of connection) |  |  | Open |  |  | 28-Nov-25: Gathering artifacts from other teams. will be closed with implementation of URL filtering facilities at IPS | [12 empty] | Security | OPEN | [10 empty] | Open | Open | Open
322 | T323 | 472 | NA |  |  |  | Security & Regulatory Compliance | Storage | User access logs& Commands to be maintained for 2 years |  |  | Open |  |  | Completed and approved | [12 empty] | Security | Closed | [8 empty] | 2025-05-19 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\NW-Security\T323 | Completed & Approved | Closed before june-2025 | Closed after June
323 | T324 | 472 | NA |  |  |  | Security & Regulatory Compliance | Deployment and Installations | Syslog to maintain for 2 years |  |  | Colosed | [15 empty] | Security | Closed | [8 empty] | 2025-05-14 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\Security\T324 | Completed & Approved | Closed before june-2025 | Closed before june-2025
324 | T325 | 472 | NA |  |  |  | Security & Regulatory Compliance | Policy Implementation | Organizational Security Policy |  |  | Open |  |  | 28-Nov-25: Document preparation in progress once done points will be closed. Security policy has been made , however same need clarification from customer to incorporate deviation from actual points. | [12 empty] | Security | OPEN | [10 empty] | Open | Open | Open
325 | T326 | 472 | NA |  |  |  | Security & Regulatory Compliance | Report | IPDR static IP report |  |  | Open | [15 empty] | Security | Closed | [8 empty] | 2025-10-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\NW-Security\T303_28-Oct-25.pdf | Closed | Closed After 14-Oct | Closed after June
326 | T327 | 472 | NA |  |  |  | Security & Regulatory Compliance | Report | Syslog NAT report |  |  | Open | [15 empty] | Security | Closed | [8 empty] | 2025-05-19 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\NW-Security\T327 | Completed & Approved | Closed before june-2025 | Closed after June
327 | T328 | 472 | NA |  |  |  | Security & Regulatory Compliance | AAA | ISE-Completed, Alepo-Completed for Nokia GPON, Accounting feature demo to be done for Tejas GPON and Ciena DWDM |  |  | Open |  |  | Confirmation of purchase of ISE. License needed to upgrade for HA | [12 empty] | Security | Closed | [8 empty] | 2025-10-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\NW-Security\M1139_29-Oct-25.pdf | Closed | Closed After 14-Oct | Completed but Verification undrer Process
328 | T329 | 472 | NA |  |  |  | Security & Regulatory Compliance | MoM Action | Cisco ISE to be integrated with AD for Authentication |  |  | Colosed | [15 empty] | Security | Closed | [8 empty] | 2025-05-19 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\NW-Security\T153 | Completed & Approved | Closed before june-2025 | Closed before june-2025
329 | T330 | 472 | NA |  |  |  | Security & Regulatory Compliance | MoM Action | syslog storage requirement for respective OEM devices |  |  | Colosed | [15 empty] | Security | Closed | [9 empty] | Artefacts Need to upload | Completed & Approved | Closed before june-2025 | Closed before june-2025
330 | T331 | 472 | NA |  |  |  | Security & Regulatory Compliance | MoM Action | Tejas OLT to integrate with Alepo AAA Tejas EMS to integrate with Alepo AAA |  |  | Open |  |  | Alepo AMC Support required for Evidence submission to customer | [12 empty] | Security | Closed | [8 empty] | 2025-11-12 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T171 | Completed & Approved | Closed after 07-Nov-25 | Open
331 | T332 | 472 | NA |  |  |  | Security & Regulatory Compliance | MoM Action | Nokia AMS to integrate with Alepo AAA |  |  | Open | [15 empty] | Security | Closed | [9 empty] | Artefacts Need to upload | Completed & Approved | Closed before june-2025 | Closed after June
332 | T333 | 472 | NA |  |  |  | Security & Regulatory Compliance | MoM Action | Alepo AAA to be integrated with AD |  |  | Open |  |  | 28-Nov-25: The Alepo team is integrating AD Once done these points will be closed. SOW, CR and BOQ Shared for approval and consideration. | [12 empty] | Security | OPEN | [10 empty] | Open | Open | Open
333 | T334 | 472 | NA |  |  |  | Security & Regulatory Compliance | Functional AT | Cisco Firewall, ISE, IPS/IDS Functional AT |  |  | Open |  |  | 28-Nov-25: Document preparation in progress once done points will be closed. Completed and Review pending. | [12 empty] | Security | OPEN | [10 empty] | Open | Open | Open
334 | T335 | 472 | NA |  |  |  | Security & Regulatory Compliance | Design & Documentation | Security LLD to finalised and submitted to T-Fiber for approval. Customer has requested a complete Security LLD that states how our security architechture is and how different security products talk to each other |  |  | Open |  |  | 28-Nov-25: Document preparation in progress once done points will be closed. Duplicate of point 306 | [12 empty] | Security | OPEN | [10 empty] | Open | Open | Open
335 | T336 | 472 | NA |  |  |  | IP/MPLS | T-Cell Solution Design | Egress QoS policy for ASR907 |  |  | Colosed | [15 empty] | IPMPLS | Closed | [8 empty] | 2025-05-05 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\QOS for TFiber Network LLD V2.0 - T339, T340, T341, T342.pdf | Completed & Approved | Closed before june-2025 | Closed before june-2025
336 | T337 | 472 | NA |  |  |  | IP/MPLS | T-Cell Solution Design | Egress QoS policy for ASR920 – QoS policy to be applied on Gigabit interfaces instead of on Port Channel (LAG) which is not suitable for CIR application |  |  | Colosed | [15 empty] | IPMPLS | Closed | [8 empty] | 2025-05-05 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\TFIBER T-CELL Service Design & Solution V4.3 T197, T336, T337, T338.pdf | Completed & Approved | Closed before june-2025 | Closed before june-2025
337 | T338 | 472 | NA |  |  |  | IP/MPLS | T-Cell Solution Design | Additional scenarios for generic Cell tower Solution shared with Cisco, Cisco to check and provide the design |  |  | Colosed | [15 empty] | IPMPLS | Closed | [8 empty] | 2025-05-05 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\TFIBER T-CELL Service Design & Solution V4.3 T197, T336, T337, T338.pdf | Completed & Approved | Closed before june-2025 | Closed before june-2025
338 | T339 | 472 | NA |  |  |  | IP/MPLS | MPLS Core network QoS | Egress Policy structure and BW as per discussion |  |  | Colosed | [15 empty] | IPMPLS | Closed | [8 empty] | 2025-05-05 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\QOS for TFiber Network LLD V2.0 - T339, T340, T341, T342.pdf | Completed & Approved | Closed before june-2025 | Closed before june-2025
339 | T340 | 472 | NA |  |  |  | IP/MPLS | MPLS Core network QoS | Egress QoS policy for ASR99xx |  |  | Colosed | [15 empty] | IPMPLS | Closed | [8 empty] | 2025-05-05 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\QOS for TFiber Network LLD V2.0 - T339, T340, T341, T342.pdf | Completed & Approved | Closed before june-2025 | Closed before june-2025
340 | T341 | 472 | NA |  |  |  | IP/MPLS | MPLS Core network QoS | Egress QoS policy for ASR907 |  |  | Colosed | [15 empty] | IPMPLS | Closed | [8 empty] | 2025-05-05 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\QOS for TFiber Network LLD V2.0 - T339, T340, T341, T342.pdf | Completed & Approved | Closed before june-2025 | Closed before june-2025
341 | T342 | 472 | NA |  |  |  | IP/MPLS | MPLS Core network QoS | Egress QoS policy for ASR920 |  |  | Colosed | [15 empty] | IPMPLS | Closed | [8 empty] | 2025-05-05 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\QOS for TFiber Network LLD V2.0 - T339, T340, T341, T342.pdf | Completed & Approved | Closed before june-2025 | Closed before june-2025
342 | T343 | 472 | NA |  |  |  | IP/MPLS | Service Solution | Design Document require SDC content to GI |  |  | Open |  |  | 22-Sep-25: Need to review plan and approve 12-Sep-25 : Peering plan submitted as per discussion on 11-Sep-25 01-Jul-25 : Design document submitted with suggested approaches. Require inputs from TFiber to | co | nduct | PoC | and fina | e service de |  | sig | n. |  |  |  |  | IPMPLS | Closed |  |  |  |  | liz |  |  |  | 2025-10-31 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\T-Fiber & SDC Peering Plan V1.1 - T193 T343.pdf | Closed | Closed After 14-Oct | Open
343 | T344 | 472 | NA |  |  |  | IP/MPLS | Service Solution | Solution document for GI connectivity (intranet & internet) TVPN |  |  | Open |  |  | 22-Sep-25:Artefacts to be uploaded 01-Jul-25 : Design document submitted with suggested approaches. Require inputs from TFiber to conduct PoC and finalize service design. | [12 empty] | IPMPLS | Closed | [8 empty] | 2025-09-23 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\T-FIBER RYTHUVEDIKA VC L3VPN Solution LLD V1.0.docx | Completed & Approved | Closed before june-2025 | Closed after June
344 | T345 | 472 | NA |  |  |  | TNOC-Ops | NOC Operation | OEM Professional services for all products post NOC operationalization |  |  | Open |  |  | AMC and TAC support provided | [12 empty] | Network | OPEN | [10 empty] | Open | Open | Open
345 | T346 | 472 | NA |  |  |  | BSS | TNOC-Ops | all EMS Devices for provisioning through BSS |  |  | Open |  |  | BSS will not directly interact with any EMS, it will be via A&O. | [12 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
346 | T347 | 472 | NA |  |  |  | BSS | Functional AT | Lead to Cash, Order to cash & Request to resolution to operate and demonestrate |  |  | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
347 | T348 | 472 | NA | P3 |  |  | TNOC-Ops | NOC Operation | Placement of T-Fiber logo and Telangana State emblem in TNOC reception area |  |  | Open |  |  | Logo design agreed with customer. Additional places sign boards to be placed as part of CR, give to commercail for quotation. | [12 empty] | Network | OPEN |  |  |  | Logo | [6 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
348 | T349 | 472 | NA |  |  |  | Security & Regulatory Compliance | Design & Documentation | TNOC operational framework with respect to processes (Incident, Problem, Major Event, Change, Version, Security, AAA, Planned Event, SLA Management etc) |  |  | Open |  |  | Customer has to choose what framework they ned to follow for end to end governance i.e COBIT, COSO, SABSA etc. Security SOP is in progress. will be aligned only after policy is approved | [12 empty] | Security | Closed | [8 empty] | 2025-11-01 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\NW-Security\T349_31-Oct-25.pdf | Completed & Approved | Closed After 14-Oct | Open
349 | T350 | 472 | NA | P3 |  |  | TNOC-Ops | NOC Operation | Manpower Structure for TNOC Operationalization |  |  | Colosed | [15 empty] | Network | Closed |  |  |  | Manpower |  |  |  |  | 2025-05-13 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\T166 | Completed & Approved | Closed before june-2025 | Closed before june-2025
350 | T351 | 472 | NA |  |  |  | TNOC-Ops | Design & Documentation | Helpdesk Readiness Plan |  |  | Open |  |  | 01-Dec-25: its documentation 1. Soft training completed on 06&07 Sep-24 2. All Resources will be from L&T only- Resource available to handle current calls 3. updated process document shared, Pending for di | scu | ssion | 4. | SOP Submi | d for inboun |  | d a | nd |  |  | outb | ound calls- Discussion Pending 5. Regulatory reports were available(DOT) 6. Integration with OSS and BSS is Pending 7. Based on trainer suggestion, implemented day to day and weekly assestments 8. Neox call Manager functioanlity validated as standlone 9. All Features required for Call Manager completed including Business Helpdesk 10. LLD and RFP Compliance also ready for review | Network | OPEN |  |  |  |  | tte | [5 empty] | Open | Open | Open
351 | T352 | 472 | NA |  |  |  | TNOC-Ops | MoM Action | Induction Training program – To be developed and feedback mechanism to be considered, for newly on-boarded resources |  |  | Colosed | [15 empty] | Network | Closed | [8 empty] | 2025-05-13 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\T166 | Completed & Approved | Closed before june-2025 | Closed before june-2025
352 | T353 | 472 | NA |  |  |  | TNOC-Ops | Helpdesk | Regulatory Compliance_PMR on QoS |  |  | Colosed | [15 empty] | Network | Closed | [8 empty] | 2025-05-13 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\T353 | Completed & Approved | Closed before june-2025 | Closed before june-2025
353 | T354 | 472 | NA | P3 |  |  | TNOC-Ops | NOC Operation | Resource deployment at TNOC |  |  | Colosed | [15 empty] | Network | Closed |  |  |  | Not related to delivery |  |  |  |  | 2025-05-13 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\T166 | Completed & Approved | Closed before june-2025 | Closed before june-2025
354 | T355 | 472 | NA | P3 |  |  | TNOC-Ops | NOC Operation | Interlocking and Interdependencies with resources of package B & C operating at TNOC |  |  | Open | [15 empty] | Network | Closed |  |  |  | Not related to delivery |  |  |  |  | 2025-05-26 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\T166 | Completed & Approved | Closed before june-2025 | Closed after June
355 | T356 | 472 | NA |  |  |  | TNOC-Ops | NOC Operation | OEM Escalation processes for NOC Applications, DBs, IT Infra and Network along with TATs aligned to SLA |  |  | Open | [15 empty] | Network | Closed | [8 empty] | 2025-07-08 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\TNOC | Completed & Approved | Closed before june-2025 | Closed after June
356 | T357 | 472 | NA | P3 |  |  | TNOC-Ops | NOC Operation | Spare for Business continuity - RS&R for NOC and DR elements and assets |  |  | Open |  |  | List shared with commercial for ordering. WIP | [12 empty] | Network | OPEN |  |  |  | Spares for NOC | [6 empty] | Open | Open | Open
357 | T358 | 472 | NA |  |  |  | TNOC-Ops | Functional AT | Network HOTO and KT from Respective Domain and Packages |  |  | Open |  |  | BSS, NSO and Security SOP training pending. Rest all done | [12 empty] | Network | OPEN | [10 empty] | Open | Open | Open
358 | T359 | 472 | NA |  | OSS | OSS | OSS | NOC Operation | OSS - stability and Operational issues with respect to inventory, ticketing and utilization modules |  |  | Open |  |  | 26-06-2025: Frequent stability issues are because of NNMi, OBM instability and Vendor asking for upgrade | [12 empty] | Applications/Tools | OPEN |  | OPEN | FALSE | [7 empty] | Open | Open | Open
359 | T360 | 472 | NA | P3 |  |  | TNOC-Ops | NOC Operation | Domain wise training |  |  | Open |  |  | BSS, NSO and Security SOP training pending. On the job training happening for OSS. Rest all domains done. | [12 empty] | Network | OPEN |  |  |  | Training | [6 empty] | Open | Open | Open
360 | T361 | 472 | NA |  |  |  | TNOC-Ops | Helpdesk | Updated Process document Submission after last Meeting with T Fiber Management |  |  | Colosed | [15 empty] | Network | Closed | [8 empty] | 2025-05-13 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\T361 | Completed & Approved | Closed before june-2025 | Closed before june-2025
361 | T362 | 472 | NA |  |  |  | TNOC-Ops | Helpdesk | Categorisation of incoming calls to be detailed and IVR to bilingual(Incoming IVR call flow) |  |  | Colosed | [15 empty] | Network | Closed | [8 empty] | 2025-05-13 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\T362 | Completed & Approved | Closed before june-2025 | Closed before june-2025
362 | T363 | 472 | NA |  |  |  | TNOC-Ops | Helpdesk | IVR Recording file required for call landing and Hold time |  |  | Colosed | [15 empty] | Network | Closed | [8 empty] | 2025-05-13 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\T363 | Completed & Approved | Closed before june-2025 | Closed before june-2025
363 | T364 | 472 | NA |  |  |  | TNOC-Ops | Helpdesk | Integration with BSS and OSS |  |  | Open |  |  | 01-Dec-25:Depends on IVR flow approval 11-Sep-25: Basic integration completed with BSS and HPSM(Ticketing). IVR has to be freezed to implement same. As per Neox is one time configuration but Since its ongo | ing | chan | ges | will happ | in IVR, So i |  | t w | oul |  |  | d be | configurble as per L&T/T Fiber- Which to be discussed. 360 View also Pending from BSS | Network | OPEN |  |  |  |  | en | [5 empty] | Open | Open | Open
364 | T365 | 472 | NA |  |  |  | TNOC-Ops | Helpdesk | Integration of SMS, E-Mail |  |  | Open |  |  | 29-Nov-25:E-mail & SMS Integration completed. SMS testing pending due to no balance in SMS striker portal. 28 Apri-2025: TFIBER to share SMS GW details to integrate with OSS/BSS. Integration must be confi | gur | able | with | out any c | impact to T |  | FIB | ER. |  |  |  |  | Network | OPEN |  |  |  |  | ost | [5 empty] | Open | Open | Open
365 | T365 | 472 | NA |  |  |  | TNOC-Ops | Helpdesk | Integration of Whatsapp, Chatbot |  |  | Open |  |  | 01-Dec-25:Not feasible 11-Sep-25: Not Part of RFP and Existing product didn’t support, need to upgrade to Omni based Solution. | [12 empty] | Network | OPEN | [10 empty] | Open | Open | Open
366 | T366 | 472 | NA |  |  |  | TNOC-Ops | Helpdesk | Fancy 4 digit number for Helpdesk or Tollfree number Availability |  |  | Open | [15 empty] | Network | Closed | [8 empty] | 2025-07-19 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\T366 | Completed & Approved | Closed before june-2025 | Closed after June
367 | T367 | 472 | NA |  |  |  | TNOC-Ops | Helpdesk | Training for Agents and Helpdesk Manager |  |  | Colosed | [15 empty] | Network | Closed | [8 empty] | 2025-05-13 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\T367 | Completed & Approved | Closed before june-2025 | Closed before june-2025
368 | T368 | 472 | NA |  |  |  | TNOC-Ops | Helpdesk | Interface mechanism between T-NOC Helpdesk and District Collector offices for complaints that may be made directly(Walk-in) to District Collector office, provision for a mini-Helpdesk node at each district, provide a facility/ hotline using which an authorised person can log a call / complaint on behalf of the District Collector Office, such mechanism to be similar to the Direct walk-in channel for customer complaints at T-NOC |  |  | Open | [15 empty] | Network | Closed | [8 empty] | 2025-07-19 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\T368 | Completed & Approved | Closed before june-2025 | Closed after June
369 | T369 | 472 | NA |  |  |  | TNOC-Ops | Helpdesk | If T-NOC is totally down for some reason like fire, earthquake, lockdown etc….then how Helpdesk will work from DR? |  |  | Open |  |  | 01-Dec-25: Helpdesk plan ready, but expecting was complete BCP Solution | [12 empty] | Network | OPEN | [10 empty] | Open | Open | Open
370 | T370 | 472 | NA |  |  |  | TNOC-Ops | Helpdesk | If all 10 lines are engaged for a longer time. Can the Helpdesk system call back to that missed call? |  |  | Open |  |  | 11-Sep-25: OEM confirmed this feature is not available/feasible Based on CDR record with Agent and Manager Login, Call back can be done manually with CDR or Agent Call report. It will be displayed in queue | to | agen | t. B | ut Missed | ll to be han |  | dle | d b |  |  | y ou | tbound team. Which required complete Set of call Center. If required Helpdesk Manager will review missed call to take action accordingly. | Network | OPEN |  |  |  |  | ca | [5 empty] | Open | Open | Open
371 | T371 | 472 | NA |  |  |  | GPON | Nokia | * Testing done for new build in T-Fiber test lab . * Plan event for OLTs new SW upgradation in production environment. |  |  | Open | Nokia OEM | OLT | 15-Nov-25: Below is the breakup of pending OLT status PKG-A : 875/883 PKG-B : 622/653 PKG-C : 419/420 All the OLTs reachabled to AMS are upgraded successfully. Having dependecny on PKG-A/B/C field teams to | ma | ke un | reac | hable OLT | o reachable | [7 empty] | GPON | OPEN |  |  |  |  | s t | [5 empty] | Open | Open | Open
372 | T372 | 472 | NA |  |  |  | GPON | Nokia | TACACS Feature |  |  | Colosed | [15 empty] | GPON | Closed | [8 empty] | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T372 | Completed & Approved | Closed before june-2025 | Closed before june-2025
373 | T373 | 472 | NA |  |  |  | NSO | Deployment and Installations | HSI (High Speed Internet to Household) implementation |  |  | Open |  |  | 19-12-2025:- Plan,scope and schedule for remaining services finalized. |  |  |  | Pending |  |  |  |  | Sayyed/RS sir |  |  |  | Applications/Tools | OPEN |  |  |  |  | 16/03/2026 : Service is not yet implemented waiting for exact technical requirement | [5 empty] | Open | Open | Open
e | T374 | 472 | NA |  |  |  | NSO | Deployment and Installations | IPTV to Household implementation |  |  | Open |  |  | 19-12-2025:- Plan,scope and schedule for remaining services finalized. |  |  |  | Pending |  |  |  |  | Sayyed/RS sir |  |  |  | Applications/Tools | OPEN |  |  |  |  | 16/03/2026 : Service is not yet implemented waiting for exact technical requirement | [5 empty] | Open | Open | Open
375 | T375 | 472 | NA |  |  |  | NSO | Deployment and Installations | VOIP to Household implementation |  |  | Open |  |  | 19-12-2025:- Plan,scope and schedule for remaining services finalized. |  |  |  | Pending |  |  |  |  | Sayyed/RS sir |  |  |  | Applications/Tools | OPEN |  |  |  |  | 16/03/2026 : Service is not yet implemented waiting for exact technical requirement | [5 empty] | Open | Open | Open
376 | T376 | 472 | NA |  |  |  | NSO | Deployment and Installations | Internet to GI (Govt. Institution) implementation |  |  | Open |  |  | 19-12-2025:- Except Tejas all completed. In the call dated 19-dec-2025 sg350 and other new scenarios identified. |  |  |  | Need Clarification |  |  |  |  | Sayyed/RS sir |  |  |  | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
377 | T377 | 472 | NA |  |  |  | NSO | Deployment and Installations | CCTV Unicast implementation |  |  | Open |  |  | 19-12-2025:- Plan,scope and schedule for remaining services finalized. |  |  |  | Pending |  |  |  |  | Sayyed/RS sir |  |  |  | Applications/Tools | OPEN |  |  |  |  | 16/03/2026 : Service is not yet implemented waiting for exact technical requirement | [5 empty] | Open | Open | Open
378 | T378 | 472 | NA |  |  |  | NSO | Deployment and Installations | CCTV Multicast implementation |  |  | Open |  |  | 19-12-2025:- Plan,scope and schedule for remaining services finalized. |  |  |  | Pending |  |  |  |  | Sayyed/RS sir |  |  |  | Applications/Tools | OPEN |  |  |  |  | 16/03/2026 : Service is not yet implemented waiting for exact technical requirement | [5 empty] | Open | Open | Open
379 | T379 | 472 | NA |  |  |  | NSO | Deployment and Installations | Cell Tower L2VPN implementation |  |  | Open |  |  | 19-12-2025:- Plan,scope and schedule for remaining services finalized. |  |  |  | Pending |  |  |  |  | Sayyed/RS sir |  |  |  | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
380 | T380 | 472 | NA |  |  |  | NSO | Deployment and Installations | Dhanush Telemedicine Application implementation |  |  | Open |  |  | 29-dec-2025: Not clear with comment |  |  | L3VPN; check with RS | [5 empty] | RS sir |  |  |  | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
381 | T381 | 472 | NA |  |  |  | NSO | Deployment and Installations | SDC content to Household and GI implementation |  |  | Open |  |  | 19-12-2025:- Plan,scope and schedule for remaining services finalized. |  |  | take input from RS | [5 empty] | Sayyed/RS sir |  |  |  | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
382 | T382 | 472 | NA |  |  |  | BSS | Development and unit testing | EY need to present landing page for suggestion - Design features of web page |  |  | Open | [15 empty] | Applications/Tools | CLOSED | [8 empty] | 2025-07-16 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\BSS\Artifact_T382 | Open | Open | Open
383 | T383 | 472 | NA |  |  |  | DC-IT | Functional AT | Cisco prime infrastructure AT |  |  | Open |  |  | 22-Sep-25: IPMPLS Domain team to submit detailed remarks on raised queries. 08-Jul-2025 - Sandeep will come back by EoD today on extension of Cisco support renewal 01-Jul-25 : Revised FAT documents submiss | ion | pend | ing | (TPA obs | ations to be |  | in | clu |  |  | ded) | OEM(Cisco) suport is required to show the new test cases, Inputs provided to OEM on 14th May & 30th Jun. OEM onboarding is in progress & LnT Contracts team is coordinating | Network | OPEN |  |  |  |  | erv | [5 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
384 | T384 | 472 | NA |  |  |  | IP/MPLS | Security | GCT implementation |  |  | Open |  |  | Confirmed from IP-MPLS team for GCT implementation. | [12 empty] | IPMPLS | Closed | [8 empty] | 2025-11-01 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\NW-Security\T384_31-Oct-25.pdf | Closed | Closed After 14-Oct | Open
385 | T385 | 472 | NA |  |  |  | NSO | Design & Documentation | solution document - GI internet solution |  |  | Open |  |  | 19-12-2025:- Network Team solution document |  |  |  | Pending |  |  |  |  | Sayyed/RS sir |  |  |  | Applications/Tools | Closed | [8 empty] | 2025-05-05 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\T-FIBER T-Net for GI Broadband Service Design LLD V1.1 - T188.pdf | Completed & Approved | Closed before june-2025 | Closed after June
386 | T386 | 472 | NA |  |  |  | Security & Regulatory Compliance | Testing | Network audit and certification by ISO certified agency(Tfiber will be arranging a partner for third party audit) |  |  | Open |  |  | 28-Nov-25: VAPT is going on, once VAPT is done points will be closed. Subject to start of certification process. | [12 empty] | Security | OPEN | [8 empty] | 2025-12-19 |  | Completed &Approved | Closed after 14-Dec-25 | Completed &Approved
387 | T387 | 472 | NA |  |  |  | Security & Regulatory Compliance | Regulatory compliance | SLA Reporting for products other than Cell Tower and GIs |  |  | Colosed | [15 empty] | Security | Closed | [8 empty] | 2025-05-13 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\T387 | Completed & Approved | Closed before june-2025 | Closed before june-2025
388 | T388 | 472 | NA |  | OSS | OSS | OSS | Helpdesk | OSS Integration with Helpdesk |  |  | Open |  |  | 17-05-2025: Artefacts needs to be collected from Sivakumar and seek approval. 26-06-2025: completed from OSS end | [12 empty] | Applications/Tools | OPEN |  | Completed With Artifacts | FALSE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
389 | T389 | 472 | NA |  | OSS | OSS | OSS | OSS | BBNL Report stabilization |  |  | Open | [15 empty] | Applications/Tools | Closed | 0 | Closed/Approved | TRUE | [6 empty] | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\OSS\T389 | Completed & Approved | Closed before june-2025 | Closed after June
390 | T390 | 472 | NA |  | OSS | OSS | OSS | OSS Dashboards | OSS Power BI Dashboard |  |  | Open |  |  | 18-Nov-25: Power BI not there, Same to be shown in new Application 09-09-2025: Requested reports are available, if any additional reports needed that can be incorporated | [12 empty] | Applications/Tools | OPEN | 09-09-2025: Requested reports are available, if any additional reports needed that can be incorporated | Completed With Artifacts | TRUE | [7 empty] | Reopened | Reopened | Completed but Verification undrer Process
391 | T391 | 472 | NA |  | OSS | OSS | OSS | OSS | Auto TT for Genset |  |  | Open |  |  | 26-06-2025: Confirmation awaited from NOC | [12 empty] | Applications/Tools | Closed |  | Completed With Artifacts | FALSE | [5 empty] | 2025-11-18 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\OSS\52 Artefcats_18112025 | Closed after 14-Nov-25 | Closed after 14-Nov-25 | Completed but Verification undrer Process
392 | T392 | 472 | NA |  | OSS | OSS | OSS | OSS | BBNL Status and Availability API integration |  |  | Open | [15 empty] | Applications/Tools | Closed | 0 | Closed/Approved | TRUE | [6 empty] | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\OSS\T392 | Completed & Approved | Closed before june-2025 | Closed after June
393 | 394 | 472 | NA |  |  |  | DC-IT | License | Once excel license for VM |  |  | Open | [15 empty] | Network | Closed | [8 empty] | 2025-07-08 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\TNOC\Artifact for - 394 | Completed & Approved | Closed before june-2025 | Closed after June
394 | T395 | 472 | NA |  |  |  | TNOC-Ops | Payments | SMS Gateway recharge |  |  | Open |  |  | SMS payment pending from Tfiber | [12 empty] | Network | Closed | [8 empty] | 2025-07-08 | Artefacts not Required | Completed & Approved | Closed before june-2025 | Closed before june-2025
395 | 396 | 472 | NA |  |  |  | TNOC-Ops | AMC | AMC status including HPE/OT |  |  | Open |  |  | In Place | [12 empty] | Network | Closed | [8 empty] | 2025-07-08 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\TNOC | Completed & Approved | Closed before june-2025 | Closed after June
396 | 397 | 472 | NA |  |  |  | TNOC-Ops | Security | Access cards - 38 QTY |  |  | Open |  |  | Access card procured | [12 empty] | Network | Closed | [8 empty] | 2025-07-08 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\TNOC | Completed & Approved | Closed before june-2025 | Closed after June
397 | 398 | 472 | NA |  |  |  | GPON | Tejas | L&T is asked to submit response against untdertakings for the GPON Tejas issues |  |  | Colosed | [15 empty] | GPON | Closed | [8 empty] | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\Tejas Undertaking | Completed & Approved | Closed before june-2025 | Closed before june-2025
398 | 399 | 472 | NA |  |  |  | GPON | Tejas | Requested Tejas to enable the TR-069 for T-Fiber deployed elements |  |  | Open | Tejas OEM | ONT | 20-Sep-25: Artefacts submiited and approved MoM point Not in RFP and L&T confirmed this is not in scope. However, confirmation awaited from OEM on the shared list of parameters | [12 empty] | GPON | Closed | [8 empty] | 2025-09-20 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\399 | Completed & Approved | Closed before june-2025 | Closed after June
399 | T400 | 472 | NA |  |  |  | GPON | Tejas | Accounting for Tejas OLT and EMS |  |  | Colosed | [15 empty] | GPON | Closed | [8 empty] | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T167 | Completed & Approved | Closed before june-2025 | Closed
400 | 401 | 472 | NA |  |  |  | GPON | Tejas | Accounting: All the parameters are not available in service created and Activated log(Including creation/activation of UNI) |  |  | Colosed | [15 empty] | GPON | Closed | [8 empty] | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T167 | Completed & Approved | Closed before june-2025 | Closed before june-2025
401 | 402 | 472 | NA |  |  |  | GPON | Tejas | Accounting: All the parameters are not available in service deactivated and deleted log(Including deactivation/deletion of UNI) |  |  | Colosed | [15 empty] | GPON | Closed | [8 empty] | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T167 | Completed & Approved | Closed before june-2025 | Closed before june-2025
402 | 403 | 472 | NA |  |  |  | GPON | Tejas | Accounting: Log is not available for OLT reboot |  |  | Colosed | [15 empty] | GPON | Closed | [8 empty] | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T167 | Completed & Approved | Closed before june-2025 | Closed before june-2025
403 | 404 | 472 | NA |  |  |  | GPON | Tejas | Accounting: Log is not available for ONT reboot |  |  | Colosed | [15 empty] | GPON | Closed | [8 empty] | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T167 | Completed & Approved | Closed before june-2025 | Closed before june-2025
404 | 405 | 472 | NA |  |  |  | GPON | Tejas | Accounting: Log is not available for the change of OLT location parameter from EMS |  |  | Colosed | [15 empty] | GPON | Closed | [8 empty] | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T167 | Completed & Approved | Closed before june-2025 | Closed before june-2025
405 | 406 | 472 | NA |  |  |  | GPON | Tejas | Enabling TACACS in Tejas OLT |  |  | Colosed | [15 empty] | GPON | Closed | [8 empty] | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T167 | Completed & Approved | Closed before june-2025 | Closed before june-2025
406 | 407 | 472 | NA |  |  |  | GPON | Tejas | CIR/PIR in OLT/EMS |  |  | Open | Tejas OEM | EMS/OLT | 20-Sep-25: CIR and PIR are different parameters but Tejas OLT considered only CIR not PIR, After combined recent meeting with OEM agreed to provide an alternate solution for config CIR and PIR seperately. | Up | date | awai | ted from | Tejas to pr |  | ovi | de |  |  | the | solution and demo for this issue. Update awaited from OEM | GPON | OPEN |  |  |  |  | OEM | [5 empty] | Open | Open | Open
407 | 408 | 472 | NA |  |  |  | GPON | Tejas | Port Description is not available for ONT Eth Ports |  |  | Colosed | [15 empty] | GPON | Closed | [8 empty] | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\ONT Ports description | Completed & Approved | Closed before june-2025 | Closed before june-2025
408 | 409 | 472 | NA |  |  |  | GPON | Tejas | Unable to modify the Service Name |  |  | Open | [15 empty] | GPON | Closed | [8 empty] | 2025-07-03 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\409 | Completed & Approved | Closed before june-2025 | Closed after June
409 | 410 | 472 | NA |  |  |  | GPON | Tejas | Special Characters not allowing in User Creation in EMS |  |  | Colosed | [15 empty] | GPON | Closed | [8 empty] | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\Special Characters | Completed & Approved | Closed before june-2025 | Closed before june-2025
410 | 411 | 472 | NA |  |  |  | GPON | Tejas | Unable to add 4th UNI in a service with 1Gb bandwidth |  |  | Colosed | [15 empty] | GPON | Closed | [8 empty] | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\Report of ONT UNI in a Service | Completed & Approved | Closed before june-2025 | Closed before june-2025
411 | 412 | 472 | NA |  |  |  | GPON | Tejas | End Customer MAC Address report from EMS |  |  | Colosed | [15 empty] | GPON | Closed | [8 empty] | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\Ens users MAC address report | Completed & Approved | Closed before june-2025 | Closed before june-2025
412 | 413 | 472 | NA |  |  |  | GPON | Tejas | If Mixed service deleted from EMS and discovered then service type is changing to HIS |  |  | Colosed | [15 empty] | GPON | Closed | [8 empty] | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\Discovery of Mixed Service | Completed & Approved | Closed before june-2025 | Closed before june-2025
413 | 414 | 472 | NA |  |  |  | GPON | Tejas | Live PM monitoring per UNI in EMS service Window |  |  | Open | [15 empty] | GPON | Closed | [8 empty] | 2025-07-10 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\416 | Completed & Approved | Closed before june-2025 | Closed after June
414 | 415 | 472 | NA |  |  |  | GPON | Tejas | Required Consolidated Service invenotry report with ONT UNI details from EMS |  |  | Colosed | [15 empty] | GPON | Closed | [8 empty] | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\Serivce Report | Completed & Approved | Closed before june-2025 | Closed before june-2025
415 | 416 | 472 | NA |  |  |  | GPON | Tejas | Unable to Enable PM from EMS |  |  | Open | [15 empty] | GPON | Closed | [8 empty] | 2025-07-07 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\414 | Completed & Approved | Closed before june-2025 | Closed after June
416 | 417 | 472 | NA |  |  |  | GPON | Tejas | While creating service profile, maximum bandwidth is not taking 1024000 only considering 1000000 |  |  | Open | [15 empty] | GPON | Closed | [8 empty] | 2025-07-31 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\417 | Completed & Approved | Closed before june-2025 | Closed after June
417 | 418 | 472 | NA |  |  |  | GPON | Tejas | Report of Syslog enabled in OLT |  |  | Colosed | [15 empty] | GPON | Closed | [8 empty] | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\Report of Syslog enabled in Tejas OLTs | Completed & Approved | Closed before june-2025 | Closed before june-2025
418 | 419 | 472 | NA |  |  |  | GPON | Tejas | Report of Radius enable in OLT |  |  | Colosed | [15 empty] | GPON | Closed | [8 empty] | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\Report of Radius enabled in Tejas OLTs | Completed & Approved | Closed before june-2025 | Closed before june-2025
419 | 420 | 472 | NA |  |  |  | GPON | Tejas | OLT (SNMP-V3) status is not updating in EMS |  |  | Colosed | [15 empty] | GPON | Closed | [8 empty] | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T167 | Completed & Approved | Closed before june-2025 | Closed before june-2025
420 | 421 | 472 | NA |  |  |  | GPON | Tejas | ONT status showing as Unexpected |  |  | Colosed | [15 empty] | GPON | Closed | [8 empty] | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\ONT Unexpected State | Completed & Approved | Closed before june-2025 | Closed before june-2025
421 | 422 | 472 | NA |  |  |  | GPON | Tejas | Unable to add multiple unis while creating mixed service |  |  | Colosed | [15 empty] | GPON | Closed | [8 empty] | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\Create Service with Mulitple UNIs | Completed & Approved | Closed before june-2025 | Closed before june-2025
422 | 423 | 472 | NA |  |  |  | GPON | Tejas | ONT ETH Port status monitoring from OSS |  |  | Colosed | [15 empty] | GPON | Closed | [8 empty] | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\Tejas LAN LOS | Completed & Approved | Closed before june-2025 | Closed before june-2025
423 | 424 | 472 | NA |  |  |  | GPON | Tejas | Unable to create service with same vlans on 2 diferent UNI ports |  |  | Colosed | [15 empty] | GPON | Closed | [8 empty] | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\Service Report | Completed & Approved | Closed before june-2025 | Closed before june-2025
424 | 425 | 472 | NA |  |  |  | GPON | Tejas | OLT Node not reachable alarm clearance and regeneration |  |  | Open | [15 empty] | GPON | Closed | [8 empty] | 2025-07-05 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\425 | Completed & Approved | Closed before june-2025 | Closed after June
425 | 426 | 472 | NA |  |  |  | GPON | Tejas | Port Description is not available for all ONT UNI Ports |  |  | Colosed | [15 empty] | GPON | Closed | [8 empty] | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\ONT Ports description | Completed & Approved | Closed before june-2025 | Closed before june-2025
426 | 427 | 472 | NA |  |  |  | GPON | Tejas | In the Manage ONT Page we need have'(District name Location Name) 'In the Location field |  |  | Colosed | [15 empty] | GPON | Closed | [8 empty] | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\OLT Partition Label in ONT Page | Completed & Approved | Closed before june-2025 | Closed before june-2025
427 | 428 | 472 | NA |  |  |  | GPON | Tejas | Automatically services converting from Active to Conflict - EMS |  |  | Colosed | [15 empty] | GPON | Closed | [8 empty] | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T167 | Completed & Approved | Closed before june-2025 | Closed before june-2025
428 | 429 | 472 | NA |  |  |  | GPON | Tejas | DIAGUSER credentials getting reset after OLT Reboot |  |  | Colosed | [15 empty] | GPON | Closed | [8 empty] | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\DIAGUSER Credentials are Not Resetting | Completed & Approved | Closed before june-2025 | Closed before june-2025
429 | 430 | 472 | NA |  |  |  | GPON | Tejas | while adding uni in EMS, list of downstream profiles are highlighting in the bottom |  |  | Open | [15 empty] | GPON | Closed | [8 empty] | 2025-07-05 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\430 | Completed & Approved | Closed before june-2025 | Closed after June
430 | 431 | 472 | NA |  |  |  | GPON | Tejas | Unable to add uni without translation in a translation service |  |  | Colosed | [15 empty] | GPON | Closed | [8 empty] | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\Add UNI in Translated Service | Completed & Approved | Closed before june-2025 | Closed before june-2025
431 | 432 | 472 | NA |  |  |  | GPON | Tejas | Nokia ONT ethernet port status is not updating under Tejas OLT | End user services working and not working status unable to monitor |  | Open | Tejas OEM | OLT/ONT | 15-Nov-25: A call will be scheduled with Tejas and Nokia, along with Tfiber for the conclusion of this issue 13-Sep-2025: Testing is in progress for the ONT ETH status for different 3rd party ONTs under T | eja | s OLT | 30- | Aug-2025: | ving depende |  | ncy | on |  |  | bot | h Tejas and Nokia. Also to test and verify the behaviour of the ONT ETH status for different 3rd party ONTs under Tejas OLT 18-Aug-2025 : Tejas updated as below As per ITU-T 988 standard, Section 9.5.1 – Physical path termination point Ethernet UNI, the Operational State attribute indicated whether the ME is capable of performing its function. As this is function of ONU, the operational state of the ONU Ethernet UNI is updated to OLT via AVC indications from the ONU. As per debugging done, the AVC indications are not received from Nokia ONU because of which OLT is not able to update UI about the “Operational State” of the ONU Ethernet port. 08-Aug-2025 : This point has been discussed in the call and TFiber asked to provide the solution. Tejas confirmed that they will check and confirm 02-Aug-2025 : This issue has been discussed with TFiber. When a LAN cable is connected to or removed from the ONT Ethernet port, the operational status is not updating in the OLT. However, the corresponding alarm is being generated and cleared as expected. This matter will be raised during the Tejas call scheduled for 04-Aug-2025 at 4:00 PM. 22-July-2025 : As per Nokia they are having the status update by alarm notification but not with the seperate byte for the status update. Same has been checking with Tejas to get the solution 18-July-2025 : A call scheduled with Nokia on 21-July-2025 to discuss on this issue 11-July-2025 : Also observed that ONT ethernet status is not updating only when Eth port is bridge mode whereas in Route status is updating. Same has been highlighted to Tejas. Working with both Nokia and Tejas for the closure 04-July-2025 : Nokia checking internally on the shared logs 03-July-2025 : Tejas responded that whenever ONT eth status is updating Nokia ONT is not sending the expected OMCI message. In the OMCI message, 3rd byte represents the status of ONT Eth which is not updating. Same has been checking with Nokia 30-June-2025 : Tejas analysing the shared logs on 23-June-2025 and Tejas has to revert with update Nokia ONT ethernet port status is not updating when connected under Tejas OLT however alarms are receiveing on ont eth port. Workaround applied as alarms available for the ONT ETH port status. Nokia has provided the required logs and Tejas is working on the same | GPON | OPEN |  |  |  |  | Ha | [5 empty] | Open | Open | Open
432 | 433 | 472 | NA |  |  |  | GPON | Tejas | Tejas ONT Software Upgrade which are connected under Nokia OLT |  |  | Open | Tejas OEM | ONT | 15-Nov-25: ONT upgrade is in progress 20-Sep-25: During the ONT software upgradation 11 ONTs got faulty, So GPON Team asked the Tejas team to provided RCA for the 11 ONTs and hold the upgradation activity | te | mpora | rely | . Tejas t | provided th |  | e R | CA |  |  | 11 O | Nt Stating that 11 ONTs got faulty not because of upgradation activity . The reason for faulty is 3 ONTs of component and 8 ONTs of Memory corrupted due to multiple reboots. Note: Based on RCA, Now upgradation activity is being taken up(1312 ONTs upgradation completed out of 9530 as on today) 13-Sep-2025: Tejas confirmed that they don't have the 9logs to provide but shared the RCA by verifyting the ONTs at the time of repair 30-Aug2025: Having dependency on Tejas. Asked Tejas to provide the supporting logs. As per Tejas RCA ONT got faulty due to component faulty and memory corruption but these ONTs are working fine before the upgarde activity and only went faulty while performing the upgrade. Tejas have provide the clarity on this to proceed the upgrade for the remaining ONTs 08-Aug-2025 : Tejas provided the below RCA As per analysis, the ONT software upgrade from NOC is not the cause for ONT going down. On 3 ONTs a component was entering faulty state, this has been replaced. Remaining 8 ONTs had a file corruption in memory due to earlier multiple reboot events, this has been resolved by Re-Programming the ONT 02-Aug-2025 : Tejas yet to respond on this issue, same will be raised during the Tejas call scheduled for 04-Aug-2025 at 4:00 PM. 25-July-2025 : Tejas working on the delivered ONTs at their repair center. Tejas yet to share the update on this 14-July-2025 : ONTs delivered at Tejas repair center on 14-July-2025. Same has been communicated to Tejas team to expedite the process and share the RCA 14-July-2025 : ONT still not delivered at Tejas repai center, seems to be courier issue. Informed to concerned team to check and make it to delivier 07-July-2025 : ONTs are intransit to Tejas repair center To provide the contract of RMA on faulty devices replacement or repair 30-June-2025 : Successfully upgraded 600 ONTs in the production environment. All of them came up operational with no issue observed. However, 11 ONTs went unresponsive, and RMA raised for those. 23-June-2025 : RMA raised with Tejas for the ONTs ONTs which are running software version lower than 2.3.5.53 are upgrading locally | GPON | OPEN |  |  |  |  | eam | [5 empty] | Open | Open | Open
433 | 434 | 472 | NA |  |  |  | GPON | Tejas | Script to change the pasword of DIAGUSER and tejas users |  |  | Colosed | [15 empty] | GPON | Closed | [8 empty] | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\434 | Completed & Approved | Closed before june-2025 | Closed before june-2025
434 | 435 | 472 | NA |  |  |  | GPON | Tejas | Unable to configure downstream profiles to the ONT UNIs -- This option is available in production EMS but not available in latest released EMS |  |  | Colosed | [15 empty] | GPON | Closed | [8 empty] | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T167 | Completed & Approved | Closed before june-2025 | Closed before june-2025
435 | 436 | 472 | NA |  |  |  | GPON | Tejas | MAC address of end device is not reflecting in COLT FDB entries whereas MAC address is available in service level FDB entries |  |  | Colosed | [15 empty] | GPON | Closed | [8 empty] | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T167 | Completed & Approved | Closed before june-2025 | Closed before june-2025
436 | 437 | 472 | NA |  |  |  | GPON | Tejas | Whenever the ONT software is being downloaded to the OLT, the OLT management going down |  |  | Open | [15 empty] | GPON | Closed | [8 empty] | 2025-07-31 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\437 | Completed & Approved | Closed before june-2025 | Closed after June
437 | 438 | 472 | NA |  |  |  | GPON | Tejas | The download bandwidth is not controlled for Nokia ONTs connected to the Tejas OLT |  |  | Colosed | [15 empty] | GPON | Closed | [8 empty] | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T167 | Completed & Approved | Closed before june-2025 | Closed before june-2025
438 | 439 | 472 | NA |  |  |  | GPON | Tejas | Unable to add node in EMS with TACACS user |  |  | Colosed | [15 empty] | GPON | Closed | [8 empty] | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T167 | Completed & Approved | Closed before june-2025 | Closed before june-2025
439 | 440 | 472 | NA |  |  |  | GPON | Tejas | API for ONT creation (Bridge/Route), location name update |  |  | Colosed | [15 empty] | GPON | Closed | [8 empty] | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API | Completed & Approved | Closed before june-2025 | Closed before june-2025
440 | 441 | 472 | NA |  |  |  | GPON | Tejas | API for GI-BB Service, combo port, mixed service - Bridge Mode with/without translation, including uplink port configuration |  |  | Colosed | [15 empty] | GPON | Closed | [8 empty] | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API | Completed & Approved | Closed before june-2025 | Closed before june-2025
441 | 442 | 472 | NA |  |  |  | GPON | Tejas | API for GI-BB Service, combo port, mixed service - Route Mode with/without translation, including uplink port configuration |  |  | Open | [15 empty] | GPON | Closed | [8 empty] | 2025-08-06 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\442 | Completed & Approved | Closed before june-2025 | Closed after June
442 | 443 | 472 | NA |  |  |  | GPON | Tejas | API for TDIA Service, combo port, mixed service - Bridge Mode(Tag, Untag) including uplink port configuration |  |  | Colosed | [15 empty] | GPON | Closed | [8 empty] | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API | Completed & Approved | Closed before june-2025 | Closed before june-2025
443 | 444 | 472 | NA |  |  |  | GPON | Tejas | API for TDIA Service, combo port, mixed service - Route Mode, including uplink port configuration |  |  | Colosed | [15 empty] | GPON | Closed | [8 empty] | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API | Completed & Approved | Closed before june-2025 | Closed before june-2025
444 | 445 | 472 | NA |  |  |  | GPON | Tejas | API for Household Services, including uplink port configuration |  |  | Colosed | [15 empty] | GPON | Closed | [8 empty] | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API | Completed & Approved | Closed before june-2025 | Closed before june-2025
445 | 446 | 472 | NA |  |  |  | GPON | Tejas | AP for IPTV services, including uplink port configuration |  |  | Colosed | [15 empty] | GPON | Closed | [8 empty] | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API | Completed & Approved | Closed before june-2025 | Closed before june-2025
446 | 447 | 472 | NA |  |  |  | GPON | Tejas | API for VOIP services, including uplink port configuration |  |  | Colosed | [15 empty] | GPON | Closed | [8 empty] | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API | Completed & Approved | Closed before june-2025 | Closed before june-2025
447 | 448 | 472 | NA |  |  |  | GPON | Tejas | API required to provision ONT along with selecting specific UNI port in ONT |  |  | Colosed | [15 empty] | GPON | Closed | [8 empty] | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API | Completed & Approved | Closed before june-2025 | Closed before june-2025
448 | 449 | 472 | NA |  |  |  | GPON | Tejas | API required to provision ONT with multiple services along with selecting specific UNI port in ONT |  |  | Colosed | [15 empty] | GPON | Closed | [8 empty] | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API | Completed & Approved | Closed before june-2025 | Closed before june-2025
449 | 450 | 472 | NA |  |  |  | GPON | Tejas | API required to provision ONT with same service on all ports |  |  | Colosed | [15 empty] | GPON | Closed | [8 empty] | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API | Completed & Approved | Closed before june-2025 | Closed before june-2025
450 | 451 | 472 | NA |  |  |  | GPON | Tejas | API to configure multiple vlans on single ONT UNI Port |  |  | Colosed | [15 empty] | GPON | Closed | [8 empty] | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API | Completed & Approved | Closed before june-2025 | Closed before june-2025
451 | 452 | 472 | NA |  |  |  | GPON | Tejas | API for the Q&Q services |  |  | Colosed | [15 empty] | GPON | Closed | [8 empty] | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API | Completed & Approved | Closed before june-2025 | Closed before june-2025
452 | 453 | 472 | NA |  |  |  | GPON | Tejas | Configuration, API for extedning services to enterprise customers for cell towers |  |  | Colosed | [15 empty] | GPON | Closed | [8 empty] | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API | Completed & Approved | Closed before june-2025 | Closed before june-2025
453 | 454 | 472 | NA |  |  |  | GPON | Tejas | API to configure Rythuvedika, MRO, School Services, CCTV |  |  | Colosed | [15 empty] | GPON | Closed | [8 empty] | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API | Completed & Approved | Closed before june-2025 | Closed before june-2025
454 | 455 | 472 | NA |  |  |  | GPON | Tejas | API to verify and enable the PM |  |  | Colosed | [15 empty] | GPON | Closed | [8 empty] | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API | Completed & Approved | Closed before june-2025 | Closed before june-2025
455 | 456 | 472 | NA |  |  |  | GPON | Tejas | API to configure Vlan and Profiles in OLT |  |  | Colosed | [15 empty] | GPON | Closed | [8 empty] | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API | Completed & Approved | Closed before june-2025 | Closed before june-2025
456 | 457 | 472 | NA |  |  |  | GPON | Tejas | Verification of the services configured by NSO through Playbook(Cisco Tool) |  |  | Colosed | [15 empty] | GPON | Closed | [8 empty] | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API to validate the configured Services | Completed & Approved | Closed before june-2025 | Closed before june-2025
457 | 458 | 472 | NA |  |  |  | GPON | Tejas | API to configure ONT UNI Port as tagged vlan |  |  | Colosed | [15 empty] | GPON | Closed | [8 empty] | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API | Completed & Approved | Closed before june-2025 | Closed before june-2025
458 | 459 | 472 | NA |  |  |  | GPON | Tejas | API to validate the profiles, vlans available in OLT,ONT |  |  | Colosed | [15 empty] | GPON | Closed | [8 empty] | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API to validate the configured Services | Completed & Approved | Closed before june-2025 | Closed before june-2025
459 | 460 | 472 | NA |  |  |  | GPON | Tejas | API to change the ONT ETH Port to Bridge to Route and Vice versa |  |  | Colosed | [15 empty] | GPON | Closed | [8 empty] | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API | Completed & Approved | Closed before june-2025 | Closed before june-2025
460 | 461 | 472 | NA |  |  |  | GPON | Tejas | API to suspend/delete the service from a ONT UNI Port |  |  | Colosed | [15 empty] | GPON | Closed | [8 empty] | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API | Completed & Approved | Closed before june-2025 | Closed before june-2025
461 | 462 | 472 | NA |  |  |  | GPON | Tejas | API to suspend/delete the complete service |  |  | Colosed | [15 empty] | GPON | Closed | [8 empty] | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API | Completed & Approved | Closed before june-2025 | Closed before june-2025
462 | 463 | 472 | NA |  |  |  | GPON | Tejas | API to modify the service- ONT, UNI Port, bandwidth, vlan, description, unatgged to tag or vice versa., |  |  | Open | Tejas OEM | EMS/OLT | 15-Nov-25: Having dependency on NSO and BSS | [12 empty] | GPON | OPEN | [10 empty] | Open | Open | Open
463 | 464 | 472 | NA |  |  |  | GPON | Tejas | API to configure and delete the WAN profiles in WiFi ONT |  |  | Colosed | [15 empty] | GPON | Closed | [8 empty] | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API | Completed & Approved | Closed before june-2025 | Closed before june-2025
464 | 465 | 472 | NA |  |  |  | GPON | Tejas | API to make PON Port admin up / down |  |  | Colosed | [15 empty] | GPON | Closed | [8 empty] | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API | Completed & Approved | Closed before june-2025 | Closed before june-2025
465 | 466 | 472 | NA |  |  |  | GPON | Tejas | API to create/delete service Profile |  |  | Colosed | [15 empty] | GPON | Closed | [8 empty] | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API | Completed & Approved | Closed before june-2025 | Closed before june-2025
466 | 467 | 472 | NA |  |  |  | GPON | Tejas | Required complete API and Template developer document |  |  | Colosed | [15 empty] | GPON | Closed | [8 empty] | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API Document | Completed & Approved | Closed before june-2025 | Closed before june-2025
467 | 468 | 472 | NA |  |  |  | GPON | Nokia | ONT Ethernet Port PM Report |  |  | Colosed | [15 empty] | GPON | Closed | [8 empty] | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\ONT ETH PM Report | Completed & Approved | Closed before june-2025 | Closed before june-2025
468 | 469 | 472 | NA |  |  |  | GPON | Nokia | ONT Wifi/Route Mode PM Report |  |  | Colosed | [15 empty] | GPON | Closed | [8 empty] | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\ONT WiFi PM Report | Completed & Approved | Closed before june-2025 | Closed before june-2025
469 | 470 | 472 | NA |  |  |  | GPON | Nokia | PM Report for 24hrs of OLT,ONT,ONT Eth Port(Bridge/Route), Wifi |  |  | Open | [15 empty] | GPON | Closed | [8 empty] | 2025-07-31 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\470 | Completed & Approved | Closed before june-2025 | Closed after June
470 | 471 | 472 | NA |  |  |  | GPON | Nokia | ONT ETH Port status monitoring from OSS |  |  | Colosed | [15 empty] | GPON | Closed | [8 empty] | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\Tejas LAN LOS | Completed & Approved | Closed before june-2025 | Closed before june-2025
471 | 472 | 472 | NA |  |  |  | GPON | Nokia | Unable to browse Internet when IPV6 configured in wifi ONT |  |  | Open | [15 empty] | GPON | Closed | [8 empty] | 2025-07-31 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\472 | Completed & Approved | Closed before june-2025 | Closed after June
472 | M1 | MOM | 2023-02-06 |  |  |  | NOC Operationalization | Dashboards | Submit a fortnightly report (Kanban chart) for monitoring all activities in TNOC, including OSS, BSS, NSO, etc. |  | Critical | Open | OSS Dashboards |  | 23-Sep-25: Approved shall be closed | [12 empty] | Network | Closed | CLOSED | 23-Sep-25: Approved shall be closed | FALSE | [5 empty] | 2025-09-23 | Artefacts not Required | Completed & Approved | Closed before june-2025 | Closed after June
473 | M10 | MOM | 2023-04-03 |  |  |  | GIS | Resource Related | Evaluation of License Sufficiency and Ramp-Up Plan |  | Critical | Open | OSS Dashboards |  | 15-Nov-25: TFIBER is a critical dependency for closing the GIS licenses | [12 empty] | Applications/Tools | OPEN | [9 empty] | #N/A | Closed | Closed | Open
474 | M100 | MOM | 2023-08-01 |  |  |  | Helpdesk | Handbook & SOPs | Call Escalation Recording Process |  | Critical | open |  |  | 25-Sep-25: Artefacts to be uploaded | [12 empty] | Helpdesk (Contact Center) | Closed | [8 empty] | 2025-09-24 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\M100 | Completed & Approved | Closed before june-2025 | Closed after June
475 | M1000 | MOM | 2024-01-25 |  |  |  | WFM |  | Adopt WFM by packages B & C and procure licenses |  | Critical | Open |  |  | 15-Npv-25: TFIBER is a critical dependency for closing the WFM license | [12 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
476 | M1001 | MOM | 2024-01-25 |  |  |  | Field Related |  | Complete implementation of Mandal rings for NoFN PH-1 to declare District Go-Live |  | Critical | Open |  |  | MR-06 & MR-25 Open due to ROW issue Rest all closed. | [12 empty] | Field Related issues | OPEN |  |  |  | Project Team | [6 empty] | Open | Open | Open
477 | M1002 | MOM | 2024-01-25 |  |  |  | Field Related |  | Restore all social welfare and tribal welfare schools to serviceable condition |  | Critical | Open |  |  | Ongoing process as per priority from clients | [12 empty] | Field Related issues | OPEN |  |  |  | Ongoing operations, O&M Team | [6 empty] | Open | Open | Open
478 | M1003 | MOM | 2024-01-25 |  |  |  | Field Related |  | Complete all GI connectivity by March '24 and secure GI payments |  | Critical | Open |  |  | Completed for | [12 empty] | Field Related issues | OPEN |  |  |  | Project Team | [6 empty] | Open | Open | Open
479 | M1004 | MOM | 2024-01-25 |  |  |  | Field Related |  | Focus on top 4 priorities for network readiness |  | Critical | Open | [15 empty] | Field Related issues | OPEN |  |  |  | Project Team | [6 empty] | Open | Open | Open
480 | M1005 | MOM | 2024-01-25 |  |  |  | Field Related |  | Make the network ready for service review by State IT&EC Minister |  | Critical | Open | [15 empty] | Field Related issues | OPEN |  |  |  | Project Team | [6 empty] | Open | Open | Open
481 | M1006 | MOM | 2024-02-13 |  |  |  | Field Related |  | Issue with status of Sangareddy district E2E completion |  | Critical | Open |  |  | 9 Mandal E2E completed , 2 WIP , balance 12 Mandal target by Dec'25 2 mandals BER/ ROW permission issue/not feasable | [12 empty] | Field Related issues | OPEN |  |  |  | Project Team | [6 empty] | Open | Open | Open
482 | M1007 | MOM | 2024-02-13 |  |  |  | Field Related |  | Status of GP migrations and POP completion |  | Critical | Open |  |  | 3520 GPs Completed as work front released till date. | [12 empty] | Field Related issues | OPEN |  |  |  | Project Team | [6 empty] | Open | Open | Open
483 | M1008 | MOM | 2024-02-13 |  |  |  | Field Related |  | Pending mandals for End-End AT |  | Critical | Open |  |  | 42 mandals WIP as per work front availability | [12 empty] | Field Related issues | OPEN |  |  |  | Project Team | [6 empty] | Open | Open | Open
484 | M1009 | MOM | 2024-02-13 |  |  |  | Security & Regulatory Compliance | Regulatory Compliance | Non-compliance with IP-MAC binding |  | Critical | Open |  |  | Port winding is possible , however it will cause difficulty with field units. need brainstormig before deployment of Mac binding | [12 empty] | Security | Closed | [8 empty] | 2025-11-01 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\NW-Security\M1009_31-Oct-25.pdf | Closed | Closed After 14-Oct | Open
485 | M101 | MOM | 2023-08-01 |  |  |  | Helpdesk | User Experience | Missed Call Feature on WhatsApp |  | Critical | open |  |  | 01-Dec-25: Not feasible 11-Sep-25: Existing product will not Support | [12 empty] | Helpdesk (Contact Center) | OPEN | [10 empty] | Open | Open | Open
486 | M1010 | MOM | 2024-02-13 |  |  |  | OEM Related |  | Issues with application integration |  | Critical | Open |  |  | 16-Oct-25: Integration of apps are tracking in individual app implementation tracker | [12 empty] | OEM Related Issues | OPEN | CLOSED | 16-Oct-25: Integration of apps are tracking in individual app implementation tracker | FALSE | [7 empty] | Open | Open | Open
487 | M1011 | MOM | 2024-02-13 |  |  |  | Security & Regulatory Compliance | Regulatory Compliance | Review of submitted policy documents |  | Critical | Open |  |  | 28-Nov-25: Document preparation in progress once done points will be closed. 02 Policy has been cleared by TPA . Work on balance policy is in process | [12 empty] | Security | OPEN | [10 empty] | Open | Open | Open
488 | M1012 | MOM | 2024-02-13 |  |  |  | NOC Operationalization |  | Status of asset management automation |  | Critical | Open |  |  | 16-Oct-25: Offline inventory will be loaded manually in Asset Manager , Online inventory will be discovered in OSS and updated in Asset manager. Compliance Asset Report will be generated from Asset Manager | [12 empty] | Network | OPEN | OPEN | 16-Oct-25: Offline inventory will be loaded manually in Asset Manager , Online inventory will be discovered in OSS and updated in Asset manager. Compliance Asset Report will be generated from Asset Manager | TRUE | [7 empty] | Open | Open | Open
489 | M1013 | MOM | 2024-02-13 |  |  |  | Security & Regulatory Compliance | Compliance | Matter of security for personnel access |  | Critical | Open |  |  | Request elaborate the point for discussion. Existing mechanism is regulating personnel access at NOC and sensitive places | [12 empty] | Security | Closed | [8 empty] | 2025-10-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\NW-Security\T36_28-Oct-25.pdf | Closed | Closed After 14-Oct | Open
490 | M1014 | MOM | 2024-02-13 |  |  |  | Security & Regulatory Compliance | Compliance | Incomplete detailing in security report |  | Critical | Open |  |  | 28-Nov-25: VAPT is going on, once VAPT is done points will be closed. Request elaborate the point for discussion. or any specific criteria need to added or removed | [12 empty] | Security | OPEN | [10 empty] | Open | Open | Open
491 | M1015 | MOM | 2024-02-13 |  |  |  | Security & Regulatory Compliance | Regulatory Compliance | Review of SSL for applications |  | Critical | Open |  |  | 28-Nov-25: Gathering artifacts from other teams. All applications owner has been insisted to use SSL for application as per security measures. And it is being ensured that application moving to Producatio | n e | nviro | nmen | t are SSL | mplied | [7 empty] | Security | OPEN |  |  |  |  | co | [5 empty] | Open | Open | Open
492 | M1016 | MOM | 2024-02-13 |  |  |  | Security & Regulatory Compliance | Regulatory Compliance | Access control policy |  | Critical | Open |  |  | ACL policy is defined as per the requested user provided imformation. | [12 empty] | Security | Closed | [8 empty] | 2025-10-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\NW-Security\M873_29-Oct-25.pdf | Closed | Closed After 14-Oct | Open
493 | M1017 | MOM | 2024-02-13 |  |  |  | Security & Regulatory Compliance | Regulatory Compliance | Concern about remote access management |  | Critical | Open |  |  | All remote management access is through VPN only . | [12 empty] | Security | Closed | [8 empty] | 2025-10-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\NW-Security\T37_28-Oct-25.pdf | Closed | Closed After 14-Oct | Open
494 | M1018 | MOM | 2024-02-13 |  |  |  | Security & Regulatory Compliance | Compliance | Inquiry on DMZ details |  | Critical | Open |  |  | DMZ policy has been shared with team inluitive for verification | [12 empty] | Security | Closed | [8 empty] | 2025-10-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\NW-Security\M873_29-Oct-25.pdf | Closed | Closed After 14-Oct | Open
495 | M1019 | MOM | 2024-02-13 |  |  |  | Security & Regulatory Compliance | Compliance | Status of leave and potential impacts |  | Critical | Open |  |  | 28-Nov-25: Gathering artifacts from other teams. Point not clear | [12 empty] | Security | OPEN | [10 empty] | Open | Open | Open
496 | M102 | MOM | 2023-08-01 |  |  |  | Helpdesk | User Experience | Automated Response for Email Complaints |  | Critical | Open |  |  | 01-Dec-25: Complaint Response is part of Ticketing Module inetgration activity | [12 empty] | Helpdesk (Contact Center) | OPEN | [10 empty] | Open | Open | Open
497 | M1020 | MOM | 2024-02-13 |  |  |  | Security & Regulatory Compliance | Compliance | Directive for approval and proper usage of tool services and resources |  | Critical | Open |  |  | All people has been extended access through RBAC form approved by AD-NoC | [12 empty] | Security | Closed | [8 empty] | 2025-11-01 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\NW-Security\M1020_31-Oct-25.pdf | Completed & Approved | Closed After 14-Oct | Open
498 | M1021 | MOM | 2024-02-13 |  |  |  | Security & Regulatory Compliance | Regulatory Compliance | Requirements for RMC's reporting |  | Critical | Open |  |  | 28-Nov-25: Gathering artifacts from other teams | [12 empty] | Security | OPEN | [10 empty] | Open | Open | Open
499 | M1022 | MOM | 2024-02-13 |  |  |  | Security & Regulatory Compliance | Regulatory Compliance | Proposal for security updates bulletin |  | Critical | Open |  |  | 28-Nov-25: To discuss with mr Sanjay to get clarifications on the points | [12 empty] | Security | OPEN | [10 empty] | Open | Open | Open
500 | M1023 | MOM | 2024-02-13 |  |  |  | Security & Regulatory Compliance | Regulatory Compliance | Implementation of SOC's best practices |  | Critical | Open |  |  | 28-Nov-25: Document preparation in progress once done points will be closed. SOC's best practices are for SOC includes SIEM,XDR and SOAR integrated Mitre ATT&CKS database. | [12 empty] | Security | OPEN | [10 empty] | Open | Open | Open
501 | M1024 | MOM | 2024-02-16 |  |  |  | BSS |  | Ticketing process and tracking |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
502 | M1025 | MOM | 2024-02-16 |  |  |  | BSS |  | Task creation in billing module |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
503 | M1026 | MOM | 2024-02-16 |  |  |  | Helpdesk | Training Module | Recruitment and training of billing officers |  | Critical | open |  |  | 12-Sep-25: its part of Business Helpdesk(T FIber) | [12 empty] | Helpdesk (Contact Center) | Closed | [8 empty] | 2025-09-24 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\M116,723,1026 | Completed & Approved | Closed before june-2025 | Closed after June
504 | M1027 | MOM | 2024-02-16 |  |  |  | BSS |  | Contact synchronization in Lead creation and conversion |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
505 | M1028 | MOM | 2024-02-16 |  |  |  | Security & Regulatory Compliance | Regulatory Compliance | Review of submitted security policy documents |  | Critical | Open |  |  | 28-Nov-25: Document preparation in progress once done points will be closed. Point Duplicated | [12 empty] | Security | OPEN | [10 empty] | Open | Open | Open
506 | M1029 | MOM | 2024-02-16 |  |  |  | Security & Regulatory Compliance | Compliance | Asset management and data classification |  | Critical | Open |  |  | 28-Nov-25: Document preparation in progress once done points will be closed. It need DLP solution to tag data as per classification | [12 empty] | Security | OPEN | [10 empty] | Open | Open | Open
507 | M103 | MOM | 2023-08-01 |  |  |  | Helpdesk | Resource Related | Helpdesk Manager Availability for 24 Hrs |  | Critical | open |  |  | 24-Sep-25: Existing Lead available during Business Hours, Remaining duration Shift Lead will Manage | [12 empty] | Helpdesk (Contact Center) | Closed | [8 empty] | 2025-09-24 | Artefacts not Required | Completed & Approved | Closed before june-2025 | Closed after June
508 | M1030 | MOM | 2024-02-16 |  |  |  | Security & Regulatory Compliance | Regulatory Compliance | Control of user and visitor access |  | Critical | Open |  |  | Already physical record is being maintained | [12 empty] | Security | Closed | [8 empty] | 2025-10-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\NW-Security\T36_28-Oct-25.pdf | Closed | Closed After 14-Oct | Open
509 | M1031 | MOM | 2024-02-16 |  |  |  | Security & Regulatory Compliance | Regulatory Compliance | Concerns about security reporting and compliance |  | Critical | Open |  |  | 28-Nov-25: To discuss with mr Sanjay to get clarifications on the points | [12 empty] | Security | OPEN | [10 empty] | Open | Open | Open
510 | M1032 | MOM | 2024-02-16 |  |  |  | Security & Regulatory Compliance | Regulatory Compliance | VPAT implementation and firmware patching |  | Critical | Open |  |  | 28-Nov-25: VAPT is going on, once VAPT is done points will be closed. VAPT will be conducted by Tfiber . Remediation for sam will be intiated thereafter | [12 empty] | Security | OPEN | [10 empty] | Open | Open | Open
511 | M1033 | MOM | 2024-02-16 |  |  |  | Security & Regulatory Compliance | Regulatory Compliance | Compliance to access management policy |  | Critical | Open |  |  | Access Management policy is as per RBAC approval. | [12 empty] | Security | Closed | [8 empty] | 2025-11-01 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\NW-Security\M1020_31-Oct-25.pdf | Closed | Closed After 14-Oct | Open
512 | M1034 | MOM | 2024-03-14 |  |  |  | NOC Operationalization | Launch Readiness | Assessing the progress achieved after the Governance meeting held on March 5, 2024. |  | Critical | Open |  |  | 23-Sep-25: Approved shall be closed | [12 empty] | Network | Closed | CLOSED | 23-Sep-25: Approved shall be closed | FALSE | [5 empty] | 2025-09-23 | Artefacts not Required | Completed & Approved | Closed before june-2025 | Closed after June
513 | M1035 | MOM | 2024-03-14 |  |  |  | BSS |  | Addressing the delays in the End-to-End demonstration of products due to billing/invoice module issues. |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
514 | M1036 | MOM | 2024-03-14 |  |  |  | NOC Operationalization | Launch Readiness | Achieving operationalization and readiness of T-NOC. |  | Critical | Open |  |  | 16-Oct-25: Covered in the existing NOC go-live plan | [12 empty] | Network | OPEN | Duplicate | 16-Oct-25: Covered in the existing NOC go-live plan | FALSE | [7 empty] | Open | Open | Open
515 | M1037 | MOM | 2024-03-14 |  |  |  | NOC Operationalization | Launch Readiness | Addressing product gaps and OEM execution delays for the readiness of 5 products. |  | Critical | Open |  |  | 16-Oct-25 : Covered in BSS implementation plan | [12 empty] | Network | OPEN | Duplicate | 16-Oct-25 : Covered in BSS implementation plan | FALSE | [7 empty] | Open | Open | Open
516 | M1038 | MOM | 2024-03-14 |  |  |  | WFM |  | Ensuring readiness of WFM integration, order fulfillment, service provisioning, and NOC critical points closure. |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
517 | M1039 | MOM | 2024-03-14 |  |  |  | NSO | Service Delivery | Ensuring the service delivery organization is structured for an interim period. |  | Critical | Open |  |  | oct-2025: Team Identified. |  |  | Rajeev/Senthil |  |  |  |  | Not Started |  |  |  |  | Applications/Tools | OPEN |  |  |  |  | Need clarity on whether the organization structure is only for NSO or for the entire service delivery team. | [5 empty] | Open | Open | Open
518 | M104 | MOM | 2023-08-01 |  |  |  | Helpdesk | Handbook & SOPs | Incident categorization to be exhaustive, response timelines to be defined and attached based on incident categorization. |  | Critical | open |  |  | 24-Sep-25: Updated Document Shared 23-Aug-23 | [12 empty] | Helpdesk (Contact Center) | Closed | [8 empty] | 2025-09-24 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\M104,105,109,111,113,115,122,123,127,128,130,132,162 | Completed & Approved | Closed before june-2025 | Closed after June
519 | M1040 | MOM | 2024-03-14 |  |  |  | Field Related | Network Availibilty | Achieving network availability reports compliance and readiness. |  | Critical | Open |  |  | closed under O&M scope | [12 empty] | Field Related issues | OPEN |  |  |  | O&M Team | [6 empty] | Open | Open | Open
520 | M1041 | MOM | 2024-03-14 |  |  |  | OEM Related | Network Availibilty | Resolving OEM-related gaps and achieving automation roadmap targets. |  | Critical | Open |  |  | 16-Oct-25: Covered in individual app tracker | [12 empty] | OEM Related Issues | OPEN | Duplicate | 16-Oct-25: Covered in individual app tracker | FALSE | [7 empty] | Open | Open | Open
521 | M1042 | MOM | 2024-03-14 |  |  |  | T&D Environment | Network Availibilty | Establishing a pre-production environment for testing applications before moving to production. |  | NON-Critical | Open |  |  | [15/09/25] Test Environment is actively used for T&D by Delivery and OEM teams. | [12 empty] | Applications | OPEN | [10 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
522 | M1043 | MOM | 2024-03-14 |  |  |  | NOC Operationalization | Launch Readiness | L&T to address the delays in demonstrating the End-to-End of the Dark Fiber product. |  | Critical | Open |  |  | 16-Oct-25 : Covered in BSS implementation plan | [12 empty] | Network | OPEN | Duplicate | 16-Oct-25 : Covered in BSS implementation plan | FALSE | [7 empty] | Open | Open | Open
523 | M1044 | MOM | 2024-03-14 |  |  |  | NOC Operationalization | NOC Readiness | L&T to complete 423 critical points and provide a summary of the status along with action required for balance points. |  | Critical | Open | [15 empty] | Network | Closed | CLOSED |  | FALSE | [5 empty] | 2025-09-23 | Artefacts not Required | Completed & Approved | Closed before june-2025 | Closed after June
524 | M1045 | MOM | 2024-03-14 |  |  |  | NOC Operationalization | NOC Readiness | L&T to ensure understanding of the interim T-NOC operationalization plan and work towards readiness. |  | Critical | Open |  |  | 16-Oct-25: Covered in the existing NOC go-live plan | [12 empty] | Network | OPEN | Duplicate | 16-Oct-25: Covered in the existing NOC go-live plan | FALSE | [7 empty] | Open | Open | Open
525 | M1046 | MOM | 2024-03-14 |  |  |  | BSS |  | L&T to be prepared for the next dry run demo and update the order management and quote management statuses. |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
526 | M1047 | MOM | 2024-03-14 |  |  |  | NOC Operationalization | NOC Readiness | L&T to provide updates and clarifications on the payment gateway, ticket functionalities, and NSO readiness. |  | Critical | Open |  |  | 16-Oct-25: Covered in BSS implementation plan | [12 empty] | Network | OPEN | Duplicate | 16-Oct-25: Covered in BSS implementation plan | FALSE | [7 empty] | Open | Open | Open
527 | M1048 | MOM | 2024-03-14 |  |  |  | WFM |  | L&T to be prepared for the demonstration of WFM for order fulfillment/service provisioning. |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
528 | M1049 | MOM | 2024-03-14 |  |  |  | T&D Environment |  | L&T to provide details on modules working in pre-production and production environments and seek approvals for transitions. |  | NON-Critical | Open |  |  | [15/09/25] Test Environment is actively used for T&D by Delivery and OEM teams. | [12 empty] | Applications | OPEN | [10 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
529 | M105 | MOM | 2023-08-01 |  |  |  | Helpdesk | Handbook & SOPs | Clarity required in the definition of roles and responsibilities of L1 and L2 agents, incident categorization to be handled at L1 level, type of queries, resolution time, escalation matrix to be better defined. |  | Critical | open |  |  | 24-Sep-25: Updated Document Shared 23-Aug-23 | [12 empty] | Helpdesk (Contact Center) | Closed | [8 empty] | 2025-09-24 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\M104,105,109,111,113,115,122,123,127,128,130,132,162 | Completed & Approved | Closed before june-2025 | Closed after June
530 | M1050 | MOM | 2024-03-14 |  |  |  | NOC Operationalization | Launch Readiness | The demonstration of the End-to-End of one product by 18th March 2024. |  | Critical | Open |  |  | 16-Oct-25: Covered in BSS implementation plan | [12 empty] | Network | OPEN | Duplicate | 16-Oct-25: Covered in BSS implementation plan | FALSE | [7 empty] | Open | Open | Open
531 | M1051 | MOM | 2024-03-14 |  |  |  | NOC Operationalization | Launch Readiness | T0 phase points to be completed by March 2024. |  | Critical | Open |  |  | 23-Sep-25: Approved shall be closed | [12 empty] | Network | Closed | CLOSED | 23-Sep-25: Approved shall be closed | FALSE | [5 empty] | 2025-09-23 | Artefacts not Required | Completed & Approved | Closed before june-2025 | Closed after June
532 | M1052 | MOM | 2024-03-14 |  |  |  | Field Related | District Completion Target | Complete E2E AT Certificate of Rangareddy, Mahbubnagar, Vikarabad & Narayanpet districts by 7th April 2024. |  | NON-Critical | Open | [15 empty] | Field Related issues | OPEN |  |  |  | Project Team | [6 empty] | Open | Open | Open
533 | M1053 | MOM | 2024-03-14 |  |  |  | T&D Environment |  | Provide a summary of applications in pre-production & production environments by 16th March 2024. |  | NON-Critical | Open |  |  | [15/09/25] Test Environment is actively used for T&D by Delivery and OEM teams. NOC submission provided in Tfiber has the T&D application from Oct-Mar2025 | [12 empty] | Applications | OPEN | [10 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
534 | M1054 | MOM | 2024-03-14 |  |  |  | OEM Related |  | Provide updates on the pre-production environment, OEM gaps, and integration of systems and applications by 16th March 2024. |  | Critical | Open |  |  | 23-Sep-25: Approved shall be closed | [12 empty] | OEM Related Issues | Closed | CLOSED | 23-Sep-25: Approved shall be closed | FALSE | [5 empty] | 2025-09-23 | Artefacts not Required | Completed & Approved | Closed before june-2025 | Closed after June
535 | M1055 | MOM | 2024-03-14 |  |  |  | NOC Operationalization | Launch Readiness | Ensure all 5 products are ready by April 2024. |  | Critical | Open |  |  | 16-Oct-25: Covered in BSS implementation plan | [12 empty] | Network | OPEN | Duplicate | 16-Oct-25: Covered in BSS implementation plan | FALSE | [7 empty] | Open | Open | Open
536 | M1056 | MOM | 2024-03-14 |  |  |  | Field Related | Network Availibilty | Achieve 97% Network availability in Gadwal & Wanaparthy from 1st April 2024. |  | NON-Critical | Open |  |  | closed under O&M scope | [12 empty] | Field Related issues | OPEN |  |  |  | O&M Team | [5 empty] | Artefacts to be uploaded | Open | Open | Open
537 | M1057 | MOM | 2024-03-14 |  |  |  | Field Related | Network Availibilty | Achieve 90% Network availability in Mahbubnagar and Rangareddy for April 2024. |  | NON-Critical | Open |  |  | closed under O&M scope | [12 empty] | Field Related issues | OPEN |  |  |  | O&M Team | [5 empty] | Artefacts to be uploaded | Open | Open | Open
538 | M1058 | MOM | 2024-03-14 |  |  |  | NOC Operationalization | Network Availibilty | All critical points for T-NOC operationalization to be completed by 30th March 2024. |  | Critical | Open |  |  | 16-Oct-25: Covered in the existing NOC go-live plan | [12 empty] | Network | OPEN | Duplicate | 16-Oct-25: Covered in the existing NOC go-live plan | FALSE | [7 empty] | Open | Open | Open
539 | M1059 | MOM | 2024-06-11 |  |  |  | NOC Operationalization |  | Interim NOC O&M: L&T to complete pending tasks and seek T-Fiber approval for the start of Interim NOC O&M. |  | Critical | Open |  |  | 16-Oct-25: Interim NOC started from 15th Oc'24 22-Sep-25: SOPs, Handbook, T0-T6 and interim NOC Plan submitted to the T fiber on XX-XX-XXXX. T Fiber team has shared 65 queries on SOP and Hanbooks. And thes | e 6 | 5 poi | nts | have bee | ncorporated |  | as | a |  |  | diff | erent points in this master tracker.(Sub domain as Handbook and SOP). Pending tasks(44 SOP, Opertaions Handbook, Full NOC Readiness plan, NOC all KPI) completed and Interim NOC plan has been Submitted. Artefacts to be uploaded in NAS Interim NOC had started in OCt24 | Network | OPEN | CLOSED | 16-Oct-25: Interim NOC started from 15th Oc'24 | FALSE |  | n i | [5 empty] | Open | Open | Open
540 | M106 | MOM | 2023-08-01 |  |  |  | Helpdesk | Mini Helpdesk | Mechanism needed between T-NOC Helpdesk and District Collector offices for complaints that may be made directly to the District Collector office. Provision for a mini-Helpdesk node at each district, with a facility/hotline for an authorized person to log a call/complaint on behalf of the District Collector Office, similar to the direct walk-in channel for customer complaints at T-NOC. |  | NON-Critical | open |  |  | 24-Sep-25: Artefacts to be uploaded | [12 empty] | Helpdesk (Contact Center) | Closed | [8 empty] | 2025-09-24 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\M106 | Completed & Approved | Closed before june-2025 | Closed after June
541 | M1060 | MOM | 2024-06-11 |  |  |  | NOC Operationalization |  | NOC Go-Live: L&T requested recognition of NOC Go-Live status despite manual provisioning; T-Fiber requires full automation for transition from interim to Full NOC. |  | Critical | Open |  |  | 16-Oct-25: Covered in NSO implementation plan | [12 empty] | Network | OPEN | Duplicate | 16-Oct-25: Covered in NSO implementation plan | FALSE | [7 empty] | Open | Open | Open
542 | M1061 | MOM | 2024-06-11 |  |  |  | NOC Operationalization |  | Functional Gaps in NOC Elements: L&T to meet with OEMs to identify scope gaps and evaluate alternate BSS solutions, presenting recommendations within a week. |  | Critical | Open |  |  | 23-Sep-25: Approved Artefacts to be Submitted | [12 empty] | Network | Closed | CLOSED | 23-Sep-25: Approved Artefacts to be Submitted | FALSE | [6 empty] | Artefacts Need to upload | Completed & Approved | Closed before june-2025 | Closed after June
543 | M1062 | MOM | 2024-06-11 |  |  |  | NOC Operationalization |  | Time Delays: L&T to comply with RFP and submit timelines for Full NOC readiness. |  | Critical | Open |  |  | 16-Oct-25: Covered in the existing NOC go-live plan | [12 empty] | Network | OPEN | Duplicate | 16-Oct-25: Covered in the existing NOC go-live plan | FALSE | [7 empty] | Open | Open | Open
544 | M1063 | MOM | 2024-06-11 |  |  |  | NOC Operationalization |  | WFM Tool Implementation: L&T to operationalize the WFM tool for Package A within one week. |  | Critical | Open |  |  | 16-Oct-25: Covered in WFM operationalization | [12 empty] | Network | OPEN | Duplicate | 16-Oct-25: Covered in WFM operationalization | FALSE | [7 empty] | Open | Open | Open
545 | M1064 | MOM | 2024-06-11 |  |  |  | NOC Operationalization |  | MB and LOA Amendment: L&T to complete MB duct reconciliation; T-Fiber to review data submitted by L&T. |  | Critical | Open |  |  | 16-Oct-25: Field item | [12 empty] | Network | OPEN | OPEN | 16-Oct-25: Field item | TRUE | [7 empty] | Open | Open | Open
546 | M1065 | MOM | 2024-06-11 |  |  |  | NOC Operationalization |  | Chemical Storage in GP PoPs: L&T to create guidelines for panchayat chemical storage handling. |  | Critical | Open |  |  | 16-Oct-25: Field item | [12 empty] | Network | OPEN | OPEN | 16-Oct-25: Field item | TRUE | [7 empty] | Open | Open | Open
547 | M1066 | MOM | 2024-06-11 |  |  |  | NOC Operationalization |  | PoP Relocation: L&T to re-offer rates for PoP relocation. |  | Critical | Open |  |  | 16-Oct-25: Field item | [12 empty] | Network | OPEN | OPEN | 16-Oct-25: Field item | TRUE | [7 empty] | Open | Open | Open
548 | M1067 | MOM | 2024-06-11 |  |  |  | NOC Operationalization |  | Centralized Billing for EB: L&T to submit a proposal for centralized billing. |  | Critical | Open |  |  | 16-Oct-25: Non critical will be taken up later | [12 empty] | Network | OPEN | OPEN | 16-Oct-25: Non critical will be taken up later | TRUE | [7 empty] | Open | Open | Open
549 | M1068 | MOM | 2024-06-11 |  |  |  | NOC Operationalization |  | L&T Cash Flow Pressures: L&T to submit invoices as per RFP compliance for payment release. |  | Critical | Open |  |  | 16-Oct-25: Non critical will be taken up later | [12 empty] | Network | OPEN | OPEN | 16-Oct-25: Non critical will be taken up later | TRUE | [7 empty] | Open | Open | Open
550 | M1069 | MOM | 2024-06-11 |  |  |  | NOC Operationalization |  | GST Payments: T-Fiber to explore options within regulatory norms to resolve GST payment issues. |  | Critical | Open |  |  | 16-Oct-25: Action on T-Fiber | [12 empty] | Network | OPEN | OPEN | 16-Oct-25: Action on T-Fiber | TRUE | [7 empty] | Open | Open | Open
551 | M107 | MOM | 2023-08-01 |  |  |  | Helpdesk | Handbook & SOPs | Clarification needed on whether general enquiries are treated as incidents. |  | NON-Critical | open |  |  | 25-Sep-25 Ans: All business queries will created as lead in BSS | [12 empty] | Helpdesk (Contact Center) | Closed | [8 empty] | 2025-09-24 | Artefacts not Required | Completed & Approved | Closed before june-2025 | Closed after June
552 | M1070 | MOM | 2024-06-11 |  |  |  | NOC Operationalization |  | Interim O&M Payment: L&T to submit supporting documents for payment against Interim O&M. |  | Critical | Open |  |  | 23-Sep-25: Approved shall be closed | [12 empty] | Network | Closed | CLOSED | 23-Sep-25: Approved shall be closed | FALSE | [5 empty] | 2025-09-23 | Artefacts not Required | Completed & Approved | Closed before june-2025 | Closed after June
553 | M1071 | MOM | 2024-06-11 |  |  |  | NOC Operationalization |  | Full NOC Readiness Plan: L&T to submit a comprehensive plan for Full NOC readiness. |  | Critical | Open |  |  | 23-Sep-25: Approved shall be closed | [12 empty] | Network | Closed | CLOSED | 23-Sep-25: Approved shall be closed | FALSE | [5 empty] | 2025-09-23 | Artefacts not Required | Completed & Approved | Closed before june-2025 | Closed after June
554 | M1072 | MOM | 2024-06-11 |  |  |  | NOC Operationalization |  | GI Connectivity: L&T to address slow progress and start NoFN connectivity. |  | Critical | Open |  |  | 23-Sep-25: NON Critical to be reviewed later | [12 empty] | Network | OPEN | OPEN | 23-Sep-25: NON Critical to be reviewed later | TRUE | [7 empty] | Open | Open | Open
555 | M1073 | MOM | 2024-06-11 |  |  |  | Field Related |  | AT Completion: L&T to complete AT of 10 districts by July 2024, accounting for monsoon season. |  | Critical | Open | [15 empty] | Field Related issues | OPEN |  |  |  | Project Team | [6 empty] | Open | Open | Open
556 | M1074 | MOM | 2024-06-11 |  |  |  | Field Related |  | RV – GIs: L&T to identify new partners to connect Rhythu Vedikas. |  | Critical | Open | [15 empty] | Field Related issues | OPEN |  |  |  | Project Team | [6 empty] | Open | Open | Open
557 | M1075 | MOM | 2024-06-11 |  |  |  | NOC Operationalization |  | SLA Achievement: L&T to improve O&M availability to meet the target of 97%. |  | Critical | Open |  |  | 22-Sep-25: MSIs Field team is working on it. Multiple dependencies like fiber rerouting, equipment faults, AT WIP for balance nodes, etc. NOC to support in terms of TT, escalations, reports. | [12 empty] | Network | Closed | [8 empty] | 2025-09-22 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\TNOC\M1075 | Completed & Approved | Closed before june-2025 | Closed after June
558 | M1076 | MOM | 2024-06-11 |  |  |  | NOC Operationalization |  | The urgency for L&T to demonstrate agreed SOPs are in place for Interim NOC O&M and to submit sample reports. |  | Critical | Open |  |  | 24-Sep-25: 44 agreed SOP doc submitted and signed off. Artefacts will be uploaded today in NAS | [12 empty] | Network | Closed | [8 empty] | 2025-09-24 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\M1076 | Completed & Approved | Closed before june-2025 | Closed after June
559 | M1077 | MOM | 2024-06-11 |  |  |  | NOC Operationalization |  | The need for L&T to address the slow progress in GI connectivity and to start NoFN connectivity. |  | Critical | Open |  |  | 23-Sep-25: NON Critical to be reviewed later | [12 empty] | Network | OPEN | OPEN | 23-Sep-25: NON Critical to be reviewed later | TRUE | [7 empty] | Open | Open | Open
560 | M1078 | MOM | 2024-06-11 |  |  |  | Field Related |  | The expectation for L&T to complete AT for multiple districts by July 2024 and to increase resources to meet targets. |  | Critical | Open | [15 empty] | Field Related issues | OPEN |  |  |  | Project Team | [6 empty] | Open | Open | Open
561 | M1079 | MOM | 2024-06-11 |  |  |  | NOC Operationalization |  | The requirement for L&T to resolve issues with OEMs and to consider ready-made BSS solutions to mitigate risks. |  | Critical | Open |  |  | 23-Sep-25: Approved shall be closed | [12 empty] | Network | Closed | CLOSED | 23-Sep-25: Approved shall be closed | FALSE | [5 empty] | 2025-09-23 | Artefacts not Required | Completed & Approved | Closed before june-2025 | Closed after June
562 | M108 | MOM | 2023-08-01 |  |  |  | Helpdesk | Handbook & SOPs | Clarification needed on whether general enquiries are treated as incidents. |  | NON-Critical | open |  |  | 25-Sep-25 Ans: All business queries will created as lead in BSS | [12 empty] | Helpdesk (Contact Center) | Closed | [8 empty] | 2025-09-24 | Artefacts not Required | Completed & Approved | Closed before june-2025 | Closed after June
563 | M1080 | MOM | 2024-06-11 |  |  |  | NOC Operationalization |  | Asset Management Policy to be drafted and submitted by L&T before 29th June 2024. |  | Critical | Open |  |  | 16-Oct-25:Covered in M1012 | [12 empty] | Network | OPEN | Duplicate | 16-Oct-25:Covered in M1012 | FALSE | [7 empty] | Open | Open | Open
564 | M1081 | MOM | 2024-06-11 |  |  |  | Security & Regulatory Compliance | NOC Operationalization | Security Audit of ILL (10G) commissioning to be completed urgently and communicated to DOT prior to service launch. |  | Critical | Open |  |  | No Provisioning for ILL security. ISP audit will be relevant in this regard. 01-Nov-25: DDOS as a service is provided by Railtel. The Agreement document is with Tfiber | [12 empty] | Security | Closed | [8 empty] | 2025-11-01 | Artefacts not Required | Closed | Closed After 14-Oct | Open
565 | M1082 | MOM | 2024-06-11 |  |  |  | NOC Operationalization |  | L&T to set up a dedicated security team for the project to resolve all pending security actions. |  | Critical | Open |  |  | 16-Oct-25: Consultant are deputed to close open points | [12 empty] | Network | OPEN | CLOSED | 16-Oct-25: Consultant are deputed to close open points | FALSE | [7 empty] | Open | Open | Open
566 | M1083 | MOM | 2024-06-11 |  |  |  | NOC Operationalization |  | L&T to finalize the appointment of a Security SME, with Vikram Khatri being considered for the role. |  | Critical | Open |  |  | 16-Oct-25: Consultant are deputed to close open points | [12 empty] | Network | OPEN | CLOSED | 16-Oct-25: Consultant are deputed to close open points | FALSE | [7 empty] | Open | Open | Open
567 | M1084 | MOM | 2024-06-11 |  |  |  | NOC Operationalization |  | L&T to send pre-read material at least one day before the next meeting. |  | Critical | Open |  |  | 23-Sep-25: Approved shall be closed | [12 empty] | Network | Closed | CLOSED | 23-Sep-25: Approved shall be closed | FALSE | [5 empty] | 2025-09-23 | Artefacts not Required | Completed & Approved | Closed before june-2025 | Closed after June
568 | M1085 | MOM | 2024-06-11 |  |  |  | NOC Operationalization |  | Mr. Rajesh Thangavelu, Security in-charge, was absent from the meeting despite specific requests for his presence. |  | Critical | Open |  |  | 23-Sep-25: Approved shall be closed | [12 empty] | Network | Closed | CLOSED | 23-Sep-25: Approved shall be closed | FALSE | [5 empty] | 2025-09-23 | Artefacts not Required | Completed & Approved | Closed before june-2025 | Closed after June
569 | M1086 | MOM | 2024-06-11 |  |  |  | NOC Operationalization |  | No action items from earlier Minutes of Meetings (MOMs) were presented in the RMC Meeting. |  | Critical | Open |  |  | 23-Sep-25: Approved shall be closed | [12 empty] | Network | Closed | CLOSED | 23-Sep-25: Approved shall be closed | FALSE | [5 empty] | 2025-09-23 | Artefacts not Required | Completed & Approved | Closed before june-2025 | Closed after June
570 | M1087 | MOM | 2024-06-11 |  |  |  | NOC Operationalization |  | No formal intimation regarding the exit of the existing Security SME (Mr. Gandhi) by L&T. |  | Critical | Open |  |  | 16-Oct-25: Discussed and formalized. | [12 empty] | Network | OPEN | CLOSED | 16-Oct-25: Discussed and formalized. | FALSE | [7 empty] | Open | Open | Open
571 | M1088 | MOM | 2024-06-11 |  |  |  | Security & Regulatory Compliance | NOC Operationalization | Cisco firewall and ISE integration is still pending despite being from the same OEM. |  | Critical | Open |  |  | 28-Nov-25: Work in Progress. Firewall is being integrated with ISE. | [12 empty] | Security | OPEN | [10 empty] | Open | Open | Open
572 | M1089 | MOM | 2024-06-11 |  |  |  | NOC Operationalization |  | Address the absence of the central Security resource in future meetings. |  | Critical | Open |  |  | 16-Oct-25: Ensured and will be taken care | [12 empty] | Network | OPEN | CLOSED | 16-Oct-25: Ensured and will be taken care | FALSE | [7 empty] | Open | Open | Open
573 | M109 | MOM | 2023-08-01 |  |  |  | Helpdesk | Handbook & SOPs | Detailed documentation needed on critical, major, minor escalations, and their related thresholds. |  | NON-Critical | open |  |  | 24-Sep-25: Updated Document Shared 23-Aug-23 | [12 empty] | Helpdesk (Contact Center) | Closed | [8 empty] | 2025-09-24 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\M104,105,109,111,113,115,122,123,127,128,130,132,162 | Completed & Approved | Closed before june-2025 | Closed after June
574 | M1090 | MOM | 2024-06-11 |  |  |  | NOC Operationalization |  | Provide closure status of all old action points in a single sheet before the next meeting. |  | Critical | Open |  |  | 23-Sep-25: Approved shall be closed | [12 empty] | Network | Closed | CLOSED | 23-Sep-25: Approved shall be closed | FALSE | [5 empty] | 2025-09-23 | Artefacts not Required | Completed & Approved | Closed before june-2025 | Closed after June
575 | M1091 | MOM | 2024-06-11 |  |  |  | Security & Regulatory Compliance | NOC Operationalization | Complete the scope for Vulnerability Assessment and Penetration Testing as defined and submit the results. |  | Critical | Open |  |  | 28-Nov-25: VAPT is going on, once VAPT is done points will be closed | [12 empty] | Security | OPEN | [10 empty] | Open | Open | Open
576 | M1092 | MOM | 2024-06-11 |  |  |  | Security & Regulatory Compliance | NOC Operationalization | Address the issue of the Cisco firewall and ISE not being integrated. |  | Critical | Open |  |  | 28-Nov-25: There are duplicate points; once the main point is closed, these duplicate points can be closed. | [12 empty] | Security | OPEN | [10 empty] | Open | Open | Open
577 | M1093 | MOM | 2024-06-14 |  |  |  | OEM Related |  | All API Documents by HP to be submitted by L&T as soon as possible. |  | Critical | Open |  |  | 23-Sep-25: Approved Artefacts to be Submitted | [12 empty] | OEM Related Issues | Closed | CLOSED | 23-Sep-25: Approved Artefacts to be Submitted | FALSE | [6 empty] | Artefacts Need to upload | Completed & Approved | Closed before june-2025 | Closed after June
578 | M1094 | MOM | 2024-06-14 |  |  |  | OEM Related |  | BBNL integration solution to be provided by the end of June 2024, with testing beginning from 24th June 2024. |  | Critical | Open |  |  | 23-Sep-25: Approved shall be closed | [12 empty] | OEM Related Issues | Closed | CLOSED | 23-Sep-25: Approved shall be closed | FALSE | [5 empty] | 2025-09-23 | Artefacts not Required | Completed & Approved | Closed before june-2025 | Closed after June
579 | M1095 | MOM | 2024-06-14 |  |  |  | OEM Related |  | Alarm enrichment with custom attributes and other new SOW items are in progress, with some attributes completed and others recently given. |  | Critical | Open |  |  | 23-Sep-25: Approved shall be closed | [12 empty] | OEM Related Issues | Closed | CLOSED | 23-Sep-25: Approved shall be closed | FALSE | [5 empty] | 2025-09-23 | Artefacts not Required | Completed & Approved | Closed before june-2025 | Closed after June
580 | M1096 | MOM | 2024-06-14 |  |  |  | OEM Related |  | L&T to map documents as per RFP requirements and identify gaps for new SOW internally to their OEMs. |  | Critical | Open |  |  | 23-Sep-25: Approved Artefacts to be Submitted | [12 empty] | OEM Related Issues | Closed | CLOSED | 23-Sep-25: Approved Artefacts to be Submitted | FALSE | [6 empty] | Artefacts Need to upload | Completed & Approved | Closed before june-2025 | Closed after June
581 | M1097 | MOM | 2024-06-14 |  |  |  | OEM Related |  | HPE to provide Admin user privilege to L&T for filtering after a professional agreement is signed. |  | Critical | Open |  |  | 23-Sep-25: Approved shall be closed | [12 empty] | OEM Related Issues | Closed | CLOSED | 23-Sep-25: Approved shall be closed | FALSE | [5 empty] | 2025-09-23 | Artefacts not Required | Completed & Approved | Closed before june-2025 | Closed after June
582 | M1098 | MOM | 2024-06-14 |  |  |  | OEM Related |  | OpenText to share all required documents by 24th June 2024. |  | Critical | Open |  |  | 23-Sep-25: Approved Artefacts to be Submitted | [12 empty] | OEM Related Issues | Closed | CLOSED | 23-Sep-25: Approved Artefacts to be Submitted | FALSE | [6 empty] | Artefacts Need to upload | Completed & Approved | Closed before june-2025 | Closed after June
583 | M1099 | MOM | 2024-06-14 |  |  |  | OEM Related |  | L&T to demonstrate the correlation engine and event alarm management for all domains. |  | Critical | Open |  |  | 16-Oct-25: Covered in OSS Operationalization | [12 empty] | OEM Related Issues | OPEN | Duplicate | 16-Oct-25: Covered in OSS Operationalization | FALSE | [7 empty] | Open | Open | Open
1169 | M476 | MOM | 2024-01-05 |  |  |  | NSO | Service provisioning | Revisit current Circuit ID logic in NSO and define new naming convention |  | Critical | Open |  |  | 29-dec-2025: Need discussion/BSS logic | [7 empty] | Completed |  |  |  |  | Applications/Tools | OPEN |  |  |  |  | BSS 13/03/2026 : Attach proof of client mail subject (Location ID and Circuit ID) & BSS and NSO Circuit Id Service Order Screenshot | Pending |  | 16/03/2026 |  |  | Open | Open | Open
585 | M110 | MOM | 2023-08-01 |  |  |  | Helpdesk | Handbook & SOPs | Feedback Collection Review Mechanism |  | NON-Critical | Open |  |  | 01-Dec-25:Not feasible, Request can sent from Neox but reponse capturing in sysytem is not available | [12 empty] | Helpdesk (Contact Center) | OPEN | [10 empty] | Open | Open | Open
586 | M1100 | MOM | 2024-06-14 |  |  |  | OEM Related |  | External API details provided by L&T are currently not functioning.(BBNL Integration) |  | Critical | Open |  |  | 23-Sep-25: Approved shall be closed | [12 empty] | OEM Related Issues | Closed | CLOSED | 23-Sep-25: Approved shall be closed | FALSE | [5 empty] | 2025-09-23 | Artefacts not Required | Completed & Approved | Closed before june-2025 | Closed after June
587 | M1101 | MOM | 2024-06-14 |  |  |  | OEM Related |  | API extension for Alarm Enrichment is not functioning, and inventory API is operational. |  | Critical | Open |  |  | 23-Sep-25: Approved shall be closed | [12 empty] | OEM Related Issues | Closed | CLOSED | 23-Sep-25: Approved shall be closed | FALSE | [5 empty] | 2025-09-23 | Artefacts not Required | Completed & Approved | Closed before june-2025 | Closed after June
588 | M1102 | MOM | 2024-06-14 |  |  |  | OEM Related |  | Service impact analysis is not available, and cross-domain RCA is not provided. |  | Critical | Open |  |  | 16-Oct-25: Covered in OSS Operationalization | [12 empty] | OEM Related Issues | OPEN | Duplicate | 16-Oct-25: Covered in OSS Operationalization | FALSE | [7 empty] | Open | Open | Open
589 | M1103 | MOM | 2024-06-14 |  |  |  | OEM Related |  | Alarm forwarding API is not working, and there is a need for service impact and network impact information. |  | Critical | Open |  |  | 16-Oct-25: Covered in Service Inventory Solution | [12 empty] | OEM Related Issues | OPEN | OPEN | 16-Oct-25: Covered in Service Inventory Solution | TRUE | [7 empty] | Open | Open | Open
590 | M1104 | MOM | 2024-06-14 |  |  |  | OEM Related |  | There is no topology and zonal view of IPMPLS, and some performance management points are pending validation. |  | Critical | Open |  |  | 16-Oct-25: Covered in OSS Operationalization | [12 empty] | OEM Related Issues | OPEN | Duplicate | 16-Oct-25: Covered in OSS Operationalization | FALSE | [7 empty] | Open | Open | Open
591 | M1105 | MOM | 2024-06-14 |  |  |  | OEM Related |  | L&T to submit all API documents, not just BBNL, and involve T-Fiber for review. |  | Critical | Open |  |  | 23-Sep-25: Approved Artefacts to be Submitted | [12 empty] | OEM Related Issues | Closed | CLOSED | 23-Sep-25: Approved Artefacts to be Submitted | FALSE | [6 empty] | Artefacts Need to upload | Completed & Approved | Closed before june-2025 | Closed after June
592 | M1106 | MOM | 2024-06-14 |  |  |  | OEM Related |  | L&T to demonstrate functionality and ensure alarm management is in place with the necessary enrichments. |  | Critical | Open |  |  | 23-Sep-25: Approved shall be closed | [12 empty] | OEM Related Issues | Closed | CLOSED | 23-Sep-25: Approved shall be closed | FALSE | [5 empty] | 2025-09-23 | Artefacts not Required | Completed & Approved | Closed before june-2025 | Closed after June
593 | M1107 | MOM | 2024-06-14 |  |  |  | OEM Related |  | OpenText to demonstrate the NNMi KPI dashboard and complete the end-to-end demo for threshold values. |  | Critical | Open |  |  | 16-Oct-25: Covered in OSS implementation tracker | [12 empty] | OEM Related Issues | OPEN | Duplicate | 16-Oct-25: Covered in OSS implementation tracker | FALSE | [7 empty] | Open | Open | Open
594 | M1108 | MOM | 2024-06-14 |  |  |  | OEM Related |  | L&T to define the scope with NSO for the Service Inventory module and ensure it is part of the deliverables. |  | Critical | Open |  |  | 16-Oct-25: Proposed service inventory solution, under review | [12 empty] | OEM Related Issues | OPEN | OPEN | 16-Oct-25: Proposed service inventory solution, under review | TRUE | [7 empty] | Open | Open | Open
595 | M1109 | MOM | 2024-06-14 |  |  |  | OEM Related |  | HPE to revisit all alarm scenarios, involve T-Fiber for review, and bring in industry best practices. |  | Critical | Open |  |  | 23-Sep-25: Approved shall be closed | [12 empty] | OEM Related Issues | Closed | CLOSED | 23-Sep-25: Approved shall be closed | FALSE | [5 empty] | 2025-09-23 | Artefacts not Required | Completed & Approved | Closed before june-2025 | Closed after June
596 | M111 | MOM | 2023-08-01 |  |  |  | Helpdesk | Handbook & SOPs | Documentation required stating that L2 agents shall make outbound calls to customers. |  | NON-Critical | open |  |  | 24-Sep-25: Updated Document Shared 23-Aug-23 | [12 empty] | Helpdesk (Contact Center) | Closed | [8 empty] | 2025-09-24 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\M104,105,109,111,113,115,122,123,127,128,130,132,162 | Completed & Approved | Closed before june-2025 | Closed after June
597 | M1110 | MOM | 2024-06-14 |  |  |  | OEM Related |  | HPE to review the RFP, compliance documents, solution documents, and HLD document, and offer the system for AT if everything is in compliance. |  | Critical | Open |  |  | 16-Oct-25: Covered in OSS ATP | [12 empty] | OEM Related Issues | OPEN | Duplicate | 16-Oct-25: Covered in OSS ATP | FALSE | [7 empty] | Open | Open | Open
598 | M1111 | MOM | 2024-06-14 |  |  |  | OEM Related |  | L&T to provide API library access and complete API documents of OpenText to T-Fiber as soon as possible, with follow-up by Director-NOC, T-Fiber. |  | Critical | Open |  |  | 23-Sep-25: Approved Artefacts to be Submitted | [12 empty] | OEM Related Issues | Closed | CLOSED | 23-Sep-25: Approved Artefacts to be Submitted | FALSE | [6 empty] | Artefacts Need to upload | Completed & Approved | Closed before june-2025 | Closed after June
599 | M1112 | MOM | 2024-06-14 |  |  |  | OEM Related |  | BBNL integration task completion by 30th June 2024, with day-to-day progress monitoring by Director-NOC, T-Fiber. |  | Critical | Open |  |  | 23-Sep-25: Approved shall be closed | [12 empty] | OEM Related Issues | Closed | CLOSED | 23-Sep-25: Approved shall be closed | FALSE | [5 empty] | 2025-09-23 | Artefacts not Required | Completed & Approved | Closed before june-2025 | Closed after June
600 | M1113 | MOM | 2024-06-14 |  |  |  | OEM Related |  | OpenText to provide a SMAX proposal with a detailed presentation for potential replacement analysis. |  | Critical | Open |  |  | 16-Oct-25: will check with OT and arrange, however OT upgrade plan was shared | [12 empty] | OEM Related Issues | OPEN | OPEN | 16-Oct-25: will check with OT and arrange, however OT upgrade plan was shared | TRUE | [7 empty] | Open | Open | Open
601 | M1114 | MOM | 2024-06-14 |  |  |  | OEM Related |  | L&T to arrange a demo for Server Performance Monitoring and submit all KPI details. |  | Critical | Open |  |  | 16-Oct-25: Covered in NNMi demo | [12 empty] | OEM Related Issues | OPEN | Duplicate | 16-Oct-25: Covered in NNMi demo | FALSE | [7 empty] | Open | Open | Open
602 | M1115 | MOM | 2024-06-14 |  |  |  | OEM Related |  | OpenText to define custom reports for centralized and customizable service level reporting. |  | Critical | Open |  |  | 16-Oct-25: to be discussed on the requirements | [12 empty] | OEM Related Issues | OPEN | OPEN | 16-Oct-25: to be discussed on the requirements | TRUE | [7 empty] | Open | Open | Open
603 | M1116 | MOM | 2024-06-14 |  |  |  | OEM Related |  | OpenText to provide a 7-year direct support commitment and an approval system via email & mobile app. |  | Critical | Open |  |  | 23-Sep-25: Approved Artefacts to be Submitted | [12 empty] | OEM Related Issues | Closed | CLOSED | 23-Sep-25: Approved Artefacts to be Submitted | FALSE | [6 empty] | Artefacts Need to upload | Completed & Approved | Closed before june-2025 | Closed after June
604 | M1117 | MOM | 2024-06-14 |  |  |  | OEM Related |  | OpenText to provide a list of device models supported for SNMP polling. |  | Critical | Open |  |  | 23-Sep-25: Approved Artefacts to be Submitted | [12 empty] | OEM Related Issues | Closed | CLOSED | 23-Sep-25: Approved Artefacts to be Submitted | FALSE | [6 empty] | Artefacts Need to upload | Completed & Approved | Closed before june-2025 | Closed after June
605 | M1118 | MOM | 2024-06-14 |  |  |  | OEM Related |  | Full API library of vTemIP is unavailable, affecting self-testing of modules. |  | Critical | Open |  |  | 23-Sep-25: Approved Artefacts to be Submitted | [12 empty] | OEM Related Issues | Closed | CLOSED | 23-Sep-25: Approved Artefacts to be Submitted | FALSE | [6 empty] | Artefacts Need to upload | Completed & Approved | Closed before june-2025 | Closed after June
606 | M1119 | MOM | 2024-06-14 |  |  |  | OEM Related |  | Product support status from OpenText and incident management issues, including ticket grouping and content filtering. |  | Critical | Open |  |  | 23-Sep-25: Approved Artefacts to be Submitted | [12 empty] | OEM Related Issues | Closed | CLOSED | 23-Sep-25: Approved Artefacts to be Submitted | FALSE | [6 empty] | Artefacts Need to upload | Completed & Approved | Closed before june-2025 | Closed after June
607 | M112 | MOM | 2023-08-01 |  |  |  | Helpdesk | Handbook & SOPs | Inquiry about how the Helpdesk addresses cases where the number of the person calling differs from the number registered in the BSS database. |  | NON-Critical | open |  |  | 11-Sep-25: Through BSS Integration and IVR flows aligned accordingly | [12 empty] | Helpdesk (Contact Center) | OPEN | [10 empty] | Open | Open | Open
608 | M1120 | MOM | 2024-06-14 |  |  |  | OEM Related |  | Unavailability of a consolidated dashboard and cross-domain topology visibility. |  | Critical | Open |  |  | 16-Oct-25: Covered in OSS implementation tracker | [12 empty] | OEM Related Issues | OPEN | Duplicate | 16-Oct-25: Covered in OSS implementation tracker | FALSE | [7 empty] | Open | Open | Open
609 | M1121 | MOM | 2024-06-14 |  |  |  | OEM Related |  | Instability of OBR and NNMi causing issues in IT event management. |  | Critical | Open |  |  | 16-Oct-25: OT stack upgrade plan shared | [12 empty] | OEM Related Issues | OPEN | OPEN | 16-Oct-25: OT stack upgrade plan shared | TRUE | [7 empty] | Open | Open | Open
610 | M1122 | MOM | 2024-06-14 |  |  |  | OEM Related |  | Concerns about the pending Network Automation and the process for implementing upgrades. |  | Critical | Open |  |  | 16-Oct-25: OT stack upgrade plan shared DUPLICATE POINT (NOC624) | [12 empty] | OEM Related Issues | OPEN | Duplicate | 16-Oct-25: OT stack upgrade plan shared | FALSE | [7 empty] | Open | Open | Open
611 | M1123 | MOM | 2024-06-14 |  |  |  | OEM Related |  | OpenText to check and revert with timelines for API library access. |  | Critical | Open |  |  | 23-Sep-25: Approved Artefacts to be Submitted | [12 empty] | OEM Related Issues | Closed | CLOSED | 23-Sep-25: Approved Artefacts to be Submitted | FALSE | [6 empty] | Artefacts Need to upload | Completed & Approved | Closed before june-2025 | Closed after June
612 | M1124 | MOM | 2024-06-14 |  |  |  | OEM Related |  | OpenText to revisit the issue of limited ticket visibility in the UI and accommodate more data. |  | Critical | Open |  |  | 23-Sep-25: Approved shall be closed | [12 empty] | OEM Related Issues | Closed | CLOSED | 23-Sep-25: Approved shall be closed | FALSE | [5 empty] | 2025-09-23 | Artefacts not Required | Completed & Approved | Closed before june-2025 | Closed after June
613 | M1125 | MOM | 2024-06-14 |  |  |  | OEM Related |  | L&T to establish a product service contract and ensure the operational team is fully engaged. |  | Critical | Open |  |  | 23-Sep-25: Approved Artefacts to be Submitted | [12 empty] | OEM Related Issues | Closed | CLOSED | 23-Sep-25: Approved Artefacts to be Submitted | FALSE | [6 empty] | Artefacts Need to upload | Completed & Approved | Closed before june-2025 | Closed after June
614 | M1126 | MOM | 2024-06-14 |  |  |  | OEM Related |  | OpenText to provide a solution for Service Level Reporting & availability and to demonstrate WAN-LAN connectivity mapping. |  | Critical | Open |  |  | 16-Oct-25: Covered in OSS implementation tracker | [12 empty] | OEM Related Issues | OPEN | Duplicate | 16-Oct-25: Covered in OSS implementation tracker | FALSE | [7 empty] | Open | Open | Open
615 | M1127 | MOM | 2024-06-14 |  |  |  | OEM Related |  | L&T to discuss with OpenText about Network Automation for Deployment and configuration check module License. |  | Critical | Open |  |  | 16-Oct-25: Covered in OSS implementation tracker | [12 empty] | OEM Related Issues | OPEN | Duplicate | 16-Oct-25: Covered in OSS implementation tracker | FALSE | [7 empty] | Open | Open | Open
616 | M1128 | MOM | 2024-06-14 |  |  |  | OEM Related |  | OpenText to deploy a dedicated resource in Hyderabad to close all open points and establish a standard test bed environment. |  | Critical | Open |  |  | 23-Sep-25: Approved shall be closed | [12 empty] | OEM Related Issues | Closed | CLOSED | 23-Sep-25: Approved shall be closed | FALSE | [5 empty] | 2025-09-23 | Artefacts not Required | Completed & Approved | Closed before june-2025 | Closed after June
617 | M1129 | MOM | 2024-06-14 |  |  |  | OEM Related |  | All demonstrations should be conducted in the presence of T-Fiber representatives, and product compliance with ITIL Gold level certification needs to be rechecked. |  | Critical | Open |  |  | 23-Sep-25: Approved Artefacts to be Submitted | [12 empty] | OEM Related Issues | Closed | CLOSED | 23-Sep-25: Approved Artefacts to be Submitted | FALSE | [6 empty] | Artefacts Need to upload | Completed & Approved | Closed before june-2025 | Closed after June
618 | M113 | MOM | 2023-08-01 |  |  |  | Helpdesk | Handbook & SOPs | Clarification needed on the sphere of activity between NOC Technical administrators and Helpdesk agents. |  | NON-Critical | open |  |  | 24-Sep-25: Updated Document Shared 23-Aug-23 | [12 empty] | Helpdesk (Contact Center) | Closed | [8 empty] | 2025-09-24 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\M104,105,109,111,113,115,122,123,127,128,130,132,162 | Completed & Approved | Closed before june-2025 | Closed after June
619 | M1130 | MOM | 2024-06-28 |  |  |  | Security & Regulatory Compliance | Compliance | L&T Security Teams & Technical Head to resolve login issues for Pkg B & C teams by the end of the next week. |  | Critical | Open |  |  | 28-Nov-25: Gathering artifacts from other teams | [12 empty] | Security | OPEN | [10 empty] | Open | Open | Open
620 | M1131 | MOM | 2024-06-28 |  |  |  | OSS | Product | L&T OSS SME to provide updates on the PMS issue with the secondary database after consultation with the OEM. |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | 0 | Completed With Artifacts | TRUE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
621 | M1132 | MOM | 2024-06-28 |  |  |  | Security & Regulatory Compliance | Compliance | L&T to work with the vendor to define a solution for integrating AD with Alepo AAA. |  | Critical | Open |  |  | 28-Nov-25: The Alepo team is integrating AD Once done these points will be closed | [12 empty] | Security | OPEN | [10 empty] | Open | Open | Open
622 | M1133 | MOM | 2024-06-28 |  |  |  | Security & Regulatory Compliance | Compliance | GPON SME to discuss with OEM and understand the reporting for categorizing users in EMS & AMS systems. |  | Critical | Open | [15 empty] | Security | Closed | [8 empty] | 2025-11-12 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\NW-Security\M1133.pdf | Completed & Approved | Closed after 07-Nov-25 | Open
623 | M1134 | MOM | 2024-06-28 |  |  |  | Security & Regulatory Compliance | Compliance | L&T Security team & DC infra team to complete the RBAC list updates with domain-wise user information. |  | Critical | Closed |  |  | 28-Nov-25: Work in Progress | [12 empty] | Security | OPEN | [10 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
624 | M1135 | MOM | 2024-06-28 |  |  |  | Security & Regulatory Compliance | Compliance | AD not integrating with Alepo AAA. |  | Critical | Open |  |  | 28-Nov-25: The Alepo team is integrating AD Once done these points will be closed | [12 empty] | Security | OPEN | [10 empty] | Open | Open | Open
625 | M1136 | MOM | 2024-06-28 |  |  |  | Security & Regulatory Compliance | Compliance | Local users not removed in EMS, AMS, etc., and not verified through AD/Alepo AAA. |  | Critical | Open |  |  | 28-Nov-25: Work in Progress | [12 empty] | Security | OPEN | [10 empty] | Open | Open | Open
626 | M1137 | MOM | 2024-06-28 |  |  |  | Security & Regulatory Compliance | Compliance | Cisco EPNM has two separate profiles for a single user after login through TACACS, which needs resolution. |  | Critical | Open | [15 empty] | Security | Closed | [8 empty] | 2025-11-12 | Artefcats not required | Completed & Approved | Closed after 07-Nov-25 | Open
627 | M1138 | MOM | 2024-06-28 |  |  |  | Security & Regulatory Compliance | Compliance | L&T does not have HPE Admin access and is missing some OT systems in OSS. |  | Critical | Open |  |  | 18-Nov-25: All user credentails to be shared(Servers, DB, Applications) | [12 empty] | Security | OPEN | 0 | No Artifact Required | TRUE | [7 empty] | Reopened | Reopened | Completed but Verification undrer Process
628 | M1139 | MOM | 2024-06-28 |  |  |  | Security & Regulatory Compliance | Compliance | ISE HA DC to DR not working due to pending ISE software upgrade. |  | Critical | Open | [15 empty] | Security | Closed | [8 empty] | 2025-10-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\NW-Security\M1139_29-Oct-25.pdf | Closed | Closed After 14-Oct | Open
629 | M114 | MOM | 2023-08-01 |  |  |  | Helpdesk | Training | Training for Helpdesk Users and Managers |  | Critical | open |  |  | 24-Sep-25: Artefacts to be uploaded | [12 empty] | Helpdesk (Contact Center) | Closed | [8 empty] | 2025-09-24 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\M114,722,134 | Completed & Approved | Closed before june-2025 | Closed after June
630 | M1140 | MOM | 2024-06-28 |  |  |  | Security & Regulatory Compliance | Compliance | L&T to share user details with Ravi for reconciliation in RBAC worksheets. |  | Critical | Open |  |  | 28-Nov-25: Gathering artifacts from other teams | [12 empty] | Security | OPEN | [10 empty] | Open | Open | Open
631 | M1141 | MOM | 2024-06-28 |  |  |  | Security & Regulatory Compliance | Compliance | L&T to ensure all users are domain verified through AD/Alepo AAA and remove local users. |  | Critical | Open |  |  | 28-Nov-25: The Alepo team is integrating AD Once done these points will be closed | [12 empty] | Security | OPEN | [10 empty] | Open | Open | Open
632 | M1142 | MOM | 2024-06-28 |  |  |  | Security & Regulatory Compliance | Compliance | L&T to follow a consistent format for user IDs across all domains. |  | Critical | Open | [15 empty] | Security | Closed | [8 empty] | 2025-11-01 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\NW-Security\T307_31-Oct-25.pdf\\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\NW-Security\M1142_31-Oct-25.pdf | Closed | Closed After 14-Oct | Open
633 | M1143 | MOM | 2024-06-28 |  |  |  | Security & Regulatory Compliance | Compliance | L&T OSS SME to initiate communication with OEMs for admin user control access. |  | Critical | Open |  |  | 18-Nov-25: All user credentails to be shared(Servers, DB, Applications) | [12 empty] | Security | OPEN | 0 | No Artifact Required | TRUE | [7 empty] | Reopened | Reopened | Completed but Verification undrer Process
634 | M1144 | MOM | 2024-06-28 |  |  |  | Security & Regulatory Compliance | Compliance | L&T to prepare a checklist, test user access domain-wise, and create users based on necessary approvals. |  | Critical | Open | [15 empty] | Security | Closed | [8 empty] | 2025-11-01 | Artefacts not Required | Closed | Closed After 14-Oct | Open
635 | M1145 | MOM | 2024-06-28 |  |  |  | Security & Regulatory Compliance | Compliance | L&T to rebuild CSM with necessary resources (storage) as a long-term solution. |  | Critical | Open | [15 empty] | Security | Closed | [8 empty] | 2025-10-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\NW-Security\M1145_29-Oct-25.pdf | Closed | Closed After 14-Oct | Open
636 | M1146 | MOM | 2024-06-28 |  |  |  | Security & Regulatory Compliance | Compliance | Mark Mr. Sandeep in any escalation emails for pending issues with L&T. |  | Critical | Open |  |  | 28-Nov-25: To discuss with mr Sanjay to get clarifications on the points Sandeep is marked in mails | [12 empty] | Security | OPEN | [10 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
637 | M1147 | MOM | 2024-07-12 |  |  |  | OEM Related |  | Cisco confirmed that Airtel uses NSO for IP/MPLS with around 70,000 devices, and Jio uses it for transport management and service provisioning. |  | Critical | Open |  |  | 16-Oct-25: it's info, no action | [12 empty] | OEM Related Issues | OPEN | CLOSED | 16-Oct-25: it's info, no action | FALSE | [7 empty] | Open | Open | Open
638 | M1148 | MOM | 2024-07-12 |  |  |  | OEM Related |  | In T-Fiber, NSO interfaces with EMS for GPON (Nokia & Tejas) and directly with network elements for Cisco IP/MPLS. |  | Critical | Open |  |  | 16-Oct-25: it's info, no action | [12 empty] | OEM Related Issues | OPEN | CLOSED | 16-Oct-25: it's info, no action | FALSE | [7 empty] | Open | Open | Open
639 | M1149 | MOM | 2024-07-12 |  |  |  | OEM Related |  | SVP, T-Fiber requested a comprehensive update on the project's progress, including accomplishments, pending tasks, and future plans. |  | Critical | Open |  |  | 16-Oct-25: it's info, ongoing | [12 empty] | OEM Related Issues | OPEN | CLOSED | 16-Oct-25: it's info, ongoing | FALSE | [7 empty] | Open | Open | Open
640 | M115 | MOM | 2023-08-01 |  |  |  | Helpdesk | Handbook & SOPs | Detailed Helpdesk Process Steps |  | Critical | open |  |  | 24-Sep-25: Updated Document Shared 23-Aug-23 | [12 empty] | Helpdesk (Contact Center) | Closed | [8 empty] | 2025-09-24 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\M104,105,109,111,113,115,122,123,127,128,130,132,162 | Completed & Approved | Closed before june-2025 | Closed after June
641 | M1150 | MOM | 2024-07-12 |  |  |  | OEM Related | Cisco | Cisco confirmed that lab licenses are provided free with production licenses and that it is standard practice to set up a pre-production environment. |  | Critical | Open |  |  | 16-Oct-25: Following with Cisco | [12 empty] | OEM Related Issues | OPEN | OPEN | 16-Oct-25: Following with Cisco | TRUE | [7 empty] | Open | Open | Open
642 | M1151 | MOM | 2024-07-12 |  |  |  | OEM Related | Cisco | Cisco assured to provide access to the Smartlicenses portal for T-Fiber and to share the full library of APIs for all A&O modules. |  | Critical | Open |  |  | 16-Oct-25: Following with Cisco | [12 empty] | OEM Related Issues | OPEN | OPEN | 16-Oct-25: Following with Cisco | TRUE | [7 empty] | Open | Open | Open
643 | M1152 | MOM | 2024-07-12 |  |  |  | OEM Related |  | Technical Support and Operations: |  | Critical | Open |  |  | 23-Sep-25: Approved shall be closed | [12 empty] | OEM Related Issues | Closed | CLOSED | 23-Sep-25: Approved shall be closed | FALSE | [5 empty] | 2025-09-23 | Artefacts not Required | Completed & Approved | Closed before june-2025 | Closed after June
644 | M1153 | MOM | 2024-07-12 |  |  |  | OEM Related |  | Discussions were held about the method of operation for NED and product lifecycle management. |  | Critical | Open |  |  | 23-Sep-25: Approved shall be closed | [12 empty] | OEM Related Issues | Closed | CLOSED | 23-Sep-25: Approved shall be closed | FALSE | [5 empty] | 2025-09-23 | Artefacts not Required | Completed & Approved | Closed before june-2025 | Closed after June
645 | M1154 | MOM | 2024-07-12 |  |  |  | OEM Related | Cisco | Cisco suggested a gradual handover process with a joint account of L&T and Cisco for a smooth transition. |  | Critical | Open |  |  | 16-Oct-25: Will take Cisco TAC support wherever required | [12 empty] | OEM Related Issues | OPEN | OPEN | 16-Oct-25: Will take Cisco TAC support wherever required | TRUE | [7 empty] | Open | Open | Open
646 | M1155 | MOM | 2024-07-12 |  |  |  | OEM Related | NSO | Director-P&E, T-Fiber inquired about the system responsible for maintaining the complete inventory within NSO. |  | Critical | Open |  |  | 16-Oct-25: scope of NSO, covered in NSO implementation tracker | [12 empty] | OEM Related Issues | OPEN | Duplicate | 16-Oct-25: scope of NSO, covered in NSO implementation tracker | FALSE | [7 empty] | Open | Open | Open
647 | M1156 | MOM | 2024-07-12 |  |  |  | OEM Related | Cisco | Cisco mentioned that full orchestration currently requires human intervention, and a service discovery and reconciliation module is needed for full automation. |  | Critical | Open |  |  | 16-Oct-25: Reconciliation will be inhouse solution along with service discovery & inventory | [12 empty] | OEM Related Issues | OPEN | OPEN | 16-Oct-25: Reconciliation will be inhouse solution along with service discovery & inventory | TRUE | [7 empty] | Open | Open | Open
648 | M1157 | MOM | 2024-07-12 |  |  |  | OEM Related |  | Concerns were raised about customization in the pre-production phase and the need to complete customizations before going live. |  | Critical | Open |  |  | 16-Oct-25: Directions for any Prod deployment and same followed | [12 empty] | OEM Related Issues | OPEN | CLOSED | 16-Oct-25: Directions for any Prod deployment and same followed | FALSE | [7 empty] | Open | Open | Open
649 | M1158 | MOM | 2024-07-12 |  |  |  | OEM Related | Cisco | Cisco emphasized the importance of a change management system for configuration changes and the need for a service audit feature. |  | Critical | Open |  |  | 16-Oct-25: scope of NSO, covered in NSO implementation tracker | [12 empty] | OEM Related Issues | OPEN | Duplicate | 16-Oct-25: scope of NSO, covered in NSO implementation tracker | FALSE | [7 empty] | Open | Open | Open
650 | M1159 | MOM | 2024-07-12 |  |  |  | OEM Related | Cisco | Cisco to provide all API libraries and hand over NED with knowledge transfers. |  | Critical | Open |  |  | 16-Oct-25: scope of NSO, covered in NSO implementation tracker | [12 empty] | OEM Related Issues | OPEN | Duplicate | 16-Oct-25: scope of NSO, covered in NSO implementation tracker | FALSE | [7 empty] | Open | Open | Open
651 | M116 | MOM | 2023-08-01 |  |  |  | Helpdesk | Handbook & SOPs | Clarification needed on addressing the subjective nature of "Non-Technical" calls. |  | Critical | open |  |  | 24-Sep-25: It will be Handled by Proposed T fiber Business Helpdesk | [12 empty] | Helpdesk (Contact Center) | Closed | [8 empty] | 2025-09-24 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\M116,723,1026 | Completed & Approved | Closed before june-2025 | Closed after June
652 | M1160 | MOM | 2024-07-12 |  |  |  | OEM Related | OSS | Inventory module and bandwidth manager are still open issues. |  | Critical | Open |  |  | 16-Oct-25: Covered in Service Inventory Solution | [12 empty] | OEM Related Issues | OPEN | Duplicate | 16-Oct-25: Covered in Service Inventory Solution | FALSE | [7 empty] | Open | Open | Open
653 | M1161 | MOM | 2024-07-12 |  |  |  | OEM Related | OSS | L&T to provide lifecycle processes and how change management and customization are done post-production. |  | Critical | Open |  |  | 16-Oct-25: scope of NSO, covered in NSO implementation tracker | [12 empty] | OEM Related Issues | OPEN | Duplicate | 16-Oct-25: scope of NSO, covered in NSO implementation tracker | FALSE | [7 empty] | Open | Open | Open
654 | M1162 | MOM | 2024-07-12 |  |  |  | OEM Related | NSO | Cisco to provide E2E topology feasibility, including bandwidth management using NSO. |  | Critical | Open |  |  | 16-Oct-25, Network & Cross Domain topology covered in OSS, service topology not in scope | [12 empty] | OEM Related Issues | OPEN | OPEN | 16-Oct-25, Network & Cross Domain topology covered in OSS, service topology not in scope | TRUE | [7 empty] | Open | Open | Open
655 | M1163 | MOM | 2024-07-12 |  |  |  | OEM Related |  | Director-P&E, T-Fiber asked for the deployment of the system in a pre-production environment for thorough testing. |  | Critical | Open |  |  | 16-Oct-25: Directions for any Prod deployment and same followed | [12 empty] | OEM Related Issues | OPEN | Duplicate | 16-Oct-25: Directions for any Prod deployment and same followed | FALSE | [7 empty] | Open | Open | Open
656 | M1164 | MOM | 2024-07-12 |  |  |  | OEM Related |  | SVP, T-Fiber requested access to all modules within the pre-production environment, along with necessary licenses. |  | Critical | Open |  |  | 16-Oct-25: TnD access provide to T-Fiber | [12 empty] | OEM Related Issues | OPEN | CLOSED | 16-Oct-25: TnD access provide to T-Fiber | FALSE | [7 empty] | Open | Open | Open
657 | M1165 | MOM | 2024-07-12 |  |  |  | OEM Related |  | Director-P&E, T-Fiber emphasized the importance of the system being modular and raised concerns about functionality without BSS. |  | Critical | Open |  |  | 23-Sep-25: Approved shall be closed | [12 empty] | OEM Related Issues | Closed | CLOSED | 23-Sep-25: Approved shall be closed | FALSE | [5 empty] | 2025-09-23 | Artefacts not Required | Completed & Approved | Closed before june-2025 | Closed after June
658 | M1166 | MOM | 2024-07-15 |  |  |  | OEM Related |  | L&T to inform T-Fiber and provide details once solution support is fully deployed. |  | Critical | Open |  |  | 16-Oct-25: LnT will take Cisco support wherever required | [12 empty] | OEM Related Issues | OPEN | OPEN | 16-Oct-25: LnT will take Cisco support wherever required | TRUE | [7 empty] | Open | Open | Open
659 | M1167 | MOM | 2024-07-15 |  |  |  | OEM Related |  | L&T to focus on solution reports and resolve operational issues related to UTM. |  | Critical | Open |  |  | 16-Oct-25: Covered in OSS operationalization | [12 empty] | OEM Related Issues | OPEN | Duplicate | 16-Oct-25: Covered in OSS operationalization | FALSE | [7 empty] | Open | Open | Open
660 | M1168 | MOM | 2024-07-15 |  |  |  | OEM Related |  | HPE to consider features not possible for alternative solutions. |  | Critical | Open |  |  | 16-Oct-25: Support will be taken if any part of RFP scope. | [12 empty] | OEM Related Issues | OPEN | OPEN | 16-Oct-25: Support will be taken if any part of RFP scope. | TRUE | [7 empty] | Open | Open | Open
661 | M1169 | MOM | 2024-07-15 |  |  |  | OEM Related |  | L&T to provide automation in the purge-auto termination process without manual intervention. |  | Critical | Open |  |  | 16-Oct-25: LnT take care of scripting & automation if feasible | [12 empty] | OEM Related Issues | OPEN | OPEN | 16-Oct-25: LnT take care of scripting & automation if feasible | TRUE | [7 empty] | Open | Open | Open
662 | M117 | MOM | 2023-08-01 |  |  |  | Helpdesk | Handbook & SOPs | Assumptions for Estimated Calls per Day |  | Critical | open |  |  | 24-Sep-25: Artefacts to be uploaded | [12 empty] | Helpdesk (Contact Center) | Closed | [8 empty] | 2025-09-24 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\M117,126,728 | Completed & Approved | Closed before june-2025 | Closed after June
663 | M1170 | MOM | 2024-07-15 |  |  |  | OEM Related |  | L&T to ensure GIS is the master source for passive infra and it should be a permanent solution. |  | Critical | Open |  |  | 23-Sep-25: Approved shall be closed | [12 empty] | OEM Related Issues | Closed | CLOSED | 23-Sep-25: Approved shall be closed | FALSE | [5 empty] | 2025-09-23 | Artefacts not Required | Completed & Approved | Closed before june-2025 | Closed after June
664 | M1171 | MOM | 2024-07-15 |  |  |  | OEM Related |  | L&T to provide all relevant data to facilitate customization requirements for business. |  | Critical | Open |  |  | 23-Sep-25: Approved shall be closed | [12 empty] | OEM Related Issues | Closed | CLOSED | 23-Sep-25: Approved shall be closed | FALSE | [5 empty] | 2025-09-23 | Artefacts not Required | Completed & Approved | Closed before june-2025 | Closed after June
665 | M1172 | MOM | 2024-07-15 |  |  |  | OEM Related |  | L&T assured that technical support would be available for the long term and operational training would continue until the complete delivery of the contract. |  | Critical | Open |  |  | 23-Sep-25: Approved shall be closed | [12 empty] | OEM Related Issues | Closed | CLOSED | 23-Sep-25: Approved shall be closed | FALSE | [5 empty] | 2025-09-23 | Artefacts not Required | Completed & Approved | Closed before june-2025 | Closed after June
666 | M1173 | MOM | 2024-07-15 |  |  |  | OEM Related |  | L&T to demonstrate all points, including completed points, to ensure transparency on solutions implemented. |  | Critical | Open |  |  | 16-Oct-25: Covered in all domain implementation trackers | [12 empty] | OEM Related Issues | OPEN | Duplicate | 16-Oct-25: Covered in all domain implementation trackers | FALSE | [7 empty] | Open | Open | Open
667 | M1174 | MOM | 2024-07-15 |  |  |  | OEM Related |  | L&T to prioritize tasks to support business along with T-Fiber to maintain efficient and effective operational workflows. |  | Critical | Open |  |  | 16-Oct-25: it's info, general guidelines | [12 empty] | OEM Related Issues | OPEN | CLOSED | 16-Oct-25: it's info, general guidelines | FALSE | [7 empty] | Open | Open | Open
668 | M1175 | MOM | 2024-07-15 |  |  |  | OEM Related |  | L&T and HPE to provide timelines for operational, delivery, and technical support, as well as a plan for out-of-the-box features. |  | Critical | Open |  |  | 16-Oct-25: It's covered in Pending SOW | [12 empty] | OEM Related Issues | OPEN | CLOSED | 16-Oct-25: It's covered in Pending SOW | FALSE | [7 empty] | Open | Open | Open
669 | M1176 | MOM | 2024-07-15 |  |  |  | OEM Related |  | L&T to provide updated LLD document and ensure that all Licenses are provided to T-Fiber as they are an asset of T-Fiber. |  | Critical | Open |  |  | 16-Oct-25: Covered in NOC go-live plan | [12 empty] | OEM Related Issues | OPEN | Duplicate | 16-Oct-25: Covered in NOC go-live plan | FALSE | [7 empty] | Open | Open | Open
670 | M1177 | MOM | 2024-07-15 |  |  |  | OEM Related |  | L&T to submit customize reports and ensure that all open HP APIs should be made available to L&T and T-Fiber. |  | Critical | Open |  |  | 23-Sep-25: Approved Artefacts to be Submitted | [12 empty] | OEM Related Issues | Closed | CLOSED | 23-Sep-25: Approved Artefacts to be Submitted | FALSE | [6 empty] | Artefacts Need to upload | Completed & Approved | Closed before june-2025 | Closed after June
671 | M1178 | MOM | 2024-07-15 |  |  |  | OEM Related |  | L&T to ensure that the pre-production environment is set up and additional infrastructure needs are met. |  | Critical | Open |  |  | 23-Sep-25: Approved shall be closed | [12 empty] | OEM Related Issues | Closed | CLOSED | 23-Sep-25: Approved shall be closed | FALSE | [5 empty] | 2025-09-23 | Artefacts not Required | Completed & Approved | Closed before june-2025 | Closed after June
672 | M1179 | MOM | 2024-07-15 |  |  |  | OEM Related |  | Director-P&E, T-Fiber emphasized the importance of delivering services and suggested scheduling calls to ensure delivery is on track. |  | Critical | Open |  |  | 23-Sep-25: Approved Artefacts to be Submitted | [12 empty] | OEM Related Issues | Closed | CLOSED | 23-Sep-25: Approved Artefacts to be Submitted | FALSE | [6 empty] | Artefacts Need to upload | Completed & Approved | Closed before june-2025 | Closed after June
673 | M118 | MOM | 2023-08-01 |  |  |  | Helpdesk | Handbook & SOPs | Readiness of Helpdesk to report on compliances and responsiveness and calculate penalties. |  | Critical | open |  |  | 24-Sep-25:Artefacts to be submitted | [12 empty] | Helpdesk (Contact Center) | OPEN | [10 empty] | Open | Open | Open
674 | M1180 | MOM | 2024-07-15 |  |  |  | OEM Related |  | Director-P&E, T-Fiber requested an out-of-box demo as per the pre-bid agreement. |  | Critical | Open |  |  | 23-Sep-25: Approved Artefacts to be Submitted | [12 empty] | OEM Related Issues | Closed | CLOSED | 23-Sep-25: Approved Artefacts to be Submitted | FALSE | [6 empty] | Artefacts Need to upload | Completed & Approved | Closed before june-2025 | Closed after June
675 | M1181 | MOM | 2024-07-15 |  |  |  | OEM Related |  | A detailed discussion is required for DR with all stakeholders, including HPE, OT, and CTRL S, for a comprehensive approach. |  | Critical | Open |  |  | 16-Oct-25: Covered in DR plan | [12 empty] | OEM Related Issues | OPEN | Duplicate | 16-Oct-25: Covered in DR plan | FALSE | [7 empty] | Open | Open | Open
676 | M1182 | MOM | 2024-07-22 |  |  |  | T&D Environment |  | MD, T-Fiber emphasized the necessity of a pre-production setup and directed L&T to submit an infrastructure proposal. |  | NON-Critical | Open |  |  | 11-Oct-25: T Fiber requested to submit reference document Historically the L&T submitted proposal was not approved. Need to work for the final setup | [12 empty] | Applications | OPEN | [10 empty] | Open | Open | Open
677 | M1183 | MOM | 2024-07-22 |  |  |  | OEM Related |  | MD, T-Fiber asked L&T to work with the OEM for a higher license count for the Work Force Management Tool (WFM) and to explore features of government tools for comparison. |  | Critical | Open |  |  | 16-Oct-25: Covered in WFM operationalization | [12 empty] | OEM Related Issues | OPEN | Duplicate | 16-Oct-25: Covered in WFM operationalization | FALSE | [7 empty] | Open | Open | Open
678 | M1184 | MOM | 2024-07-22 |  |  |  | OEM Related | All OEM's | Concerns were raised about the delay in onboarding OEMs like OpenText, HP, and Cisco. |  | Critical | Open |  |  | 16-Oct-25: HPE and OT onboarded, Cisco TAC support available | [12 empty] | OEM Related Issues | OPEN | CLOSED | 16-Oct-25: HPE and OT onboarded, Cisco TAC support available | FALSE | [7 empty] | Open | Open | Open
679 | M1185 | MOM | 2024-07-22 |  |  |  | OEM Related |  | Concerns were raised about the lack of response from Nokia on Hybrid mode solutioning. |  | Critical | Open |  |  | 23-Sep-25: Approved shall be closed | [12 empty] | OEM Related Issues | Closed | CLOSED | 23-Sep-25: Approved shall be closed | FALSE | [5 empty] | 2025-09-23 | Artefacts not Required | Completed & Approved | Closed before june-2025 | Closed after June
680 | M1186 | MOM | 2024-12-09 |  |  |  | NOC Operationalization |  | Principal Consultant to be added in WA groups (only NOC , Service Delivery, Project Delivery , and Technology wise group along with OEMs) |  | Critical | Closed |  |  | 23-Sep-25: Approved shall be closed | [12 empty] | Network | Closed | CLOSED | 23-Sep-25: Approved shall be closed | FALSE | [5 empty] | 2025-09-23 | Artefacts not Required | Completed & Approved | Closed before june-2025 | Closed before june-2025
681 | M1187 | MOM | 2024-12-09 |  |  |  | OEM Related |  | OEM wise physical meeting to be called |  | Critical | Closed |  |  | 23-Sep-25: Approved shall be closed | [12 empty] | OEM Related Issues | Closed | CLOSED | 23-Sep-25: Approved shall be closed | FALSE | [5 empty] | 2025-09-23 | Artefacts not Required | Completed & Approved | Closed before june-2025 | Closed before june-2025
682 | M1188 | MOM | 2024-12-09 |  |  |  | Helpdesk |  | Helpdesk LLD/HLD to be discussed in detailed |  | Critical | Open | [15 empty] | Helpdesk (Contact Center) | OPEN | [10 empty] | Open | Open | Open
683 | M1189 | MOM | 2024-12-09 |  |  |  | NOC Operationalization |  | Only one Issue Tracker to be maintained to track whatever is discussed during current week review |  | Critical | Closed |  |  | 16-Oct-25: all issues trackers covered in implementation tracker | [12 empty] | Network | OPEN | CLOSED | 16-Oct-25: all issues trackers covered in implementation tracker | FALSE | [7 empty] | Open | Open | Open
684 | M119 | MOM | 2023-08-01 |  |  |  | Helpdesk | Handbook & SOPs | Live Intrusion of Calls |  | Critical | open |  |  | 24-Sep-25: Artfcats to be uploaded 11-Sep-25: Feature Available, Shall be demonstrated | [12 empty] | Helpdesk (Contact Center) | Closed | [8 empty] | 2025-09-24 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\M119,733 | Completed & Approved | Closed before june-2025 | Closed after June
685 | M1190 | MOM | 2024-12-09 | P3 |  |  | NOC Operationalization |  | Share NOC Dec24 roaster |  | Critical | Closed |  |  | Roaster shared | [12 empty] | Network | Closed |  |  |  | Daily oprational task |  |  |  |  | 2025-09-24 | "\\172.28.9.23\TNOC_Roaster Plan | Completed & Approved | Closed before june-2025 | Closed before june-2025
686 | M1191 | MOM | 2024-12-09 |  |  |  | NOC Operationalization |  | OSS to be discussed on 10Dec24 or today |  | Critical | Closed |  |  | 23-Sep-25: Approved shall be closed | [12 empty] | Network | Closed | CLOSED | 23-Sep-25: Approved shall be closed | FALSE | [5 empty] | 2025-09-23 | Artefacts not Required | Completed & Approved | Closed before june-2025 | Closed before june-2025
687 | M1192 | MOM | 2024-12-09 |  |  |  | NOC Operationalization |  | Send all presentations to Principal Consultant |  | Critical | Closed |  |  | 23-Sep-25: Approved shall be closed | [12 empty] | Network | Closed | CLOSED | 23-Sep-25: Approved shall be closed | FALSE | [5 empty] | 2025-09-23 | Artefacts not Required | Completed & Approved | Closed before june-2025 | Closed before june-2025
688 | M1193 | MOM | 2024-12-09 |  | OSS | OSS | OSS | NOC Operationalization | Change Mgmt. system to be made up, currently its manual on mails/excel |  | Critical | Open | [15 empty] | Applications/Tools | Closed | 0 | Completed With Artifacts | TRUE | [5 empty] | 2025-11-18 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\OSS\52 Artefcats_18112025 | Closed after 14-Nov-25 | Closed after 14-Nov-25 | Completed but Verification undrer Process
689 | M1194 | MOM | 2024-12-09 |  |  |  | BSS |  | Aravindham have personal challenges, can come on MS Team. Request him to come for 2 day for physical meeting |  | Critical | Closed | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
690 | M1195 | MOM | 2024-12-09 |  |  |  | NSO | Service provisioning | IP Schema to discussed |  | Critical | Closed |  |  | 29-dec-2025: Need discussion | [7 empty] | Not Started |  |  |  |  | Applications/Tools | OPEN |  |  |  |  | Need clarity on whether this refers to IPv4, IPv6, or both. | [5 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
691 | M1196 | MOM | 2024-12-09 |  |  |  | NOC Operationalization |  | Current PRIORITY discussion to be done for : NOC Review, OSS, DC-Infra, Call Centre HLD/LLD, IP MPLS. Balance to be communicated during the sessions |  | NON-Critical | Closed |  |  | 23-Sep-25: Approved shall be closed | [12 empty] | Network | Closed | CLOSED | 23-Sep-25: Approved shall be closed | FALSE | [5 empty] | 2025-09-23 | Artefacts not Required | Completed & Approved | Closed before june-2025 | Closed before june-2025
692 | M1197 | MOM | 2024-12-09 | P3 |  |  | NOC Operationalization |  | Different kinds of reports to be discussed : Daily reports/dashboards, Capacity reports for all nodes/links (like ISP Util, Capacities utilization, licenses , availability reports for PCK-A/B/C technology wise, etc.) |  | Critical | Closed |  |  | Discussed and reports sent to Principal COnsultant | [12 empty] | Network | Closed |  |  |  | Covered in OSS |  |  |  |  | 2025-09-19 | Artefacts not Required | Completed & Approved | Closed before june-2025 | Closed before june-2025
693 | M1198 | MOM | 2024-12-09 |  | OSS | OSS | OSS | BBNL | CDOT integration with NMS is highest priority. The team should be actively engaged with teams and visit sites. |  | Critical | Closed | [15 empty] | Applications/Tools | Closed | 0 | Completed With Artifacts | TRUE | [5 empty] | 2025-11-18 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\OSS\52 Artefcats_18112025 | Closed after 14-Nov-25 | Closed after 14-Nov-25 | Completed but Verification undrer Process
694 | M1199 | MOM | 2024-12-09 | P3 |  |  | NOC Operationalization |  | Principal Consultant meeting with NOC L3s |  | Critical | Closed |  |  | Meeting was done | [12 empty] | Network | Closed |  |  |  | Not related to delivery |  |  |  |  | 2025-09-19 | Artefacts not Required | Completed & Approved | Closed before june-2025 | Closed before june-2025
695 | M12 | MOM | 2023-04-03 |  |  |  | T&D Environment | T&D Environment | Test Lab Setup Equipments and Plan |  | NON-Critical | Open |  |  | 11-Oct-25: T Fiber requested to submit reference document Historically the L&T submitted proposal was not approved. Need to work for the final setup | [12 empty] | Applications | OPEN | [10 empty] | Open | Open | Open
696 | M120 | MOM | 2023-08-01 |  |  |  | Helpdesk | Handbook & SOPs | Duration of Call Measurement |  | Critical | open |  |  | 24-Sep-25: Artfcats to be uploaded 11-Sep-25: Feature Available, Shall be demonstrated | [12 empty] | Helpdesk (Contact Center) | Closed | [8 empty] | 2025-09-24 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\M120,129 | Completed & Approved | Closed before june-2025 | Closed after June
697 | M1200 | MOM | 2024-12-09 |  |  |  | NOC Operationalization |  | NOC 2.0 Mission : 30th April - All systems should be live. BSS KNOT(phase1) should be ready by 15th March OSS should be ready by Jan end NSO should be ready by mid-March |  | Critical | Open |  |  | 16-Oct-25: Covered in NOC go-live plan | [12 empty] | Network | OPEN | Duplicate | 16-Oct-25: Covered in NOC go-live plan | FALSE | [7 empty] | Open | Open | Open
698 | M1201 | MOM | 2024-12-09 |  |  |  | NOC Operationalization |  | L&T should recommend systems that should be procured for better efficiencies. A tendering process may be taken up as suitable by TFIBER. |  | Critical | Closed |  |  | 16-Oct-25: General guidelines | [12 empty] | Network | OPEN | CLOSED | 16-Oct-25: General guidelines | FALSE | [7 empty] | Open | Open | Open
699 | M1202 | MOM | 2024-12-09 |  |  |  | NOC Operationalization |  | Map of technology vis-à-vis OEM vis-à-vis issues |  | Critical | Closed |  |  | 23-Sep-25: Approved Artefacts to be Submitted | [12 empty] | Network | Closed | CLOSED | 23-Sep-25: Approved Artefacts to be Submitted | FALSE | [6 empty] | Artefacts Need to upload | Completed & Approved | Closed before june-2025 | Closed before june-2025
700 | M1203 | MOM | 2024-12-09 | P3 |  |  | NOC Operationalization |  | Passive Infra-Additional capacity needed in the NOC |  | Critical | Closed |  |  | TFiber team had to share this as per future plan. DC Passive deployed capacity is already as per RFP and AT completed | [12 empty] | Network | Closed |  |  |  | No clarity on requirment |  |  |  |  | 2025-09-19 | Artefacts not Required | Completed & Approved | Closed before june-2025 | Closed before june-2025
701 | M1204 | MOM | 2024-12-09 | P3 |  |  | NOC Operationalization |  | CCTV to be configured on Principal Consultant office and laptop. L&T to come up with solution |  | Critical | Closed |  |  | Discussed with TFiber later on, not needed | [12 empty] | Network | Closed |  |  |  | Not related to delivery |  |  |  |  | 2025-09-19 | Artefacts not Required | Completed & Approved | Closed before june-2025 | Closed before june-2025
702 | M1205 | MOM | 2024-12-09 |  |  |  | NOC Operationalization |  | Test labs and staging environment, currently project equipment's (routers, GPON, etc.) are being used |  | Critical | Closed |  |  | 23-Sep-25: NON Critical to be reviewed later | [12 empty] | Network | OPEN | OPEN | 23-Sep-25: NON Critical to be reviewed later | TRUE | [7 empty] | Open | Open | Open
703 | M1206 | MOM | 2024-12-09 |  |  |  | DC-IT | NOC Operationalization | HLD and LLD documents to be revised for DC Infra |  | NON-Critical | Open |  |  | Work in progress | [12 empty] | Network | OPEN | [10 empty] | Open | Open | Open
704 | M1207 | MOM | 2024-12-10 |  |  |  | BSS |  | One call with BSS and NSO SME to be done tomorrow morning |  | Critical | Closed | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
705 | M1208 | MOM | 2024-12-10 |  |  |  | OEM Related |  | Tejas : TR069 feature to be enabled for TFIBER network |  | NON-Critical | Open |  |  | 23-Sep-25: Approved shall be closed | [12 empty] | OEM Related Issues | Closed | CLOSED | 23-Sep-25: Approved shall be closed | FALSE | [5 empty] | 2025-09-23 | Artefacts not Required | Completed & Approved | Closed before june-2025 | Closed after June
706 | M1209 | MOM | 2024-12-10 |  |  |  | OEM Related |  | One resource from Tejas to be placed at TNOC for sorting out Tejas related issues |  | Critical | Closed |  |  | 23-Sep-25: Approved shall be closed | [12 empty] | OEM Related Issues | Closed | CLOSED | 23-Sep-25: Approved shall be closed | FALSE | [5 empty] | 2025-09-23 | Artefacts not Required | Completed & Approved | Closed before june-2025 | Closed before june-2025
707 | M121 | MOM | 2023-08-01 |  |  |  | Helpdesk | Handbook & SOPs | Exceptions in IVR User Response |  | Critical | open |  |  | 24-Sep-25: Approved and shall be closed | [12 empty] | Helpdesk (Contact Center) | Closed | [8 empty] | 2025-09-24 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\M121,170,99,726 | Completed & Approved | Closed before june-2025 | Closed after June
708 | M1210 | MOM | 2024-12-10 |  |  |  | NOC Operationalization |  | Tejas: Pending API to be given on priority |  | Critical | Closed | [15 empty] | Network | Closed | [8 empty] | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API | Completed & Approved | Closed before june-2025 | Closed before june-2025
709 | M1211 | MOM | 2024-12-10 |  |  |  | NOC Operationalization |  | Make one WhatsApp group for Tejas only (LTTS, TFIBER, Tejas) |  | Critical | Closed |  |  | 23-Sep-25: Approved shall be closed | [12 empty] | Network | Closed | CLOSED | 23-Sep-25: Approved shall be closed | FALSE | [5 empty] | 2025-09-23 | Artefacts not Required | Completed & Approved | Closed before june-2025 | Closed before june-2025
710 | M1212 | MOM | 2024-12-10 |  |  |  | NOC Operationalization |  | Suggested one format for SME tasks tracking Each SME to update that tracker putting all critical/major/minor tasks/issues listed in this. To be updated on daily basis with dates |  | Critical | Closed |  |  | 23-Sep-25: Approved shall be closed | [12 empty] | Network | Closed | CLOSED | 23-Sep-25: Approved shall be closed | FALSE | [5 empty] | 2025-09-23 | Artefacts not Required | Completed & Approved | Closed before june-2025 | Closed before june-2025
711 | M1213 | MOM | 2024-12-10 |  |  |  | NSO | Service provisioning | 27 services NSO licenses details to be shared with Principal Consultant |  | Critical | Closed |  |  | 29-dec-2025: Need discussion. Infra team owner | [7 empty] | On-Hold |  |  |  |  | Applications/Tools | OPEN |  |  |  |  | Need to check with Ravibhushan | [5 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
712 | M1214 | MOM | 2024-12-10 |  |  |  | NSO | Service provisioning | NSO VMs details for T&D to be shared with Principal Consultant along with issue details (what support needed from Cisco) |  | Critical | Closed |  |  | 29-dec-2025: Need discussion. Infra team owner | [7 empty] | Not Started |  |  |  |  | Applications/Tools | OPEN |  |  |  |  | Infra Team – Ravi - 16/03/2026:Will share VM data (only testing VMs). - 18/03/2026: Received VM information.(MAIL:FW: NSO Update : Internal discussion) | [5 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
713 | M1215 | MOM | 2024-12-10 |  |  |  | NSO | Service provisioning | Trial licenses will be given as stop gap arrangement for NSO T&D setup. VM details to be shared with Ravindra (MAC id , etc.) by LTTS |  | Critical | Closed |  |  | 29-12-2025:- Rajeev/L&T working on it | [12 empty] | Applications/Tools | OPEN |  |  |  |  | Rajeev | [5 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
714 | M1216 | MOM | 2024-12-10 |  |  |  | OEM Related | Cisco EPNM | License issue for EPNM and ISE to be resolved |  | Critical | Open |  |  | 16-Oct-25: Following with Cisco & Ingram | [12 empty] | OEM Related Issues | OPEN | OPEN | 16-Oct-25: Following with Cisco & Ingram | TRUE | [7 empty] | Open | Open | Open
715 | M1217 | MOM | 2024-12-10 |  |  |  | NOC Operationalization |  | One resource from Tejas to be placed at TNOC for sorting out Tejas related issues |  | Critical | Closed |  |  | 23-Sep-25: Approved shall be closed | [12 empty] | Network | Closed | CLOSED | 23-Sep-25: Approved shall be closed | FALSE | [5 empty] | 2025-09-23 | Artefacts not Required | Completed & Approved | Closed before june-2025 | Closed before june-2025
716 | M1218 | MOM | 2024-12-10 |  |  |  | NSO | Service provisioning | Agreed SOW for NSO to be shared |  | Critical | Closed |  |  | 29-dec-2025: Need discussion | [7 empty] | Not Started |  |  |  |  | Applications/Tools | OPEN |  |  |  |  | Need Clarity | [5 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
717 | M1219 | MOM | 2024-12-10 |  |  |  | NSO | Service provisioning | SOW for Cisco NSO - by when quotation will be closed by Cisco? Cisco to revert back with quotation timelines, probably tomorrow, also with TAT for implementation |  | Critical | Open |  |  | 29-dec-2025: Need discussion | [7 empty] | Not Started |  |  |  |  | Applications/Tools | OPEN |  |  |  |  | Need Clarity | [5 empty] | Open | Open | Open
718 | M122 | MOM | 2023-08-01 |  |  |  | Helpdesk | Handbook & SOPs | The unit of measurement is required for all Key Performance Indicator (KPI) parameters. |  | Critical | open |  |  | 24-Sep-25: Updated Document Shared 23-Aug-23 | [12 empty] | Helpdesk (Contact Center) | Closed | [8 empty] | 2025-09-24 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\M104,105,109,111,113,115,122,123,127,128,130,132,162 | Completed & Approved | Closed before june-2025 | Closed after June
719 | M1220 | MOM | 2024-12-10 |  |  |  | NOC Operationalization |  | Make one WhatsApp group for NSO only (LTTS, TFIBER, OEM) |  | Critical | Closed |  |  | 23-Sep-25: Approved shall be closed | [12 empty] | Network | Closed | CLOSED | 23-Sep-25: Approved shall be closed | FALSE | [5 empty] | 2025-09-23 | Artefacts not Required | Completed & Approved | Closed before june-2025 | Closed before june-2025
720 | M1221 | MOM | 2024-12-10 |  |  |  | NSO | Service provisioning | Dark Fiber as a service |  | Critical | Closed |  |  | 29-dec-2025: Need discussion,NSO owner ? | [7 empty] | On-Hold |  |  |  |  | Applications/Tools | OPEN |  |  |  |  | - 12/03/2026:Ritik Shared Dark Fiber file. - 16/03/2026: In NSO, work is in progress. | [5 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
721 | M1222 | MOM | 2024-12-10 |  |  |  | NSO | Service provisioning | List down all services which are needed for launch (As per LTTS understanding). During 2PM workshop tomorrow KNOT, Aravindham, Ashish, Ravindra Cisco, TFIBER will be there on call |  | Critical | Closed |  |  | 29-dec-2025: Need discussion | [7 empty] | Completed |  |  |  |  | Applications/Tools | OPEN |  |  |  |  | Need Clarity (SCCM Services list) | Pending |  | 17/03/2026 (Cross Check) |  |  | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
722 | M1223 | MOM | 2024-12-10 |  |  |  | OEM Related |  | SG350 switch EOS/EOL: GP all OK. Mandal/Zonal level have some discrepancy like less ports compared to current version or at least match to RFP |  | NON-Critical | Open |  |  | 16-Oct-25: SG350 replacement letter submitted, working on for other switches | [12 empty] | OEM Related Issues | OPEN | Duplicate | 16-Oct-25: SG350 replacement letter submitted, working on for other switches | FALSE | [7 empty] | Open | Open | Open
723 | M1224 | MOM | 2024-12-10 |  |  |  | NOC Operationalization |  | Make other WhatsApp group for Cisco other domains (apart from NSO). Make Ravindar Admin to add other Cisco team members. (LTTS except NSO, TF, Cisco) |  | Critical | Closed |  |  | 23-Sep-25: Approved shall be closed | [12 empty] | Network | Closed | CLOSED | 23-Sep-25: Approved shall be closed | FALSE | [5 empty] | 2025-09-23 | Artefacts not Required | Completed & Approved | Closed before june-2025 | Closed before june-2025
724 | M1225 | MOM | 2024-12-10 |  |  |  | OEM Related | Cisco | SG350 switch: EOSale/EOL/LDOHWS (Last date of HW support which is Oct2026. Till LDOHWS that RMA will be given with new CBS model. Post that support will stop. Mail request to be send to Cisco to extend support. |  | NON-Critical | Open |  |  | 16-Oct-25: SG350 replacement letter submitted, working on for other switches | [12 empty] | OEM Related Issues | OPEN | OPEN | 16-Oct-25: SG350 replacement letter submitted, working on for other switches | TRUE | [7 empty] | Open | Open | Open
725 | M1226 | MOM | 2024-12-10 |  |  |  | OEM Related |  | EPNM license upgraded, in smart account licenses are not working. Its issue with PKG-A only (PKG-B/C had procured separately 5.x so they don’t have this issue, while LTTS procured 2.x as per Ravindra) |  | Critical | Open |  |  | 16-Oct-25: Following with Cisco & Ingram | [12 empty] | OEM Related Issues | OPEN | Duplicate | 16-Oct-25: Following with Cisco & Ingram | FALSE | [7 empty] | Open | Open | Open
726 | M1227 | MOM | 2024-12-10 |  |  |  | BSS |  | Is our network integrated with Aadhar servers, GST? LTTS confirmed it is not integrated |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
727 | M1228 | MOM | 2024-12-10 |  |  |  | NOC Operationalization |  | Agreement status for all OEM to be shared |  | Critical | Closed |  |  | 23-Sep-25: Approved Artefacts to be Submitted | [12 empty] | Network | Closed | CLOSED | 23-Sep-25: Approved Artefacts to be Submitted | FALSE | [6 empty] | Artefacts Need to upload | Completed & Approved | Closed before june-2025 | Closed before june-2025
728 | M1229 | MOM | 2024-12-10 |  | OSS | OSS | OSS | BBNL | BBNL - API : is top priority. Each day update to be sent to Principal Consultant |  | Critical | Closed | [15 empty] | Applications/Tools | Closed | 0 | Completed With Artifacts | TRUE | [5 empty] | 2025-11-18 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\OSS\52 Artefcats_18112025 | Closed after 14-Nov-25 | Closed after 14-Nov-25 | Completed but Verification undrer Process
729 | M123 | MOM | 2023-08-01 |  |  |  | Helpdesk | Handbook & SOPs | Sample Methods for KPI Calculations |  | Critical | open |  |  | 24-Sep-25: Updated Document Shared 23-Aug-23 | [12 empty] | Helpdesk (Contact Center) | Closed | [8 empty] | 2025-09-24 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\M104,105,109,111,113,115,122,123,127,128,130,132,162 | Completed & Approved | Closed before june-2025 | Closed after June
730 | M1230 | MOM | 2024-12-10 |  | OSS | OSS | OSS | BBNL | Tomorrow 3 PM. will call Rupa Maan and Akhilesh Gupta Sir for BBNL API |  | Critical | Closed | [15 empty] | Applications/Tools | OPEN | 0 | No Artifact Required | TRUE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
731 | M1231 | MOM | 2024-12-10 |  |  |  | OEM Related |  | Principal Consultant Room Dashboard - Excel sheet sent, to discuss and finetune. Discussed. Need this report through OSS, to be added in HPE/OT scope once they are onboarded - discuss jointly with TFIBER along with OEM |  | Critical | Open |  |  | 16-Oct-25: Dashboard created and shown | [12 empty] | OEM Related Issues | OPEN | CLOSED | 16-Oct-25: Dashboard created and shown | FALSE | [7 empty] | Open | Open | Open
732 | M1232 | MOM | 2024-12-10 |  |  |  | NOC Operationalization |  | All inhouse automation : LLD to be made by SME and handover to Ops & TFIBER team |  | NON-Critical | Open |  |  | 16-Oct-25: LLDs are submitted for inhouse solution | [12 empty] | Network | OPEN | CLOSED | 16-Oct-25: LLDs are submitted for inhouse solution | FALSE | [7 empty] | Open | Open | Open
733 | M1233 | MOM | 2024-12-10 |  |  |  | OEM Related |  | OSS out of Scope: 1. Service Topology 2. Retail Services (5Mn), 3. Services & Service KPI Monitoring. As per SOR this is not there. This is for Principal Consultant information |  | Critical | Closed |  |  | 16-Oct-25: Non scope items informed to T-Fiber | [12 empty] | OEM Related Issues | OPEN | OPEN | 16-Oct-25: Non scope items informed to T-Fiber | TRUE | [7 empty] | Open | Open | Open
734 | M1234 | MOM | 2024-12-10 |  |  |  | OEM Related |  | Share all OSS documents (RFP points, LLD, FRS, etc.) |  | Critical | Closed |  |  | 23-Sep-25: Approved shall be closed | [12 empty] | OEM Related Issues | Closed | CLOSED | 23-Sep-25: Approved shall be closed | FALSE | [5 empty] | 2025-09-23 | Artefacts not Required | Completed & Approved | Closed before june-2025 | Closed before june-2025
735 | M1235 | MOM | 2024-12-10 |  |  |  | NOC Operationalization |  | Make P1/P2/P3 list for all pending tasks for all domain P1: 25% P2 : 30% P3 : 45% And then list of some additional ask if needed like new HW or software required. |  | Critical | Closed |  |  | 23-Sep-25: Approved shall be closed | [12 empty] | Network | Closed | CLOSED | 23-Sep-25: Approved shall be closed | FALSE | [5 empty] | 2025-09-23 | Artefacts not Required | Completed & Approved | Closed before june-2025 | Closed before june-2025
736 | M1236 | MOM | 2024-12-10 |  | OSS | OSS | OSS | BBNL | Manoj: Complete BBNL ask tasks will be completed by 12 Dec24 (only GP and Block Node status API pending). Sanjay: Uptime gap ~7% to be addressed. For this, HPE support needed. Then only we can go to BBNL for closure. Alarm re-synchronization issue - need HPE support. Interim solution implemented (1 Hr). Same for Inventory. |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | 0 | No Artifact Required | TRUE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
737 | M1237 | MOM | 2024-12-10 |  |  |  | OEM Related |  | Bottomline for OSS: Engagement with HPE and OT to start to get all OSS open/pending tasks done |  | Critical | Open |  |  | 23-Sep-25: Approved shall be closed | [12 empty] | OEM Related Issues | Closed | CLOSED | 23-Sep-25: Approved shall be closed | FALSE | [5 empty] | 2025-09-23 | Artefacts not Required | Completed & Approved | Closed before june-2025 | Closed after June
738 | M1238 | MOM | 2024-12-10 |  |  |  | OEM Related | All OEM's | Priority engagement with HPE/OT/Cisco/Aleppo needed to meet Apr25 target. Current payment/cash flow issues hindering this right now |  | Critical | Open |  |  | 16-Oct-25: HPE and OT onboarded, Cisco TAC support available | [12 empty] | OEM Related Issues | OPEN | Duplicate | 16-Oct-25: HPE and OT onboarded, Cisco TAC support available | FALSE | [7 empty] | Open | Open | Open
739 | M1239 | MOM | 2024-12-10 |  |  |  | NOC Operationalization |  | Pending AT for all Application and DC systems to be shared by tomorrow |  | Critical | Open |  |  | 16-Oct-25: Covered in all Domains ATP plans | [12 empty] | Network | OPEN | Duplicate | 16-Oct-25: Covered in all Domains ATP plans | FALSE | [7 empty] | Open | Open | Open
740 | M124 | MOM | 2023-08-01 |  |  |  | Helpdesk | Handbook & SOPs | Inquiry into how Customer Satisfaction (CSAT) is measured and whether there is a mechanism for transactional feedback. |  | Critical | Open | [15 empty] | Helpdesk (Contact Center) | OPEN | [10 empty] | Open | Open | Open
741 | M1240 | MOM | 2024-12-10 | P3 |  |  | NOC Operationalization |  | Major nodes/links utilization report to be shared (Deployed V/s Utilized) by tomorrow |  | Critical | Closed |  |  | Report shared | [12 empty] | Network | Closed |  |  |  | Covered in OSS |  |  |  |  | 2025-09-19 | Artefacts not Required | Completed & Approved | Closed before june-2025 | Closed before june-2025
742 | M1241 | MOM | 2024-12-10 |  |  |  | NOC Operationalization |  | Did anyone visited DR Ctrl-S location at Mumbai? No, except of earlier L&T Delivery Head Principal Consultant: Will plan visit to this location in future |  | Critical | Open |  |  | 16-Oct-25: Visit will be arranged | [12 empty] | Network | OPEN | OPEN | 16-Oct-25: Visit will be arranged | TRUE | [7 empty] | Open | Open | Open
743 | M1242 | MOM | 2024-12-10 | P3 |  |  | NOC Operationalization |  | Send Cluster wise utilization report for DC infra |  | Critical | Closed |  |  | Report shared | [12 empty] | Network | Closed |  |  |  | Daily oprational task |  |  |  |  | 2025-09-19 | Artefacts not Required | Completed & Approved | Closed before june-2025 | Closed before june-2025
744 | M1243 | MOM | 2024-12-10 | P3 |  |  | NOC Operationalization |  | Login in OSS, BSS, ticketing, NSO and to share all links with Principal Consultant |  | Critical | Closed |  |  | Login ID made and link shared | [12 empty] | Network | Closed |  |  |  | Not related to delivery |  |  |  |  | 2025-09-19 | Artefacts not Required | Completed & Approved | Closed before june-2025 | Closed before june-2025
745 | M1244 | MOM | 2024-12-10 |  |  |  | OEM Related | Neox | Neox team to be called for meeting |  | Critical | Open |  |  | 16-Oct-25: Teams meeting arranged | [12 empty] | OEM Related Issues | OPEN | CLOSED | 16-Oct-25: Teams meeting arranged | FALSE | [7 empty] | Open | Open | Open
746 | M1245 | MOM | 2024-12-10 | P3 |  |  | NOC Operationalization |  | Access to NAS server to be provided to Principal Consultant to get access to HLD / LLD / reports. |  | NON-Critical | Closed |  |  | Access given | [12 empty] | Network | Closed |  |  |  | Not related to delivery |  |  |  |  | 2025-09-19 | Artefacts not Required | Completed & Approved | Closed before june-2025 | Closed before june-2025
747 | M1246 | MOM | 2024-12-10 | P3 |  |  | NOC Operationalization |  | Dashboards samples were shared by the Principal Consultant, a brief discussions carried on how critical data to be presented |  | Critical | Closed |  |  | Report shared as per Principal Consultant review | [12 empty] | Network | Closed |  |  |  | Covered in OSS |  |  |  |  | 2025-09-19 | Artefacts not Required | Completed & Approved | Closed before june-2025 | Closed before june-2025
748 | M1247 | MOM | 2024-12-11 |  |  |  | IP/MPLS | NOC Operationalization | Actual implemented IP MPLS ring details needed. |  | Critical | Closed |  |  | RIng details shared | [12 empty] | IPMPLS | Closed | [8 empty] | After Jun-25 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\Link topology of PKG A B C updated as on 05082025.xlsx | Completed & Approved | Closed before june-2025 | Closed before june-2025
749 | M1248 | MOM | 2024-12-11 |  |  |  | NOC Operationalization |  | Share Test Setup proposal which was sent to TFIBER by LTTS. |  | Critical | Open |  |  | 23-Sep-25: Approved shall be closed | [12 empty] | Network | Closed | CLOSED | 23-Sep-25: Approved shall be closed | FALSE | [5 empty] | 2025-09-23 | Artefacts not Required | Completed & Approved | Closed before june-2025 | Closed after June
750 | M1249 | MOM | 2024-12-11 | P3 |  |  | NOC Operationalization |  | What is total scope of the project V/S implementation. And then total equipment procured Vs installed Vs Available in field and at DC |  | Critical | Closed |  |  | Report shared | [12 empty] | Network | Closed |  |  |  | Covered in OSS |  |  |  |  | 2025-09-19 | Artefacts not Required | Completed & Approved | Closed before june-2025 | Closed before june-2025
751 | M125 | MOM | 2023-08-01 |  |  |  | Helpdesk | Handbook & SOPs | Expression of First Call Resolution (FCR) as a percentage |  | Critical | Open | [15 empty] | Helpdesk (Contact Center) | OPEN | [10 empty] | Open | Open | Open
752 | M1250 | MOM | 2024-12-11 |  |  |  | OEM Related | HPSM | In Asset Manager deployed inventory status is available. WH equipment data also available for PKG-B & C. |  | Critical | Closed |  |  | 16-Oct-25: WH updated for all Packages | [12 empty] | OEM Related Issues | OPEN | CLOSED | 16-Oct-25: WH updated for all Packages | FALSE | [7 empty] | Open | Open | Open
753 | M1251 | MOM | 2024-12-11 | P3 |  |  | NOC Operationalization |  | Tomorrow Field Project team discussion is scheduled (Different Packages , Different Slots, Need OSS and NOC team) |  | Critical | Closed |  |  | Meetin conducted | [12 empty] | Network | Closed |  |  |  | Not related to delivery |  |  |  |  | 2025-09-19 | Artefacts not Required | Completed & Approved | Closed before june-2025 | Closed before june-2025
754 | M1252 | MOM | 2024-12-11 | P3 |  |  | NOC Operationalization |  | Inventory, down, nodes/links with aging, team deployed in field to be shown to them |  | Critical | Closed |  |  | Data shown especially DWDM, Mandal, GP and UPS | [12 empty] | Network | Closed |  |  |  | Covered in OSS |  |  |  |  | 2025-09-19 | Artefacts not Required | Completed & Approved | Closed before june-2025 | Closed before june-2025
755 | M1253 | MOM | 2024-12-11 |  | OSS | OSS | OSS | BBNL | Make a Focused WhatsApp group for BBNL |  | Critical | Closed | [15 empty] | Applications/Tools | OPEN | 0 | No Artifact Required | TRUE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
756 | M1254 | MOM | 2024-12-11 |  |  |  | IP/MPLS | NOC Operationalization | Holistic IP planning for all service type to be done based on discussion in near future |  | Critical | Closed | [15 empty] | IPMPLS | Closed | [8 empty] | After Jun-25 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\TFiber IP Plan Details.zip | Completed & Approved | Closed before june-2025 | Closed before june-2025
757 | M1255 | MOM | 2024-12-11 |  |  |  | NOC Operationalization |  | Official mail to IPNIC from TFIBER MD office for additional IPs to be sent |  | Critical | Open | [15 empty] | Network | OPEN | [10 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
758 | M1256 | MOM | 2024-12-11 |  |  |  | NOC Operationalization |  | For all equipment's, need confirmation mail/letter from all OEMs for IPv4 and IPv6 dual stack implementation compliance |  | Critical | Open |  |  | 16-Oct-25: OEM confirmation arranged | [12 empty] | Network | OPEN | CLOSED | 16-Oct-25: OEM confirmation arranged | FALSE | [7 empty] | Open | Open | Open
759 | M1257 | MOM | 2024-12-11 |  |  |  | NOC Operationalization |  | A consistent process of design review to acceptance of artefact is missing. Requested Principal Consultant to agree process to set a design authority |  | Critical | Closed | [15 empty] | Network | OPEN | [10 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
760 | M1258 | MOM | 2024-12-11 |  |  |  | BSS |  | Capture Aadhar integration need in our requirement doc / soln/SOW for BSS/NSO. |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
761 | M1259 | MOM | 2024-12-11 |  |  |  | NOC Operationalization |  | What BSS & NSO does? Can you make flow of processes/data/provisioning/delivery etc. across BSS, NSO, OSS, EMS, Billing, Helpdesk |  | Critical | Closed |  |  | 16-Oct-25: Covered system integrations | [12 empty] | Network | OPEN | Duplicate | 16-Oct-25: Covered system integrations | FALSE | [7 empty] | Open | Open | Open
762 | M126 | MOM | 2023-08-01 |  |  |  | Helpdesk | Handbook & SOPs | Review of Agent Utilization Formula |  | Critical | open |  |  | 25-Sep-25: Artefacts to be uploaded | [12 empty] | Helpdesk (Contact Center) | Closed | [8 empty] | 2025-09-24 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\M117,126,728 | Completed & Approved | Closed before june-2025 | Closed after June
763 | M1260 | MOM | 2024-12-11 |  |  |  | NOC Operationalization |  | What all services are automated and what is not automated list to be provided |  | Critical | Closed |  |  | 16-Oct-25: Covered in BSS/NSO | [12 empty] | Network | OPEN | Duplicate | 16-Oct-25: Covered in BSS/NSO | FALSE | [7 empty] | Open | Open | Open
764 | M1261 | MOM | 2024-12-11 |  |  |  | BSS |  | Business flow discussed like existing telecom operator customer mgmt. case study . BSS Workout sheet made by Principal Consultant will be sent to you, and will discuss in detailed along with KNOT, TFIBER, TFIBER business/finance team when Aravindhan comes over to HYD at TFIBER office |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
765 | M1262 | MOM | 2024-12-13 | P3 |  |  | NOC Operationalization |  | Make Node Availability as per today's format as suggested by Principal Consultant |  | Critical | Closed |  |  | Report shared as per Principal Consultant review | [12 empty] | Network | Closed |  |  |  | Covered in OSS |  |  |  |  | 2025-09-19 | Artefacts not Required | Completed & Approved | Closed before june-2025 | Closed before june-2025
766 | M1263 | MOM | 2024-12-13 | P3 |  |  | NOC Operationalization |  | All nodes/applications AMC details to be shared |  | Critical | Closed |  |  | AMC status shared | [12 empty] | Network | Closed |  |  |  | Infrastructure |  |  |  |  | 2025-09-24 | \\172.28.9.23\tnocreports\AMC | Completed & Approved | Closed before june-2025 | Closed before june-2025
767 | M1264 | MOM | 2024-12-31 | P3 |  |  | NOC Operationalization |  | Network alarms to be reduced, currently 90K alarms |  | Critical | Closed |  |  | Report shared. Field related alarms exists as per field anamolies | [12 empty] | Network | Closed |  |  |  | Covered in OSS |  |  |  |  | 2025-09-19 | Artefacts not Required | Completed & Approved | Closed before june-2025 | Closed before june-2025
768 | M1265 | MOM | 2025-02-14 |  |  |  | NOC Operationalization |  | Go-live plan discussion and action items to be tracked and closed |  | Critical | Closed |  |  | 16-Oct-25: Covered in NOC go-live plan | [12 empty] | Network | OPEN | Duplicate | 16-Oct-25: Covered in NOC go-live plan | FALSE | [7 empty] | Open | Open | Open
769 | M1266 | MOM | 2025-02-14 | P3 |  |  | NOC Operationalization |  | One-to-one meeting with complete TNOC resources to be completed |  | Critical | Open |  |  | Scheduled as per Principal Consultant availability | [12 empty] | Network | Closed |  |  |  | Not related to delivery |  |  |  |  | 2025-09-19 | Artefacts not Required | Completed & Approved | Closed before june-2025 | Closed after June
770 | M1267 | MOM | 2025-02-14 |  |  |  | OEM Related | Nokia | All APIs to be taken from Nokia |  | Critical | Open |  |  | 23-Sep-25: Approved Artefacts to be Submitted | [12 empty] | OEM Related Issues | Closed | CLOSED | 23-Sep-25: Approved Artefacts to be Submitted | FALSE | [6 empty] | Artefacts Need to upload | Completed & Approved | Closed before june-2025 | Closed after June
771 | M1268 | MOM | 2025-02-14 |  |  |  | NOC Operationalization |  | Undertaking from L&T is needed for all In-House software |  | Critical | Open |  |  | 23-Sep-25: Approved Artefacts to be Submitted | [12 empty] | Network | Closed | CLOSED | 23-Sep-25: Approved Artefacts to be Submitted | FALSE | [6 empty] | Artefacts Need to upload | Completed & Approved | Closed before june-2025 | Closed after June
772 | M1269 | MOM | 2025-02-14 | P3 |  |  | NOC Operationalization |  | PKG-A WH inventory data to be uploaded in Asset Manager |  | Critical | Open |  |  | Done | [12 empty] | Network | Closed |  |  |  | Covered in OSS |  |  |  |  | 2025-09-19 | Artefacts not Required | Completed & Approved | Closed before june-2025 | Closed after June
773 | M127 | MOM | 2023-08-01 |  |  |  | Helpdesk | Handbook & SOPs | Customer-Specific SLA Flows |  | Critical | open |  |  | 24-Sep-25: Updated Document Shared 23-Aug-23 | [12 empty] | Helpdesk (Contact Center) | Closed | [8 empty] | 2025-09-24 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\M104,105,109,111,113,115,122,123,127,128,130,132,162 | Completed & Approved | Closed before june-2025 | Closed after June
774 | M1270 | MOM | 2025-02-14 |  |  |  | Helpdesk | Handbook & SOPs | Helpdesk IVR: after selecting any number (apart from configured 1/2/3), call is getting disconnected. This need to be corrected |  | Critical | open |  |  | 24-Sep-25: Artefacts to be uploaded | [12 empty] | Helpdesk (Contact Center) | Closed | [8 empty] | 2025-09-24 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\M1270 | Completed & Approved | Closed before june-2025 | Closed after June
775 | M1271 | MOM | 2025-04-03 |  |  |  | NOC Operationalization |  | One slide to be presented showing status of work capturing: a. Status (last week actions), b) Issues, c) Achievements d) Plan for Next week. Only major points to be mentioned |  | Critical | Closed |  |  | 23-Sep-25: Approved shall be closed | [12 empty] | Network | Closed | CLOSED | 23-Sep-25: Approved shall be closed | FALSE | [5 empty] | 2025-09-23 | Artefacts not Required | Completed & Approved | Closed before june-2025 | Closed before june-2025
776 | M1272 | MOM | 2025-04-03 |  |  |  | NOC Operationalization |  | Review slides to capture: 1. Tech/SME/OEM wise update 2. Domain Status - one slide for each domain 3. HLD/LLD/FAT update 4. Detailed HLD/LLD/FAT open points list: 20-30 points 5. Other important points (NOC also like DWDM losses, infra issues at ZOnal/mandal, etc.) 6. 742 Tracker, MoM update |  | NON-Critical | Closed |  |  | 23-Sep-25: Approved shall be closed | [12 empty] | Network | Closed | CLOSED | 23-Sep-25: Approved shall be closed | FALSE | [5 empty] | 2025-09-23 | Artefacts not Required | Completed & Approved | Closed before june-2025 | Closed before june-2025
777 | M1273 | MOM | 2025-04-03 |  |  |  | NOC Operationalization |  | Aggressive followups with TPA to be done by L&T SMEs. Post 2-3 followups, then come to Principal Consultant for support alongwith TPA |  | Critical | Open |  |  | 23-Sep-25: Approved shall be closed | [12 empty] | Network | Closed | CLOSED | 23-Sep-25: Approved shall be closed | FALSE | [5 empty] | 2025-09-23 | Artefacts not Required | Completed & Approved | Closed before june-2025 | Closed after June
778 | M1274 | MOM | 2025-04-03 |  |  |  | GIS | User Experience | GIS: Make a PPT for operationalisation of GIS Ops & updation. This will be shared to PKG-B & C |  | Critical | Open | Gtech | [14 empty] | Applications/Tools | OPEN | [10 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
779 | M1275 | MOM | 2025-04-03 |  |  |  | NOC Operationalization |  | Incorporate MoM points in HLD/LLD documents |  | NON-Critical | Closed |  |  | 16-Oct-25: Covered in respective HLD/LLD | [12 empty] | Network | OPEN | CLOSED | 16-Oct-25: Covered in respective HLD/LLD | FALSE | [7 empty] | Open | Open | Open
780 | M1276 | MOM | 2025-04-03 |  |  |  | NOC Operationalization |  | Make proper justification for A&O for Tfiber MD approval. Shpw project plan. Show previous delivered systems like IPDR, BBNL solution which his made solely by L&T inhouse team. Include Support system/mechanism to Tfiber during 7 years and post L&T exit project |  | Critical | Closed |  |  | 23-Sep-25: Approved Artefacts to be Submitted | [12 empty] | Network | Closed | CLOSED | 23-Sep-25: Approved Artefacts to be Submitted | FALSE | [6 empty] | Artefacts Need to upload | Completed & Approved | Closed before june-2025 | Closed before june-2025
781 | M1277 | MOM | 2025-04-03 |  |  |  | NSO | Service provisioning | GI-BB Demo to be shown to Principal Consultant on 15th April2025 |  | Critical | Closed |  |  | 29-dec-2025: Need discussion.E2E demo provide | [7 empty] | Completed |  |  |  |  | Applications/Tools | OPEN |  |  |  |  | Need Clarity (Demo done can we attach committed order screenshot) | Pending |  | 17/03/2026 (Cross Check) |  |  | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
782 | M1278 | MOM | 2025-04-03 |  |  |  | NOC Operationalization |  | Every Thursday 11 AM review meeting to be planned with Principal Consultant on NOC project |  | Critical | Closed |  |  | 23-Sep-25: Approved shall be closed | [12 empty] | Network | Closed | CLOSED | 23-Sep-25: Approved shall be closed | FALSE | [5 empty] | 2025-09-23 | Artefacts not Required | Completed & Approved | Closed before june-2025 | Closed before june-2025
783 | M128 | MOM | 2023-08-01 |  |  |  | Helpdesk | Handbook & SOPs | Exhaustive List of General Enquiries |  | Critical | open |  |  | 24-Sep-25: Updated Document Shared 23-Aug-23 | [12 empty] | Helpdesk (Contact Center) | Closed | [8 empty] | 2025-09-24 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\M104,105,109,111,113,115,122,123,127,128,130,132,162 | Completed & Approved | Closed before june-2025 | Closed after June
784 | M129 | MOM | 2023-08-01 |  |  |  | Helpdesk | Handbook & SOPs | DoT KPIs Coverage in KPI Section |  | Critical | open |  |  | 24-Sep-25: Artfcats to be uploaded 11-Sep-25: Feature Available, Shall be demonstrated | [12 empty] | Helpdesk (Contact Center) | Closed | [8 empty] | 2025-09-24 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\M120,129 | Completed & Approved | Closed before june-2025 | Closed after June
785 | M13 | MOM | 2023-04-03 |  | OSS | OSS | OSS | Functional AT Plan | Quality test report submission for DWDM & IPMPLS each zonal path. |  | Critical | Open | OSS Dashboards | [14 empty] | Applications/Tools | OPEN | 0 | Not Relevant To OSS | TRUE | [7 empty] | Open | Open | Open
786 | M130 | MOM | 2023-08-01 |  |  |  | Helpdesk | Handbook & SOPs | FAQs Based on Case Studies |  | Critical | open |  |  | 24-Sep-25: Updated Document Shared 23-Aug-23 | [12 empty] | Helpdesk (Contact Center) | Closed | [8 empty] | 2025-09-24 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\M104,105,109,111,113,115,122,123,127,128,130,132,162 | Completed & Approved | Closed before june-2025 | Closed after June
787 | M131 | MOM | 2023-08-01 |  |  |  | Helpdesk | Handbook & SOPs | Request to differentiate between registered users and registered numbers using examples. |  | Critical | Open |  |  | 01-Dec-25:Duplicate-M112 11-Sep-25: BSS Integration to be completed | [12 empty] | Helpdesk (Contact Center) | OPEN | [10 empty] | Open | Open | Open
788 | M132 | MOM | 2023-08-01 |  |  |  | Helpdesk | Handbook & SOPs | the roles and responsibilities of NOC and Field Personnel be separate according to the RASCI matrix |  | Critical | open |  |  | 24-Sep-25: Updated Document Shared 23-Aug-23 | [12 empty] | Helpdesk (Contact Center) | Closed | [8 empty] | 2025-09-24 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\M104,105,109,111,113,115,122,123,127,128,130,132,162 | Completed & Approved | Closed before june-2025 | Closed after June
789 | M133 | MOM | 2023-08-01 |  |  |  | Helpdesk | Handbook & SOPs | Inclusion of Master and Child Service Level Agreement (SLA) monitoring; if any SLA is breached, a proper escalation matrix should be available for speedy escalation and resolution of the issue. |  | Critical | open | [15 empty] | Helpdesk (Contact Center) | OPEN | [10 empty] | Open | Open | Open
790 | M134 | MOM | 2023-08-01 |  |  |  | Helpdesk | Training | Training for Call Transferring |  | Critical | open |  |  | 24-Sep-25: Trianing completed, Artefacts to be uploaded | [12 empty] | Helpdesk (Contact Center) | Closed | [8 empty] | 2025-09-24 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\M114,722,134 | Completed & Approved | Closed before june-2025 | Closed after June
791 | M135 | MOM | 2023-08-01 |  |  |  | Helpdesk | User Experience | Proactive Intimation of Planned Downtime |  | Critical | open |  |  | 01-Dec-25: Currently its manual activity, once integration with BSS, OSS completed this can be achieved 24-Sep-25: Part of Neox integration with BSS/OSS | [12 empty] | Helpdesk (Contact Center) | OPEN | [10 empty] | Open | Open | Open
792 | M136 | MOM | 2023-08-23 |  |  |  | BSS | Notification Template | comprehensive list of event notification scenarios and implementation plan. |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
793 | M137 | MOM | 2023-08-23 |  |  |  | BSS | Improvement | Complete User Group creation |  | Critical | Closed | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
794 | M138 | MOM | 2023-08-23 |  |  |  | BSS | Improvement | customizable columns |  | Critical | Closed | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
795 | M139 | MOM | 2023-08-23 |  |  |  | BSS | Dashboards | Summary of Leads |  | NON-Critical | Closed | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
796 | M14 | MOM | 2023-04-16 |  | OSS | OSS | OSS | Full NOC Readiness | Secretary, DoT enquired to show the MTTR through against individual TT in the OSS |  | Critical | Open | OSS Dashboards | [14 empty] | Applications/Tools | OPEN | need to check | Completed | FALSE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
797 | M140 | MOM | 2023-08-23 |  |  |  | BSS | Improvement | Advance Search options |  | NON-Critical | Open |  |  | It is available OOB | [12 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
798 | M141 | MOM | 2023-08-23 |  |  |  | BSS | Resource Related | Structure & Composition of Service Delivery group |  | NON-Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
799 | M142 | MOM | 2023-08-23 |  |  |  | BSS | Resource Related | Roles & Responsibility of Service Delivery group |  | NON-Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
800 | M143 | MOM | 2023-08-23 |  |  |  | BSS | User Experience | Notification with status changes from Opportunity - RFO - RFS – Order |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
801 | M144 | MOM | 2023-08-23 |  |  |  | BSS | Handbook & SOPs | Process for Data Integrity of Bulk upload |  | NON-Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
802 | M145 | MOM | 2023-08-23 |  | OSS | OSS | OSS | Manual Feasibility Plan | Plan for manual feasibility in the OSS |  | NON-Critical | Open | [15 empty] | Applications/Tools | OPEN | need to check | Completed | FALSE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
803 | M146 | MOM | 2023-08-23 |  |  |  | BSS | Dashboards | Summary before Feasibility Result |  | NON-Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
804 | M147 | MOM | 2023-08-23 |  |  |  | BSS | Manual Feasibility Plan | Order Fulfilment - Exception Scenarios |  | NON-Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
805 | M148 | MOM | 2023-08-23 |  |  |  | BSS | Action points | Ensure that site editing is restricted |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
806 | M149 | MOM | 2023-08-23 |  |  |  | BSS | Data Upload | Entire network POI/ PoP status, including 12751 GPs, 1 NOC, all zones, districts & Mandal nodes, is available in the CRM database |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
807 | M15 | MOM | 2023-04-16 |  | OSS | OSS | OSS | Full NOC Readiness | Secretary, DoT advised to show more KPIs, Video wall extension is required |  | Critical | Open | OSS Dashboards | [14 empty] | Applications/Tools | OPEN | All power BI dashboards, SM MTTR Dashboards | Completed | FALSE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
808 | M150 | MOM | 2023-08-23 |  |  |  | BSS | CSP User Experience | Telugu Subtitles in CSP |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
809 | M151 | MOM | 2023-08-23 |  |  |  | BSS | CSP User Experience | Google Location Pickup |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
810 | M152 | MOM | 2023-08-23 |  |  |  | BSS | CSP User Experience | Lat/Long coordinates and LGD codes should be removed from the search bar. |  | Critical | Closed | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
811 | M153 | MOM | 2023-08-23 |  |  |  | BSS | CSP User Experience | Check Residential" should be changed with a more appropriate term. |  | NON-Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
812 | M154 | MOM | 2023-08-23 |  |  |  | BSS | CSP User Experience | Introduce a "Thank You" page after a lead is submitted, displaying the lead number. This lead number could be useful for Helpdesk also. |  | NON-Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
813 | M155 | MOM | 2023-08-23 |  |  |  | BSS | CSP User Experience | The term "External" should be replaced with "Internal." |  | NON-Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
814 | M156 | MOM | 2023-08-23 |  |  |  | BSS | CSP User Experience | "Value-Add Partners" Tab |  | NON-Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
815 | M157 | MOM | 2023-08-23 |  |  |  | BSS | CSP User Experience | Landing Page Content |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
816 | M158 | MOM | 2023-08-23 |  |  |  | BSS | CSP User Experience | The term "Last Miles" should be changed to "Partners. |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
817 | M159 | MOM | 2023-08-23 |  |  |  | BSS | CSP User Experience | The "Government/Cell Tower/Enterprise" tab should have a dropdown for various services & information. |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
818 | M16 | MOM | 2023-04-19 |  |  |  | GIS | Functional AT Plan | Loading Sample Data and Internal Quality Test Report Submission |  | NON-Critical | Open | OSS Dashboards | [14 empty] | Applications/Tools | OPEN | [10 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
819 | M160 | MOM | 2023-08-23 |  |  |  | BSS | CSP User Experience | Chatbot Feature |  | NON-Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
820 | M161 | MOM | 2023-08-23 |  |  |  | BSS | CSP User Experience | Leads Summary for B2B Partner |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
821 | M162 | MOM | 2023-08-31 |  |  |  | BSS | User Experience | CRM should be in IST Times |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
822 | M163 | MOM | 2023-08-31 |  |  |  | BSS | User Experience | User Group training for administrator to Add/Modify the user access in CSP and CRM |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
823 | M164 | MOM | 2023-08-31 |  |  |  | BSS | Billing Related | SSL Certificate implementation |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
824 | M165 | MOM | 2023-08-31 |  |  |  | BSS | User Experience | Corporate Number for WhatsApp |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
825 | M166 | MOM | 2023-09-08 |  |  |  | BSS | Handbook & SOPs | Order Fulfilment Process |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
826 | M167 | MOM | 2023-09-08 |  |  |  | BSS | Handbook & SOPs | Service Delivery Process |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
827 | M168 | MOM | 2023-09-08 |  |  |  | BSS | Handbook & SOPs | Service Delivery Team Resource and responsibilities & relationship with other packages |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
828 | M169 | MOM | 2023-09-08 |  |  |  | BSS | Handbook & SOPs | Clearly define user system mapping with specific process steps with documentation for clarity |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
829 | M17 | MOM | 2023-05-18 |  |  |  | GIS | Functional AT Plan | Basic GIS Tool UAT for TPA |  | Critical | Open | OSS Dashboards |  | 15-Nov-25: The ATP was submitted, discussed with the TPA, and all feedback was incorporated. The revised ATP has also been sent | [12 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
830 | M170 | MOM | 2023-09-08 |  |  |  | Helpdesk | User Experience | Change in IVRS Welcome Message |  | Critical | open |  |  | 24-Sep-25: Approved and shall be closed 11-Sep-25: Changed and operational Now | [12 empty] | Helpdesk (Contact Center) | Closed | [8 empty] | 2025-09-24 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\M121,170,99,726 | Completed & Approved | Closed before june-2025 | Closed after June
831 | M171 | MOM | 2023-09-08 |  |  |  | Helpdesk | Resource Related | Other package involvement |  | Critical | open |  |  | 24-Sep-25: Artefacts to be submitted 11-Sep-25: Clarified as its only L&T Manpower | [12 empty] | Helpdesk (Contact Center) | Closed | [8 empty] | 2025-09-24 | Artefacts Need to upload | Completed & Approved | Closed before june-2025 | Closed after June
832 | M172 | MOM | 2023-09-12 | P3 |  |  | NOC Operationalization | Handbook & SOPs | SOPs Submission |  | Critical | Closed |  |  | Agreed SOPs are submitted and agreed with TFiber | [12 empty] | Network | Closed |  |  |  | Documentation |  |  |  |  | 2025-09-24 | \\172.28.9.23\tnocreports\Approved Process and SOP_ T Fiber\SOP | Completed & Approved | Closed before june-2025 | Closed before june-2025
833 | M173 | MOM | 2023-09-12 |  |  |  | NOC Operationalization | OEM's Details | Submit details on OEM alignment, warranty, AMC, and engagement status for go-live and post-go-live phases, location-wise & application-wise, to Director-Contracts, T-Fiber |  | Critical | Open | [15 empty] | Network | OPEN | [10 empty] | Open | Open | Open
834 | M174 | MOM | 2023-09-12 |  |  |  | Helpdesk | Improvement | Streamlining of Helpdesk and Ticketing system |  | Critical | open |  |  | 11-Sep-25: Same has been Submitted, its ongoing activity | [12 empty] | Helpdesk (Contact Center) | OPEN | [10 empty] | Open | Open | Open
835 | M175 | MOM | 2023-09-12 | P3 |  |  | NOC Operationalization | Dashboards | Dashboards for each element of the Video Wall, specifying manual or automatic clarity |  | Critical | Completed |  |  | Curently Video wall is displaying dashboards as per agreement with TFiber | [12 empty] | Network | Closed |  |  |  | Covered in OSS |  |  |  |  | 2025-09-19 | Artefacts not Required | Completed & Approved | Closed before june-2025 | Closed after June
836 | M176 | MOM | 2023-09-12 | P3 |  |  | NOC Operationalization | Resource Related | T-NOC Resource details and deployment with Roles and Responsibilities |  | Critical | Completed |  |  | TNOC resource is deployed as per RFP. Manpower report is shared on weekly basis. | [12 empty] | Network | Closed |  |  |  | Not related to delivery |  |  |  |  | 2025-09-24 | \\172.28.9.23\tnocreports\TNOC Manpower_CVs\NOC Resources Details & Roles | Completed & Approved | Closed before june-2025 | Closed after June
837 | M177 | MOM | 2023-09-12 |  |  |  | Security & Regulatory Compliance | Patch update | Engagements with vendors for Patch Delivery and Testing |  | Critical | Open |  |  | 28-Nov-25: To discuss with mr Sanjay to get clarifications on the points | [12 empty] | Security | OPEN | [10 empty] | Open | Open | Open
838 | M178 | MOM | 2023-09-12 |  |  |  | NOC Operationalization | Dashboards | SLA Monitoring and Network Performance Statistics |  | Critical | Open |  |  | 16-Oct-25:Covered in OSS implementation tracker | [12 empty] | Network | OPEN | Duplicate | 16-Oct-25:Covered in OSS implementation tracker | FALSE | [7 empty] | Open | Open | Open
839 | M179 | MOM | 2023-09-12 |  |  |  | NOC Operationalization | O&M Strategy | Spares Management |  | Critical | Open |  |  | 16-Oct-25: Covered in Asset Management | [12 empty] | Network | OPEN | Duplicate | 16-Oct-25: Covered in Asset Management | FALSE | [7 empty] | Open | Open | Open
840 | M18 | MOM | 2023-05-18 |  | OSS | OSS | OSS | Integration | IP MPLS auto trouble tickets |  | Critical | Open | OSS Dashboards |  | 09-09-2025: Stabilization needed | [12 empty] | Applications/Tools | OPEN | 09-09-2025: Stabilization needed | Completed With Artifacts | TRUE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
841 | M180 | MOM | 2023-09-12 |  |  |  | NOC Operationalization | O&M Strategy | Repair and Replacement process |  | Critical | Completed |  |  | 23-Sep-25: Approved shall be closed | [12 empty] | Network | Closed | CLOSED | 23-Sep-25: Approved shall be closed | FALSE | [5 empty] | 2025-09-23 | Artefacts not Required | Completed & Approved | Closed before june-2025 | Closed after June
842 | M181 | MOM | 2023-09-12 |  |  |  | BSS | Dynamic Feature | Overall capability to support the creation of innovative new products and seamless customer experience |  | NON-Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
843 | M182 | MOM | 2023-09-22 |  |  |  | NSO | Service provisioning | NSO provisioning is happening through EMS and asked for the list of provisioning/monitoring features being limited or constrained due to any interoperability issues in a multi-vendor eco-system. |  | Critical | Open |  |  | 29-dec-2025: Need discussion | [7 empty] | On-Hold |  |  |  |  | Applications/Tools | OPEN |  |  |  |  | Tejas NED is currently not working. |  |  | NSO Upgradation |  |  | Open | Open | Open
844 | M183 | MOM | 2023-09-22 |  | OSS | OSS | OSS | Service provisioning | Role of OSS in Service Provisioning |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | 0 | OPEN | TRUE | [7 empty] | Open | Open | Open
845 | M184 | MOM | 2023-09-22 |  |  |  | NOC Operationalization | O&M Strategy | Redundancy Plan for NSO and OSS |  | Critical | Open |  |  | 16-Oct-25: T-Fiber asked to implement only NSO | [12 empty] | Network | OPEN | CLOSED | 16-Oct-25: T-Fiber asked to implement only NSO | FALSE | [7 empty] | Open | Open | Open
846 | M185 | MOM | 2023-09-22 |  |  |  | NOC Operationalization | O&M Strategy | Limitations in OSS and NSO Scalability for post go live |  | Critical | Open |  |  | 16-Oct-25: Scalability issues shared | [12 empty] | Network | OPEN | OPEN | 16-Oct-25: Scalability issues shared | TRUE | [7 empty] | Open | Open | Open
847 | M186 | MOM | 2023-09-22 |  |  |  | BSS | Dynamic Feature | Enhance BSS to allow flexibility in creating, modifying, adding, and deleting product categories |  | NON-Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
848 | M187 | MOM | 2023-09-22 |  |  |  | NSO | Handbook & SOPs | Train in-house L&T resources in NSO and NEDs for reduced dependency on Cisco. |  | Critical | Open |  |  | 29-dec-2025: Need discussion | [7 empty] | Not Started |  |  |  |  | Applications/Tools | OPEN |  |  |  |  | Need Clarity | [5 empty] | Open | Open | Open
849 | M188 | MOM | 2023-09-22 |  |  |  | BSS | Notification Template | Notification Template Flexibility |  | NON-Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
850 | M189 | MOM | 2023-09-22 |  |  |  | BSS | Notification Template | CP to be changed to CP-TFGCLT |  | NON-Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
851 | M19 | MOM | 2023-05-18 |  |  |  | BSS | Resource Related | Inter-Dependence Matrix and Resource Identification |  | Critical | Open | OSS Dashboards | [14 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
852 | M190 | MOM | 2023-09-22 |  |  |  | BSS | CSP User Experience | Ensure that only the logos of the Government of Telangana and T-Fiber are used in the CSP. |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
853 | M191 | MOM | 2023-09-22 |  |  |  | BSS | Billing Related | CAF detailed analysis related to TRAI |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
854 | M192 | MOM | 2023-09-22 |  |  |  | BSS | CSP User Experience | Clearly mention on the Landing Page that services are currently extended only for Rural Telangana; Capture and store leads for requests from Urban Telangana. |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
855 | M193 | MOM | 2023-09-22 |  |  |  | BSS | CSP User Experience | User guides such as "May I help you", Chatbots, Videos |  | NON-Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
856 | M194 | MOM | 2023-09-22 |  |  |  | BSS | CSP User Experience | Definitions of terminologies to be available on mouseover |  | NON-Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
857 | M195 | MOM | 2023-09-22 |  |  |  | DR | O&M Strategy | a brief note on what is required to be delivered by CtrlS for DR |  | NON-Critical | Open |  |  | Work in progress | [12 empty] | DR | OPEN | [10 empty] | Open | Open | Open
858 | M196 | MOM | 2023-09-22 |  |  |  | DR | Functional AT Plan | Share the test results of DR systems with T-Fiber. |  | NON-Critical | Open |  |  | Work in progress | [12 empty] | DR | OPEN | [10 empty] | Open | Open | Open
859 | M197 | MOM | 2023-09-22 |  |  |  | BSS | Integration | WFM-SMS Gateway integration |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
860 | M198 | MOM | 2023-09-22 |  |  |  | BSS | CSP User Experience | L&T, to update the Landing Page to cater to all specified segments such as Pin code, Address, Lat-Long, or address pulling from Google API is required |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
861 | M199 | MOM | 2023-09-22 |  |  |  | BSS | Notification Template | Replace "Re-confirm" with "View" in the notification template. |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
862 | M2 | MOM | 2023-02-06 | P3 |  |  | NOC Operationalization | Handbook & SOPs | T-Fiber requested the inclusion of Protocol Manager and Regulatory roles in the TNOC organization chart. Also, emphasized clear demarcation and mapping of resources with names, roles, and responsibilities |  | Critical | Completed | OSS Dashboards |  | NOC resources details is shared on weekly basis. Roles of NOC is as per RFP. | [12 empty] | Network | Closed |  |  |  | Not related to delivery |  |  |  |  | 2025-09-19 | Artefacts not Required | Completed & Approved | Closed before june-2025 | Closed after June
863 | M20 | MOM | 2023-05-18 |  |  |  | BSS | Full NOC Readiness | Roadmap for Network Service Order Fulfilment and Service Assurance |  | Critical | Open | OSS Dashboards | [14 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
864 | M200 | MOM | 2023-09-22 |  |  |  | BSS | Notification Template | Ensure that SMS includes a link to the CSP. |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
865 | M201 | MOM | 2023-09-22 |  |  |  | BSS | Functional AT Plan | Perform testing of negative scenarios to identify and address any issues or vulnerabilities |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
866 | M202 | MOM | 2023-09-22 |  |  |  | BSS | CSP User Experience | Validate all mandatory fields and associated asterisks to ensure completeness and accuracy of data entry |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
867 | M203 | MOM | 2023-09-22 |  |  |  | BSS | Billing Related | Establish a mechanism to confirm the synchronization between the current account and the payment portal. |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
868 | M204 | MOM | 2023-09-22 |  |  |  | BSS | CSP User Experience | Display Progress in CSP Post-Order |  | NON-Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
869 | M205 | MOM | 2023-09-22 |  |  |  | BSS | CSP User Experience | User-Friendly Product Naming |  | NON-Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
870 | M206 | MOM | 2023-09-22 |  |  |  | BSS | Action points | Address and resolve issues related to using the backspace key on the webpage, ensuring smooth navigation to the previous page. |  | NON-Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
871 | M207 | MOM | 2023-09-22 |  |  |  | BSS | Billing Related | Payments and policies : BSS billing module should have various frameworks of full payment, part payment, advance payment, based on customer credit worthiness , based on discount policy etc. |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
872 | M208 | MOM | 2023-09-22 |  |  |  | BSS | CSP User Experience | Time Duration of OTP need to be fixed with timer |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
873 | M209 | MOM | 2023-09-22 |  |  |  | BSS | CSP User Experience | Implement 'Request to Re-send OTP' |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
874 | M21 | MOM | 2023-06-01 |  |  |  | GIS | User Experience | Google Map availability in Geo Media Tool with real time navigation |  | Critical | Open | OSS Dashboards |  | 15-Nov-25: Real MOM Point :- Google Map availability in Geo Media Tool, Hexagon clarified that Google Map feature is not available in Geo Media as it is a client based independent tool which can be install | ed | in cl | ient | PCs; how | r, end users |  | ca | n u |  |  | se O | SM and/or Bing maps along with Geo media Remarks :- Google Map availability in Geo Media Tool, Hexagon clarified that Google Map feature is not available in Geo Media as it is a client based independent tool which can be installed in client PCs; however, end users can use OSM and/or Bing maps along with Geo media | Applications/Tools | OPEN |  |  |  |  | eve | [5 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
875 | M210 | MOM | 2023-09-22 |  |  |  | BSS | Billing Related | Implement a system to generate a revised Proforma Invoice with the latest date if the ordering process is stopped and resumed. |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
876 | M211 | MOM | 2023-09-22 |  |  |  | BSS | CSP User Experience | Configure the CSP portal to display only orders relevant to the specific customer, enhancing user experience and clarity. |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
877 | M212 | MOM | 2023-09-22 |  |  |  | BSS | Service provisioning | Reservation of Bandwidth at Provisioning |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
878 | M213 | MOM | 2023-09-22 |  |  |  | BSS | CSP User Experience | Customer Care should in bold |  | NON-Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
879 | M214 | MOM | 2023-09-22 |  |  |  | BSS | Billing Related | Align Order Confirmation with Payment Receipt |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
880 | M215 | MOM | 2023-09-22 |  |  |  | BSS | Improvement | Improve 'Pick Order' Button and Placeholder |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
881 | M216 | MOM | 2023-09-22 |  |  |  | BSS | Billing Related | Implement Alerts for CAF Approval and Payment |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
882 | M217 | MOM | 2023-09-22 |  |  |  | BSS | Improvement | Customer Dashboards with visible website name for branding |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
883 | M218 | MOM | 2023-09-22 |  |  |  | BSS | User Experience | Make Site ID More Relevant for Order Selection |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
884 | M219 | MOM | 2023-09-22 |  |  |  | BSS | Improvement | Display Opportunity ID and Order ID Differently columns |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
885 | M22 | MOM | 2023-06-01 |  |  |  | GIS | User Experience | Fixed Topology Nomenclature |  | Critical | Open | OSS Dashboards | [14 empty] | Applications/Tools | OPEN | [10 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
886 | M220 | MOM | 2023-09-22 |  |  |  | BSS | Action points | Address Missing Scroll Bar in Some Pages |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
887 | M221 | MOM | 2023-09-22 |  |  |  | BSS | Billing Related | Incorporate a partial payment option for larger or priority accounts, allowing T-Fiber to decide on a case-by-case basis, along with an approval matrix. |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
888 | M222 | MOM | 2023-09-22 |  |  |  | BSS | Action points | Rectify the issue with the 'Show Password' option to ensure its proper functionality |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
889 | M223 | MOM | 2023-09-22 |  |  |  | BSS | Billing Related | Mandate the selection of the payment window (half-yearly or annually) during the ordering process, making it clear to the customer, rather than defaulting to monthly. |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
890 | M224 | MOM | 2023-09-22 |  |  |  | BSS | Improvement | Modify the order submission process to collect secondary phone numbers and email IDs, as required. |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
891 | M225 | MOM | 2023-09-22 |  |  |  | BSS | Billing Related | Implement a restriction to prevent order placement without the completion of payment, ensuring a secure and controlled ordering process. |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
892 | M226 | MOM | 2023-09-22 |  |  |  | BSS | Improvement | Standardize colour coding across all UX/UI elements for consistency and a unified visual experience. |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
893 | M227 | MOM | 2023-09-22 |  |  |  | BSS | Improvement | Allow users to refresh and continue after prolonged inactivity, enhancing the user experience and preventing disruptions |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
894 | M228 | MOM | 2023-09-22 |  |  |  | BSS | Improvement | Welcome Message Placement |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
895 | M229 | MOM | 2023-09-22 |  |  |  | BSS | Improvement | Introduce a flashing indicator for orders to attract attention and improve visibility. |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
896 | M23 | MOM | 2023-06-01 |  |  |  | GIS | User Experience | Character size in G-Tech |  | Critical | Open | OSS Dashboards | [14 empty] | Applications/Tools | OPEN | [10 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
897 | M230 | MOM | 2023-09-22 |  |  |  | BSS | User Experience | Add a visual indication for users to select the service under the Create Order page. |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
898 | M231 | MOM | 2023-09-22 |  |  |  | BSS | Action points | Investigate and address the issue where no details are displayed upon clicking on "Customer Premises Equipment." |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
899 | M232 | MOM | 2023-09-22 |  |  |  | BSS | Improvement | Rephrase the error message that appears when clicking on the Remove button under Create Order Step 3 for better clarity. |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
900 | M233 | MOM | 2023-09-22 |  |  |  | BSS | Improvement | Display Recurring Charge Frequency in Order Summary |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
901 | M234 | MOM | 2023-09-22 |  |  |  | BSS | User Experience | Display Instructions for CAF Download |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
902 | M235 | MOM | 2023-09-22 |  |  |  | BSS | User Experience | Indicate File Type and Size at Confirmation Stage |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
903 | M236 | MOM | 2023-09-22 |  |  |  | BSS | User Experience | Implement Preview Option for Uploaded Documents |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
904 | M237 | MOM | 2023-09-22 |  |  |  | BSS | Improvement | Emphasize the purpose of the "Edit Proceed" button for user understanding and clarity. |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
905 | M238 | MOM | 2023-09-22 |  |  |  | BSS | Action points | Resolve Issues with "Edit Proceed" Button |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
906 | M239 | MOM | 2023-09-22 |  |  |  | BSS | Improvement | Digitally Sign Proforma Invoice |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
907 | M24 | MOM | 2023-06-01 |  |  |  | GIS | User Experience | Searching for location accuracy in G-Tech with pinpoint accuracy |  | Critical | Open | OSS Dashboards | [14 empty] | Applications/Tools | OPEN | [10 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
908 | M240 | MOM | 2023-09-26 |  |  |  | NOC Operationalization | Handbook & SOPs | Provide clarification on the status of HOTO (Handover to Operations) and Knowledge Transfer. |  | Critical | Open |  |  | 23-Sep-25: Approved shall be closed | [12 empty] | Network | Closed | CLOSED | 23-Sep-25: Approved shall be closed | FALSE | [5 empty] | 2025-09-23 | Artefacts not Required | Completed & Approved | Closed before june-2025 | Closed after June
909 | M241 | MOM | 2023-09-26 |  |  |  | NOC Operationalization | Functional AT Plan | Systems functional Acceptance Tests Plan yet |  | Critical | Completed |  |  | 16-Oct-25: Covered in ATP Plans FAT documents shared, Tracker & updates are sent on periodic basis | [12 empty] | Network | OPEN | Duplicate | 16-Oct-25: Covered in ATP Plans | FALSE | [7 empty] | Open | Open | Open
910 | M242 | MOM | 2023-09-26 |  |  |  | NOC Operationalization | Full NOC Readiness | Launch Road Map |  | Critical | Completed |  |  | 16-Oct-25: Covered in NOC go-live plan 12 NOC points, 472 Tracker is being tracked with timelines and updates / reiew happening on regular basis | [12 empty] | Network | OPEN | Duplicate | 16-Oct-25: Covered in NOC go-live plan | FALSE | [7 empty] | Open | Open | Open
911 | M243 | MOM | 2023-09-26 |  |  |  | T&D Environment | T&D Environment | Provide details on the completion status of test and development of systems. |  | NON-Critical | Open |  |  | [15/09/25] Test Environment is actively used for T&D by Delivery and OEM teams. NOC submission provided in Tfiber has the T&D application from Oct-Mar2025 | [12 empty] | Applications | OPEN | [10 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
912 | M244 | MOM | 2023-09-26 |  |  |  | NOC Operationalization | Full NOC Readiness | Provide assurance that comprehensive solutions and designs will be within the specified list, considering anything beyond as a change request. |  | Critical | Open |  |  | 23-Sep-25: NON Critical to be reviewd later | [12 empty] | Network | OPEN | OPEN | 23-Sep-25: NON Critical to be reviewed later | TRUE | [7 empty] | Open | Open | Open
913 | M245 | MOM | 2023-09-26 |  |  |  | WFM | WFM Application | Clarify the distinction between smart app and WFM. |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
914 | M246 | MOM | 2023-09-26 |  |  |  | NSO | Service provisioning | IP Pool analysis with clearly define the ownership structure of IPs, specifying whether it's co-ownership or complete ownership by the OEM. |  | NON-Critical | Open |  |  | 29-dec-2025: Need discussion.already covered | [7 empty] | Not Started |  |  |  |  | Applications/Tools | OPEN |  |  |  |  | Jyothi | [5 empty] | Open | Open | Open
915 | M247 | MOM | 2023-09-26 |  |  |  | T&D Environment | T&D Environment | Clarify constraints related to infra upgradation for testing & development. |  | NON-Critical | Open |  |  | 11-Oct-25: Need to list out requirement of T&D for all Domains. [15/09/25] It was decided to setup T&D using existing infra in DC in the interim | [12 empty] | Applications | OPEN | [10 empty] | Open | Open | Open
916 | M248 | MOM | 2023-09-26 |  |  |  | NOC Operationalization | Full NOC Readiness | Consider RFP, technical bid, and solutions for understanding the requirements of a staging system after go-live. |  | Critical | Open |  |  | 16-Oct-25: General guidelines | [12 empty] | Network | OPEN | CLOSED | 16-Oct-25: General guidelines | FALSE | [7 empty] | Open | Open | Open
917 | M249 | MOM | 2023-09-26 |  |  |  | NOC Operationalization | OEM's Details | Provide all OEMs' test cases & certificates for T-Fiber network testing |  | Critical | Open |  |  | 16-Oct-25: Covered in ATP Plans | [12 empty] | Network | OPEN | Duplicate | 16-Oct-25: Covered in ATP Plans | FALSE | [7 empty] | Open | Open | Open
918 | M25 | MOM | 2023-06-01 |  |  |  | GIS | User Experience | Self-address auto-population in G-Tech |  | Critical | Open | OSS Dashboards |  | 15-Npv-25: Duplicate with Point- 80 | [12 empty] | Applications/Tools | [11 empty] | Open | Open | Open
919 | M250 | MOM | 2023-10-11 |  |  |  | NOC Operationalization | Full NOC Readiness | Full NOC to be ready by 10th Nov'23 |  | Critical | Open |  |  | 23-Sep-25: Approved shall be closed | [12 empty] | Network | Closed | CLOSED | 23-Sep-25: Approved shall be closed | FALSE | [5 empty] | 2025-09-23 | Artefacts not Required | Completed & Approved | Closed before june-2025 | Closed after June
920 | M251 | MOM | 2023-10-11 |  |  |  | BSS | Resource Related | BSS Expert onboarding |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
921 | M252 | MOM | 2023-10-11 |  |  |  | Security & Regulatory Compliance | Functional AT Plan | Share scope and test plans of the External Audit. |  | Critical | Open |  |  | 28-Nov-25: VAPT is going on, once VAPT is done points will be closed. External audit is done by 3rd party broughtin by Tfiber | [12 empty] | Security | OPEN | [10 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
922 | M253 | MOM | 2023-10-11 |  |  |  | Security & Regulatory Compliance | Physical Execution | Physical User access : Button is used for exit and still L&T have to finalise vendor |  | Critical | Open | [15 empty] | Security | Closed | [8 empty] | 2025-11-01 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\NW-Security\M253_31-Oct-25.pdf | Closed | Closed After 14-Oct | Open
923 | M254 | MOM | 2023-10-11 |  |  |  | Security & Regulatory Compliance | Dashboards | QoS reporting- Breakdown between automated and manual aspects |  | Critical | Open |  |  | 30-Oct-25 Send mail to siva kumar ,QoS reporting- Breakdown between automated and manual aspects, As per Sanjay Sir please move Point M254 out of the Security domain. | [12 empty] | Security | OPEN | [10 empty] | Open | Open | Open
924 | M255 | MOM | 2023-10-18 |  |  |  | BSS | CSP User Experience | Back Button to be available in the Payment Screen. |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
925 | M256 | MOM | 2023-10-18 |  |  |  | BSS | CSP User Experience | Guidelines to be available to the user in the CAF upload stage, what to upload in CAF upload stage is not clear. |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
926 | M257 | MOM | 2023-10-18 |  |  |  | BSS | CSP User Experience | Add a disclaimer for “Subject to Verification of CAF”, with notification trigger |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
927 | M258 | MOM | 2023-10-18 |  |  |  | BSS | CSP User Experience | Unable to view offline payment transactions uploaded |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
928 | M259 | MOM | 2023-10-18 |  |  |  | BSS | CSP User Experience | Mandatory sections of the CAF to be highlighted. |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
929 | M26 | MOM | 2023-06-01 |  |  |  | GIS | User Experience | GPON Fiber Termination plan adherence |  | Critical | Open | Gtech | [14 empty] | Applications/Tools | OPEN | [10 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
930 | M260 | MOM | 2023-10-18 |  |  |  | BSS | CSP User Experience | Notifications for ticket via SMS and Email not received. |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
931 | M261 | MOM | 2023-10-18 |  |  |  | BSS | CSP User Experience | Received a Pop-up for incorrect entry of OTP despite entering the correct OTP |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
932 | M262 | MOM | 2023-10-18 |  |  |  | BSS | CSP User Experience | Raised single ticket in CSP, however 3 distinct tickets are visible in CSP with same narration of issue, notification or alerts not received for any of these tickets. |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
933 | M263 | MOM | 2023-10-18 |  |  |  | BSS | CSP User Experience | tickets raised are visible at the department level only, is this possible to be made available Departmental user wise? |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
934 | M264 | MOM | 2023-10-18 |  |  |  | BSS | CSP User Experience | Searching by Order ID is case sensitive. |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
935 | M265 | MOM | 2023-10-18 |  |  |  | BSS | CSP User Experience | Receiving the “Pending Feasibility” confirmation message, then receiving result as “Feasible” |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
936 | M266 | MOM | 2023-10-18 |  |  |  | BSS | CSP User Experience | How does BSS handle dismantled GPs if there is no real-time sync between GIS-OSS |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
937 | M267 | MOM | 2023-10-18 |  |  |  | BSS | CSP User Experience | Cygnet product name showing in the top of the tab, to be removed. |  | NON-Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
938 | M268 | MOM | 2023-10-18 |  |  |  | BSS | CSP User Experience | GP names are not aligned to government list |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
939 | M269 | MOM | 2023-10-18 |  |  |  | BSS | CSP User Experience | Plot number to be renamed as Plot / House no |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
940 | M27 | MOM | 2023-06-07 |  |  |  | GIS | Handbook & SOPs | Approval mechanism for object changes/deletion |  | Critical | Open | Gtech |  | 15-Nov-25: Duplicate with Point- 81 | [12 empty] | Applications/Tools | [10 empty] | #N/A | Closed | Closed | Open
941 | M270 | MOM | 2023-10-18 |  |  |  | BSS | CSP User Experience | In case of Manual Provisioning, is there a stage for Validation? |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
942 | M271 | MOM | 2023-10-18 |  |  |  | BSS | CSP User Experience | Unable to enter the OTP, Unable to close the Pop-up window for OTP, require either a “Close” button OR closing the Pop-up should be allowed by clicking outside the Pop-up. |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
943 | M272 | MOM | 2023-10-18 |  |  |  | BSS | CSP User Experience | Unable to go back to Home Screen |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
944 | M273 | MOM | 2023-10-18 |  |  |  | BSS | CSP User Experience | In Landing Page, number of GPs is mentioned as 12,751, this number to be validated. |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
945 | M274 | MOM | 2023-10-18 |  |  |  | BSS | CSP User Experience | Back Button required in Create Order and Order Summary screens |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
946 | M275 | MOM | 2023-10-18 |  |  |  | BSS | CSP User Experience | What is the purpose of displaying segment as G2G in CAF ? |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
947 | M276 | MOM | 2023-10-18 |  |  |  | BSS | CSP User Experience | How does a GI customer know the Site ID to be entered. |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
948 | M277 | MOM | 2023-10-18 |  |  |  | BSS | CSP User Experience | Payment is showing as Net banking for all transactions, including offline transactions. |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
949 | M278 | MOM | 2023-10-18 |  |  |  | BSS | CSP User Experience | Unable to see Order Summary just before Payment. |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
950 | M279 | MOM | 2023-10-18 |  |  |  | BSS | CSP User Experience | Notification of Success / Failure to be available on Order Submission. |  | NON-Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
951 | M28 | MOM | 2023-06-07 |  |  |  | GIS | Handbook & SOPs | Change Management Log/User Log history |  | Critical | Open | Gtech |  | 15-Nov-25: Duplicate with Point- 82 | [12 empty] | Applications/Tools | [10 empty] | #N/A | Closed | Closed | Open
952 | M280 | MOM | 2023-10-18 |  |  |  | BSS | CSP User Experience | In Payment Screen, add a disclaimer that “Payment details are subject to verification for offline payments” to cover for the scenario of wrong / incorrect Payment ID provided by the user. |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
953 | M281 | MOM | 2023-10-18 |  |  |  | BSS | CSP User Experience | Is a location added in CSP visible in the CRM as a lead? |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
954 | M282 | MOM | 2023-10-18 |  |  |  | BSS | CSP User Experience | While adding a new location using the map, searching by name is working (example- Jagtial), however searching by Lat-Long is not working. |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
955 | M283 | MOM | 2023-10-18 |  |  |  | BSS | CSP User Experience | Added a location, but GP name is not getting populated, how is this address added in the CRM, received a pop-up alert for location confirmation, but this location is not added to the list. |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
956 | M284 | MOM | 2023-10-18 |  |  |  | BSS | CSP User Experience | Product Selection screen did not display “Last Mile Connectivity” with no view to scroll right, either restrict the size of the location name or display all columns in a single page. |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
957 | M285 | MOM | 2023-10-18 |  |  |  | BSS | CSP User Experience | Email notifications not being triggered for a few actions where events are not configured |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
958 | M286 | MOM | 2023-10-18 |  |  |  | BSS | CSP User Experience | Received order confirmation, but no notifications received for payment, no notification on save order. |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
959 | M287 | MOM | 2023-10-18 |  |  |  | BSS | CSP User Experience | What is the Transaction number? |  | NON-Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
960 | M288 | MOM | 2023-10-18 |  |  |  | BSS | CSP User Experience | While adding a new address, selected a gram panchayat, changed Lat-Long, provided address details, successfully added these details, but the address for GP name is not seen, to be shown. |  | NON-Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
961 | M289 | MOM | 2023-10-19 |  |  |  | NOC Operationalization | Interim NOC | Provide a list of points that need to be available for the Network Launch targeted for November 30th, 2023. Identify the points that will be included in the roadmap and specify the timelines for their implementation |  | Critical | Completed |  |  | 23-Sep-25: Approved shall be closed | [12 empty] | Network | Closed | CLOSED | 23-Sep-25: Approved shall be closed | FALSE | [5 empty] | 2025-09-23 | Artefacts not Required | Completed & Approved | Closed before june-2025 | Closed after June
962 | M29 | MOM | 2023-06-07 |  |  |  | GIS | Handbook & SOPs | Data Validation Rules document |  | Critical | Open | Gtech | [14 empty] | Applications/Tools | OPEN | [10 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
963 | M290 | MOM | 2023-10-19 |  |  |  | NOC Operationalization | Interim NOC | explain their approach for handling Operations and Maintenance (O&M) to meet the SLAs (Service Level Agreements) and provide process documents for features that are currently unavailable. |  | Critical | Open |  |  | 23-Sep-25: Approved shall be closed | [12 empty] | Network | Closed | CLOSED | 23-Sep-25: Approved shall be closed | FALSE | [5 empty] | 2025-09-23 | Artefacts not Required | Completed & Approved | Closed before june-2025 | Closed after June
964 | M291 | MOM | 2023-10-19 |  |  |  | NOC Operationalization | Interim NOC | To clarify how they plan to transition the O&M responsibilities and data once the currently unavailable features are made available. |  | Critical | Open |  |  | 23-Sep-25: Approved shall be closed | [12 empty] | Network | Closed | CLOSED | 23-Sep-25: Approved shall be closed | FALSE | [5 empty] | 2025-09-23 | Artefacts not Required | Completed & Approved | Closed before june-2025 | Closed after June
965 | M292 | MOM | 2023-10-19 |  |  |  | NOC Operationalization | Interim NOC | Evidence from L&T on the timelines for fulfilling the feature gaps |  | Critical | Open |  |  | 23-Sep-25: Approved shall be closed | [12 empty] | Network | Closed | CLOSED | 23-Sep-25: Approved shall be closed | FALSE | [5 empty] | 2025-09-23 | Artefacts not Required | Completed & Approved | Closed before june-2025 | Closed after June
966 | M293 | MOM | 2023-10-19 |  |  |  | BSS | GeM Integration | GeM integration with BSS: the point may be deferred for 6 months, with timeline to be added by L&T for next review, L&T to issue a Note (Note 1) recording this statement. |  | NON-Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
967 | M294 | MOM | 2023-10-19 |  |  |  | GPON | Interim NOC | Request a Note (Note 2) from L&T addressing the impact of the unavailability of NBI API availability for BW query Dependent on new OLT build for GI deployment and how NOC operations will be managed in the interim period until the required features are developed and integrated with seamless transition. |  | Critical | Open | Nokia OEM | AMS | Duplicate point of 472 - T175 | [12 empty] | GPON | OPEN |  |  |  | Duplicate | [6 empty] | Open | Open | Open
968 | M295 | MOM | 2023-10-19 |  |  |  | GPON | Integration | Point No. 175: CR for Nokia API integration to resolve BW query and PMS-related issues. 1. Note 2 should also cover Point No. 175. 2. Set a target completion date of November 20th '23 for this activity. |  | Critical | Open | Nokia OEM | AMS | Duplicate point of 472 - T175 | [12 empty] | GPON | OPEN |  |  |  | Duplicate | [6 empty] | Open | Open | Open
969 | M296 | MOM | 2023-10-19 |  |  |  | GPON | Upgradation | Point No. 179: Troubleshooting required with Tejas and Nokia for Tejas ONT firmware upgrade issue. 1. Technical Head from L&T to seek support from L&T-Contracts team and aim for implementation within 15-20 days from the resolution of the issue. 2. L&T to submit the agreed Scope between L&T and NOC OEMs (primarily OSS, BSS, NSO) by October 24th '23. 3.Request a Note (Note 3) outlining the interim/final solution and an undertaking co-signed by Package Owners to be submitted by October 26th '23. 4.Target completion of Point No. 179 by November 20th '23. |  | Critical | Open | [15 empty] | GPON | Closed | [8 empty] | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T179 | Completed & Approved | Closed before june-2025 | Closed after June
970 | M297 | MOM | 2023-10-19 |  |  |  | GPON | Upgradation | Point No. 180: Nokia ONT to support NAT, DHCP in both Router and Bridge modes. 1. Instruct L&T to identify the number of ONTs in the warehouse and send them to the Nokia Warehouse immediately for upgrade. 2. Coordinate with Package B&C for similar actions. 3.Note 4 on the mitigation and deployment plan for remediation, along with the timelines, testing to be part of the method of deployment. |  | Critical | Open | Nokia OEM | ONT | Duplicate point of 472 - T180 | [12 empty] | GPON | Closed |  |  |  | Completed | [5 empty] | Artefacts not Required | Open | Open | Open
971 | M298 | MOM | 2023-10-19 |  |  |  | IP/MPLS | Service Solution | Point No. 186: IPTV to Household ,Point No. 190: CCTV Multicast ,Point No. 193: SDC content to Household and GI ,Point No. 194: Incremental Product/ Services finalization in T-Fiber network,Point No. 197: Service Provisioning PoC for SCCM/NSO - MVPN (all scenarios) ,Point No. 198: Simulation and testing network for parameters like network convergence etc & Point No. 344: CCTV Solution - solution to start PoC with DC connectivity at Cyberabad location as receiver and Sircilla NVR as source. To respond with relevant evidence on how the scope is contracted between L&T and its NOC OEMs, how L&T will implement the Network AT given the Launch date of 30th November ’23. |  | Critical | Open |  |  | 25-Sep-25: Aretfacts to be uploaded for closure All updated in 472 tracker 186, 190 - Closed 344 - CCTV PoC completed. 193 - Plan re-submitted on 12-Sep-25 198 - Pending, OEM dependancy 197 - NSO point | [12 empty] | IPMPLS | Closed | [8 empty] | 2025-05-05 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\House Hold VoIP Services Design LLD V1.2 - t187.pdf | Completed & Approved | Closed before june-2025 | Closed after June
972 | M299 | MOM | 2023-10-19 |  |  |  | NSO | Design features | Point No. 221: MAG/GAC ports reservation feasibility for services booked in BSS with payments made. - BSS-SME, L&T to seek clarity on port reservation as a business requirement and the time period required for reservation. - Head Telecom Networks, L&T to record the statement that the port reservation is not a blocker for Network Launch. - Request a Note (Note 5) documenting the statement made by Head Telecom Networks. - L&T to make a decision on the period of port reservation considering the scope of NOC O&M for 7 years. |  | Critical | Open |  |  | 29-dec-2025: Need discussion.already covered. Infra team to guide | [7 empty] | Not Started |  |  |  |  | Applications/Tools | OPEN |  |  |  |  | BSS (Ports feasibility check with BSS team for any proof) 16/03/2026 : Based on screenshot jyothi will provide details related to network side 17/03/2026 : can be closed after discussion with Customer,Reservation of ports is not feasible - the solution and viability not agreed confirmed by BSS team |  |  | Not Feasible |  | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\CCTV Multicast Solution LLD V1.2 - T190.pdf | Open | Open | Open
973 | M3 | MOM | 2023-03-27 |  |  |  | NOC Operationalization | Full NOC Readiness | Present a plan on how digital processes and tools will be used for GI connectivity provisioning, customer acceptance, and O&M functions |  | Critical | Open | OSS Dashboards |  | 16-Oct-25: Covered in BSS HLD | [12 empty] | Network | OPEN | Duplicate | 16-Oct-25: Covered in BSS HLD | FALSE | [6 empty] | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\CCTV Multicast Solution LLD V1.2 - T190.pdf | Open | Open | Open
974 | M30 | MOM | 2023-06-07 |  |  |  | GIS | User Experience | Show duct length, Cable length, chambers, and joint closures in a Mandal |  | NON-Critical | Open | Gtech | [14 empty] | Applications/Tools | OPEN | [10 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
975 | M300 | MOM | 2023-10-19 |  |  |  | NSO | Development & Unit Testing | Point No. 223: IPTV tested needs to be finalised for additional configuration for multicast and tested as per lab availability and final sign off Technical Head, L&T to get the solution sign-off from T-Fiber for additional IPTV configuration and testing. - Target implementation date set for November 15th '23. - Request a Note (Note 6) recording the statement that this point is not a blocker for Network Launch. |  | Critical | Open |  |  | 29-dec-2025: Need discussion | [7 empty] | On-Hold |  |  |  |  | Applications/Tools | OPEN |  |  |  |  | No Service started yet |  |  | Not Feasible |  |  | Open | Open | Open
976 | M301 | MOM | 2023-10-19 |  | OSS | OSS | New BSS | Integration | Point No. 251: Fetch SLA violation by BSS billing & Point No. 252 Circuit performance data to BSS CRM L&T to provide an outline of the interim solution before the Service Inventory solution from HP is in place. - Ensure no impact on operations during the interim period. - L&T proposes interim measures such as manual computation of downtime, manual SLA performance management, etc. - Request an Undertaking (Note 7) confirming that the interim solution will have no cost impact to T-Fiber. - Timelines for interim milestones and emphasize the need to plan for the final deliverables and a seamless transition. - Segment Head, L&T to provide clear confirmation by the 1st week of November '23. |  | Critical | Open | [15 empty] | #N/A | OPEN | 0 | Not Relevant To OSS | TRUE | [7 empty] | Open | Open | Open
977 | M302 | MOM | 2023-10-19 |  | OSS | OSS | New BSS | Integration | Point No. 264: Network Downtime, fault reported to be mapped with BSS to consider during billing process & Point No. 265: Feasibility Engine & Point No. 266: Commercial engine to be designed along with rules to Budgetary calculation for network and customer feasibilities L&T to submit the SOW agreed between L&T and HP by EoD 19th October ’23. |  | Critical | Open | [15 empty] | #N/A | OPEN | 0 | Not Relevant To OSS | TRUE | [7 empty] | Open | Open | Open
978 | M303 | MOM | 2023-10-19 |  | OSS | OSS | OSS | Development & Unit Testing | Point No. 267: Port Block against Service ID ( Note 5) |  | Critical | Open |  |  | Additional Scope (This is not give to HPE/OT) | [12 empty] | Applications/Tools | OPEN |  | Additional Scope | FALSE | [7 empty] | Open | Open | Open
979 | M304 | MOM | 2023-10-19 |  | OSS | OSS | OSS | Design & Documentation | Point No. 272: Infra team to maintain the SSH connectivity • Security-SME, L&T to submit the design document for SSH. |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | 0 | Completed With Artifacts | TRUE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
980 | M305 | MOM | 2023-10-19 |  | OSS | OSS | OSS | Dashboards | Point No. 280: Cross domain Corelation and exact reason for any outage in Network till ONT Port with E2E topology is targeted for closure by November 15th '23. |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | Pending | Duplicate | FALSE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
981 | M306 | MOM | 2023-10-19 |  | OSS | OSS | OSS | Dashboards | Point No. 282: For ONT Down cases, Some of the Alarms and cause code given by OEM is not matching with RFO provided by field engineer with target date as 25th October ’23. |  | Critical | Open |  |  | 15-09-2025: Demostrated in the Demo/UAT call | [12 empty] | Applications/Tools | OPEN | 15-09-2025: Demostrated in the Demo/UAT call | Completed With Artifacts | TRUE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
982 | M307 | MOM | 2023-10-19 |  | OSS | OSS | OSS | Dashboards | Point No. 283: Alert Mechanism (event rule) when power supply is through UPS which is running on Battery backup mode then there should be alert in the form of SMS sent to field team so outages can be avoided or minimized proactively. target date is 15th November ’23. |  | Critical | Open |  |  | 09-09-2025: It can be enabled based on customer confirmation | [12 empty] | Applications/Tools | OPEN | Pending | Completed | FALSE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
983 | M308 | MOM | 2023-10-19 |  | OSS | OSS | OSS | Dashboards | Point No. 290: IP MPLS node status report to be automated (Zonal / Mandal/GP) along with Alias Name (Like Actual Mandal /GP names) -Feasibility check required if Alias can be updated & fetched by OSS tool will be informed |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | 0 | Completed | TRUE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
984 | M309 | MOM | 2023-10-19 |  | OSS | OSS | OSS | Dashboards | Point No. 292: Customised dashboard template with available set of fields for different set of user views by 20th Oct'23 |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | 0 | Completed With Artifacts | TRUE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
985 | M31 | MOM | 2023-06-07 |  |  |  | GIS | User Experience | Correct Actual Measure Length and Loop length in BOQ |  | NON-Critical | Open | Gtech | [14 empty] | Applications/Tools | OPEN | [10 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
986 | M310 | MOM | 2023-10-19 |  | OSS | OSS | OSS | Dashboards | Point No. 294: OSS MTTR report to include additional columns like RFO, Sub RFO, Resolution etc. By 20th Oct'23 |  | Critical | Open | [15 empty] | Applications/Tools | Closed | 0 | Completed With Artifacts | TRUE | [5 empty] | 2025-11-18 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\OSS\52 Artefcats_18112025 | Closed after 14-Nov-25 | Closed after 14-Nov-25 | Completed but Verification undrer Process
987 | M311 | MOM | 2023-10-19 |  | OSS | OSS | OSS | Dashboards | Point No. 296: Service Management dashboard should list planned outages and corelate TT if that is on same device or NW component by 20th Oct'23 |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | 0 | Duplicate | TRUE | [7 empty] | Open | Open | Open
988 | M312 | MOM | 2023-10-19 |  |  |  | Security & Regulatory Compliance | Regulatory Compliance | Point No. 308: IPDR - Developing in-house solution, also exploring with external vendors. to obtain clarity from the Regulator on the requirements, along with the industry best practices. • VP-Program, T-Fiber asked L&T to revert on the next steps by 26th October ’23. |  | Critical | Open | [15 empty] | Security | Closed | [8 empty] | 2025-10-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\NW-Security\T303_28-Oct-25.pdf | Closed | Closed After 14-Oct | Open
989 | M313 | MOM | 2023-10-19 |  |  |  | Security & Regulatory Compliance | Regulatory Compliance | Point No. 312: SLA Reporting for Cell Tower and GIs • Head Telecom Networks, L&T mentioned that two approaches are under consideration, solution approach to be finalised, target for completion is 30th November ’23. |  | Critical | Open | [15 empty] | Security | OPEN | [10 empty] | Open | Open | Open
990 | M314 | MOM | 2023-10-19 |  | OSS | OSS | OSS | Resource Related | SVP, T-Fiber emphasized the importance of L&T establishing its own resources for the HPE related tasks and they should not rely solely on one individual. |  | Critical | Open |  |  | 09-09-2025: Taken support from vigility Team | [12 empty] | Applications/Tools | OPEN | 09-09-2025: Taken support from vigility Team | Completed | TRUE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
991 | M315 | MOM | 2023-10-19 |  |  |  | Security & Regulatory Compliance | User Traceability | Point No. 316: User Traceability,targeted for closure by 15th November ’23. this point to be included in the SOPs for NOC. |  | Critical | Open | [15 empty] | Security | OPEN | [10 empty] | Open | Open | Open
992 | M316 | MOM | 2023-10-19 |  |  |  | Security & Regulatory Compliance | Policy Implementation | Point No. 318: Policy Implementation – Network Forensics the process for tracing all incidents including security incidents is yet to be put in place, targeted for 15th November ’23. |  | Critical | Open |  |  | 28-Nov-25: VAPT is going on, once VAPT is done points will be closed | [12 empty] | Security | OPEN | [10 empty] | Open | Open | Open
993 | M317 | MOM | 2023-10-19 |  |  |  | Security & Regulatory Compliance | Report | Point no. 326: IPDR static IP report SVP, T-Fiber asked for the Regulatory aspects to be discovered by 26th October ’23. |  | Critical | Open | [15 empty] | Security | Closed | [8 empty] | 2025-10-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\NW-Security\T303_28-Oct-25.pdf | Closed | Closed After 14-Oct | Open
994 | M318 | MOM | 2023-10-19 |  |  |  | Security & Regulatory Compliance | Design features | Point No. 333: Alepo AAA to be integrated with AD SVP, T-Fiber asked for an SOP to be defined for this. • SVP, T-Fiber asked for a note (Note 8) recording this statement. |  | Critical | Open |  |  | 28-Nov-25: The Alepo team is integrating AD Once done these points will be closed. This is Security point | [12 empty] | Security | OPEN | [10 empty] | Open | Open | Open
995 | M319 | MOM | 2023-10-19 |  |  |  | NSO | Design & Documentation | Point No. 343: SDC content to GI – Design document required. Head Telecom Networks, L&T to update on the next steps by 26th October ’23. |  | NON-Critical | Open |  |  | 29-dec-2025: Need discussion | [7 empty] | Not Started |  |  |  |  | Applications/Tools | OPEN |  |  |  |  | Need Clarity | [5 empty] | Open | Open | Open
996 | M32 | MOM | 2023-06-07 |  |  |  | GIS | Handbook & SOPs | Detailed validation document |  | NON-Critical | Open | Gtech | [14 empty] | Applications/Tools | OPEN | [10 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
997 | M320 | MOM | 2023-10-19 |  |  |  | Helpdesk | Demo | Assistant Director-P&E, T-Fiber asked L&T to submit the Helpdesk Compliance report along with a summary with respect to RFP by 23rd October’23 and the Demonstration on Helpdesk NEOX to be scheduled after the compliance report submission. |  | Critical | open |  |  | 01-Dec-25: Artefcats to be submitted 11-Sep-25: Compliance report has been Submitted | [12 empty] | Helpdesk (Contact Center) | OPEN | [10 empty] | Open | Open | Open
998 | M321 | MOM | 2023-10-19 |  |  |  | BSS | Development & Unit Testing | Point No. 16: Development and Unit Testing - Service Assurance and trouble tickets To be linked with the points in follow-up with HP for completion by March ’24, with clarity on next steps by 1st week of November. |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
999 | M322 | MOM | 2023-10-19 |  |  |  | DR | DNS Switchover | Point No. 79: to confirm that DNS switchover between DC and DR locations should be automatic • Chief Delivery Officer, LTTS updated that this in follow-up with Cisco and CtrlS, next update by 26th October ’23. |  | NON-Critical | Closed |  |  | [15/09/25] Completed | [12 empty] | DR | Closed | [9 empty] | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\DR\Artifact for - T79 | Completed & Approved | Closed before june-2025 | Closed before june-2025
1000 | M323 | MOM | 2023-10-19 |  |  |  | DWDM | Integration with OSS | Point No. 103: DWDM-OSS integration - Service Inventory Data Availability in HPE OSS & Point No. 237: DWDM-OSS integration - Service inventory data availability in HPE OSS • Technical Head, L&T updated that this is targeted for closure by 15th November ’23. |  | Critical | Open |  |  | Duplicate Already covered in 472-points, Ref Point No. 103 & 237 | [12 empty] | DWDM |  |  |  |  | Duplicate | [6 empty] | Open | Open | Open
1001 | M324 | MOM | 2023-10-19 |  |  |  | DWDM | Integration with OSS | Point No. 104 – DWDM-OSS integration: Planned Event Service Impact analysis report & Point No. 238: DWDM-OSS integration: For planned event service impact analysis data / report SVP, T-Fiber asked for the SOP that shall be put in place by L&T until the Service Inventory solution from HP is in place |  | Critical | Open |  |  | Duplicate Already covered in 472-points, Ref Point No. 104& 238 | [12 empty] | DWDM |  |  |  |  | Duplicate | [6 empty] | Open | Open | Open
1002 | M325 | MOM | 2023-10-19 |  | OSS | OSS | OSS | Integration | Point No. 231: Ciena DWDM Network Topology has been created in HPE OSS topology MAP along with neighbour NE details. SVP, T-Fiber suggested that this requirement may be revisited later. |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | 0 | Completed With Artifacts | TRUE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1003 | M326 | MOM | 2023-10-19 |  | OSS | OSS | OSS | Design Features | Point No. 259: OSS E2E Topology it will be completed by 30th December’23 |  | Critical | Open |  |  | This point is already covered under point no. 584. and Point no. 633 under 472 tracker column | [12 empty] | Applications/Tools | OPEN | This point is already covered under point no. 584. and Point no. 633 under 472 tracker column | Duplicate | TRUE | [7 empty] | Open | Open | Open
1004 | M327 | MOM | 2023-10-19 |  | OSS | OSS | OSS | Dashboards | Point No. 275: In OSS management dashboard, Block count should count only Mandal OLTs and not GP OLTs target date as 30th December ’23. |  | Critical | Open | [15 empty] | Applications/Tools | Closed | 0 | Completed With Artifacts | TRUE | [5 empty] | 2025-11-18 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\OSS\52 Artefcats_18112025 | Closed after 14-Nov-25 | Closed after 14-Nov-25 | Completed but Verification undrer Process
1005 | M328 | MOM | 2023-10-19 |  | OSS | OSS | OSS | Design Features | Point No. 281: Problem Management report for various recurring outages for the given period target date as 30th December ’23 |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | 0 | Completed | TRUE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1006 | M329 | MOM | 2023-10-19 |  | OSS | OSS | OSS | Design Features | Point No. 287: Exact SPAN/Link details must be taken from GIS (Including Lat, Long) for Fiber cut/outage scenario to understand fix is permanent or temporary in nature and impact on Multiple Nodes/GP’s. |  | Critical | Open | [15 empty] | Applications/Tools |  | 0 | Duplicate | TRUE | [7 empty] | Open | Open | Open
1007 | M33 | MOM | 2023-06-07 |  |  |  | GIS | User Experience | Hyperlink real images to GPs and Mandals |  | Critical | Open | Gtech | [14 empty] | Applications/Tools | OPEN | [10 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1008 | M330 | MOM | 2023-10-19 |  | OSS | OSS | OSS | Dashboards | Point No. 288: Report for Backup Status (success/failure) of all VM (source it from Vcenter Report) L&T to conclude discussions with HP to obtain the target date. |  | Critical | Open |  |  | 09-09-2025: managed at vmware(comvault) by DCInfra Team | [12 empty] | Applications/Tools | OPEN | 09-09-2025: managed at vmware(comvault) by DCInfra Team | Not-Feasible | TRUE | [7 empty] | Open | Open | Open
1009 | M331 | MOM | 2023-10-19 |  | OSS | OSS | OSS | Dashboards | Point No. 289: DC Active infra-Health check-up /Utilization and Resource Availability report L&T to conclude discussions with HP to obtain the target date. |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | 0 | Completed | TRUE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1010 | M332 | MOM | 2023-10-19 |  | OSS | OSS | OSS | Dashboards | Point No. 293: Service VLAN status report from EMS (Nokia and Tejas) Technical Head, L&T to conclude discussions to obtain the target date. |  | Critical | Open |  |  | It will be available from intranet portal | [12 empty] | Applications/Tools | OPEN |  | Completed With Artifacts | FALSE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1011 | M333 | MOM | 2023-11-03 |  |  |  | BSS | Service provisioning | UD,SD Peramaters to be captured. |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1012 | M334 | MOM | 2023-11-03 |  |  |  | NSO | Service provisioning | NSO inventory manager funtionality to check. |  | Critical | Open |  |  | 29-dec-2025: Need discussion. Which inventory. Internal to NSO/CISCO | [7 empty] | Not Started |  |  |  |  | Applications/Tools | OPEN |  |  |  |  | Need Clarity | [5 empty] | Open | Open | Open
1013 | M335 | MOM | 2023-11-03 |  |  |  | BSS | Service provisioning | UD perameters for product based to be prepared. |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1014 | M336 | MOM | 2023-11-03 |  |  |  | BSS | Service provisioning | Ashish to comeback with Design plan for Inventory Manager at NSO |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1015 | M337 | MOM | 2023-11-03 |  |  |  | BSS | Service provisioning | Arvindam to comeback with product wise UD perameters |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1016 | M338 | MOM | 2023-11-03 |  |  |  | BSS | Service provisioning | Additional information for VRF, VLAN , Inner vlan etc to capture in Master DB |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1017 | M339 | MOM | 2023-11-03 |  |  |  | BSS | Service provisioning | As per Cisco LLD All 28 types of L2, L3 models to be mapped aginest products |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1018 | M34 | MOM | 2023-06-07 |  |  |  | GIS | Installation | 100TB storage for LIDAR survey data |  | Critical | Open | Gtech | [14 empty] | Applications/Tools | OPEN | [10 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1019 | M340 | MOM | 2023-11-03 |  |  |  | BSS | Service Codes | GL code to be mapped based on subtype GI under sub type Central & State |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1020 | M341 | MOM | 2023-11-03 |  |  |  | BSS | Service Codes | Define the Code for Circuit type , Customer type , customer service type etc in single format |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1021 | M342 | MOM | 2023-11-03 |  |  |  | BSS | Service Codes | Define design plan for House hold services in GPON Level |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1022 | M343 | MOM | 2023-11-03 |  |  |  | BSS | Service Codes | Define Household plan for provisioning as per the GPON plan design |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1023 | M344 | MOM | 2023-11-03 |  |  |  | BSS | Service Codes | OSS Method of distance from GIS need to comeback with plan |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1024 | M345 | MOM | 2023-11-03 |  |  |  | BSS | Service Codes | Aravindam to update on previous meetings updates to be updated in next in continuous meetings |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1025 | M346 | MOM | 2023-11-17 |  |  |  | Helpdesk | Demo | Neox helpdesk Demo : |  | Critical | Open | [15 empty] | Helpdesk (Contact Center) | OPEN | [10 empty] | Open | Open | Open
1026 | M347 | MOM | 2023-11-17 |  |  |  | Helpdesk | Compliance | Neox Compliance confirmation : |  | Critical | open |  |  | 01-Dec-25: Duplicate, Same as M320 11-Sep-25: Compliance report has been Submitted | [12 empty] | Helpdesk (Contact Center) | OPEN | [10 empty] | Open | Open | Open
1027 | M348 | MOM | 2023-11-17 |  |  |  | NOC Operationalization | Action Points | 370 points out of which 24 points which are already covered in 370 : Praveen to share indicating the reference of 24 points by |  | Critical | Closed |  |  | 23-Sep-25: Approved shall be closed | [12 empty] | Network | Closed | CLOSED | 23-Sep-25: Approved shall be closed | FALSE | [5 empty] | 2025-09-23 | Artefacts not Required | Completed & Approved | Closed before june-2025 | Closed before june-2025
1028 | M349 | MOM | 2023-11-17 |  |  |  | NOC Operationalization | Action Points | 196 points closure along with artefacts : |  | Critical | Closed |  |  | 23-Sep-25: Approved shall be closed | [12 empty] | Network | Closed | CLOSED | 23-Sep-25: Approved shall be closed | FALSE | [5 empty] | 2025-09-23 | Artefacts not Required | Completed & Approved | Closed before june-2025 | Closed before june-2025
1029 | M35 | MOM | 2023-06-07 |  |  |  | GIS | Training | Hands-on Training on GIS tool |  | NON-Critical | Open | Gtech | [14 empty] | Applications/Tools | OPEN | [10 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1030 | M350 | MOM | 2023-11-17 | P3 |  |  | NOC Operationalization | Documentation | Revised Organization structure : |  | Critical | Completed |  |  | NOC structure and manpower details shared | [12 empty] | Network | Closed |  |  |  | Not related to delivery |  |  |  |  | 2025-09-19 | Artefacts not Required | Completed & Approved | Closed before june-2025 | Closed after June
1031 | M351 | MOM | 2023-11-17 |  |  |  | BSS | Demo | Second Dry Run (details to be shared later) : week starting |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1032 | M352 | MOM | 2023-11-17 |  |  |  | NOC Operationalization | Documentation | Artefacts storage link : |  | Critical | Completed |  |  | 23-Sep-25: Approved shall be closed | [12 empty] | Network | Closed | CLOSED | 23-Sep-25: Approved shall be closed | FALSE | [5 empty] | 2025-09-23 | Artefacts not Required | Completed & Approved | Closed before june-2025 | Closed after June
1033 | M353 | MOM | 2023-11-17 |  |  |  | Security & Regulatory Compliance | Regulatory Compliance | Security Assessment Review Meeting : week starting |  | Critical | Open |  |  | 28-Nov-25: To discuss with mr Sanjay to get clarifications on the points | [12 empty] | Security | OPEN | [10 empty] | Open | Open | Open
1034 | M354 | MOM | 2023-11-17 |  |  |  | NOC Operationalization | Resource Related | HP & Cisco OEM teams onboarding from 20th November'23. |  | Critical | Closed |  |  | 23-Sep-25: Approved shall be closed | [12 empty] | Network | Closed | CLOSED | 23-Sep-25: Approved shall be closed | FALSE | [5 empty] | 2025-09-23 | Artefacts not Required | Completed & Approved | Closed before june-2025 | Closed before june-2025
1035 | M355 | MOM | 2023-11-17 |  |  |  | NOC Operationalization | Documentation | Letter from all OEMs apart from Cisco & HP to be submitted by 22nd November'23 |  | Critical | Open |  |  | 23-Sep-25: Approved Artefacts to be Submitted | [12 empty] | Network | Closed | CLOSED | 23-Sep-25: Approved Artefacts to be Submitted | FALSE | [6 empty] | Artefacts Need to upload | Completed & Approved | Closed before june-2025 | Closed after June
1036 | M356 | MOM | 2023-11-17 |  |  |  | NOC Operationalization | Documentation | Letter from from Cisco & HP to be submitted by 24th November'23 |  | Critical | Open |  |  | 23-Sep-25: Approved Artefacts to be Submitted | [12 empty] | Network | Closed | CLOSED | 23-Sep-25: Approved Artefacts to be Submitted | FALSE | [6 empty] | Artefacts Need to upload | Completed & Approved | Closed before june-2025 | Closed after June
1037 | M357 | MOM | 2023-11-17 |  |  |  | NOC Operationalization | Documentation | Letter of confirmation for closure of issues with Tejas & Nokia on or before 30th November’23 |  | Critical | Open |  |  | 23-Sep-25: Approved Artefacts to be Submitted | [12 empty] | Network | Closed | CLOSED | 23-Sep-25: Approved Artefacts to be Submitted | FALSE | [6 empty] | Artefacts Need to upload | Completed & Approved | Closed before june-2025 | Closed after June
1038 | M358 | MOM | 2023-11-17 |  |  |  | NOC Operationalization | Meeting | Date for All OEMs Meeting |  | Critical | Open |  |  | 23-Sep-25: Approved shall be closed | [12 empty] | Network | Closed | CLOSED | 23-Sep-25: Approved shall be closed | FALSE | [5 empty] | 2025-09-23 | Artefacts not Required | Completed & Approved | Closed before june-2025 | Closed after June
1039 | M359 | MOM | 2023-11-17 |  |  |  | BSS | Resource Related | BSS-SME visit & extended stay for backlog clearance and sharing agenda prior to visit |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1040 | M36 | MOM | 2023-06-07 |  |  |  | GIS | Dashboards | Discuss and Develop Dashboard for GIS tool |  | NON-Critical | Open | Gtech | [14 empty] | Applications/Tools | OPEN | [10 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1041 | M360 | MOM | 2023-11-17 |  |  |  | NOC Operationalization | Documentation | Revert pending on 8 Notes(Undertaking) |  | Critical | Open |  |  | 23-Sep-25: Approved shall be closed | [12 empty] | Network | Closed | CLOSED | 23-Sep-25: Approved shall be closed | FALSE | [5 empty] | 2025-09-23 | Artefacts not Required | Completed & Approved | Closed before june-2025 | Closed after June
1042 | M361 | MOM | 2023-11-17 |  |  |  | Helpdesk | Resource Related | Dimensioning of Helpdesk calls |  | Critical | open |  |  | 24-Sep-25: Approved and shall be closed 11-Sep-25: Changed and operational Now | [12 empty] | Helpdesk (Contact Center) | Closed | [8 empty] | 2025-09-24 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\M117,126,728 | Completed & Approved | Closed before june-2025 | Closed after June
1043 | M362 | MOM | 2023-11-17 | P3 |  |  | NOC Operationalization | Documentation | Revert on 26 SOPS & O&M Handbook |  | Critical | Open |  |  | SOP agreed and signed off. O&M Handbook WIP | [12 empty] | Network | OPEN |  |  |  | Documentation | [6 empty] | Open | Open | Open
1044 | M363 | MOM | 2023-11-17 | P3 |  |  | NOC Operationalization | Documentation | Measurable KPI for individual TNOC team |  | Critical | Completed |  |  | NOC role KRA and KPI submitted to TFiber | [12 empty] | Network | Closed |  |  |  | Not related to delivery |  |  |  |  | 2025-09-24 | \\172.28.9.23\tnocreports\TNOC Manpower_CVs\NOC Resources Details & Roles | Completed & Approved | Closed before june-2025 | Closed after June
1045 | M364 | MOM | 2023-11-17 | P3 |  |  | NOC Operationalization | Resource Related | Service delivery & Service assurance Manager |  | Critical | Completed |  |  | Not part of RFP. Service Provisioning is being done by NOC team | [12 empty] | Network | Closed |  |  |  | Not related to delivery |  |  |  |  | 2025-09-19 | Artefacts not Required | Completed & Approved | Closed before june-2025 | Closed after June
1046 | M365 | MOM | 2023-11-17 | P3 |  |  | NOC Operationalization | Resource Related | Plan for Manpower augmentation to handle Infra Alarm in TNOC & field to finalize O&M |  | Critical | Completed |  |  | NOC manpower is deputed as per RFP and manpower report is shared with TFiber on weekly basis | [12 empty] | Network | Closed |  |  |  | Not related to delivery |  |  |  |  | 2025-09-19 | Artefacts not Required | Completed & Approved | Closed before june-2025 | Closed after June
1047 | M366 | MOM | 2023-11-17 |  |  |  | BSS | Dry Run | BSS product system readiness for usage |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1048 | M367 | MOM | 2023-11-17 |  |  |  | NOC Operationalization | Resource Related | Additional resources for fast tracking of project |  | Critical | Open |  |  | 23-Sep-25: Approved shall be closed | [12 empty] | Network | Closed | CLOSED | 23-Sep-25: Approved shall be closed | FALSE | [5 empty] | 2025-09-23 | Artefacts not Required | Completed & Approved | Closed before june-2025 | Closed after June
1049 | M368 | MOM | 2023-11-28 |  |  |  | NOC Operationalization | Meeting | L&T to communicate with OEMs and arrange a meeting on behalf of T-Fiber. 1. To seek evidence from L&T on the commitment from respective OEMs of BSS, OSS, NSO, GIS, GPON on closure of gaps identified so far, related to the operationalization of various systems along with firm dates for delivery from respective OEMs for the same. 2. L&T to provide a plan on how the NOC O&M will be handled with SOPs where relevant in the interim period. 3. How L&T transitions the systems from the interim to the final state without any business impact while ensuring data integrity. |  | Critical | Open |  |  | 23-Sep-25: Approved shall be closed | [12 empty] | Network | Closed | CLOSED | 23-Sep-25: Approved shall be closed | FALSE | [5 empty] | 2025-09-23 | Artefacts not Required | Completed & Approved | Closed before june-2025 | Closed after June
1050 | M369 | MOM | 2023-11-28 |  |  |  | Security & Regulatory Compliance | Regulatory Compliance | Fast-track track closure of Regulatory and security requirements along with SLA monitoring for the immediate start of Business related to Cell Tower, GI BB, GI ILL & VPN service delivery. |  | Critical | Open | [15 empty] | Security | OPEN | [10 empty] | Open | Open | Open
1051 | M37 | MOM | 2023-06-07 |  |  |  | GIS | User Experience | New validation Logic to be incorporated in DI tool - if Depth is zero and construction method is HDD/OT, Protection is required |  | NON-Critical | Open | Gtech | [14 empty] | Applications/Tools | OPEN | [10 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1052 | M370 | MOM | 2023-11-28 |  |  |  | NOC Operationalization | Demo | L&T to prepare and execute the next DRY run effectively. |  | Critical | Open |  |  | 23-Sep-25: Approved shall be closed | [12 empty] | Network | Closed | CLOSED | 23-Sep-25: Approved shall be closed | FALSE | [5 empty] | 2025-09-23 | Artefacts not Required | Completed & Approved | Closed before june-2025 | Closed after June
1053 | M371 | MOM | 2023-11-28 |  |  |  | NOC Operationalization | Documentation | L&T to develop a comprehensive presentation on product readiness and NOC operationalization schedule. |  | Critical | Completed |  |  | 23-Sep-25: Approved shall be closed | [12 empty] | Network | Closed | CLOSED | 23-Sep-25: Approved shall be closed | FALSE | [5 empty] | 2025-09-23 | Artefacts not Required | Completed & Approved | Closed before june-2025 | Closed after June
1054 | M372 | MOM | 2023-12-12 |  |  |  | Security & Regulatory Compliance | RMC meeting | Submit Acceptable Usage Policy document with suggested changes |  | Critical | Open | [15 empty] | Security | Closed | [8 empty] | 2025-10-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\NW-Security\M372_29-Oct-25.pdf | Closed | Closed After 14-Oct | Open
1055 | M373 | MOM | 2023-12-12 |  |  |  | Security & Regulatory Compliance | RMC meeting | Complete the configuration of CA signed SSL certificate |  | Critical | Open |  |  | 28-Nov-25: There are duplicate points; once the main point is closed, these duplicate points can be closed. | [12 empty] | Security | OPEN | [10 empty] | Open | Open | Open
1056 | M374 | MOM | 2023-12-12 |  |  |  | Security & Regulatory Compliance | RMC meeting | Concur with T-Fiber for annual external VAPT testing |  | Critical | Open |  |  | 28-Nov-25: VAPT is going on, once VAPT is done points will be closed | [12 empty] | Security | OPEN | [8 empty] | 2025-12-19 |  | Completed &Approved | Completed &Approved | Completed &Approved
1057 | M375 | MOM | 2023-12-12 |  |  |  | Security & Regulatory Compliance | RMC meeting | Submit Vulnerability Management Policy |  | Critical | Open |  |  | 28-Nov-25: VAPT is going on, once VAPT is done points will be closed | [12 empty] | Security | OPEN | [10 empty] | Open | Open | Open
1058 | M376 | MOM | 2023-12-12 |  |  |  | Security & Regulatory Compliance | RMC meeting | List and share the Security Policy documents and SOPS |  | Critical | Open |  |  | 28-Nov-25: Document preparation in progress once done points will be closed. Docs List is shared | [12 empty] | Security | OPEN | [10 empty] | Open | Open | Open
1059 | M377 | MOM | 2023-12-12 |  |  |  | Security & Regulatory Compliance | RMC meeting | Upload all RMC MoMs to the shared folder and share access |  | Critical | Open |  |  | 28-Nov-25: To discuss with mr Sanjay to get clarifications on the points | [12 empty] | Security | OPEN | [10 empty] | Open | Open | Open
1060 | M378 | MOM | 2023-12-12 |  |  |  | Security & Regulatory Compliance | RMC meeting | Submit Asset Management policy |  | Critical | Open |  |  | 28-Nov-25: Document preparation in progress once done points will be closed. | [12 empty] | Security | OPEN | [10 empty] | Open | Open | Open
1061 | M379 | MOM | 2023-12-12 |  |  |  | Security & Regulatory Compliance | RMC meeting | Submit onboarding/offboarding policy |  | Critical | Open |  |  | 28-Nov-25: Document preparation in progress once done points will be closed. | [12 empty] | Security | OPEN | [10 empty] | Open | Open | Open
1062 | M38 | MOM | 2023-06-15 |  |  |  | BSS | Resource Related | Billing Expert onboarding |  | Critical | Open | Billing | [14 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1063 | M380 | MOM | 2023-12-12 |  |  |  | Security & Regulatory Compliance | RMC meeting | Submit scope of work for External VAPT |  | Critical | Open |  |  | 28-Nov-25: VAPT is going on, once VAPT is done points will be closed | [12 empty] | Security | OPEN | [8 empty] | 2025-12-19 |  | Completed &Approved | Completed &Approved | Completed &Approved
1064 | M381 | MOM | 2023-12-12 |  |  |  | Security & Regulatory Compliance | RMC meeting | Collect Cryptography encryption model document from all OEMs |  | Critical | Open |  |  | 28-Nov-25: Gathering artifacts from other teams | [12 empty] | Security | OPEN | [10 empty] | Open | Open | Open
1065 | M382 | MOM | 2023-12-12 |  |  |  | Security & Regulatory Compliance | RMC meeting | Submit the revised undertaking for Tejas - Alepo and Nokia |  | Critical | Open |  |  | 28-Nov-25: Gathering artifacts from other teams | [12 empty] | Security | OPEN | [10 empty] | Open | Open | Open
1066 | M383 | MOM | 2023-12-12 |  |  |  | Security & Regulatory Compliance | RMC meeting | Provide compliance documents for all applications and devices |  | Critical | Open |  |  | 28-Nov-25: To discuss with mr Sanjay to get clarifications on the points | [12 empty] | Security | OPEN | [10 empty] | Open | Open | Open
1067 | M384 | MOM | 2023-12-12 |  |  |  | Security & Regulatory Compliance | RMC meeting | Submit document on Privilege management |  | Critical | Open |  |  | 28-Nov-25: Document preparation in progress once done points will be closed. | [12 empty] | Security | OPEN | [10 empty] | Open | Open | Open
1068 | M385 | MOM | 2023-12-12 |  |  |  | Security & Regulatory Compliance | RMC meeting | Submit password management policy |  | Critical | Open |  |  | 28-Nov-25: Document preparation in progress once done points will be closed. | [12 empty] | Security | OPEN | [10 empty] | Open | Open | Open
1069 | M386 | MOM | 2023-12-12 |  |  |  | Security & Regulatory Compliance | RMC meeting | Submit artefacts for all banners |  | Critical | Open |  |  | 28-Nov-25: Gathering artifacts from other teams | [12 empty] | Security | OPEN | [10 empty] | Open | Open | Open
1070 | M387 | MOM | 2023-12-12 |  |  |  | Security & Regulatory Compliance | RMC meeting | Submit internal/external, Trusted, untrusted zone checklist |  | Critical | Open | [15 empty] | Security | Closed | [8 empty] | 2025-10-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\NW-Security\M873_29-Oct-25.pdf | Closed | Closed After 14-Oct | Open
1071 | M388 | MOM | 2023-12-12 |  |  |  | Security & Regulatory Compliance | RMC meeting | Submit internal network policies details |  | Critical | Open |  |  | 28-Nov-25: Document preparation in progress once done points will be closed. | [12 empty] | Security | OPEN | [10 empty] | Open | Open | Open
1072 | M389 | MOM | 2023-12-12 |  |  |  | Security & Regulatory Compliance | RMC meeting | Submit SSL implementation report for all APIs |  | Critical | Open |  |  | 28-Nov-25: There are duplicate points; once the main point is closed, these duplicate points can be closed. | [12 empty] | Security | OPEN | [10 empty] | Open | Open | Open
1073 | M39 | MOM | 2023-06-15 |  |  |  | BSS | Handbook & SOPs | State of maturity of all Business process flows mentioned in the HLD |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1074 | M390 | MOM | 2023-12-12 |  |  |  | Security & Regulatory Compliance | RMC meeting | Submit Acceptable Usage Policy |  | Critical | Open | [15 empty] | Security | Closed | [8 empty] | 2025-10-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\NW-Security\M372_29-Oct-25.pdf | Closed | Closed After 14-Oct | Open
1075 | M391 | MOM | 2023-12-12 |  |  |  | Security & Regulatory Compliance | RMC meeting | Submit Security endpoints list of Infra, workstations |  | Critical | Open |  |  | 28-Nov-25: To discuss with mr Sanjay to get clarifications on the points | [12 empty] | Security | OPEN | [10 empty] | Open | Open | Open
1076 | M392 | MOM | 2023-12-12 |  |  |  | Security & Regulatory Compliance | RMC meeting | Submit SOP for security policies |  | Critical | Open |  |  | 28-Nov-25: There are duplicate points; once the main point is closed, these duplicate points can be closed. | [12 empty] | Security | OPEN | [10 empty] | Open | Open | Open
1077 | M393 | MOM | 2023-12-12 |  |  |  | Security & Regulatory Compliance | RMC meeting | Submit DR reports for all Applications |  | Critical | Open |  |  | 28-Nov-25: To discuss with mr Sanjay to get clarifications on the points | [12 empty] | Security | OPEN | [10 empty] | Open | Open | Open
1078 | M394 | MOM | 2023-12-12 |  |  |  | Security & Regulatory Compliance | RMC meeting | Submit attendance list for security awareness trainings |  | Critical | Open |  |  | 28-Nov-25: To discuss with mr Sanjay to get clarifications on the points | [12 empty] | Security | OPEN | [10 empty] | Open | Open | Open
1079 | M395 | MOM | 2023-12-12 |  |  |  | Security & Regulatory Compliance | RMC meeting | Finalize backup duration and frequency, and provide utilization report |  | Critical | Open |  |  | 28-Nov-25: To discuss with mr Sanjay to get clarifications on the points | [12 empty] | Security | OPEN | [10 empty] | Open | Open | Open
1080 | M396 | MOM | 2023-12-12 |  |  |  | Security & Regulatory Compliance | RMC meeting | Submit a report capturing online and offline storage status |  | Critical | Open |  |  | 28-Nov-25: To discuss with mr Sanjay to get clarifications on the points | [12 empty] | Security | OPEN | [10 empty] | Open | Open | Open
1081 | M397 | MOM | 2023-12-12 |  |  |  | Security & Regulatory Compliance | RMC meeting | Finalize Technology Risk Management checklist |  | Critical | Open |  |  | 28-Nov-25: There are duplicate points; once the main point is closed, these duplicate points can be closed. | [12 empty] | Security | OPEN | [10 empty] | Open | Open | Open
1082 | M398 | MOM | 2023-12-12 |  |  |  | Security & Regulatory Compliance | RMC meeting | Further audit and VAPT by Allied Boston |  | Critical | Open |  |  | 28-Nov-25: VAPT is going on, once VAPT is done points will be closed. Audit done by Allied Boston | [12 empty] | Security | OPEN | [8 empty] | 2025-12-19 |  | Completed &Approved | Completed &Approved | Completed &Approved
1083 | M399 | MOM | 2023-12-15 |  |  |  | WFM | Mobile Application | Arrange a demonstration of WFM Tool for field operations |  | Critical | Open |  |  | 15-Nov-25:Multiple demonstrations of the WFM application have been conducted for Package A, along with three months of training provided to the field team. Additionally, for Packages B and C, demonstration | s w | ere c | ondu | cted thre | imes each | [7 empty] | Applications/Tools | [5 empty] | e t | [5 empty] | Open | Open | Open
1084 | M4 | MOM | 2023-03-27 |  |  |  | BSS | Service provisioning | BSS-based provisioning for regularizing 3000 GI through NOC BSS, with scalability to 30,000 GIs. |  | Critical | Open | OSS Dashboards | [14 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1085 | M40 | MOM | 2023-06-19 |  |  |  | GIS | User Experience | Download active port connectivity details |  | Critical | Open | Gtech |  | 15-Nov-25: Link Trace Report Download | [12 empty] | Applications/Tools | OPEN | [10 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1086 | M400 | MOM | 2023-12-15 |  |  |  | WFM | Mobile Application | Clarity on GPS tracking availability and battery consumption |  | Critical | Open |  |  | 15-Nov-25: Real MOM Point :- WFM Mobile App Features: L&T to provide clarity on GPS tracking availability, polling frequency, photo upload feature, file size limitations, and supported Android and iOS vers | ion | s. Re | mark | s :- Dur | the demo, i |  | t w | as |  |  | clar | ified that person tracking is based on GPS available in the mobile application. Battery consumption depends on the device’s battery condition. Testing confirmed minimal variance even when the application runs throughout the day. | Applications/Tools | OPEN |  |  |  |  | ing | [5 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1087 | M401 | MOM | 2023-12-15 |  |  |  | WFM | Mobile Application | WFM Mobile App Features: L&T to provide clarity on GPS tracking availability, polling frequency, photo upload feature, file size limitations, and supported Android and iOS versions. |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1088 | M402 | MOM | 2023-12-15 |  |  |  | WFM | Mobile Application | Clarify on photo upload feature and impact on mobile phone memory |  | NON-Critical | Open |  |  | 15-Nov-25: Real MOM Point :- WFM Mobile App Features: L&T to provide clarity on GPS tracking availability, polling frequency, photo upload feature, file size limitations, and supported Android and iOS vers | ion | s. R | emar | ks:- It | explained t |  | hat | th |  |  | e im | age upload functionality is integrated into the application, allowing users to upload images directly from the app or from their gallery. All images are stored on application servers. | Applications/Tools | OPEN |  |  |  |  | was | [5 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1089 | M403 | MOM | 2023-12-15 |  |  |  | WFM | Mobile Application | Clarity on offline data storage feature availability |  | NON-Critical | Open |  |  | 15-Nov-25: Real MOM Point :- WFM Mobile App Features: L&T to provide clarity on GPS tracking availability, polling frequency, photo upload feature, file size limitations, and supported Android and iOS vers | ion | s. Re | mark | s:- The | o also clari |  | fie | d t |  |  | hat | if a user is offline, they can capture photographs and upload them later when online. The gallery uploads feature supports this functionality. 11-7-2025:- Offline data, such as images and documents, can be uploaded either from the mobile gallery or directly using the camera. To support the storage of LIDAR survey data and GIS images, an 80 TB NAS storage system has already been deployed at the NOC Data Center | Applications/Tools | OPEN |  |  |  |  | dem | [5 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1090 | M404 | MOM | 2023-12-15 |  |  |  | WFM | Mobile Application | Clarity on file size limitations during upload |  | NON-Critical | Open |  |  | 15-Nov-25: Real MOM Point :- WFM Mobile App Features: L&T to provide clarity on GPS tracking availability, polling frequency, photo upload feature, file size limitations, and supported Android and iOS vers | ion | s. Re | mark | s :- Duri | demo it has |  | com | mun |  |  | icat | ed the application compresses images captured by the camera before sending them to the server, regardless of their original size. | Applications/Tools | OPEN |  |  |  |  | ng | [5 empty] | Open | Open | Open
1091 | M405 | MOM | 2023-12-15 |  |  |  | WFM | Mobile Application | The urgency for L&T to demonstrate the WFM tool for field operations and to provide detailed information on its features and capabilities. |  | NON-Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1092 | M406 | MOM | 2023-12-15 |  |  |  | WFM | Mobile Application | Clarify the usage differences between GIS and WFM mobile apps |  | NON-Critical | Open |  |  | 15-Nov-25: The document outlining the differences between the GIS and WFM mobile applications has been prepared and demonstrated in the TFIBER Core Room. There are no pending actions for this item | [12 empty] | Applications/Tools | OPEN | [9 empty] | #N/A | Closed | Closed | Open
1093 | M407 | MOM | 2023-12-15 |  |  |  | WFM | Mobile Application | Security Assurance: L&T to provide the NDA signed with M/S Lepton, assure API security, and share the contract copy. |  | NON-Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1094 | M408 | MOM | 2023-12-15 |  |  |  | WFM | Mobile Application | Geo-fencing: L&T to explain how geo-fencing shall work for a fiber route and how it will be assigned for Mandal and GP locations. |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1095 | M409 | MOM | 2023-12-15 |  |  |  | WFM | Mobile Application | Ticket Allocation: L&T to start manual ticket allocation and freeze the process for node and link ticket allocation. |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1096 | M41 | MOM | 2023-06-19 |  |  |  | GIS | User Experience | Real-time sync of topology details from OSS |  | Critical | Open | Gtech | [14 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1097 | M410 | MOM | 2023-12-15 |  |  |  | WFM | Mobile Application | Ticket Allocation: L&T to start manual ticket allocation and freeze the process for node and link ticket allocation. |  | NON-Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1098 | M411 | MOM | 2023-12-15 |  |  |  | WFM | Mobile Application | Use of document forms from the Operations Handbook by the WFM app |  | Critical | Open |  |  | 15-Nov-25: The WFM SOP has been created, demonstrated, submitted, and approved, along with the Interim O&M activities completed in April 2024 | [12 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1099 | M412 | MOM | 2023-12-15 |  |  |  | WFM | Mobile Application | Summary Dashboards/Management Reports: L&T to provide inputs based on Operations best practices for weekly/monthly management reports from the WFM package. |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1100 | M413 | MOM | 2023-12-19 |  |  |  | WFM | Mobile Application | WFM Tool Demonstration: L&T to arrange a demonstration of the WFM tool usage for field operations soon. |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1101 | M414 | MOM | 2023-12-19 |  |  |  | BSS | Improvement | Investigate and expedite the issue on slowness of BSS Test Environment |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1102 | M415 | MOM | 2023-12-19 |  |  |  | BSS | Dashboards | Explore web-based Analytic tools for performance benchmarking |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1103 | M416 | MOM | 2023-12-19 |  |  |  | BSS | Compliance | Review the status of points with "No Change" status and obtain T-Fiber's consensus before rendering items as "Closed". |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1104 | M417 | MOM | 2023-12-19 |  |  |  | BSS | Improvement | Verify the feature allowing multiple locations per customer |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1105 | M418 | MOM | 2023-12-19 |  |  |  | BSS | Improvement | Cross-reference user experience feedback with related points |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1106 | M419 | MOM | 2023-12-19 |  |  |  | BSS | SMS Integration | Implement notification of SMS dispatch in the CSP and provision of a link in SMS to the CSP page allowing T-Fiber user to Approve or Reject |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1107 | M42 | MOM | 2023-06-19 |  |  |  | GIS | User Experience | automate active connectivity within site with logical link name populated from OSS |  | Critical | Open | Gtech |  | 15-Nov-25: Based on discussions with the OSS and GIS teams, integration is not feasible, and automation of connectivity cannot be implemented, 11th July 2025, a discussion is needed with Siva Sir to explor | e i | n-hou | se s | olution p | ibilities. | [7 empty] | Applications/Tools | [5 empty] | oss | [5 empty] | Open | Open | Open
1108 | M420 | MOM | 2023-12-19 |  |  |  | BSS | Product Demo | Provide a demo to showcase product catalogue configurability |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1109 | M421 | MOM | 2023-12-19 |  |  |  | BSS | Product Demo | Provide a demo of Backend Validation and share a document with the steps for validation |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1110 | M422 | MOM | 2023-12-19 |  |  |  | BSS | Product Demo | Address the delay in data load due to system limitation in the production instance |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1111 | M423 | MOM | 2023-12-19 |  |  |  | BSS | Product Demo | Define a benchmark for page loading, login, browsing, and payment scenarios |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1112 | M424 | MOM | 2023-12-19 |  |  |  | BSS | Product Demo | Review the status of Point no. 52 from Dry Run 1 with a demo |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1113 | M425 | MOM | 2023-12-19 |  |  |  | BSS | Product Demo | Ensure uniform colour coding across the website |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1114 | M426 | MOM | 2023-12-19 |  |  |  | BSS | Product Demo | Address the change of website heading for customer dashboards prior to moving into production |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1115 | M427 | MOM | 2023-12-19 |  |  |  | BSS | Product Demo | Arrange for a demo of current products since significant time has passed since the Dry Run |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1116 | M428 | MOM | 2023-12-19 |  |  |  | BSS | Product Demo | Show the flows of Dark Fiber with BSS and WFM |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1117 | M429 | MOM | 2023-12-19 |  |  |  | BSS | Product Demo | Hold discussions for T-Cell product integration with respective OEMs |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1118 | M43 | MOM | 2023-06-19 |  |  |  | GIS | Functional AT Plan | TPA to validate active-active connectivity |  | Critical | Open | Gtech | [14 empty] | Applications/Tools | OPEN | [10 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1119 | M430 | MOM | 2023-12-19 |  |  |  | BSS | Product Demo | Complete T-Cell, T-VPN, and GI-ILL |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1120 | M431 | MOM | 2023-12-19 |  |  |  | BSS | Product Demo | Address delay in support for enabling newer products |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1121 | M432 | MOM | 2023-12-19 |  |  |  | BSS | Product Demo | Complete T-Cell, T-VPN and GI-ILL on priority before impending visit to NOC by Hon’ Minister |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1122 | M433 | MOM | 2023-12-19 |  |  |  | BSS | Product Demo | Include headers and check across pages in the CSP |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1123 | M434 | MOM | 2023-12-19 |  |  |  | BSS | Product Demo | Start working on the CSP for listed schools |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1124 | M435 | MOM | 2023-12-19 |  |  |  | BSS | Product Demo | Clarify scenario where GP location is feasible, whereas the feasibility of end customer location is yet to be ascertained |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1125 | M436 | MOM | 2023-12-19 |  |  |  | BSS | Product Demo | Include feasibility logic for S1, and S2 splitters |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1126 | M437 | MOM | 2023-12-19 |  |  |  | BSS | Product Demo | Present the logic for Bandwidth feasibility in the backhaul, network capacity planning to be progressively provisioned, and operationalised |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1127 | M438 | MOM | 2023-12-19 |  |  |  | BSS | Improvement | Address immediate need for NSO inventory to be part of the final solution for feasibility |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1128 | M439 | MOM | 2023-12-19 |  |  |  | BSS | Resource Related | Ask Segment Head, L&T to discuss with EVP, T-Fiber on the adequacy of NMS works resources |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1129 | M44 | MOM | 2023-06-19 |  |  |  | GIS | User Experience | Add card/module/slot level details |  | Critical | Open | Gtech |  | 15-Nov-25: Duplicate with Point- 90 | [12 empty] | Applications/Tools | [11 empty] | Open | Open | Open
1130 | M440 | MOM | 2023-12-19 |  |  |  | BSS | Improvement | Clarify that Repository Module for Uploading of MSA, CAF form and other documents of a particular customer is in CRM, not in CSP |  | NON-Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1131 | M441 | MOM | 2023-12-19 |  |  |  | BSS | Integration | Incorporate advanced features in the CSP's WhatsApp Integration |  | NON-Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1132 | M442 | MOM | 2023-12-19 |  |  |  | BSS | User Experience | On-board an internal UI/UX resource and engage them with T-Fiber |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1133 | M443 | MOM | 2023-12-28 |  |  |  | BSS | Product Demo | Complete T-VPN and T-DILL |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1134 | M444 | MOM | 2023-12-28 |  |  |  | BSS | Product Demo | Complete basic products by |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1135 | M445 | MOM | 2023-12-28 |  |  |  | BSS | Product Demo | Complete GI-BB, T-Cell, Dark Fiber |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1136 | M446 | MOM | 2023-12-28 |  | OSS | OSS | OSS | HPSM | Remove duplicate TroubleTicket issue |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | confirmation reuired from NOC Team | Completed With Artifacts | FALSE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1137 | M447 | MOM | 2023-12-28 |  |  |  | Security & Regulatory Compliance | Regulatory Compliance | Finalize scope of external audit in consultation with T-Fiber |  | Critical | Open |  |  | 28-Nov-25: VAPT is going on, once VAPT is done points will be closed. Audit done by Allied Boston | [12 empty] | Security | OPEN | [8 empty] | 2025-12-19 |  | Completed &Approved | Completed &Approved | Completed &Approved
1138 | M448 | MOM | 2023-12-28 |  |  |  | Security & Regulatory Compliance | Regulatory Compliance | Conduct external audit |  | Critical | Open |  |  | 28-Nov-25: VAPT is going on, once VAPT is done points will be closed. Audit done by Allied Boston | [12 empty] | Security | OPEN | [8 empty] | 2025-12-19 |  | Completed &Approved | Completed &Approved | Completed &Approved
1139 | M449 | MOM | 2023-12-28 |  |  |  | Helpdesk | Training | Improve maturity of Helpdesk to handle incoming calls |  | Critical | Open |  |  | 24-Sep-25: Approved and shall be closed | [12 empty] | Helpdesk (Contact Center) | Closed | [8 empty] | 2025-09-24 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\M114,722,134 | Completed & Approved | Closed before june-2025 | Closed after June
1140 | M45 | MOM | 2023-06-19 |  |  |  | GIS | User Experience | Ensure Topology name uniqueness |  | Critical | Open | Gtech |  | 15-Nov-25:Duplicate with Point- 128 | [12 empty] | Applications/Tools | [11 empty] | Open | Open | Open
1141 | M450 | MOM | 2023-12-28 |  | OSS | OSS | OSS | HPSM | Freeze the process for node ticket allocation |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | 0 | Completed With Artifacts | TRUE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1142 | M451 | MOM | 2023-12-28 |  |  |  | NOC Operationalization | Action Points | Cover all requirements from workshops, RFP, and discussions in the roadmap |  | Critical | Open |  |  | 23-Sep-25: Approved shall be closed | [12 empty] | Network | Closed | CLOSED | 23-Sep-25: Approved shall be closed | FALSE | [5 empty] | 2025-09-23 | Artefacts not Required | Completed & Approved | Closed before june-2025 | Closed after June
1143 | M452 | MOM | 2023-12-28 |  | OSS | OSS | OSS | Action Points | Generate SLA reports automatically from NOC |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | 0 | Completed With Artifacts | TRUE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1144 | M453 | MOM | 2023-12-28 |  |  |  | NOC Operationalization | Action Points | Submit a Roadmap covering all requirements raised in all Workshops, the RFP requirements, the 396-point Worksheet maintained by L&T, and all the discussions |  | Critical | Open |  |  | 23-Sep-25: Approved shall be closed | [12 empty] | Network | Closed | CLOSED | 23-Sep-25: Approved shall be closed | FALSE | [5 empty] | 2025-09-23 | Artefacts not Required | Completed & Approved | Closed before june-2025 | Closed after June
1145 | M454 | MOM | 2023-12-28 |  |  |  | NOC Operationalization | Action Points | Explore templates from BBNL NOC for invoice settlement |  | Critical | Open |  |  | 23-Sep-25: NON Critical to be reviewd later | [12 empty] | Network | OPEN | OPEN | 23-Sep-25: NON Critical to be reviewed later | TRUE | [7 empty] | Open | Open | Open
1146 | M455 | MOM | 2023-12-28 |  | OSS | OSS | OSS | HPSM | Ensure cross-domain RCA, SIA, Helpdesk and Network Service Topology are in place |  | Critical | Open |  |  | Inhouse solution | [12 empty] | Applications/Tools | OPEN | Pending | OPEN | FALSE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1147 | M456 | MOM | 2023-12-28 |  |  |  | NOC Operationalization | Action Points | Deliver NOC before the end of T3 |  | Critical | Open |  |  | 16-Oct-25: Covered in NOC go-live plan | [12 empty] | Network | OPEN | Duplicate | 16-Oct-25: Covered in NOC go-live plan | FALSE | [7 empty] | Open | Open | Open
1148 | M457 | MOM | 2024-01-04 |  | OSS | OSS | OSS | HPSM | Implement ticket tracking with OSS Service Manager |  | Critical | Open | [15 empty] | Applications/Tools | Closed | need to check | Completed With Artifacts | FALSE | [5 empty] | 2025-11-18 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\OSS\52 Artefcats_18112025 | Closed after 14-Nov-25 | Closed after 14-Nov-25 | Completed but Verification undrer Process
1149 | M458 | MOM | 2024-01-04 |  |  |  | BSS | Product category | Complete T-DILL & T-VPN |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1150 | M459 | MOM | 2024-01-04 |  |  |  | BSS | Product category | Discuss network design for T-DILL with AD-P&E, T-Fiber & IPMPLS-SME |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1151 | M46 | MOM | 2023-06-19 |  |  |  | GIS | User Experience | BoQ feature to download passive/active devices separately |  | Critical | Open | Gtech | [14 empty] | Applications/Tools | OPEN | [10 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1152 | M460 | MOM | 2024-01-04 |  |  |  | NSO | Service Solution | Submit a plan for the completion of the 28 services, along with dependencies |  | Critical | Open |  |  | 19-12-2025:- Plan for services identified. | [7 empty] | Not Started |  |  |  |  | Applications/Tools | OPEN |  |  |  |  | Need Clarity | [5 empty] | Open | Open | Open
1153 | M461 | MOM | 2024-01-04 |  |  |  | BSS | Product category | Conduct a product discussion audit |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1154 | M462 | MOM | 2024-01-04 |  |  |  | BSS | Product category | Submit evidence on commitment from OEMs for integration of various systems with BSS |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1155 | M463 | MOM | 2024-01-04 |  |  |  | NSO | Service Solution | Submit a road map for the completion of the 28 services and all variants |  | Critical | Open |  |  | 19-12-2025:- Plan for services identified.same as above | [7 empty] | Not Started |  |  |  |  | Applications/Tools | OPEN |  |  |  |  | Need Clarity | [5 empty] | Open | Open | Open
1156 | M464 | MOM | 2024-01-04 |  |  |  | NSO | Service Solution | Initiate weekly meetings and share progress updates |  | Critical | Open |  |  | 29-dec-2025: Need discussion/BSS logic | [7 empty] | Not Started |  |  |  |  | Applications/Tools | OPEN |  |  |  |  | Need Clarity | [5 empty] | Open | Open | Open
1157 | M465 | MOM | 2024-01-04 |  |  |  | BSS | Product category | Finalize network design and initiate the implementation of Mandal-to-Mandal and Mandal-to-GP dark fiber process |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1158 | M466 | MOM | 2024-01-04 |  |  |  | BSS | Product category | Prepare for mock audit regarding bill desk integration and prepare a road map for the dry run of T-DILL & T-VPN |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1159 | M467 | MOM | 2024-01-04 |  |  |  | BSS | Product category | Finalize details of services of T3 & T4 |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1160 | M468 | MOM | 2024-01-04 |  | OSS | OSS | OSS | Service Solution | Resolve discrepancies in readiness status of Fault Management, Network Performance Management Security Management, Regulatory Compliances, Service Delivery- Feasibility, DR readiness, and Technical Helpdesk |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | 0 | OPEN | TRUE | [7 empty] | Open | Open | Open
1161 | M469 | MOM | 2024-01-04 |  |  |  | NOC Operationalization | O&M Strategy | Achieve readiness of all 'T0' NOC functions |  | Critical | Open |  |  | 23-Sep-25: Approved shall be closed | [12 empty] | Network | Closed | CLOSED | 23-Sep-25: Approved shall be closed | FALSE | [5 empty] | 2025-09-23 | Artefacts not Required | Completed & Approved | Closed before june-2025 | Closed after June
1162 | M47 | MOM | 2023-06-19 |  |  |  | GIS | User Experience | Bulk Feasibility closure case reports from GIS |  | Critical | Open | Gtech |  | To fulfill this requirement, an external feasibility application or tool is needed, as it cannot be achieved within the GIS application, 11 July 2025:- TFIBER is not agreed, asked to take with L&T upper ma | nag | ement | [10 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1163 | M470 | MOM | 2024-01-04 |  |  |  | NOC Operationalization | O&M Strategy | Submit details of remaining services of T3 & T4 |  | Critical | Open |  |  | 16-Oct-25: Covered in BSS Operationalization | [12 empty] | Network | OPEN | Duplicate | 16-Oct-25: Covered in BSS Operationalization | FALSE | [7 empty] | Open | Open | Open
1164 | M471 | MOM | 2024-01-04 |  |  |  | NOC Operationalization | O&M Strategy | Start daily meetings and share progress updates |  | Critical | Open |  |  | 23-Sep-25: Approved shall be closed | [12 empty] | Network | Closed | CLOSED | 23-Sep-25: Approved shall be closed | FALSE | [5 empty] | 2025-09-23 | Artefacts not Required | Completed & Approved | Closed before june-2025 | Closed after June
1165 | M472 | MOM | 2024-01-04 |  |  |  | BSS | Product category | Ensure all 29 BSNL locations are loaded for lead to order presentation |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1166 | M473 | MOM | 2024-01-04 |  |  |  | BSS | Product category | Submit confirmation responses along with product notes on all raised points |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1167 | M474 | MOM | 2024-01-05 |  |  |  | BSS | Product category | Review and finalize the Unique ID code convention for various attributes |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1168 | M475 | MOM | 2024-01-05 |  |  |  | BSS | Product category | Provide demo on Circuit ID generation process and integrate it in BSS |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1171 | M478 | MOM | 2024-01-05 |  |  |  | NSO | Service provisioning | Make A&O independent of BSS for generating Circuit ID |  | Critical | Open |  |  | 29-12-2025:- Circuit ID is given by BSS as input | [7 empty] | Completed |  |  |  |  | Applications/Tools | OPEN |  |  |  |  | BSS 13/03/2026 : Attach proof of client mail subject (Location ID and Circuit ID) & BSS and NSO Circuit Id Service Order Screenshot | Pending |  | 16/03/2026 |  |  | Open | Open | Open
1170 | M477 | MOM | 2024-01-05 |  |  |  | NSO | Service provisioning | Ensure GUI interface to initiate the order from NSO directly |  | Critical | Open |  |  | 29-dec-2025: Need discussion | [7 empty] | Completed |  |  |  |  | Applications/Tools | OPEN | [5 empty] | Pending |  | 2026-12-03 |  |  | Open | Open | Open
1172 | M479 | MOM | 2024-01-05 |  |  |  | NSO | Service provisioning | Circuit ID should distinguish origin system if a new front-end system is introduced |  | Critical | Open |  |  | 29-12-2025:- Circuit ID is given by BSS as input | [7 empty] | Completed |  |  |  |  | Applications/Tools | OPEN |  |  |  |  | BSS 13/03/2026 : Attach proof of client mail subject (Location ID and Circuit ID) & BSS and NSO Circuit Id Service Order Screenshot | Pending |  | 16/03/2026 |  |  | Open | Open | Open
1174 | M480 | MOM | 2024-01-05 |  |  |  | NSO | Service provisioning | Ensure Circuit ID isn't limited to 6/8 digits; it should follow the industry-recommended approach |  | Critical | Open |  |  | 29-12-2025:- Circuit ID is given by BSS as input | [7 empty] | Completed |  |  |  |  | Applications/Tools | OPEN |  |  |  |  | BSS 13/03/2026 : Attach proof of client mail subject (Location ID and Circuit ID) & BSS and NSO Circuit Id Service Order Screenshot | Pending |  | 16/03/2026 |  |  | Open | Open | Open
1173 | M48 | MOM | 2023-06-19 |  |  |  | GIS | User Experience | Route path identification through Google |  | Critical | Open | Gtech | [14 empty] | Applications/Tools | OPEN | [10 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1574 | M840 | MOM | 2023-11-03 |  |  |  | NSO | Service Delivery | Define the Code for Circuit type , Customer type , customer service type etc in single format |  | Critical | Open |  |  | 29-dec-2025: Need discussion | [7 empty] | Completed |  |  |  |  | Applications/Tools | OPEN |  |  |  |  | BSS 13/03/2026 : Attach proof of client mail subject (Location ID and Circuit ID) & BSS and NSO Circuit Id Service Order Screenshot | Pending |  | 16/03/2026 |  |  | Open | Open | Open
1175 | M481 | MOM | 2024-01-05 |  |  |  | BSS | Product category | Provide option to add new Customer ID during onboarding a new customer |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1176 | M482 | MOM | 2024-01-05 |  |  |  | BSS | Product category | Proceed with Payment approach Option 3 including one-time and recurring invoice generation |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1177 | M483 | MOM | 2024-01-05 |  |  |  | BSS | Product category | If purchase order and CAF are already loaded in the CRM and mapped with customer account, the CAF generation and approval process should be skipped |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1178 | M484 | MOM | 2024-01-05 |  |  |  | BSS | Billing Related | L&T and NMSworks to conduct a detailed training session on operational activities of the Billing module post invoice generation |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1179 | M485 | MOM | 2024-01-05 |  |  |  | BSS | Integration | Offer option to perform manual assignment and auto-assignment of Task Tickets |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1180 | M486 | MOM | 2024-01-05 |  |  |  | BSS | Dry Run | Demonstrate the complete Buyer and Seller journey |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1181 | M487 | MOM | 2024-01-05 |  |  |  | BSS | Design & Documentation | Ensure workflows/activities carried outside the BSS system are captured and mapped in BSS process flows |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1182 | M488 | MOM | 2024-01-05 |  |  |  | BSS | Billing Related | Introduce new column in the invoice template to distinguish billing items as ONE TIME or RECURRING |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1183 | M489 | MOM | 2024-01-05 |  |  |  | BSS | Billing Related | Review the solution of automatic QR code generation integration with Clear Tax or any other third party portal |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1184 | M49 | MOM | 2023-06-19 |  |  |  | GIS | User Experience | Network portal search functionality for objects |  | Critical | Open | Gtech | [14 empty] | Applications/Tools | OPEN | [10 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1185 | M490 | MOM | 2024-01-05 |  |  |  | BSS | Billing Related | Pending changes suggested by the Finance Director should be incorporated into the invoice template |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1186 | M491 | MOM | 2024-01-05 |  |  |  | BSS | Billing Related | Onboard Pioneer and start generating bills |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1187 | M492 | MOM | 2024-01-05 |  |  |  | BSS | Billing Related | Provide a detailed approach on how BSS is integrated with Bill Desk |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1188 | M493 | MOM | 2024-01-05 |  |  |  | BSS | Billing Related | Finalize bill desk integration-related final solution documents covering aspects suggested by Assistant Director-P&E, T-Fiber |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1189 | M494 | MOM | 2024-01-05 |  |  |  | BSS | Billing Related | Pending discussions from October’23 regarding bill desk integration should be completed |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1190 | M495 | MOM | 2024-01-05 |  |  |  | BSS | Design Features | Schedule a separate session with OEMs regarding Ticketing process through OSS/BSS referring to the current design template |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1191 | M496 | MOM | 2024-01-18 |  |  |  | BSS | Design Features | Finalize the Unique ID code convention for various attributes |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1192 | M497 | MOM | 2024-01-18 |  |  |  | BSS | Design Features | Integrate Circuit ID generation process in BSS |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1193 | M498 | MOM | 2024-01-18 |  |  |  | BSS | Design Features | Discuss and define a new naming convention for Circuit ID |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1194 | M499 | MOM | 2024-01-18 |  |  |  | BSS | Design Features | Review direct order through GUI interface |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1195 | M5 | MOM | 2023-03-27 |  |  |  | NSO | Full NOC Readiness | variance in L2 & L3, requiring time to understand along with NSO & OSS SMEs |  | Critical | Open | OSS Dashboards |  | 29-dec-2025: Need discussion | [7 empty] | Not Started |  |  |  |  | Applications/Tools | OPEN |  |  |  |  | Need Clarity | [5 empty] | Open | Open | Open
1196 | M50 | MOM | 2023-06-19 |  |  |  | GIS | User Experience | GIS function for bulk feasibility report |  | Critical | Open | Gtech |  | 15-Nov-25:To fulfill this requirement, an external feasibility application or tool is needed, as it cannot be achieved within the GIS application,11 July 2025:- TFIBER is not agreed, asked to take with L&T | up | per m | anag | ement | [8 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1197 | M500 | MOM | 2024-01-18 |  |  |  | BSS | Design Features | Make dependency of A&O for generating Circuit ID independent of BSS |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1198 | M501 | MOM | 2024-01-18 |  |  |  | BSS | Design Features | Circuit ID should distinguish the origin if a new front-end system is introduced |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1199 | M502 | MOM | 2024-01-18 |  |  |  | BSS | Design Features | Include option to introduce new Customer ID when onboarding a new customer |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1200 | M503 | MOM | 2024-01-18 |  |  |  | BSS | Design Features | Transition from Excel-based format to live data for Lit-up and other relevant data |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1201 | M504 | MOM | 2024-01-18 |  |  |  | BSS | Design Features | Capture whether the network is linear or ring based |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1202 | M505 | MOM | 2024-01-18 |  |  |  | BSS | Design Features | Review and finalize the definition of 'Ready for Service' |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1203 | M506 | MOM | 2024-01-18 |  |  |  | BSS | Design Features | Implement user access control for converting from RFO to RFS in BSS |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1204 | M507 | MOM | 2024-01-18 |  |  |  | BSS | Design Features | Use terms from the industry library for representing 'Ready for Service', etc. |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1205 | M508 | MOM | 2024-01-18 |  |  |  | BSS | Design Features | Retry the implementation of the Mandal-to-Mandal and Mandal-to-GP dark fiber process |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1206 | M509 | MOM | 2024-01-18 |  |  |  | BSS | Design Features | Integrate with GIS for live data capturing for feasibility check |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1207 | M51 | MOM | 2023-06-19 |  |  |  | GIS | User Experience | building logic / intelligence to populate the relevant information in the BoQ, presently available as a dump. |  | Critical | Open | Gtech | [14 empty] | Applications/Tools | OPEN | [10 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1208 | M510 | MOM | 2024-01-18 |  |  |  | BSS | Design Features | Correct and finalize the changes suggested in the Lead page |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1209 | M511 | MOM | 2024-01-18 |  |  |  | BSS | Design Features | Enable communication to customers via Quote Tab in system |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1210 | M512 | MOM | 2024-01-18 |  |  |  | BSS | Design Features | Review Service order Form and related attributes |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1211 | M513 | MOM | 2024-01-18 |  |  |  | BSS | Design Features | Implement immediate Dark Fiber service for Mandal to GP and Mandal to Mandal |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1212 | M514 | MOM | 2024-01-18 |  |  |  | BSS | Design Features | Bring the approach for Bulk Feasibility into use |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1213 | M515 | MOM | 2024-01-18 |  |  |  | BSS | Design Features | Confirm the list of personnel who will be part of BSS operations |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1214 | M516 | MOM | 2024-01-18 |  |  |  | BSS | Design Features | Solve the issue of Document repository not being tagged with the order number |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1215 | M517 | MOM | 2024-01-18 |  |  |  | BSS | Design Features | Present a lead to order and GIS integration way forward for BSNL locations |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1216 | M518 | MOM | 2024-01-18 |  |  |  | BSS | Design Features | Confirm the timeline for GI-BB |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1217 | M519 | MOM | 2024-01-18 |  |  |  | BSS | Design Features | Confirm the timeline for T-Cell |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1218 | M52 | MOM | 2023-06-19 |  |  |  | GIS | Integration | GIS integration with WFM tool |  | Critical | Open | Gtech | [14 empty] | Applications/Tools | OPEN | [10 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1219 | M520 | MOM | 2024-01-18 |  |  |  | BSS | Design Features | Discuss with T-Fiber regarding Route Mode and Bridge Mode for Internet Leased Line product |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1220 | M521 | MOM | 2024-01-24 |  |  |  | NSO | O&M Strategy | Complete basic six products and field O&M |  | Critical | Open |  |  | 29-dec-2025: Need discussion | [7 empty] | Not Started |  |  |  |  | Applications/Tools | OPEN |  |  |  |  | Jyothi | [5 empty] | Open | Open | Open
1221 | M522 | MOM | 2024-01-24 |  |  |  | BSS | Design & Documentation | Complete delivery of 24 variant products |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1222 | M523 | MOM | 2024-01-24 |  |  |  | BSS | Design & Documentation | Submit documentation for each of 6 products with respect to flow, regulatory, connectivity to other elements signed off with T-Fiber |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1223 | M524 | MOM | 2024-01-24 |  |  |  | NOC Operationalization | Design & Documentation | Provide final timeline for all conditional approvals & workshop tracker and detailed scope document |  | Critical | Open |  |  | 23-Sep-25: Approved shall be closed | [12 empty] | Network | Closed | CLOSED | 23-Sep-25: Approved shall be closed | FALSE | [5 empty] | 2025-09-23 | Artefacts not Required | Completed & Approved | Closed before june-2025 | Closed after June
1224 | M525 | MOM | 2024-01-24 |  | OSS | OSS | OSS | Design Features | Present the readiness of service inventory module |  | Critical | Open |  |  | Inhouse solution | [12 empty] | Applications/Tools | OPEN |  | Duplicate | FALSE | [7 empty] | Open | Open | Open
1225 | M526 | MOM | 2024-01-24 |  |  |  | NOC Operationalization | Design & Documentation | Share detailed scope document and conditional approvals & workshops tracker |  | Critical | Open |  |  | 23-Sep-25: Approved shall be closed | [12 empty] | Network | Closed | CLOSED | 23-Sep-25: Approved shall be closed | FALSE | [5 empty] | 2025-09-23 | Artefacts not Required | Completed & Approved | Closed before june-2025 | Closed after June
1226 | M527 | MOM | 2024-01-24 |  |  |  | Helpdesk | Helpdesk | Obtain T-Fiber's review in the next two days and submit revised Helpdesk SOPs |  | Critical | open |  |  | 24-Sep-25: Artefcts to be submiited for closure 11-Sep-25: Same has been Submitted | [12 empty] | Helpdesk (Contact Center) | Closed | [8 empty] | 2025-09-24 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\M1076 | Completed & Approved | Closed before june-2025 | Closed after June
1227 | M528 | MOM | 2024-01-24 |  |  |  | NOC Operationalization | O&M Strategy | Discuss and revert all pending points with MD(I/C), T-Fiber, and T-Fiber Operations Team |  | Critical | Open |  |  | 23-Sep-25: Approved shall be closed | [12 empty] | Network | Closed | CLOSED | 23-Sep-25: Approved shall be closed | FALSE | [5 empty] | 2025-09-23 | Artefacts not Required | Completed & Approved | Closed before june-2025 | Closed after June
1228 | M529 | MOM | 2024-01-24 |  |  |  | NSO | Design Features | Provide road map detailing how the 6 products will move from manual process to automation |  | Critical | Open |  |  | 29-dec-2025: Need discussion | [7 empty] | Not Started |  |  |  |  | Applications/Tools | OPEN |  |  |  |  | Jyothi | [5 empty] | Open | Open | Open
1229 | M53 | MOM | 2023-06-19 |  |  |  | GIS | User Experience | Automation of active connectivity |  | Critical | Open | Gtech |  | 15-Nov-25:Duplicate with Point- 145 | [12 empty] | Applications/Tools | [11 empty] | Open | Open | Open
1230 | M530 | MOM | 2024-01-24 |  |  |  | NSO | Design Features | Share a plan about how 6 products Dark Fiber, GI-BB, T-Cell, T-VPN, T-Dill will move from manual process to automation |  | Critical | Open |  |  | 19-12-2025:- Plan for services identified. | [7 empty] | Not Started |  |  |  |  | Applications/Tools | OPEN |  |  |  |  | Jyothi | [5 empty] | Open | Open | Open
1231 | M531 | MOM | 2024-01-24 |  |  |  | BSS | Design Features | Finalize the readiness of all modules, including ticketing, Helpdesk, full automation, and WFM |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1232 | M532 | MOM | 2024-01-24 |  |  |  | GIS | Design Features | Discuss internally and provide a feasible response about leading the GIS data update process |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1233 | M533 | MOM | 2024-01-24 |  |  |  | Helpdesk | Design Features | Arrange Helpdesk toll-free (1800-XXX-XX) number |  | Critical | Open |  |  | 11-09-2025: Same as T366(472) Closed | [12 empty] | Helpdesk (Contact Center) | Closed | [8 empty] | 2025-07-19 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\T366 | Completed & Approved | Closed before june-2025 | Closed after June
1234 | M534 | MOM | 2024-01-24 |  |  |  | Helpdesk | Design Features | Share finalized notification readiness of SMS, WhatsApp & Email formats for T-Fiber customers |  | Critical | Open |  |  | 01-Dec-25: Aretfacts to be submitted | [12 empty] | Helpdesk (Contact Center) | OPEN | [10 empty] | Open | Open | Open
1235 | M535 | MOM | 2024-01-24 |  |  |  | Helpdesk | Helpdesk | Arrange a demonstration of Helpdesk and IVR functions flow |  | Critical | open |  |  | 23-Sep-25: Demo completed shall be closed 11-Sep-25: Complied, Part of Interim NOC KPI | [12 empty] | Helpdesk (Contact Center) | Closed | [8 empty] | 2025-09-24 | Artefacts not Required | Completed & Approved | Closed before june-2025 | Closed after June
1236 | M536 | MOM | 2024-01-24 |  |  |  | Security & Regulatory Compliance | Compliance | Ensure L&T meets all regulatory compliance for poducts and provide NOC operationalisation |  | Critical | Open |  |  | 28-Nov-25: To discuss with mr Sanjay to get clarifications on the points | [12 empty] | Security | OPEN | [10 empty] | Open | Open | Open
1237 | M537 | MOM | 2024-01-25 |  |  |  | WFM | WFM Application | Complete the WFM-OSS integration |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1238 | M538 | MOM | 2024-01-25 |  |  |  | WFM | WFM Application | Understand use cases of WFM integration with BSS |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1239 | M539 | MOM | 2024-01-25 |  |  |  | OSS | WFM Application | Define authorization of PoP RFS criteria for approval |  | Critical | Open |  |  | Not a WFM Point 11th July 2025:-this point needs to be discussed with Siva Sir to explore the possibility of accommodating the feature in the respective application, as it is not related to WFM | [12 empty] | Applications/Tools | OPEN | Need clarity on this point | OPEN | FALSE | [7 empty] | Open | Open | Open
1240 | M54 | MOM | 2023-06-19 |  |  |  | GIS | Integration | Sync issue error alerts in OSS and GIS |  | Critical | Open | Gtech | [14 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1241 | M540 | MOM | 2024-01-25 |  |  |  | WFM | WFM Application | Complete Fault Management and Trouble Ticketing assignment (OSS to WFM) |  | Critical | Open |  |  | 15-Nov-25:DWDM Completed | [12 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1242 | M541 | MOM | 2024-01-25 |  |  |  | WFM | WFM Application | Distinguish between the use of GIS mobile app and WFM mobile app |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1243 | M542 | MOM | 2024-01-25 |  |  |  | WFM | WFM Application | Submit the NDA signed between L&T and M/S Lepton |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1244 | M543 | MOM | 2024-01-25 |  |  |  | WFM | WFM Application | Submit sample reports and dashboards of WFM package |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1245 | M544 | MOM | 2024-01-25 |  |  |  | WFM | WFM Application | Verify proposed solution for WFM |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1246 | M545 | MOM | 2024-01-25 |  |  |  | WFM | WFM Application | Dry run and operationalize three routes for testing WFM with actual data |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1247 | M546 | MOM | 2024-01-25 |  |  |  | WFM | WFM Application | Conduct weekly training sessions for patrollers on WFM app |  | Critical | Open |  |  | 15-Nov-25:Completed on 100 Licenced Users, three months weekly training provide to PKG-A, Training given to PKG-B & C also | [12 empty] | Applications/Tools | OPEN | [10 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1248 | M547 | MOM | 2024-01-25 |  |  |  | WFM | WFM Application | Check and confirm the watermarking feature on photos taken by field users |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1249 | M548 | MOM | 2024-02-13 |  |  |  | Security & Regulatory Compliance | RMC meeting | Implement IP-MAC binding to prevent IP spoofing |  | Critical | Open | [15 empty] | Security | Closed | [9 empty] | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\NW-Security\M1009_31-Oct-25.pdf | Closed | Closed After 14-Oct | Open
1250 | M549 | MOM | 2024-02-13 |  |  |  | Security & Regulatory Compliance | RMC meeting | Ensure the standardization of usernames across applications |  | Critical | Open | [15 empty] | Security | Closed | [9 empty] | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\NW-Security\T307_31-Oct-25.pdf\\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\NW-Security\M1142_31-Oct-25.pdf | Closed | Closed After 14-Oct | Open
1251 | M55 | MOM | 2023-06-22 |  |  |  | Security & Regulatory Compliance | Audit | Scope submission for external audit |  | Critical | Open |  |  | 28-Nov-25: VAPT is going on, once VAPT is done points will be closed. Audit done by Allied Boston. And further external audit to be done by TFiber vendor | [12 empty] | Security | OPEN | [8 empty] | 2025-12-19 |  | Completed &Approved | Completed &Approved | Completed &Approved
1252 | M550 | MOM | 2024-02-13 |  |  |  | Security & Regulatory Compliance | RMC meeting | Obtain T-Fiber's review and approval for policy documents |  | Critical | Open |  |  | 28-Nov-25: Document preparation in progress once done, points will be closed. As process this is being followed. Mails being sent for approvals. This point is adhered | [12 empty] | Security | OPEN | [10 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1253 | M551 | MOM | 2024-02-13 |  |  |  | BSS | Product | Work on implementing the guidelines for Dark Fiber from T-Fiber and GIS team |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1254 | M552 | MOM | 2024-02-13 |  |  |  | BSS | Product | Get clarity on integration rules and timeline for activating 'Ready for Order' and 'Ready for Service' statuses |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1255 | M553 | MOM | 2024-02-13 |  |  |  | BSS | Product | Implement user access control for converting from RFO to RFS |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1256 | M554 | MOM | 2024-02-13 |  |  |  | BSS | Product | Populate data fields automatically while feeding site information |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1257 | M555 | MOM | 2024-02-13 |  |  |  | BSS | Product | Submit a document explaining reformatted guidelines for service |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1258 | M556 | MOM | 2024-02-13 |  |  |  | Security & Regulatory Compliance | RMC meeting | Initiate the implementation of Mandal-to-Mandal and Mandal-to-GP dark fiber process |  | Critical | Open | [15 empty] | Security | OPEN | [10 empty] | Open | Open | Open
1259 | M557 | MOM | 2024-02-13 |  |  |  | GIS | Feasibility | Introduce the approach for Bulk Feasibility |  | Critical | Open |  |  | 15-Nov-25:To fulfill this requirement, an external feasibility application or tool is needed, as it cannot be achieved within the GIS application, 11 July 2025:- TFIBER is not agreed, asked to take with L | &T | upper | man | agement | discussion |  | & m | ail |  |  | ini | tiated by me for internal top management, there is commercial involved to meet this feature. | Applications/Tools | OPEN |  |  |  |  | the | [5 empty] | Open | Open | Open
1260 | M558 | MOM | 2024-02-13 |  |  |  | BSS |  | Capture and demonstrate BSS integration with Bill Desk |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1261 | M559 | MOM | 2024-02-13 |  |  |  | BSS |  | Ensure all 29 BSNL locations are loaded for lead to order presentation |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1262 | M56 | MOM | 2023-06-22 |  |  |  | Security & Regulatory Compliance | Audit | External agency Audit with certification |  | Critical | Open |  |  | 28-Nov-25: VAPT is going on, once VAPT is done points will be closed. Audit done by Allied Boston. And further external audit to be done by TFiber vendor | [12 empty] | Security | OPEN | [10 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1263 | M560 | MOM | 2024-02-13 |  |  |  | Security & Regulatory Compliance | RMC meeting | Finalize GI-BB timeline |  | Critical | Open | [15 empty] | Security | OPEN | [10 empty] | Open | Open | Open
1264 | M561 | MOM | 2024-02-13 |  |  |  | Security & Regulatory Compliance | RMC meeting | Finalize T-Cell timeline |  | Critical | Open | [15 empty] | Security | OPEN | [10 empty] | Open | Open | Open
1265 | M562 | MOM | 2024-02-13 |  |  |  | Security & Regulatory Compliance | RMC meeting | Make user access control to convert from RFO to RFS |  | Critical | Open | [15 empty] | Security | OPEN | [10 empty] | Open | Open | Open
1266 | M563 | MOM | 2024-02-13 |  |  |  | Security & Regulatory Compliance | RMC meeting | Revisit the actual requirements of SSL certifications and implementation policies |  | Critical | Open |  |  | 28-Nov-25: There are duplicate points; once the main point is closed, these duplicate points can be closed. Duplicate point. Hence clsoing this point | [12 empty] | Security | OPEN | [10 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1267 | M564 | MOM | 2024-02-13 |  |  |  | Security & Regulatory Compliance | RMC meeting | Submit a document with details on implementing the suggested process changes |  | Critical | Open |  |  | 28-Nov-25: Gathering artifacts from other teams | [12 empty] | Security | OPEN | [10 empty] | Open | Open | Open
1268 | M565 | MOM | 2024-02-13 |  |  |  | Security & Regulatory Compliance | RMC meeting | Develop a standard training program followed by quizzes for improving security |  | Critical | Open |  |  | 28-Nov-25: To discuss with mr Sanjay to get clarifications on the points | [12 empty] | Security | OPEN | [10 empty] | Open | Open | Open
1269 | M566 | MOM | 2024-02-13 |  |  |  | Security & Regulatory Compliance | RMC meeting | Start a weekly security bulletin |  | Critical | Open |  |  | 28-Nov-25: There are duplicate points; once the main point is closed, these duplicate points can be closed. | [12 empty] | Security | OPEN | [10 empty] | Open | Open | Open
1270 | M567 | MOM | 2024-02-13 |  |  |  | Security & Regulatory Compliance | RMC meeting | Study the best practices of the State Security Operations Center and implement them |  | Critical | Open |  |  | 28-Nov-25: Document preparation in progress once done points will be closed. | [12 empty] | Security | OPEN | [10 empty] | Open | Open | Open
1271 | M568 | MOM | 2024-02-14 |  |  |  | NSO | Service provisioning | Resolve issues with the NSO features |  | Critical | Open |  |  | 29-dec-2025: Need discussion | [7 empty] | Not Started |  |  |  |  | Applications/Tools | OPEN |  |  |  |  | Need Clarity | [5 empty] | Open | Open | Open
1272 | M569 | MOM | 2024-02-14 |  |  |  | NSO | Service provisioning | Fast track the making of the pre-production environment |  | Critical | Open |  |  | 29-dec-2025: Need discussion.rajeev | [12 empty] | Applications/Tools | OPEN |  |  |  |  | Rajeev | [5 empty] | Open | Open | Open
1273 | M57 | MOM | 2023-06-22 |  |  |  | Security & Regulatory Compliance | Audit | external auditor to be government empanelled (MeitY / STQC). |  | Critical | Open |  |  | 28-Nov-25: VAPT is going on, once VAPT is done points will be closed. Audit done by Allied Boston. And further external audit to be done by TFiber vendor | [12 empty] | Security | OPEN | [10 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1274 | M570 | MOM | 2024-02-14 |  |  |  | NSO | Service provisioning | Upload government orders in the BSS |  | Critical | Open |  |  | 29-dec-2025: Need discussion.NOT NSO | [7 empty] | Not Started |  |  |  |  | Applications/Tools | OPEN |  |  |  |  | Need Clarity BSS (need to align NSO for data migration) - 13/03/2026 : Refer mail sent by sandeep sir(End customer Data uploading) | [5 empty] | Open | Open | Open
1275 | M571 | MOM | 2024-02-14 |  |  |  | NSO | Service provisioning | Re-initiate the daily cadence calls |  | Critical | Open |  |  | 29-dec-2025: Need discussion | [7 empty] | Not Started |  |  |  |  | Applications/Tools | OPEN |  |  |  |  | Need Clarity | [5 empty] | Open | Open | Open
1276 | M572 | MOM | 2024-02-14 |  |  |  | NSO | Service provisioning | Make all products for the government and cellular business segments ready by |  | Critical | Open |  |  | 19-12-2025:- Plan for services identified. | [7 empty] | Not Started |  |  |  |  | Applications/Tools | OPEN |  |  |  |  | Need Clarity | [5 empty] | Open | Open | Open
1277 | M573 | MOM | 2024-02-14 |  |  |  | BSS | Dry Run | Finish all Dry runs |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1278 | M574 | MOM | 2024-02-14 |  |  |  | NSO | Service provisioning | Work parallelly on household business products |  | Critical | Open |  |  | 19-12-2025:- Plan for services identified. | [7 empty] | Not Started |  |  |  |  | Applications/Tools | OPEN |  |  |  |  | Need Clarity | [5 empty] | Open | Open | Open
1279 | M575 | MOM | 2024-02-14 |  |  |  | NSO | Service provisioning | Onboard all L&T SMEs and involve OEMs for 15th March'24 target |  | Critical | Open |  |  | 29-dec-2025: Need discussion | [7 empty] | Not Started |  |  |  |  | Applications/Tools | OPEN |  |  |  |  | Need Clarity | [5 empty] | Open | Open | Open
1280 | M576 | MOM | 2024-02-14 |  |  |  | Helpdesk | Helpdesk | Ensure helpdesk is ready by |  | Critical | Open | [15 empty] | Helpdesk (Contact Center) | OPEN | [10 empty] | Open | Open | Open
1281 | M577 | MOM | 2024-02-14 |  |  |  | NOC Operationalization | O&M Strategy | Provide daily updates on the progress made in NOC by |  | Critical | Open |  |  | 23-Sep-25: Approved shall be closed | [12 empty] | Network | Closed | CLOSED | 23-Sep-25: Approved shall be closed | FALSE | [5 empty] | 2025-09-23 | Artefacts not Required | Completed & Approved | Closed before june-2025 | Closed after June
1282 | M578 | MOM | 2024-02-14 |  |  |  | NOC Operationalization | O&M Strategy | Resolve all issues |  | Critical | Open |  |  | 23-Sep-25: Approved shall be closed | [12 empty] | Network | Closed | CLOSED | 23-Sep-25: Approved shall be closed | FALSE | [5 empty] | 2025-09-23 | Artefacts not Required | Completed & Approved | Closed before june-2025 | Closed after June
1283 | M579 | MOM | 2024-02-14 |  |  |  | NOC Operationalization | O&M Strategy | Establish two distinct setup—one for live operations, another for pre-production |  | Critical | Completed |  |  | 23-Sep-25: Approved shall be closed | [12 empty] | Network | Closed | CLOSED | 23-Sep-25: Approved shall be closed | FALSE | [5 empty] | 2025-09-23 | Artefacts not Required | Completed & Approved | Closed before june-2025 | Closed after June
1284 | M58 | MOM | 2023-06-22 |  |  |  | Security & Regulatory Compliance | Audit | simulation of attacks on the network and hardening of applications in the NOC |  | Critical | Open |  |  | 28-Nov-25: VAPT is going on, once VAPT is done points will be closed | [12 empty] | Security | OPEN | [10 empty] | Open | Open | Open
1285 | M580 | MOM | 2024-02-14 |  |  |  | NOC Operationalization | O&M Strategy | Share all related details for pre-production setup to Director-NOC, T-Fiber |  | Critical | Completed |  |  | 23-Sep-25: Approved shall be closed | [12 empty] | Network | Closed | CLOSED | 23-Sep-25: Approved shall be closed | FALSE | [5 empty] | 2025-09-23 | Artefacts not Required | Completed & Approved | Closed before june-2025 | Closed after June
1286 | M581 | MOM | 2024-02-16 |  |  |  | BSS | O&M Strategy | Implement ticket tracking with OSS Service Manager |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1287 | M582 | MOM | 2024-02-16 |  |  |  | BSS | GIS | Address challenge in BSS-GIS integration |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1288 | M583 | MOM | 2024-02-16 |  |  |  | BSS | GIS | Ensure collection of required / optional parameters at each step |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1289 | M584 | MOM | 2024-02-16 |  |  |  | BSS | CRM | Reconsider requirement for document collection in CAF approval stage |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1290 | M585 | MOM | 2024-02-16 |  |  |  | BSS | CRM | Introduce 'Manual reference ID' attribute in service order form |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1291 | M586 | MOM | 2024-02-16 |  |  |  | BSS | CRM | Enable option to close or update work order status manually |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1292 | M587 | MOM | 2024-02-16 |  |  |  | BSS | CRM | Alter selections or drop-down options in Lead, Opportunity, and Service Order page |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1293 | M588 | MOM | 2024-02-16 |  |  |  | BSS | CRM | Renaming certain attributes in the Opportunity Screen |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1294 | M589 | MOM | 2024-02-16 |  |  |  | BSS | CRM | Rename 'Normal Loss' attribute to 'Optical Loss' in service order form |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1295 | M59 | MOM | 2023-06-22 |  |  |  | WFM | Mobile Application | Mobile App supported in Android & IOS |  | Critical | Open |  |  | 15-Nov-25:This item has been completed. The WFM mobile application supports both Android and iOS versions for the Smart Operation and Smart Inventory modules, and users are actively utilizing them | [12 empty] | Applications/Tools | OPEN | [9 empty] | #N/A | Closed | Closed | Open
1296 | M590 | MOM | 2024-02-16 |  |  |  | BSS | CRM | Add multiple reference documents received from customer in service order |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1297 | M591 | MOM | 2024-02-16 |  |  |  | BSS | BSS | Display order count bar chart in the Dashboard |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1298 | M592 | MOM | 2024-02-16 |  |  |  | BSS | BSS | Issues observed in the generated CAF to be resolved |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1299 | M593 | MOM | 2024-02-16 |  |  |  | BSS | GIS | Automatically populate Site FDMS name post-GIS integration |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1300 | M594 | MOM | 2024-02-16 |  |  |  | BSS | BSS | Limit 'retry' options in BSS until process failure |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1301 | M595 | MOM | 2024-02-16 |  |  |  | BSS | WFM Application | Ensure multiple tasks tied to single work order are visible in WFM |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1302 | M596 | MOM | 2024-02-16 |  |  |  | BSS | WFM Application | Make manual acceptance function available in BSS for WFM |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1303 | M597 | MOM | 2024-02-16 |  |  |  | BSS | NSO | Resolve configuration issues to operationalize Product Catalogue module |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1304 | M598 | MOM | 2024-02-16 |  |  |  | BSS | BSS | Physical survey and customer signoff to be included in the next step |  | NON-Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1305 | M599 | MOM | 2024-02-16 |  |  |  | BSS | WFM Application | Feedback on WFM stages to be given in the next meeting |  | NON-Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1306 | M6 | MOM | 2023-03-27 |  |  |  | NOC Operationalization | Handbook & SOPs | Clear accountability and responsibility of SMEs, along with an presented RASCI matrix |  | Critical | Completed | NSO |  | 23-Sep-25: Approved shall be closed | [12 empty] | Network | Closed | CLOSED | 23-Sep-25: Approved shall be closed | FALSE | [5 empty] | 2025-09-23 | Artefacts not Required | Completed & Approved | Closed before june-2025 | Closed after June
1307 | M60 | MOM | 2023-06-28 |  |  |  | NOC Operationalization | Handbook & SOPs | Classification of Procedures and processes from ITIL and eTOM |  | Critical | Open |  |  | 23-Sep-25: Approved shall be closed | [12 empty] | Network | Closed | CLOSED | 23-Sep-25: Approved shall be closed | FALSE | [5 empty] | 2025-09-23 | Artefacts not Required | Completed & Approved | Closed before june-2025 | Closed after June
1308 | M600 | MOM | 2024-02-16 |  |  |  | BSS | WFM Application | Generate customer signoff through WFM and create separate tabs for storing OTDR traces and customer signoff |  | NON-Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1309 | M601 | MOM | 2023-07-03 |  |  |  | Security & Regulatory Compliance | Internal Audit | Security Audit |  | Critical | Open |  |  | 28-Nov-25: VAPT is going on, once VAPT is done points will be closed | [12 empty] | Security | OPEN | [10 empty] | Open | Open | Open
1310 | M602 | MOM | 2023-07-03 |  |  |  | Security & Regulatory Compliance | Internal Security | Acceptable Usage of information |  | Critical | Open | [15 empty] | Security | Closed | [8 empty] | 2025-10-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\NW-Security\M372_29-Oct-25.pdf | Closed | Closed After 14-Oct | Open
1311 | M603 | MOM | 2023-07-03 |  |  |  | Security & Regulatory Compliance | Safety | ERT and mock drills |  | Critical | Open |  |  | Mock drills, safety briefing and training is done | [12 empty] | Security | OPEN | [10 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1312 | M604 | MOM | 2023-07-03 |  |  |  | Security & Regulatory Compliance | Internal Security | Gate pass for materials |  | Critical | Open |  |  | Gate pass process in place at TNOC | [12 empty] | Security | OPEN | [10 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1313 | M605 | MOM | 2023-07-03 |  |  |  | Security & Regulatory Compliance | Internal Security | VAPT |  | Critical | Open |  |  | 28-Nov-25: VAPT is going on, once VAPT is done points will be closed | [12 empty] | Security | OPEN | [10 empty] | Open | Open | Open
1314 | M606 | MOM | 2023-07-03 |  |  |  | Security & Regulatory Compliance | Internal Security | Security Incident management |  | Critical | Open |  |  | 28-Nov-25: To discuss with mr Sanjay to get clarifications on the points | [12 empty] | Security | OPEN | [10 empty] | Open | Open | Open
1315 | M607 | MOM | 2023-07-03 |  |  |  | Security & Regulatory Compliance | Safety | Training |  | Critical | Open |  |  | Mock drills, safety briefing and training is done | [12 empty] | Security | OPEN | [10 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1316 | M608 | MOM | 2023-07-03 |  |  |  | Security & Regulatory Compliance | Internal Security | Assest Management |  | Critical | Open |  |  | 28-Nov-25: There are duplicate points; once the main point is closed, these duplicate points can be closed. | [12 empty] | Security | OPEN | [10 empty] | Open | Open | Open
1317 | M609 | MOM | 2023-07-03 |  |  |  | Security & Regulatory Compliance | Internal Security | Crytography |  | Critical | Open |  |  | 28-Nov-25: VAPT is going on, once VAPT is done points will be closed | [12 empty] | Security | OPEN | [8 empty] | 2025-12-19 |  | Completed &Approved | Completed &Approved | Completed &Approved
1318 | M61 | MOM | 2023-06-28 |  |  |  | NOC Operationalization | Resource Related | L&T with ITIL or eTOM certifications |  | Critical | Open |  |  | 16-Oct-25: Will share the team certifications | [12 empty] | Network | OPEN | OPEN | 16-Oct-25: Will share the team certifications | TRUE | [7 empty] | Open | Open | Open
1319 | M610 | MOM | 2023-07-03 |  |  |  | Security & Regulatory Compliance | Internal Security | Access control |  | Critical | Open |  |  | 28-Nov-25: Physical access control in place at TNOC. FOr system Access control, this is duplicate point | [12 empty] | Security | Closed | [8 empty] | 2025-11-29 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\NW-Security\T36_28-Oct-25.pdf | Closed | Closed After 14-Oct | Completed but Verification undrer Process
1320 | M611 | MOM | 2023-07-04 | P3 |  |  | NOC Operationalization | Operational Handbook | Incorporate changes into the proposed operational framework as per T-Fiber's review, including adding a Vision and Mission statement, identifying additional relevant processes, updating the organisation structure, and correcting inconsistencies in the documentation of processes. |  | Critical | Open |  |  | SOPs approved, have flow diagrams | [12 empty] | Network | Closed |  |  |  | Documentation |  |  |  |  | 2025-09-24 | \\172.28.9.23\tnocreports\Approved Process and SOP_ T Fiber\SOP | Completed & Approved | Closed before june-2025 | Closed after June
1321 | M612 | MOM | 2023-07-04 |  |  |  | NOC Operationalization | Operational Handbook | Detail flow charts of the processes into SOPs. |  | Critical | Open |  |  | 24-Sep-25: Updated Document Shared 23-Aug-23 | [12 empty] | Network | Closed | [8 empty] | 2025-09-24 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\M104,105,109,111,113,115,122,123,127,128,130,132,162 | Completed & Approved | Closed before june-2025 | Closed after June
1322 | M613 | MOM | 2023-07-04 |  | OSS | OSS | OSS | O&M Strategy | Justify the use of the implemented HPSM tool as best suited to ITIL compliant processes. |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | 0 | No Artifact Required | TRUE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1323 | M614 | MOM | 2023-07-04 |  |  |  | NOC Operationalization | O&M Strategy | Revert on the segregation of current, interim, and final organisation structure along with the timelines in which these should be applicable. |  | Critical | Open |  |  | 23-Sep-25: Approved shall be closed | [12 empty] | Network | Closed | CLOSED | 23-Sep-25: Approved shall be closed | FALSE | [5 empty] | 2025-09-23 | Artefacts not Required | Completed & Approved | Closed before june-2025 | Closed after June
1324 | M615 | MOM | 2023-07-04 |  |  |  | NOC Operationalization | Hiddencove suggestions | Include the processes recommended by the external auditor (Hiddencove) such as Handover deployment to Operation process, Service Request Process, Configuration Management, Asset Management, Critical Event Management, Site Access Management, Handover Deployment to Operations Process (Transition Process). |  | Critical | Open |  |  | 16-Oct-25: External VAPT audit in progress | [12 empty] | Network | OPEN | OPEN | 16-Oct-25: External VAPT audit in progress | TRUE | [7 empty] | Open | Open | Open
1325 | M616 | MOM | 2023-07-04 |  |  |  | NOC Operationalization | O&M Strategy | Include a Continuous Improvement framework covering the process of identification/initiation of the areas for continuous improvement on a regular basis. Standard frameworks like KAIZEN Or PDCA are suggested. |  | Critical | Open |  |  | 23-Sep-25: Approved shall be closed | [12 empty] | Network | Closed | CLOSED | 23-Sep-25: Approved shall be closed | FALSE | [5 empty] | 2025-09-23 | Artefacts not Required | Completed & Approved | Closed before june-2025 | Closed after June
1326 | M617 | MOM | 2023-07-04 | P3 |  |  | NOC Operationalization | Escalation Matrix | Include aspects like document processes, RASCI & Escalation Matrix in NOC Operational Framework. |  | Critical | Open | [15 empty] | Network | OPEN |  |  |  | Documentation | [6 empty] | Open | Open | Open
1327 | M618 | MOM | 2023-07-04 |  |  |  | NOC Operationalization | O&M Strategy | Highlight the processes that will be implemented and ready by 15th August ’23 and provide a roadmap of which module will be ready by when. |  | Critical | Open |  |  | 23-Sep-25: Approved shall be closed | [12 empty] | Network | Closed | CLOSED | 23-Sep-25: Approved shall be closed | FALSE | [5 empty] | 2025-09-23 | Artefacts not Required | Completed & Approved | Closed before june-2025 | Closed after June
1328 | M619 | MOM | 2023-07-04 | P3 |  |  | NOC Operationalization | Escalation Matrix | Define clear roles and responsibilities related to L1, L2 & L3 with an appropriate number of resources which should be according to the fault rates. |  | Critical | Open |  |  | 24-Sep-25: Updated Document Shared 23-Aug-23 | [12 empty] | Network | Closed |  |  |  | Not related to delivery |  |  |  |  | 2025-09-24 | \\172.28.9.23\tnocreports\TNOC Manpower_CVs\NOC Resources Details & Roles | Completed & Approved | Closed before june-2025 | Closed after June
1329 | M62 | MOM | 2023-06-28 | P3 |  |  | NOC Operationalization | Handbook & SOPs | All KPIs details submission |  | Critical | Completed |  |  | NOC KPI report for submitted and signed for Oct24 to Dec24. Jan to March25 KPI submitted but sign-off pending with TFiber | [12 empty] | Network | Closed |  |  |  | Documentation |  |  |  |  | 2025-09-24 | \\172.28.9.23\tnocreports\Monthly KPI Reports\FY 24-25\NOV-24\Interim NOC KPI for Signoff_ NOV-24 | Completed & Approved | Closed before june-2025 | Closed after June
1330 | M620 | MOM | 2023-07-04 |  |  |  | NOC Operationalization | GIS | Ensure the coverage of GIS operations as part of a single integrated picture of NOC, Field including handovers to/from Field and NOC. |  | Critical | Open |  |  | 23-Sep-25: Approved shall be closed | [12 empty] | Network | Closed | CLOSED | 23-Sep-25: Approved shall be closed | FALSE | [5 empty] | 2025-09-23 | Artefacts not Required | Completed & Approved | Closed before june-2025 | Closed after June
1331 | M621 | MOM | 2023-07-04 |  |  |  | Helpdesk | Helpdesk | Evaluate the readiness of the current Helpdesk to start taking calls for GI and validate the sufficiency of the Helpdesk based on the fault rate, waiting time for each agent etc. by 15th July'23 |  | Critical | open |  |  | 24-Sep-25: Approved and shall be closed 11-Sep-25: Changed and operational Now | [12 empty] | Helpdesk (Contact Center) | Closed | [8 empty] | 2025-09-24 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\M117,126,728 | Completed & Approved | Closed before june-2025 | Closed after June
1332 | M622 | MOM | 2023-07-04 | P3 |  |  | NOC Operationalization | O&M Strategy | Submission of the proposed TNOC Operational Framework document on 9th July ’23 for review. |  | Critical | Open |  |  | 223-Sep-25: Artefacts uploded | [12 empty] | Network | Closed |  |  |  | Documentation |  |  |  |  | 2025-09-22 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\TNOC\M622 | Completed & Approved | Closed before june-2025 | Closed after June
1333 | M623 | MOM | 2023-07-04 |  |  |  | NOC Operationalization | O&M Strategy | Next review on Operational Framework by 11th July ’23. |  | Critical | Open |  |  | 23-Sep-25: Approved shall be closed | [12 empty] | Network | Closed | CLOSED | 23-Sep-25: Approved shall be closed | FALSE | [5 empty] | 2025-09-23 | Artefacts not Required | Completed & Approved | Closed before june-2025 | Closed after June
1334 | M624 | MOM | 2023-07-04 |  |  |  | NOC Operationalization | O&M Strategy | Develop a process and framework for order fulfillment, ensuring that all applications and tools are ready for production. |  | Critical | Open |  |  | 16-Oct-25: Covered in 22 BSS processes & submitted | [12 empty] | Network | OPEN | CLOSED | 16-Oct-25: Covered in 22 BSS processes & submitted | FALSE | [7 empty] | Open | Open | Open
1335 | M625 | MOM | 2023-07-04 |  |  |  | NOC Operationalization | O&M Strategy | Prepare a more comprehensive plan for product catalog and infrastructure management and maintenance. |  | Critical | Open |  |  | 16-Oct-25: Covered in BSS HLD | [12 empty] | Network | OPEN | Duplicate | 16-Oct-25: Covered in BSS HLD | FALSE | [7 empty] | Open | Open | Open
1336 | M626 | MOM | 2023-07-04 |  |  |  | NOC Operationalization | O&M Strategy | Develop a comprehensive plan for improving network service management and address any issues related to MPLS-related resources. |  | Critical | Open |  |  | 16-Oct-25: Will discuss and take it up | [12 empty] | Network | OPEN | OPEN | 16-Oct-25: Will discuss and take it up | TRUE | [7 empty] | Open | Open | Open
1337 | M627 | MOM | 2023-07-04 |  |  |  | NOC Operationalization | Dry Run | Schedule the first dry run for the NOC Operationalization for 24th July '23. |  | Critical | Open |  |  | 23-Sep-25: Approved shall be closed | [12 empty] | Network | Closed | CLOSED | 23-Sep-25: Approved shall be closed | FALSE | [5 empty] | 2025-09-23 | Artefacts not Required | Completed & Approved | Closed before june-2025 | Closed after June
1338 | M628 | MOM | 2023-07-04 |  |  |  | WFM | Mobile Application | Develop and present mobile applications that are functional and meet the needs and preferences of users by 15th August '23. |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1339 | M629 | MOM | 2023-07-04 |  |  |  | NOC Operationalization |  | The Tools Assigned the Operation to be ready and deployed by 9th July '23. |  | Critical | Open |  |  | 16-Oct-25: Covered in NOC go-live plan | [12 empty] | Network | OPEN | Duplicate | 16-Oct-25: Covered in NOC go-live plan | FALSE | [7 empty] | Open | Open | Open
1340 | M63 | MOM | 2023-06-28 |  |  |  | NOC Operationalization | Handbook & SOPs | The difference between problem and issue management. |  | Critical | Open |  |  | 23-Sep-25: Approved shall be closed | [12 empty] | Network | Closed | CLOSED | 23-Sep-25: Approved shall be closed | FALSE | [5 empty] | 2025-09-23 | Artefacts not Required | Completed & Approved | Closed before june-2025 | Closed after June
1341 | M630 | MOM | 2023-07-04 |  |  |  | NOC Operationalization |  | HLD & LLD Approval: L&T to expedite closure of pending points with daily discussions, aiming for 6th April '23. |  | NON-Critical | Open |  |  | 16-Oct-25: Covered in NOC go-live plan | [12 empty] | Network | OPEN | Duplicate | 16-Oct-25: Covered in NOC go-live plan | FALSE | [7 empty] | Open | Open | Open
1342 | M631 | MOM | 2023-07-04 |  |  |  | BSS | T-Cell Launch | Cell Tower Launch: CRM-based demo by L&T with manual NSO loop and GIS by 27th March '23. |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1343 | M632 | MOM | 2023-07-04 |  |  |  | BSS | T-Cell Launch | Dependencies for Cell Tower Launch: L&T to address payment gateway integration, product catalog sign-off, and E2E flows with T-Fiber approval. |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1344 | M633 | MOM | 2023-07-04 |  |  |  | BSS | T-Cell Launch | GIS Feasibility for Cell Tower: L&T to present an alternative solution within 2 to 3 days and document risks and mitigation for seamless migration. |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1345 | M634 | MOM | 2023-07-04 |  |  |  | GIS | GIS Completion | GIS OEM - Hexagon: L&T to ensure GIS readiness within 2 to 4 weeks for service provisioning automation. |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1346 | M635 | MOM | 2023-07-04 |  |  |  | OEM Related | Security | Cisco Firewall Limitation: L&T to demonstrate GI Internet workflow by 5th April '23 and confirm support for full capacity of 30 thousand institutions. |  | Critical | Open |  |  | 23-Sep-25: Approved shall be closed | [12 empty] | OEM Related Issues | Closed | CLOSED | 23-Sep-25: Approved shall be closed | FALSE | [5 empty] | 2025-09-23 | Artefacts not Required | Completed & Approved | Closed before june-2025 | Closed after June
1347 | M636 | MOM | 2023-07-04 |  |  |  | PM Tool Issue | PM Tool Issue | Digital Process for GI Connectivity: L&T to present a plan for digital process and tools usage by 5th April '23, with the possibility of presenting earlier in Cadence calls. |  | NON-Critical | Open |  |  | 23-Sep-25: Approved shall be closed | [12 empty] | Applications | Closed | CLOSED | 23-Sep-25: Approved shall be closed | FALSE | [5 empty] | 2025-09-23 | Artefacts not Required | Completed & Approved | Closed before june-2025 | Closed after June
1348 | M637 | MOM | 2023-07-04 |  |  |  | BSS | BSS | BSS Cadence Calls: L&T to initiate and lead the required Cadence calls to meet project timelines. |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1349 | M638 | MOM | 2023-07-04 |  |  |  | NOC Operationalization | Resource Augmentation | IPMPLS SME Resignation: L&T to address the resignation and retention of the IPMPLS SME. |  | Critical | Open |  |  | 23-Sep-25: Approved shall be closed | [12 empty] | Network | Closed | CLOSED | 23-Sep-25: Approved shall be closed | FALSE | [5 empty] | 2025-09-23 | Artefacts not Required | Completed & Approved | Closed before june-2025 | Closed after June
1350 | M639 | MOM | 2023-07-04 |  |  |  | NOC Operationalization | Communication Matrix | Project SPOC: Mr. Anthony from L&T to coordinate across all domains to deliver the project. |  | Critical | Open |  |  | 23-Sep-25: Approved shall be closed | [12 empty] | Network | Closed | CLOSED | 23-Sep-25: Approved shall be closed | FALSE | [5 empty] | 2025-09-23 | Artefacts not Required | Completed & Approved | Closed before june-2025 | Closed after June
1351 | M64 | MOM | 2023-06-28 |  |  |  | NOC Operationalization | Handbook & SOPs | Establish a configuration management system to monitor all changes in NOC operations |  | Critical | Completed |  |  | 16-Oct-25: Covered in change management SOP | [12 empty] | Network | OPEN | CLOSED | 16-Oct-25: Covered in change management SOP | FALSE | [7 empty] | Open | Open | Open
1352 | M640 | MOM | 2023-07-04 |  |  |  | NOC Operationalization | Service Solution | T-NOC Operationalisation Plan: L&T to present a phased plan on 27th March '23 for minimal readiness by 5th April, stage 2 by 20th April, and stage 3 by 30th April, with the entire T-NOC operational by 30th April and launch by 15th May '23. |  | Critical | Open |  |  | 16-Oct-25: Covered in NOC go-live plan | [12 empty] | Network | OPEN | OPEN | 16-Oct-25: Covered in NOC go-live plan | TRUE | [7 empty] | Open | Open | Open
1353 | M641 | MOM | 2023-07-04 |  |  |  | Field Related | Resource Augmentation | Resource Deployment for District Delivery: L&T to ramp up resources to meet the delivery target of five and a half districts by 7th April '23. |  | Critical | Open | [15 empty] | Field Related issues | OPEN |  |  |  | Project Team | [5 empty] | Artefacts to be uploaded | Open | Open | Open
1354 | M642 | MOM | 2023-07-04 |  |  |  | Field Related | Zonal Path connectivity | Zonal Path Completion: L&T to complete Medak to Mahbubnagar Zonal path by 31st March and AT by 15th April '23; AT of other completed zonal paths by 31st March '23. |  | Critical | Open | [15 empty] | Field Related issues | OPEN |  |  |  | Project Team | [6 empty] | Open | Open | Open
1355 | M643 | MOM | 2023-07-05 |  |  |  | GIS | GIS Completion | Evaluate the current readiness status of the GIS tool and address the pending issues. |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1356 | M644 | MOM | 2023-07-05 |  |  |  | BSS | BSS | Ensure that the product being developed meets all the discussed and agreed-upon requirements and features. |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1357 | M645 | MOM | 2023-07-05 |  |  |  | BSS | Dry Run | Complete the BSS Demo according to the feedback points received and demonstrate progress on the same by the first week of May. |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1358 | M646 | MOM | 2023-07-05 |  |  |  | NOC Operationalization | NOC Operationalization | Develop and present a comprehensive proposal for improving the appearance of T-NOC. |  | Critical | Open |  |  | TNOC passive infra delivered, AT done | [12 empty] | Network | Closed |  |  |  | Need clarity |  |  |  |  | 2025-09-19 | Artefacts not Required | Completed & Approved | Closed before june-2025 | Closed after June
1359 | M647 | MOM | 2023-07-05 |  |  |  | GIS | GIS Completion | Submit revise plan for Complete GIS Tool (Basic) Readiness by 30th April’23, GIS Tool (Advanced) Readiness by 31st May’23, and GIS Tool (Integration) Readiness by 30th June’23. |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1360 | M648 | MOM | 2023-07-05 |  |  |  | GIS | GIS Completion | Submit responses on concerns of the number of GIS licences for data upload and readiness of current helpdesk to start taking calls for GI. |  | Critical | Open |  |  | 15-Nov-25:TFIBER is a critical dependency for closing the GIS licenses | [12 empty] | Applications/Tools | OPEN | [10 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1361 | M649 | MOM | 2023-07-05 | P3 |  |  | NOC Operationalization | Operational Framework | Identify and rectify inconsistencies in the document processes presented in the NOC's Operational Framework. |  | Critical | Open | [15 empty] | Network | OPEN |  |  |  | Documentation | [6 empty] | Open | Open | Open
1362 | M65 | MOM | 2023-06-28 | P3 |  |  | NOC Operationalization | Handbook & SOPs | Create an archival policy for documentation storage, including retrieval systems, access matrix, and policies |  | Critical | Open | [15 empty] | Network | OPEN |  |  |  | Documentation | [6 empty] | Open | Open | Open
1363 | M650 | MOM | 2023-07-05 |  |  |  | BSS | Dry Run | Provide BSS Demo with actual auto-feasibility check by 6th April. |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1364 | M651 | MOM | 2023-07-05 |  |  |  | BSS | Dry Run | Present a clear day-wise plan for BSS readiness by 30th September 2023 for full-fledged production with automated GIS. |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1365 | M652 | MOM | 2023-07-05 |  |  |  | Field Related | Full NOC Readiness | Complete the connection of 589 Mandals by 1st week of June, with an expectation of minimum 3 hours and maximum of 5 hours for each Mandal. |  | Critical | Open | [15 empty] | Field Related issues | OPEN |  |  |  | Project Team | [6 empty] | Open | Open | Open
1366 | M653 | MOM | 2023-07-05 |  |  |  | NOC Operationalization | Full NOC Readiness | Highlight the processes that will be implemented and ready by 15th August ’23 and provide a roadmap of which module will be ready by when during the meeting on 4th July'23. |  | Critical | Open |  |  | 16-Oct-25: Processes covered in SOP | [12 empty] | Network | OPEN | CLOSED | 16-Oct-25: Processes covered in SOP | FALSE | [7 empty] | Open | Open | Open
1367 | M654 | MOM | 2023-07-05 |  |  |  | Security & Regulatory Compliance | Full NOC Readiness | Still update on the perceived firewall limitation issue is pending , asked on 3rd April'24 |  | Critical | Open |  |  | 28-Nov-25: To discuss with mr Sanjay to get clarifications on the points | [12 empty] | Security | OPEN | [10 empty] | Open | Open | Open
1368 | M655 | MOM | 2023-07-05 |  |  |  | BSS | WFM Application | Submit internal E2E Project Plan on 31st March’23 as committed for review. |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1369 | M656 | MOM | 2023-07-05 |  |  |  | BSS | Dry Run | BSS Demo on 6th April’23 must provide order feasibility. |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1370 | M657 | MOM | 2023-07-05 |  |  |  | NOC Operationalization | Operational Framework | Ensure that all references to processes from ITIL and eTOM are clearly explained and utilized in the operational framework. |  | Critical | Open |  |  | 23-Sep-25: Approved shall be closed | [12 empty] | Network | Closed | CLOSED | 23-Sep-25: Approved shall be closed | FALSE | [5 empty] | 2025-09-23 | Artefacts not Required | Completed & Approved | Closed before june-2025 | Closed after June
1371 | M658 | MOM | 2023-07-05 | P3 |  |  | NOC Operationalization | Escalation Matrix | Implement a robust RASCI & Escalation Matrix in the NOC Operational Framework. |  | Critical | Open | [15 empty] | Network | Closed |  |  |  | Not related to delivery |  |  |  |  | 2025-09-19 | Artefacts not Required | Completed & Approved | Closed before june-2025 | Closed after June
1372 | M659 | MOM | 2023-07-05 |  |  |  | GIS | GIS Completion | Integrate the processes recommended by the external auditor into the process flow of GIS readiness. |  | Critical | Open |  |  | 15-Nov-25:GIS SOP | [12 empty] | Applications/Tools | OPEN | [10 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1373 | M66 | MOM | 2023-06-28 | P3 |  |  | NOC Operationalization | Handbook & SOPs | Define categories of problems along with a resolution approach plan |  | Critical | Open | [15 empty] | Network | OPEN |  |  |  | Documentation | [6 empty] | Open | Open | Open
1374 | M660 | MOM | 2023-07-05 |  |  |  | BSS | GIS | Perform manual feasibility checking until the GIS tool is ready and data is uploaded into the tool. |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1375 | M661 | MOM | 2023-07-05 |  |  |  | BSS | GI Demo | Showcase the GI demo by the end of May. |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1376 | M662 | MOM | 2023-07-05 |  |  |  | GIS | GIS Completion | Improve coordination with GIS, OEMs, and explore the possibility of developing a new GIS OEM to deliver the requirements of T-Fiber. |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1377 | M663 | MOM | 2023-07-05 |  |  |  | Helpdesk | Helpdesk | Take the performance measurement processes into consideration for measuring the performance of the identified Helpdesk resources. |  | Critical | Open |  |  | 24-Sep-25: Approved and shall be closed | [12 empty] | Helpdesk (Contact Center) | Closed | [8 empty] | 2025-09-24 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\M114,722,134 | Completed & Approved | Closed before june-2025 | Closed after June
1378 | M664 | MOM | 2023-07-05 |  |  |  | BSS | CRM | Handle more professionally the field activity portion of the CRM flow. |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1379 | M665 | MOM | 2023-07-05 |  |  |  | NSO | NSO | Arrive at feasible alternatives to handle situations such as NSO provisioning timeouts, submit alternative approaches in such scenarios and revert with exact steps taken to achieve this. |  | Critical | Open |  |  | 29-dec-2025: resolved | [7 empty] | Not Started |  |  |  |  | Applications/Tools | OPEN |  |  |  |  | Jyothi | [5 empty] | Open | Open | Open
1380 | M666 | MOM | 2023-07-05 |  |  |  | NOC Operationalization | Daily Meetings | Officially commence up the daily stand-up call on 16th June ’23, with the call to be held routinely from this date. |  | Critical | Open |  |  | 23-Sep-25: Approved shall be closed | [12 empty] | Network | Closed | CLOSED | 23-Sep-25: Approved shall be closed | FALSE | [5 empty] | 2025-09-23 | Artefacts not Required | Completed & Approved | Closed before june-2025 | Closed after June
1381 | M667 | MOM | 2023-07-05 |  |  |  | BSS | Dry Run | BSS Demo on 6th April ’23 to provide order feasibility. |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1382 | M668 | MOM | 2023-07-05 |  |  |  | NOC Operationalization | Operational Framework | Review of the Operational Framework by 11th July ’23. |  | Critical | Open |  |  | 23-Sep-25: Approved shall be closed | [12 empty] | Network | Closed | CLOSED | 23-Sep-25: Approved shall be closed | FALSE | [5 empty] | 2025-09-23 | Artefacts not Required | Completed & Approved | Closed before june-2025 | Closed after June
1383 | M669 | MOM | 2023-07-05 |  |  |  | BSS | T-Cell Launch | Showcase the demo for T-Cell on 6th April ’23. |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1384 | M67 | MOM | 2023-06-28 |  |  |  | NOC Operationalization | Handbook & SOPs | Adopt a continuous improvement framework such as DMAIC and Kaizen for process improvement |  | Critical | Open |  |  | 23-Sep-25: Approved shall be closed | [12 empty] | Network | Closed | CLOSED | 23-Sep-25: Approved shall be closed | FALSE | [5 empty] | 2025-09-23 | Artefacts not Required | Completed & Approved | Closed before june-2025 | Closed after June
1385 | M670 | MOM | 2023-07-05 |  |  |  | BSS | Billing Related | Auto-approval of the Invoice by Finance users. |  | NON-Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1386 | M671 | MOM | 2023-07-05 |  |  |  | Helpdesk | Helpdesk | Make Helpdesk operational by 15th July ’23. |  | Critical | Open | [15 empty] | Helpdesk (Contact Center) | OPEN | [10 empty] | Open | Open | Open
1387 | M672 | MOM | 2023-07-21 |  |  |  | BSS | BSS | BSS Readiness Confirmation: L&T to review and update overall readiness for E2E NOC by EOD 8th September '23, including confirmation on launch deliverables and interim launch processes . |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1388 | M673 | MOM | 2023-07-21 |  |  |  | BSS | Dry Run | BSS Demo Observations: L&T to address observations from the BSS Demo on 24th July '23 and action items from the meeting with Director-Finance, T-Fiber . |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1389 | M674 | MOM | 2023-07-21 |  |  |  | WFM |  | WFM Integration: L&T commenced WFM integration and will arrange a demonstration for field operations . |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1390 | M675 | MOM | 2023-07-21 |  |  |  | BSS | NSO | Static IP and UI/UX Changes: Ready for demonstration by L&T . |  | NON-Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1391 | M676 | MOM | 2023-07-21 |  |  |  | Security & Regulatory Compliance | Compliance | Security and Compliance: L&T to address critical security-related activities for launch and regulatory compliances with specific target dates . |  | Critical | Open |  |  | 28-Nov-25: To discuss with mr Sanjay to get clarifications on the points | [12 empty] | Security | OPEN | [10 empty] | Open | Open | Open
1392 | M677 | MOM | 2023-07-21 |  |  |  | BSS | Billing Related | Payment Gateway Completion: If SSL Certificate is provided by 11th September '23, L&T to complete the payment gateway by 30th September '23 . |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1393 | M678 | MOM | 2023-07-21 |  |  |  | BSS | Dry Run | BSS E2E Demo: Chief Delivery Officer, L&T proposed to have the E2E BSS Demo on 4th July '23, with features to be confirmed by 1st July '23 . |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1394 | M679 | MOM | 2023-07-21 |  |  |  | WFM |  | Mobile App & WFM: SVP, T-Fiber requested clarity on the number of mobile apps and urged L&T to freeze the scope in consultation with MSI B and C. Demo with M/S Lepton scheduled for 21st June '23 . |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1395 | M68 | MOM | 2023-07-04 | P3 |  |  | NOC Operationalization | Handbook & SOPs | RASCI & Escalation Matrix in NOC Operational Framework |  | Critical | Closed |  |  | OEM, vendor , Field/NOC escalation matrix available. This is a point in 472 tracker as well and this point is approved by TFiber | [12 empty] | Network | Closed |  |  |  | Not related to delivery |  |  |  |  | 2025-09-19 | Artefacts not Required | Completed & Approved | Closed before june-2025 | Closed before june-2025
1396 | M680 | MOM | 2023-07-21 |  |  |  | NSO | NSO related | NSO Competency Plan: L&T to put in place an NSO competency plan . |  | Critical | Open |  |  | 29-dec-2025: Need discussion. More team members needed | [7 empty] | Not Started |  |  |  |  | Applications/Tools | OPEN |  |  |  |  | Need Clarity | [5 empty] | Open | Open | Open
1397 | M681 | MOM | 2023-07-21 |  |  |  | T&D Environment | Testing Environment | Separation of T&D and Production Environments: L&T to provide a plan addressing the requirement for separate environments . |  | NON-Critical | Open |  |  | [15/09/2025] Clusters are segregated for Production vis-à-vis pre-production | [12 empty] | Applications | Closed | [9 empty] | Artefacts Need to upload | Completed & Approved | Closed before june-2025 | Closed after June
1398 | M682 | MOM | 2023-07-21 |  |  |  | BSS | Testing Environment | Onboarding of Billing Specialist: L&T to update on the onboarding process for a long-term Billing Specialist . |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1399 | M683 | MOM | 2023-07-21 |  |  |  | BSS | Billing Related | Closure of CRM Billing Process and Invoice Format: L&T to close action items regarding CRM Billing Process and Invoice format . |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1400 | M684 | MOM | 2023-07-21 |  |  |  | BSS | Action Points | BSS Roadmap Progress: L&T to demonstrate completed points for closure and include related test cases . |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1401 | M685 | MOM | 2023-07-21 |  |  |  | BSS | Dry Run | Next BSS Demo for Cell Tower: L&T to confirm the date of the next BSS Demo for Cell Tower by 21st August '23 . |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1402 | M686 | MOM | 2023-07-21 |  |  |  | BSS | Action Points | User Groups Demonstration: L&T to showcase the demonstration on user groups along with the demo for Cell Tower . |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1403 | M687 | MOM | 2023-07-21 |  |  |  | BSS | Action Points | Next BSS Demo Schedule: Scheduled for 23rd August '23, to include RFS/RFO status, notification templates, UI/UX validation, and exception scenarios . |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1404 | M688 | MOM | 2023-07-21 |  |  |  | BSS | Regulatory Compliance | Regulatory Reports Review: L&T to identify available reports in BSS as Ready/WIP by 21st August '23 and review with T-Fiber for approval . |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1405 | M689 | MOM | 2023-07-26 |  |  |  | WFM |  | Finalise and share the scope of work (SOW) for Work Force Management solution implementation with M/S Lepton. |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1406 | M69 | MOM | 2023-07-04 | P3 |  |  | NOC Operationalization | Handbook & SOPs | clear definition of roles and responsibilities related to L1, L2 & L3 with number of resources which should be according to the fault rates. |  | Critical | Completed |  |  | NOC manpower report is shared on weekly basis. Manpower is as per RFP count. KRA is also submitted for L1/L2/L3 roles | [12 empty] | Network | Closed |  |  |  | Not related to delivery |  |  |  |  | 2025-09-24 | \\172.28.9.23\tnocreports\TNOC Manpower_CVs\NOC Resources Details & Roles | Completed & Approved | Closed before june-2025 | Closed after June
1407 | M690 | MOM | 2023-07-26 |  |  |  | WFM |  | Support for translation to Telugu to be checked with M/S Lepton. |  | Critical | Open |  |  | 15-Nov-25:Duplicate with Point- 177 | [12 empty] | Applications/Tools | [11 empty] | Open | Open | Open
1408 | M691 | MOM | 2023-07-26 |  |  |  | WFM |  | Clarity on the term “As-is solution to be deployed” under Order Management is to be provided. |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1409 | M692 | MOM | 2023-07-26 |  |  |  | WFM |  | Support for Barcode scanning as well as QR code scanning to be checked with M/S Lepton. |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1410 | M693 | MOM | 2023-07-26 |  |  |  | BSS | Dry Run | Preparation for a dry run of BSS to include WFM. |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1411 | M694 | MOM | 2023-07-26 |  |  |  | WFM |  | Receive clarification on the support for re-assignment of workflow in case a Field Technician is on leave. |  | Critical | Open |  |  | 15-Nov-25:Manager has to reassign TT to different FE | [12 empty] | Applications/Tools | OPEN | [10 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1412 | M695 | MOM | 2023-07-26 |  |  |  | WFM |  | Verify processes for recording of timelocks of patrol routes. |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1413 | M696 | MOM | 2023-07-26 |  |  |  | WFM |  | Improve the clarity, definition, and availability of existing filters in WFM dashboards. |  | Critical | Open |  |  | 15-Nov-25:Duplicate with Point- 186 | [12 empty] | Applications/Tools | [11 empty] | Open | Open | Open
1414 | M697 | MOM | 2023-07-26 |  |  |  | WFM |  | Video upload support. |  | Critical | Open |  |  | 15-Nov-25:Duplicate with Point- 187 | [12 empty] | Applications/Tools | [11 empty] | Open | Open | Open
1415 | M698 | MOM | 2023-07-26 |  |  |  | WFM |  | Support for Workforce Management productivity statistics mentioned that this shall fall under the customisation scope. |  | Critical | Open |  |  | 15-Nov-25:Duplicate with Point- 188 | [12 empty] | Applications/Tools | [11 empty] | Open | Open | Open
1416 | M699 | MOM | 2023-07-26 |  |  |  | WFM |  | Coordination required with NOC, Operations, and Projects team of 3 MSIs for the WFM Demo of 3 Packages including BSS-SME- L&T. |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1417 | M7 | MOM | 2023-04-03 |  |  |  | NOC Operationalization | Full NOC Readiness | Request for submission of Test Reports, outcomes, and documentation on a common server for continuous testing and monitoring. (Shared Folder) |  | Critical | Completed | OSS Dashboards |  | 24-Sep-25: All Field and Interim NOC KPIs, reports, forms are available in shared folder.Artefacts will be uploaded today in NAS | [12 empty] | Network | Closed | [8 empty] | 2025-09-24 | \\172.28.9.23\tnocreports | Completed & Approved | Closed before june-2025 | Closed after June
1418 | M70 | MOM | 2023-07-04 | P3 |  |  | NOC Operationalization | Audit | Checklist for issue handling and first level troubleshooting |  | Critical | Completed |  |  | Checklist available with Helpdesk | [12 empty] | Network | Closed |  |  |  | Daily oprational task |  |  |  |  | 2025-09-19 | Artefacts not Required | Completed & Approved | Closed before june-2025 | Closed after June
1419 | M700 | MOM | 2023-07-26 |  |  |  | WFM |  | Asses if NOC Work Force Management is handled by the proposed WFM tool |  | Critical | Open |  |  | 15-Nov-25:Duplicate with Point- 189 | [12 empty] | Applications/Tools | [11 empty] | Open | Open | Open
1420 | M701 | MOM | 2023-07-26 |  |  |  | WFM |  | Samples or actual reports and dashboards based on operational processes to be presented by 28th July’23. |  | Critical | Open |  |  | 15-Nov-25:Duplicate with Point- 207 | [12 empty] | Applications/Tools | [11 empty] | Open | Open | Open
1421 | M702 | MOM | 2023-07-26 |  |  |  | WFM |  | Assessment to ensure that planned Event Manpower assignment is covered by the WFM solution. |  | Critical | Open |  |  | 15-Nov-25:Duplicate with Point- 190 | [12 empty] | Applications/Tools | [11 empty] | Open | Open | Open
1422 | M703 | MOM | 2023-07-26 |  |  |  | WFM |  | Assessment about whether the proposed WFM solution supports field personnel to schedule appointments with end customers. |  | Critical | Open |  |  | 15-Nov-25:Duplicate with Point- 194 | [12 empty] | Applications/Tools | [11 empty] | Open | Open | Open
1423 | M704 | MOM | 2023-07-26 |  |  |  | WFM |  | Ensure the licenses for WFM are perpetual. |  | Critical | Open |  |  | 15-Nov-25:Duplicate with Point- 196 | [12 empty] | Applications/Tools | [11 empty] | Open | Open | Open
1424 | M705 | MOM | 2023-07-26 |  |  |  | NOC Operationalization | Launch Readiness | Assessment and redistribution of support because of the launch date approaching on 15th August. |  | Critical | Open |  |  | 23-Sep-25: Approved shall be closed | [12 empty] | Network | Closed | CLOSED | 23-Sep-25: Approved shall be closed | FALSE | [5 empty] | 2025-09-23 | Artefacts not Required | Completed & Approved | Closed before june-2025 | Closed after June
1425 | M706 | MOM | 2023-08-01 |  |  |  | GIS | Launch Readiness | Each MSI needs to commit to the target for Mandal upload in the GIS tool for business readiness. |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1426 | M707 | MOM | 2023-08-01 |  |  |  | GIS | Launch Readiness | Commit target dates for GIS Data Upload for each package. |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1427 | M708 | MOM | 2023-08-01 |  |  |  | GIS | Launch Readiness | Package A needs to provide a day by day Mandal upload action plan to meet the committed target dates. |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1428 | M709 | MOM | 2023-08-01 |  |  |  | GIS | Launch Readiness | Packages B and C are expected to submit a proposal to hasten data upload in consultation with GIS-SME, Pkg-A. |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1429 | M71 | MOM | 2023-07-04 |  |  |  | NOC Operationalization | Audit | Latency/Jitter & Backbone packet loss SLAs |  | Critical | Completed |  |  | Report & SLA compliance is shared on monhtly basis | [12 empty] | Network | OPEN | [10 empty] | Open | Open | Open
1430 | M710 | MOM | 2023-08-01 |  |  |  | Field Related | Launch Readiness | MSIs to prioritise a district-wise approach over a scattered approach. |  | Critical | Open | [15 empty] | Field Related issues | OPEN |  |  |  | Project Team | [6 empty] | Open | Open | Open
1431 | M711 | MOM | 2023-08-01 |  |  |  | Field Related | Mandal Rings | The status of Mandal Rings completion i.e. GIS uploading done, splicing pending, attribute updating is pending. |  | NON-Critical | Open |  |  | completed for 110 Mandals and balance in progress with mandal readiness by acitive & passive | [12 empty] | Field Related issues | OPEN |  |  |  | Project Team | [6 empty] | Open | Open | Open
1432 | M712 | MOM | 2023-08-01 |  |  |  | GIS | Launch Readiness | The current committed dates for GIS Data Upload are not meeting the expectations of T-Fiber. |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1433 | M713 | MOM | 2023-08-01 |  |  |  | Helpdesk | Launch Readiness | Complete Helpdesk integration with OSS and BSS. |  | Critical | Open | [15 empty] | Helpdesk (Contact Center) | OPEN | [10 empty] | Open | Open | Open
1434 | M714 | MOM | 2023-08-01 |  |  |  | BSS | Launch Readiness | Set up SMS based alerting. |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1435 | M715 | MOM | 2023-08-01 |  |  |  | Helpdesk | Launch Readiness | Handle 150-160 calls per day in Helpdesk. |  | Critical | open |  |  | 24-Sep-25: Approved and shall be closed 11-Sep-25: Changed and operational Now | [12 empty] | Helpdesk (Contact Center) | Closed | [8 empty] | 2025-09-24 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\M117,126,728 | Completed & Approved | Closed before june-2025 | Closed after June
1436 | M716 | MOM | 2023-08-01 |  |  |  | Helpdesk | Launch Readiness | Ensure that Helpdesk SLAs from the RFP are met. |  | Critical | open | [15 empty] | Helpdesk (Contact Center) | OPEN | [10 empty] | Open | Open | Open
1437 | M717 | MOM | 2023-08-01 |  | OSS | OSS | OSS | Launch Readiness | Deploy the Knowledge Management module in HPSM. |  | Critical | Open | [15 empty] | Applications/Tools | Closed | 0 | Completed With Artifacts | TRUE | [5 empty] | 2025-11-18 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\OSS\52 Artefcats_18112025 | Closed after 14-Nov-25 | Closed after 14-Nov-25 | Completed but Verification undrer Process
1438 | M718 | MOM | 2023-08-01 |  |  |  | Helpdesk | Launch Readiness | Make the number for reaching Helpdesk toll-free. |  | Critical | Open |  |  | 11-09-2025: Same as T366(472) Closed | [12 empty] | Helpdesk (Contact Center) | Closed | [8 empty] | 2025-07-19 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\T366 | Completed & Approved | Closed before june-2025 | Closed after June
1439 | M719 | MOM | 2023-08-01 |  |  |  | BSS | Launch Readiness | Create and finalize multiple channels of communication to the Helpdesk such as SMS, WhatsApp, and email. |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1440 | M72 | MOM | 2023-07-04 | P3 |  |  | NOC Operationalization | Handbook & SOPs | service management of configuration |  | Critical | Open | [15 empty] | Network | OPEN |  |  |  | Documentation | [6 empty] | Open | Open | Open
1441 | M720 | MOM | 2023-08-01 |  | OSS | OSS | OSS | Launch Readiness | Define incident categorisation. |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | need to check | Completed With Artifacts | FALSE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1442 | M721 | MOM | 2023-08-01 |  |  |  | Helpdesk | Launch Readiness | Specify features of Helpdesk not presently available for future deployment. |  | Critical | Open | [15 empty] | Helpdesk (Contact Center) | OPEN | [10 empty] | Open | Open | Open
1443 | M722 | MOM | 2023-08-01 |  |  |  | Helpdesk | Launch Readiness | Training for Helpdesk users and managers for call center response and management. |  | Critical | open |  |  | 24-Sep:25: Artefacts to sbumitted | [12 empty] | Helpdesk (Contact Center) | Closed | [8 empty] | 2025-09-24 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\M114,722,134 | Completed & Approved | Closed before june-2025 | Closed after June
1444 | M723 | MOM | 2023-08-01 |  |  |  | Helpdesk | Launch Readiness | Set up a mechanism for non-technical call handling improvement. |  | Critical | open |  |  | 25-Sep-25: aretfacts to be sumitted for closure 11-Sep-25: Established Business Helpdesk Setup at T Fiber office | [12 empty] | Helpdesk (Contact Center) | Closed | [8 empty] | 2025-09-24 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\M116,723,1026 | Completed & Approved | Closed before june-2025 | Closed after June
1445 | M724 | MOM | 2023-08-01 |  |  |  | Helpdesk | Launch Readiness | Get readiness of Helpdesk and Business to accept issues with order login. |  | Critical | open |  |  | 25-Sep-25: aretfacts to be sumitted for closure 11-Sep-25: Established Business Helpdesk Setup at T Fiber office | [12 empty] | Helpdesk (Contact Center) | Closed | [8 empty] | 2025-09-24 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\M724 | Completed & Approved | Closed before june-2025 | Closed after June
1446 | M725 | MOM | 2023-08-01 |  |  |  | Helpdesk | Launch Readiness | Determine how to handle calls originating from different packages given the shared Helpdesk agents. |  | Critical | open |  |  | 24-Sep-25: IVR Flows made ready Accordingly | [12 empty] | Helpdesk (Contact Center) | Closed | [8 empty] | 2025-09-24 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\M725,735 | Completed & Approved | Closed before june-2025 | Closed after June
1447 | M726 | MOM | 2023-08-01 |  |  |  | Helpdesk | Launch Readiness | Problems with not supporting Telugu language in IVR and Helpdesk. |  | Critical | open |  |  | 24-Sep-25: Now its in 3 Languages | [12 empty] | Helpdesk (Contact Center) | Closed | [8 empty] | 2025-09-24 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\M121,170,99,726 | Completed & Approved | Closed before june-2025 | Closed after June
1448 | M727 | MOM | 2023-08-01 |  |  |  | Helpdesk | Launch Readiness | Unclear about support for integration with WhatsApp. |  | Critical | open |  |  | 01-Dec-25: Not feasible 11-Se-25:This Prouct Not Support | [12 empty] | Helpdesk (Contact Center) | OPEN | [10 empty] | Open | Open | Open
1449 | M728 | MOM | 2023-08-01 |  |  |  | Helpdesk | Resource Augmentation | Confirm if the current load handled by Helpdesk is sufficient. |  | Critical | open |  |  | 24-Sep-25: Artefcats to be submitted 11-Sep-25: Data Shared | [12 empty] | Helpdesk (Contact Center) | Closed | [8 empty] | 2025-09-24 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\M117,126,728 | Completed & Approved | Closed before june-2025 | Closed after June
1450 | M729 | MOM | 2023-08-01 |  |  |  | Helpdesk | Launch Readiness | Concern over non-availability of Helpdesk Manager between 10 PM – 6 AM and how emergencies are handled during this time. |  | Critical | open |  |  | 24-Sep-25: Existing Lead available during Business Hours, Remaining duration Shift Lead will Manage | [12 empty] | Helpdesk (Contact Center) | Closed | [8 empty] | 2025-09-24 | Artefacts not Required | Completed & Approved | Closed before june-2025 | Closed after June
1451 | M73 | MOM | 2023-07-26 |  |  |  | WFM | User Experience | Support for translation to Telugu |  | Critical | Open |  |  | 15-Nocv-25:As per OEM this point is not feasible 11 July 2025:- A follow-up discussion with the OEM is required to assess feasibility. If it is found to be unfeasible, a call should be arranged with Sanja | y S | ir al | ong | with the | team & arte |  | fac | ts |  |  | need | s to submit | Applications/Tools | [5 empty] | OEM | [5 empty] | Open | Open | Open
1452 | M730 | MOM | 2023-08-01 |  |  |  | NOC Operationalization | Launch Readiness | The relationship between people and functions as realised by RASCI matrix needs improvement. |  | Critical | Open |  |  | 23-Sep-25: Approved shall be closed | [12 empty] | Network | Closed | CLOSED | 23-Sep-25: Approved shall be closed | FALSE | [5 empty] | 2025-09-23 | Artefacts not Required | Completed & Approved | Closed before june-2025 | Closed after June
1453 | M731 | MOM | 2023-08-01 |  |  |  | Helpdesk | Launch Readiness | Differentiate between registered users and registered numbers. |  | Critical | Open |  |  | 01-Dec-25: Duplucate, Same as M112 11-Sep-25: BSS Integration to be completed | [12 empty] | Helpdesk (Contact Center) | OPEN | [10 empty] | Open | Open | Open
1454 | M732 | MOM | 2023-08-01 |  |  |  | Helpdesk | Launch Readiness | Resolve confusion over the categorisation of incoming queries. |  | Critical | open | [15 empty] | Helpdesk (Contact Center) | OPEN | [10 empty] | Open | Open | Open
1455 | M733 | MOM | 2023-08-01 |  |  |  | Helpdesk |  | Check how the Call management system can support live intrusion of calls for instant feedback. |  | Critical | open |  |  | 24-Sep-25:Artefacts to be submitted 11-Sep-25: Feature is available, Shall be demonstrated | [12 empty] | Helpdesk (Contact Center) | Closed | [8 empty] | 2025-09-24 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\M119,733 | Completed & Approved | Closed before june-2025 | Closed after June
1456 | M734 | MOM | 2023-08-01 |  |  |  | Helpdesk |  | Define how readiness of Helpdesk to report on compliances and responsiveness and penalties calculation. |  | Critical | open |  |  | 01-Dec-25: Duplucate, Same as M118 | [12 empty] | Helpdesk (Contact Center) | OPEN | [10 empty] | Open | Open | Open
1457 | M735 | MOM | 2023-08-04 |  |  |  | Helpdesk |  | Determine how the Helpdesk to NOC and Field is going to be integrated with the operational framework when they currently lack synergy. |  | Critical | open |  |  | 11-Sep-25: IVR Flows are aligned accordingly, Post Approval and Implementation we can meet expectations | [12 empty] | Helpdesk (Contact Center) | Closed | [8 empty] | 2025-09-24 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\M725,735 | Completed & Approved | Closed before june-2025 | Closed after June
1458 | M736 | MOM | 2023-08-04 |  |  |  | Helpdesk |  | Concern over Toll-free levels availability for the Helpdesk. |  | Critical | Open | [15 empty] | Helpdesk (Contact Center) | OPEN | [10 empty] | Open | Open | Open
1459 | M737 | MOM | 2023-08-18 |  |  |  | BSS | NSO | BSS Readiness and Demo: L&T to demonstrate Static IP and UI/UX changes, with WFM integration not part of the demonstration. |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1460 | M738 | MOM | 2023-08-18 |  |  |  | WFM | WFM Application | WFM Tool Usage Demonstration: L&T to arrange a demonstration of WFM tool usage for field operations soon. |  | Critical | Open |  |  | 15-Nov-25:Duplicate with Point- 235 | [12 empty] | Applications/Tools | [11 empty] | Open | Open | Open
1461 | M739 | MOM | 2023-08-18 |  |  |  | BSS | Billing Related | Payment Gateway Completion: L&T to complete the payment gateway by 30th September '23 if SSL Certificate is provided by 11th September '23. |  | Critical | Open |  |  | DUPLICATE POINT (M739) | [12 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1462 | M74 | MOM | 2023-07-26 |  |  |  | WFM | Handbook & SOPs | Scope of Order Processing and Service Ticket Management |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1463 | M740 | MOM | 2023-08-18 |  |  |  | Security & Regulatory Compliance | Compliance | Security Related Activities: L&T to address various security and compliance sub-activities with specific target dates. |  | Critical | Open |  |  | 28-Nov-25: To discuss with mr Sanjay to get clarifications on the points | [12 empty] | Security | OPEN | [10 empty] | Open | Open | Open
1464 | M741 | MOM | 2023-08-18 |  |  |  | BSS | BSS | BSS Integration with Lepton WFM: L&T to complete the demo of BSS Integration with Lepton WFM by 25th August '23. |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1465 | M742 | MOM | 2023-08-18 |  |  |  | BSS | NSO | NSO Competency Plan: L&T to put in place an NSO competency plan. |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1466 | M743 | MOM | 2023-08-18 |  |  |  | BSS | T&D Environment | Separation of T&D and Production Environments: L&T to provide a plan addressing the requirement for separate environments. |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1467 | M744 | MOM | 2023-08-18 |  |  |  | BSS | Resource Augmentation | Onboarding of Billing Specialist: L&T to update on the onboarding process for a long-term Billing Specialist. |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1468 | M745 | MOM | 2023-08-18 |  |  |  | BSS | Billing Related | Closure of CRM Billing Process and Invoice Format: L&T to close action items regarding CRM Billing Process and Invoice format. |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1469 | M746 | MOM | 2023-08-18 |  |  |  | BSS | T&D Environment | BSS Roadmap Progress: L&T to demonstrate completed points for closure and include related test cases. |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1470 | M747 | MOM | 2023-08-18 |  |  |  | BSS | Dry Run | Next BSS Demo for Cell Tower: L&T to confirm the date of the next BSS Demo for Cell Tower by 21st August '23. |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1471 | M748 | MOM | 2023-08-18 |  |  |  | BSS | Dry Run | User Groups Demonstration: L&T to showcase the demonstration on user groups along with the demo for Cell Tower. |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1472 | M749 | MOM | 2023-08-18 |  |  |  | BSS | Dry Run | Next BSS Demo Schedule: Scheduled for 23rd August '23, to include RFS/RFO status, notification templates, UI/UX validation, and exception scenarios. |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1473 | M75 | MOM | 2023-07-26 |  |  |  | WFM | Handbook & SOPs | Document references in SOW to be shared |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1474 | M750 | MOM | 2023-08-18 |  |  |  | BSS | Regulatory Compliance | Regulatory Reports Review: L&T to identify available reports in BSS as Ready/WIP by 21st August '23 and review with T-Fiber for approval. |  | Critical | Open |  |  | DUPLICATE POINT (M688) | [12 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1475 | M751 | MOM | 2023-08-18 |  |  |  | BSS |  | Dedication of Time to T-Fiber Project: Chief Delivery Officer, L&T to confirm dedicating 2 days a week to the T-Fiber Project in Hyderabad leading up to the Network Launch. |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1476 | M752 | MOM | 2023-08-23 |  |  |  | BSS |  | Review of alert and notification templates and implementation. |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1477 | M753 | MOM | 2023-08-23 |  |  |  | BSS |  | Lead data presentation for Airtel and GI_BB customers. |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1478 | M754 | MOM | 2023-08-23 |  |  |  | BSS |  | Walkthrough of Ready for Service (RFS) Process. |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1479 | M755 | MOM | 2023-08-23 |  |  |  | BSS |  | Identifying and addressing challenges for user experience in CRM. |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1480 | M756 | MOM | 2023-08-23 |  |  |  | BSS |  | Development of BSS demo of CSP. |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1481 | M757 | MOM | 2023-08-23 |  |  |  | BSS |  | Analysis of the issue impacting BSS demo. |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1482 | M758 | MOM | 2023-08-23 |  |  |  | NOC Operationalization |  | Fixing issues with OSS - BSS integration. |  | Critical | Open |  |  | 16-Oct-25: Covered in OSS-BSS integration | [12 empty] | Network | OPEN | Duplicate | 16-Oct-25: Covered in OSS-BSS integration | FALSE | [7 empty] | Open | Open | Open
1483 | M759 | MOM | 2023-08-23 |  |  |  | BSS |  | Establish a comprehensive list of event notification scenarios and implementation plan. |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1484 | M76 | MOM | 2023-07-26 |  |  |  | WFM | User Experience | WFM tool's own Google Map |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1485 | M760 | MOM | 2023-08-23 |  |  |  | BSS |  | Identify and create more user groups according to the business and workflow requirements. |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1486 | M761 | MOM | 2023-08-23 |  |  |  | BSS |  | Resolve discrepancies with manual updates for RFO and RFS status. |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1487 | M762 | MOM | 2023-08-23 |  |  |  | WFM |  | Respond to the query of WFM integration. |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1488 | M763 | MOM | 2023-08-23 |  |  |  | BSS |  | Improve user experience for better data accuracy. |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1489 | M764 | MOM | 2023-08-23 |  |  |  | BSS |  | Ensure the BSS-Lead, L&T and Head Telecom Practice, L&T to discuss and create more user groups according to the business and workflow requirements. |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1490 | M765 | MOM | 2023-08-23 |  |  |  | BSS |  | Introduce a status/bucket "Renewal" for orders that need further work / rectification. |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1491 | M766 | MOM | 2023-08-23 |  |  |  | BSS |  | Ensure that the entire network POI/ PoP status including 12751 GPs, 1 NOC, all zones, districts & Mandal nodes should be available in CRM database. |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1492 | M767 | MOM | 2023-08-23 |  |  |  | BSS |  | Address observations made in the CSP by L&T and implement changes. |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1493 | M768 | MOM | 2023-08-23 |  |  |  | BSS | T-Cell Launch | Propose the next date for T-Cell Demo. |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1494 | M769 | MOM | 2023-08-31 |  |  |  | NOC Operationalization |  | L&T to review NOC readiness and demonstrate service excellence for launch; separate meeting for 360 View presentation on 31st August '23. |  | Critical | Open |  |  | 16-Oct-25:Covered in BSS Operationalization | [12 empty] | Network | OPEN | Duplicate | 16-Oct-25:Covered in BSS Operationalization | FALSE | [7 empty] | Open | Open | Open
1495 | M77 | MOM | 2023-07-26 |  |  |  | WFM | Improvement | Support for Re-assignment of workflow in case of leave |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1496 | M770 | MOM | 2023-08-31 |  |  |  | NOC Operationalization | Launch Readiness | Implement IST in SCCM and confirm BSS readiness for live customers like Airtel by 31st August '23. |  | Critical | Open |  |  | 16-Oct-25: Covered in NSO implementation plan | [12 empty] | Network | OPEN | Duplicate | 16-Oct-25: Covered in NSO implementation plan | FALSE | [7 empty] | Open | Open | Open
1497 | M771 | MOM | 2023-08-31 |  |  |  | NOC Operationalization | NOC Operationalization | Data cleanup before Airtel onboarding and present GI migration approach from trial to production. |  | Critical | Open |  |  | 23-Sep-25: Approved shall be closed | [12 empty] | Network | Closed | CLOSED | 23-Sep-25: Approved shall be closed | FALSE | [5 empty] | 2025-09-23 | Artefacts not Required | Completed & Approved | Closed before june-2025 | Closed after June
1498 | M772 | MOM | 2023-08-31 |  | OSS | Security & OSS | All Domain | WhatsApp | List pending action items from T-Fiber; SSL certificate and WhatsApp Integration expected closure in 2-3 days. |  | NON-Critical | Open |  |  | 16-Oct-25: What's Up integrated with BSS | [12 empty] | Applications/Tools | OPEN | OPEN | 16-Oct-25: What's Up integrated with BSS | TRUE | [7 empty] | Open | Open | Open
1499 | M773 | MOM | 2023-08-31 |  |  |  | BSS |  | Share status updates on BSS action items by 1st September '23. |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1500 | M774 | MOM | 2023-08-31 |  |  |  | WFM |  | Schedule WFM integration with BSS demo for 15th September '23. |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1501 | M775 | MOM | 2023-09-08 |  |  |  | Field Related | GI Connectivity | Rectification and progress of GI Connectivity. |  | NON-Critical | Open |  |  | Maintainance in progress for go Live districts | [12 empty] | Field Related issues | OPEN |  |  |  | O&M Team | [6 empty] | Open | Open | Open
1502 | M776 | MOM | 2023-09-08 |  |  |  | NOC Operationalization | Launch Readiness | Completion of Pause-Mechanism and QOS Visibility part of the committed deliverables. |  | Critical | Open |  |  | 16-Oct-25: Covered in OSS implementation tracker | [12 empty] | Network | OPEN | Duplicate | 16-Oct-25: Covered in OSS implementation tracker | FALSE | [7 empty] | Open | Open | Open
1503 | M777 | MOM | 2023-09-08 |  |  |  | NOC Operationalization | Launch Readiness | Reviewing readiness for launch, readiness of O&M Approach, and readiness of NOC from a multiple perspectives. |  | Critical | Open |  |  | 16-Oct-25: Covered in NOC go-live plan | [12 empty] | Network | OPEN | Duplicate | 16-Oct-25: Covered in NOC go-live plan | FALSE | [7 empty] | Open | Open | Open
1504 | M778 | MOM | 2023-09-08 |  |  |  | NOC Operationalization |  | Submissio of module wise Functional Acceptance Test Plan. |  | Critical | Open |  |  | 16-Oct-25: Covered in ATP Plans | [12 empty] | Network | OPEN | Duplicate | 16-Oct-25: Covered in ATP Plans | FALSE | [7 empty] | Open | Open | Open
1505 | M779 | MOM | 2023-09-08 |  |  |  | NOC Operationalization | Launch Readiness | Implementation and readiness in order for Interim Launch from NOC to field level. |  | Critical | Open |  |  | 23-Sep-25: Approved shall be closed | [12 empty] | Network | Closed | CLOSED | 23-Sep-25: Approved shall be closed | FALSE | [5 empty] | 2025-09-23 | Artefacts not Required | Completed & Approved | Closed before june-2025 | Closed after June
1506 | M78 | MOM | 2023-07-26 |  |  |  | WFM | Improvement | Support for pre-defined routes |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1507 | M780 | MOM | 2023-09-08 |  |  |  | Security & Regulatory Compliance | NOC Operationalization | Establishing a security system including hardware, IT Infra, and Applications security certifications. |  | Critical | Open |  |  | 28-Nov-25: To discuss with mr Sanjay to get clarifications on the points | [12 empty] | Security | OPEN | [10 empty] | Open | Open | Open
1508 | M781 | MOM | 2023-09-08 |  |  |  | NOC Operationalization |  | Submit report capturing the number of test cases and their status. |  | Critical | Open |  |  | 16-Oct-25: Covered in ATP Plans | [12 empty] | Network | OPEN | Duplicate | 16-Oct-25: Covered in ATP Plans | FALSE | [7 empty] | Open | Open | Open
1509 | M782 | MOM | 2023-09-08 |  |  |  | NOC Operationalization | Launch Readiness | Include more sample sites in the 2nd Dry Run by the end of September' 23. |  | Critical | Open |  |  | 23-Sep-25: Approved shall be closed | [12 empty] | Network | Closed | CLOSED | 23-Sep-25: Approved shall be closed | FALSE | [5 empty] | 2025-09-23 | Artefacts not Required | Completed & Approved | Closed before june-2025 | Closed after June
1510 | M783 | MOM | 2023-09-08 |  |  |  | NOC Operationalization | Launch Readiness | Review and finalize the process design related to Service Delivery linked to manpower. |  | Critical | Open |  |  | 23-Sep-25: Approved Artefacts to be Submitted | [12 empty] | Network | Closed | CLOSED | 23-Sep-25: Approved Artefacts to be Submitted | FALSE | [6 empty] | Artefacts Need to upload | Completed & Approved | Closed before june-2025 | Closed after June
1511 | M784 | MOM | 2023-09-08 |  |  |  | NOC Operationalization |  | LLD (Revised) with OADM Solution (Ciena) |  | NON-Critical | Open | [15 empty] | Network | Closed | [9 empty] | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\DWDM\Artefact - T90 | Completed & Approved | Closed before june-2025 | Closed after June
1512 | M785 | MOM | 2023-09-08 |  |  |  | T&D Environment | Testing Environment | BSS T&D license to be accessible by 30/6/23. It will be moved to a production environment afterward. |  | NON-Critical | Open |  |  | [15/09/2025] KNOT BSS T&D is setup | [12 empty] | Applications | Closed | [9 empty] | Artefacts Need to upload | Completed & Approved | Closed before june-2025 | Closed after June
1513 | M786 | MOM | 2023-09-08 |  |  |  | NOC Operationalization | Launch Readiness | The readiness of E2E NOC will be reviewed and updated by 8th Sep ‘23. |  | Critical | Open |  |  | 23-Sep-25: Approved shall be closed | [12 empty] | Network | Closed | CLOSED | 23-Sep-25: Approved shall be closed | FALSE | [5 empty] | 2025-09-23 | Artefacts not Required | Completed & Approved | Closed before june-2025 | Closed after June
1514 | M787 | MOM | 2023-09-08 |  |  |  | NOC Operationalization | Launch Readiness | The status of pending deliverables that were committed for delivery by 15th August ’23 has not been mentioned to have been met by specific dates. |  | Critical | Open |  |  | 23-Sep-25: Approved shall be closed | [12 empty] | Network | Closed | CLOSED | 23-Sep-25: Approved shall be closed | FALSE | [5 empty] | 2025-09-23 | Artefacts not Required | Completed & Approved | Closed before june-2025 | Closed after June
1515 | M788 | MOM | 2023-09-08 |  |  |  | NOC Operationalization | Launch Readiness | T-NOC Readiness Confirmation: EVP, T-Fiber requested confirmation on launch deliverables and interim launch processes by EOD 8th September '23. |  | Critical | Open |  |  | 23-Sep-25: Approved shall be closed | [12 empty] | Network | Closed | CLOSED | 23-Sep-25: Approved shall be closed | FALSE | [5 empty] | 2025-09-23 | Artefacts not Required | Completed & Approved | Closed before june-2025 | Closed after June
1516 | M789 | MOM | 2023-09-08 |  |  |  | NOC Operationalization |  | Review of Pending Activities: Director-P&E, T-Fiber to review and update the status of 92 pending activities related to the 15th August '23 deliverables. |  | Critical | Open |  |  | 23-Sep-25: Approved shall be closed | [12 empty] | Network | Closed | CLOSED | 23-Sep-25: Approved shall be closed | FALSE | [5 empty] | 2025-09-23 | Artefacts not Required | Completed & Approved | Closed before june-2025 | Closed after June
1517 | M79 | MOM | 2023-07-26 |  |  |  | WFM | User Experience | Support for recording timeclocks of patrol routes |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1518 | M790 | MOM | 2023-09-08 |  |  |  | NOC Operationalization |  | Revised LLD for DWDM: Technical Head, L&T submitted the revised LLD for approval. |  | NON-Critical | Open |  |  | 23-Sep-25: Approved shall be closed | [12 empty] | Network | Closed | CLOSED | 23-Sep-25: Approved shall be closed | FALSE | [5 empty] | 2025-09-23 | Artefacts not Required | Completed & Approved | Closed before june-2025 | Closed after June
1519 | M791 | MOM | 2023-09-08 |  |  |  | Security & Regulatory Compliance | Compliance | Risk Assessment: VP-Program emphasized the need for a Risk register with a responsible SPOC and response plan. |  | Critical | Open |  |  | 28-Nov-25: To discuss with mr Sanjay to get clarifications on the points | [12 empty] | Security | OPEN | [10 empty] | Open | Open | Open
1520 | M792 | MOM | 2023-09-08 |  |  |  | BSS |  | Payment Gateway Completion: L&T to complete the payment gateway by 30th September '23 if SSL Certificate is provided by 11th September '23. |  | Critical | Open |  |  | DUPLICATE POINT (M739) | [12 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1521 | M793 | MOM | 2023-09-08 |  |  |  | Security & Regulatory Compliance | Compliance | Security Related Activities: Director-P&E, T-Fiber stressed the importance of security activities for launch and regulatory compliances. |  | Critical | Open |  |  | 28-Nov-25: To discuss with mr Sanjay to get clarifications on the points | [12 empty] | Security | OPEN | [10 empty] | Open | Open | Open
1522 | M794 | MOM | 2023-09-08 |  |  |  | Security & Regulatory Compliance | Compliance | Security and Compliance Sub-Activities: L&T to address various security and compliance sub-activities with specific target dates ranging from 31st August to 15th September '23. |  | Critical | Open |  |  | 28-Nov-25: To discuss with mr Sanjay to get clarifications on the points | [12 empty] | Security | OPEN | [10 empty] | Open | Open | Open
1523 | M795 | MOM | 2023-09-08 |  |  |  | Security & Regulatory Compliance | Compliance | Alepo AAA and TACACS Integration: Alepo to test integration with Nokia and Ciena nodes on TACACS with supporting artefacts of testing. |  | Critical | Open | [15 empty] | Security | Closed | [8 empty] | 2025-11-12 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T372 | Completed & Approved | Closed after 07-Nov-25 | Open
1524 | M796 | MOM | 2023-09-08 |  |  |  | Security & Regulatory Compliance | Compliance | OSS Firewall Ports: L&T to address OSS firewall ports required for security compliance. |  | Critical | Open | [15 empty] | Security | OPEN | 0 | Completed | TRUE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1525 | M797 | MOM | 2023-09-08 |  |  |  | Security & Regulatory Compliance | Compliance | Security LLD: Customer requested a complete Security LLD that outlines the security architecture and interactions between security products. |  | Critical | Open |  |  | 28-Nov-25: Document preparation in progress once done points will be closed. | [12 empty] | Security | OPEN | [10 empty] | Open | Open | Open
1526 | M798 | MOM | 2023-09-08 |  |  |  | Security & Regulatory Compliance | Compliance | External Audit and VAPT: L&T to conduct external audits and vulnerability assessments for applications and network elements. |  | Critical | Open |  |  | 28-Nov-25: VAPT is going on, once VAPT is done points will be closed. Audit done by Allied Boston. And further external audit to be done by TFiber vendor | [12 empty] | Security | OPEN | [8 empty] | 2025-12-19 |  | Completed &Approved | Completed &Approved | Completed &Approved
1527 | M799 | MOM | 2023-09-12 |  |  |  | WFM |  | L&T is to submit a proposal to T-Fiber on the scope to be showcased in the proposed WFM-BSS demonstration. |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1528 | M8 | MOM | 2023-04-03 |  |  |  | NOC Operationalization | Full NOC Readiness | All Test Plans to be submitted to TPA in coordination with Package B&C; reviewed by Assistant Director Technical, T-Fiber. |  | Critical | Open | OSS Dashboards |  | 23-Sep-25: Approved shall be closed | [12 empty] | Network | Closed | CLOSED | 23-Sep-25: Approved shall be closed | FALSE | [5 empty] | 2025-09-23 | Artefacts not Required | Completed & Approved | Closed before june-2025 | Closed after June
1529 | M80 | MOM | 2023-07-26 |  |  |  | WFM | User Experience | Support for Barcode and QR code scanning |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1530 | M800 | MOM | 2023-09-12 |  |  |  | WFM |  | L&T is to identify a product owner for WFM. |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1531 | M801 | MOM | 2023-09-22 |  |  |  | NOC Operationalization | Launch Readiness | Overcoming technical issues hampering the setup for the 1st Dry Run. |  | Critical | Open |  |  | 23-Sep-25: Approved shall be closed | [12 empty] | Network | Closed | CLOSED | 23-Sep-25: Approved shall be closed | FALSE | [5 empty] | 2025-09-23 | Artefacts not Required | Completed & Approved | Closed before june-2025 | Closed after June
1532 | M802 | MOM | 2023-09-22 |  |  |  | NOC Operationalization | Launch Readiness | Reviewing the setup for 1st Dry Run observed by the EVP, T-Fiber. |  | Critical | Open |  |  | 23-Sep-25: Approved shall be closed | [12 empty] | Network | Closed | CLOSED | 23-Sep-25: Approved shall be closed | FALSE | [5 empty] | 2025-09-23 | Artefacts not Required | Completed & Approved | Closed before june-2025 | Closed after June
1533 | M803 | MOM | 2023-09-22 |  |  |  | NOC Operationalization | Launch Readiness | Gaining clarity on roles and functionalities of NSO and OSS. |  | Critical | Open |  |  | 16-Oct-25: Covered in NSO implementation plan | [12 empty] | Network | OPEN | Duplicate | 16-Oct-25: Covered in NSO implementation plan | FALSE | [7 empty] | Open | Open | Open
1534 | M804 | MOM | 2023-09-22 |  |  |  | BSS |  | Overcoming technical issues observed in CSP and CRM. |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1535 | M805 | MOM | 2023-09-22 |  |  |  | BSS |  | Reviewing processes of order booking to be communicated more simply and effectively to the end users. |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1536 | M806 | MOM | 2023-09-22 |  |  |  | NOC Operationalization |  | L&T to identify provisioning/monitoring features limited because of interoperability issues in a multi-vendor eco-system. |  | Critical | Open |  |  | 16-Oct-25 Covered in GPON implementation plan | [12 empty] | Network | OPEN | Duplicate | 16-Oct-25 Covered in GPON implementation plan | FALSE | [7 empty] | Open | Open | Open
1537 | M807 | MOM | 2023-09-22 |  |  |  | NOC Operationalization |  | L&T to articulate how NSO and OSS are complementing each other and their roles in service provisioning. |  | Critical | Open |  |  | 16-Oct-25: Covered in NSO implementation plan | [12 empty] | Network | OPEN | Duplicate | 16-Oct-25: Covered in NSO implementation plan | FALSE | [7 empty] | Open | Open | Open
1538 | M808 | MOM | 2023-09-22 |  |  |  | NOC Operationalization |  | L&T to provide the redundancy plan if entire DC were to go down and the backup measures if NSO were to fail. |  | Critical | Open |  |  | 16-Oct-25: Covered in DC-DR Plan | [12 empty] | Network | OPEN | Duplicate | 16-Oct-25: Covered in DC-DR Plan | FALSE | [7 empty] | Open | Open | Open
1539 | M809 | MOM | 2023-09-22 |  |  |  | NOC Operationalization |  | L&T to work towards a system that is foolproof, automated, futuristic, and provides seamless service experience for end users. |  | Critical | Open |  |  | 16-Oct-25: General guidelines | [12 empty] | Network | OPEN | CLOSED | 16-Oct-25: General guidelines | FALSE | [7 empty] | Open | Open | Open
1540 | M81 | MOM | 2023-07-26 |  |  |  | WFM | Handbook & SOPs | Confirmation of SOW addressing Packages B and C |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1541 | M810 | MOM | 2023-09-22 |  |  |  | NOC Operationalization | Dry Run | L&T to propose the date for the 2nd Dry Run inclusive of Internet Leased Line, P2P, and P2MP flavors of service. |  | Critical | Open |  |  | 23-Sep-25: Approved shall be closed | [12 empty] | Network | Closed | CLOSED | 23-Sep-25: Approved shall be closed | FALSE | [5 empty] | 2025-09-23 | Artefacts not Required | Completed & Approved | Closed before june-2025 | Closed after June
1542 | M811 | MOM | 2023-09-22 |  |  |  | NOC Operationalization | Dry Run | L&T to confirm target date for E2E BSS Demo. |  | Critical | Open |  |  | 16-Oct-25:Covered in BSS Operationalization | [12 empty] | Network | OPEN | Duplicate | 16-Oct-25:Covered in BSS Operationalization | FALSE | [7 empty] | Open | Open | Open
1543 | M812 | MOM | 2023-09-22 |  |  |  | NOC Operationalization | Dry Run | L&T to consider the creation of a template for tracking observations. |  | Critical | Open |  |  | 23-Sep-25: Approved shall be closed | [12 empty] | Network | Closed | CLOSED | 23-Sep-25: Approved shall be closed | FALSE | [5 empty] | 2025-09-23 | Artefacts not Required | Completed & Approved | Closed before june-2025 | Closed after June
1544 | M813 | MOM | 2023-09-22 |  |  |  | NOC Operationalization | NSO | Provision of training for L&T pool of resources in NSO and development of NEDs. |  | Critical | Open |  |  | 16-Oct-25: LnT team has provided training on NSO | [12 empty] | Network | OPEN | CLOSED | 16-Oct-25: LnT team has provided training on NSO | FALSE | [7 empty] | Open | Open | Open
1545 | M814 | MOM | 2023-09-22 |  |  |  | NOC Operationalization |  | L&T to create a timetable displaying the percentage of progress on activities week-wise and fortnight-wise. |  | Critical | Open |  |  | 23-Sep-25: Approved shall be closed | [12 empty] | Network | Closed | CLOSED | 23-Sep-25: Approved shall be closed | FALSE | [5 empty] | 2025-09-23 | Artefacts not Required | Completed & Approved | Closed before june-2025 | Closed after June
1546 | M815 | MOM | 2023-09-22 |  |  |  | NOC Operationalization |  | L&T to confirm the features ready for showcase in the E2E Demo by 25th September’23. |  | Critical | Open |  |  | 23-Sep-25: Approved shall be closed | [12 empty] | Network | Closed | CLOSED | 23-Sep-25: Approved shall be closed | FALSE | [5 empty] | 2025-09-23 | Artefacts not Required | Completed & Approved | Closed before june-2025 | Closed after June
1547 | M816 | MOM | 2023-09-22 |  |  |  | NOC Operationalization |  | Target the 2nd Dry Run on 30th September ’23 with more ONTs, covering GI BB, Point to point, dedicated ILL & Dark fiber by end of L&T. |  | Critical | Open |  |  | 23-Sep-25: Approved shall be closed | [12 empty] | Network | Closed | CLOSED | 23-Sep-25: Approved shall be closed | FALSE | [5 empty] | 2025-09-23 | Artefacts not Required | Completed & Approved | Closed before june-2025 | Closed after June
1548 | M817 | MOM | 2024-09-26 |  |  |  | T&D Environment | AT Process | Defining and aligning with the acceptance criteria for each system in the NOC. |  | NON-Critical | Open |  |  | 16-Oct-25: TnD environment has been build from the limited resources from the Prod | [12 empty] | Applications | OPEN | OPEN | 16-Oct-25: TnD environment has been build from the limited resources from the Prod | TRUE | [7 empty] | Open | Open | Open
1549 | M818 | MOM | 2023-09-26 |  |  |  | Helpdesk |  | Inclusion of Helpdesk and other missing items as per the RFP and solution in the Build. |  | Critical | Open |  |  | 24-Sep-25: Approved and shall be closed, Accordingly Helpdesk LLD Aligning | [12 empty] | Helpdesk (Contact Center) | Closed | [8 empty] | 2025-09-24 | Artefacts not Required | Completed & Approved | Closed before june-2025 | Closed after June
1550 | M819 | MOM | 2023-09-26 |  |  |  | T&D Environment | T&D Environment | Implementation of Test and Development environment. |  | NON-Critical | Open |  |  | [15/09/2025] Clusters are segregated for Production vis-à-vis pre-production | [12 empty] | Applications | Closed | [9 empty] | Artefacts Need to upload | Completed & Approved | Closed before june-2025 | Closed after June
1551 | M82 | MOM | 2023-07-26 |  |  |  | WFM | User Experience | Clear definition and availability of existing filters in WFM dashboards |  | Critical | Open |  |  | 11-Jul-2025:- The dashboard and report filter options should be showcased during the WFM application demonstration. | [12 empty] | Applications/Tools | OPEN | [10 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1552 | M820 | MOM | 2023-09-26 |  |  |  | T&D Environment | T&D Environment | Discussion on the requirements for Test Lab/Staging environment. |  | NON-Critical | Open |  |  | [15/09/2025] Interim T&D is setup, finalised option detailing pending | [12 empty] | Applications | Closed | [9 empty] | Artefacts Need to upload | Completed & Approved | Closed before june-2025 | Closed after June
1553 | M821 | MOM | 2023-10-18 |  |  |  | BSS | CSP Testing | Adding a back button on the payment screen. |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1554 | M822 | MOM | 2023-10-18 |  |  |  | BSS | CSP Testing | Providing guidelines for the CAF upload stage and adding a disclaimer for "Subject to Verification of CAF." |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1555 | M823 | MOM | 2023-10-18 |  |  |  | BSS | CSP Testing | Ensuring offline payment transactions are viewable and mandatory sections of the CAF are highlighted. |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1556 | M824 | MOM | 2023-10-18 |  |  |  | BSS | CSP Testing | Addressing issues with ticket creation, notification, and enquiry handling in the CSP. |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1557 | M825 | MOM | 2023-10-18 |  |  |  | BSS | CSP Testing | Clarifying the bulk upload of leads and the feasibility of integrating such a feature in the CSP. |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1558 | M826 | MOM | 2023-10-18 |  |  |  | BSS | CSP Testing | Resolving user interface issues such as incorrect OTP entry pop-ups, case sensitivity in order ID searches, and real-time synchronization between GIS-OSS for feasibility checks. |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1559 | M827 | MOM | 2023-10-18 |  |  |  | BSS | CSP Testing | Removing unnecessary elements from the UI, aligning GP names with government lists, and modifying the sequence of address fields. |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1560 | M828 | MOM | 2023-10-18 |  |  |  | BSS | CSP Testing | Integrating Google API for auto-populating details based on service location selection. |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1561 | M829 | MOM | 2023-10-18 |  |  |  | BSS | CSP Testing | Ensuring proper display and functionality of various screens within the CSP, including payment and order summary screens. |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1562 | M83 | MOM | 2023-07-26 |  |  |  | WFM | User Experience | Upload of video |  | Critical | Open |  |  | 15-Nov-25:As per OEM this point is not feasible 11 July 2025:- A follow-up discussion with the OEM is required to assess feasibility. If it is found to be unfeasible, a call should be arranged with Sanja | y S | ir al | ong | with the | team & arte |  | fac | ts |  |  | need | s to submit | Applications/Tools | [5 empty] | OEM | [5 empty] | Open | Open | Open
1563 | M830 | MOM | 2023-10-18 |  |  |  | BSS | CSP Testing | Configuring event-based email notifications for actions within the CSP. |  | NON-Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1564 | M831 | MOM | 2023-10-19 |  |  |  | IPDR | Regulatory Compliance | Clarity from the Regulator on IPDR requirements to be obtained by L&T: Discussion on industry best practices and regulatory aspects to be concluded by 26th October '23. |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1679 | M935 | MOM | 2024-01-05 |  |  |  | NSO | Service provisioning | GUI Interface for NSO |  | Critical | Open |  |  | 29-12-2025:- Already present | [7 empty] | Completed |  |  |  |  | Applications/Tools | OPEN | [5 empty] | Pending |  | 2026-12-03 |  |  | Open | Open | Open
1566 | M833 | MOM | 2023-11-03 |  |  |  | NSO | Service Delivery | NSo inventory manager funtionality to check. |  | Critical | Open |  |  | .duplicate | [7 empty] | Duplicate Point |  |  |  |  | Applications/Tools | OPEN |  |  |  |  | Duplicate artifact — refer to M334. |  |  | Duplicate |  |  | Open | Open | Open
1567 | M834 | MOM | 2023-11-03 |  |  |  | NSO | Service Delivery | UD perameters for product based to be prepared. |  | Critical | Open |  |  | 29-dec-2025: Need discussion | [7 empty] | Completed |  |  |  |  | Applications/Tools | OPEN | [5 empty] | Pending |  | 13/03/2026 |  |  | Open | Open | Open
1568 | M835 | MOM | 2023-11-03 |  |  |  | NSO | Service Delivery | Ashish to comeback with Design plan for Inventory Manager at NSO |  | Critical | Open |  |  | 29-dec-2025: Need discussion | [7 empty] | Not Started |  |  |  |  | Applications/Tools | OPEN |  |  |  |  | Need Clarity | [5 empty] | Open | Open | Open
1569 | M836 | MOM | 2023-11-03 |  |  |  | NSO | Service Delivery | Arvindam to comeback with product wise UD perameters |  | Critical | Open |  |  | 29-dec-2025: Need discussion | [7 empty] | Not Started |  |  |  |  | Applications/Tools | OPEN |  |  |  |  | Need Clarity | [5 empty] | Open | Open | Open
1570 | M837 | MOM | 2023-11-03 |  |  |  | NSO | Service Delivery | Additional information for VRF, VLAN , Inner vlan etc to capture in Master DB |  | Critical | Open |  |  | 29-dec-2025: Need discussion.Network design team | [7 empty] | Not Started |  |  |  |  | Applications/Tools | OPEN |  |  |  |  | Jyothi | [5 empty] | Open | Open | Open
1571 | M838 | MOM | 2023-11-03 |  |  |  | NSO | Service Delivery | As per Cisco LLD All 28 types of L2, L3 models to be mapped aginest products |  | Critical | Open |  |  | 29-dec-2025: Need discussion | [7 empty] | Not Started |  |  |  |  | Applications/Tools | OPEN |  |  |  |  | Need Clarity | [5 empty] | Open | Open | Open
1572 | M839 | MOM | 2023-11-03 |  |  |  | NSO | Service Delivery | GL code to be mapped based on subtype GI under sub type Central & State |  | Critical | Open |  |  | 29-dec-2025: Need discussion.NSO requirement ? | [7 empty] | Not Started |  |  |  |  | Applications/Tools | OPEN |  |  |  |  | Jyothi | [5 empty] | Open | Open | Open
1573 | M84 | MOM | 2023-07-26 |  |  |  | WFM | Dashboards | Support for Workforce Management productivity statistics |  | Critical | Open |  |  | 11-Jul-2025:- Various reports should be demonstrated during the WFM application demo to showcase its capabilities. | [12 empty] | Applications/Tools | OPEN | [10 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1577 | M843 | MOM | 2023-11-03 |  |  |  | NSO | Service Delivery | OSS Method of distance from GIS need to comeback with plan |  | Critical | Open | [10 empty] | Not Started |  |  |  |  | Applications/Tools | OPEN |  |  |  |  | OSS Comments (16/03/2026): Not available. |  |  | Not Feasible |  |  | Open | Open | Open
1575 | M841 | MOM | 2023-11-03 |  |  |  | NSO | Service Delivery | Define design plan for House hold services in GPON Level |  | Critical | Open |  |  | 29-dec-2025: Need discussion.infra team | [7 empty] | Not Started |  |  |  |  | Applications/Tools | OPEN |  |  |  |  | Need Clarity | [5 empty] | Open | Open | Open
1576 | M842 | MOM | 2023-11-03 |  |  |  | NSO | Service Delivery | Define Household plan for provisioning as per the GPON plan design |  | Critical | Open | [10 empty] | Not Started |  |  |  |  | Applications/Tools | OPEN |  |  |  |  | Need Clarity | [5 empty] | Open | Open | Open
584 | M11 | MOM | 2023-04-03 |  |  |  | NSO | Functional AT Plan | Use-Cases Testing under NSO |  | Critical | Open | OSS Dashboards |  | 29-dec-2025: Need discussion | [7 empty] | Not Started |  |  |  |  | Applications/Tools | OPEN |  |  |  |  | - 11/03/2026: Received sample document from Manoj. - 12/03/2026: Requested cross‑check with Sandeep sir. - 13/03/2026: Inputs provided by Sandeep sir. - Mail Subject: WFM ATP Document Submission - Action: Sayyad to send approved GPON FAT document. - 16/03/2026: Received GPON FAT document from Sayyad. | [5 empty] | Open | Open | Open
1578 | M844 | MOM | 2023-11-03 |  |  |  | NSO | Service Delivery | Aravindam to update on previous meetings updates to be updated in next in continuous meetings |  | Critical | Open | [10 empty] | Not Started |  |  |  |  | Applications/Tools | OPEN |  |  |  |  | Need Clarity | [5 empty] | Open | Open | Open
1579 | M845 | MOM | 2023-11-17 |  |  |  | Helpdesk |  | Neox Helpdesk Demo: Scheduled for either 23rd or 24th November. |  | Critical | Open | [15 empty] | Helpdesk (Contact Center) | OPEN | [10 empty] | Open | Open | Open
1580 | M846 | MOM | 2023-11-17 |  |  |  | Helpdesk |  | Neox Compliance Confirmation: Closed on 17th November. |  | Critical | open |  |  | 01-Dec-25: Duplucate, Same as M320 11-Sep-25 Same has been Submitted | [12 empty] | Helpdesk (Contact Center) | OPEN | [10 empty] | Open | Open | Open
1581 | M847 | MOM | 2023-11-17 |  |  |  | Helpdesk |  | Reference for 24 Points: Praveen to share the reference of 24 points by 20th November. |  | Critical | open |  |  | 01-Dec-25: Duplucate, Same as M320 | [12 empty] | Helpdesk (Contact Center) | OPEN | [10 empty] | Open | Open | Open
1582 | M848 | MOM | 2023-11-17 |  |  |  | OEM Related | GPON | Closure of Issues with Tejas & Nokia: Letter of confirmation for closure to be submitted on or before 30th November ’23. |  | Critical | Open |  |  | 23-Sep-25: Approved shall be closed | [12 empty] | OEM Related Issues | Closed | CLOSED | 23-Sep-25: Approved shall be closed | FALSE | [5 empty] | 2025-09-23 | Artefacts not Required | Completed & Approved | Closed before june-2025 | Closed after June
1583 | M849 | MOM | 2023-11-17 |  |  |  | OEM Related | GPON | OEM Teams Onboarding: HP & Cisco OEM teams to be onboarded from 20th November '23. |  | Critical | Open |  |  | 23-Sep-25: Approved shall be closed | [12 empty] | OEM Related Issues | Closed | CLOSED | 23-Sep-25: Approved shall be closed | FALSE | [5 empty] | 2025-09-23 | Artefacts not Required | Completed & Approved | Closed before june-2025 | Closed after June
1584 | M85 | MOM | 2023-07-26 |  |  |  | WFM | Improvement | Check if NOC Workforce Management is handled by the proposed WFM tool |  | Critical | Open |  |  | 15-Nov-25:The WFM application is designed to manage field force operations, task assignments, and service delivery. Separate licenses & functionally & user role will be required for managing NOC resources. | 1 | 2025-07-01 | y 20 | 25:- A no | needs to be |  | sen | t t |  |  | o Sa | njay Sir outlining the benefits, potential duplication of work, and any associated drawbacks. | Applications/Tools | OPEN |  |  |  |  | te | [5 empty] | Open | Open | Open
1585 | M850 | MOM | 2023-11-17 |  |  |  | OEM Related |  | Letters from OEMs: Letters from all OEMs, excluding Cisco & HP, to be submitted by 22nd November '23. Letters from Cisco & HP to be submitted by 24th November '23. |  | Critical | Open |  |  | 23-Sep-25: Approved shall be closed | [12 empty] | OEM Related Issues | Closed | CLOSED | 23-Sep-25: Approved shall be closed | FALSE | [5 empty] | 2025-09-23 | Artefacts not Required | Completed & Approved | Closed before june-2025 | Closed after June
1586 | M851 | MOM | 2023-11-28 |  |  |  | Security & Regulatory Compliance | Compliance | Regulatory and Security Requirements: L&T to fast-track the closure of regulatory and security requirements, along with SLA monitoring for the immediate start of business services. |  | Critical | Open |  |  | 28-Nov-25: To discuss with mr Sanjay to get clarifications on the points. Duplicate point. Hence clsoing this point | [12 empty] | Security | OPEN | [10 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1587 | M852 | MOM | 2023-12-12 |  |  |  | NOC Operationalization |  | Submit updated Acceptable Usage Policy |  | Critical | Open |  |  | 16-Oct-25: Submitted for review | [12 empty] | Network | OPEN | OPEN | 16-Oct-25: Submitted for review | TRUE | [7 empty] | Open | Open | Open
1588 | M853 | MOM | 2023-12-12 |  |  |  | Security & Regulatory Compliance | Compliance | Complete configuration of CA signed SSL certificate for all web-based applications |  | Critical | Open |  |  | 28-Nov-25: There are duplicate points; once the main point is closed, these duplicate points can be closed. | [12 empty] | Security | OPEN | [10 empty] | Open | Open | Open
1589 | M854 | MOM | 2023-12-12 |  |  |  | Security & Regulatory Compliance | Compliance | Obtain T-Fiber’s approval for annual external VAPT testing |  | Critical | Open |  |  | 28-Nov-25: VAPT is going on, once VAPT is done points will be closed. Audit done by Allied Boston. And further external audit to be done by TFiber vendor | [12 empty] | Security | OPEN | [10 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1590 | M855 | MOM | 2023-12-12 |  |  |  | Security & Regulatory Compliance | Compliance | Submit Vulnerability Management Policy as part of Patch Management Policy |  | Critical | Open |  |  | 28-Nov-25: Document preparation in progress once done points will be closed. | [12 empty] | Security | OPEN | [10 empty] | Open | Open | Open
1591 | M856 | MOM | 2023-12-12 |  |  |  | Security & Regulatory Compliance | Compliance | Submit a list of Security Policy documents and all SOPs, Checklist |  | Critical | Open |  |  | 28-Nov-25: There are duplicate points; once the main point is closed, these duplicate points can be closed. | [12 empty] | Security | OPEN | [10 empty] | Open | Open | Open
1592 | M857 | MOM | 2023-12-12 |  |  |  | Security & Regulatory Compliance | Compliance | Deliver security policy documents and SOPs for launch |  | Critical | Open |  |  | 28-Nov-25: There are duplicate points; once the main point is closed, these duplicate points can be closed. | [12 empty] | Security | OPEN | [10 empty] | Open | Open | Open
1593 | M858 | MOM | 2023-12-12 |  |  |  | Security & Regulatory Compliance | Compliance | Upload RMC MoMs to shared folder and grant access to T-Fiber |  | Critical | Open |  |  | 28-Nov-25: Gathering artifacts from other teams | [12 empty] | Security | OPEN | [10 empty] | Open | Open | Open
1594 | M859 | MOM | 2023-12-12 |  |  |  | Security & Regulatory Compliance | Compliance | Provide comments against each sub-point in Internal Audit Report |  | Critical | Open |  |  | 28-Nov-25: VAPT is going on, once VAPT is done points will be closed | [12 empty] | Security | OPEN | [10 empty] | Open | Open | Open
1595 | M86 | MOM | 2023-07-26 |  |  |  | WFM | Improvement | Coverage of Planned Event Manpower assignment by WFM solution |  | Critical | Open |  |  | 15-Nov-25:OT System Dependency | [12 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1596 | M860 | MOM | 2023-12-12 |  |  |  | Security & Regulatory Compliance | Compliance | Submit Asset Management policy |  | Critical | Open |  |  | 28-Nov-25: There are duplicate points; once the main point is closed, these duplicate points can be closed. Duplicate point. Hence clsoing this point | [12 empty] | Security | OPEN | [10 empty] | Open | Open | Open
1597 | M861 | MOM | 2023-12-12 |  |  |  | Security & Regulatory Compliance | Compliance | Submit onboarding/offboarding policy |  | Critical | Open |  |  | 28-Nov-25: There are duplicate points; once the main point is closed, these duplicate points can be closed. Duplicate point. Hence clsoing this point | [12 empty] | Security | OPEN | [10 empty] | Open | Open | Open
1598 | M862 | MOM | 2023-12-12 |  |  |  | Security & Regulatory Compliance | Compliance | Report on the management of physical and environmental security |  | Critical | Open | [15 empty] | Security | Closed | [8 empty] | 2025-11-12 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\NW-Security\M862_04-Nov-25.pdf | Completed & Approved | Closed after 07-Nov-25 | Open
1599 | M863 | MOM | 2023-12-12 |  |  |  | Security & Regulatory Compliance | Compliance | Provide review of work scope for External VAPT prior |  | Critical | Open |  |  | 28-Nov-25: VAPT is going on, once VAPT is done points will be closed | [12 empty] | Security | OPEN | [8 empty] | 2025-12-19 |  | Completed &Approved | Completed &Approved | Completed &Approved
1600 | M864 | MOM | 2023-12-12 |  |  |  | Security & Regulatory Compliance | Compliance | Close Vulnerability & patch management after audit document is finalized |  | Critical | Open |  |  | 28-Nov-25: VAPT is going on, once VAPT is done points will be closed | [12 empty] | Security | OPEN | [10 empty] | Open | Open | Open
1601 | M865 | MOM | 2023-12-12 |  |  |  | Security & Regulatory Compliance | Compliance | Submit Cryptography encryption model document |  | Critical | Open |  |  | 28-Nov-25: There are duplicate points; once the main point is closed, these duplicate points can be closed. | [12 empty] | Security | OPEN | [10 empty] | Open | Open | Open
1602 | M866 | MOM | 2023-12-12 |  |  |  | OEM Related | Tejas Related | Submit updated undertakings for Tejas - Alepo and Nokia |  | Critical | Open |  |  | 23-Sep-25: Approved shall be closed | [12 empty] | OEM Related Issues | Closed | CLOSED | 23-Sep-25: Approved shall be closed | FALSE | [5 empty] | 2025-09-23 | Artefacts not Required | Completed & Approved | Closed before june-2025 | Closed after June
1603 | M867 | MOM | 2023-12-12 |  |  |  | Security & Regulatory Compliance | Compliance | Provide compliance with supporting documents for all applications & devices |  | Critical | Open |  |  | 28-Nov-25: To discuss with mr Sanjay to get clarifications on the points | [12 empty] | Security | OPEN | [10 empty] | Open | Open | Open
1604 | M868 | MOM | 2023-12-12 |  |  |  | Security & Regulatory Compliance | Compliance | Submit document on Privilege management |  | Critical | Open | [15 empty] | Security | Closed | [8 empty] | 2025-11-12 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\NW-Security\M1020_31-Oct-25.pdf | Completed & Approved | Closed after 07-Nov-25 | Open
1605 | M869 | MOM | 2023-12-12 |  |  |  | Security & Regulatory Compliance | Compliance | Submit a password management policy for the entire Network |  | Critical | Open |  |  | 28-Nov-25: Document preparation in progress once done points will be closed. | [12 empty] | Security | OPEN | [10 empty] | Open | Open | Open
1606 | M87 | MOM | 2023-07-26 |  |  |  | WFM | Handbook & SOPs | Overall fitment of WFM in E2E applications architecture with integration touchpoints highlighted, along with the WFM flows |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1607 | M870 | MOM | 2023-12-12 |  |  |  | Security & Regulatory Compliance | Compliance | Disable all Remote access |  | Critical | Open |  |  | 28-Nov-25: To discuss with mr Sanjay to get clarifications on the points | [12 empty] | Security | OPEN | [10 empty] | Open | Open | Open
1608 | M871 | MOM | 2023-12-12 |  |  |  | Security & Regulatory Compliance | Compliance | Submit artefacts for all banners |  | Critical | Open |  |  | 28-Nov-25: Gathering artifacts from other teams | [12 empty] | Security | OPEN | [10 empty] | Open | Open | Open
1609 | M872 | MOM | 2023-12-12 |  |  |  | Security & Regulatory Compliance | Compliance | Submit checklist of internal/external, Trusted, untrusted zones |  | Critical | Open | [15 empty] | Security | Closed | [8 empty] | 2025-10-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\NW-Security\M873_29-Oct-25.pdf | Closed | Closed After 14-Oct | Open
1610 | M873 | MOM | 2023-12-12 |  |  |  | Security & Regulatory Compliance | Compliance | Submit details of the policies for DMZ and internet-facing interfaces |  | Critical | Open | [15 empty] | Security | Closed | [8 empty] | 2025-10-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\NW-Security\M873_29-Oct-25.pdf | Closed | Closed After 14-Oct | Open
1611 | M874 | MOM | 2023-12-12 |  |  |  | Security & Regulatory Compliance | Compliance | Re-audit of Section 4.8 with the response captured in 4 sub-points |  | Critical | Open |  |  | 28-Nov-25: VAPT is going on, once VAPT is done points will be closed | [12 empty] | Security | OPEN | [10 empty] | Open | Open | Open
1612 | M875 | MOM | 2023-12-12 |  |  |  | Security & Regulatory Compliance | Compliance | Submit list of APIs for all applications with risk information & conduct detailed audit on API security |  | Critical | Open |  |  | 28-Nov-25: VAPT is going on, once VAPT is done points will be closed | [12 empty] | Security | OPEN | [10 empty] | Open | Open | Open
1613 | M876 | MOM | 2023-12-12 |  |  |  | Security & Regulatory Compliance | Compliance | Submit Security Endpoints List of Infrastructure, Workstations, etc. |  | Critical | Open |  |  | 28-Nov-25: To discuss with mr Sanjay to get clarifications on the points. Completed . Also Screenshot has been taken during security audit . | [12 empty] | Security | OPEN | [10 empty] | Open | Open | Open
1614 | M877 | MOM | 2023-12-12 |  |  |  | Security & Regulatory Compliance | Compliance | Provide a list of applications generating Syslog, not generating syslog |  | Critical | Open |  |  | 28-Nov-25: To discuss with mr Sanjay to get clarifications on the points. integration of application with syslog is still undergoing will; be submitted soon. | [12 empty] | Security | OPEN | [10 empty] | Open | Open | Open
1615 | M878 | MOM | 2023-12-12 |  |  |  | Security & Regulatory Compliance | Compliance | Submit DR reports for all Applications that have been tested for DC-DR switchover |  | Critical | Open |  |  | 28-Nov-25: There are duplicate points; once the main point is closed, these duplicate points can be closed. DC-dr failover will be shown during FATS for Application | [12 empty] | Security | OPEN | [10 empty] | Open | Open | Open
1616 | M879 | MOM | 2023-12-12 |  |  |  | Security & Regulatory Compliance | Compliance | Submit attendance list for security awareness trainings, ensure all NOC resources attend |  | Critical | Open |  |  | 28-Nov-25: To discuss with mr Sanjay to get clarifications on the points. Last training conducted on 23 May25, and mail sent | [12 empty] | Security | OPEN | [10 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1617 | M88 | MOM | 2023-07-26 |  |  |  | WFM | Handbook & SOPs | Clarity required on the scope of WFM under Phase-2 and sharing of Phase-1 & 2 scope with T-Fiber |  | Critical | Open |  |  | 15-Nov-25:BSS Integration was on phase-II however it has integrated in phase-I | [12 empty] | Applications/Tools | OPEN | [10 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1618 | M880 | MOM | 2023-12-12 |  |  |  | Security & Regulatory Compliance | Compliance | Finalise the duration and frequency of backup, provide storage utilisation report weekly, provide config backup details of all routers/switches/devices, submit weekly report capturing online & offline storage status |  | Critical | Open |  |  | 28-Nov-25: Document preparation in progress once done points will be closed. The point is already under discussion and duration of back up has been already mentioned as per ISO 27001 Data retention policy | . C | ustoi | mer | mat tailo | t as per the |  | ir | req |  |  | uire | ment | Security | OPEN |  |  |  |  | r i | [5 empty] | Open | Open | Open
1619 | M881 | MOM | 2023-12-15 |  |  |  | WFM |  | WFM Tool Demonstration: L&T to arrange a demonstration of the WFM tool usage for field operations soon. |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1620 | M882 | MOM | 2023-12-15 |  |  |  | WFM |  | WFM Mobile App Features: L&T to provide clarity on GPS tracking availability, polling frequency, photo upload feature, file size limitations, and supported Android and iOS versions. |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1621 | M883 | MOM | 2023-12-15 |  |  |  | WFM |  | Offline Data Storage: L&T to address the lack of offline data storage feature in the mobile application. |  | Critical | Open |  |  | 11-Jul-2025:- Offline data, such as images and documents, can be uploaded either from the mobile gallery or directly using the camera. To support the storage of LIDAR survey data and GIS images, an 80 TB N | AS | stora | ge s | ystem has | ready been d |  | epl | oye |  |  | d at | the NOC Data Center | Applications/Tools | OPEN |  |  |  |  | al | [5 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1622 | M884 | MOM | 2023-12-15 |  |  |  | WFM |  | Workflow Simulation: L&T to simulate a fiber cut and explain the workflow for clearing the fault and updating GIS. |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1623 | M885 | MOM | 2023-12-15 |  |  |  | WFM |  | Security Assurance: L&T to provide the NDA signed with M/S Lepton, assure API security, and share the contract copy. |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1624 | M886 | MOM | 2023-12-15 |  |  |  | GIS | GIS Related | Geo-fencing: L&T to explain how geo-fencing shall work for a fiber route and how it will be assigned for Mandal and GP locations. |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1625 | M887 | MOM | 2023-12-15 |  |  |  | WFM | GIS Completion | Ticket Allocation: L&T to start manual ticket allocation and freeze the process for node and link ticket allocation. |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1626 | M888 | MOM | 2023-12-15 | P3 |  |  | NOC Operationalization | Operational Handbook | Operations Handbook: L&T to share document forms from the Operations Handbook to be used by the WFM app. |  | Critical | Open | [15 empty] | Network | OPEN |  |  |  | Documentation | [6 empty] | Open | Open | Open
1627 | M889 | MOM | 2023-12-15 |  |  |  | WFM |  | Summary Dashboards/Management Reports: L&T to provide inputs based on Operations best practices for weekly/monthly management reports from the WFM package. |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1628 | M89 | MOM | 2023-07-26 |  |  |  | WFM | Integration | Integration with Material Management systems, ERP systems, and On-Demand dashboards to be covered in Phase-2 |  | Critical | Open |  |  | 15-Nov-25:For GI service delivery, the ONT inventory management feature has been given into the WFM application & integration completed between web & mobile also with BSS . application supports ONT authent | ica | tion | and | inventory | acking. Addi |  | tio | nal |  |  | ly, | various dashboards have been provided within the WFM application to enhance monitoring and management capabilities | Applications/Tools | OPEN |  |  |  |  | tr | [5 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1629 | M890 | MOM | 2023-12-15 |  |  |  | WFM |  | The urgency for L&T to demonstrate the WFM tool for field operations and to provide detailed information on its features and capabilities. |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1630 | M891 | MOM | 2023-12-15 |  |  |  | WFM |  | The necessity for L&T to address the absence of offline data storage in the mobile application and to simulate a fiber cut workflow. |  | Critical | Open |  |  | 15-Nov-25:Duplicate with Point- 237 | [12 empty] | Applications/Tools | [11 empty] | Open | Open | Open
1631 | M892 | MOM | 2023-12-15 |  |  |  | WFM |  | The requirement for L&T to assure security in the WFM package, including API security and geo-fencing capabilities. |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1632 | M893 | MOM | 2023-12-15 |  |  |  | WFM |  | The expectation for L&T to provide comprehensive management reports and dashboards to support process improvements and operational efficiency. |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1633 | M894 | MOM | 2023-12-19 |  |  |  | BSS |  | BSS Test Environment: VP-Program, T-Fiber requested BSS-SME, L&T to investigate and expedite the resolution of the slowness in the BSS Test Environment. |  | NON-Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1634 | M895 | MOM | 2023-12-19 |  |  |  | BSS |  | Performance Benchmarking Tools: BSS-SME, L&T to explore web-based analytic tools for performance benchmarking. |  | NON-Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1635 | M896 | MOM | 2023-12-19 |  |  |  | BSS |  | Status of Action Items: VP-Program, T-Fiber emphasized that action items marked as "Completed" should only be rendered "Closed" upon concurrence from T-Fiber. |  | NON-Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1636 | M897 | MOM | 2023-12-19 |  |  |  | BSS |  | SMS and CSP Integration: BSS-SME, L&T to implement SMS dispatch notification in CSP and include a link to the CSP page for T-Fiber USER to Approve or Reject. |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1637 | M898 | MOM | 2023-12-19 |  |  |  | BSS |  | Product Catalogue Demo: SVP, T-Fiber requested a demo to showcase the configurable product catalogue feature. |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1638 | M899 | MOM | 2023-12-19 |  |  |  | BSS |  | Backend Validation Demo: Director-P&E, T-Fiber asked for a demo of Backend Validation and a document with validation steps. |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1639 | M9 | MOM | 2023-04-03 |  |  |  | NOC Operationalization | Full NOC Readiness | Demonstration of Repository Module |  | Critical | Open | Helpdesk |  | 24-Sep-25: Approved and shall be closed, its NAS Created in NOC for all Domains documentaton | [12 empty] | Network | Closed | [8 empty] | 2025-09-24 | \\172.28.9.23\tnocreports | Completed & Approved | Closed before june-2025 | Closed after June
1640 | M90 | MOM | 2023-07-26 |  |  |  | WFM | Improvement | Proposed WFM solution support field personnel to schedule appointments with end customers |  | Critical | Open |  |  | 15-Nov-25:Customer appointment is being handled by BSS and FE appointment by WFM | [12 empty] | Applications/Tools | OPEN | [10 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1641 | M900 | MOM | 2023-12-19 |  |  |  | BSS |  | Page Load Benchmark: Director-P&E, T-Fiber requested a benchmark for page loading to be defined. |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1642 | M901 | MOM | 2023-12-19 |  |  |  | BSS |  | Payment Gateway Integration: BSS-SME, L&T confirmed integration is completed with a test account. |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1643 | M902 | MOM | 2023-12-19 |  |  |  | BSS |  | BSS E2E Demo: Chief Delivery Officer, L&T proposed to have the E2E BSS Demo on 4th July '23, with features to be confirmed by 1st July '23. |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1644 | M903 | MOM | 2023-12-19 |  |  |  | WFM |  | Mobile App & WFM: SVP, T-Fiber requested clarity on the number of mobile apps and urged L&T to freeze the scope in consultation with MSI B and C. Demo with M/S Lepton scheduled for 21st June '23. |  | Critical | Open |  |  | 15-Nov-25:Duplicate with Point- 214 | [12 empty] | Applications/Tools | [11 empty] | Open | Open | Open
1645 | M904 | MOM | 2023-12-19 |  |  |  | GIS | GIS Completion | BSS-SME, L&T to ensure Dark Fiber with BSS and WFM flows can be shown by 30th December '23. |  | Critical | Open |  |  | 15-Nov-25:Dark fiber integration has been completed with the OLD BSS-WFM system, and a demonstration has been provided. The new BSS system now needs to be prepared to support this integration, Dependency O | n N | ew BS | S | [9 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1646 | M905 | MOM | 2023-12-19 |  |  |  | NOC Operationalization | Launch Readiness | T-Cell, T-VPN, and GI-ILL Completion: SVP, T-Fiber called for these to be completed on priority before the visit by Hon’ Minister. |  | Critical | Open |  |  | 16-Oct-25: Covered in NSO implementation Plan | [12 empty] | Network | OPEN | Duplicate | 16-Oct-25: Covered in NSO implementation Plan | FALSE | [7 empty] | Open | Open | Open
1647 | M906 | MOM | 2023-12-19 |  |  |  | GIS | Feasibility Logic | Feasibility Logic: SVP, T-Fiber asked for the feasibility logic to include S1, S2 splitters and to be demonstrated in the next demo. |  | Critical | Open |  |  | 15-Nov-25:Dependency On OSS Splitter View has been given to OSS team | [12 empty] | Applications/Tools | OPEN | [10 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1648 | M907 | MOM | 2023-12-19 |  |  |  | OSS | Feasibility Logic | Bandwidth Feasibility Logic: Director-P&E, T-Fiber requested the logic for Bandwidth feasibility in the backhaul to be provisioned and operationalised immediately. |  | Critical | Open |  |  | This point not related to GIS,11th July 2025:- As discussed with Sanjay Sir, this points need to be move to the OSS team. | [12 empty] | Applications/Tools | OPEN |  | OPEN | FALSE | [7 empty] | Open | Open | Open
1649 | M908 | MOM | 2023-12-19 |  |  |  | BSS | Resource Augmentation | NMS Works Resources: SVP, T-Fiber requested a discussion with EVP, T-Fiber on the adequacy of NMS works resources. |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1650 | M909 | MOM | 2023-12-19 |  |  |  | BSS | BSS | Repository Module for Document Upload: BSS-SME, L&T to ensure the module is available in CRM and discussed with OEM. |  | NON-Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1651 | M91 | MOM | 2023-07-26 |  |  |  | WFM | Handbook & SOPs | Finalization of Operational Processes linked to WFM workflows |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1652 | M910 | MOM | 2023-12-19 |  |  |  | BSS | WhatsApp | WhatsApp Integration: BSS-SME, L&T to incorporate advanced features into WhatsApp Integration with CSP. |  | NON-Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1653 | M911 | MOM | 2023-12-19 |  |  |  | BSS |  | UI/UX Resource: BSS-SME, L&T updated that an internal UI/UX resource has been onboarded. |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1654 | M912 | MOM | 2023-12-19 |  |  |  | BSS |  | Discussions on the BSS roadmap, including the status of action items from the dry run and CSP testing exercise. |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1655 | M913 | MOM | 2023-12-19 |  |  |  | Field Related | District Completion Target | The urgency for STL to complete E2E for additional districts by 07th April '23 and the need to resolve issues impacting project progress. |  | NON-Critical | Open | [15 empty] | Field Related issues | OPEN |  |  |  | Project Team | [6 empty] | Open | Open | Open
1656 | M914 | MOM | 2023-12-19 |  |  |  | NOC Operationalization |  | The necessity for STL to complete T-NOC Operationalization by 6th April 2023 to begin commercialization. |  | Critical | Open | [15 empty] | Network | Closed |  |  |  | Not related to delivery |  |  |  |  | 2025-09-22 | Artefacts not Required | Completed & Approved | Closed before june-2025 | Closed after June
1657 | M915 | MOM | 2023-12-19 |  |  |  | Field Related | Resource Augmentation | The requirement for STL to address resource productivity issues and ensure sufficient resources for project completion. |  | NON-Critical | Open | [15 empty] | Field Related issues | OPEN |  |  |  | Project Team | [6 empty] | Open | Open | Open
1658 | M916 | MOM | 2023-12-19 |  |  |  | Field Related | Payment Related | The need for T-Fiber to expedite payment processes and for STL to provide a senior resource to orchestrate project completion efforts. |  | NON-Critical | Open | [15 empty] | Field Related issues | OPEN |  |  |  | Project Team | [6 empty] | Open | Open | Open
1659 | M917 | MOM | 2023-12-19 |  |  |  | NOC Operationalization |  | The presentation of a comprehensive T-NOC operationalisation plan by STL, with clear phases and readiness stages. |  | Critical | Open | [15 empty] | Network | Closed |  |  |  | Not related to delivery |  |  |  |  | 2025-09-22 | Artefacts not Required | Completed & Approved | Closed before june-2025 | Closed after June
1660 | M918 | MOM | 2023-12-19 |  |  |  | Field Related | Zonal Path connectivity | The completion of zonal paths and the delivery of districts within the committed timelines. |  | NON-Critical | Open | [15 empty] | Field Related issues | OPEN |  |  |  | Project Team | [6 empty] | Open | Open | Open
1661 | M919 | MOM | 2023-12-28 |  |  |  | NOC Operationalization | Launch Readiness | Achieve T-VPN and T-DILL completion by 31st Jan '24; confirm Dark Fiber P2P link target date later. |  | Critical | Open |  |  | 16-Oct-25: Covered in NSO implementation Plan | [12 empty] | Network | OPEN | Duplicate | 16-Oct-25: Covered in NSO implementation Plan | FALSE | [7 empty] | Open | Open | Open
1662 | M92 | MOM | 2023-07-26 |  |  |  | WFM | Resource Related | Perpetual licenses for WFM |  | Critical | Open |  |  | 15-Nov-25:TFIBER is a critical dependency for closing the WFM license | [12 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1663 | M920 | MOM | 2023-12-28 |  |  |  | NOC Operationalization | Launch Readiness | Ensure basic products are available by end of April '24; complete all 28 products within 2 months beyond April '24. |  | Critical | Open |  |  | 16-Oct-25: Covered in NSO implementation Plan | [12 empty] | Network | OPEN | Duplicate | 16-Oct-25: Covered in NSO implementation Plan | FALSE | [7 empty] | Open | Open | Open
1664 | M921 | MOM | 2023-12-28 |  |  |  | NSO | Service Delivery | Develop Service Delivery – Provisioning through OSS module; address potential failures and industry best practices. |  | Critical | Open | [10 empty] | Not Started |  |  |  |  | Applications/Tools | OPEN |  |  |  |  | Jyothi | [5 empty] | Open | Open | Open
1665 | M922 | MOM | 2023-12-28 |  |  |  | OEM Related | Service Delivery | Manual KPI for service assurance due to lack of OEM confirmation; address concerns about NSO and OSS use. |  | Critical | Open |  |  | 16-Oct-25: Manual KPIs are submitted as part of interim NOC | [12 empty] | OEM Related Issues | OPEN | CLOSED | 16-Oct-25: Manual KPIs are submitted as part of interim NOC | FALSE | [7 empty] | Open | Open | Open
1666 | M923 | MOM | 2023-12-28 |  |  |  | OEM Related |  | Align L&T and OEM with product vision and delivery cadence; consider product development strategy. |  | Critical | Open |  |  | 23-Sep-25: Approved shall be closed | [12 empty] | OEM Related Issues | Closed | CLOSED | 23-Sep-25: Approved shall be closed | FALSE | [5 empty] | 2025-09-23 | Artefacts not Required | Completed & Approved | Closed before june-2025 | Closed after June
1667 | M924 | MOM | 2023-12-28 |  |  |  | NSO | Resource Augmentation | NSO resource available from 3rd January '24; ensure readiness to operate remotely and train L&T resources. |  | Critical | Open | [10 empty] | Not Started |  |  |  |  | Applications/Tools | OPEN |  |  |  |  | Need Clarity | [5 empty] | Open | Open | Open
1668 | M925 | MOM | 2023-12-28 |  |  |  | NOC Operationalization | Launch Readiness | Conduct Dry Run for 3 Products (GI-BB, T-CELL, Dark Fiber) on 5th January '24 with BSS & WFM; share date soon. |  | Critical | Open |  |  | 16-Oct-25:Covered in BSS Operationalization | [12 empty] | Network | OPEN | OPEN | 16-Oct-25:Covered in BSS Operationalization | TRUE | [7 empty] | Open | Open | Open
1669 | M926 | MOM | 2023-12-28 |  |  |  | NOC Operationalization | Communication Matrix | Initiate daily meetings with T-Fiber; share progress updates daily. |  | Critical | Open |  |  | 23-Sep-25: Approved shall be closed | [12 empty] | Network | Closed | CLOSED | 23-Sep-25: Approved shall be closed | FALSE | [5 empty] | 2025-09-23 | Artefacts not Required | Completed & Approved | Closed before june-2025 | Closed after June
1670 | M927 | MOM | 2023-12-28 |  |  |  | NOC Operationalization | O&M Related | Start daily uptime report immediately; resolve duplicate TroubleTicket issue within the week. |  | Critical | Open |  |  | 24-Sep-25: Approved and shall be closed | [12 empty] | Network | Closed | [8 empty] | 2025-09-24 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\M927 | Completed & Approved | Closed before june-2025 | Closed after June
1671 | M928 | MOM | 2023-12-28 |  |  |  | Security & Regulatory Compliance | Compliance | Clarify NOC resource roles and seating; discuss and fix scope for external audit by 3rd Jan '24; conduct External Audit by 31st January '24. |  | Critical | Open |  |  | 28-Nov-25: Document preparation in progress once done points will be closed. Audit done by Allied Boston. And further external audit to be done by TFiber vendor. Scope has been submitted to customer for e | xte | rnal | Audi | t. NOC te | role and KR |  | A s | har |  |  | ed w | ith Tfiber | Security | OPEN |  |  |  |  | ams | [5 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1672 | M929 | MOM | 2023-12-28 |  |  |  | Helpdesk |  | Address maturity of the Helpdesk; clarify integration aspects and ensure Helpdesk is ready to handle calls. |  | Critical | Open | [15 empty] | Helpdesk (Contact Center) | OPEN | [10 empty] | Open | Open | Open
1673 | M93 | MOM | 2023-07-26 |  |  |  | WFM | Handbook & SOPs | To check for potential overlapping functions between proposed WFM app and GIS O&M app, and accordingly streamline the Operational process |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1674 | M930 | MOM | 2023-12-28 |  |  |  | NOC Operationalization | Launch Readiness | Cover all requirements in the roadmap with completion dates; explore standard templates for SLA reports to settle invoices with BBNL. |  | Critical | Open |  |  | 23-Sep-25: Approved shall be closed | [12 empty] | Network | Closed | CLOSED | 23-Sep-25: Approved shall be closed | FALSE | [5 empty] | 2025-09-23 | Artefacts not Required | Completed & Approved | Closed before june-2025 | Closed after June
1675 | M931 | MOM | 2023-12-28 |  |  |  | NOC Operationalization | O&M Related | Provide clarity on Alarm Correlation, cross-domain RCA, SIA, Helpdesk design, Network and Service Topology. |  | Critical | Open |  |  | 16-Oct-25: Covered in OSS implementation plan | [12 empty] | Network | OPEN | Duplicate | 16-Oct-25: Covered in OSS implementation plan | FALSE | [7 empty] | Open | Open | Open
1676 | M932 | MOM | 2023-12-28 |  |  |  | NOC Operationalization | Launch Readiness | Deliver NOC before the end of T3 as mandated by EVP, T-Fiber. |  | Critical | Open |  |  | 23-Sep-25: Approved shall be closed | [12 empty] | Network | Closed | CLOSED | 23-Sep-25: Approved shall be closed | FALSE | [5 empty] | 2025-09-23 | Artefacts not Required | Completed & Approved | Closed before june-2025 | Closed after June
1677 | M933 | MOM | 2024-01-05 |  |  |  | BSS | BSS | BSS readiness |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1678 | M934 | MOM | 2024-01-05 |  |  |  | BSS | Product category | Unique ID – Naming Convention |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1565 | M832 | MOM | 2023-11-03 |  |  |  | NSO | Service Delivery | UD,SD Peramaters to be captured. |  | Critical | Open |  |  | 29-12-2025:- Captured by SCCM | [7 empty] | Completed |  |  |  |  | Applications/Tools | OPEN | [5 empty] | Pending |  | 13/03/2026 |  |  | Open | Open | Open
1680 | M936 | MOM | 2024-01-05 |  |  |  | BSS | Billing Related | Payment Approach & Integration |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1681 | M937 | MOM | 2024-01-05 |  |  |  | BSS | Billing Related | Invoice Template |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1682 | M938 | MOM | 2024-01-05 |  |  |  | BSS | Billing Related | Integration of Bill Desk & Other Points |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1683 | M939 | MOM | 2024-01-18 |  |  |  | BSS | Product category | BSS progress session for Dark Fiber |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1684 | M94 | MOM | 2023-07-26 |  |  |  | WFM | Improvement | Manual overwrite of data |  | Critical | Open |  |  | 11-Jul-2025:-WFM does not allow any manual data overwrite scenarios | [12 empty] | Applications/Tools | OPEN | [10 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1685 | M940 | MOM | 2024-01-18 |  |  |  | OSS | Integration | Integrate live data for location feasibility |  | Critical | Open | Gtech |  | This point not related to GIS,External Feasibility Tool is required ,11th July 2025:- As discussed with Sanjay Sir, this points need to be move to the OSS team. | [12 empty] | Applications/Tools | OPEN |  | OPEN | FALSE | [7 empty] | Open | Open | Open
1686 | M941 | MOM | 2024-01-18 |  |  |  | OSS | Integration | Review and align ‘Ready for Service’ nomenclature |  | Critical | Open | Gtech |  | This point not related to GIS, 11th July 2025:-this point needs to be discussed with Siva Sir to explore the possibility of accommodating the feature in the respective application, as it is not related to | GIS | [11 empty] | Applications/Tools | OPEN | Need clarity on this point | OPEN | FALSE | [7 empty] | Open | Open | Open
1687 | M942 | MOM | 2024-01-18 |  |  |  | BSS | CRM | Implement auto-population of fields in CRM |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1688 | M943 | MOM | 2024-01-18 |  |  |  | BSS |  | Implement user access control for RFO to RFS conversion |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1689 | M944 | MOM | 2024-01-18 |  |  |  | BSS | GIS | Integrate BSS with GIS for distance calculation |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1690 | M945 | MOM | 2024-01-18 |  |  |  | BSS |  | Provide updates and roadmap for Lead/Opportunity/Order conversion process |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1691 | M946 | MOM | 2024-01-18 |  |  |  | BSS |  | Implement Mandal to GP and Mandal to Mandal Dark fiber service |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1692 | M947 | MOM | 2024-01-18 |  |  |  | BSS |  | Clarify the list of individuals involved in BSS operations |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1693 | M948 | MOM | 2024-01-18 |  |  |  | BSS |  | Resolve document upload feature with order tagging |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1694 | M949 | MOM | 2024-01-18 |  |  |  | BSS |  | Prepare for soft launch in accordance with management's direction |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1695 | M95 | MOM | 2023-07-26 |  |  |  | WFM | User Experience | Verification process for checking whether the field technician has gone to the required location or not. |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1696 | M950 | MOM | 2024-01-18 |  |  |  | BSS |  | Upload BSNL locations for demonstration and discuss GIS integration and document repository issues |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1697 | M951 | MOM | 2024-01-18 |  |  |  | BSS |  | Confirm timeline for GI-BB and T-Cell |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1698 | M952 | MOM | 2024-01-18 |  |  |  | BSS |  | Discuss Route and Bridge Mode for Internet Leased Line product |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1699 | M953 | MOM | 2024-01-24 |  |  |  | NOC Operationalization |  | NOC Readiness Review |  | Critical | Open |  |  | 23-Sep-25: Approved shall be closed | [12 empty] | Network | Closed | CLOSED | 23-Sep-25: Approved shall be closed | FALSE | [5 empty] | 2025-09-23 | Artefacts not Required | Completed & Approved | Closed before june-2025 | Closed after June
1700 | M954 | MOM | 2024-01-24 |  |  |  | NOC Operationalization |  | Ensure full delivery of NOC including field O&M and basic six products |  | Critical | Open |  |  | 23-Sep-25: Approved shall be closed | [12 empty] | Network | Closed | CLOSED | 23-Sep-25: Approved shall be closed | FALSE | [5 empty] | 2025-09-23 | Artefacts not Required | Completed & Approved | Closed before june-2025 | Closed after June
1701 | M955 | MOM | 2024-01-24 |  |  |  | NOC Operationalization |  | Confirm readiness of all NOC modules including ticketing, Helpdesk and WFM |  | Critical | Open |  |  | 16-Oct-25: Covered in NOC go-live plan | [12 empty] | Network | OPEN | Duplicate | 16-Oct-25: Covered in NOC go-live plan | FALSE | [7 empty] | Open | Open | Open
1702 | M956 | MOM | 2024-01-24 |  |  |  | NOC Operationalization |  | Deliver service inventory module |  | Critical | Open |  |  | 16-Oct-25: Service inventory solution deployed under review | [12 empty] | Network | OPEN | OPEN | 16-Oct-25: Service inventory solution deployed under review | TRUE | [7 empty] | Open | Open | Open
1703 | M957 | MOM | 2024-01-24 |  |  |  | NOC Operationalization |  | Create a tracker sheet for conditional approvals and workshop points |  | Critical | Open |  |  | 16-Oct-25: Covered in all Domain trackers | [12 empty] | Network | OPEN | Duplicate | 16-Oct-25: Covered in all Domain trackers | FALSE | [7 empty] | Open | Open | Open
1704 | M958 | MOM | 2024-01-24 |  |  |  | NOC Operationalization |  | Submit detailed plan for module-wise readiness |  | Critical | Open |  |  | 23-Sep-25: Approved shall be closed | [12 empty] | Network | Closed | CLOSED | 23-Sep-25: Approved shall be closed | FALSE | [5 empty] | 2025-09-23 | Artefacts not Required | Completed & Approved | Closed before june-2025 | Closed after June
1705 | M959 | MOM | 2024-01-24 |  |  |  | NOC Operationalization |  | Present documentation for automation of 6 products |  | Critical | Open |  |  | 16-Oct-25: Covered in BSS Operationalization | [12 empty] | Network | OPEN | Duplicate | 16-Oct-25: Covered in BSS Operationalization | FALSE | [7 empty] | Open | Open | Open
1706 | M96 | MOM | 2023-08-01 |  |  |  | Helpdesk | User Experience | Toll Free-Number |  | NON-Critical | Open |  |  | 11-09-2025: Same as T366(472) Closed | [12 empty] | Helpdesk (Contact Center) | Closed | [8 empty] | 2025-07-19 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\T366 | Completed & Approved | Closed before june-2025 | Closed after June
1707 | M960 | MOM | 2024-01-24 |  |  |  | NOC Operationalization |  | Submit package for NOC readiness, roadmaps, and sheets |  | Critical | Open |  |  | 23-Sep-25: Approved shall be closed | [12 empty] | Network | Closed | CLOSED | 23-Sep-25: Approved shall be closed | FALSE | [5 empty] | 2025-09-23 | Artefacts not Required | Completed & Approved | Closed before june-2025 | Closed after June
1708 | M961 | MOM | 2024-01-24 |  |  |  | NOC Operationalization |  | Engage OEMs till end-to-end stabilization of services |  | Critical | Open |  |  | 23-Sep-25: Approved shall be closed | [12 empty] | Network | Closed | CLOSED | 23-Sep-25: Approved shall be closed | FALSE | [5 empty] | 2025-09-23 | Artefacts not Required | Completed & Approved | Closed before june-2025 | Closed after June
1709 | M962 | MOM | 2024-01-24 |  |  |  | NOC Operationalization |  | Discuss pending points and close the final scope with T-Fiber |  | Critical | Open |  |  | 23-Sep-25: Approved shall be closed | [12 empty] | Network | Closed | CLOSED | 23-Sep-25: Approved shall be closed | FALSE | [5 empty] | 2025-09-23 | Artefacts not Required | Completed & Approved | Closed before june-2025 | Closed after June
1710 | M963 | MOM | 2024-01-24 |  |  |  | NOC Operationalization |  | Share a business continuity plan for 6 manual to automated product transitions |  | Critical | Open |  |  | 16-Oct-25: Covered in BSS Operationalization | [12 empty] | Network | OPEN | Duplicate | 16-Oct-25: Covered in BSS Operationalization | FALSE | [7 empty] | Open | Open | Open
1711 | M964 | MOM | 2024-01-24 |  |  |  | NOC Operationalization |  | Present NOC pre-production testing and environment plan |  | Critical | Open |  |  | 23-Sep-25: Approved shall be closed | [12 empty] | Network | Closed | CLOSED | 23-Sep-25: Approved shall be closed | FALSE | [5 empty] | 2025-09-23 | Artefacts not Required | Completed & Approved | Closed before june-2025 | Closed after June
1712 | M965 | MOM | 2024-01-24 |  |  |  | NOC Operationalization |  | Confirm list of BSS operation team members |  | Critical | Open |  |  | 23-Sep-25: Approved shall be closed | [12 empty] | Network | Closed | CLOSED | 23-Sep-25: Approved shall be closed | FALSE | [5 empty] | 2025-09-23 | Artefacts not Required | Completed & Approved | Closed before june-2025 | Closed after June
1713 | M966 | MOM | 2024-01-24 |  |  |  | WFM | NOC Operationalization | Update the GIS data and confirm its operation SOP |  | Critical | Open |  |  | 15-Nov-25:The GIS SOP has been created, demonstrated, submitted, and approved, along with the Interim O&M activities completed in April 2024, GIS is already operational. | [12 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1714 | M967 | MOM | 2024-01-24 |  |  |  | NOC Operationalization |  | Deploy senior resource for managing T-Fiber helpdesk |  | Critical | Open |  |  | 16-Oct-25: 1 senior resource from LnT handling Helpdesk Manager | [12 empty] | Network | OPEN | CLOSED | 16-Oct-25: 1 senior resource from LnT handling Helpdesk Manager | FALSE | [7 empty] | Open | Open | Open
1715 | M968 | MOM | 2024-01-24 |  |  |  | NOC Operationalization |  | Separate helpdesk and call center desk with transition plan |  | Critical | Open |  |  | 01-Dec-25: Only technical helpdesk in scope which is operational, also Business helpdesk was ready with setup 2 resources at T fiber office | [12 empty] | Network | OPEN | [10 empty] | Open | Open | Open
1716 | M969 | MOM | 2024-01-24 |  |  |  | NOC Operationalization |  | Arrange toll-free number and update on notification formats readiness |  | Critical | Open | [15 empty] | Network | OPEN | [10 empty] | Open | Open | Open
1717 | M97 | MOM | 2023-08-01 |  |  |  | Helpdesk | User Experience | Different communication channels such as SMS, WhatsApp, Email |  | Critical | open |  |  | 11- Sep-25: SMS and E-mail Integrated and Whatsapp existing Product will not support | [12 empty] | Helpdesk (Contact Center) | OPEN | [10 empty] | Open | Open | Open
1718 | M970 | MOM | 2024-01-24 |  |  |  | NOC Operationalization |  | Integrate WhatsApp for customer communication through calls with IVR |  | Critical | Open |  |  | 01-Dec-25: Not feasible | [12 empty] | Network | OPEN | [10 empty] | Open | Open | Open
1719 | M971 | MOM | 2024-01-24 |  |  |  | NOC Operationalization |  | Provide updates on NOC progress and ensure commitment dates are met |  | Critical | Open |  |  | 23-Sep-25: Approved shall be closed | [12 empty] | Network | Closed | CLOSED | 23-Sep-25: Approved shall be closed | FALSE | [5 empty] | 2025-09-23 | Artefacts not Required | Completed & Approved | Closed before june-2025 | Closed after June
1720 | M972 | MOM | 2024-01-24 |  |  |  | NOC Operationalization |  | Deploy stable standard product for IPDR |  | Critical | Open |  |  | 23-Sep-25: Approved shall be closed | [12 empty] | Network | Closed | CLOSED | 23-Sep-25: Approved shall be closed | FALSE | [5 empty] | 2025-09-23 | Artefacts not Required | Completed & Approved | Closed before june-2025 | Closed after June
1721 | M973 | MOM | 2024-01-24 |  |  |  | NOC Operationalization |  | Ensure pre-scheduled meetings occur without SMEs absence |  | Critical | Open |  |  | 23-Sep-25: Approved shall be closed | [12 empty] | Network | Closed | CLOSED | 23-Sep-25: Approved shall be closed | FALSE | [5 empty] | 2025-09-23 | Artefacts not Required | Completed & Approved | Closed before june-2025 | Closed after June
1722 | M974 | MOM | 2024-01-24 |  |  |  | NOC Operationalization |  | Prepare NOC for review by the State IT&EC Minister and PS-ITE&C |  | Critical | Open |  |  | 24-Sep-25: Closed, Meeting completed | [12 empty] | Network | Closed | [8 empty] | 2025-09-24 | Artefacts not Required | Completed & Approved | Closed before june-2025 | Closed after June
1723 | M975 | MOM | 2024-01-24 |  |  |  | NOC Operationalization |  | Project Review with 3 MSIs |  | Critical | Open |  |  | 23-Sep-25: Approved shall be closed | [12 empty] | Network | Closed | CLOSED | 23-Sep-25: Approved shall be closed | FALSE | [5 empty] | 2025-09-23 | Artefacts not Required | Completed & Approved | Closed before june-2025 | Closed after June
1724 | M976 | MOM | 2024-01-24 | P3 |  |  | NOC Operationalization |  | Resource mobilization and network availability |  | Critical | Open |  |  | NOC resources available, availability report being shared | [12 empty] | Network | Closed |  |  |  | Not related to delivery |  |  |  |  | 2025-09-19 | Artefacts not Required | Completed & Approved | Closed before june-2025 | Closed after June
1725 | M977 | MOM | 2024-01-24 |  |  |  | NOC Operationalization |  | Adoption of WFM by packages B & C |  | Critical | Open |  |  | 16-Oct-25: Covered in WFM Operationalization | [12 empty] | Network | OPEN | Duplicate | 16-Oct-25: Covered in WFM Operationalization | FALSE | [7 empty] | Open | Open | Open
1726 | M978 | MOM | 2024-01-24 |  |  |  | Field Related |  | Implementation of Mandal rings of NoFN PH-1 |  | NON-Critical | Open | [15 empty] | Field Related issues | OPEN |  |  |  | Project Team | [6 empty] | Open | Open | Open
1727 | M979 | MOM | 2024-01-24 |  |  |  | NOC Operationalization |  | Restoration of social welfare and tribal welfare schools to service |  | Critical | Open |  |  | 23-Sep-25: Approved shall be closed | [12 empty] | Network | Closed | CLOSED | 23-Sep-25: Approved shall be closed | FALSE | [5 empty] | 2025-09-23 | Artefacts not Required | Completed & Approved | Closed before june-2025 | Closed after June
1728 | M98 | MOM | 2023-08-01 |  |  |  | Helpdesk | Dashboards | Categorization of Incoming Queries |  | Critical | open |  |  | 11- Sep-25: Available in Neox Application | [12 empty] | Helpdesk (Contact Center) | OPEN | [10 empty] | Open | Open | Open
1729 | M980 | MOM | 2024-01-24 |  |  |  | Field Related |  | Complete all GI connectivity before March '24 |  | Critical | Open | [15 empty] | Field Related issues | OPEN |  |  |  | Project Team | [5 empty] | Artefacts to be uploaded | Open | Open | Open
1730 | M981 | MOM | 2024-01-24 |  |  |  | NOC Operationalization |  | Focus on top 4 network readiness priorities |  | Critical | Open |  |  | 23-Sep-25: Approved shall be closed | [12 empty] | Network | Closed | CLOSED | 23-Sep-25: Approved shall be closed | FALSE | [5 empty] | 2025-09-23 | Artefacts not Required | Completed & Approved | Closed before june-2025 | Closed after June
1731 | M982 | MOM | 2024-01-25 |  |  |  | WFM | NOC Operationalization | WFM Patrolling App Demo |  | Critical | Open |  |  | 15-Noc-25:Multiple demonstrations of the WFM application have been conducted for Package A, along with three months of training provided to the field team. Additionally, for Packages B and C, demonstration | s w | ere c | ondu | cted thre | imes each | [7 empty] | Applications/Tools | OPEN |  |  |  |  | e t | [5 empty] | Open | Open | Open
1732 | M983 | MOM | 2024-01-25 |  |  |  | WFM | NOC Operationalization | Complete WFM-OSS integration |  | Critical | Open |  |  | 15-Nov-25:MPLS & DWDM TT integration completed, GPON TT is pending as there is dependency on OT team for this integration | [12 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1733 | M984 | MOM | 2024-01-25 |  |  |  | NOC Operationalization |  | Submit solution document for PoP RFS |  | Critical | Open |  |  | 23-Sep-25: Approved shall be closed | [12 empty] | Network | Closed | CLOSED | 23-Sep-25: Approved shall be closed | FALSE | [5 empty] | 2025-09-23 | Artefacts not Required | Completed & Approved | Closed before june-2025 | Closed after June
1734 | M985 | MOM | 2024-01-25 |  |  |  | WFM | NOC Operationalization | Understand use cases of WFM integration with BSS |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1735 | M986 | MOM | 2024-01-25 |  | OSS | OSS | OSS |  | Complete Fault Management and Trouble Ticketing |  | Critical | Open | [15 empty] | Applications/Tools | Closed | 0 | No Artifact Required | TRUE | [5 empty] | 2025-11-18 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\OSS\52 Artefcats_18112025 | Closed after 14-Nov-25 | Closed after 14-Nov-25 | Completed but Verification undrer Process
1736 | M987 | MOM | 2024-01-25 |  |  |  | WFM | NOC Operationalization | Clarify GIS vs WFM mobile app usage |  | Critical | Open |  |  | 15-Nov-25:The document outlining the differences between the GIS and WFM mobile applications has been prepared and demonstrated in the TFIBER Core Room. There are no pending actions for this item | [12 empty] | Applications/Tools | OPEN | [9 empty] | #N/A | Closed | Closed | Open
1737 | M988 | MOM | 2024-01-25 |  |  |  | WFM | NOC Operationalization | Submit the NDA signed between L&T and M/S Lepton |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1738 | M989 | MOM | 2024-01-25 |  |  |  | Security & Regulatory Compliance | NOC Operationalization | Ensure API security measures |  | Critical | Open |  |  | 28-Nov-25: To discuss with mr Sanjay to get clarifications on the points Applicationer has been asked to collect from Developers | [12 empty] | Security | OPEN | [10 empty] | Open | Open | Open
1739 | M99 | MOM | 2023-08-01 |  |  |  | Helpdesk | User Experience | Bilingual IVR |  | Critical | open |  |  | 24-Sep-25: Now its in 3 Languages | [12 empty] | Helpdesk (Contact Center) | Closed | [8 empty] | 2025-09-24 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\M121,170,99,726 | Completed & Approved | Closed before june-2025 | Closed after June
1740 | M990 | MOM | 2024-01-25 |  | OSS | OSS | OSS |  | Submit sample dashboards/reports |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | 0 | Completed | TRUE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1741 | M991 | MOM | 2024-01-25 | P3 |  |  | NOC Operationalization |  | Provide Operations Handbook document forms |  | Critical | Open | [15 empty] | Network | OPEN |  |  |  | Documentation | [6 empty] | Open | Open | Open
1742 | M992 | MOM | 2024-01-25 |  |  |  | NOC Operationalization |  | Clarify attendance watermarking feature |  | Critical | Open |  |  | 23-Sep-25: Approved shall be closed | [12 empty] | Network | Closed | CLOSED | 23-Sep-25: Approved shall be closed | FALSE | [5 empty] | 2025-09-23 | Artefacts not Required | Completed & Approved | Closed before june-2025 | Closed after June
1743 | M993 | MOM | 2024-01-25 |  |  |  | NOC Operationalization |  | Schedule weekly training for patrollers |  | Critical | Open |  |  | 23-Sep-25: Approved shall be closed | [12 empty] | Network | Closed | CLOSED | 23-Sep-25: Approved shall be closed | FALSE | [5 empty] | 2025-09-23 | Artefacts not Required | Completed & Approved | Closed before june-2025 | Closed after June
1744 | M994 | MOM | 2024-01-25 |  |  |  | NOC Operationalization |  | Update on previous MoM action items |  | Critical | Open |  |  | 23-Sep-25: Approved shall be closed | [12 empty] | Network | Closed | CLOSED | 23-Sep-25: Approved shall be closed | FALSE | [5 empty] | 2025-09-23 | Artefacts not Required | Completed & Approved | Closed before june-2025 | Closed after June
1745 | M995 | MOM | 2024-01-25 |  |  |  | BSS |  | Continue defining logic for Dark Fiber and GI-BB products |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1746 | M996 | MOM | 2024-01-25 |  |  |  | WFM | NOC Operationalization | Dry run and operationalize three routes for testing WFM with actual data |  | Critical | Open | [15 empty] | Applications/Tools | OPEN | [10 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1747 | M997 | MOM | 2024-01-25 |  |  |  | Field Related |  | Improve resource mobilization & achieve 65% network availability |  | NON-Critical | Open | [15 empty] | Field Related issues | OPEN |  |  |  | Project Team | [6 empty] | Open | Open | Open
1748 | M998 | MOM | 2024-01-25 |  |  |  | Field Related |  | Engage partners for O&M resources augmentation and ensure active spares availability |  | NON-Critical | Open | [15 empty] | Field Related issues | OPEN |  |  |  | O&M Team | [6 empty] | Open | Open | Open
1749 | M999 | MOM | 2024-01-25 |  |  |  | Field Related |  | Deploy committed resources and achieve network availability |  | NON-Critical | Open | [15 empty] | Field Related issues | OPEN |  |  |  | O&M Team | [6 empty] | Open | Open | Open
1750 | NOC1 | NOC | NA |  | OSS | OSS | OSS | DC | DC Active Infra uptime & SLA Daily |  | Critical |  | HPSM | Incident Management | [13 empty] | Applications/Tools | OPEN | 0 | WIP | TRUE | [7 empty] | Open | Open | Open
1751 | NOC10 | NOC | NA |  | OSS | OSS | OSS | DC | DC Passive infra uptime & SLA Weekly |  | Critical |  | HPSM | Incident Management | [13 empty] | Applications/Tools | OPEN | 0 | Completed With Artifacts | TRUE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1752 | NOC100 | NOC | NA |  |  |  | GPON | OSS | Governenmnet Institutions ( GI ) links delivery. Preparation and publishing of KPI Daily |  | Critical | OPEN | NNMI | NPS | OPEN-DEPENDENT | [12 empty] | Applications/Tools | OPEN |  | Open-Dependent | FALSE | [7 empty] | Open | Open | Open
1753 | NOC101 | NOC | NA |  |  |  | GPON | OSS | Governenmnet Institutions ( GI ) links delivery. Preparation and publishing of KPI Weekly |  | Critical | OPEN | NNMI | NPS | OPEN-DEPENDENT | [12 empty] | Applications/Tools | OPEN |  | Open-Dependent | FALSE | [7 empty] | Open | Open | Open
1754 | NOC102 | NOC | NA |  |  |  | GPON | OSS | Governenmnet Institutions ( GI ) links delivery. Preparation and publishing of KPI Monthly |  | Critical | OPEN | NNMI | NPS | OPEN-DEPENDENT | [12 empty] | Applications/Tools | OPEN |  | Open-Dependent | FALSE | [7 empty] | Open | Open | Open
1755 | NOC103 | NOC | NA |  |  |  | GPON | OSS | Governenmnet Institutions ( GI ) links delivery. Preparation and publishing of KPI (Selective from and to dates) |  | Critical | OPEN | NNMI | NPS | OPEN-DEPENDENT | [12 empty] | Applications/Tools | OPEN |  | Open-Dependent | FALSE | [7 empty] | Open | Open | Open
1756 | NOC104 | NOC | NA |  |  |  | GPON | OSS | Published GP Network uptime (like, total scope, litup count and availability according to the category) Daily |  | Critical | COMPLETED | HPSM | Incident Management | [13 empty] | Applications/Tools | OPEN | live data | Completed With Artifacts | FALSE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1757 | NOC105 | NOC | NA |  |  |  | GPON | OSS | Published GP Network uptime (like, total scope, litup count and availability according to the category) Weekly |  | Critical | OPEN | HPSM | Incident Management | 26-Sep-2025: GPON , DWDM, Routers, switches and UPS we can take monthly and Daily reports from UOC. For UPS, Routers and switches we can take hourly, weekly, monthly on demand and any selective period ba | sis | from | NNM | I. L&T c | eyed that, A |  | s p | er |  |  | the | agreed scope of work between L&T, TFiber, HP and OT this hourly and weekly granuality not given in the scope, also availability based on alarm. As per the confirmation from Manoj L&T, The existing tool can only give daily and monthly reports only. Apart from that the system doesn't have capabilities to generate other reports. Vigility need to co-ordinate with OEM and confirm the feasibility. | Applications/Tools | OPEN | 26-Sep-2025: GPON , DWDM, Routers, switches and UPS we can take monthly and Daily reports from UOC. For UPS, Routers and switches we can take hourly, weekly, monthly on demand and any selective period basis from NNMI. L&T conveyed that, As per the agreed scope of work between L&T, TFiber, HP and OT this hourly and weekly granuality not given in the scope, also availability based on alarm. As per the confirmation from Manoj L&T, The existing tool can only give daily and monthly reports only. Apart from that the system doesn't have capabilities to generate other reports. Vigility need to co-ordinate with OEM and confirm the feasibility. | Not-Feasible | FALSE |  | onv | [5 empty] | Open | Open | Open
1758 | NOC106 | NOC | NA |  |  |  | GPON | OSS | Published GP Network uptime (like, total scope, litup count and availability according to the category) Monthly |  | Critical | COMPLETED | HPSM | Incident Management | [13 empty] | Applications/Tools | OPEN | live data | Completed With Artifacts | FALSE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1759 | NOC107 | NOC | NA |  |  |  | GPON | OSS | Published GP Network uptime (like, total scope, litup count and availability according to the category) (Selective from and to dates) |  | Critical | COMPLETED | HPSM | Incident Management | [13 empty] | Applications/Tools | OPEN | 0 | Completed With Artifacts | TRUE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1760 | NOC108 | NOC | NA |  |  |  | GPON | OSS | Publishing Package wise and District wise GP Network uptime and GP TT resolution MTTR dashboard Daily |  | Critical | COMPLETED | HPSM | Incident Management | [13 empty] | Applications/Tools | OPEN | 0 | Completed With Artifacts | TRUE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1761 | NOC109 | NOC | NA |  |  |  | GPON | OSS | Publishing Package wise and District wise GP Network uptime and GP TT resolution MTTR dashboard Weekly |  | Critical | COMPLETED | HPSM | Incident Management | [13 empty] | Applications/Tools | OPEN | 0 | Completed With Artifacts | TRUE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1762 | NOC11 | NOC | NA |  | OSS | OSS | OSS | DC | DC Passive infra uptime & SLA Monthly |  | Critical |  | HPSM | Incident Management | [13 empty] | Applications/Tools | OPEN | 0 | Completed With Artifacts | TRUE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1763 | NOC110 | NOC | NA |  |  |  | GPON | OSS | Publishing Package wise and District wise GP Network uptime and GP TT resolution MTTR dashboard Monthly |  | Critical | COMPLETED | HPSM | Incident Management | [13 empty] | Applications/Tools | OPEN | 0 | Completed With Artifacts | TRUE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1764 | NOC111 | NOC | NA |  |  |  | GPON | OSS | Publishing Package wise and District wise GP Network uptime and GP TT resolution MTTR dashboard (Selective from and to dates) |  | Critical | OPEN | HPSM | Incident Management | Availability is available in UOC for Daily and monthly only. MTTR Report is available from SM on Daily , Weekly, monthly and customized period. Dashboards made available as per requirements against MTTR | [12 empty] | Applications/Tools | OPEN | Availability is available in UOC for Daily and monthly only. MTTR Report is available from SM on Daily , Weekly, monthly and customized period. Dashboards made available as per requirements against MTTR | Completed With Artifacts | TRUE | [7 empty] | Open | Open | Open
1765 | NOC112 | NOC | NA |  |  |  | GPON | OSS | Published Mandal Network uptime (like, total scope, litup count and availability according to the category) Hourly |  | Critical | OPEN | HPSM | Incident Management | Availability is available in UOC for Daily and monthly only. | [12 empty] | Applications/Tools | OPEN | Availability is available in UOC for Daily and monthly only. | Not-Feasible | TRUE | [7 empty] | Open | Open | Open
1766 | NOC113 | NOC | NA |  |  |  | GPON | OSS | Published Mandal Network uptime (like, total scope, litup count and availability according to the category) Daily |  | Critical | COMPLETED | HPSM | Incident Management | [13 empty] | Applications/Tools | OPEN | 0 | Completed With Artifacts | TRUE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1767 | NOC114 | NOC | NA |  |  |  | GPON | OSS | Published Mandal Network uptime (like, total scope, litup count and availability according to the category) Weekly |  | Critical | OPEN | HPSM | Incident Management | Additional Scope (Total scope value is not possible to display in HPSM) | [12 empty] | Applications/Tools | OPEN |  | Not-Feasible | FALSE | [7 empty] | Open | Open | Open
1768 | NOC115 | NOC | NA |  |  |  | GPON | OSS | Published Mandal Network uptime (like, total scope, litup count and availability according to the category) Monthly |  | Critical | COMPLETED | HPSM | Incident Management | [13 empty] | Applications/Tools | OPEN | 0 | Completed With Artifacts | TRUE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1769 | NOC116 | NOC | NA |  |  |  | GPON | OSS | Published Mandal Network uptime (like, total scope, litup count and availability according to the category) (Selective from and to dates) |  | Critical | COMPLETED | HPSM | Incident Management | [13 empty] | Applications/Tools | OPEN | 0 | Not-Feasible | TRUE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1770 | NOC117 | NOC | NA |  |  |  | GPON | OSS | Publishing Package wise and district wise Mandal Network uptime and Mandal TT resolution MTTR dashboard Daily |  | Critical | COMPLETED | HPSM | Incident Management | [13 empty] | Applications/Tools | OPEN | 0 | Completed With Artifacts | TRUE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1771 | NOC118 | NOC | NA |  |  |  | GPON | OSS | Publishing Package wise and district wise Mandal Network uptime and Mandal TT resolution MTTR dashboard Weekly |  | Critical | COMPLETED | HPSM | Incident Management | [13 empty] | Applications/Tools | OPEN | 0 | Completed With Artifacts | TRUE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1772 | NOC119 | NOC | NA |  |  |  | GPON | OSS | Publishing Package wise and district wise Mandal Network uptime and Mandal TT resolution MTTR dashboard Monthly |  | Critical | COMPLETED | HPSM | Incident Management | [13 empty] | Applications/Tools | OPEN | 0 | Completed With Artifacts | TRUE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1773 | NOC12 | NOC | NA |  | OSS | OSS | OSS | DC | DC Passive infra uptime & SLA (Selective from and to dates) |  | Critical |  | HPSM | Incident Management | [13 empty] | Applications/Tools | OPEN | 0 | Completed With Artifacts | TRUE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1774 | NOC120 | NOC | NA |  |  |  | GPON | OSS | Publishing Package wise and district wise Mandal Network uptime and Mandal TT resolution MTTR dashboard (Selective from and to dates) |  | Critical | OPEN | HPSM | Incident Management | Uptime and MMTR are two separate reports. | [12 empty] | Applications/Tools | OPEN |  | Completed With Artifacts | FALSE | [7 empty] | Open | Open | Open
1775 | NOC121 | NOC | NA |  | OSS | OSS | All Domain | OSS | Based on DFR, prepare and publishing domain wise Ticketing dashboard Hourly |  | Critical | COMPLETED | HPSM | Incident Management | [13 empty] | Applications/Tools | OPEN | 0 | Completed With Artifacts | TRUE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1776 | NOC122 | NOC | NA |  | OSS | OSS | All Domain | OSS | Based on DFR, prepare and publishing domain wise Ticketing dashboard Daily |  | Critical | COMPLETED | HPSM | Incident Management | [13 empty] | Applications/Tools | OPEN | 0 | Completed With Artifacts | TRUE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1777 | NOC123 | NOC | NA |  | OSS | OSS | All Domain | OSS | Based on DFR, prepare and publishing domain wise Ticketing dashboard Weekly |  | Critical | COMPLETED | HPSM | Incident Management | [13 empty] | Applications/Tools | OPEN | 0 | Completed With Artifacts | TRUE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1778 | NOC124 | NOC | NA |  | OSS | OSS | All Domain | OSS | Based on DFR, prepare and publishing domain wise Ticketing dashboard Monthly |  | Critical | COMPLETED | HPSM | Incident Management | [13 empty] | Applications/Tools | OPEN | 0 | Completed With Artifacts | TRUE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1779 | NOC125 | NOC | NA |  | OSS | OSS | All Domain | OSS | Based on DFR, prepare and publishing domain wise Ticketing dashboard (Selective from and to dates) |  | Critical | COMPLETED | HPSM | Incident Management | [13 empty] | Applications/Tools | OPEN | 0 | Completed With Artifacts | TRUE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1780 | NOC126 | NOC | NA |  | OSS | OSS | All Domain | OSS | Publishing of total field network devices dashboard Daily |  | Critical | COMPLETED | OSS Dashboards | UTM | [13 empty] | Applications/Tools | OPEN | Power BI DB - Device status will be live in the dashboard | Completed With Artifacts | FALSE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1781 | NOC127 | NOC | NA |  | OSS | OSS | All Domain | OSS | Publishing of total field network devices dashboard Weekly |  | Critical | NOT_FEASIBLE | OSS Dashboards | UTM | [13 empty] | Applications/Tools | OPEN | 0 | Not-Feasible | TRUE | [7 empty] | Open | Open | Open
1782 | NOC128 | NOC | NA |  | OSS | OSS | All Domain | OSS | Publishing of total field network devices dashboard Monthly |  | Critical | COMPLETED | OSS Dashboards | UTM | Device status will be live in the dashboard | [12 empty] | Applications/Tools | OPEN | Device status will be live in the dashboard | Completed With Artifacts | TRUE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1783 | NOC129 | NOC | NA |  | OSS | OSS | All Domain | OSS | Publishing of total field network devices dashboard (Selective from and to dates) |  | Critical | NOT_FEASIBLE | OSS Dashboards | UTM | [13 empty] | Applications/Tools | OPEN | 0 | Not-Feasible | TRUE | [7 empty] | Open | Open | Open
1784 | NOC13 | NOC | NA |  | OSS | OSS | OSS | DC | DC Network link uptime & SLA Daily |  | Critical |  | HPSM | Incident Management | [13 empty] | Applications/Tools | OPEN | 0 | Completed | TRUE | [7 empty] | Open | Open | Open
1785 | NOC130 | NOC | NA |  | OSS | OSS | OSS | Field Passive Infra | Preparion and publishing Field Passive Infra Devices Uptime dashboard (Zone,Mandal,GP wise) Daily |  | Critical | COMPLETED | HPSM | Incident Management | [13 empty] | Applications/Tools | OPEN | 0 | Completed With Artifacts | TRUE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1786 | NOC131 | NOC | NA |  | OSS | OSS | OSS | Field Passive Infra | Preparion and publishing Field Passive Infra Devices Uptime dashboard (Zone,Mandal,GP wise) Weekly |  | Critical | NOT_FEASIBLE | HPSM | Incident Management | [13 empty] | Applications/Tools | OPEN | 0 | Not-Feasible | TRUE | [7 empty] | Open | Open | Open
1787 | NOC132 | NOC | NA |  | OSS | OSS | OSS | Field Passive Infra | Preparion and publishing Field Passive Infra Devices Uptime dashboard (Zone,Mandal,GP wise) Monthly |  | Critical | COMPLETED | HPSM | Incident Management | [13 empty] | Applications/Tools | OPEN | 0 | Completed With Artifacts | TRUE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1788 | NOC133 | NOC | NA |  | OSS | OSS | OSS | Field Passive Infra | Preparion and publishing Field Passive Infra Devices Uptime dashboard (Zone,Mandal,GP wise) (Selective from and to dates) |  | Critical | COMPLETED | NNMI | NPS | [13 empty] | Applications/Tools | OPEN | available-weekly in NPS not in UOC | Completed With Artifacts | FALSE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1789 | NOC134 | NOC | NA |  | OSS | OSS | OSS | Planned Events | Publishing Planned Events dashboard of all the packages(like , PE applied,Success,cancelation etc) Daily |  | Critical | COMPLETED | NNMI | NPS | [13 empty] | Applications/Tools | OPEN | there is no dashboard | Completed With Artifacts | FALSE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1790 | NOC135 | NOC | NA |  | OSS | OSS | OSS | Planned Events | Publishing Planned Events dashboard of all the packages(like , PE applied,Success,cancelation etc) Weekly |  | Critical | COMPLETED | NNMI | NPS | [13 empty] | Applications/Tools | OPEN | 0 | Completed With Artifacts | TRUE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1791 | NOC136 | NOC | NA |  | OSS | OSS | OSS | Planned Events | Publishing Planned Events dashboard of all the packages(like , PE applied,Success,cancelation etc) Monthly |  | Critical | COMPLETED | NNMI | NPS | [13 empty] | Applications/Tools | OPEN | 0 | Completed With Artifacts | TRUE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1792 | NOC137 | NOC | NA |  | OSS | OSS | OSS | Planned Events | Publishing Planned Events dashboard of all the packages(like , PE applied,Success,cancelation etc) (Selective from and to dates) |  | Critical | COMPLETED | NNMI | NPS | [13 empty] | Applications/Tools | OPEN | 0 | Completed With Artifacts | TRUE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1793 | NOC138 | NOC | NA |  | OSS | OSS | OSS | DC IT Active Infra | Preparation and publishing of all DC IT devices availability dashboard Daily |  | NON-Critical |  | HPSM | Incident Management | [13 empty] | Applications/Tools | OPEN | 0 | WIP | TRUE | [7 empty] | Open | Open | Open
1794 | NOC139 | NOC | NA |  | OSS | OSS | OSS | DC IT Active Infra | Preparation and publishing of all DC IT devices availability dashboard Weekly |  | NON-Critical |  | HPSM | Incident Management | [13 empty] | Applications/Tools | OPEN | 0 | WIP | TRUE | [7 empty] | Open | Open | Open
1795 | NOC14 | NOC | NA |  | OSS | OSS | OSS | DC | DC Network link uptime & SLA Weekly |  | Critical |  | HPSM | Incident Management | [13 empty] | Applications/Tools | OPEN | 0 | Not-Feasible | TRUE | [7 empty] | Open | Open | Open
1796 | NOC140 | NOC | NA |  | OSS | OSS | OSS | DC IT Active Infra | Preparation and publishing of all DC IT devices availability dashboard Monthly |  | NON-Critical |  | HPSM | Incident Management | [13 empty] | Applications/Tools | OPEN | 0 | Completed | TRUE | [7 empty] | Open | Open | Open
1797 | NOC141 | NOC | NA |  | OSS | OSS | OSS | DC IT Active Infra | Preparation and publishing of all DC IT devices availability dashboard (Selective from and to dates) |  | NON-Critical |  | HPSM | Incident Management | [13 empty] | Applications/Tools | OPEN | 0 | Not-Feasible | TRUE | [7 empty] | Open | Open | Open
1798 | NOC142 | NOC | NA |  |  |  | DC Passive Infra | OSS | Preparation and publishing of all DC Non IT devices availability dashboard Daily |  | NON-Critical |  | HPSM | Incident Management | [13 empty] | Applications/Tools | OPEN | 0 | Completed | TRUE | [7 empty] | Open | Open | Open
1799 | NOC143 | NOC | NA |  |  |  | DC Passive Infra | OSS | Preparation and publishing of all DC Non IT devices availability dashboard Weekly |  | NON-Critical |  | HPSM | Incident Management | [13 empty] | Applications/Tools | OPEN | 0 | Not-Feasible | TRUE | [7 empty] | Open | Open | Open
1800 | NOC144 | NOC | NA |  |  |  | DC Passive Infra | OSS | Preparation and publishing of all DC Non IT devices availability dashboard Monthly |  | NON-Critical |  | HPSM | Incident Management | [13 empty] | Applications/Tools | OPEN | 0 | Completed | TRUE | [7 empty] | Open | Open | Open
1801 | NOC145 | NOC | NA |  |  |  | DC Passive Infra | OSS | Preparation and publishing of all DC Non IT devices availability dashboard (Selective from and to dates) |  | NON-Critical |  | HPSM | Incident Management | [13 empty] | Applications/Tools | OPEN | 0 | Not-Feasible | TRUE | [7 empty] | Open | Open | Open
1802 | NOC146 | NOC | NA |  | OSS | OSS | OSS | OSS | Preparation and publishing of all application availability dashboard Daily |  | Critical | COMPLETED | OSS Dashboards | UOC | 09-09-2025: Sitescope based application URL monitoring | [12 empty] | Applications/Tools | OPEN | 09-09-2025: Sitescope based application URL monitoring | Completed With Artifacts | TRUE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1803 | NOC147 | NOC | NA |  | OSS | OSS | OSS | OSS | Preparation and publishing of all application availability dashboard Weekly |  | Critical | COMPLETED | OSS Dashboards | UOC | [13 empty] | Applications/Tools | OPEN | sitescope | Completed With Artifacts | FALSE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1804 | NOC148 | NOC | NA |  | OSS | OSS | OSS | OSS | Preparation and publishing of all application availability dashboard Monthly |  | Critical | COMPLETED | OSS Dashboards | UOC | 09-09-2025: Sitescope based application URL monitoring | [12 empty] | Applications/Tools | OPEN | 09-09-2025: Sitescope based application URL monitoring | Completed With Artifacts | TRUE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1805 | NOC149 | NOC | NA |  | OSS | OSS | OSS | OSS | Preparation and publishing of all application availability dashboard (Selective from and to dates) |  | Critical | COMPLETED | OSS Dashboards | UOC | 09-09-2025: Sitescope based application URL availability monitoring | [12 empty] | Applications/Tools | OPEN | 09-09-2025: Sitescope based application URL availability monitoring | Completed With Artifacts | TRUE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1806 | NOC15 | NOC | NA |  | OSS | OSS | OSS | DC | DC Network link uptime & SLA Monthly |  | Critical |  | HPSM | Incident Management | [13 empty] | Applications/Tools | OPEN | 0 | Completed | TRUE | [7 empty] | Open | Open | Open
1807 | NOC150 | NOC | NA |  | OSS | OSS | OSS | OSS | Service assurance & Dashboards |  | Critical |  | OSS Dashboards | HPE Telco Unified OSS Console | Power Bi | [12 empty] | Applications/Tools | OPEN |  | Completed | FALSE | [7 empty] | Open | Open | Open
1808 | NOC151 | NOC | NA |  | OSS | OSS | OSS | OSS | Network Service Assurance Dashboards |  | Critical |  | OSS Dashboards | HPE Telco Unified OSS Console | [13 empty] | Applications/Tools | OPEN | dashboard is not there | Completed With Artifacts | FALSE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1809 | NOC152 | NOC | NA |  | OSS | OSS | OSS | OSS | Business Service Assurance Dashboards |  | Critical |  | OSS Dashboards | HPE Telco Unified OSS Console | [13 empty] | Applications/Tools | OPEN | 0 | Not Relevant To OSS | TRUE | [7 empty] | Open | Open | Open
1810 | NOC153 | NOC | NA |  | OSS | OSS | OSS | OSS | Customer Service Dashboards |  | Critical |  | OSS Dashboards | HPE Telco Unified OSS Console | It will be available in BSS | [12 empty] | Applications/Tools | OPEN |  | OPEN | FALSE | [7 empty] | Open | Open | Open
1811 | NOC154 | NOC | NA |  | OSS | OSS | OSS | OSS | Security Assurance Dashboard |  | Critical |  | OSS Dashboards | HPE Telco Unified OSS Console | It will be available in BSS | [12 empty] | Applications/Tools | OPEN | MTTR Reports for all domain including customer tickets | Completed With Artifacts | FALSE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1812 | NOC155 | NOC | NA |  | OSS | OSS | OSS | OSS | Service Inventory |  | Critical |  | OSS Dashboards | HPE Telco Unified OSS Console | Inhouse solution | [12 empty] | Applications/Tools | OPEN |  | OPEN | FALSE | [7 empty] | Open | Open | Open
1813 | NOC156 | NOC | NA |  | OSS | OSS | OSS | OSS | Service Monitoring |  | Critical |  | OSS Dashboards | HPE Telco Unified OSS Console | [13 empty] | Applications/Tools | OPEN | 0 | OPEN | TRUE | [7 empty] | Open | Open | Open
1814 | NOC157 | NOC | NA |  | OSS | OSS | New BSS | OSS | OSS Intigration for POC Locations LCO,RMSO & MSO |  | Critical | OPEN | HPSM | Incident Management | Aditional Scope for OT/HPE | [12 empty] | #N/A | OPEN |  | Not Relevant To OSS | FALSE | [7 empty] | Open | Open | Open
1815 | NOC158 | NOC | NA |  | OSS | OSS | New BSS | OSS | OSS Intigration for Live LCO , RMSO & MSO |  | Critical | OPEN | HPSM | Incident Management | Aditional Scope for OT/HPE | [12 empty] | #N/A | OPEN |  | Not Relevant To OSS | FALSE | [7 empty] | Open | Open | Open
1816 | NOC159 | NOC | NA |  | OSS | OSS | OSS | OSS | Video customer inventory , Internet customer inventory , Bandwidth allocation inventory count etc., |  | Critical | OPEN | HPSM | Incident Management | Aditional Scope for OT/HPE | [12 empty] | Applications/Tools | OPEN |  | OPEN | FALSE | [7 empty] | Open | Open | Open
1817 | NOC16 | NOC | NA |  | OSS | OSS | OSS | DC | DC Network link uptime & SLA (Selective from and to dates) |  | Critical |  | HPSM | Incident Management | [13 empty] | Applications/Tools | OPEN | 0 | Not-Feasible | TRUE | [7 empty] | Open | Open | Open
1818 | NOC160 | NOC | NA |  |  |  | DC Passive Infra | OSS | Preparation and publishing of all DC passive infra(Internal, OEM) PM dashboard Daily |  | NON-Critical |  | OSS Dashboards | UOC | [13 empty] | Applications/Tools | OPEN | 0 | OPEN | TRUE | [7 empty] | Open | Open | Open
1819 | NOC161 | NOC | NA |  |  |  | DC Passive Infra | OSS | Preparation and publishing of all DC passive infra(Internal, OEM) PM dashboard Weekly |  | NON-Critical |  | OSS Dashboards | UOC | [13 empty] | Applications/Tools | OPEN | 0 | OPEN | TRUE | [7 empty] | Open | Open | Open
1820 | NOC162 | NOC | NA |  |  |  | DC Passive Infra | OSS | Preparation and publishing of all DC passive infra(Internal, OEM) PM dashboard Monthly |  | NON-Critical |  | OSS Dashboards | UOC | [13 empty] | Applications/Tools | OPEN | 0 | OPEN | TRUE | [7 empty] | Open | Open | Open
1821 | NOC163 | NOC | NA |  |  |  | DC Passive Infra | OSS | Preparation and publishing of all DC passive infra(Internal, OEM) PM dashboard (Selective from and to dates) |  | NON-Critical |  | OSS Dashboards | UOC | [13 empty] | Applications/Tools | OPEN | 0 | OPEN | TRUE | [7 empty] | Open | Open | Open
1822 | NOC164 | NOC | NA |  | OSS | OSS | OSS | NOC | Preparation and publishing of all devices, application, software AMC dashboard Daily |  | Critical |  | OSS Dashboards | Asset Manager | Report is available in Asset manager | [12 empty] | Applications/Tools | OPEN |  | Completed | FALSE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1823 | NOC165 | NOC | NA |  | OSS | OSS | OSS | NOC | Preparation and publishing of all devices, application, software AMC dashboard Weekly |  | Critical |  | OSS Dashboards | Asset Manager | [13 empty] | Applications/Tools | OPEN | 0 | Completed With Artifacts | TRUE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1824 | NOC166 | NOC | NA |  | OSS | OSS | OSS | NOC | Preparation and publishing of all devices, application, software AMC dashboard Monthly |  | Critical |  | OSS Dashboards | Asset Manager | [13 empty] | Applications/Tools | OPEN | 0 | Not-Feasible | TRUE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1825 | NOC167 | NOC | NA |  | OSS | OSS | OSS | NOC | Preparation and publishing of all devices, application, software AMC dashboard (Selective from and to dates) |  | Critical |  | OSS Dashboards | Asset Manager | [13 empty] | Applications/Tools | OPEN | 0 | Completed With Artifacts | TRUE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1826 | NOC168 | NOC | NA |  | OSS | OSS | OSS | NOC | Publishing of all major events in Tnoc dashboard Daily |  | Critical |  | HPSM | Incident Management | [13 empty] | Applications/Tools | OPEN | ONLY live dashboard is available in Power BI | Completed With Artifacts | FALSE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1827 | NOC169 | NOC | NA |  | OSS | OSS | OSS | NOC | Publishing of all major events in Tnoc dashboard Weekly |  | Critical |  | HPSM | Incident Management | [13 empty] | Applications/Tools | OPEN | 0 | Completed With Artifacts | TRUE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1828 | NOC17 | NOC | NA |  |  |  | BSS | Service Provisioning | configure of GI services and tracking and publishing data Daily |  | Critical | OPEN | BSS | CRM | It will be available in NSO and BSS | [12 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1829 | NOC170 | NOC | NA |  | OSS | OSS | OSS | NOC | Publishing of all major events in Tnoc dashboard Monthly |  | Critical |  | HPSM | Incident Management | [13 empty] | Applications/Tools | OPEN | 0 | Completed With Artifacts | TRUE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1830 | NOC171 | NOC | NA |  | OSS | OSS | OSS | NOC | Publishing of all major events in Tnoc dashboard (Selective from and to dates) |  | Critical |  | HPSM | Incident Management | [13 empty] | Applications/Tools | OPEN | 0 | Completed With Artifacts | TRUE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1831 | NOC172 | NOC | NA |  | OSS | OSS | OSS | BBNL Reports | Publishing of BBNL dashboard Daily |  | Critical | COMPLETED | HPSM | Incident Management | [13 empty] | Applications/Tools | OPEN | 0 | Completed With Artifacts | TRUE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1832 | NOC173 | NOC | NA |  | OSS | OSS | OSS | BBNL Reports | Publishing of BBNL dashboard Weekly |  | Critical | NOT_FEASIBLE | HPSM | Incident Management | 11-Oct-25: BBNL do not ask weekly hence it is not delivered | [12 empty] | Applications/Tools |  | 11-Oct-25: BBNL do not ask weekly hence it is not delivered | Deferred | TRUE | [7 empty] | Open | Open | Open
1833 | NOC174 | NOC | NA |  | OSS | OSS | OSS | BBNL Reports | Publishing of BBNL dashboard Monthly |  | Critical | COMPLETED | HPSM | Incident Management | [13 empty] | Applications/Tools | OPEN | 0 | Completed With Artifacts | TRUE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1834 | NOC175 | NOC | NA |  | OSS | OSS | OSS | BBNL Reports | Publishing of BBNL dashboard (Selective from and to dates) |  | Critical | NOT_FEASIBLE | HPSM | Incident Management | 11-Oct-25: BBNL do not ask Selective from and to dates hence it is not delivered | [12 empty] | Applications/Tools |  | 11-Oct-25: BBNL do not ask Selective from and to dates hence it is not delivered | Deferred | TRUE | [7 empty] | Open | Open | Open
1835 | NOC176 | NOC | NA |  | OSS | OSS | OSS | Field Passive Infra | Publishing of Field Passive infra total devices dashboard Daily |  | Critical | COMPLETED | NNMI | NNMI | 09-09-2025: Inventory Dashboard visible for live data which is refreshing 6 times a day. | [12 empty] | Applications/Tools | OPEN | 09-09-2025: Inventory Dashboard visible for live data which is refreshing 6 times a day. | Completed With Artifacts | TRUE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1836 | NOC177 | NOC | NA |  | OSS | OSS | OSS | Field Passive Infra | Publishing of Field Passive infra total devices dashboard Weekly |  | Critical | NOT_FEASIBLE | NNMI | NNMI | [13 empty] | Applications/Tools | OPEN | 0 | Not-Feasible | TRUE | [7 empty] | Open | Open | Open
1837 | NOC178 | NOC | NA |  | OSS | OSS | OSS | Field Passive Infra | Publishing of Field Passive infra total devices dashboard Monthly |  | Critical | COMPLETED | NNMI | NNMI | Live report is available in UOC | [12 empty] | Applications/Tools | OPEN | Live report is available in UOC | Completed With Artifacts | TRUE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1838 | NOC179 | NOC | NA |  | OSS | OSS | OSS | Field Passive Infra | Publishing of Field Passive infra total devices dashboard (Selective from and to dates) |  | Critical | COMPLETED | NNMI | NNMI | Live report is available in UOC | [12 empty] | Applications/Tools | OPEN | Live report is available in UOC | Completed With Artifacts | TRUE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1839 | NOC18 | NOC | NA |  |  |  | BSS | Service Provisioning | configure of GI services and tracking and publishing data Weekly |  | Critical | OPEN | BSS | CRM | It will be available in NSO and BSS | [12 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1840 | NOC180 | NOC | NA |  |  |  | DWDM | OSS | Published Zonal Network uptime (like, total scope, litup count and availability according to the category) Daily |  | Critical | COMPLETED | HPSM | Incident Management | [13 empty] | Applications/Tools | OPEN | 0 | Completed With Artifacts | TRUE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1841 | NOC181 | NOC | NA |  |  |  | DWDM | OSS | Published Zonal Network uptime (like, total scope, litup count and availability according to the category) Weekly |  | Critical | OPEN | HPSM | Incident Management | Uptime and MMTR are two separate reports. | [12 empty] | Applications/Tools | OPEN |  | Not-Feasible | FALSE | [7 empty] | Open | Open | Open
1842 | NOC182 | NOC | NA |  |  |  | DWDM | OSS | Published Zonal Network uptime (like, total scope, litup count and availability according to the category) Monthly |  | Critical | COMPLETED | HPSM | Incident Management | [13 empty] | Applications/Tools | Closed | 0 | Completed With Artifacts | TRUE | [5 empty] | 2025-11-18 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\OSS\52 Artefcats_18112025 | Closed after 14-Nov-25 | Closed after 14-Nov-25 | Completed but Verification undrer Process
1843 | NOC183 | NOC | NA |  |  |  | DWDM | OSS | Published Zonal Network uptime (like, total scope, litup count and availability according to the category) (Selective from and to dates) |  | Critical | COMPLETED | HPSM | Incident Management | [13 empty] | Applications/Tools | OPEN | 0 | Completed With Artifacts | TRUE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1844 | NOC184 | NOC | NA |  |  |  | DWDM | OSS | Publishing Package wise , district wise and node wise (like DWDM,OADM) Zonal Network uptime and Mandal TT resolution MTTR dashboard Daily |  | Critical | COMPLETED | HPSM | Incident Management | [13 empty] | Applications/Tools | OPEN | 0 | Completed With Artifacts | TRUE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1845 | NOC185 | NOC | NA |  |  |  | DWDM | OSS | Publishing Package wise , district wise and node wise (like DWDM,OADM) Zonal Network uptime and Mandal TT resolution MTTR dashboard Weekly |  | Critical | COMPLETED | HPSM | Incident Management | [13 empty] | Applications/Tools | OPEN | 0 | Completed With Artifacts | TRUE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1846 | NOC186 | NOC | NA |  |  |  | DWDM | OSS | Publishing Package wise , district wise and node wise (like DWDM,OADM) Zonal Network uptime and Mandal TT resolution MTTR dashboard Monthly |  | Critical | COMPLETED | HPSM | Incident Management | [13 empty] | Applications/Tools | OPEN | 0 | Completed With Artifacts | TRUE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1847 | NOC187 | NOC | NA |  |  |  | DWDM | OSS | Publishing Package wise , district wise and node wise (like DWDM,OADM) Zonal Network uptime and Mandal TT resolution MTTR dashboard (Selective from and to dates) |  | Critical | OPEN | HPSM | Incident Management | Uptime and MMTR are two separate reports. | [12 empty] | Applications/Tools | OPEN |  | Completed With Artifacts | FALSE | [7 empty] | Open | Open | Open
1848 | NOC188 | NOC | NA |  |  |  | DWDM | OSS | Preparation and publishing of Zonal link summary , uptime and MTTR dashboard Daily |  | Critical | COMPLETED | HPSM | Incident Management | 11-09-2025: Uptime/Availability and MTTR is available for daily and monthly | [12 empty] | Applications/Tools | OPEN | 11-09-2025: Uptime/Availability and MTTR is available for daily and monthly | Completed With Artifacts | TRUE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1849 | NOC189 | NOC | NA |  |  |  | DWDM | OSS | Preparation and publishing of Zonal link summary , uptime and MTTR dashboard Weekly |  | Critical | OPEN | HPSM | Incident Management | 11-09-2025: Uptime/Availability and MTTR is available for daily and monthly | [12 empty] | Applications/Tools | OPEN | 11-09-2025: Uptime/Availability and MTTR is available for daily and monthly | WIP | TRUE | [7 empty] | Open | Open | Open
1850 | NOC19 | NOC | NA |  |  |  | BSS | Service Provisioning | configure of GI services and tracking and publishing data Monthly |  | Critical | OPEN | BSS | CRM | It will be available in NSO and BSS | [12 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1851 | NOC190 | NOC | NA |  |  |  | DWDM | OSS | Preparation and publishing of Zonal link summary , uptime and MTTR dashboard Monthly |  | Critical | OPEN | HPSM | Incident Management | 11-09-2025: Uptime/Availability and MTTR is available for daily and monthly | [12 empty] | Applications/Tools | OPEN | 11-09-2025: Uptime/Availability and MTTR is available for daily and monthly | WIP | TRUE | [7 empty] | Open | Open | Open
1852 | NOC191 | NOC | NA |  |  |  | DWDM | OSS | Preparation and publishing of Zonal link summary , uptime and MTTR dashboard (Selective from and to dates) |  | Critical | OPEN | HPSM | Incident Management | Uptime and MMTR are two separate reports. | [12 empty] | Applications/Tools | OPEN |  | Completed With Artifacts | FALSE | [7 empty] | Open | Open | Open
1853 | NOC192 | NOC | NA |  |  |  | DWDM | OSS | Preparing and publishing Zonal Link Fiber MTTR dashboard Daily |  | Critical | OPEN | HPSM | Incident Management | [13 empty] | Applications/Tools | OPEN | 0 | Completed With Artifacts | TRUE | [7 empty] | Open | Open | Open
1854 | NOC193 | NOC | NA |  |  |  | DWDM | OSS | Preparing and publishing Zonal Link Fiber MTTR dashboard Weekly |  | Critical | OPEN | HPSM | Incident Management | [13 empty] | Applications/Tools | OPEN | 0 | WIP | TRUE | [7 empty] | Open | Open | Open
1855 | NOC194 | NOC | NA |  |  |  | DWDM | OSS | Preparing and publishing Zonal Link Fiber MTTR dashboard Monthly |  | Critical | OPEN | HPSM | Incident Management | [13 empty] | Applications/Tools | OPEN | 0 | WIP | TRUE | [7 empty] | Open | Open | Open
1856 | NOC195 | NOC | NA |  |  |  | DWDM | OSS | Preparing and publishing Zonal Link Fiber MTTR dashboard (Selective from and to dates) |  | Critical | OPEN | HPSM | Incident Management | Uptime and MMTR are two separate reports. | [12 empty] | Applications/Tools | OPEN |  | WIP | FALSE | [7 empty] | Open | Open | Open
1857 | NOC196 | NOC | NA |  |  |  | DWDM | OSS | Preparation and publishing dashboard for major events happened in network Hourly |  | Critical | OPEN | HPSM | Incident Management | Option is Availale in UOC (FAS) to check major alarms | [12 empty] | Applications/Tools | OPEN | Option is Availale in UOC (FAS) to check major alarms | Completed With Artifacts | TRUE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1858 | NOC197 | NOC | NA |  |  |  | DWDM | OSS | Preparation and publishing dashboard for major events happened in network Daily |  | Critical | COMPLETED | HPSM | Incident Management | [13 empty] | Applications/Tools | OPEN | 0 | Completed With Artifacts | TRUE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1859 | NOC198 | NOC | NA |  |  |  | DWDM | OSS | Preparation and publishing dashboard for major events happened in network Weekly |  | Critical | COMPLETED | HPSM | Incident Management | [13 empty] | Applications/Tools | OPEN | 0 | Completed With Artifacts | TRUE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1860 | NOC199 | NOC | NA |  |  |  | DWDM | OSS | Preparation and publishing dashboard for major events happened in network Monthly |  | Critical | COMPLETED | HPSM | Incident Management | [13 empty] | Applications/Tools | OPEN | 0 | Completed With Artifacts | TRUE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1861 | NOC2 | NOC | NA |  | OSS | OSS | OSS | DC | DC Active Infra uptime & SLA Weekly |  | Critical |  | HPSM | Incident Management | [13 empty] | Applications/Tools | OPEN | 0 | OPEN | TRUE | [7 empty] | Open | Open | Open
1862 | NOC20 | NOC | NA |  |  |  | BSS | Service Provisioning | configure of GI services and tracking and publishing data (Selective from and to dates) |  | Critical | OPEN | BSS | CRM | It will be available in NSO and BSS | [12 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
1863 | NOC200 | NOC | NA |  |  |  | DWDM | OSS | Preparation and publishing dashboard for major events happened in network (Selective from and to dates) |  | Critical | COMPLETED | HPSM | Incident Management | [13 empty] | Applications/Tools | OPEN | 0 | Completed With Artifacts | TRUE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1864 | NOC201 | NOC | NA |  |  |  | DWDM | OSS | Preparation and publishing of all DC DWDM devices availability dashboard Daily |  | Critical | COMPLETED | OSS Dashboards | UOC | [13 empty] | Applications/Tools | OPEN | 0 | Completed With Artifacts | TRUE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1865 | NOC202 | NOC | NA |  |  |  | DWDM | OSS | Preparation and publishing of all DC DWDM devices availability dashboard Weekly |  | Critical | NOT_FEASIBLE | OSS Dashboards | UOC | [13 empty] | Applications/Tools | OPEN | 0 | Not-Feasible | TRUE | [7 empty] | Open | Open | Open
1866 | NOC203 | NOC | NA |  |  |  | DWDM | OSS | Preparation and publishing of all DC DWDM devices availability dashboard Monthly |  | Critical | COMPLETED | OSS Dashboards | UOC | [13 empty] | Applications/Tools | OPEN | 0 | Completed With Artifacts | TRUE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1867 | NOC204 | NOC | NA |  |  |  | DWDM | OSS | Preparation and publishing of all DC DWDM devices availability dashboard (Selective from and to dates) |  | Critical | COMPLETED | OSS Dashboards | UOC | 18-Nov-25: Dashboard Not Available, Report is available | [12 empty] | Applications/Tools | OPEN | 0 | Completed With Artifacts | TRUE | [7 empty] | Reopened | Reopened | Completed but Verification undrer Process
1868 | NOC205 | NOC | NA |  |  |  | DWDM | OSS | T-NOC Report : Zonal Links DWDM DFR Status as on 15-May-2025 Action to be taken on Top Most Priority Daily |  | Critical | COMPLETED | HPSM | Incident Management | [13 empty] | Applications/Tools | OPEN | 0 | Completed With Artifacts | TRUE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1869 | NOC206 | NOC | NA |  |  |  | DWDM | OSS | T-NOC Report : Zonal Links DWDM DFR Status as on 15-May-2025 Action to be taken on Top Most Priority Weekly |  | Critical | COMPLETED | HPSM | Incident Management | 09-09-2025: Ticket data based on Service Manager | [12 empty] | Applications/Tools | OPEN | 09-09-2025: Ticket data based on Service Manager | Completed With Artifacts | TRUE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1870 | NOC207 | NOC | NA |  |  |  | DWDM | OSS | T-NOC Report : Zonal Links DWDM DFR Status as on 15-May-2025 Action to be taken on Top Most Priority Monthly |  | Critical | COMPLETED | HPSM | Incident Management | [13 empty] | Applications/Tools | OPEN | 0 | Completed With Artifacts | TRUE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1871 | NOC208 | NOC | NA |  |  |  | DWDM | OSS | T-NOC Report : Zonal Links DWDM DFR Status as on 15-May-2025 Action to be taken on Top Most Priority (Selective from and to dates) |  | Critical | COMPLETED | HPSM | Incident Management | [13 empty] | Applications/Tools | OPEN | 0 | Completed With Artifacts | TRUE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1872 | NOC209 | NOC | NA |  |  |  | DWDM | OSS | Zonal High Received Span Losses with TT for PKG_A Daily |  | Critical | OPEN | OSS Dashboards | UOC | [13 empty] | Applications/Tools | Closed | 0 | Completed With Artifacts | TRUE | [5 empty] | 2025-11-18 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\OSS\52 Artefcats_18112025 | Closed after 14-Nov-25 | Closed after 14-Nov-25 | Completed but Verification undrer Process
1873 | NOC21 | NOC | NA |  | OSS | OSS | OSS | Service Assurance | Monitoring,tracking of field details, Tracking of GI services form and prepare Service assurance dashboard Hourly |  | NON-Critical | OPEN | HPSM | Incident Management | OPEN-DEPENDENT | [12 empty] | Applications/Tools | OPEN |  | Open-Dependent | FALSE | [7 empty] | Open | Open | Open
1874 | NOC210 | NOC | NA |  |  |  | DWDM | OSS | Zonal High Received Span Losses with TT for PKG_A Weekly |  | Critical | OPEN | OSS Dashboards | UOC | [13 empty] | Applications/Tools | Closed | 0 | Completed With Artifacts | TRUE | [5 empty] | 2025-11-18 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\OSS\52 Artefcats_18112025 | Closed after 14-Nov-25 | Closed after 14-Nov-25 | Completed but Verification undrer Process
1875 | NOC211 | NOC | NA |  |  |  | DWDM | OSS | Zonal High Received Span Losses with TT for PKG_A Monthly |  | Critical | OPEN | OSS Dashboards | UOC | [13 empty] | Applications/Tools | Closed | 0 | Completed With Artifacts | TRUE | [5 empty] | 2025-11-18 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\OSS\52 Artefcats_18112025 | Closed after 14-Nov-25 | Closed after 14-Nov-25 | Completed but Verification undrer Process
1876 | NOC212 | NOC | NA |  |  |  | DWDM | OSS | Zonal High Received Span Losses with TT for PKG_A (Selective from and to dates) |  | Critical | OPEN | OSS Dashboards | UOC | [13 empty] | Applications/Tools | Closed | 0 | Completed With Artifacts | TRUE | [5 empty] | 2025-11-18 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\OSS\52 Artefcats_18112025 | Closed after 14-Nov-25 | Closed after 14-Nov-25 | Completed but Verification undrer Process
1877 | NOC213 | NOC | NA |  |  |  | DWDM | OSS | Zonal High Received Span Losses with TT for PKG_B Daily |  | Critical | OPEN | OSS Dashboards | UOC | [13 empty] | Applications/Tools | Closed | 0 | Completed With Artifacts | TRUE | [5 empty] | 2025-11-18 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\OSS\52 Artefcats_18112025 | Closed after 14-Nov-25 | Closed after 14-Nov-25 | Completed but Verification undrer Process
1878 | NOC214 | NOC | NA |  |  |  | DWDM | OSS | Zonal High Received Span Losses with TT for PKG_B Weekly |  | Critical | OPEN | OSS Dashboards | UOC | [13 empty] | Applications/Tools | Closed | 0 | Completed With Artifacts | TRUE | [5 empty] | 2025-11-18 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\OSS\52 Artefcats_18112025 | Closed after 14-Nov-25 | Closed after 14-Nov-25 | Completed but Verification undrer Process
1879 | NOC215 | NOC | NA |  |  |  | DWDM | OSS | Zonal High Received Span Losses with TT for PKG_B Monthly |  | Critical | OPEN | OSS Dashboards | UOC | [13 empty] | Applications/Tools | Closed | 0 | Completed With Artifacts | TRUE | [5 empty] | 2025-11-18 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\OSS\52 Artefcats_18112025 | Closed after 14-Nov-25 | Closed after 14-Nov-25 | Completed but Verification undrer Process
1880 | NOC216 | NOC | NA |  |  |  | DWDM | OSS | Zonal High Received Span Losses with TT for PKG_B (Selective from and to dates) |  | Critical | OPEN | OSS Dashboards | UOC | [13 empty] | Applications/Tools | Closed | 0 | Completed With Artifacts | TRUE | [5 empty] | 2025-11-18 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\OSS\52 Artefcats_18112025 | Closed after 14-Nov-25 | Closed after 14-Nov-25 | Completed but Verification undrer Process
1881 | NOC217 | NOC | NA |  |  |  | DWDM | OSS | Zonal High Received Span Losses with TT for PKG_C Daily |  | Critical | OPEN | OSS Dashboards | UOC | [13 empty] | Applications/Tools | Closed | 0 | Completed With Artifacts | TRUE | [5 empty] | 2025-11-18 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\OSS\52 Artefcats_18112025 | Closed after 14-Nov-25 | Closed after 14-Nov-25 | Completed but Verification undrer Process
1882 | NOC218 | NOC | NA |  |  |  | DWDM | OSS | Zonal High Received Span Losses with TT for PKG_C Weekly |  | Critical | OPEN | OSS Dashboards | UOC | [13 empty] | Applications/Tools | Closed | 0 | Completed With Artifacts | TRUE | [5 empty] | 2025-11-18 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\OSS\52 Artefcats_18112025 | Closed after 14-Nov-25 | Closed after 14-Nov-25 | Completed but Verification undrer Process
1883 | NOC219 | NOC | NA |  |  |  | DWDM | OSS | Zonal High Received Span Losses with TT for PKG_C Monthly |  | Critical | OPEN | OSS Dashboards | UOC | [13 empty] | Applications/Tools | Closed | 0 | Completed With Artifacts | TRUE | [5 empty] | 2025-11-18 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\OSS\52 Artefcats_18112025 | Closed after 14-Nov-25 | Closed after 14-Nov-25 | Completed but Verification undrer Process
1884 | NOC22 | NOC | NA |  | OSS | OSS | OSS | Service Assurance | Monitoring,tracking of field details, Tracking of GI services form and prepare Service assurance dashboard Daily |  | NON-Critical | OPEN | HPSM | Incident Management | OPEN-DEPENDENT | [12 empty] | Applications/Tools | OPEN |  | Open-Dependent | FALSE | [7 empty] | Open | Open | Open
1885 | NOC220 | NOC | NA |  |  |  | DWDM | OSS | Zonal High Received Span Losses with TT for PKG_C (Selective from and to dates) |  | Critical | OPEN | OSS Dashboards | UOC | [13 empty] | Applications/Tools | Closed | 0 | Completed With Artifacts | TRUE | [5 empty] | 2025-11-18 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\OSS\52 Artefcats_18112025 | Closed after 14-Nov-25 | Closed after 14-Nov-25 | Completed but Verification undrer Process
1886 | NOC221 | NOC | NA |  | OSS | OSS | OSS | GPON/IPMPLS | Monitoring and published of Dark Fiber and TSWAN KPI Daily |  | Critical | OPEN | HPSM | Incident Management | OPEN-DEPENDENT | [12 empty] | Applications/Tools | OPEN |  | Open-Dependent | FALSE | [7 empty] | Open | Open | Open
1887 | NOC222 | NOC | NA |  | OSS | OSS | OSS | GPON/IPMPLS | Monitoring and published of Dark Fiber and TSWAN KPI Weekly |  | Critical | OPEN | HPSM | Incident Management | OPEN-DEPENDENT | [12 empty] | Applications/Tools | OPEN |  | Open-Dependent | FALSE | [7 empty] | Open | Open | Open
1888 | NOC223 | NOC | NA |  | OSS | OSS | OSS | GPON/IPMPLS | Monitoring and published of Dark Fiber and TSWAN KPI Monthly |  | Critical | OPEN | HPSM | Incident Management | OPEN-DEPENDENT | [12 empty] | Applications/Tools | OPEN |  | Open-Dependent | FALSE | [7 empty] | Open | Open | Open
1889 | NOC224 | NOC | NA |  | OSS | OSS | OSS | GPON/IPMPLS | Monitoring and published of Dark Fiber and TSWAN KPI (Selective from and to dates) |  | Critical | OPEN | HPSM | Incident Management | OPEN-DEPENDENT | [12 empty] | Applications/Tools | OPEN |  | Open-Dependent | FALSE | [7 empty] | Open | Open | Open
1890 | NOC225 | NOC | NA |  |  |  | IP/MPLS | OSS | Preparation and publishing of GP to GP and GP to Mandal link summary , uptime and MTTR dashboard Hourly |  | Critical | OPEN | HPSM | Incident Management | 11-09-2025: Uptime/Availability and MTTR is available for daily and monthly | [12 empty] | Applications/Tools | OPEN | 11-09-2025: Uptime/Availability and MTTR is available for daily and monthly | Completed With Artifacts | TRUE | [7 empty] | Open | Open | Open
1891 | NOC226 | NOC | NA |  |  |  | IP/MPLS | OSS | Preparation and publishing of GP to GP and GP to Mandal link summary , uptime and MTTR dashboard Daily |  | Critical | COMPLETED | HPSM | Incident Management | 11-09-2025: Uptime/Availability and MTTR is available for daily and monthly | [12 empty] | Applications/Tools | OPEN | 11-09-2025: Uptime/Availability and MTTR is available for daily and monthly | Completed With Artifacts | TRUE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1892 | NOC227 | NOC | NA |  |  |  | IP/MPLS | OSS | Preparation and publishing of GP to GP and GP to Mandal link summary , uptime and MTTR dashboard Weekly |  | Critical | COMPLETED | HPSM | Incident Management | [13 empty] | Applications/Tools | OPEN | We dont have weekly report | Completed With Artifacts | FALSE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1893 | NOC228 | NOC | NA |  |  |  | IP/MPLS | OSS | Preparation and publishing of GP to GP and GP to Mandal link summary , uptime and MTTR dashboard Monthly |  | Critical | OPEN | HPSM | Incident Management | 11-09-2025: Uptime/Availability and MTTR is available for daily and monthly | [12 empty] | Applications/Tools | OPEN | 11-09-2025: Uptime/Availability and MTTR is available for daily and monthly | Completed With Artifacts | TRUE | [7 empty] | Open | Open | Open
1894 | NOC229 | NOC | NA |  |  |  | IP/MPLS | OSS | Preparation and publishing of GP to GP and GP to Mandal link summary , uptime and MTTR dashboard (Selective from and to dates) |  | Critical | OPEN | HPSM | Incident Management | 11-09-2025: Uptime/Availability and MTTR is available for daily and monthly | [12 empty] | Applications/Tools | OPEN | 11-09-2025: Uptime/Availability and MTTR is available for daily and monthly | Completed With Artifacts | TRUE | [7 empty] | Open | Open | Open
1895 | NOC23 | NOC | NA |  | OSS | OSS | OSS | Service Assurance | Monitoring,tracking of field details, Tracking of GI services form and prepare Service assurance dashboard Weekly |  | NON-Critical | OPEN | HPSM | Incident Management | OPEN-DEPENDENT | [12 empty] | Applications/Tools | OPEN |  | Open-Dependent | FALSE | [7 empty] | Open | Open | Open
1896 | NOC230 | NOC | NA |  |  |  | IP/MPLS | OSS | Preparation and publishing of Mandal to Mandal and Mandal to Zonal link summary , uptime and MTTR dashboard Daily |  | Critical | COMPLETED | HPSM | Incident Management | 11-09-2025: Uptime/Availability and MTTR is available for daily and monthly | [12 empty] | Applications/Tools | OPEN | 11-09-2025: Uptime/Availability and MTTR is available for daily and monthly | Completed With Artifacts | TRUE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1897 | NOC231 | NOC | NA |  |  |  | IP/MPLS | OSS | Preparation and publishing of Mandal to Mandal and Mandal to Zonal link summary , uptime and MTTR dashboard Weekly |  | Critical | OPEN | HPSM | Incident Management | 11-09-2025: Uptime/Availability and MTTR is available for daily and monthly | [12 empty] | Applications/Tools | OPEN | 11-09-2025: Uptime/Availability and MTTR is available for daily and monthly | Completed With Artifacts | TRUE | [7 empty] | Open | Open | Open
1898 | NOC232 | NOC | NA |  |  |  | IP/MPLS | OSS | Preparation and publishing of Mandal to Mandal and Mandal to Zonal link summary , uptime and MTTR dashboard Monthly |  | Critical | OPEN | HPSM | Incident Management | 11-09-2025: Uptime/Availability and MTTR is available for daily and monthly | [12 empty] | Applications/Tools | OPEN | 11-09-2025: Uptime/Availability and MTTR is available for daily and monthly | Completed With Artifacts | TRUE | [7 empty] | Open | Open | Open
1899 | NOC233 | NOC | NA |  |  |  | IP/MPLS | OSS | Preparation and publishing of Mandal to Mandal and Mandal to Zonal link summary , uptime and MTTR dashboard (Selective from and to dates) |  | Critical | OPEN | HPSM | Incident Management | 11-09-2025: Uptime/Availability and MTTR is available for daily and monthly | [12 empty] | Applications/Tools | OPEN | 11-09-2025: Uptime/Availability and MTTR is available for daily and monthly | WIP | TRUE | [7 empty] | Open | Open | Open
1900 | NOC234 | NOC | NA |  |  |  | IP/MPLS | OSS | High priority link like Tfiber ring monitoring and publishing KPI Hourly |  | Critical | OPEN | HPSM | Incident Management | Manually group needs to form in the NNMi and from that group it can be monitored. Venkatesh is giving KT to Operation team | [12 empty] | Applications/Tools | OPEN | Manually group needs to form in the NNMi and from that group it can be monitored. Venkatesh is giving KT to Operation team | Completed With Artifacts | TRUE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1901 | NOC235 | NOC | NA |  |  |  | IP/MPLS | OSS | High priority link like Tfiber ring monitoring and publishing KPI Daily |  | Critical | COMPLETED | HPSM | Incident Management | [13 empty] | Applications/Tools | OPEN | 0 | Completed With Artifacts | TRUE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1902 | NOC236 | NOC | NA |  |  |  | IP/MPLS | OSS | High priority link like Tfiber ring monitoring and publishing KPI Weekly |  | Critical | OPEN | HPSM | Incident Management | Manually group needs to form in the NNMi and from that group it can be monitored. Venkatesh is giving KT to Operation team | [12 empty] | Applications/Tools | OPEN | Manually group needs to form in the NNMi and from that group it can be monitored. Venkatesh is giving KT to Operation team | Completed With Artifacts | TRUE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1903 | NOC237 | NOC | NA |  |  |  | IP/MPLS | OSS | High priority link like Tfiber ring monitoring and publishing KPI Monthly |  | Critical | COMPLETED | HPSM | Incident Management | [13 empty] | Applications/Tools | OPEN | 0 | Completed With Artifacts | TRUE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1904 | NOC238 | NOC | NA |  |  |  | IP/MPLS | OSS | High priority link like Tfiber ring monitoring and publishing KPI (Selective from and to dates) |  | Critical | COMPLETED | HPSM | Incident Management | [13 empty] | Applications/Tools | OPEN | 0 | Completed With Artifacts | TRUE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1905 | NOC239 | NOC | NA |  |  |  | IP/MPLS | OSS | Enteprise Services Delivery ( Aitel Towers, Airtel LWEsite, pioneer etc ) Monitoring, preparation KPI like Service Up reports Hourly |  | Critical | OPEN | HPSM | Incident Management | OPEN-DEPENDENT | [12 empty] | Applications/Tools | OPEN |  | Open-Dependent | FALSE | [7 empty] | Open | Open | Open
1906 | NOC24 | NOC | NA |  | OSS | OSS | OSS | Service Assurance | Monitoring,tracking of field details, Tracking of GI services form and prepare Service assurance dashboard Monthly |  | NON-Critical | OPEN | HPSM | Incident Management | OPEN-DEPENDENT | [12 empty] | Applications/Tools | OPEN |  | Open-Dependent | FALSE | [7 empty] | Open | Open | Open
1907 | NOC240 | NOC | NA |  |  |  | IP/MPLS | OSS | Enteprise Services Delivery ( Aitel Towers, Airtel LWEsite, pioneer etc ) Monitoring, preparation KPI like Service Up reports Daily |  | Critical | OPEN | HPSM | Incident Management | OPEN-DEPENDENT | [12 empty] | Applications/Tools | OPEN |  | Open-Dependent | FALSE | [7 empty] | Open | Open | Open
1908 | NOC241 | NOC | NA |  |  |  | IP/MPLS | OSS | Enteprise Services Delivery ( Aitel Towers, Airtel LWEsite, pioneer etc ) Monitoring, preparation KPI like Service Up reports Weekly |  | Critical | OPEN | HPSM | Incident Management | OPEN-DEPENDENT | [12 empty] | Applications/Tools | OPEN |  | Open-Dependent | FALSE | [7 empty] | Open | Open | Open
1909 | NOC242 | NOC | NA |  |  |  | IP/MPLS | OSS | Enteprise Services Delivery ( Aitel Towers, Airtel LWEsite, pioneer etc ) Monitoring, preparation KPI like Service Up reports Monthly |  | Critical | OPEN | HPSM | Incident Management | OPEN-DEPENDENT | [12 empty] | Applications/Tools | OPEN |  | Open-Dependent | FALSE | [7 empty] | Open | Open | Open
1910 | NOC243 | NOC | NA |  |  |  | IP/MPLS | OSS | Enteprise Services Delivery ( Aitel Towers, Airtel LWEsite, pioneer etc ) Monitoring, preparation KPI like Service Up reports (Selective from and to dates) |  | Critical | OPEN | HPSM | Incident Management | OPEN-DEPENDENT | [12 empty] | Applications/Tools | OPEN |  | Open-Dependent | FALSE | [7 empty] | Open | Open | Open
1911 | NOC244 | NOC | NA |  |  |  | IP/MPLS | OSS | Preparation and publishing of Enterprise Customer Service KPIs like availability, packet drops, latency, jitter & bandwidth utilization Daily |  | Critical | COMPLETED | HPSM | Incident Management | [13 empty] | Applications/Tools | OPEN | 0 | Completed With Artifacts | TRUE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1912 | NOC245 | NOC | NA |  |  |  | IP/MPLS | OSS | Preparation and publishing of Enterprise Customer Service KPIs like availability, packet drops, latency, jitter & bandwidth utilization Weekly |  | Critical | COMPLETED | HPSM | Incident Management | [13 empty] | Applications/Tools | OPEN | 0 | Completed With Artifacts | TRUE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1913 | NOC246 | NOC | NA |  |  |  | IP/MPLS | OSS | Preparation and publishing of Enterprise Customer Service KPIs like availability, packet drops, latency, jitter & bandwidth utilization Monthly |  | Critical | COMPLETED | HPSM | Incident Management | [13 empty] | Applications/Tools | OPEN | availability, packet drops & bandwidth utilization is there | Completed With Artifacts | FALSE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1914 | NOC247 | NOC | NA |  |  |  | IP/MPLS | OSS | Preparation and publishing of Enterprise Customer Service KPIs like availability, packet drops, latency, jitter & bandwidth utilization (Selective from and to dates) |  | Critical | COMPLETED | HPSM | Incident Management | [13 empty] | Applications/Tools | OPEN | availability, packet drops & bandwidth utilization is there | Completed With Artifacts | FALSE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1915 | NOC248 | NOC | NA |  |  |  | IP/MPLS | OSS | Preparation and publishing of all DC MPLS Network devices availability dashboard Daily |  | Critical | COMPLETED | NNMI | NPS | [13 empty] | Applications/Tools | OPEN | 0 | Completed With Artifacts | TRUE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1916 | NOC249 | NOC | NA |  |  |  | IP/MPLS | OSS | Preparation and publishing of all DC MPLS Network devices availability dashboard Weekly |  | Critical | NOT_FEASIBLE | NNMI | NPS | [13 empty] | Applications/Tools |  | available- hourly & weekly in NPS | Completed With Artifacts | FALSE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1917 | NOC25 | NOC | NA |  | OSS | OSS | OSS | Service Assurance | Monitoring,tracking of field details, Tracking of GI services form and prepare Service assurance dashboard(Selective from and to dates) |  | NON-Critical | OPEN | HPSM | Incident Management | OPEN-DEPENDENT | [12 empty] | Applications/Tools | OPEN |  | Open-Dependent | FALSE | [7 empty] | Open | Open | Open
1918 | NOC250 | NOC | NA |  |  |  | IP/MPLS | OSS | Preparation and publishing of all DC MPLS Network devices availability dashboard Monthly |  | Critical | COMPLETED | NNMI | NPS | [13 empty] | Applications/Tools | OPEN | 0 | Completed With Artifacts | TRUE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1919 | NOC251 | NOC | NA |  |  |  | IP/MPLS | OSS | Preparation and publishing of all DC MPLS Network devices availability dashboard (Selective from and to dates) |  | Critical | COMPLETED | NNMI | NPS | [13 empty] | Applications/Tools | OPEN | 0 | Completed With Artifacts | TRUE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1920 | NOC252 | NOC | NA |  |  |  | IP/MPLS | OSS | Prepartion and publishing of Core link availability and utilization dashboard Hourly |  | Critical | COMPLETED | HPSM | Incident Management | Link Group can be created in NNMi and monitor for only IPMPLS links | [12 empty] | Applications/Tools | OPEN | Link Group can be created in NNMi and monitor for only IPMPLS links | Completed With Artifacts | TRUE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1921 | NOC253 | NOC | NA |  |  |  | IP/MPLS | OSS | Prepartion and publishing of Core link availability and utilization dashboard Daily |  | Critical | COMPLETED | NNMI | NPS | [13 empty] | Applications/Tools | OPEN | 0 | Completed With Artifacts | TRUE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1922 | NOC254 | NOC | NA |  |  |  | IP/MPLS | OSS | Prepartion and publishing of Core link availability and utilization dashboard Weekly |  | Critical | COMPLETED | NNMI | NPS | [13 empty] | Applications/Tools | OPEN | 0 | Completed With Artifacts | TRUE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1923 | NOC255 | NOC | NA |  |  |  | IP/MPLS | OSS | Prepartion and publishing of Core link availability and utilization dashboard Monthly |  | Critical | COMPLETED | NNMI | NPS | [13 empty] | Applications/Tools | OPEN | 0 | Completed With Artifacts | TRUE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1924 | NOC256 | NOC | NA |  |  |  | IP/MPLS | OSS | Prepartion and publishing of Core link availability and utilization dashboard (Selective from and to dates) |  | Critical | COMPLETED | NNMI | NPS | Link Group can be created in NNMi and monitor for only IPMPLS links | [12 empty] | Applications/Tools | OPEN | Link Group can be created in NNMi and monitor for only IPMPLS links | Completed With Artifacts | TRUE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1925 | NOC257 | NOC | NA |  |  |  | IP/MPLS | OSS | Package A Low RX Optical Power Levels in IPMPLS Network Daily |  | Critical | OPEN | NNMI | NNMI | 09-09-2025: Need confirmation from OT for "Low RX Optical Power Levels" KPI | [12 empty] | Applications/Tools | OPEN | 09-09-2025: Need confirmation from OT for "Low RX Optical Power Levels" KPI | OPEN | TRUE | [7 empty] | Open | Open | Open
1926 | NOC258 | NOC | NA |  |  |  | IP/MPLS | OSS | Package A Low RX Optical Power Levels in IPMPLS Network Weekly |  | Critical | OPEN | NNMI | NNMI | [13 empty] | Applications/Tools | OPEN | 0 | OPEN | TRUE | [7 empty] | Open | Open | Open
1927 | NOC259 | NOC | NA |  |  |  | IP/MPLS | OSS | Package A Low RX Optical Power Levels in IPMPLS Network Monthly |  | Critical | OPEN | NNMI | NNMI | 09-09-2025: Need confirmation from OT for "Low RX Optical Power Levels" KPI | [12 empty] | Applications/Tools | OPEN | 09-09-2025: Need confirmation from OT for "Low RX Optical Power Levels" KPI | OPEN | TRUE | [7 empty] | Open | Open | Open
1928 | NOC26 | NOC | NA |  | OSS | OSS | OSS | Service Monitoring | Monitoring,tracking service details, Tracking of GI services uptime Service assurance dashboard Daily |  | Critical | OPEN | HPSM | Incident Management | OPEN-DEPENDENT | [12 empty] | Applications/Tools | OPEN |  | Open-Dependent | FALSE | [7 empty] | Open | Open | Open
1929 | NOC260 | NOC | NA |  |  |  | IP/MPLS | OSS | Package A Low RX Optical Power Levels in IPMPLS Network (Selective from and to dates) |  | Critical | OPEN | NNMI | NNMI | 09-09-2025: Need confirmation from OT for "Low RX Optical Power Levels" KPI | [12 empty] | Applications/Tools | OPEN | 09-09-2025: Need confirmation from OT for "Low RX Optical Power Levels" KPI | OPEN | TRUE | [7 empty] | Open | Open | Open
1930 | NOC261 | NOC | NA |  |  |  | IP/MPLS | OSS | Package B Low RX Optical Power Levels in IPMPLS Network Daily |  | Critical | OPEN | NNMI | NNMI | 09-09-2025: Need confirmation from OT for "Low RX Optical Power Levels" KPI | [12 empty] | Applications/Tools | OPEN | 09-09-2025: Need confirmation from OT for "Low RX Optical Power Levels" KPI | OPEN | TRUE | [7 empty] | Open | Open | Open
1931 | NOC262 | NOC | NA |  |  |  | IP/MPLS | OSS | Package B Low RX Optical Power Levels in IPMPLS Network Weekly |  | Critical | OPEN | NNMI | NNMI | [13 empty] | Applications/Tools | OPEN | 0 | OPEN | TRUE | [7 empty] | Open | Open | Open
1932 | NOC263 | NOC | NA |  |  |  | IP/MPLS | OSS | Package B Low RX Optical Power Levels in IPMPLS Network Monthly |  | Critical | OPEN | NNMI | NNMI | 09-09-2025: Need confirmation from OT for "Low RX Optical Power Levels" KPI | [12 empty] | Applications/Tools | OPEN | 09-09-2025: Need confirmation from OT for "Low RX Optical Power Levels" KPI | OPEN | TRUE | [7 empty] | Open | Open | Open
1933 | NOC264 | NOC | NA |  |  |  | IP/MPLS | OSS | Package B Low RX Optical Power Levels in IPMPLS Network (Selective from and to dates) |  | Critical | OPEN | NNMI | NNMI | 09-09-2025: Need confirmation from OT for "Low RX Optical Power Levels" KPI | [12 empty] | Applications/Tools | OPEN | 09-09-2025: Need confirmation from OT for "Low RX Optical Power Levels" KPI | OPEN | TRUE | [7 empty] | Open | Open | Open
1934 | NOC265 | NOC | NA |  |  |  | IP/MPLS | OSS | Package C Low RX Optical Power Levels in IPMPLS Network Daily |  | Critical | OPEN | NNMI | NNMI | 09-09-2025: Need confirmation from OT for "Low RX Optical Power Levels" KPI | [12 empty] | Applications/Tools | OPEN | 09-09-2025: Need confirmation from OT for "Low RX Optical Power Levels" KPI | OPEN | TRUE | [7 empty] | Open | Open | Open
1935 | NOC266 | NOC | NA |  |  |  | IP/MPLS | OSS | Package C Low RX Optical Power Levels in IPMPLS Network Weekly |  | Critical | OPEN | NNMI | NNMI | [13 empty] | Applications/Tools | OPEN | 0 | OPEN | TRUE | [7 empty] | Open | Open | Open
1936 | NOC267 | NOC | NA |  |  |  | IP/MPLS | OSS | Package C Low RX Optical Power Levels in IPMPLS Network Monthly |  | Critical | OPEN | NNMI | NNMI | 09-09-2025: Need confirmation from OT for "Low RX Optical Power Levels" KPI | [12 empty] | Applications/Tools | OPEN | 09-09-2025: Need confirmation from OT for "Low RX Optical Power Levels" KPI | OPEN | TRUE | [7 empty] | Open | Open | Open
1937 | NOC268 | NOC | NA |  |  |  | IP/MPLS | OSS | Package C Low RX Optical Power Levels in IPMPLS Network (Selective from and to dates) |  | Critical | OPEN | NNMI | NNMI | 09-09-2025: Need confirmation from OT for "Low RX Optical Power Levels" KPI | [12 empty] | Applications/Tools | OPEN | 09-09-2025: Need confirmation from OT for "Low RX Optical Power Levels" KPI | OPEN | TRUE | [7 empty] | Open | Open | Open
1938 | NOC269 | NOC | NA |  |  |  | IP/MPLS | OSS | Mandal Link Down + GP Link Down DFR Daily |  | Critical | COMPLETED | HPSM | Incident Management | 09-09-2025: Need confirmation from OT for "Low RX Optical Power Levels" KPI | [12 empty] | Applications/Tools | OPEN | 09-09-2025: Need confirmation from OT for "Low RX Optical Power Levels" KPI | Completed With Artifacts | TRUE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1939 | NOC27 | NOC | NA |  | OSS | OSS | OSS | Service Monitoring | Monitoring,tracking service details, Tracking of GI services uptime Service assurance dashboard Weekly |  | Critical | OPEN | HPSM | Incident Management | OPEN-DEPENDENT | [12 empty] | Applications/Tools | OPEN |  | Open-Dependent | FALSE | [7 empty] | Open | Open | Open
1940 | NOC270 | NOC | NA |  |  |  | IP/MPLS | OSS | Mandal Link Down + GP Link Down DFR Weekly |  | Critical | COMPLETED | HPSM | Incident Management | [13 empty] | Applications/Tools | OPEN | 0 | Completed With Artifacts | TRUE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1941 | NOC271 | NOC | NA |  |  |  | IP/MPLS | OSS | Mandal Link Down + GP Link Down DFR Monthly |  | Critical | COMPLETED | HPSM | Incident Management | [13 empty] | Applications/Tools | OPEN | 0 | Completed With Artifacts | TRUE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1942 | NOC272 | NOC | NA |  |  |  | IP/MPLS | OSS | Mandal Link Down + GP Link Down DFR (Selective from and to dates) |  | Critical | COMPLETED | HPSM | Incident Management | [13 empty] | Applications/Tools | OPEN | 0 | Completed With Artifacts | TRUE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1943 | NOC273 | NOC | NA |  | OSS | OSS | All Domain | OSS | All Domain RMA Tracker //Daily Daily//Domain And package wise Filtering |  | Critical | COMPLETED | HPSM | Incident Management | Direct integration with OEM portal is not in scope, however manual ticket can be created in service manager using 'RMA_TAC' category and monitor the status and progress | [12 empty] | Applications/Tools | OPEN | Direct integration with OEM portal is not in scope, however manual ticket can be created in service manager using 'RMA_TAC' category and monitor the status and progress | Completed With Artifacts | TRUE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1944 | NOC274 | NOC | NA |  | OSS | OSS | All Domain | OSS | All Domain RMA Tracker //Daily Weekly Domain and package Wise Filtering |  | Critical | COMPLETED | HPSM | Incident Management | Direct integration with OEM portal is not in scope, however manual ticket can be created in service manager using 'RMA_TAC' category and monitor the status and progress | [12 empty] | Applications/Tools | OPEN | Direct integration with OEM portal is not in scope, however manual ticket can be created in service manager using 'RMA_TAC' category and monitor the status and progress | Completed With Artifacts | TRUE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1945 | NOC275 | NOC | NA |  | OSS | OSS | All Domain | OSS | All Domain RMA Tracker //Daily Monthly Domain and package Wise Filtering |  | Critical | COMPLETED | HPSM | Incident Management | Direct integration with OEM portal is not in scope, however manual ticket can be created in service manager using 'RMA_TAC' category and monitor the status and progress | [12 empty] | Applications/Tools | OPEN | Direct integration with OEM portal is not in scope, however manual ticket can be created in service manager using 'RMA_TAC' category and monitor the status and progress | Completed With Artifacts | TRUE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1946 | NOC276 | NOC | NA |  | OSS | OSS | All Domain | OSS | All OEM_TAC Cases Tracker Daily Domain and package Wise Filtering |  | Critical | COMPLETED | HPSM | Incident Management | Direct integration with OEM portal is not in scope, however manual ticket can be created in service manager using 'RMA_TAC' category and monitor the status and progress | [12 empty] | Applications/Tools | OPEN | Direct integration with OEM portal is not in scope, however manual ticket can be created in service manager using 'RMA_TAC' category and monitor the status and progress | Completed With Artifacts | TRUE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1947 | NOC277 | NOC | NA |  | OSS | OSS | All Domain | OSS | All OEM_TAC Cases Tracker Weekly Domain and package Wise Filtering |  | Critical | COMPLETED | HPSM | Incident Management | Direct integration with OEM portal is not in scope, however manual ticket can be created in service manager using 'RMA_TAC' category and monitor the status and progress | [12 empty] | Applications/Tools | OPEN | Direct integration with OEM portal is not in scope, however manual ticket can be created in service manager using 'RMA_TAC' category and monitor the status and progress | Completed With Artifacts | TRUE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1948 | NOC278 | NOC | NA |  | OSS | OSS | All Domain | OSS | All OEM_TAC Cases Tracker Monthly Domain and package Wise Filtering |  | Critical | COMPLETED | HPSM | Incident Management | Direct integration with OEM portal is not in scope, however manual ticket can be created in service manager using 'RMA_TAC' category and monitor the status and progress | [12 empty] | Applications/Tools | OPEN | Direct integration with OEM portal is not in scope, however manual ticket can be created in service manager using 'RMA_TAC' category and monitor the status and progress | Completed With Artifacts | TRUE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1949 | NOC279 | NOC | NA |  | OSS | OSS | All Domain | OSS | All OEM_TAC Cases Tracker (Selective from and to dates) Domain and package Wise Filtering |  | Critical | COMPLETED | HPSM | Incident Management | Direct integration with OEM portal is not in scope, however manual ticket can be created in service manager using 'RMA_TAC' category and monitor the status and progress | [12 empty] | Applications/Tools | OPEN | Direct integration with OEM portal is not in scope, however manual ticket can be created in service manager using 'RMA_TAC' category and monitor the status and progress | Completed With Artifacts | TRUE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1950 | NOC28 | NOC | NA |  | OSS | OSS | OSS | Service Monitoring | Monitoring,tracking service details, Tracking of GI services uptime Service assurance dashboard Monthly |  | Critical | OPEN | HPSM | Incident Management | OPEN-DEPENDENT | [12 empty] | Applications/Tools | OPEN |  | Open-Dependent | FALSE | [7 empty] | Open | Open | Open
1951 | NOC280 | NOC | NA |  | OSS | OSS | All Domain | OSS | All Sites Infra OPEN TTs details for HRT(High Temparature) Alarm Daily |  | Critical | COMPLETED | HPSM | Incident Management | [13 empty] | Applications/Tools | Closed | need to check | Completed With Artifacts | FALSE | [5 empty] | 2025-11-18 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\OSS\52 Artefcats_18112025 | Closed after 14-Nov-25 | Closed after 14-Nov-25 | Completed but Verification undrer Process
1952 | NOC281 | NOC | NA |  | OSS | OSS | All Domain | OSS | All Sites Infra OPEN TTs details for HRT(High Temparature) Alarm Weekly |  | Critical | COMPLETED | HPSM | Incident Management | [13 empty] | Applications/Tools | Closed | need to check | Completed With Artifacts | FALSE | [5 empty] | 2025-11-18 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\OSS\52 Artefcats_18112025 | Closed after 14-Nov-25 | Closed after 14-Nov-25 | Completed but Verification undrer Process
1953 | NOC282 | NOC | NA |  | OSS | OSS | All Domain | OSS | All Sites Infra OPEN TTs details for HRT(High Temparature) Alarm Monthly |  | Critical | COMPLETED | HPSM | Incident Management | [13 empty] | Applications/Tools | Closed | need to check | Completed With Artifacts | FALSE | [5 empty] | 2025-11-18 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\OSS\52 Artefcats_18112025 | Closed after 14-Nov-25 | Closed after 14-Nov-25 | Completed but Verification undrer Process
1954 | NOC283 | NOC | NA |  | OSS | OSS | All Domain | OSS | All Sites Infra OPEN TTs details for HRT(High Tempararure) Alarm (Selective from and to dates) |  | Critical | COMPLETED | HPSM | Incident Management | [13 empty] | Applications/Tools | Closed | need to check | Completed With Artifacts | FALSE | [5 empty] | 2025-11-18 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\OSS\52 Artefcats_18112025 | Closed after 14-Nov-25 | Closed after 14-Nov-25 | Completed but Verification undrer Process
1955 | NOC284 | NOC | NA |  | OSS | OSS | OSS | Field Passive Infra | Field Passive Infra :: Package Wise District Level Visibility Status Daily |  | Critical | COMPLETED | NNMI | NNMI | 09-09-2025: live status will be available | [12 empty] | Applications/Tools | OPEN | 09-09-2025: live status will be available | Completed With Artifacts | TRUE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1956 | NOC285 | NOC | NA |  | OSS | OSS | OSS | Field Passive Infra | Field Passive Infra :: Package Wise District Level Visibility Status Weekly |  | Critical | NOT_FEASIBLE | NNMI | NNMI | [13 empty] | Applications/Tools | OPEN | 0 | Not-Feasible | TRUE | [7 empty] | Open | Open | Open
1957 | NOC286 | NOC | NA |  | OSS | OSS | OSS | Field Passive Infra | Field Passive Infra :: Package Wise District Level Visibility Status Monthly |  | Critical | NOT_FEASIBLE | NNMI | NNMI | [13 empty] | Applications/Tools | OPEN | 0 | Not-Feasible | TRUE | [7 empty] | Open | Open | Open
1958 | NOC287 | NOC | NA |  | OSS | OSS | OSS | Field Passive Infra | Field Passive Infra :: Package Wise District Level Visibility Status (Selective from and to dates) |  | Critical | NOT_FEASIBLE | NNMI | NNMI | [13 empty] | Applications/Tools | OPEN | avaiable in NNMI , assign to someone from oSSteam | Not-Feasible | FALSE | [7 empty] | Open | Open | Open
1959 | NOC288 | NOC | NA |  | OSS | OSS | OSS | Field Passive Infra | NNMI :: Integration Status with Reachability Daily |  | Critical | COMPLETED | NNMI | NNMI | [13 empty] | Applications/Tools | OPEN | 0 | Completed With Artifacts | TRUE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1960 | NOC289 | NOC | NA |  | OSS | OSS | OSS | Field Passive Infra | NNMI :: Integration Status with Reachability Weekly |  | Critical | COMPLETED | NNMI | NNMI | [13 empty] | Applications/Tools | OPEN | 0 | Completed With Artifacts | TRUE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1961 | NOC29 | NOC | NA |  | OSS | OSS | OSS | Service Monitoring | Monitoring,tracking service details, Tracking of GI services uptime Service assurance dashboard (Selective from and to dates) |  | Critical | OPEN | HPSM | Incident Management | OPEN-DEPENDENT | [12 empty] | Applications/Tools | OPEN |  | Open-Dependent | FALSE | [7 empty] | Open | Open | Open
1962 | NOC290 | NOC | NA |  | OSS | OSS | OSS | Field Passive Infra | NNMI :: Integration Status with Reachability Monthly |  | Critical | COMPLETED | NNMI | NNMI | [13 empty] | Applications/Tools | OPEN | 0 | Completed With Artifacts | TRUE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1963 | NOC291 | NOC | NA |  | OSS | OSS | OSS | Field Passive Infra | NNMI :: Integration Status with Reachability (Selective from and to dates) |  | Critical | COMPLETED | NNMI | NNMI | [13 empty] | Applications/Tools | OPEN | 0 | Completed With Artifacts | TRUE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1964 | NOC292 | NOC | NA |  | OSS | OSS | OSS | Field Passive Infra | PKG -A :: Open TTs for O&M GP for UPS Daily |  | Critical | COMPLETED | HPSM | Incident Management | [13 empty] | Applications/Tools | OPEN | 0 | Completed With Artifacts | TRUE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1965 | NOC293 | NOC | NA |  | OSS | OSS | OSS | Field Passive Infra | PKG -A :: Open TTs for O&M GP for UPS Weekly |  | Critical | COMPLETED | HPSM | Incident Management | [13 empty] | Applications/Tools | OPEN | 0 | Completed With Artifacts | TRUE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1966 | NOC294 | NOC | NA |  | OSS | OSS | OSS | Field Passive Infra | PKG -A :: Open TTs for O&M GP for UPS Monthly |  | Critical | COMPLETED | HPSM | Incident Management | [13 empty] | Applications/Tools | OPEN | 0 | Completed With Artifacts | TRUE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1967 | NOC295 | NOC | NA |  | OSS | OSS | OSS | Field Passive Infra | PKG -A :: Open TTs for O&M GP for UPS (Selective from and to dates) |  | Critical | COMPLETED | HPSM | Incident Management | [13 empty] | Applications/Tools | OPEN | 0 | Completed With Artifacts | TRUE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1968 | NOC296 | NOC | NA |  | OSS | OSS | OSS | Field Passive Infra | PKG -B :: Open TTs for O&M GP for UPS Daily |  | Critical | COMPLETED | HPSM | Incident Management | [13 empty] | Applications/Tools | OPEN | 0 | Completed With Artifacts | TRUE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1969 | NOC297 | NOC | NA |  | OSS | OSS | OSS | Field Passive Infra | PKG -B :: Open TTs for O&M GP for UPS Weekly |  | Critical | COMPLETED | HPSM | Incident Management | [13 empty] | Applications/Tools | OPEN | 0 | Completed With Artifacts | TRUE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1970 | NOC298 | NOC | NA |  | OSS | OSS | OSS | Field Passive Infra | PKG -B :: Open TTs for O&M GP for UPS Monthly |  | Critical | COMPLETED | HPSM | Incident Management | [13 empty] | Applications/Tools | OPEN | 0 | Completed With Artifacts | TRUE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1971 | NOC299 | NOC | NA |  | OSS | OSS | OSS | Field Passive Infra | PKG -B :: Open TTs for O&M GP for UPS (Selective from and to dates) |  | Critical | COMPLETED | HPSM | Incident Management | [13 empty] | Applications/Tools | OPEN | 0 | Completed With Artifacts | TRUE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1972 | NOC3 | NOC | NA |  | OSS | OSS | OSS | DC | DC Active Infra uptime & SLA Monthly |  | Critical |  | HPSM | Incident Management | [13 empty] | Applications/Tools | OPEN | 0 | OPEN | TRUE | [7 empty] | Open | Open | Open
1973 | NOC30 | NOC | NA |  |  |  | Helpdesk | OSS | Service Delivery & Service Assurance Dash Board Daily |  | Critical | COMPLETED | HPSM | Incident Management | 11-09-2025: BSS will display all delivery data as well as service ticket informations in the CRM portal. OSS will maintain only technical information. | [12 empty] | Applications/Tools | OPEN | 11-09-2025: BSS will display all delivery data as well as service ticket informations in the CRM portal. OSS will maintain only technical information. | Completed With Artifacts | TRUE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1974 | NOC300 | NOC | NA |  | OSS | OSS | OSS | Field Passive Infra | PKG -C :: Open TTs for O&M GP for UPS Daily |  | Critical | COMPLETED | HPSM | Incident Management | [13 empty] | Applications/Tools | OPEN | 0 | Completed With Artifacts | TRUE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1975 | NOC301 | NOC | NA |  | OSS | OSS | OSS | Field Passive Infra | PKG -C :: Open TTs for O&M GP for UPS Weekly |  | Critical | COMPLETED | HPSM | Incident Management | [13 empty] | Applications/Tools | OPEN | 0 | Completed With Artifacts | TRUE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1976 | NOC302 | NOC | NA |  | OSS | OSS | OSS | Field Passive Infra | PKG -C :: Open TTs for O&M GP for UPS Monthly |  | Critical | COMPLETED | HPSM | Incident Management | [13 empty] | Applications/Tools | OPEN | 0 | Completed With Artifacts | TRUE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1977 | NOC303 | NOC | NA |  | OSS | OSS | OSS | Field Passive Infra | PKG -C :: Open TTs for O&M GP for UPS (Selective from and to dates) |  | Critical | COMPLETED | HPSM | Incident Management | [13 empty] | Applications/Tools | OPEN | 0 | Completed With Artifacts | TRUE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1978 | NOC304 | NOC | NA |  | OSS | OSS | OSS | Field Passive Infra | SNMP issues _ Report Daily |  | Critical | COMPLETED | NNMI | NNMI | 09-09-2025: Live status will be available | [12 empty] | Applications/Tools | OPEN | 09-09-2025: Live status will be available | Completed With Artifacts | TRUE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1979 | NOC305 | NOC | NA |  | OSS | OSS | OSS | Field Passive Infra | SNMP issues _ Report Weekly |  | Critical | NOT_FEASIBLE | NNMI | NNMI | [13 empty] | Applications/Tools |  | 0 | Completed With Artifacts | TRUE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1980 | NOC306 | NOC | NA |  | OSS | OSS | OSS | Field Passive Infra | SNMP issues _ Report Monthly |  | Critical | NOT_FEASIBLE | NNMI | NNMI | [13 empty] | Applications/Tools |  | 0 | Completed With Artifacts | TRUE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1981 | NOC307 | NOC | NA |  | OSS | OSS | OSS | Field Passive Infra | SNMP issues _ Report (Selective from and to dates) |  | Critical | NOT_FEASIBLE | NNMI | NNMI | [13 empty] | Applications/Tools |  | 0 | Completed With Artifacts | TRUE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1982 | NOC308 | NOC | NA |  | OSS | OSS | OSS | Field Passive Infra | Mandal EB & Zonal DG Running report Daily |  | Critical | OPEN | HPSM | Incident Management | [13 empty] | Applications/Tools | OPEN | 0 | Not-Feasible | TRUE | [7 empty] | Open | Open | Open
1983 | NOC309 | NOC | NA |  | OSS | OSS | OSS | Field Passive Infra | Mandal EB & Zonal DG Running report Weekly |  | Critical | OPEN | HPSM | Incident Management | [13 empty] | Applications/Tools | OPEN | 0 | Not-Feasible | TRUE | [7 empty] | Open | Open | Open
1984 | NOC31 | NOC | NA |  |  |  | Helpdesk | OSS | Service Delivery & Service Assurance Dash Board Weekly |  | Critical | COMPLETED | HPSM | Incident Management | 11-09-2025: BSS will display all delivery data as well as service ticket informations in the CRM portal. OSS will maintain only technical information. | [12 empty] | Applications/Tools | OPEN | we have only live data | Completed With Artifacts | FALSE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1985 | NOC310 | NOC | NA |  | OSS | OSS | OSS | Field Passive Infra | Mandal EB & Zonal DG Running report Monthly |  | Critical | OPEN | HPSM | Incident Management | [13 empty] | Applications/Tools | OPEN | 0 | Not-Feasible | TRUE | [7 empty] | Open | Open | Open
1986 | NOC311 | NOC | NA |  | OSS | OSS | OSS | Field Passive Infra | Mandal EB & Zonal DG Running report (Selective from and to dates) |  | Critical | OPEN | HPSM | Incident Management | [13 empty] | Applications/Tools | OPEN | 0 | Not-Feasible | TRUE | [7 empty] | Open | Open | Open
1987 | NOC312 | NOC | NA |  | OSS | OSS | OSS | Field Passive Infra | DG Running status NNMi Logs Daily |  | Critical | COMPLETED | NNMI | NNMI | [13 empty] | Applications/Tools | Closed | 0 | Completed With Artifacts | TRUE | [5 empty] | 2025-11-18 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\OSS\52 Artefcats_18112025 | Closed after 14-Nov-25 | Closed after 14-Nov-25 | Completed but Verification undrer Process
1988 | NOC313 | NOC | NA |  | OSS | OSS | OSS | Field Passive Infra | DG Running status NNMi Logs Weekly |  | Critical | COMPLETED | NNMI | NNMI | [13 empty] | Applications/Tools | OPEN | 0 | Completed With Artifacts | TRUE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1989 | NOC314 | NOC | NA |  | OSS | OSS | OSS | Field Passive Infra | DG Running status NNMi Logs Monthly |  | Critical | COMPLETED | NNMI | NNMI | [13 empty] | Applications/Tools | Closed | 0 | Completed With Artifacts | TRUE | [5 empty] | 2025-11-18 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\OSS\52 Artefcats_18112025 | Closed after 14-Nov-25 | Closed after 14-Nov-25 | Completed but Verification undrer Process
1990 | NOC315 | NOC | NA |  | OSS | OSS | OSS | Field Passive Infra | DG Running status NNMi Logs (Selective from and to dates) |  | Critical | COMPLETED | NNMI | NNMI | [13 empty] | Applications/Tools | OPEN | 0 | Completed With Artifacts | TRUE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1991 | NOC316 | NOC | NA |  | OSS | OSS | OSS | Service Monitoring | Customised Dashboard as per Department/Service/Locations, etc.. Daily |  | Critical | COMPLETED | HPSM | Incident Management | 09-09-2025: Only Availability | [12 empty] | Applications/Tools | OPEN | 09-09-2025: Only Availability | Completed With Artifacts | TRUE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1992 | NOC317 | NOC | NA |  | OSS | OSS | OSS | Service Monitoring | Customised Dashboard as per Department/Service/Locations, etc..Weekly |  | Critical | NOT_FEASIBLE | HPSM | Incident Management | [13 empty] | Applications/Tools | OPEN | 0 | Not-Feasible | TRUE | [7 empty] | Open | Open | Open
1993 | NOC318 | NOC | NA |  | OSS | OSS | OSS | Service Monitoring | Customised Dashboard as per Department/Service/Locations, etc..Monthly |  | Critical | NOT_FEASIBLE | HPSM | Incident Management | [13 empty] | Applications/Tools | OPEN | 0 | Not-Feasible | TRUE | [7 empty] | Open | Open | Open
1994 | NOC319 | NOC | NA |  | OSS | OSS | OSS | Service Monitoring | Customised Dashboard as per Department/Service/Locations, etc..Selective Dates |  | Critical | NOT_FEASIBLE | HPSM | Incident Management | [13 empty] | Applications/Tools | OPEN | 0 | Not-Feasible | TRUE | [7 empty] | Open | Open | Open
1995 | NOC32 | NOC | NA |  |  |  | Helpdesk | OSS | Service Delivery & Service Assurance Dash Board Monthly |  | Critical | COMPLETED | HPSM | Incident Management | 11-09-2025: BSS will display all delivery data as well as service ticket informations in the CRM portal. OSS will maintain only technical information. | [12 empty] | Applications/Tools | OPEN | we have only live data | Completed With Artifacts | FALSE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1996 | NOC320 | NOC | NA |  | OSS | OSS | OSS | Service Monitoring | T-NOC Report :: GI Sites SD SA Report Daily |  | Critical | COMPLETED | HPSM | Incident Management | 09-09-2025: SD report to be collected from BSS. Ticketing & utilization report is available in OSS. | [12 empty] | Applications/Tools | OPEN | 09-09-2025: SD report to be collected from BSS. Ticketing & utilization report is available in OSS. | Completed With Artifacts | TRUE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1997 | NOC321 | NOC | NA |  | OSS | OSS | OSS | Service Monitoring | T-NOC Report :: GI Sites SD SA Report Weekly |  | Critical | NOT_FEASIBLE | HPSM | Incident Management | [13 empty] | Applications/Tools |  | 0 | Completed With Artifacts | TRUE | [7 empty] | Open | Open | Open
1998 | NOC322 | NOC | NA |  | OSS | OSS | OSS | Service Monitoring | T-NOC Report :: GI Sites SD SA Report Monthly |  | Critical | COMPLETED | HPSM | Incident Management | 09-09-2025: SD report to be collected from BSS. Ticketing & utilization report is available in OSS. | [12 empty] | Applications/Tools | OPEN | 09-09-2025: SD report to be collected from BSS. Ticketing & utilization report is available in OSS. | Completed With Artifacts | TRUE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
1999 | NOC323 | NOC | NA |  | OSS | OSS | OSS | Service Monitoring | T-NOC Report :: GI Sites SD SA Report (Selective from and to dates) |  | Critical | COMPLETED | HPSM | Incident Management | 09-09-2025: SD report to be collected from BSS. Ticketing & utilization report is available in OSS. | [12 empty] | Applications/Tools | OPEN | 09-09-2025: SD report to be collected from BSS. Ticketing & utilization report is available in OSS. | Completed With Artifacts | TRUE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
2000 | NOC324 | NOC | NA |  | OSS | OSS | OSS | Service Monitoring | List of GI with bandwidth Utilization Details Daily |  | Critical | COMPLETED | OSS Dashboards | PMS(UOC) | [13 empty] | Applications/Tools | Closed | 0 | Completed With Artifacts | TRUE | [5 empty] | 2025-11-18 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\OSS\52 Artefcats_18112025 | Closed after 14-Nov-25 | Closed after 14-Nov-25 | Completed but Verification undrer Process
2001 | NOC325 | NOC | NA |  | OSS | OSS | OSS | Service Monitoring | List of GI with bandwidth Utilization Details Weekly |  | Critical | NOT_FEASIBLE | OSS Dashboards | PMS(UOC) | [13 empty] | Applications/Tools | OPEN | 0 | Not-Feasible | TRUE | [7 empty] | Open | Open | Open
2002 | NOC326 | NOC | NA |  | OSS | OSS | OSS | Service Monitoring | List of GI with bandwidth Utilization Details Monthly |  | Critical | COMPLETED | OSS Dashboards | PMS(UOC) | [13 empty] | Applications/Tools | Closed | 0 | Completed With Artifacts | TRUE | [5 empty] | 2025-11-18 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\OSS\52 Artefcats_18112025 | Closed after 14-Nov-25 | Closed after 14-Nov-25 | Completed but Verification undrer Process
2003 | NOC327 | NOC | NA |  | OSS | OSS | OSS | Service Monitoring | List of GI with bandwidth Utilization Details (Selective from and to dates) |  | Critical | NOT_FEASIBLE | OSS Dashboards | PMS(UOC) | [13 empty] | Applications/Tools | OPEN | 0 | Not-Feasible | TRUE | [7 empty] | Open | Open | Open
2004 | NOC328 | NOC | NA |  | OSS | OSS | OSS | Service Monitoring | T-NOC :: Status Summary of Bandwidth Utilization & Non Utilization of WIFI Routers in GB & ONTs Status Daily |  | Critical | COMPLETED | OSS Dashboards | PMS(UOC) | [13 empty] | Applications/Tools | OPEN | ont bw | Completed With Artifacts | FALSE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
2005 | NOC329 | NOC | NA |  | OSS | OSS | OSS | Service Monitoring | T-NOC :: Status Summary of Bandwidth Utilization & Non Utilization of WIFI Routers in GB & ONTs Status Weekly |  | Critical | NOT_FEASIBLE | OSS Dashboards | PMS(UOC) | [13 empty] | Applications/Tools | OPEN | 0 | Not-Feasible | TRUE | [7 empty] | Open | Open | Open
2006 | NOC33 | NOC | NA |  |  |  | Helpdesk | OSS | Service Delivery & Service Assurance Dash Board (Selective from and to dates) |  | Critical | COMPLETED | HPSM | Incident Management | 11-09-2025: BSS will display all delivery data as well as service ticket informations in the CRM portal. OSS will maintain only technical information. | [12 empty] | Applications/Tools | OPEN | we have only live data | Completed With Artifacts | FALSE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
2007 | NOC330 | NOC | NA |  | OSS | OSS | OSS | Service Monitoring | T-NOC :: Status Summary of Bandwidth Utilization & Non Utilization of WIFI Routers in GB & ONTs Status Monthly |  | Critical | COMPLETED | OSS Dashboards | PMS(UOC) | [13 empty] | Applications/Tools | OPEN | 0 | Completed With Artifacts | TRUE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
2008 | NOC331 | NOC | NA |  | OSS | OSS | OSS | Service Monitoring | T-NOC :: Status Summary of Bandwidth Utilization & Non Utilization of WIFI Routers in GB & ONTs Status (Selective from and to dates) |  | Critical | NOT_FEASIBLE | OSS Dashboards | PMS(UOC) | [13 empty] | Applications/Tools | OPEN | 0 | Not-Feasible | TRUE | [7 empty] | Open | Open | Open
2009 | NOC332 | NOC | NA |  | OSS | OSS | New BSS | Service Monitoring | Request for FTTH Connection Details Sheet for T-Fiber Daily |  | Critical | OPEN | OSS Dashboards | PMS(UOC) | Not Relevent to OSS, It should come from BSS | [12 empty] | #N/A | OPEN |  | Not Relevant To OSS | FALSE | [7 empty] | Open | Open | Open
2010 | NOC333 | NOC | NA |  | OSS | OSS | New BSS | Service Monitoring | Request for FTTH Connection Details Sheet for T-Fiber Weekly |  | Critical | OPEN | OSS Dashboards | PMS(UOC) | Not Relevent to OSS, It should come from BSS | [12 empty] | #N/A | OPEN |  | Not Relevant To OSS | FALSE | [7 empty] | Open | Open | Open
2011 | NOC334 | NOC | NA |  | OSS | OSS | New BSS | Service Monitoring | Request for FTTH Connection Details Sheet for T-Fiber Monthly |  | Critical | OPEN | OSS Dashboards | PMS(UOC) | Not Relevent to OSS, It should come from BSS | [12 empty] | #N/A | OPEN |  | Not Relevant To OSS | FALSE | [7 empty] | Open | Open | Open
2012 | NOC335 | NOC | NA |  | OSS | OSS | New BSS | Service Monitoring | Request for FTTH Connection Details Sheet for T-Fiber (Selective from and to dates) |  | Critical | OPEN | OSS Dashboards | PMS(UOC) | Not Relevent to OSS, It should come from BSS | [12 empty] | #N/A | OPEN |  | Not Relevant To OSS | FALSE | [7 empty] | Open | Open | Open
2013 | NOC336 | NOC | NA |  | OSS | OSS | New BSS | Service Monitoring | Service Delivery & Service Assurance Dash Board (Signed Forms) Daily |  | Critical | OPEN | HPSM | Incident Management | Aditional Scope for OT/HPE | [12 empty] | #N/A | OPEN |  | Not Relevant To OSS | FALSE | [7 empty] | Open | Open | Open
2014 | NOC337 | NOC | NA |  | OSS | OSS | New BSS | Service Monitoring | Service Delivery & Service Assurance Dash Board (Signed Forms) Weekly |  | Critical | OPEN | HPSM | Incident Management | Aditional Scope for OT/HPE | [12 empty] | #N/A | OPEN |  | Not Relevant To OSS | FALSE | [7 empty] | Open | Open | Open
2015 | NOC338 | NOC | NA |  | OSS | OSS | New BSS | Service Monitoring | Service Delivery & Service Assurance Dash Board (Signed Forms) Monthly |  | Critical | OPEN | HPSM | Incident Management | Aditional Scope for OT/HPE | [12 empty] | #N/A | OPEN |  | Not Relevant To OSS | FALSE | [7 empty] | Open | Open | Open
2016 | NOC339 | NOC | NA |  | OSS | OSS | New BSS | Service Monitoring | Service Delivery & Service Assurance Dash Board (Signed Forms) (Selective from and to dates) |  | Critical | OPEN | HPSM | Incident Management | Aditional Scope for OT/HPE | [12 empty] | #N/A | OPEN |  | Not Relevant To OSS | FALSE | [7 empty] | Open | Open | Open
2017 | NOC34 | NOC | NA |  |  |  | Helpdesk | OSS | Incident Reporting and Field Assignment(Any failure/incident on any part of the network infrastructure or its facilities shall be communicated immediately to Helpdesk by Network Monitoring team/ field representative / end user giving details of the incident/fault/problem.) Daily |  | Critical |  | HPSM | Incident Management | 09-09-2025: Integration with WFM is in place to give live trigger to FE and SMS/email integration also in place to give notification to configured escallation matrix | [12 empty] | Applications/Tools | OPEN | 09-09-2025: Integration with WFM is in place to give live trigger to FE and SMS/email integration also in place to give notification to configured escallation matrix | Not-Feasible | TRUE | [7 empty] | Open | Open | Open
2018 | NOC340 | NOC | NA |  | OSS | OSS | All Domain | OSS | PE Mapping with MTTR report Daily |  | Critical | OPEN | HPSM | Incident Management | [13 empty] | Applications/Tools | OPEN | 0 | WIP | TRUE | [7 empty] | Open | Open | Open
2019 | NOC341 | NOC | NA |  | OSS | OSS | All Domain | OSS | PE Mapping with MTTR report Weekly |  | Critical | OPEN | HPSM | Incident Management | [13 empty] | Applications/Tools | OPEN | 0 | WIP | TRUE | [7 empty] | Open | Open | Open
2020 | NOC342 | NOC | NA |  | OSS | OSS | All Domain | OSS | PE Mapping with MTTR report Monthly |  | Critical | OPEN | HPSM | Incident Management | [13 empty] | Applications/Tools | OPEN | 0 | WIP | TRUE | [7 empty] | Open | Open | Open
2021 | NOC343 | NOC | NA |  | OSS | OSS | All Domain | OSS | PE Mapping with MTTR report (Selective from and to dates) |  | Critical | NOT_FEASIBLE | HPSM | Incident Management | [13 empty] | Applications/Tools |  | 0 | Completed | TRUE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
2022 | NOC344 | NOC | NA |  |  |  | BSS | Service Delivery | GI GP Wifi HH Delivery Status Daily |  | Critical | OPEN | BSS | CRM | [13 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2023 | NOC345 | NOC | NA |  |  |  | BSS | Service Delivery | GI GP Wifi HH Delivery Status Weekly |  | Critical | OPEN | BSS | CRM | [13 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2024 | NOC346 | NOC | NA |  |  |  | BSS | Service Delivery | GI GP Wifi HH Delivery Status Monthly |  | Critical | OPEN | BSS | CRM | [13 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2025 | NOC347 | NOC | NA |  |  |  | BSS | Service Delivery | GI GP Wifi HH Delivery Status (Selective from and to dates) |  | Critical | OPEN | BSS | CRM | [13 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2026 | NOC348 | NOC | NA |  |  |  | BSS | Service Delivery | Service IDs for all GI Locatinos Daily |  | Critical | OPEN | BSS | CRM | [13 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2027 | NOC349 | NOC | NA |  |  |  | BSS | Service Delivery | Service IDs for all GI Locatinos Weekly |  | Critical | OPEN | BSS | CRM | [13 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2028 | NOC35 | NOC | NA |  |  |  | Helpdesk | OSS | Incident Reporting and Field Assignment(Any failure/incident on any part of the network infrastructure or its facilities shall be communicated immediately to Helpdesk by Network Monitoring team/ field representative / end user giving details of the incident/fault/problem.) Weekly |  | Critical |  | HPSM | Incident Management | [13 empty] | Applications/Tools | Closed | 0 | Completed With Artifacts | TRUE | [5 empty] | 2025-11-18 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\OSS\52 Artefcats_18112025 | Closed after 14-Nov-25 | Closed after 14-Nov-25 | Completed but Verification undrer Process
2029 | NOC350 | NOC | NA |  |  |  | BSS | Service Delivery | Service IDs for all GI Locatinos Monthly |  | Critical | OPEN | BSS | CRM | [13 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2030 | NOC351 | NOC | NA |  |  |  | BSS | Service Delivery | Service IDs for all GI Locatinos (Selective from and to dates) |  | Critical | OPEN | BSS | CRM | [13 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2031 | NOC352 | NOC | NA |  |  |  | BSS | Service Delivery | Household Delivery Status Report Daily |  | Critical | OPEN | BSS | CRM | [13 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2032 | NOC353 | NOC | NA |  |  |  | BSS | Service Delivery | Household Delivery Status Report Weekly |  | Critical | OPEN | BSS | CRM | [13 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2033 | NOC354 | NOC | NA |  |  |  | BSS | Service Delivery | Household Delivery Status Report Monthly |  | Critical | OPEN | BSS | CRM | [13 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2034 | NOC355 | NOC | NA |  |  |  | BSS | Service Delivery | Household Delivery Status Report (Selective from and to dates) |  | Critical | OPEN | BSS | CRM | [13 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2035 | NOC356 | NOC | NA |  | OSS | OSS | All Domain | OSS | Alarm seviority(Critical/major/Minor)(Domain wise Filter) Daily |  | Critical | COMPLETED | OSS Dashboards | VTemip | [13 empty] | Applications/Tools | Closed | 0 | Completed With Artifacts | TRUE | [5 empty] | 2025-11-18 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\OSS\52 Artefcats_18112025 | Closed after 14-Nov-25 | Closed after 14-Nov-25 | Completed but Verification undrer Process
2036 | NOC357 | NOC | NA |  | OSS | OSS | All Domain | OSS | Alarm seviority(Critical/major/Minor)(Domain wise Filter) Weekly |  | Critical | COMPLETED | OSS Dashboards | VTemip | [13 empty] | Applications/Tools | Closed | 0 | Completed With Artifacts | TRUE | [5 empty] | 2025-11-18 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\OSS\52 Artefcats_18112025 | Closed after 14-Nov-25 | Closed after 14-Nov-25 | Completed but Verification undrer Process
2037 | NOC358 | NOC | NA |  | OSS | OSS | All Domain | OSS | Alarm seviority(Critical/major/Minor)(Domain wise Filter) Monthly |  | Critical | COMPLETED | OSS Dashboards | VTemip | [13 empty] | Applications/Tools | Closed | 0 | Completed With Artifacts | TRUE | [5 empty] | 2025-11-18 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\OSS\52 Artefcats_18112025 | Closed after 14-Nov-25 | Closed after 14-Nov-25 | Completed but Verification undrer Process
2038 | NOC359 | NOC | NA |  | OSS | OSS | All Domain | OSS | Alarm seviority(Critical/major/Minor)(Domain wise Filter) (Selective from and to dates) |  | Critical | COMPLETED | OSS Dashboards | VTemip | [13 empty] | Applications/Tools | Closed | 0 | Completed With Artifacts | TRUE | [5 empty] | 2025-11-18 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\OSS\52 Artefcats_18112025 | Closed after 14-Nov-25 | Closed after 14-Nov-25 | Completed but Verification undrer Process
2039 | NOC36 | NOC | NA |  |  |  | Helpdesk | OSS | Incident Reporting and Field Assignment(Any failure/incident on any part of the network infrastructure or its facilities shall be communicated immediately to Helpdesk by Network Monitoring team/ field representative / end user giving details of the incident/fault/problem.) Monthly |  | Critical |  | HPSM | Incident Management | 09-09-2025: Integration with WFM is in place to give live trigger to FE and SMS/email integration also in place to give notification to configured escallation matrix | [12 empty] | Applications/Tools | OPEN | 09-09-2025: Integration with WFM is in place to give live trigger to FE and SMS/email integration also in place to give notification to configured escallation matrix | Not-Feasible | TRUE | [7 empty] | Open | Open | Open
2040 | NOC360 | NOC | NA |  | OSS | OSS | All Domain | OSS | Inventory Dashboard and Report(Domain wise Filter) Daily |  | Critical | COMPLETED | OSS Dashboards | UTM | [13 empty] | Applications/Tools | OPEN | 0 | Completed With Artifacts | TRUE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
2041 | NOC361 | NOC | NA |  | OSS | OSS | All Domain | OSS | Inventory Dashboard and Report(Domain wise Filter) Weekly |  | Critical | NOT_FEASIBLE | OSS Dashboards | UTM | [13 empty] | Applications/Tools | OPEN | 0 | Not-Feasible | TRUE | [7 empty] | Open | Open | Open
2042 | NOC362 | NOC | NA |  | OSS | OSS | All Domain | OSS | Inventory Dashboard and Report(Domain wise Filter) Monthly |  | Critical | NOT_FEASIBLE | OSS Dashboards | UTM | [13 empty] | Applications/Tools | OPEN | 0 | Not-Feasible | TRUE | [7 empty] | Open | Open | Open
2043 | NOC363 | NOC | NA |  | OSS | OSS | All Domain | OSS | Inventory Dashboard and Report(Domain wise Filter) (Selective from and to dates) |  | Critical | NOT_FEASIBLE | OSS Dashboards | UTM | [13 empty] | Applications/Tools | OPEN | 0 | Not-Feasible | TRUE | [7 empty] | Open | Open | Open
2044 | NOC364 | NOC | NA |  | OSS | OSS | All Domain | OSS | Correlation within Domain and cross domain Daily |  | Critical |  | OSS Dashboards | UCA | 16-Oct-25: Report can not be generated for this but we can realize it's implementation by seeing reduction in TT count | [12 empty] | Applications/Tools | OPEN | Report can not be generated for this but we can realize it's implementation by seeing reduction in TT count | OPEN | FALSE | [7 empty] | Open | Open | Open
2045 | NOC365 | NOC | NA |  | OSS | OSS | All Domain | OSS | Correlation within Domain and cross domain Weekly |  | Critical | DUPLICATE POINT | OSS Dashboards | UCA | 16-Oct-25: Report can not be generated for this but we can realize it's implementation by seeing reduction in TT count | [12 empty] | Applications/Tools | OPEN | Report can not be generated for this but we can realize it's implementation by seeing reduction in TT count | OPEN | FALSE | [7 empty] | Open | Open | Open
2046 | NOC366 | NOC | NA |  | OSS | OSS | All Domain | OSS | Correlation within Domain and cross domain Monthly |  | Critical |  | OSS Dashboards | UCA | 16-Oct-25: Report can not be generated for this but we can realize it's implementation by seeing reduction in TT count | [12 empty] | Applications/Tools | OPEN | Report can not be generated for this but we can realize it's implementation by seeing reduction in TT count | OPEN | FALSE | [7 empty] | Open | Open | Open
2047 | NOC367 | NOC | NA |  | OSS | OSS | All Domain | OSS | Correlation within Domain and cross domain (Selective from and to dates) |  | Critical |  | OSS Dashboards | UCA | 16-Oct-25: Report can not be generated for this but we can realize it's implementation by seeing reduction in TT count | [12 empty] | Applications/Tools | OPEN | Report can not be generated for this but we can realize it's implementation by seeing reduction in TT count | OPEN | FALSE | [7 empty] | Open | Open | Open
2048 | NOC368 | NOC | NA |  | OSS | OSS | OSS | DC IT Active Infra | Service Monitoring of All DC Elements(DC WAN, Leaf, Spine and Service riding on these Network and Servers) Daily |  | Critical |  | HPSM | Incident Management | [13 empty] | Applications/Tools | OPEN | 0 | OPEN | TRUE | [7 empty] | Open | Open | Open
2049 | NOC369 | NOC | NA |  | OSS | OSS | OSS | DC IT Active Infra | Service Monitoring of All DC Elements(DC WAN, Leaf, Spine and Service riding on these Network and Servers) Weekly |  | Critical |  | HPSM | Incident Management | [13 empty] | Applications/Tools | OPEN | 0 | OPEN | TRUE | [7 empty] | Open | Open | Open
2050 | NOC37 | NOC | NA |  |  |  | Helpdesk | OSS | Incident Reporting and Field Assignment(Any failure/incident on any part of the network infrastructure or its facilities shall be communicated immediately to Helpdesk by Network Monitoring team/ field representative / end user giving details of the incident/fault/problem.) (Selective from and to dates) |  | Critical |  | HPSM | Incident Management | 09-09-2025: Integration with WFM is in place to give live trigger to FE and SMS/email integration also in place to give notification to configured escallation matrix | [12 empty] | Applications/Tools | OPEN | 09-09-2025: Integration with WFM is in place to give live trigger to FE and SMS/email integration also in place to give notification to configured escallation matrix | Not-Feasible | TRUE | [7 empty] | Open | Open | Open
2051 | NOC370 | NOC | NA |  | OSS | OSS | OSS | DC IT Active Infra | Service Monitoring of All DC Elements(DC WAN, Leaf, Spine and Service riding on these Network and Servers) Monthly |  | Critical |  | HPSM | Incident Management | [13 empty] | Applications/Tools | OPEN | 0 | OPEN | TRUE | [7 empty] | Open | Open | Open
2052 | NOC371 | NOC | NA |  | OSS | OSS | OSS | DC IT Active Infra | Service Monitoring of All DC Elements(DC WAN, Leaf, Spine and Service riding on these Network and Servers) (Selective from and to dates) |  | Critical |  | HPSM | Incident Management | [13 empty] | Applications/Tools | OPEN | 0 | OPEN | TRUE | [7 empty] | Open | Open | Open
2053 | NOC372 | NOC | NA |  | OSS | OSS | All Domain | OSS | Interface Utilisation(>80%) Hourly |  | Critical | COMPLETED | NNMI | NPS | 09-09-2025: Threshold limits needs tobe enabled and on that threshold limit the alarms to be generated and that alarm should qualify for ticket generation as per requirement | [12 empty] | Applications/Tools | OPEN | 09-09-2025: Threshold limits needs tobe enabled and on that threshold limit the alarms to be generated and that alarm should qualify for ticket generation as per requirement-need to check with govind | Completed With Artifacts | FALSE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
2054 | NOC373 | NOC | NA |  | OSS | OSS | All Domain | OSS | Interface Utilisation(>80%) Daily |  | Critical | COMPLETED | NNMI | NPS | 09-09-2025: Threshold limits needs tobe enabled and on that threshold limit the alarms to be generated and that alarm should qualify for ticket generation as per requirement | [12 empty] | Applications/Tools | OPEN | 09-09-2025: Threshold limits needs tobe enabled and on that threshold limit the alarms to be generated and that alarm should qualify for ticket generation as per requirement | Completed With Artifacts | TRUE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
2055 | NOC374 | NOC | NA |  | OSS | OSS | All Domain | OSS | Interface Utilisation(>80%) Weekly |  | Critical | COMPLETED | NNMI | NPS | 09-09-2025: Threshold limits needs tobe enabled and on that threshold limit the alarms to be generated and that alarm should qualify for ticket generation as per requirement | [12 empty] | Applications/Tools | OPEN | 09-09-2025: Threshold limits needs tobe enabled and on that threshold limit the alarms to be generated and that alarm should qualify for ticket generation as per requirement | Completed With Artifacts | TRUE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
2056 | NOC375 | NOC | NA |  | OSS | OSS | All Domain | OSS | Interface Utilisation(>80%) Monthly |  | Critical | COMPLETED | NNMI | NPS | 09-09-2025: Threshold limits needs tobe enabled and on that threshold limit the alarms to be generated and that alarm should qualify for ticket generation as per requirement | [12 empty] | Applications/Tools | OPEN | 09-09-2025: Threshold limits needs tobe enabled and on that threshold limit the alarms to be generated and that alarm should qualify for ticket generation as per requirement | Completed With Artifacts | TRUE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
2057 | NOC376 | NOC | NA |  | OSS | OSS | All Domain | OSS | Interface Utilisation(% of Utilisation configurable) |  | Critical | COMPLETED | NNMI | NPS | 09-09-2025: Threshold limits needs tobe enabled and on that threshold limit the alarms to be generated and that alarm should qualify for ticket generation as per requirement | [12 empty] | Applications/Tools | OPEN | 09-09-2025: Threshold limits needs tobe enabled and on that threshold limit the alarms to be generated and that alarm should qualify for ticket generation as per requirement | Completed With Artifacts | TRUE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
2058 | NOC377 | NOC | NA |  | OSS | OSS | All Domain | OSS | Interface Utilisation(Polling Duration configurable) |  | Critical | COMPLETED | NNMI | NPS | 09-09-2025: Threshold limits needs tobe enabled and on that threshold limit the alarms to be generated and that alarm should qualify for ticket generation as per requirement | [12 empty] | Applications/Tools | OPEN | 09-09-2025: Threshold limits needs tobe enabled and on that threshold limit the alarms to be generated and that alarm should qualify for ticket generation as per requirement | Completed With Artifacts | TRUE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
2059 | NOC378 | NOC | NA |  | OSS | OSS | All Domain | OSS | Interface Utilisation(>80%) (Selective from and to dates) |  | Critical | COMPLETED | NNMI | NPS | 09-09-2025: Threshold limits needs tobe enabled and on that threshold limit the alarms to be generated and that alarm should qualify for ticket generation as per requirement | [12 empty] | Applications/Tools | OPEN | 09-09-2025: Threshold limits needs tobe enabled and on that threshold limit the alarms to be generated and that alarm should qualify for ticket generation as per requirement | Completed With Artifacts | TRUE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
2060 | NOC379 | NOC | NA |  | OSS | OSS | All Domain | OSS | CPU/RAM(>80%) Daily |  | Critical | COMPLETED | NNMI | NPS | 09-09-2025: Threshold limits needs tobe enabled and on that threshold limit the alarms to be generated and that alarm should qualify for ticket generation as per requirement | [12 empty] | Applications/Tools | OPEN | 09-09-2025: Threshold limits needs tobe enabled and on that threshold limit the alarms to be generated and that alarm should qualify for ticket generation as per requirement | Completed With Artifacts | TRUE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
2061 | NOC38 | NOC | NA |  |  |  | Helpdesk | Help Desk | Help Desk managing and publishing KPI like Total I/O call, answereed call withing time frame etc. Hourly |  | NON-Critical |  | Helpdesk | Dial center | 24-Sep-25: Option available to Choose Dates, daily, Weekly and Monthly But not Direct as Daily, Weekly, Monthly | [12 empty] | Applications/Tools | Closed | [8 empty] | 2025-09-24 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\NOC38,39,40,41,42 | Completed & Approved | Closed before june-2025 | Closed after June
2062 | NOC380 | NOC | NA |  | OSS | OSS | All Domain | OSS | CPU/RAM(>80%) Weekly |  | Critical | COMPLETED | NNMI | NPS | 09-09-2025: Threshold limits needs tobe enabled and on that threshold limit the alarms to be generated and that alarm should qualify for ticket generation as per requirement | [12 empty] | Applications/Tools | OPEN | 09-09-2025: Threshold limits needs tobe enabled and on that threshold limit the alarms to be generated and that alarm should qualify for ticket generation as per requirement | Completed With Artifacts | TRUE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
2063 | NOC381 | NOC | NA |  | OSS | OSS | All Domain | OSS | CPU/RAM(>80%) Monthly |  | Critical | COMPLETED | NNMI | NPS | 09-09-2025: Threshold limits needs tobe enabled and on that threshold limit the alarms to be generated and that alarm should qualify for ticket generation as per requirement | [12 empty] | Applications/Tools | OPEN | 09-09-2025: Threshold limits needs tobe enabled and on that threshold limit the alarms to be generated and that alarm should qualify for ticket generation as per requirement | Completed With Artifacts | TRUE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
2064 | NOC382 | NOC | NA |  | OSS | OSS | All Domain | OSS | CPU/RAM(% of Utilisation configurable) |  | Critical | COMPLETED | NNMI | NPS | 09-09-2025: Threshold limits needs tobe enabled and on that threshold limit the alarms to be generated and that alarm should qualify for ticket generation as per requirement | [12 empty] | Applications/Tools | OPEN | 09-09-2025: Threshold limits needs tobe enabled and on that threshold limit the alarms to be generated and that alarm should qualify for ticket generation as per requirement | Completed With Artifacts | TRUE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
2065 | NOC383 | NOC | NA |  | OSS | OSS | All Domain | OSS | CPU/RAM(Polling Duration configurable) |  | Critical | COMPLETED | NNMI | NPS | 09-09-2025: Threshold limits needs tobe enabled and on that threshold limit the alarms to be generated and that alarm should qualify for ticket generation as per requirement | [12 empty] | Applications/Tools | OPEN | 09-09-2025: Threshold limits needs tobe enabled and on that threshold limit the alarms to be generated and that alarm should qualify for ticket generation as per requirement | Completed With Artifacts | TRUE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
2066 | NOC384 | NOC | NA |  | OSS | OSS | All Domain | OSS | CPU/RAM(>80%) (Selective from and to dates) |  | Critical | COMPLETED | NNMI | NPS | 09-09-2025: Threshold limits needs tobe enabled and on that threshold limit the alarms to be generated and that alarm should qualify for ticket generation as per requirement | [12 empty] | Applications/Tools | OPEN | 09-09-2025: Threshold limits needs tobe enabled and on that threshold limit the alarms to be generated and that alarm should qualify for ticket generation as per requirement | Completed With Artifacts | TRUE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
2067 | NOC385 | NOC | NA |  | OSS | OSS | All Domain | OSS | Incident/Alarm Notifciation via SMS, E-mail and Call, Whatsapp as per escalation Matrix (Selective from and to dates) |  | Critical | COMPLETED | HPSM | Incident Management | 09-09-2025: SMS & EMAIL is integrated. Whatsapp & Call not feasible | [12 empty] | Applications/Tools | Closed | 09-09-2025: SMS & EMAIL is integrated. Whatsapp & Call not feasible-earlier it was present as there was no credit it was stopped | Completed With Artifacts | FALSE | [5 empty] | 2025-11-18 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\OSS\52 Artefcats_18112025 | Closed after 14-Nov-25 | Closed after 14-Nov-25 | Completed but Verification undrer Process
2068 | NOC386 | NOC | NA |  | OSS | OSS | All Domain | OSS | Node(POP) wise Availability Daily |  | Critical | COMPLETED | HPSM | Incident Management | [13 empty] | Applications/Tools | OPEN | 0 | Completed With Artifacts | TRUE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
2069 | NOC387 | NOC | NA |  | OSS | OSS | All Domain | OSS | Node(POP) wise Availability Weekly |  | Critical | NOT_FEASIBLE | HPSM | Incident Management | [13 empty] | Applications/Tools | OPEN | 0 | Not-Feasible | TRUE | [7 empty] | Open | Open | Open
2070 | NOC388 | NOC | NA |  | OSS | OSS | All Domain | OSS | Node(POP) wise Availability Monthly |  | Critical | COMPLETED | HPSM | Incident Management | [13 empty] | Applications/Tools | OPEN | 0 | Completed With Artifacts | TRUE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
2071 | NOC389 | NOC | NA |  | OSS | OSS | All Domain | OSS | Node(POP) wise Availability (Selective from and to dates) |  | Critical | NOT_FEASIBLE | HPSM | Incident Management | [13 empty] | Applications/Tools | OPEN | 0 | Not-Feasible | TRUE | [7 empty] | Open | Open | Open
2072 | NOC39 | NOC | NA |  |  |  | Helpdesk | Help Desk | Help Desk managing and publishing KPI like Total I/O call, answereed call withing time frame etc. Daily |  | NON-Critical |  | Helpdesk | Dial center | 24-Sep-25: Option available to Choose Dates, daily, Weekly and Monthly But not Direct as Daily, Weekly, Monthly | [12 empty] | Applications/Tools | Closed | [8 empty] | 2025-09-24 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\NOC38,39,40,41,42 | Completed & Approved | Closed before june-2025 | Closed after June
2073 | NOC390 | NOC | NA |  | OSS | OSS | All Domain | OSS | Equipment wise Availability Daily |  | Critical | COMPLETED | HPSM | Incident Management | [13 empty] | Applications/Tools | OPEN | 0 | Completed With Artifacts | TRUE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
2074 | NOC391 | NOC | NA |  | OSS | OSS | All Domain | OSS | Equipment wise Availability Weekly |  | Critical | NOT_FEASIBLE | HPSM | Incident Management | [13 empty] | Applications/Tools | OPEN | 0 | Not-Feasible | TRUE | [7 empty] | Open | Open | Open
2075 | NOC392 | NOC | NA |  | OSS | OSS | All Domain | OSS | Equipment wise Availability Monthly |  | Critical | COMPLETED | HPSM | Incident Management | [13 empty] | Applications/Tools | OPEN | for DWDN no monthly report inUOC | Completed With Artifacts | FALSE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
2076 | NOC393 | NOC | NA |  | OSS | OSS | All Domain | OSS | Equipment wise Availability (Selective from and to dates) |  | Critical | NOT_FEASIBLE | HPSM | Incident Management | [13 empty] | Applications/Tools | OPEN | 0 | Not-Feasible | TRUE | [7 empty] | Open | Open | Open
2077 | NOC394 | NOC | NA |  | OSS | OSS | All Domain | OSS | Link wise Uptime Daily |  | Critical | COMPLETED | HPSM | Incident Management | [13 empty] | Applications/Tools | Closed | 0 | Completed With Artifacts | TRUE | [5 empty] | 2025-11-18 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\OSS\52 Artefcats_18112025 | Closed after 14-Nov-25 | Closed after 14-Nov-25 | Completed but Verification undrer Process
2078 | NOC395 | NOC | NA |  | OSS | OSS | All Domain | OSS | Link wise Uptime Weekly |  | Critical | NOT_FEASIBLE | HPSM | Incident Management | [13 empty] | Applications/Tools | OPEN | 0 | Not-Feasible | TRUE | [7 empty] | Open | Open | Open
2079 | NOC396 | NOC | NA |  | OSS | OSS | All Domain | OSS | Link wise Uptime Monthly |  | Critical | COMPLETED | HPSM | Incident Management | [13 empty] | Applications/Tools | Closed | 0 | Completed With Artifacts | TRUE | [5 empty] | 2025-11-18 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\OSS\52 Artefcats_18112025 | Closed after 14-Nov-25 | Closed after 14-Nov-25 | Completed but Verification undrer Process
2080 | NOC397 | NOC | NA |  | OSS | OSS | All Domain | OSS | Link wise Uptime (Selective from and to dates) |  | Critical | NOT_FEASIBLE | HPSM | Incident Management | [13 empty] | Applications/Tools | OPEN | 0 | Not-Feasible | TRUE | [7 empty] | Open | Open | Open
2081 | NOC398 | NOC | NA |  | OSS | OSS | All Domain | OSS | Link wise MTTR Daily |  | Critical | OPEN | HPSM | Incident Management | [13 empty] | Applications/Tools | OPEN | 0 | Completed With Artifacts | TRUE | [7 empty] | Open | Open | Open
2082 | NOC399 | NOC | NA |  | OSS | OSS | All Domain | OSS | Link wise MTTR Weekly |  | Critical | OPEN | HPSM | Incident Management | [13 empty] | Applications/Tools | OPEN | 0 | Completed With Artifacts | TRUE | [7 empty] | Open | Open | Open
2083 | NOC4 | NOC | NA |  | OSS | OSS | OSS | DC | DC Active Infra uptime & SLA Custom(Selective from and to dates) |  | Critical |  | HPSM | Incident Management | [13 empty] | Applications/Tools | OPEN | 0 | Not-Feasible | TRUE | [7 empty] | Open | Open | Open
2084 | NOC40 | NOC | NA |  |  |  | Helpdesk | Help Desk | Help Desk managing and publishing KPI like Total I/O call, answereed call withing time frame etc. Weekly |  | NON-Critical |  | Helpdesk | Dial center | 24-Sep-25: Option available to Choose Dates, daily, Weekly and Monthly But not Direct as Daily, Weekly, Monthly | [12 empty] | Applications/Tools | Closed | [8 empty] | 2025-09-24 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\NOC38,39,40,41,42 | Completed & Approved | Closed before june-2025 | Closed after June
2085 | NOC400 | NOC | NA |  | OSS | OSS | All Domain | OSS | Link wise MTTR Monthly |  | Critical | OPEN | HPSM | Incident Management | [13 empty] | Applications/Tools | OPEN | 0 | Completed With Artifacts | TRUE | [7 empty] | Open | Open | Open
2086 | NOC401 | NOC | NA |  | OSS | OSS | All Domain | OSS | Link wise MTTR (Selective from and to dates) |  | Critical | NOT_FEASIBLE | HPSM | Incident Management | [13 empty] | Applications/Tools |  | 0 | Completed With Artifacts | TRUE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
2087 | NOC402 | NOC | NA |  | OSS | OSS | OSS | DC and Field IPMPLS | IPSLA Daily(Packet Drops, Latency, Jitter, ect..) |  | Critical | COMPLETED | NNMI | NPS | [13 empty] | Applications/Tools | OPEN | 0 | Completed With Artifacts | TRUE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
2088 | NOC403 | NOC | NA |  | OSS | OSS | OSS | DC and Field IPMPLS | IPSLA Weekly(Packet drops, latency, jitter, etc..) |  | Critical | COMPLETED | NNMI | NPS | [13 empty] | Applications/Tools | OPEN | Only Packet drops data is available , Latency and Jitter is not available. | Completed With Artifacts | FALSE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
2089 | NOC404 | NOC | NA |  | OSS | OSS | OSS | DC and Field IPMPLS | IPSLA Monthly (Packet drops, latency, jitter, etc..) |  | Critical | COMPLETED | NNMI | NPS | [13 empty] | Applications/Tools | OPEN | Only Packet drops data is available , Latency and Jitter is not available. | Completed With Artifacts | FALSE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
2090 | NOC405 | NOC | NA |  | OSS | OSS | OSS | DC and Field IPMPLS | IPSLA (Selective from and to dates)(Packet drops, latency, jitter, etc..) |  | Critical | COMPLETED | NNMI | NPS | [13 empty] | Applications/Tools | OPEN | Only Packet drops data is available , Latency and Jitter is not available. | Completed With Artifacts | FALSE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
2091 | NOC406 | NOC | NA |  | OSS | OSS | OSS | DC and Field IPMPLS | IPSLA (Packet drops to be configurable and existing >1% to be reported in Dashboard |  | Critical | COMPLETED | NNMI | NPS | [13 empty] | Applications/Tools | OPEN | To be checked | OPEN | FALSE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
2092 | NOC407 | NOC | NA |  | OSS | OSS | OSS | DC and Field IPMPLS | IPSLA (Latency to be configurable and existing >10ms to be reported in Dashboard |  | Critical | COMPLETED | NNMI | NPS | [13 empty] | Applications/Tools | OPEN | To be checked | OPEN | FALSE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
2093 | NOC408 | NOC | NA |  | OSS | OSS | OSS | DC and Field IPMPLS | IPSLA (Jitter to be configurable and existing >30ms to be reported in Dashboard |  | Critical | COMPLETED | NNMI | NPS | [13 empty] | Applications/Tools | OPEN | To be checked | OPEN | FALSE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
2094 | NOC409 | NOC | NA |  | OSS | OSS | OSS | DC and Field IPMPLS | Traffic Utilisation covering All QoS Partameters Daily |  | Critical | OPEN | NNMI | NPS | 09-09-2025: Need to discuss with OT | [12 empty] | Applications/Tools | OPEN | 09-09-2025: Need to discuss with OT | OPEN | TRUE | [7 empty] | Open | Open | Open
2095 | NOC41 | NOC | NA |  |  |  | Helpdesk | Help Desk | Help Desk managing and publishing KPI like Total I/O call, answereed call withing time frame etc. Monthly |  | NON-Critical |  | Helpdesk | Dial center | 24-Sep-25: Option available to Choose Dates, daily, Weekly and Monthly But not Direct as Daily, Weekly, Monthly | [12 empty] | Applications/Tools | Closed | [8 empty] | 2025-09-24 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\NOC38,39,40,41,42 | Completed & Approved | Closed before june-2025 | Closed after June
2096 | NOC410 | NOC | NA |  | OSS | OSS | OSS | DC and Field IPMPLS | Traffic Utilisation covering All QoS Partameters Weekly |  | Critical | OPEN | NNMI | NPS | 09-09-2025: Need to discuss with OT | [12 empty] | Applications/Tools | OPEN | 09-09-2025: Need to discuss with OT | OPEN | TRUE | [7 empty] | Open | Open | Open
2097 | NOC411 | NOC | NA |  | OSS | OSS | OSS | DC and Field IPMPLS | Traffic Utilisation covering All QoS Partameters Monthly |  | Critical | OPEN | NNMI | NPS | 09-09-2025: Need to discuss with OT | [12 empty] | Applications/Tools | OPEN | 09-09-2025: Need to discuss with OT | OPEN | TRUE | [7 empty] | Open | Open | Open
2098 | NOC412 | NOC | NA |  | OSS | OSS | OSS | DC and Field IPMPLS | Traffic Utilisation covering All QoS Partameters (Selective from and to dates) |  | Critical | OPEN | NNMI | NPS | 09-09-2025: Need to discuss with OT | [12 empty] | Applications/Tools | OPEN | 09-09-2025: Need to discuss with OT | OPEN | TRUE | [7 empty] | Open | Open | Open
2099 | NOC413 | NOC | NA |  | OSS | OSS | OSS | BBNL Reports | Block and GP Status Daily |  | Critical | COMPLETED | HPSM | Incident Management | [13 empty] | Applications/Tools | Closed | 0 | Completed With Artifacts | TRUE | [5 empty] | 2025-11-18 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\OSS\52 Artefcats_18112025 | Closed after 14-Nov-25 | Closed after 14-Nov-25 | Completed but Verification undrer Process
2100 | NOC414 | NOC | NA |  | OSS | OSS | OSS | BBNL Reports | Block and GP Status Weekly |  | Critical | NOT_FEASIBLE | HPSM | Incident Management | 11-Oct-25: BBNL do not ask weekly hence it is not delivered | [12 empty] | Applications/Tools |  | 11-Oct-25: BBNL do not ask weekly hence it is not delivered | Deferred | TRUE | [7 empty] | Open | Open | Open
2101 | NOC415 | NOC | NA |  | OSS | OSS | OSS | BBNL Reports | Block and GP Status Monthly |  | Critical | COMPLETED | HPSM | Incident Management | [13 empty] | Applications/Tools | Closed | 0 | Completed With Artifacts | TRUE | [5 empty] | 2025-11-18 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\OSS\52 Artefcats_18112025 | Closed after 14-Nov-25 | Closed after 14-Nov-25 | Completed but Verification undrer Process
2102 | NOC416 | NOC | NA |  | OSS | OSS | OSS | BBNL Reports | Block and GP Status (Selective from and to dates) |  | Critical | NOT_FEASIBLE | HPSM | Incident Management | 11-Oct-25: BBNL do not ask Selective from and to dates hence it is not delivered | [12 empty] | Applications/Tools |  | 11-Oct-25: BBNL do not ask Selective from and to dates hence it is not delivered | Deferred | TRUE | [7 empty] | Open | Open | Open
2103 | NOC417 | NOC | NA |  | OSS | OSS | OSS | BBNL Reports | Block and GP Availability Daily |  | Critical | COMPLETED | HPSM | Incident Management | [13 empty] | Applications/Tools | Closed | 0 | Completed With Artifacts | TRUE | [5 empty] | 2025-11-18 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\OSS\52 Artefcats_18112025 | Closed after 14-Nov-25 | Closed after 14-Nov-25 | Completed but Verification undrer Process
2104 | NOC418 | NOC | NA |  | OSS | OSS | OSS | BBNL Reports | Block and GP Availability Weekly |  | Critical | NOT_FEASIBLE | HPSM | Incident Management | 11-Oct-25: BBNL do not ask weekly hence it is not delivered | [12 empty] | Applications/Tools |  | 11-Oct-25: BBNL do not ask weekly hence it is not delivered | Deferred | TRUE | [7 empty] | Open | Open | Open
2105 | NOC419 | NOC | NA |  | OSS | OSS | OSS | BBNL Reports | Block and GP Availability Monthly |  | Critical | COMPLETED | HPSM | Incident Management | [13 empty] | Applications/Tools | Closed | 0 | Completed With Artifacts | TRUE | [5 empty] | 2025-11-18 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\OSS\52 Artefcats_18112025 | Closed after 14-Nov-25 | Closed after 14-Nov-25 | Completed but Verification undrer Process
2106 | NOC42 | NOC | NA |  |  |  | Helpdesk | Help Desk | Help Desk managing and publishing KPI like Total I/O call, answereed call withing time frame etc. (Selective from and to dates) |  | NON-Critical |  | Helpdesk | Dial center | 24-Sep-25: Option available to Choose Dates, daily, Weekly and Monthly But not Direct as Daily, Weekly, Monthly | [12 empty] | Applications/Tools | Closed | [8 empty] | 2025-09-24 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\NOC38,39,40,41,42 | Completed & Approved | Closed before june-2025 | Closed after June
2107 | NOC420 | NOC | NA |  | OSS | OSS | OSS | BBNL Reports | Block and GP Availability (Selective from and to dates) |  | Critical | NOT_FEASIBLE | HPSM | Incident Management | 11-Oct-25: BBNL do not ask Selective from and to dates hence it is not delivered | [12 empty] | Applications/Tools |  | 11-Oct-25: BBNL do not ask Selective from and to dates hence it is not delivered | Deferred | TRUE | [7 empty] | Open | Open | Open
2108 | NOC421 | NOC | NA |  |  |  | New BSS | BBNL Reports | FTTH Connections and their utilisation(Including Household) Daily |  | Critical | OPEN | BSS | CRM | [13 empty] | #N/A | OPEN | 0 | Not Relevant To OSS | TRUE | [7 empty] | Open | Open | Open
2109 | NOC422 | NOC | NA |  |  |  | New BSS | BBNL Reports | FTTH Connections and their utilisation(Including Household) Weekly |  | Critical | OPEN | BSS | CRM | [13 empty] | #N/A | OPEN | 0 | Not Relevant To OSS | TRUE | [7 empty] | Open | Open | Open
2110 | NOC423 | NOC | NA |  |  |  | New BSS | BBNL Reports | FTTH Connections and their utilisation(Including Household) Monthly |  | Critical | OPEN | BSS | CRM | [13 empty] | #N/A | OPEN | 0 | Not Relevant To OSS | TRUE | [7 empty] | Open | Open | Open
2111 | NOC424 | NOC | NA |  |  |  | New BSS | BBNL Reports | FTTH Connections and their utilisation(Including Household) (Selective from and to dates) |  | Critical | OPEN | BSS | CRM | [13 empty] | #N/A | OPEN | 0 | Not Relevant To OSS | TRUE | [7 empty] | Open | Open | Open
2112 | NOC425 | NOC | NA |  |  |  | BSS | Regulatory Compliance | Customer connections Daily |  | Critical | OPEN | BSS | CRM | [13 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2113 | NOC426 | NOC | NA |  |  |  | BSS | Regulatory Compliance | Customer connections Weekly |  | Critical | OPEN | BSS | CRM | [13 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2114 | NOC427 | NOC | NA |  |  |  | BSS | Regulatory Compliance | Customer connections Monthly |  | Critical | OPEN | BSS | CRM | [13 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2115 | NOC428 | NOC | NA |  |  |  | BSS | Regulatory Compliance | Customer connections (Selective from and to dates) |  | Critical | OPEN | BSS | CRM | [13 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2116 | NOC429 | NOC | NA |  |  |  | BSS | Regulatory Compliance | Billing Daily |  | Critical | OPEN | BSS | Billing | [13 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2117 | NOC43 | NOC | NA |  | OSS | OSS | OSS | Service Assurance | Raised Proactive and reactive TT for all service deliverable sites and troubleshoot, escalation to field, follow up with field and resolve the issue Hourly |  | Critical | COMPLETED | HPSM | Incident Management | [13 empty] | Applications/Tools | OPEN | 0 | Completed With Artifacts | TRUE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
2118 | NOC430 | NOC | NA |  |  |  | BSS | Regulatory Compliance | Billing Weekly |  | Critical | OPEN | BSS | Billing | [13 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2119 | NOC431 | NOC | NA |  |  |  | BSS | Regulatory Compliance | Billing Monthly |  | Critical | OPEN | BSS | Billing | [13 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2120 | NOC432 | NOC | NA |  |  |  | BSS | Regulatory Compliance | Billing (Selective from and to dates) |  | Critical | OPEN | BSS | Billing | [13 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2121 | NOC433 | NOC | NA |  |  |  | BSS | Regulatory Compliance | Waiver Daily |  | Critical | OPEN | BSS | Billing | [13 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2122 | NOC434 | NOC | NA |  |  |  | BSS | Regulatory Compliance | Waiver Weekly |  | Critical | OPEN | BSS | Billing | [13 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2123 | NOC435 | NOC | NA |  |  |  | BSS | Regulatory Compliance | Waiver Monthly |  | Critical | OPEN | BSS | Billing | [13 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2124 | NOC436 | NOC | NA |  |  |  | BSS | Regulatory Compliance | Waiver (Selective from and to dates) |  | Critical | OPEN | BSS | Billing | [13 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2125 | NOC437 | NOC | NA |  |  |  | IPDR | Regulatory | Customer data logs(Session with MAC) Daily |  | Critical |  | IPDR | IPDR | [13 empty] | Applications/Tools | OPEN | [10 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
2126 | NOC438 | NOC | NA |  |  |  | IPDR | Regulatory | Customer data logs(Session with MAC) Weekly |  | Critical |  | IPDR | IPDR | [13 empty] | Applications/Tools | OPEN | [10 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
2127 | NOC439 | NOC | NA |  |  |  | IPDR | Regulatory | Customer data logs(Session with MAC) Monthly |  | Critical |  | IPDR | IPDR | [13 empty] | Applications/Tools | OPEN | [10 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
2128 | NOC44 | NOC | NA |  | OSS | OSS | OSS | Service Assurance | Raised Proactive and reactive TT for all service deliverable sites and troubleshoot, escalation to field, follow up with field and resolve the issue Daily |  | Critical | COMPLETED | HPSM | Incident Management | 18-Nov-25:Proactive TT to be raised based on Service inventory which we are Deploying and Recent Service Status API to BSS | [12 empty] | Applications/Tools | OPEN | 0 | Completed With Artifacts | TRUE | [7 empty] | Reopened | Reopened | Completed but Verification undrer Process
2129 | NOC440 | NOC | NA |  |  |  | IPDR | Regulatory | Customer data logs(Session with MAC) (Selective from and to dates) |  | Critical |  | IPDR | IPDR | [13 empty] | Applications/Tools | OPEN | [10 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
2130 | NOC441 | NOC | NA |  |  |  | BSS | Regulatory Compliance | Service Delivery TAT Dashboard and Reporting Daily |  | Critical | OPEN | BSS | CRM | [13 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2131 | NOC442 | NOC | NA |  |  |  | BSS | Regulatory Compliance | Service Delivery TAT Dashboard and Reporting Weekly |  | Critical | OPEN | BSS | CRM | [13 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2132 | NOC443 | NOC | NA |  |  |  | BSS | Regulatory Compliance | Service Delivery TAT Dashboard and Reporting Monthly |  | Critical | OPEN | BSS | CRM | [13 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2133 | NOC444 | NOC | NA |  |  |  | BSS | Regulatory Compliance | Service Delivery TAT Dashboard and Reporting (Selective from and to dates) |  | Critical | OPEN | BSS | CRM | [13 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2134 | NOC445 | NOC | NA |  | OSS | OSS | OSS | Service Monitoring | VLAN |  | Critical | OPEN | HPSM | Service Inventory | OPEN-DEPENDENT | [12 empty] | Applications/Tools | OPEN |  | Completed With Artifacts | FALSE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
2135 | NOC446 | NOC | NA |  | OSS | OSS | OSS | Service Monitoring | ONT Downlink Port(Service segregation 4- UPS, 1-4 for Services) |  | Critical | NOT_FEASIBLE | HPSM | Service Inventory | [13 empty] | Applications/Tools | OPEN | 0 | Not-Feasible | TRUE | [7 empty] | Open | Open | Open
2136 | NOC447 | NOC | NA |  | OSS | OSS | OSS | Service Monitoring | Service ID Mapping for UPS and Customer services |  | Critical | OPEN | HPSM | Service Inventory | OPEN-DEPENDENT | [12 empty] | Applications/Tools | OPEN |  | Open-Dependent | FALSE | [7 empty] | Open | Open | Open
2137 | NOC448 | NOC | NA |  |  |  | NSO | Service Provisioning | Service Provision using NSO Daily |  | Critical |  | NSO | SCCM | 29-12-2025:- Can be done via SCCM | [12 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2138 | NOC449 | NOC | NA |  |  |  | NSO | Service Provisioning | Service template configuration |  | Critical |  | NSO | SCCM | 29-12-2025:- Can be done via SCCM | [12 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2139 | NOC45 | NOC | NA |  | OSS | OSS | OSS | Service Assurance | Raised Proactive and reactive TT for all service deliverable sites and troubleshoot, escalation to field, follow up with field and resolve the issue Weekly |  | Critical | COMPLETED | HPSM | Incident Management | 18-Nov-25: Proactive TT to be raised based on Service inventory which we are Deploying and Recent Service Status API to BSS | [12 empty] | Applications/Tools | OPEN | 0 | Completed With Artifacts | TRUE | [7 empty] | Reopened | Reopened | Completed but Verification undrer Process
2140 | NOC450 | NOC | NA |  |  |  | BSS | Service Provisioning | ILL(G2G) Daily |  | Critical | OPEN | BSS | CRM | [13 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2141 | NOC451 | NOC | NA |  |  |  | BSS | Service Provisioning | ILL(G2G) with QoS Daily |  | Critical | OPEN | BSS | CRM | [13 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2142 | NOC452 | NOC | NA |  |  |  | BSS | Service Provisioning | ILL(G2G) with QoS Weekly |  | Critical | COMPLETED | BSS | CRM | 09-09-2025: If IPMPLS Node interface for customer link then possible | [12 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2143 | NOC453 | NOC | NA |  |  |  | BSS | Service Provisioning | ILL(G2G) with QoS Monthly |  | Critical | OPEN | BSS | CRM | [13 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2144 | NOC454 | NOC | NA |  |  |  | BSS | Service Provisioning | ILL(G2G) with QoS (Selective from and to dates) |  | Critical | OPEN | BSS | CRM | [13 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2145 | NOC455 | NOC | NA |  |  |  | BSS | Service Provisioning | GI BB(G2G) Direct Bandwidth Daily |  | Critical | OPEN | BSS | CRM | [13 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2146 | NOC456 | NOC | NA |  |  |  | BSS | Service Provisioning | GI BB(G2G) Direct Bandwidth Weekly |  | Critical | COMPLETED | BSS | CRM | 09-09-2025: If IPMPLS Node interface for customer link then possible | [12 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2147 | NOC457 | NOC | NA |  |  |  | BSS | Service Provisioning | GI BB(G2G) Direct Bandwidth Monthly |  | Critical | OPEN | BSS | CRM | [13 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2148 | NOC458 | NOC | NA |  |  |  | BSS | Service Provisioning | GI BB(G2G) Direct Bandwidth (Selective from and to dates) |  | Critical | OPEN | BSS | CRM | [13 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2149 | NOC459 | NOC | NA |  |  |  | BSS | Service Provisioning | GI BB(G2G) Bandidth with QoS filtered Daily |  | Critical | OPEN | BSS | CRM | [13 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2150 | NOC46 | NOC | NA |  | OSS | OSS | OSS | Service Assurance | Raised Proactive and reactive TT for all service deliverable sites and troubleshoot, escalation to field, follow up with field and resolve the issue Monthly |  | Critical | COMPLETED | HPSM | Incident Management | 18-Nov-25: Proactive TT to be raised based on Service inventory which we are Deploying and Recent Service Status API to BSS | [12 empty] | Applications/Tools | OPEN | 0 | Completed With Artifacts | TRUE | [7 empty] | Reopened | Reopened | Completed but Verification undrer Process
2151 | NOC460 | NOC | NA |  |  |  | BSS | Service Provisioning | GI BB(G2G) Bandidth with QoS filtered Weekly |  | Critical | COMPLETED | BSS | CRM | 09-09-2025: If IPMPLS Node interface for customer link then possible | [12 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2152 | NOC461 | NOC | NA |  |  |  | BSS | Service Provisioning | GI BB(G2G) Bandidth with QoS filtered Monthly |  | Critical | OPEN | BSS | CRM | [13 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2153 | NOC462 | NOC | NA |  |  |  | BSS | Service Provisioning | GI BB(G2G) Bandidth with QoS filtered (Selective from and to dates) |  | Critical | OPEN | BSS | CRM | [13 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2154 | NOC463 | NOC | NA |  |  |  | BSS | Service Provisioning | Dark Fiber Daily |  | Critical | OPEN | BSS | CRM | [13 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2155 | NOC464 | NOC | NA |  |  |  | BSS | Service Provisioning | Dark Fiber Weekly |  | Critical | OPEN | BSS | CRM | [13 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2156 | NOC465 | NOC | NA |  |  |  | BSS | Service Provisioning | Dark Fiber Monthly |  | Critical | OPEN | BSS | CRM | [13 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2157 | NOC466 | NOC | NA |  |  |  | BSS | Service Provisioning | Dark Fiber (Selective from and to dates) |  | Critical | OPEN | BSS | CRM | [13 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2158 | NOC467 | NOC | NA |  |  |  | BSS | Service Provisioning | Household(G2C) Daily |  | Critical | OPEN | BSS | CRM | [13 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2159 | NOC468 | NOC | NA |  |  |  | BSS | Service Provisioning | Household(G2C) Weekly |  | Critical | OPEN | BSS | CRM | [13 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2160 | NOC469 | NOC | NA |  |  |  | BSS | Service Provisioning | Household(G2C) Monthly |  | Critical | OPEN | BSS | CRM | [13 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2161 | NOC47 | NOC | NA |  | OSS | OSS | OSS | Service Assurance | Raised Proactive and reactive TT for all service deliverable sites and troubleshoot, escalation to field, follow up with field and resolve the issue (Selective from and to dates) |  | Critical | COMPLETED | HPSM | Incident Management | 18-Nov-25: Proactive TT to be raised based on Service inventory which we are Deploying and Recent Service Status API to BSS | [12 empty] | Applications/Tools | OPEN | 0 | Completed With Artifacts | TRUE | [7 empty] | Reopened | Reopened | Completed but Verification undrer Process
2162 | NOC470 | NOC | NA |  |  |  | BSS | Service Provisioning | Household(G2C) (Selective from and to dates) |  | Critical | OPEN | BSS | CRM | [13 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2163 | NOC471 | NOC | NA |  |  |  | BSS | Service Provisioning | VPN(B2B) Daily |  | Critical | OPEN | BSS | CRM | [13 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2164 | NOC472 | NOC | NA |  |  |  | BSS | Service Provisioning | VPN(B2B) Weekly |  | Critical | OPEN | BSS | CRM | [13 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2165 | NOC473 | NOC | NA |  |  |  | BSS | Service Provisioning | VPN(B2B) Monthly |  | Critical | OPEN | BSS | CRM | [13 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2166 | NOC474 | NOC | NA |  |  |  | BSS | Service Provisioning | VPN(B2B) (Selective from and to dates) |  | Critical | OPEN | BSS | CRM | [13 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2167 | NOC475 | NOC | NA |  |  |  | BSS | Service Provisioning | VPN(B2B)with filtered QoS Daily |  | Critical | OPEN | BSS | CRM | [13 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2168 | NOC476 | NOC | NA |  |  |  | BSS | Service Provisioning | VPN(B2B)with filtered QoS Weekly |  | Critical | OPEN | BSS | CRM | [13 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2169 | NOC477 | NOC | NA |  |  |  | BSS | Service Provisioning | VPN(B2B)with filtered QoS Monthly |  | Critical | OPEN | BSS | CRM | [13 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2170 | NOC478 | NOC | NA |  |  |  | BSS | Service Provisioning | VPN(B2B)with filtered QoS (Selective from and to dates) |  | Critical | OPEN | BSS | CRM | [13 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2171 | NOC479 | NOC | NA |  |  |  | BSS | Service Provisioning | Enterprise(B2B) Daily |  | Critical | OPEN | BSS | CRM | [13 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2172 | NOC48 | NOC | NA |  |  |  | GPON | OSS | Summary Status of complete 424 Mandal OLTs ( Blocks ) of PKG-ABC Daily |  | Critical | COMPLETED | HPSM | Incident Management | 18-Nov-25: Repeated count in a Day should be captured | [12 empty] | Applications/Tools | OPEN | 0 | Completed With Artifacts | TRUE | [7 empty] | Reopened | Reopened | Completed but Verification undrer Process
2173 | NOC480 | NOC | NA |  |  |  | BSS | Service Provisioning | Enterprise(B2B) Weekly |  | Critical | OPEN | BSS | CRM | [13 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2174 | NOC481 | NOC | NA |  |  |  | BSS | Service Provisioning | Enterprise(B2B) Monthly |  | Critical | OPEN | BSS | CRM | [13 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2175 | NOC482 | NOC | NA |  |  |  | BSS | Service Provisioning | Enterprise(B2B) (Selective from and to dates) |  | Critical | OPEN | BSS | CRM | [13 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2176 | NOC483 | NOC | NA |  |  |  | BSS | Service Provisioning | Enterprise(B2B) with filtered QoS Daily |  | Critical | OPEN | BSS | CRM | [13 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2177 | NOC484 | NOC | NA |  |  |  | BSS | Service Provisioning | Enterprise(B2B) with filtered QoS Weekly |  | Critical | OPEN | BSS | CRM | [13 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2178 | NOC485 | NOC | NA |  |  |  | BSS | Service Provisioning | Enterprise(B2B) with filtered QoS Monthly |  | Critical | OPEN | BSS | CRM | [13 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2179 | NOC486 | NOC | NA |  |  |  | BSS | Service Provisioning | Enterprise(B2B) with filtered QoS (Selective from and to dates) |  | Critical | OPEN | BSS | CRM | [13 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2180 | NOC487 | NOC | NA |  |  |  | BSS | Service Provisioning | Partner(B2B2C) Daily |  | Critical | COMPLETED | BSS | CRM | [13 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2181 | NOC488 | NOC | NA |  |  |  | BSS | Service Provisioning | Partner(B2B2C) Weekly |  | Critical | COMPLETED | BSS | CRM | [13 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2182 | NOC489 | NOC | NA |  |  |  | BSS | Service Provisioning | Partner(B2B2C) Monthly |  | Critical | COMPLETED | BSS | CRM | [13 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2183 | NOC49 | NOC | NA |  |  |  | GPON | OSS | Summary Status of complete 424 Mandal OLTs ( Blocks ) of PKG-ABC Weekly |  | Critical | NOT_FEASIBLE | HPSM | Incident Management | 16-Oct-25: Live data -bothUOC and POWErbi | [12 empty] | Applications/Tools | OPEN | Live data -bothUOC and POWErbi | Not-Feasible | FALSE | [7 empty] | Open | Open | Open
2184 | NOC490 | NOC | NA |  |  |  | BSS | Service Provisioning | Partner(B2B2C) (Selective from and to dates) |  | Critical | COMPLETED | BSS | CRM | [13 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2185 | NOC491 | NOC | NA |  |  |  | BSS | Service Provisioning | Partner(B2B2C) with Filtered QoS Daily |  | Critical | OPEN | BSS | CRM | [13 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2186 | NOC492 | NOC | NA |  |  |  | BSS | Service Provisioning | Partner(B2B2C) with Filtered QoS Weekly |  | Critical | OPEN | BSS | CRM | [13 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2187 | NOC493 | NOC | NA |  |  |  | BSS | Service Provisioning | Partner(B2B2C) with Filtered QoS Monthly |  | Critical | OPEN | BSS | CRM | [13 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2188 | NOC494 | NOC | NA |  |  |  | BSS | Service Provisioning | Partner(B2B2C) with Filtered QoS (Selective from and to dates) |  | Critical | OPEN | BSS | CRM | [13 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2189 | NOC495 | NOC | NA |  |  |  | BSS | Service Provisioning | T-cell (P2MP) Daily |  | Critical | OPEN | BSS | CRM | [13 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2190 | NOC496 | NOC | NA |  |  |  | BSS | Service Provisioning | T-cell (P2MP) Weekly |  | Critical | OPEN | BSS | CRM | [13 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2191 | NOC497 | NOC | NA |  |  |  | BSS | Service Provisioning | T-cell (P2MP) Monthly |  | Critical | OPEN | BSS | CRM | [13 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2192 | NOC498 | NOC | NA |  |  |  | BSS | Service Provisioning | T-cell (P2MP) (Selective from and to dates) |  | Critical | OPEN | BSS | CRM | [13 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2193 | NOC499 | NOC | NA |  |  |  | BSS | Service Provisioning | T-cell P2MP with Filtered QoS Daily |  | Critical | OPEN | BSS | CRM | [13 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2194 | NOC5 | NOC | NA |  | OSS | OSS | OSS | DC | DC Applications uptime & SLA Daily |  | Critical |  | HPSM | Incident Management | [13 empty] | Applications/Tools | OPEN | 0 | OPEN | TRUE | [7 empty] | Open | Open | Open
2195 | NOC50 | NOC | NA |  |  |  | GPON | OSS | Summary Status of complete 424 Mandal OLTs ( Blocks ) of PKG-ABC Monthly |  | Critical | COMPLETED | HPSM | Incident Management | 18-Nov-25: Repeated count should be captured | [12 empty] | Applications/Tools | OPEN | only Live data | Completed With Artifacts | FALSE | [7 empty] | Reopened | Reopened | Completed but Verification undrer Process
2196 | NOC500 | NOC | NA |  |  |  | BSS | Service Provisioning | T-cell P2MP with Filtered QoS Weekly |  | Critical | OPEN | BSS | CRM | [13 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2197 | NOC501 | NOC | NA |  |  |  | BSS | Service Provisioning | T-cell P2MP with Filtered QoS Monthly |  | Critical | OPEN | BSS | CRM | [13 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2198 | NOC502 | NOC | NA |  |  |  | BSS | Service Provisioning | T-cell P2MP with Filtered QoS (Selective from and to dates) |  | Critical | OPEN | BSS | CRM | [13 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2199 | NOC503 | NOC | NA |  |  |  | BSS | Service Provisioning | T-cell (P2P) Daily |  | Critical | OPEN | BSS | CRM | [13 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2200 | NOC504 | NOC | NA |  |  |  | BSS | Service Provisioning | T-cell (P2P) Weekly |  | Critical | OPEN | BSS | CRM | [13 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2201 | NOC505 | NOC | NA |  |  |  | BSS | Service Provisioning | T-cell (P2P) Monthly |  | Critical | OPEN | BSS | CRM | [13 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2202 | NOC506 | NOC | NA |  |  |  | BSS | Service Provisioning | T-cell (P2P) (Selective from and to dates) |  | Critical | OPEN | BSS | CRM | [13 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2203 | NOC507 | NOC | NA |  |  |  | BSS | Service Provisioning | T-cell P2P with Filtered QoS Daily |  | Critical | OPEN | BSS | CRM | [13 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2204 | NOC508 | NOC | NA |  |  |  | BSS | Service Provisioning | T-cell P2P with Filtered QoS Weekly |  | Critical | OPEN | BSS | CRM | [13 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2205 | NOC509 | NOC | NA |  |  |  | BSS | Service Provisioning | T-cell P2P with Filtered QoS Monthly |  | Critical | OPEN | BSS | CRM | [13 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2206 | NOC51 | NOC | NA |  |  |  | GPON | OSS | Summary Status of complete 424 Mandal OLTs ( Blocks ) of PKG-ABC (Selective from and to dates) |  | Critical | COMPLETED | HPSM | Incident Management | 18-Nov-25: Repeated count should be captured | [12 empty] | Applications/Tools | OPEN | Live data | Completed With Artifacts | FALSE | [7 empty] | Reopened | Reopened | Completed but Verification undrer Process
2207 | NOC510 | NOC | NA |  |  |  | BSS | Service Provisioning | T-cell P2P with Filtered QoS (Selective from and to dates) |  | Critical | OPEN | BSS | CRM | [13 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2208 | NOC511 | NOC | NA |  | OSS | OSS | OSS and NSO | Service Provisioning | Bandwidth Feasibility for New Provisioning, Exising configured bandwidth to be made available at OSS Daily |  | Critical | OPEN | OSS and NSO | Service Inventory, SCCM | 14-09-2025: We can get this report from BSS by downloading services provisioned for the perticular week | [12 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2209 | NOC512 | NOC | NA |  | OSS | OSS | OSS and NSO | Service Provisioning | Bandwidth Feasibility for New Provisioning, Exising configured bandwidth to be made available at OSS Weekly |  | Critical | OPEN | OSS and NSO | Service Inventory, SCCM | 14-09-2025: We can get this report from BSS by downloading services provisioned for the perticular week | [12 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2210 | NOC513 | NOC | NA |  | OSS | OSS | OSS and NSO | Service Provisioning | Bandwidth Feasibility for New Provisioning, Exising configured bandwidth to be made available at OSS Monthly |  | Critical | OPEN | OSS and NSO | Service Inventory, SCCM | 14-09-2025: We can get this report from BSS by downloading services provisioned for the perticular month | [12 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2211 | NOC514 | NOC | NA |  | OSS | OSS | OSS and NSO | Service Provisioning | Bandwidth Feasibility for New Provisioning, Exising configured bandwidth to be made available at OSS (Selective from and to dates) |  | Critical | OPEN | OSS and NSO | Service Inventory, SCCM | 14-09-2025: We can get this report from BSS by downloading services provisioned for the selected period | [12 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2212 | NOC515 | NOC | NA |  | OSS | OSS | OSS | Service Provisioning | Capacity augmentationn based on Feasible/NON- Feasible status count and required bandwidth Daily |  | Critical | COMPLETED | OSS | Service Inventory, UTM | 09-09-2025: Desired output will be shown through BSS but actual data is fetching from the OSS (UTM +GIS). | [12 empty] | Applications/Tools | OPEN | 09-09-2025: Desired output will be shown through BSS but actual data is fetching from the OSS (UTM +GIS). | Completed | TRUE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
2213 | NOC516 | NOC | NA |  | OSS | OSS | OSS | Service Provisioning | Capacity augmentationn based on Feasible/NON- Feasible status count and required bandwidth Weekly |  | Critical | NOT_FEASIBLE | OSS | Service Inventory, UTM | [13 empty] | Applications/Tools | OPEN | 0 | Not-Feasible | TRUE | [7 empty] | Open | Open | Open
2214 | NOC517 | NOC | NA |  | OSS | OSS | OSS | Service Provisioning | Capacity augmentationn based on Feasible/NON- Feasible status count and required bandwidth Monthly |  | Critical | COMPLETED | OSS | Service Inventory, UTM | 09-09-2025: Desired output will be shown through BSS but actual data is fetching from the OSS (UTM +GIS). | [12 empty] | Applications/Tools | OPEN | 09-09-2025: Desired output will be shown through BSS but actual data is fetching from the OSS (UTM +GIS). | Completed | TRUE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
2215 | NOC518 | NOC | NA |  | OSS | OSS | OSS | Service Provisioning | Capacity augmentationn based on Feasible/NON- Feasible status count and required bandwidth (Selective from and to dates) |  | Critical | COMPLETED | OSS | Service Inventory, UTM | 09-09-2025: Desired output will be shown through BSS but actual data is fetching from the OSS (UTM +GIS). | [12 empty] | Applications/Tools | OPEN | 09-09-2025: Desired output will be shown through BSS but actual data is fetching from the OSS (UTM +GIS). | Completed | TRUE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
2216 | NOC519 | NOC | NA |  |  |  | WFM | WFM | User level view for Number of tasks assigned/resolved/closed Daily |  | Critical |  | WFM | Corrective | 15-Nov-25:Development Completed & Reports are available | [12 empty] | Applications/Tools | OPEN | [10 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
2217 | NOC52 | NOC | NA |  |  |  | GPON | OSS | Summary of Lit-up GPs Status_8894 as on 14-05-2025_4PM(Revised) Daily |  | Critical | COMPLETED | HPSM | Incident Management | [13 empty] | Applications/Tools | OPEN | 0 | Completed With Artifacts | TRUE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
2218 | NOC520 | NOC | NA |  |  |  | WFM | WFM | User level view for Number of tasks assigned/resolved/closed Weekly |  | Critical |  | WFM | Incident Management | 15-Nov-25:Development Completed & Reports are available | [12 empty] | Applications/Tools | OPEN | [10 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
2219 | NOC521 | NOC | NA |  |  |  | WFM | WFM | User level view for Number of tasks assigned/resolved/closed Monthly |  | Critical |  | WFM | Incident Management | 15-Nov-25:Development Completed & Reports are available | [12 empty] | Applications/Tools | OPEN | [10 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
2220 | NOC522 | NOC | NA |  |  |  | WFM | WFM | User level view for Number of tasks assigned/resolved/closed (Selective from and to dates) |  | Critical |  | WFM | Smart track | 15-Nov-25:Development Completed & Reports are available | [12 empty] | Applications/Tools | OPEN | [10 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
2221 | NOC523 | NOC | NA |  |  |  | WFM | WFM | Management Dashboard Patroller Daily |  | Critical |  | WFM | Smart track | 15-Nov-25:The development is complete and can be demonstrated through three methods: reports, dashboards, and single-click interaction on the map | [12 empty] | Applications/Tools | OPEN | [10 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
2222 | NOC524 | NOC | NA |  |  |  | WFM | WFM | Management Dashboard Patroller Weekly |  | Critical |  | WFM | Smart track | 15-Nov-25:The development is complete and can be demonstrated through three methods: reports, dashboards, and single-click interaction on the map | [12 empty] | Applications/Tools | OPEN | [10 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
2223 | NOC525 | NOC | NA |  |  |  | WFM | WFM | Management Dashboard Patroller Monthly |  | Critical |  | WFM | Smart track | 15-Nov-25:The development is complete and can be demonstrated through three methods: reports, dashboards, and single-click interaction on the map | [12 empty] | Applications/Tools | OPEN | [10 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
2224 | NOC526 | NOC | NA |  |  |  | WFM | WFM | Management Dashboard Patroller (Selective from and to dates) |  | Critical |  | WFM | Smart track | 15-Nov-25:The development is complete and can be demonstrated through three methods: reports, dashboards, and single-click interaction on the map | [12 empty] | Applications/Tools | OPEN | [10 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
2225 | NOC527 | NOC | NA |  |  |  | WFM | WFM | Management Dashboard FRT Daily |  | Critical |  | WFM | Smart track | 15-Nov-25:The development is complete and can be demonstrated through three methods: reports, dashboards, and single-click interaction on the map | [12 empty] | Applications/Tools | OPEN | [10 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
2226 | NOC528 | NOC | NA |  |  |  | WFM | WFM | Management Dashboard FRT Weekly |  | Critical |  | WFM | Smart track | 15-Nov-25:The development is complete and can be demonstrated through three methods: reports, dashboards, and single-click interaction on the map | [12 empty] | Applications/Tools | OPEN | [10 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
2227 | NOC529 | NOC | NA |  |  |  | WFM | WFM | Management Dashboard FRT Monthly |  | Critical |  | WFM | Smart track | 15-Nov-25:The development is complete and can be demonstrated through three methods: reports, dashboards, and single-click interaction on the map | [12 empty] | Applications/Tools | OPEN | [10 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
2228 | NOC53 | NOC | NA |  |  |  | GPON | OSS | Summary of Lit-up GPs Status_8894 as on 14-05-2025_4PM(Revised) Weekly |  | Critical | NOT_FEASIBLE | HPSM | Incident Management | [13 empty] | Applications/Tools | OPEN | 0 | Not-Feasible | TRUE | [7 empty] | Open | Open | Open
2229 | NOC530 | NOC | NA |  |  |  | WFM | WFM | Management Dashboard FRT (Selective from and to dates) |  | Critical |  | WFM | Smart track | 15-Nov-25:The development is complete and can be demonstrated through three methods: reports, dashboards, and single-click interaction on the map | [12 empty] | Applications/Tools | OPEN | [10 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
2230 | NOC531 | NOC | NA |  |  |  | WFM | WFM | Management Dashboard Engineers Daily |  | Critical |  | WFM | Smart track | 15-Nov-25:The development is complete and can be demonstrated through three methods: reports, dashboards, and single-click interaction on the map | [12 empty] | Applications/Tools | OPEN | [10 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
2231 | NOC532 | NOC | NA |  |  |  | WFM | WFM | Management Dashboard Engineers Weekly |  | Critical |  | WFM | Smart track | 15-Nov-25:The development is complete and can be demonstrated through three methods: reports, dashboards, and single-click interaction on the map | [12 empty] | Applications/Tools | OPEN | [10 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
2232 | NOC533 | NOC | NA |  |  |  | WFM | WFM | Management Dashboard Engineers Monthly |  | Critical |  | WFM | Smart track | 15-Nov-25:The development is complete and can be demonstrated through three methods: reports, dashboards, and single-click interaction on the map | [12 empty] | Applications/Tools | OPEN | [10 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
2233 | NOC534 | NOC | NA |  |  |  | WFM | WFM | Management Dashboard Engineers (Selective from and to dates) |  | Critical |  | WFM | Smart track | 15-Nov-25:The development is complete and can be demonstrated through three methods: reports, dashboards, and single-click interaction on the map | [12 empty] | Applications/Tools | OPEN | [10 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
2234 | NOC535 | NOC | NA |  |  |  | Helpdesk | BSS | Integration to be Aligned with Approved IVR flow(All Customers) Daily |  | NON-Critical |  | BSS | CRM | 01-Dec-25: IVR Flows Submitted for Approval, Post Approval inetgration will be aligned accordingly | [12 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2235 | NOC536 | NOC | NA |  |  |  | Helpdesk | BSS | Integration to be Aligned with Approved IVR flow(All Customers) Weekly |  | NON-Critical |  | BSS | CRM | 01-Dec-25: IVR Flows Submitted for Approval, Post Approval inetgration will be aligned accordingly | [12 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2236 | NOC537 | NOC | NA |  |  |  | Helpdesk | BSS | Integration to be Aligned with Approved IVR flow(All Customers) Monthly |  | NON-Critical |  | BSS | CRM | 01-Dec-25: IVR Flows Submitted for Approval, Post Approval inetgration will be aligned accordingly | [12 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2237 | NOC538 | NOC | NA |  |  |  | Helpdesk | BSS | Integration to be Aligned with Approved IVR flow(All Customers) (Selective from and to dates) |  | NON-Critical |  | BSS | CRM | 01-Dec-25: IVR Flows Submitted for Approval, Post Approval inetgration will be aligned accordingly | [12 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2238 | NOC539 | NOC | NA |  |  |  | Helpdesk | BSS | Integration to be Aligned with Approved IVR flow(All Enterprise) Daily |  | NON-Critical |  | BSS | CRM | 01-Dec-25: IVR Flows Submitted for Approval, Post Approval inetgration will be aligned accordingly | [12 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2239 | NOC54 | NOC | NA |  |  |  | GPON | OSS | Summary of Lit-up GPs Status_8894 as on 14-05-2025_4PM(Revised) Monthly |  | Critical | NOT_FEASIBLE | HPSM | Incident Management | [13 empty] | Applications/Tools | OPEN | 0 | Not-Feasible | TRUE | [7 empty] | Open | Open | Open
2240 | NOC540 | NOC | NA |  |  |  | Helpdesk | BSS | Integration to be Aligned with Approved IVR flow(All Enterprise) Weekly |  | NON-Critical |  | BSS | CRM | 01-Dec-25: IVR Flows Submitted for Approval, Post Approval inetgration will be aligned accordingly | [12 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2241 | NOC541 | NOC | NA |  |  |  | Helpdesk | BSS | Integration to be Aligned with Approved IVR flow(All Enterprise) Monthly |  | NON-Critical |  | BSS | CRM | 01-Dec-25: IVR Flows Submitted for Approval, Post Approval inetgration will be aligned accordingly | [12 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2242 | NOC542 | NOC | NA |  |  |  | Helpdesk | BSS | Integration to be Aligned with Approved IVR flow(All Enterprise) (Selective from and to dates) |  | NON-Critical |  | BSS | CRM | 01-Dec-25: IVR Flows Submitted for Approval, Post Approval inetgration will be aligned accordingly | [12 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2243 | NOC543 | NOC | NA |  |  |  | Helpdesk | BSS | Integration to be Aligned with Approved IVR flow(All Partners) Daily |  | NON-Critical |  | BSS | CRM | 01-Dec-25: IVR Flows Submitted for Approval, Post Approval inetgration will be aligned accordingly | [12 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2244 | NOC544 | NOC | NA |  |  |  | Helpdesk | BSS | Integration to be Aligned with Approved IVR flow(All Partners) Weekly |  | NON-Critical |  | BSS | CRM | 01-Dec-25: IVR Flows Submitted for Approval, Post Approval inetgration will be aligned accordingly | [12 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2245 | NOC545 | NOC | NA |  |  |  | Helpdesk | BSS | Integration to be Aligned with Approved IVR flow(All Partners) Monthly |  | NON-Critical |  | BSS | CRM | 01-Dec-25: IVR Flows Submitted for Approval, Post Approval inetgration will be aligned accordingly | [12 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2246 | NOC546 | NOC | NA |  |  |  | Helpdesk | BSS | Integration to be Aligned with Approved IVR flow(All Partners) (Selective from and to dates) |  | NON-Critical |  | BSS | CRM | 01-Dec-25: IVR Flows Submitted for Approval, Post Approval inetgration will be aligned accordingly | [12 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2247 | NOC547 | NOC | NA |  |  |  | Helpdesk | OSS | Integration to be Aligned with Approved IVR flow(MSI) Daily |  | NON-Critical |  | HPSM | Incident Management | 01-Dec-25: IVR Flows Submitted for Approval, Post Approval inetgration will be aligned accordingly | [12 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2248 | NOC548 | NOC | NA |  |  |  | Helpdesk | OSS | Integration to be Aligned with Approved IVR flow(MSI) Weekly |  | NON-Critical |  | HPSM | Incident Management | 01-Dec-25: IVR Flows Submitted for Approval, Post Approval inetgration will be aligned accordingly | [12 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2249 | NOC549 | NOC | NA |  |  |  | Helpdesk | OSS | Integration to be Aligned with Approved IVR flow(MSI) Monthly |  | NON-Critical |  | HPSM | Incident Management | 01-Dec-25: IVR Flows Submitted for Approval, Post Approval inetgration will be aligned accordingly | [12 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2250 | NOC55 | NOC | NA |  |  |  | GPON | OSS | Summary of Lit-up GPs Status_8894 as on 14-05-2025_4PM(Revised) (Selective from and to dates) |  | Critical | NOT_FEASIBLE | HPSM | Incident Management | [13 empty] | Applications/Tools | OPEN | 0 | Not-Feasible | TRUE | [7 empty] | Open | Open | Open
2251 | NOC550 | NOC | NA |  |  |  | Helpdesk | OSS | Integration to be Aligned with Approved IVR flow(MSI) (Selective from and to dates) |  | NON-Critical |  | HPSM | Incident Management | 01-Dec-25: IVR Flows Submitted for Approval, Post Approval inetgration will be aligned accordingly | [12 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2252 | NOC551 | NOC | NA |  |  |  | Helpdesk | OSS | Integration to be Aligned with Approved IVR flow(NOC) Daily |  | NON-Critical |  | HPSM | Incident Management | 01-Dec-25: IVR Flows Submitted for Approval, Post Approval inetgration will be aligned accordingly | [12 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2253 | NOC552 | NOC | NA |  |  |  | Helpdesk | OSS | Integration to be Aligned with Approved IVR flow(NOC) Weekly |  | NON-Critical |  | HPSM | Incident Management | 01-Dec-25: IVR Flows Submitted for Approval, Post Approval inetgration will be aligned accordingly | [12 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2254 | NOC553 | NOC | NA |  |  |  | Helpdesk | OSS | Integration to be Aligned with Approved IVR flow(NOC) Monthly |  | NON-Critical |  | HPSM | Incident Management | 01-Dec-25: IVR Flows Submitted for Approval, Post Approval inetgration will be aligned accordingly | [12 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2255 | NOC554 | NOC | NA |  |  |  | Helpdesk | OSS | Integration to be Aligned with Approved IVR flow(NOC) (Selective from and to dates) |  | NON-Critical |  | HPSM | Incident Management | 01-Dec-25: IVR Flows Submitted for Approval, Post Approval inetgration will be aligned accordingly | [12 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2256 | NOC555 | NOC | NA |  |  |  | NSO | Service Provisioning | VLAN Planning |  | Critical | OPEN | NSO | SCCM/Playbook | 29-dec-2025: Need discussion.Network Team | [12 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2257 | NOC556 | NOC | NA |  |  |  | NSO | Service Provisioning | IPV4 and IPV6 Planning |  | Critical | OPEN | NSO | SCCM/Playbook | 29-dec-2025: Need discussion.Network Team | [12 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2258 | NOC557 | NOC | NA |  |  |  | BSS | Service Provisioning | Migration of Existing customers provision via BSS-NSO |  | Critical | OPEN | BSS, NSO | CRM, SCCM | [13 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2259 | NOC558 | NOC | NA |  | OSS | OSS | All Domain | OSS | TT should not be generated for planned event window and Affected CI |  | Critical | OPEN | HPSM | Change Management | [13 empty] | Applications/Tools | OPEN | 0 | OPEN | TRUE | [7 empty] | Open | Open | Open
2260 | NOC559 | NOC | NA |  | OSS | OSS | All Domain | OSS | Planned event to be rejected/Postponed incase another side Ring is open |  | Critical | COMPLETED | HPSM | Change Management | [13 empty] | Applications/Tools | OPEN | consider SS from mail | Completed With Artifacts | FALSE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
2261 | NOC56 | NOC | NA |  |  |  | GPON | OSS | T-NOC Report :: Summary of O&M Cluster OLTs status Daily |  | Critical | COMPLETED | HPSM | Incident Management | [13 empty] | Applications/Tools | OPEN | 0 | Completed With Artifacts | TRUE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
2262 | NOC560 | NOC | NA |  |  |  | WFM | WFM | Field Remarks like ETR, RFO updation pending against Open Task |  | Critical |  | WFM | Smart track | [13 empty] | Applications/Tools | OPEN | [10 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
2263 | NOC561 | NOC | NA |  |  |  | WFM | WFM | Field team working without events and as a part of corrective actions at Passive |  | Critical |  | WFM | Smart track | 11-Jul-2025:- SM & WFM Intigration is WIP | [12 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2264 | NOC562 | NOC | NA |  | OSS | OSS&WFM | OSS | OSS | Auto Escalation Matrix |  | Critical |  | HPSM | Incident Management | 09-09-2025: its configurable item and can be modified on demand | [12 empty] | Applications/Tools | Closed | 09-09-2025: its configurable item and can be modified on demand | Completed With Artifacts | TRUE | [5 empty] | 2025-11-18 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\OSS\52 Artefcats_18112025 | Closed after 14-Nov-25 | Closed after 14-Nov-25 | Completed but Verification undrer Process
2265 | NOC563 | NOC | NA |  | OSS | OSS | All Domain | OSS | Configutable paramters for SLA |  | Critical | COMPLETED | NNMI | NPS | [13 empty] | Applications/Tools | Closed | 0 | Completed With Artifacts | TRUE | [5 empty] | 2025-11-18 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\OSS\52 Artefcats_18112025 | Closed after 14-Nov-25 | Closed after 14-Nov-25 | Completed but Verification undrer Process
2266 | NOC564 | NOC | NA |  |  |  | GPON | GPON | Requested Tejas to enable the TR-069 for T-Fiber deployed elements |  | Critical |  | Tejas OEM | ONT | Duplicate point of 472 - 399 | [12 empty] | Applications/Tools | OPEN |  |  |  | Duplicate | [6 empty] | Open | Open | Open
2267 | NOC565 | NOC | NA |  |  |  | GPON | GPON | CIR/PIR in OLT/EMS |  | Critical |  | Tejas OEM | EMS/OLT | Duplicate point of 472 - 407 | [12 empty] | Applications/Tools | OPEN |  |  |  | Duplicate | [6 empty] | Open | Open | Open
2268 | NOC566 | NOC | NA |  |  |  | GPON | GPON | Unable to modify the Service Name |  | Critical |  | Tejas OEM | EMS | [13 empty] | Applications/Tools | Closed | [8 empty] | 2025-07-03 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\409 | Completed & Approved | Closed before june-2025 | Closed after June
2269 | NOC567 | NOC | NA |  |  |  | GPON | GPON | Live PM monitoring per UNI in EMS service Window |  | Critical |  | Tejas OEM | EMS | [13 empty] | Applications/Tools | Closed | [8 empty] | 2025-07-10 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\416 | Completed & Approved | Closed before june-2025 | Closed after June
2270 | NOC568 | NOC | NA |  |  |  | GPON | GPON | Unable to Enable PM from EMS |  | Critical |  | Tejas OEM | EMS | [13 empty] | Applications/Tools | Closed | [8 empty] | 2025-07-07 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\414 | Completed & Approved | Closed before june-2025 | Closed after June
2271 | NOC569 | NOC | NA |  |  |  | GPON | GPON | While creating service profile, maximum bandwidth is not taking 1024000 only considering 1000000 |  | Critical |  | Tejas OEM | EMS | [13 empty] | Applications/Tools | Closed | [8 empty] | 2025-07-31 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\417 | Completed & Approved | Closed before june-2025 | Closed after June
2272 | NOC57 | NOC | NA |  |  |  | GPON | OSS | T-NOC Report :: Summary of O&M Cluster OLTs status Weekly |  | Critical | NOT_FEASIBLE | HPSM | Incident Management | [13 empty] | Applications/Tools | OPEN | 0 | Not-Feasible | TRUE | [7 empty] | Open | Open | Open
2273 | NOC570 | NOC | NA |  |  |  | GPON | GPON | OLT Node not reachable alarm clearance and regeneration |  | Critical |  | Tejas OEM | EMS | [13 empty] | Applications/Tools | Closed | [8 empty] | 2025-07-05 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\425 | Completed & Approved | Closed before june-2025 | Closed after June
2274 | NOC571 | NOC | NA |  |  |  | GPON | GPON | while adding uni in EMS, list of downstream profiles are highlighting in the bottom |  | Critical |  | Tejas OEM | EMS | [13 empty] | Applications/Tools | Closed | [8 empty] | 2025-07-05 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\430 | Completed & Approved | Closed before june-2025 | Closed after June
2275 | NOC572 | NOC | NA |  |  |  | GPON | GPON | Nokia ONT ethernet port status is not updating |  | Critical |  | Tejas OEM | ONT | Duplicate point of 472 - 432 | [12 empty] | Applications/Tools | OPEN |  |  |  | Duplicate | [6 empty] | Open | Open | Open
2276 | NOC573 | NOC | NA |  |  |  | GPON | GPON | Tejas ONT Software Upgrade which are connected under Nokia OLT |  | Critical |  | Tejas OEM | ONT | Duplicate point of 472 - 433 | [12 empty] | Applications/Tools | OPEN |  |  |  | Duplicate | [6 empty] | Open | Open | Open
2277 | NOC574 | NOC | NA |  |  |  | GPON | GPON | API for GI-BB Service, combo port, mixed service - Route Mode with/without translation, including uplink port configuration |  | Critical |  | Tejas OEM | EMS | [13 empty] | Applications/Tools | Closed | [8 empty] | 2025-08-06 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\442 | Completed & Approved | Closed before june-2025 | Closed after June
2278 | NOC575 | NOC | NA |  |  |  | GPON | GPON | API for TDIA Service, combo port, mixed service - Route Mode with/without translation, including uplink port configuration |  | Critical |  | Tejas OEM | EMS | [13 empty] | Applications/Tools | Closed | [8 empty] | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API | Completed & Approved | Closed before june-2025 | Closed after June
2279 | NOC576 | NOC | NA |  |  |  | GPON | GPON | API to restirct/block the PON port to a specific customer |  | Critical |  | Tejas OEM | EMS | 15-Nov-25: OEM confirmed API will be made availble in next release of EMS on March-2026 | [12 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2280 | NOC577 | NOC | NA |  |  |  | GPON | GPON | API to modify the service- ONT, UNI Port, bandwidth, vlan, description, unatgged to tag or vice versa., |  | Critical |  | Tejas OEM | EMS | Duplicate point of 472 - 463 | [12 empty] | Applications/Tools | OPEN |  |  |  | Duplicate | [6 empty] | Open | Open | Open
2281 | NOC578 | NOC | NA |  |  |  | GPON | GPON | PIR not working in route mode |  | Critical |  | Tejas OEM | OLT | Duplicate point of 472 - 407 | [12 empty] | Applications/Tools | OPEN |  |  |  | Duplicate | [6 empty] | Open | Open | Open
2282 | NOC579 | NOC | NA |  |  |  | GPON | GPON | Nokia ONT/3rd party ONT under Tejas OLT Remote access for WAN port |  | Critical |  | Tejas OEM | OLT/ONT | 15-Nov-25: A call will be scheduled with Tejas and Nokia, along with Tfiber for the conclusion of this issue OEM confirmed this feature is not available OEM confirmed this feature is not available 20-Sep-2 | 5:00 | T Fib | er t | eam asked | arrange mee |  | tin | g w |  |  | ith | Tejas, Nokia OEM | Applications/Tools | OPEN |  |  |  |  | to | [5 empty] | Open | Open | Open
2283 | NOC58 | NOC | NA |  |  |  | GPON | OSS | T-NOC Report :: Summary of O&M Cluster OLTs status Monthly |  | Critical | NOT_FEASIBLE | HPSM | Incident Management | [13 empty] | Applications/Tools | OPEN | 0 | Not-Feasible | TRUE | [7 empty] | Open | Open | Open
2284 | NOC580 | NOC | NA |  |  |  | GPON | GPON | Unable to browse Internet when IPV6 configured in wifi ONT |  | Critical |  | Nokia OEM | AMS | [13 empty] | Applications/Tools | Closed | [8 empty] | 2025-07-31 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\472 | Completed & Approved | Closed before june-2025 | Closed after June
2285 | NOC581 | NOC | NA |  |  |  | GPON | GPON | Hybrid Mode of the G-240G-E ONT |  | Critical |  | Nokia OEM | ONT | Duplicate point of 472 - T180 | [12 empty] | Applications/Tools | Closed |  |  |  | Completed | [5 empty] | Artefacts not Required | Open | Open | Open
2286 | NOC582 | NOC | NA |  |  |  | GPON | GPON | Nokia ONT under Nokia OLT Remote access for WAN port |  | Critical |  | Nokia OEM | OLT/ONT | 15-Nov-25: A call will be scheduled with Tejas and Nokia, along with Tfiber for the conclusion of this issue OEM confirmed this feature is not available OEM confirmed this feature is not available 20-Sep-2 | 5:00 | T Fib | er t | eam asked | arrange mee |  | tin | g w |  |  | ith | Tejas, Nokia OEM | Applications/Tools | OPEN |  |  |  |  | to | [5 empty] | Open | Open | Open
2287 | NOC583 | NOC | NA |  |  |  | GPON | GPON | Tejas ONT/3rd party ONT under Nokia OLT Remote access for WAN port |  | Critical |  | Nokia OEM | OLT/ONT | 15-Nov-25:A call will be scheduled with Tejas and Nokia, along with Tfiber for the conclusion of this issue OEM confirmed this feature is not available 20-Sep-25: T Fiber team asked to arrange meeting with | Te | jas, | Noki | a OEM | [8 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2288 | NOC584 | NOC | NA |  |  |  | GPON | GPON | Nokia ONT under Tejas OLT Remote access for WAN port |  | Critical |  | Nokia OEM | OLT/ONT | 15-Nov-25:A call will be scheduled with Tejas and Nokia, along with Tfiber for the conclusion of this issue OEM confirmed this feature is not available 20-Sep-25: T Fiber team asked to arrange meeting with | Te | jas, | Noki | a OEM | [8 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2289 | NOC585 | NOC | NA |  |  |  | GPON | GPON | ONT cosumed count is showing wrong in license page |  | Critical |  | Nokia OEM | AMS | 15-Nov-25 : OEM has shared the plan of action for AMS upgrade. Post discussion, will take the necessary approvals for the implementation To resolve this issue, AMS to be upgraded and plan of action is awai | ted | from | OEM | To resol | this issue, |  | AMS | to |  |  | be | upgraded and plan of action is awaited from OEM 20-Sep-25: Licensing conumption quantity not showing in Nokia AMS for discovered ONTs.Nokia OEM informed to address this issue Nokia AMS software need to be upgraded. As requested by Nokia team required pre-requsuits shared with Nokia OEM.yet to receive upgradation plan from Nokia Team. | Applications/Tools | OPEN |  |  |  |  | ve | [5 empty] | Open | Open | Open
2290 | NOC586 | NOC | NA |  |  |  | GPON | GPON | API and Template for ILL Service - Bridge Mode, including uplink port configuration |  | Critical |  | Nokia OEM | AMS | 15-Nov-25:A call will be scheduled with Tejas and Nokia, along with Tfiber for the conclusion of this issue OEM confirmed API/Template is not available for uplink port configuration | [12 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2291 | NOC587 | NOC | NA |  |  |  | GPON | GPON | API and Template for ILL Service - Route Mode, including uplink port configuration |  | Critical |  | Nokia OEM | AMS | 15-Nov-25:A call will be scheduled with Tejas and Nokia, along with Tfiber for the conclusion of this issue OEM confirmed API/Template is not available for uplink port configuration OEM confirmed API/Templ | ate | is n | ot a | vailable | uplink port |  | co | nfi |  |  | gura | tion | Applications/Tools | OPEN |  |  |  |  | for | [5 empty] | Open | Open | Open
2292 | NOC588 | NOC | NA |  |  |  | GPON | GPON | API and Template for Household Services, including uplink port configuration |  | Critical |  | Nokia OEM | AMS | 15-Nov-25:A call will be scheduled with Tejas and Nokia, along with Tfiber for the conclusion of this issue OEM confirmed API/Template is not available for uplink port configuration OEM confirmed API/Templ | ate | is n | ot a | vailable | uplink port |  | co | nfi |  |  | gura | tion | Applications/Tools | OPEN |  |  |  |  | for | [5 empty] | Open | Open | Open
2293 | NOC589 | NOC | NA |  |  |  | GPON | GPON | API and Template for IPTV services, including uplink port configuration |  | Critical |  | Nokia OEM | AMS | 15-Nov-25:A call will be scheduled with Tejas and Nokia, along with Tfiber for the conclusion of this issue OEM confirmed API/Template is not available for uplink port configuration | [12 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2294 | NOC59 | NOC | NA |  |  |  | GPON | OSS | T-NOC Report :: Summary of O&M Cluster OLTs status (Selective from and to dates) |  | Critical | NOT_FEASIBLE | HPSM | Incident Management | [13 empty] | Applications/Tools | OPEN | 0 | Not-Feasible | TRUE | [7 empty] | Open | Open | Open
2295 | NOC590 | NOC | NA |  |  |  | GPON | GPON | API, Template and configuration for VOIP services, including uplink port configuration |  | Critical |  | Nokia OEM | AMS | 15-Nov-25:A call will be scheduled with Tejas and Nokia, along with Tfiber for the conclusion of this issue OEM confirmed API/Template is not available for uplink port configuration | [12 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2296 | NOC591 | NOC | NA |  |  |  | GPON | GPON | API and Template for GI-BB Service - Bridge Mode, including uplink port configuration |  | Critical |  | Nokia OEM | AMS | 15-Nov-25:A call will be scheduled with Tejas and Nokia, along with Tfiber for the conclusion of this issue OEM confirmed API/Template is not available for uplink port configuration | [12 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2297 | NOC592 | NOC | NA |  |  |  | GPON | GPON | API and Template for GI-BB Service - Route Mode, including uplink port configuration |  | Critical |  | Nokia OEM | AMS | 15-Nov-25:A call will be scheduled with Tejas and Nokia, along with Tfiber for the conclusion of this issue OEM confirmed API/Template is not available for uplink port configuration | [12 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2298 | NOC593 | NOC | NA |  |  |  | GPON | GPON | API to fetch the configured services in AMS, including uplink port configuration |  | Critical |  | Nokia OEM | AMS | 15-Nov-25:A call will be scheduled with Tejas and Nokia, along with Tfiber for the conclusion of this issue OEM confirmed API/Template is not available for uplink port configuration | [12 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2299 | NOC594 | NOC | NA |  |  |  | GPON | GPON | Configuration, API and Template for applying QOS for the different types of services |  | Critical |  | Nokia OEM | AMS | API has to share by OEM | [12 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2300 | NOC595 | NOC | NA |  |  |  | GPON | GPON | API and Template required to provision ONT along with selecting specific UNI port in ONT |  | Critical |  | Nokia OEM | AMS | API has to share by OEM | [12 empty] | Applications/Tools | Closed | [8 empty] | 2025-11-15 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\NOC595 | Closed after 14-Nov-25 | Closed after 14-Nov-25 | Open
2301 | NOC596 | NOC | NA |  |  |  | GPON | GPON | API and Template required to provision ONT with multiple services along with selecting specific UNI port in ONT |  | Critical |  | Nokia OEM | AMS | 15-11-2025: This has been raised with Nokia, had a call for breifing the requirement. Update awaited from Nokia API has to share by OEM | [12 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2302 | NOC597 | NOC | NA |  |  |  | GPON | GPON | API and Template required to provision ONT with same service on all ports |  | Critical |  | Nokia OEM | AMS | 15-11-2025: This has been raised with Nokia, had a call for breifing the requirement. Update awaited from Nokia API has to share by OEM | [12 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2303 | NOC598 | NOC | NA |  |  |  | GPON | GPON | API and Template to configure multiple vlans on single ONT UNI Port |  | Critical |  | Nokia OEM | AMS | 15-11-2025: This has been raised with Nokia, had a call for breifing the requirement. Update awaited from Nokia API has to share by OEM | [12 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2304 | NOC599 | NOC | NA |  |  |  | GPON | GPON | Configuration, API and Template for extedning services to enterprise customers |  | Critical |  | Nokia OEM | AMS | 15-11-2025: This has been raised with Nokia, had a call for breifing the requirement. Update awaited from Nokia API has to share by OEM | [12 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2305 | NOC6 | NOC | NA |  | OSS | OSS | OSS | DC | DC Applications uptime & SLA Weekly |  | Critical |  | HPSM | Incident Management | [13 empty] | Applications/Tools | OPEN | 0 | OPEN | TRUE | [7 empty] | Open | Open | Open
2306 | NOC60 | NOC | NA |  |  |  | GPON | OSS | Router UP - OLT Down cases Daily |  | Critical | COMPLETED | NNMI | NNMI | [13 empty] | Applications/Tools | OPEN | To be updated by Manoj | Completed With Artifacts | FALSE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
2307 | NOC600 | NOC | NA |  |  |  | GPON | GPON | API and Template to verify and enable the PM |  | Critical |  | Nokia OEM | AMS | 15-11-2025: This has been raised with Nokia, had a call for breifing the requirement. Update awaited from Nokia API has to share by OEM | [12 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2308 | NOC601 | NOC | NA |  |  |  | GPON | GPON | API and Template to configure Vlan and Profiles in OLT |  | Critical |  | Nokia OEM | AMS | 15-Nov-25:A call will be scheduled with Tejas and Nokia, along with Tfiber for the conclusion of this issue OEM confirmed API/Template is not available API has to share by OEM | [12 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2309 | NOC602 | NOC | NA |  |  |  | GPON | GPON | Required complete API and Template developer document |  | Critical |  | Nokia OEM | AMS | OEM shared the document of APC template creation but required document for the API attributes | [12 empty] | Applications/Tools | Closed | [8 empty] | 2025-11-15 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\NOC602 | Closed after 14-Nov-25 | Closed after 14-Nov-25 | Open
2310 | NOC603 | NOC | NA |  |  |  | GPON | GPON | API and Template to validate the profiles, vlans available in OLT,ONT |  | Critical |  | Nokia OEM | AMS | API has to share by OEM | [12 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2311 | NOC604 | NOC | NA |  |  |  | GPON | GPON | API and Template to restirct/block the PON port to a specific customer |  | Critical |  | Nokia OEM | AMS | 15-Nov-25:A call will be scheduled with Tejas and Nokia, along with Tfiber for the conclusion of this issue OEM confirmed API/Template is not available API has to share by OEM | [12 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2312 | NOC605 | NOC | NA |  |  |  | GPON | GPON | API and Template to modify the service- ONT, UNI Port, bandwidth, vlan, description, unatgged to tag or vice versa., |  | Critical |  | Nokia OEM | AMS | API has to share by OEM | [12 empty] | Applications/Tools | Closed | [8 empty] | 2025-11-15 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\NOC605 | Closed after 14-Nov-25 | Closed after 14-Nov-25 | Open
2313 | NOC606 | NOC | NA |  |  |  | GPON | GPON | API and Template to configure,modify,suspend,delete the WAN profiles in WiFi ONT |  | Critical |  | Nokia OEM | AMS | 15-Nov-25:A call will be scheduled with Tejas and Nokia, along with Tfiber for the conclusion of this issue OEM confirmed API/Template is not available | [12 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2314 | NOC607 | NOC | NA |  |  |  | GPON | GPON | Verification of the service provisioning templates which are prepared for the different types of services |  | Critical |  | Nokia OEM | AMS | 15-11-2025: This has been raised with Nokia, had a call for breifing the requirement. Update awaited from Nokia API has to share by OEM | [12 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2315 | NOC608 | NOC | NA |  |  |  | GPON | GPON | Verification of the services configured by NSO through Playbook(Cisco Tool) |  | Critical |  | Nokia OEM | AMS | 15-Nov-25: API has to share by OEM | [12 empty] | Applications/Tools | OPEN | [9 empty] | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API to validate the configured Services | Open | Open | Open
2316 | NOC609 | NOC | NA |  |  |  | GPON | GPON | Mapping bandiwdth profiles per vlan in a ONT UNI | 20-Sep-25: As per Nokia OEM, Mapping BW profiles per service BW on ONT Interface.Meeting to be arranged with Nokia OEM | Critical |  | Nokia OEM | OLT/ONT | 15-Nov-25: Update awaited from OEM | [12 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2317 | NOC61 | NOC | NA |  |  |  | GPON | OSS | Router UP - OLT Down cases Weekly |  | Critical | COMPLETED | NNMI | NNMI | [13 empty] | Applications/Tools | OPEN | To be updated by Manoj | Completed With Artifacts | FALSE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
2318 | NOC610 | NOC | NA |  |  |  | GPON | GPON | NOKIA ONT is not supporting for bandwidth Rate Limit configuration On ONT LAN Ethernet port (UNI) when connected under Tejas OLT | 20-Sep-25:Guidelines have to share with all 3 packages to deploy balance scope as Tejas OLT- Tejas ONT and Nokia OLT-Nokia ONT | Critical |  | Nokia OEM | ONT | 15-Nov-25:A call will be scheduled with Tejas and Nokia, along with Tfiber for the conclusion of this issue OEM confirmed Rate Limit is not supported by Nokia ONTs | [12 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2319 | NOC611 | NOC | NA |  |  |  | GPON | GPON | PM Report for 24hrs of OLT,ONT,ONT Eth Port(Bridge/Route), Wifi |  | Critical |  | Nokia OEM | AMS | [13 empty] | Applications/Tools | Closed | [8 empty] | 2025-07-31 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\470 | Completed & Approved | Closed before june-2025 | Closed after June
2320 | NOC612 | NOC | NA |  |  |  | GPON | GPON | Nokia ONT ethernet port status is not updating |  | Critical | DUPLICATE POINT (NOC572) | Nokia OEM | OLT/ONT | Duplicate point of 472 - 432 | [12 empty] | Applications/Tools | OPEN |  |  |  | Duplicate | [6 empty] | Open | Open | Open
2321 | NOC613 | NOC | NA |  |  |  | GPON | GPON | Unable to provide available download bandwidth of PON Port for Nokia devices (Nokia BW Query) |  | Critical |  | Nokia OEM | AMS | Duplicate point of 472 - T175 | [12 empty] | Applications/Tools | OPEN |  |  |  | Duplicate | [6 empty] | Open | Open | Open
2322 | NOC614 | NOC | NA |  | OSS | OSS | All Domain | OSS | EOL and EOS Through inventory Dashboard-Weekly |  | Critical | COMPLETED | HPSM | Asset Manager | [13 empty] | Applications/Tools | OPEN | we dont have dashboard only report is available | Completed With Artifacts | FALSE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
2323 | NOC615 | NOC | NA |  | OSS | OSS | All Domain | OSS | EOL and EOS Through inventory Dashboard-Monthly |  | Critical | COMPLETED | HPSM | Asset Manager | [13 empty] | Applications/Tools | OPEN | we dont have dashboard only report is available | Completed With Artifacts | FALSE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
2324 | NOC616 | NOC | NA |  | OSS | OSS | All Domain | OSS | Infra Server Url Services Intigration |  | Critical | COMPLETED | HPSM | Site scope | [13 empty] | Applications/Tools | OPEN | 0 | Completed With Artifacts | TRUE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
2325 | NOC617 | NOC | NA |  | OSS | OSS | All Domain | OSS | Infra Server Url Services Monitoring |  | Critical | COMPLETED | HPSM | Site scope | [13 empty] | Applications/Tools | OPEN | 0 | Completed With Artifacts | TRUE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
2326 | NOC618 | NOC | NA |  | OSS | OSS | All Domain | OSS | Infra Server Url Services Reporting |  | Critical | COMPLETED | HPSM | Site scope | [13 empty] | Applications/Tools | OPEN | 0 | Completed With Artifacts | TRUE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
2327 | NOC619 | NOC | NA |  | OSS | OSS | All Domain | OSS | real-time information |  | Critical | COMPLETED | HPSM | Site scope | 09-09-2025: Ticket, status, Inventory, Alarms, etc are available in real time | [12 empty] | Applications/Tools | OPEN | 09-09-2025: Ticket, status, Inventory, Alarms, etc are available in real time | Completed With Artifacts | TRUE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
2328 | NOC62 | NOC | NA |  |  |  | GPON | OSS | Router UP - OLT Down cases Monthly |  | Critical | COMPLETED | NNMI | NNMI | [13 empty] | Applications/Tools | OPEN | To be updated by Manoj | Completed With Artifacts | FALSE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
2329 | NOC620 | NOC | NA |  | OSS | OSS | All Domain | OSS | Health of the Performance for Traffic |  | Critical | COMPLETED | HPSM | NNM iSPI | [13 empty] | Applications/Tools | OPEN | 0 | Completed With Artifacts | TRUE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
2330 | NOC621 | NOC | NA |  | OSS | OSS | All Domain | OSS | Analyze Flow Packets |  | Critical | COMPLETED | HPSM | NNM iSPI | [13 empty] | Applications/Tools | OPEN | 0 | Completed With Artifacts | TRUE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
2331 | NOC622 | NOC | NA |  | OSS | OSS | All Domain | OSS | Performance for Traffic Maps |  | Critical | COMPLETED | HPSM | NNM iSPI | [13 empty] | Applications/Tools | OPEN | 0 | Completed With Artifacts | TRUE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
2332 | NOC623 | NOC | NA |  |  |  | NSO | NSO | NSO Intigration for POC Locations LCO,RMSO & MSO |  | Critical |  | NSO | SCCM/Playbook | 29-dec-2025: Need discussion.Network Team | [12 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2333 | NOC624 | NOC | NA |  |  |  | NSO | NSO | Video customer inventory , Internet customer inventory , Bandwidth allocation inventory count etc., |  | Critical |  | NSO | SCCM/Playbook | 29-dec-2025: Need discussion.Network Team | [12 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2334 | NOC625 | NOC | NA |  |  |  | NSO | NSO | NSO Intigration for Live Locations LCO,RMSO & MSO |  | Critical |  | NSO | SCCM/Playbook | 29-dec-2025: Need discussion.Network Team | [12 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2335 | NOC626 | NOC | NA |  |  |  | NSO | NSO | Video customer inventory , Internet customer inventory , Bandwidth allocation inventory count etc., |  | Critical | DUPLICATE POINT (NOC624) | NSO | SCCM/Playbook | 29-dec-2025: Need discussion.Network Team | [12 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2336 | NOC627 | NOC | NA |  |  |  | BSS | BSS | TFiber BSS to be integrated with Partners SMS & BSS (LCO, RMSO & MSO etc..) for POC Locations |  | Critical | OPEN | KNOT | CRM | [13 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2337 | NOC628 | NOC | NA |  |  |  | BSS | BSS | After completion of POC Same solution shall be implemented for All Household of Telangana (TFiber BSS to be integrated with all other Partners SMS & BSS for Live (LCO , RMSO & MSO etc..)) |  | Critical | OPEN | KNOT | CRM | [13 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2338 | NOC629 | NOC | NA |  |  |  | BSS | BSS | New Customer order HouseHolds |  | Critical | OPEN | KNOT | CRM | [13 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2339 | NOC63 | NOC | NA |  |  |  | GPON | OSS | Router UP - OLT Down cases (Selective from and to dates) |  | Critical | COMPLETED | NNMI | NNMI | [13 empty] | Applications/Tools | OPEN | To be updated by Manoj | Completed With Artifacts | FALSE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
2340 | NOC630 | NOC | NA |  |  |  | BSS | BSS | Existing customer alignment for order |  | Critical | OPEN | KNOT | CRM | DUPLICATE POINT (NOC630) | [12 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2341 | NOC631 | NOC | NA |  |  |  | BSS | BSS | Customer service ID allocation |  | Critical | OPEN | KNOT | CRM | DUPLICATE POINT (NOC631) | [12 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2342 | NOC632 | NOC | NA |  |  |  | BSS | BSS | Activation & Deactivation update to BSS |  | Critical | OPEN | KNOT | CRM | DUPLICATE POINT (NOC632) | [12 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2343 | NOC633 | NOC | NA |  |  |  | BSS | BSS | New customer package & billing |  | Critical | OPEN | KNOT | Billing | DUPLICATE POINT (NOC633) | [12 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2344 | NOC634 | NOC | NA |  |  |  | BSS | BSS | Existing customer renewal & package modification update |  | Critical | OPEN | KNOT | Billing | DUPLICATE POINT (NOC634) | [12 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2345 | NOC635 | NOC | NA |  |  |  | BSS | BSS | Customer address change intigration |  | Critical | OPEN | KNOT | Billing | DUPLICATE POINT (NOC635) | [12 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2346 | NOC636 | NOC | NA |  |  |  | BSS | BSS | Customer Discount update to BSS |  | Critical | OPEN | KNOT | Billing | DUPLICATE POINT (NOC636) | [12 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2347 | NOC637 | NOC | NA |  |  |  | BSS | BSS | Partner Dashboard Number of customers through TFiber |  | Critical | OPEN | BSS | CRM | [13 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2348 | NOC638 | NOC | NA |  |  |  | BSS | BSS | Partner Dashboard Uptime SLA customers through TFiber |  | Critical | OPEN | HPSM | Incident Management | [13 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2349 | NOC639 | NOC | NA |  |  |  | BSS | BSS | Partner Dashboard Access |  | Critical | OPEN | BSS | CRM | [13 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2350 | NOC64 | NOC | NA |  |  |  | GPON | OSS | ONTs down more than 8 hrs. list Daily |  | Critical | COMPLETED | OSS Dashboards | UOC | 09-09-2025: Aging Report available, Stabilization Required | [12 empty] | Applications/Tools | OPEN | we have only live data | Completed With Artifacts | FALSE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
2351 | NOC640 | NOC | NA |  |  |  | BSS | BSS | TFiber BSS to be Implemented for all GI of Telangana |  | Critical | OPEN | KNOT | CRM | [13 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2352 | NOC641 | NOC | NA |  |  |  | BSS | BSS | After completion of POC Same solution shall be implemented for All Government Institutions of Telangana (TFiber BSS to be Utilized for go Live ) |  | Critical | OPEN | KNOT | CRM | [13 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2353 | NOC642 | NOC | NA |  |  |  | BSS | BSS | New Customer order GI |  | Critical | OPEN | KNOT | CRM | [13 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2354 | NOC643 | NOC | NA |  |  |  | BSS | BSS | Existing customer alignment for order |  | Critical | DUPLICATE POINT (NOC630) | KNOT | CRM | DUPLICATE POINT (NOC630) | [12 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2355 | NOC644 | NOC | NA |  |  |  | BSS | BSS | Customer service ID allocation |  | Critical | DUPLICATE POINT (NOC631) | KNOT | CRM | DUPLICATE POINT (NOC631) | [12 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2356 | NOC645 | NOC | NA |  |  |  | BSS | BSS | Activation & Deactivation update to BSS |  | Critical | DUPLICATE POINT (NOC632) | KNOT | CRM | DUPLICATE POINT (NOC632) | [12 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2357 | NOC646 | NOC | NA |  |  |  | BSS | BSS | New customer package & billing |  | Critical | DUPLICATE POINT (NOC633) | KNOT | Billing | DUPLICATE POINT (NOC633) | [12 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2358 | NOC647 | NOC | NA |  |  |  | BSS | BSS | Existing customer renewal & package modification update |  | Critical | DUPLICATE POINT (NOC634) | KNOT | Billing | DUPLICATE POINT (NOC634) | [12 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2359 | NOC648 | NOC | NA |  |  |  | BSS | BSS | Customer address change intigration |  | Critical | DUPLICATE POINT (NOC635) | KNOT | Billing | DUPLICATE POINT (NOC635) | [12 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2360 | NOC649 | NOC | NA |  |  |  | BSS | BSS | Customer Discount update to BSS |  | Critical | DUPLICATE POINT (NOC636) | KNOT | Billing | DUPLICATE POINT (NOC636) | [12 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2361 | NOC65 | NOC | NA |  |  |  | GPON | OSS | ONTs down more than 8 hrs. list Weekly |  | Critical | COMPLETED | OSS Dashboards | UOC | 09-09-2025: Aging Report available, Stabilization Required | [12 empty] | Applications/Tools | OPEN | we have only live data | Completed With Artifacts | FALSE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
2362 | NOC650 | NOC | NA |  |  |  | BSS | BSS | Customer Dashboard Number of customers through TFiber |  | Critical | OPEN | BSS | CRM | DUPLICATE POINT (NOC650) | [12 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2363 | NOC651 | NOC | NA |  |  |  | BSS | BSS | Customer Dashboard Uptime SLA customers through TFiber |  | Critical | OPEN | HPSM | Incident Management | DUPLICATE POINT (NOC651) | [12 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2364 | NOC652 | NOC | NA |  |  |  | BSS | BSS | Customer Dashboard Access |  | Critical | OPEN | BSS | CRM | DUPLICATE POINT (NOC652) | [12 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2365 | NOC653 | NOC | NA |  |  |  | BSS | BSS | TFiber BSS to be Implemented for all Enterprice P2p & P2MP services in Telangana |  | Critical | OPEN | KNOT | CRM | [13 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2366 | NOC654 | NOC | NA |  |  |  | BSS | BSS | After completion of POC Same solution shall be implemented for All Enterprice P2p & P2MP services in Telangana (TFiber BSS to be Utilized for go Live ) |  | Critical | OPEN | KNOT | CRM | [13 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2367 | NOC655 | NOC | NA |  |  |  | BSS | BSS | New Customer order Enterprice |  | Critical | OPEN | KNOT | CRM | [13 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2368 | NOC656 | NOC | NA |  |  |  | BSS | BSS | Existing customer alignment for order |  | Critical | DUPLICATE POINT (NOC630) | KNOT | CRM | DUPLICATE POINT (NOC630) | [12 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2369 | NOC657 | NOC | NA |  |  |  | BSS | BSS | Customer service ID allocation |  | Critical | DUPLICATE POINT (NOC631) | KNOT | CRM | DUPLICATE POINT (NOC631) | [12 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2370 | NOC658 | NOC | NA |  |  |  | BSS | BSS | Activation & Deactivation update to BSS |  | Critical | DUPLICATE POINT (NOC632) | KNOT | CRM | DUPLICATE POINT (NOC632) | [12 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2371 | NOC659 | NOC | NA |  |  |  | BSS | BSS | New customer package & billing |  | Critical | DUPLICATE POINT (NOC633) | KNOT | Billing | DUPLICATE POINT (NOC633) | [12 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2372 | NOC66 | NOC | NA |  |  |  | GPON | OSS | ONTs down more than 8 hrs. list Monthly |  | Critical | COMPLETED | OSS Dashboards | UOC | [13 empty] | Applications/Tools | OPEN | we have only live data | Completed With Artifacts | FALSE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
2373 | NOC660 | NOC | NA |  |  |  | BSS | BSS | Existing customer renewal & package modification update |  | Critical | DUPLICATE POINT (NOC634) | KNOT | Billing | DUPLICATE POINT (NOC634) | [12 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2374 | NOC661 | NOC | NA |  |  |  | BSS | BSS | Customer address change intigration |  | Critical | DUPLICATE POINT (NOC635) | KNOT | Billing | DUPLICATE POINT (NOC635) | [12 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2375 | NOC662 | NOC | NA |  |  |  | BSS | BSS | Customer Discount update to BSS |  | Critical | DUPLICATE POINT (NOC636) | KNOT | Billing | DUPLICATE POINT (NOC636) | [12 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2376 | NOC663 | NOC | NA |  |  |  | BSS | BSS | Customer Dashboard Number of customers through TFiber |  | NON-Critical | DUPLICATE POINT (NOC650) | BSS | CRM | DUPLICATE POINT (NOC650) | [12 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2377 | NOC664 | NOC | NA |  |  |  | BSS | BSS | Customer Dashboard Uptime SLA customers through TFiber |  | NON-Critical | DUPLICATE POINT (NOC651) | HPSM | Incident Management | DUPLICATE POINT (NOC651) | [12 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2378 | NOC665 | NOC | NA |  |  |  | BSS | BSS | Customer Dashboard Access |  | NON-Critical | DUPLICATE POINT (NOC652) | BSS | CRM | DUPLICATE POINT (NOC652) | [12 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2379 | NOC666 | NOC | NA |  |  |  | NSO | Service Solutions | GI-BB |  | Critical |  | NSO | SCCM/Playbook | 29-12-2025: Completed and Tested | [12 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2380 | NOC667 | NOC | NA |  |  |  | NSO | Service Solutions | T-CELL |  | Critical |  | NSO | SCCM/Playbook | 29-dec-2025: Need discussion.Network Team | [12 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2381 | NOC668 | NOC | NA |  |  |  | NSO | Service Solutions | HH Triple Play (Internet, IPTV, VoIP) |  | Critical |  | NSO | SCCM/Playbook | 29-dec-2025: Need discussion.Network Team | [12 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2382 | NOC669 | NOC | NA |  |  |  | NSO | Service Solutions | CCTV Unicast |  | Critical |  | NSO | SCCM/Playbook | 29-dec-2025: Need discussion.Network Team | [12 empty] | Applications/Tools | OPEN | [9 empty] | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\Centrailzed CCTV Surveillance Monitoring over T-Fiber Network-Solution Doucment_Initial Draft V1.0 - T189.pdf | Open | Open | Open
2383 | NOC67 | NOC | NA |  |  |  | GPON | OSS | ONTs down more than 8 hrs. list (Selective from and to dates) |  | Critical | COMPLETED | OSS Dashboards | UOC | [13 empty] | Applications/Tools | OPEN | we have only live data | Completed With Artifacts | FALSE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
2384 | NOC670 | NOC | NA |  |  |  | NSO | Service Solutions | CCTV Multicast |  | Critical |  | NSO | SCCM/Playbook | 29-dec-2025: Need discussion.Network Team | [12 empty] | Applications/Tools | OPEN | [9 empty] | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\CCTV Multicast Solution LLD V1.2 - T190.pdf | Open | Open | Open
2385 | NOC671 | NOC | NA |  |  |  | NSO | Service Solutions | T-DIA (ILL) |  | Critical |  | NSO | SCCM/Playbook | 29-12-2025: Completed and Tested | [12 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2386 | NOC672 | NOC | NA |  |  |  | NSO | Service Solutions | L2VPN |  | Critical |  | NSO | SCCM/Playbook | 29-dec-2025: Need discussion.Network Team | [12 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2387 | NOC673 | NOC | NA |  |  |  | NSO | Service Solutions | L3VPN |  | Critical |  | NSO | SCCM/Playbook | 29-dec-2025: Need discussion.Network Team | [12 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2388 | NOC674 | NOC | NA |  |  |  | NSO | Service Solutions | TVPN - Rythu Vedika |  | Critical |  | NSO | SCCM/Playbook | 29-dec-2025: Need discussion.Network Team | [12 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2389 | NOC675 | NOC | NA |  |  |  | NSO | Service Solutions | TVPN - DHQ to SHQ Connectivity |  | Critical |  | NSO | SCCM/Playbook | 29-dec-2025: Need discussion.Network Team | [12 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2390 | NOC676 | NOC | NA |  |  |  | NSO | Service Solutions | TVPN - MRO Office Connectivity |  | Critical |  | NSO | SCCM/Playbook | 29-dec-2025: Need discussion.Network Team | [12 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2391 | NOC677 | NOC | NA |  |  |  | NSO | Service Solutions | SDC/TSWAN integration |  | Critical |  | NSO | SCCM/Playbook | 29-dec-2025: Need discussion.Network Team | [12 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2392 | NOC678 | NOC | NA |  |  |  | NSO | Service Solutions | TSP NNI |  | Critical |  | NSO | SCCM/Playbook | 29-dec-2025: Need discussion.Network Team | [12 empty] | Applications/Tools | OPEN | [10 empty] | Open | Open | Open
2393 | NOC68 | NOC | NA |  |  |  | GPON | OSS | Mandal OLT down more than 6 hrs. list Daily |  | Critical | COMPLETED | OSS Dashboards | UOC | 09-09-2025: Aging Report available, Stabilization Required | [12 empty] | Applications/Tools | OPEN | we have only live data | Completed With Artifacts | FALSE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
2394 | NOC69 | NOC | NA |  |  |  | GPON | OSS | Mandal OLT down more than 6 hrs. list Weekly |  | Critical | COMPLETED | OSS Dashboards | UOC | 09-09-2025: Aging Report available, Stabilization Required | [12 empty] | Applications/Tools | OPEN | we have only live data | Completed With Artifacts | FALSE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
2395 | NOC7 | NOC | NA |  | OSS | OSS | OSS | DC | DC Applications uptime & SLA Monthly |  | Critical |  | HPSM | Incident Management | [13 empty] | Applications/Tools | OPEN | 0 | OPEN | TRUE | [7 empty] | Open | Open | Open
2396 | NOC70 | NOC | NA |  |  |  | GPON | OSS | Mandal OLT down more than 6 hrs. list Monthly |  | Critical | COMPLETED | OSS Dashboards | UOC | [13 empty] | Applications/Tools | OPEN | we have only live data | Completed With Artifacts | FALSE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
2397 | NOC71 | NOC | NA |  |  |  | GPON | OSS | Mandal OLT down more than 6 hrs. list (Selective from and to dates) |  | Critical | COMPLETED | OSS Dashboards | UOC | [13 empty] | Applications/Tools | OPEN | we have only live data | Completed With Artifacts | FALSE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
2398 | NOC72 | NOC | NA |  |  |  | GPON | OSS | HH_PM Utilization Dump _PKGA_PKGC Daily |  | NON-Critical | COMPLETED | NNMI | NPS | [13 empty] | Applications/Tools | OPEN | 0 | Completed With Artifacts | TRUE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
2399 | NOC73 | NOC | NA |  |  |  | GPON | OSS | HH_PM Utilization Dump _PKGA_PKGC Weekly |  | NON-Critical | NOT_FEASIBLE | NNMI | NPS | [13 empty] | Applications/Tools | OPEN | 0 | Not-Feasible | TRUE | [7 empty] | Open | Open | Open
2400 | NOC74 | NOC | NA |  |  |  | GPON | OSS | HH_PM Utilization Dump _PKGA_PKGC Monthly |  | NON-Critical | COMPLETED | NNMI | NPS | [13 empty] | Applications/Tools | OPEN | 0 | Completed With Artifacts | TRUE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
2401 | NOC75 | NOC | NA |  |  |  | GPON | OSS | HH_PM Utilization Dump _PKGA_PKGC (Selective from and to dates) |  | NON-Critical | NOT_FEASIBLE | NNMI | NPS | [13 empty] | Applications/Tools | OPEN | 0 | Not-Feasible | TRUE | [7 empty] | Open | Open | Open
2402 | NOC76 | NOC | NA |  |  |  | GPON | OSS | Summary of Lit-up GPs Status_8895 Daily |  | NON-Critical | DUPLICATE POINT | HPSM | Incident Management | DUPLICATE POINT | [12 empty] | Applications/Tools | OPEN |  | Duplicate | FALSE | [6 empty] | Artefacts to be uploaded | Open | Open | Open
2403 | NOC77 | NOC | NA |  |  |  | GPON | OSS | Summary of Lit-up GPs Status_8895 Weekly |  | NON-Critical | DUPLICATE POINT | HPSM | Incident Management | DUPLICATE POINT | [12 empty] | Applications/Tools | OPEN |  | Duplicate | FALSE | [6 empty] | Artefacts to be uploaded | Open | Open | Open
2404 | NOC78 | NOC | NA |  |  |  | GPON | OSS | Summary of Lit-up GPs Status_8895 Monthly |  | NON-Critical | DUPLICATE POINT | HPSM | Incident Management | DUPLICATE POINT | [12 empty] | Applications/Tools | OPEN |  | Duplicate | FALSE | [6 empty] | Artefacts to be uploaded | Open | Open | Open
2405 | NOC79 | NOC | NA |  |  |  | GPON | OSS | Summary of Lit-up GPs Status_8895 (Selective from and to dates) |  | Critical | DUPLICATE POINT | HPSM | Incident Management | DUPLICATE POINT | [12 empty] | Applications/Tools | OPEN |  | Duplicate | FALSE | [6 empty] | Artefacts to be uploaded | Open | Open | Open
2406 | NOC8 | NOC | NA |  | OSS | OSS | OSS | DC | DC Applications uptime & SLA (Selective from and to dates) |  | Critical |  | HPSM | Incident Management | [13 empty] | Applications/Tools | OPEN | 0 | Not-Feasible | TRUE | [7 empty] | Open | Open | Open
2407 | NOC80 | NOC | NA |  |  |  | GPON | OSS | GPON OLT TT trend dashboard Daily |  | Critical | COMPLETED | HPSM | Incident Management | [13 empty] | Applications/Tools | OPEN | 0 | Completed With Artifacts | TRUE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
2408 | NOC81 | NOC | NA |  |  |  | GPON | OSS | GPON OLT TT trend dashboard Weekly |  | Critical | COMPLETED | HPSM | Incident Management | [13 empty] | Applications/Tools | OPEN | 0 | Completed With Artifacts | TRUE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
2409 | NOC82 | NOC | NA |  |  |  | GPON | OSS | GPON OLT TT trend dashboard Monthly |  | Critical | COMPLETED | HPSM | Incident Management | [13 empty] | Applications/Tools | OPEN | 0 | Completed With Artifacts | TRUE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
2410 | NOC83 | NOC | NA |  |  |  | GPON | OSS | GPON OLT TT trend dashboard (Selective from and to dates) |  | Critical | COMPLETED | HPSM | Incident Management | [13 empty] | Applications/Tools | OPEN | 0 | Completed With Artifacts | TRUE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
2411 | NOC84 | NOC | NA |  |  |  | GPON | OSS | GPON ONT TT trend dashboard Daily |  | Critical | COMPLETED | HPSM | Incident Management | [13 empty] | Applications/Tools | OPEN | 0 | Completed With Artifacts | TRUE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
2412 | NOC85 | NOC | NA |  |  |  | GPON | OSS | GPON ONT TT trend dashboard Weekly |  | Critical | COMPLETED | HPSM | Incident Management | [13 empty] | Applications/Tools | OPEN | 0 | Completed With Artifacts | TRUE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
2413 | NOC86 | NOC | NA |  |  |  | GPON | OSS | GPON ONT TT trend dashboard Monthly |  | Critical | COMPLETED | HPSM | Incident Management | [13 empty] | Applications/Tools | OPEN | 0 | Completed With Artifacts | TRUE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
2414 | NOC87 | NOC | NA |  |  |  | GPON | OSS | GPON ONT TT trend dashboard (Selective from and to dates) |  | Critical | COMPLETED | HPSM | Incident Management | [13 empty] | Applications/Tools | OPEN | 0 | Completed With Artifacts | TRUE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
2415 | NOC88 | NOC | NA |  |  |  | GPON | OSS | POP uptime_ GP Mandal and Zonal Daily |  | Critical | COMPLETED | HPSM | Incident Management | [13 empty] | Applications/Tools | OPEN | availablity | Completed With Artifacts | FALSE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
2416 | NOC89 | NOC | NA |  |  |  | GPON | OSS | POP uptime_ GP Mandal and Zonal Weekly |  | Critical | NOT_FEASIBLE | HPSM | Incident Management | [13 empty] | Applications/Tools | OPEN | 0 | Not-Feasible | TRUE | [7 empty] | Open | Open | Open
2417 | NOC9 | NOC | NA |  | OSS | OSS | OSS | DC | DC Passive infra uptime & SLA Daily |  | Critical |  | HPSM | Incident Management | [13 empty] | Applications/Tools | OPEN | 0 | Completed With Artifacts | TRUE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
2418 | NOC90 | NOC | NA |  |  |  | GPON | OSS | POP uptime_ GP Mandal and Zonal Monthly |  | Critical | COMPLETED | HPSM | Incident Management | [13 empty] | Applications/Tools | OPEN | 0 | Completed With Artifacts | TRUE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
2419 | NOC91 | NOC | NA |  |  |  | GPON | OSS | POP uptime_ GP Mandal and Zonal (Selective from and to dates) |  | Critical | NOT_FEASIBLE | HPSM | Incident Management | [13 empty] | Applications/Tools | OPEN | 0 | Not-Feasible | TRUE | [7 empty] | Open | Open | Open
2420 | NOC92 | NOC | NA |  |  |  | GPON | OSS | Weekly BW utilization Supporting data Daily |  | NON-Critical | COMPLETED | OSS Dashboards | PMS(UOC) | [13 empty] | Applications/Tools | Closed | 0 | Completed With Artifacts | TRUE | [5 empty] | 2025-11-18 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\OSS\52 Artefcats_18112025 | Closed after 14-Nov-25 | Closed after 14-Nov-25 | Completed but Verification undrer Process
2421 | NOC93 | NOC | NA |  |  |  | GPON | OSS | Weekly BW utilization Supporting data Weekly |  | NON-Critical | NOT_FEASIBLE | OSS Dashboards | PMS(UOC) | [13 empty] | Applications/Tools | OPEN | 0 | Not-Feasible | TRUE | [7 empty] | Open | Open | Open
2422 | NOC94 | NOC | NA |  |  |  | GPON | OSS | Weekly BW utilization Supporting data Monthly |  | NON-Critical | COMPLETED | OSS Dashboards | PMS(UOC) | [13 empty] | Applications/Tools | Closed | 0 | Completed With Artifacts | TRUE | [5 empty] | 2025-11-18 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\OSS\52 Artefcats_18112025 | Closed after 14-Nov-25 | Closed after 14-Nov-25 | Completed but Verification undrer Process
2423 | NOC95 | NOC | NA |  |  |  | GPON | OSS | Weekly BW utilization Supporting data (Selective from and to dates) |  | NON-Critical | NOT_FEASIBLE | OSS Dashboards | PMS(UOC) | [13 empty] | Applications/Tools | OPEN | 0 | Not-Feasible | TRUE | [7 empty] | Open | Open | Open
2424 | NOC96 | NOC | NA |  |  |  | GPON | OSS | T-NOC Report :: Migrated & Duplicated GPs still available both Tejas EMS & Nokia AMS Daily |  | NON-Critical | COMPLETED | HPSM | Incident Management | 09-09-2025: It has to handle manuaaly by downloading report | [12 empty] | Applications/Tools | OPEN | Live data is there .......and dublicate is not there and it is inventory do not have weekly daily monthly and selective dates | Completed With Artifacts | FALSE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
2425 | NOC97 | NOC | NA |  |  |  | GPON | OSS | T-NOC Report :: Migrated & Duplicated GPs still available both Tejas EMS & Nokia AMS Weekly |  | NON-Critical | NOT_FEASIBLE | HPSM | Incident Management | [13 empty] | Applications/Tools |  | Live data is there .......and dublicate is not there and it is inventory do not have weekly daily monthly and selective dates | Completed With Artifacts | FALSE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
2426 | NOC98 | NOC | NA |  |  |  | GPON | OSS | T-NOC Report :: Migrated & Duplicated GPs still available both Tejas EMS & Nokia AMS Monthly |  | NON-Critical | COMPLETED | HPSM | Incident Management | 09-09-2025: It has to handle manuaaly by downloading report | [12 empty] | Applications/Tools | OPEN | Live data is there .......and dublicate is not there and it is inventory do not have weekly daily monthly and selective dates | Completed With Artifacts | FALSE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
2427 | NOC99 | NOC | NA |  |  |  | GPON | OSS | T-NOC Report :: Migrated & Duplicated GPs still available both Tejas EMS & Nokia AMS (Selective from and to dates) |  | NON-Critical | COMPLETED | HPSM | Incident Management | 09-09-2025: It has to handle manuaaly by downloading report | [12 empty] | Applications/Tools | OPEN | Live data is there .......and dublicate is not there and it is inventory do not have weekly daily monthly and selective dates | Completed With Artifacts | FALSE | [7 empty] | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process
2428 | T2A | 472 | NA |  |  |  | Security & Regulatory Compliance | Security | Ciena to comply the password policy for MCP and field nodes, though Alepo AAA. |  |  | Open |  |  | 28-Nov-25: To discuss with mr Sanjay to get clarifications on the points. Password managment policy for ciena need to be finalised and to be approved by authority prior implentations | [12 empty] | Security | OPEN | [10 empty] | Open | Open | Open
`

## LLD
LLD Action Points | NSO Status | NSO Comments(10/03/2026) | Review TNOC (09/03/2026) Comments | Owner | Status
1. TCell P2p (P2Mp covered TCELL p2p product to be included). | Completed | Configuration can be added if available | Use test lab for configuration on 2 routers (MAG,GAC) | Mahesh & Jyothi | Done
2. GI ILL (configuration concept available but not covered as product Automation list). | Completed |  |  | Mahesh & Jyothi | Done
` | Inprogress |  | Sayyad:Alternate solution work is in progress suggested by Tfiber(In 3 days will complete this) | Mahesh & Jyothi | Hold From Sayyad
4. ONT Bridge Mode (DHCP to check). | Inprogress |  | Sayyad:when ONT in bridge mode DHCP will not be released by ONT, | Mahesh & Jyothi | Hold From Sayyad
5. DWDM/OTN product not covered (Low level to Include). | Completed | Refer document sent by ritik | CIENA testing not possible only information can be provided because we dont have ciena on test lab for OADM and OTN | Mahesh & Jyothi | Done
6. Re-Try and provision mechanism parameter to check , number of retries. | How many times can we re-provision | NSO Team | NSO Team 8/5/2026 : read nso document | Mahesh & Jyothi | Hold NSO
7. RFS to be discussed ( Node reachability vs TFiber OWN Connectivity). | Need Clarity | NSO Team | NSO 8/5/2026 : read nso document Initially Tfiber has given the matrics for RFS however it will be taken care in the feasibility. | Mahesh & Jyothi | Hold NSO
8. Zone also can be included for service delivery. | Need Clarity | As of now No Service Delivery in Zone | As of now No at present no service has been provided from zonal(ZCR) however POC can be performed and demonstrated. | Mahesh & Jyothi
9. Additionally Second configuration of PON port not working to be resolved while already existing customer is in use, We cant go live without this option. This was working when Cisco has done the Demo now its not working. | Completed |  | already done each olt port has 64 connectivities, with splitter given access to customers. | Mahesh & Jyothi | Jayant sir
10. ONT LAN Ports unshut while configuration done based on number of services & requirement. | Completed | Refer document sent by Sayyad | Sayyad:It is a part of existing service provision api's | Mahesh & Jyothi | Done
11. NSO Vlan asignment models. | Completed | Ok | Ok | Mahesh & Jyothi | Done
12. IP Pool asignment models. | Completed | Check GI-BB & TDIA | GI-BB & TDIA | Mahesh & Jyothi | Done
13. IPv6 provisioning for GI delivery to include. | Completed | Provide service delivery IP not the network.Once IPV6 is tested come and discuss with govind sir | Provide service delivery IP not the network.Once IPV6 is tested come and discuss with govind sir | Mahesh & Jyothi | Done
14. Traffic priority for Qos in GPON not covered. | Completed | QoS Profile OLT OR ONT DONE |  | Mahesh & Jyothi | Done
NOTE: Configuration for all Points : Either NSO or Network
In Entire documentation there is no configuration.

## Sheet3 (hidden)
Total Open Points | Closure Review Pending | Duplicate | Not Feasible | WIP
63 | 23 | 6 | 4 | 30

## 472 Deailed Sheet (hidden)
Slno | UniqueID | Category | Meeting Date | Priority | Ramana | Ramana-Domain | Domain | Sub-Domain | Action Point | Impact | Priority | Baseline Status | xx | Application | Module | Remarks | Remarks | Organization | Owner | Owner(L&T) | Target Date to Complete | Open | Revised Status (L&T) As on 18-Sep-2025 | Approved BY (TF) | Approval Date(TF) | Link of evidences | R | S | T | U | V | W | X | Tfiber-Cat | Derived Status (L&T) | OSS | OSS Remarks | Ramana Remarks as on 19-Sep-2025 | T Fiber Appoved Date | Artefacts | Target Date | Qty | Ramana-Remarks | Updated on 13-Oct-2025
1 | T1 | 472 | NA |  |  |  | Security & Regulatory Compliance | Configuration | Integration testing of All supported devices is complete and adding all the devices is underway. |  |  | Open |  |  |  |  | what ever request has come all are integrated with ISE , any new device request comes same will be added . Also Aleppo PO get relaesed for ADintegration , it will also get integrated with AD. |  |  | Sarmendra |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | 472Security & Regulatory Compliance | Security | OPEN | [6 empty] | 1 | Open | Open
2 | T2 | 472 | NA |  |  |  | DWDM | Integration with Alepo | RADIUS Configuration Testing on Ciena Node & EMS (MCP) |  |  | Colosed | [7 empty] | Suresh Kumar |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-05-06 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\DWDM\Artefact - T106 | [6 empty] | 472DWDM | DWDM | CLOSED |  |  |  | 2025-05-06 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\DWDM\Artefact - T106 |  | 1 | Completed & Approved | Closed before june-2025
3 | T3 | 472 | NA |  |  |  | Security & Regulatory Compliance | Integration | Accouting data from Ciena MCP and field nodes to be captured in Alepo AAA |  | Critical | Open |  |  |  |  | MCP upgradation is in pipeline . same will be completed by 25 Sep 2025 |  |  | Sarmendra |  | Open | WIP | [9 empty] | 472Security & Regulatory Compliance | Security | OPEN | [6 empty] | 1 | Open | Open
4 | T3 | 472 | NA |  |  |  | DWDM | Integration with Alepo | TACACS+/Radius testing for AAA on ciena node |  |  | Open |  |  |  |  | 20-09-2025: 8.1 MCP software Patch upgradation will be completed by 27-Sep-25, After completetion of upgrdation AAA functionalities will be tested for ciena devices by using radius 13-09-25:MCP upgradation is in progress, will be able to check the logs by next week 28-08-2025: Activity is in progress, target to complete by 25th Sep'25 Authentication and Authorization tested and found OK for Node and MCP. 19-08-2025: Due to issue in disk partition and file type of storage, activity is not started 10-08-2025: OEM confirmation recieved and activity is planned from 18th August'25. 05-July-2025: DC OSS to DR MCP communication is through now, need to integrate and test before activity 12-July-2025: DC OSS to DR MCP integration testing done. Alarms and Autoticketing functioning as expected. Upgradation activity will be scheduled as per OEM confirmation, Target date - 30-07-25 26-July-2025: Schedule awaited from OEM 30-June-2025: DC OSS to DR MCP connectivity to be extended for PE approval, WIP. Target date - 30-07-25 15-06-25: Targeting to close the upgradation by month end, 30-06-25 30-05-2025: Accounting issue resolved in latest MCP version, verified in 8.2 Ver (Node logs are now capturing in MCP). Upgradation schedule awaited from Teleindia for our MCP from 7.1-P02 5/21/2025: Correlation to identified to find the user logged in at the specific time 28APR'25: As discussed with Sanjay sir, if user id not avaialble pls. try for correlation with IP. Some how Correlation to be done. In Accounting, Node and MCP logs are successfully reporting in Alepo with below limitation. Node Logs - Active profile name (ADMIN/RADIUS) is displayed against User ID (Ciena confirmed it is as per design no changes are possible) | L&T |  | Suresh Kumar |  | Open | WIP | [9 empty] | 472DWDM | DWDM | OPEN | [6 empty] | 1 | Open | Open
5 | T4 | 472 | NA |  |  |  | Security & Regulatory Compliance | Security | Alepo confirmed that Alepo AAA supports TACACS, Alepo to test Nokia and Ciena nodes integration on TACACS , with supporting artefacts of testing. 1.TACACS Testing with Tejas, Nokia, Ciena 2. Alepo Testing with Tejas, Nokia and Ciena |  |  | Open |  |  |  |  | 1.TACACS Testing with Tejas, Nokia, Ciena completed 2. Alepo Testing with Tejas, Nokia and Ciena |  |  | Sarmendra |  |  | CLOSURE REVIEW PENDING | [9 empty] | 472Security & Regulatory Compliance | Security | OPEN |  |  |  |  | Artefacts to be Submitted |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
6 | T5 | 472 | NA |  |  |  | Security & Regulatory Compliance | Functional AT | Had a meeting with Ashwani from Alepo and sent him updated test cases. He is working on data gathering and will send us back by Tuesday. |  |  | Open |  |  |  |  | FAT were submitted to customer, Customer observation in being work out. Target to resubmission.- 23.07.25 |  |  | Sarmendra |  |  | CLOSURE REVIEW PENDING | [9 empty] | 472Security & Regulatory Compliance | Security | OPEN |  |  |  |  | Artefacts to be Submitted |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
7 | T6 | 472 | NA |  |  |  | BSS | Installation | Installation of BSS Application |  |  | Open |  |  |  |  | 29-08-2025: Design and Solution document to be shared with GM NOC and Physical instllation of BSS need to validate according to solution from L&T Side before submitting for for review with T Fiber 26-06-2025: We have offered Installation AT. TFIBER has asked DC architecture review including license validity |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | 472BSS | Applications/Tools | OPEN | [6 empty] | 1 | Open | Open
8 | T7 | 472 | NA |  |  |  | BSS | Integration | Initial Integration with Third Party Applications (OSS & NSO) |  |  | Open |  |  |  |  | 26-06-2025: OSS Integration is done. NSO integration is pending. Awaiting NSO Team. |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | 472BSS | Applications/Tools | OPEN | [6 empty] | 1 | Open | Open
9 | T8 | 472 | NA |  |  |  | BSS | Integration | OSS interfaces |  |  | Open |  |  |  |  | 26-06-2025: Feasibility API & Ticket API integration is completed. |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | 472BSS | Applications/Tools | OPEN | [6 empty] | 1 | Open | Open
10 | T9 | 472 | NA |  |  |  | BSS | Integration | NSO interfaces |  |  | Open |  |  |  |  | 26-06-2025: Awaiting NSO Team |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | 472BSS | Applications/Tools | OPEN | [6 empty] | 1 | Open | Open
11 | T10 | 472 | NA |  |  |  | BSS | Integration | GeM Portal |  |  | Open | [7 empty] | Manoj Nibrad |  | Open | Open | On-Hold confirmation mail received from NOC Director | 2025-07-16 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\BSS\Artifact_T10 | [6 empty] | 472BSS | Applications/Tools | CLOSED |  |  |  | 2025-07-16 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\BSS\Artifact_T10 |  | 1 | Open | Open
12 | T11 | 472 | NA |  |  |  | BSS | Development and unit testing | Import Sub-Departments, Import Leads, Campaign Management, Opportunity/Quote/order Management, order booking and Service Order workflow for tested services |  |  | Open |  |  |  |  | 29-08-2025: All points are completed Import Sub-Departments, Import Leads, Opportunity/Quote/order Management, order booking and Service Order workflow for tested services Demo to be conducted to TFIBER. "Campaign Management" is Pending where inputs are required from TFIBER Business team 26-06-2025: Awaiting few inputs from TFIBER |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | 472BSS | Applications/Tools | OPEN | [6 empty] | 1 | Open | Open
13 | T12 | 472 | NA |  |  |  | BSS | Development and unit testing | Product/Service Catalogue integration |  |  | Open |  |  |  |  | 29-08-2025: Feature is available to admin User(Product Team) to configure new product based on requirement. BSS Team will provide Demo to the TFIBER (business team([Uday]/Solution Team[Sanjay]) for their acceptance. 26-06-2025: Artifacts submitted. Closure review is pending with TFIBER |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | 472BSS | Applications/Tools | OPEN | [6 empty] | 1 | Open | Open
14 | T13 | 472 | NA |  |  |  | BSS | Development and unit testing | Billing, Discounts & Adjustments, Invoice generation, Bill Formatting |  |  | Open |  |  |  |  | 29-08-2025: Feature is made available in the BSS application, BSS Team will provide demo to TFIBER Team (Business [Uday] & Finance[Bhaskar]) 26-06-2025: Artifacts submitted. Closure review is pending with TFIBER |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | 472BSS | Applications/Tools | OPEN | [6 empty] | 1 | Open | Open
15 | T14 | 472 | NA |  |  |  | BSS | Development and unit testing | Feasibility API response from OSS for service provisioning request |  |  | Open |  |  |  |  | 29-08-2025: Feaibility API is already integrated with BSS and demonstrated in GIBB demo and it is applicable for all products. 26-06-2025: Artifacts submitted. Closure review is pending with TFIBER |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | 472BSS | Applications/Tools | OPEN | [6 empty] | 1 | Open | Open
16 | T15 | 472 | NA |  |  |  | BSS | Development and unit testing | SMS notification, email gateway, Field engineer mobile app readiness |  |  | Open |  |  |  |  | 29-08-2025: Integration is already completed and applicable for all product same has demonstrated to TFIBER during GIBB demo session. 26-06-2025: Artifacts submitted. Closure review is pending with TFIBER |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | 472BSS | Applications/Tools | OPEN | [6 empty] | 1 | Open | Open
17 | T16 | 472 | NA |  |  |  | BSS | Development and unit testing | Service Assurance and trouble tickets |  |  | Open |  |  |  |  | 29-08-2025: Integration with Service Manager is done for technical ticket and BSS have functionality to handle the non-technical ticket in BSS itself. BSS team will demonstrate this functionality to TFIBER. Sanjay Sir needs to confirm demo date. 26-06-2025: Artifacts submitted. Closure review is pending with TFIBER |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | 472BSS | Applications/Tools | OPEN | [6 empty] | 1 | Open | Open
18 | T17 | 472 | NA |  |  |  | BSS | Development and unit testing | Customer Self care portal development for T-CELL, T-NET, L0 |  |  | Open |  |  |  |  | 29-08-2025: Webportal is available. BSS team needs to demonstrate to TFIBER team. Sanjay Sir needs to confirm demo date. 26-06-2025: Artifacts submitted. Closure review is pending with TFIBER |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | 472BSS | Applications/Tools | OPEN | [6 empty] | 1 | Open | Open
19 | T18 | 472 | NA |  |  |  | BSS | Integration | Integration modules Like on board Un-Assist & dependent module to be completed for all products from system to be initiated a workshop and to be closed in next 2 Weeks |  |  | Open |  |  |  |  | 29-08-2025: Seek input from Business team (Uday) and deploy post assisted completion. 26-06-2025: Input awaited from TFIBER |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | 472BSS | Applications/Tools | OPEN | [6 empty] | 1 | Open | Open
20 | T19 | 472 | NA |  |  |  | BSS | MoM Action | T-Cell service definition for workflow implementation in BSS for creating Spoke primary and secondary |  |  | Open |  |  |  |  | 29-08-2025:Update product concept note similar to GIBB and share with TFIBER for review 26-06-2025: We can deliver this post getting product concept note from TFIBER |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | 472BSS | Applications/Tools | OPEN | [6 empty] | 1 | Open | Open
21 | T20 | 472 | NA |  |  |  | BSS | Development and unit testing | Rules for primary and secondary spoke implementation in BSS- - GP with shortest distance will be primary - To display dropdown and concerned user group to select and confirm |  |  | Open |  |  |  |  | #N/A |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | 472BSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
22 | T21 | 472 | NA |  |  |  | BSS | MoM Action | BSS firewall ports required for Security compliance |  |  | Open |  |  |  |  | BSS has to forward list of Port as per deiffrent modules of application |  |  | Sarmendra |  | Open | WIP | [9 empty] | 472BSS | Applications/Tools | OPEN | [6 empty] | 1 | Open | Open
23 | T22 | 472 | NA |  |  |  | BSS | Security | Roadmap for password policy implementation in CSP |  |  | Open |  |  |  |  | Ciriteria for Paswword policy hase been Shared wioth BSS team . BSS team has to implement and submit report for verifications. |  |  | Sarmendra |  | Open | WIP | [9 empty] | 472BSS | Applications/Tools | OPEN | [6 empty] | 1 | Open | Open
24 | T23 | 472 | NA |  |  |  | BSS | Security | DMZ requirements for CSP |  |  | Open |  |  |  |  | IP amd URL required by BSS foir NAT through DMZ has been Completed |  |  | Sarmendra |  | Open | WIP | [9 empty] | 472BSS | Applications/Tools | OPEN | [6 empty] | 1 | Open | Open
25 | T24 | 472 | NA |  |  |  | BSS | MoM Action | PoP location confirmation usergroup for connectivity to O&M |  |  | Open |  |  |  |  | 29-08-2025: Seek input from O&M team (Umesh) 26-06-2025: Input awaited from TFIBER |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | 472BSS | Applications/Tools | OPEN | [6 empty] | 1 | Open | Open
26 | T25 | 472 | NA |  |  |  | BSS | MoM Action | Product concept note configuration in BSS queries to be shared |  |  | Open |  |  |  |  | 29-08-2025: Queries to be prepared and share with TFIBER for discussion. 17-07-2025: Business Team of TFIBER needs to finalize and confirm all product. 26-06-2025: Need Product concept note from TFIBER |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | 472BSS | Applications/Tools | OPEN | [6 empty] | 1 | Open | Open
27 | T26 | 472 | NA |  |  |  | BSS | MoM Action | Location id logic for NSO provisioning |  |  | Open |  |  |  |  | 29-08-2025: Ciruit ID logic PPT shared by Sivakumar, needs to use and implement in BSS. 26-06-2025: Timeline 30th July is considering NSO support is available in 2-3 days |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | 472BSS | Applications/Tools | OPEN | [6 empty] | 1 | Open | Open
28 | T27 | 472 | NA |  |  |  | BSS | Integration | Tariff plan parameters viz. 5G, 4G finalisation. (BSS should capture QOS parameter & Requirements) |  |  | Open |  |  |  |  | 29-08-2025: Product Can be configured in BSS product catalogue Demo to be given to TFIBER 26-06-2025: Input awaited from TFIBER |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | 472BSS | Applications/Tools | OPEN | [6 empty] | 1 | Open | Open
29 | T28 | 472 | NA |  |  |  | IP/MPLS | Functional AT | Internal AT 83% complete. Waiting Cisco to update data sent by Vikram and then we will submit to TPA ( for pending cases, we just need a maintanence window to test as it is impacting activity) This is for ISE |  |  | Open |  |  |  |  | FAT documents were submitted to TPA , However it has some common observation which will be discussed with TPA team by Mr Sharma. Subsequently , correction will be made in FAT doc |  |  | Sarmendra |  | Open | WIP | [9 empty] | 472IP/MPLS | IPMPLS | OPEN | [6 empty] | 1 | Open | Open
30 | T29 | 472 | NA |  |  |  | IP/MPLS | Functional AT | CSM is having memory issues. Need to sort it out before we do AT. Working on settling that with Cisco. Memory will be allocated and tested in the first week of July |  |  | Open |  |  |  |  | CSM has been replaced by ASDM |  |  | Sarmendra |  | Open | WIP | [9 empty] | 472IP/MPLS | IPMPLS | OPEN | [6 empty] | 1 | Open | Open
31 | T30 | 472 | NA |  |  |  | IP/MPLS | Functional AT | Internal AT 72% complete. Waiting on Cisco to update data sent by Vikram and then we will submit to TPA. ( for pending cases, we just need a maintanence window to test as it is impacting activity) |  |  | Open |  |  |  |  | FAT documents were submitted to TPA , However it has some common observation which will be discussed with TPA team by Mr Sharma. Subsequently , correction will be made in FAT doc |  |  | Sarmendra |  | Open | WIP | [9 empty] | 472IP/MPLS | IPMPLS | OPEN | [6 empty] | 1 | Open | Open
32 | T31 | 472 | NA |  |  |  | Security & Regulatory Compliance | Security | Internal Audit for all applications |  |  | Open |  |  |  |  | Application audited partally , howver PT audit couldnot be done due to lack of necessary tools. Same has been requested with LTTS team , but it could not be materialised. |  |  | Sarmendra |  | Open | WIP | [9 empty] | 472Security & Regulatory Compliance | Security | OPEN | [6 empty] | 1 | Open | Open
33 | T32 | 472 | NA |  |  |  | Security & Regulatory Compliance | Security | Internal audit for network elements |  |  | Open |  |  |  |  | Network elemants auditted including NOC end points , However PT for same is pending. |  |  | Sarmendra |  | Open | WIP | [9 empty] | 472Security & Regulatory Compliance | Security | OPEN | [6 empty] | 1 | Open | Open
34 | T33 | 472 | NA |  |  |  | BSS | Security | Security policies to evolve related to DOT/CDOT etc |  |  | Open |  |  |  |  | 29-08-2025: Collect data from Sivakumar and read user to access the data by DOT. 26-06-2025: Waiting for inputs for multiple deliverables |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | 472BSS | Applications/Tools | OPEN | [6 empty] | 1 | Open | Open
35 | T34 | 472 | NA |  |  |  | IP/MPLS | Security | external Audit for all applications (Tfiber will be arranging a partner for third party audit) |  |  | Open |  |  |  |  | Awaited TSTG Audit party to engage |  |  | Sarmendra |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | 472IP/MPLS | IPMPLS | OPEN | [6 empty] | 1 | Open | Open
36 | T35 | 472 | NA |  |  |  | IP/MPLS | Security | external audit for network elements(Tfiber will be arranging a partner for third party audit) |  |  | Open |  |  |  |  | Awaited TSTG Audit party to engage |  |  | Sarmendra |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | 472IP/MPLS | IPMPLS | OPEN | [6 empty] | 1 | Open | Open
37 | T36 | 472 | NA |  |  |  | Security & Regulatory Compliance | Security | Physical user access |  |  | Open |  |  |  |  | Has completed , Artefacts will be resubmitted. |  |  | Sarmendra |  | Open | REOPENED |  |  | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\NW-Security\T36 | [6 empty] | 472Security & Regulatory Compliance | Security | OPEN |  |  |  |  | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\NW-Security\T36 |  | 1 | Open | Open
38 | T37 | 472 | NA |  |  |  | Security & Regulatory Compliance | Security | Virtual user access-VPN |  |  | Open |  |  |  |  | Has completed , Artefacts will be resubmitted. |  |  | Sarmendra |  | Open | REOPENED | [9 empty] | 472Security & Regulatory Compliance | Security | OPEN | [6 empty] | 1 | Open | Open
39 | T38 | 472 | NA |  |  |  | Security & Regulatory Compliance | Security | Role based severity access |  |  | Open |  |  |  |  | Completed and Review pending. Artfacts submitted |  |  | Sarmendra |  | Open | WIP | [9 empty] | 472Security & Regulatory Compliance | Security | OPEN | [6 empty] | 1 | Open | Open
40 | T39 | 472 | NA |  |  |  | Security & Regulatory Compliance | Security | ISE integration with Cisco elements |  |  | Open |  |  |  |  | Artefacts will be submitted. |  |  | Sarmendra |  |  | CLOSURE REVIEW PENDING | [9 empty] | 472Security & Regulatory Compliance | Security | OPEN |  |  |  |  | Artefacts to be Submitted |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
41 | T40 | 472 | NA |  |  |  | Security & Regulatory Compliance | Regulatory | Regulatory Compliance with respect DoT policies 1. Security Policy-Complied 2. Security Architecture of Telecom Network-Complied 3. Information Security Risk Assessment and Risk Treatment processes and their implementation plan-WIP, Target: Dec 2024 reviewed with customer. 4. Recruitment processes and employee's record-WIP, Target:12-10-2025 5. Controls for effectiveness of security management-WIP, Target: 28 -02-2025 6. Evidence of monitoring, measurement results and management reviews of security management-WIP, Target: 28-02-2025 7. Security Audit programs and audit results-Complied 8. Inventory management and classification of information assets and their handling Completed 9. Procedure for responding to information and network security incidents-WIP, Target: 28-02-2025 - SIRT reviewed 10. Main S/W updation and changes-WIP, Target: 28-02-2025 11. Supply chain of products (HW/SW). To be taken from manufacturer/supplier-Communicated to Sekhar. WIP, Target: 14-02-2025 12. SW details and documentation obtained from manufacturers/supplier-Communicated to Sekhar WIP, Target: 14-02-2025 13. O&M procedures in the form of manual-O&M manual and OEM wise manuals WIP, Target: 14-02-2025 14. Processes for internal and external communication relevant to the security management-WIP, Target: 07-3-2025 |  |  | Open |  |  |  |  | Confirmation of purchase of ISE. License needed to upgrade for HA |  |  | Sarmendra |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | 472Security & Regulatory Compliance | Security | OPEN |  |  |  |  | #VALUE! |  | 1 | Open | Open
42 | T41 | 472 | NA |  |  |  | DC-IT | Servers and Strorage (Deployment and Installations) | 1. Compute & Storage |  |  | Open |  |  |  |  | 11-Oct-25: As per the OEM's/SME's request, storage is allocated as per requirements. Artifacts are Captured. OEM Confirmation Emails to be captured as a Reference. |  |  | Ravi Kishore |  | Open | REOPENED |  |  | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\DC IT-Infra\Artifact for - T41 | [6 empty] | 472DC-IT | Network | OPEN | [6 empty] | 1 | Open | Open
43 | T42 | 472 | NA |  |  |  | DC-IT | Servers and Strorage (Deployment and Installations) | 2. Virtulization |  |  | Colosed | [7 empty] | Ravi Kishore |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-05-14 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\DC IT-Infra\Artifact for -T42 | [6 empty] | 472DC-IT | Network | CLOSED |  |  |  | 2025-05-14 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\DC IT-Infra\Artifact for -T42 |  | 1 | Completed & Approved | Closed before june-2025
44 | T43 | 472 | NA |  |  |  | DC-IT | Servers and Strorage (Deployment and Installations) | 3. Anti-virus |  |  | Colosed | [7 empty] | Ravi Kishore |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-05-14 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\DC IT-Infra\Artifact for -T43 | [6 empty] | 472DC-IT | Network | CLOSED |  |  |  | 2025-05-14 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\DC IT-Infra\Artifact for -T43 |  | 1 | Completed & Approved | Closed before june-2025
45 | T44 | 472 | NA |  |  |  | DC-IT | Servers and Strorage (Deployment and Installations) | 4. VM's Deployment Application Installations |  |  | Colosed | [7 empty] | Ravi Kishore |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-05-14 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\DC IT-Infra\Artifact for -T44 | [6 empty] | 472DC-IT | Network | CLOSED |  |  |  | 2025-05-14 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\DC IT-Infra\Artifact for -T44 |  | 1 | Completed & Approved | Closed before june-2025
46 | T45 | 472 | NA |  |  |  | DC-IT | Commvault Backup | Application Installation |  |  | Colosed | [7 empty] | Ravi Kishore |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-05-14 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\DC IT-Infra\Artifact for - T45 | [6 empty] | 472DC-IT | Network | CLOSED |  |  |  | 2025-05-14 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\DC IT-Infra\Artifact for - T45 |  | 1 | Completed & Approved | Closed before june-2025
47 | T46 | 472 | NA |  |  |  | DC-IT | Commvault Backup | Application Configuration |  |  | Colosed | [7 empty] | Ravi Kishore |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-05-14 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\DC IT-Infra\Artifact for - T46 | [6 empty] | 472DC-IT | Network | CLOSED |  |  |  | 2025-05-14 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\DC IT-Infra\Artifact for - T46 |  | 1 | Completed & Approved | Closed before june-2025
48 | T47 | 472 | NA |  |  |  | DC-IT | Commvault Backup | Application Installation AT |  |  | Colosed | [7 empty] | Ravi Kishore |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-05-14 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\DC IT-Infra\Artifact for - T47 | [6 empty] | 472DC-IT | Network | CLOSED |  |  |  | 2025-05-14 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\DC IT-Infra\Artifact for - T47 |  | 1 | Completed & Approved | Closed before june-2025
49 | T48 | 472 | NA |  |  |  | DC-IT | Commvault Backup | Application Functional AT |  |  | Open |  |  |  |  | Working on the Extra Test cases which are received from the TPA & T-Fiber. |  |  | Ravi Kishore |  | Open | WIP |  |  | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\DC IT-Infra\Artifact for - T48 | [6 empty] | 472DC-IT | Network | OPEN | [6 empty] | 1 | Open | Open
50 | T49 | 472 | NA |  |  |  | DC-IT | LLD | LLD Approved conditionally with few punch points. Updated LLD to be submitted |  |  | Open |  |  |  |  | Working on DC IT-Infra Server and storage-MoM Points received from the T-Fiber. |  |  | Ravi Kishore |  | Open | WIP |  |  | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\DC IT-Infra\Artifact for - T49 | [6 empty] | 472DC-IT | Network | OPEN | [6 empty] | 1 | Open | Open
51 | T50 | 472 | NA |  |  |  | DC-IT | MoM Action | Radware , A10 Configuration file needed to be shared to RaviKishore |  |  | Open |  |  |  |  | Artfacts submitted . point Closure on 10 Jul 25 |  |  | Sarmendra |  |  | COMPLETED & APPROVED |  |  | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\NW-Security\T50 | [6 empty] | 472DC-IT | Network | CLOSED |  |  |  |  | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\NW-Security\T50 |  | 1 | Completed & Approved | Closed after June
52 | T51 | 472 | NA |  |  |  | DC-IT | Commvault Backup | Backup retention and Backup activity (such as when incremental backup,full backup are scheduled and time duration required to complete such backup). Application Wise Backup Retention should be as per DOT Guidelines |  |  | Colosed | [7 empty] | Ravi Kishore |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-05-14 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\DC IT-Infra\Artifact for - T51 | [6 empty] | 472DC-IT | Network | CLOSED |  |  |  | 2025-05-14 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\DC IT-Infra\Artifact for - T51 |  | 1 | Completed & Approved | Closed before june-2025
53 | T52 | 472 | NA |  |  |  | DC-IT | Commvault Backup | Backup solution should have hot , cold and archieve storage inorder to decrease the backup size/capacity in long run. |  |  | Colosed | [7 empty] | Ravi Kishore |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-05-14 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\DC IT-Infra\Artifact for - T52 | [6 empty] | 472DC-IT | Network | CLOSED |  |  |  | 2025-05-14 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\DC IT-Infra\Artifact for - T52 |  | 1 | Completed & Approved | Closed before june-2025
54 | T53 | 472 | NA |  |  |  | DC-IT | SSD storage migration – EPNM/PI | EPNM/PI VMs migration to SSD Storage |  |  | Colosed | [7 empty] | Ravi Kishore |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-05-14 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\DC IT-Infra\Artifact for - T53 | [6 empty] | 472DC-IT | Network | CLOSED |  |  |  | 2025-05-14 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\DC IT-Infra\Artifact for - T53 |  | 1 | Completed & Approved | Closed before june-2025
55 | T54 | 472 | NA |  |  |  | DC-IT | SSD storage migration – ISE/FMC | ISE & FMC VMs migration to SSD Storage |  |  | Colosed | [7 empty] | Ravi Kishore |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-05-14 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\DC IT-Infra\Artifact for - T54 | [6 empty] | 472DC-IT | Network | CLOSED |  |  |  | 2025-05-14 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\DC IT-Infra\Artifact for - T54 |  | 1 | Completed & Approved | Closed before june-2025
56 | T55 | 472 | NA |  |  |  | DC-IT | MoM Action | VM Placing should be verified & rectified, Same service VM needs to be placed in different Physical Server/host. |  |  | Colosed | [7 empty] | Ravi Kishore |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-05-14 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\DC IT-Infra\Artifact for - T55 | [6 empty] | 472DC-IT | Network | CLOSED |  |  |  | 2025-05-14 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\DC IT-Infra\Artifact for - T55 |  | 1 | Completed & Approved | Closed before june-2025
57 | T56 | 472 | NA |  |  |  | DC-IT | MoM Action | SOP documents needs to be provided |  |  | Open |  |  |  |  | SOP documents submitted to Operations team. Remaining pending documents to be prepared periodically. |  |  | Ravi Kishore |  | Open | REOPENED |  |  | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\DC IT-Infra\Artifact for - T56 | [6 empty] | 472DC-IT | Network | OPEN | [6 empty] | 1 | Open | Open
58 | T57 | 472 | NA |  |  |  | DC-IT | LLD | Approved conditionally with few punch points. Updated LLD to be submitted |  |  | Open |  |  |  |  | 14-Aug-25 : Discussion was done with TPA and Tfiber and submitted updated LLD document. 18-Jun-25 : Updated DC Network LLD submitted on 18-Jun-25 for TFiber review | L&T |  | RS Rao |  |  | COMPLETED & APPROVED | [9 empty] | 472DC-IT | Network | CLOSED |  |  |  | 2025-08-14 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\DC Network LLD V1.7 14-Aug-2025.pdf |  | 1 | Completed & Approved | Closed after June
59 | T58 | 472 | NA |  |  |  | DC-IT | Cisco EPNM | Cisco EPNM infrastructure AT |  |  | Open |  |  |  |  | 22-Sep-25: IPMPLS Domain team to submit detailed remarks on raised queries. 08-Jul-2025 - Sandeep will come back by EoD today on extension of Cisco support renewal 01-Jul-25 : Revised FAT documents submission pending (TPA observations to be included) OEM(Cisco) suport is required to show the new test cases, Inputs provided to OEM on 14th May & 30th Jun. OEM onboarding is in progress & LnT Contracts team coordinating | L&T | RS Rao | RS Rao |  | Open | Open | [9 empty] | 472DC-IT | Network | OPEN | [6 empty] | 1 | Open | Open
60 | T59 | 472 | NA |  |  |  | DC-IT | Cisco PI | Cisco prime infrastructure AT |  |  | Open |  |  |  |  | 22-Sep-25: IPMPLS Domain team to submit detailed remarks on raised queries. 08-Jul-2025 - Sandeep will come back by EoD today on extension of Cisco support renewal 01-Jul-25 : Revised FAT documents submission pending (TPA observations to be included) OEM(Cisco) suport is required to show the new test cases, Inputs provided to OEM on 14th May & 30th Jun. OEM onboarding is in progress & LnT Contracts team is coordinating | L&T | RS Rao | RS Rao |  | Open | Open | [9 empty] | 472DC-IT | Network | OPEN | [6 empty] | 1 | Open | Open
61 | T60 | 472 | NA |  |  |  | DC-IT | NTP | Installation |  |  | Colosed | [7 empty] | RS Rao |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-05-05 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\Primary NTP - T60,T61,T62.pdf \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\Secondary NTP - T60,T61,T62.pdf | [6 empty] | 472DC-IT | Network | CLOSED |  |  |  | 2025-05-05 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\Primary NTP - T60,T61,T62.pdf \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\Secondary NTP - T60,T61,T62.pdf |  | 1 | Completed & Approved | Closed before june-2025
62 | T61 | 472 | NA |  |  |  | DC-IT | NTP | Configuration |  |  | Colosed | [7 empty] | RS Rao |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-05-05 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\Primary NTP - T60,T61,T62.pdf \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\Secondary NTP - T60,T61,T62.pdf | [6 empty] | 472DC-IT | Network | CLOSED |  |  |  | 2025-05-05 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\Primary NTP - T60,T61,T62.pdf \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\Secondary NTP - T60,T61,T62.pdf |  | 1 | Completed & Approved | Closed before june-2025
63 | T62 | 472 | NA |  |  |  | DC-IT | NTP | NTP Installation AT |  |  | Colosed | [7 empty] | RS Rao |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-05-05 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\Primary NTP - T60,T61,T62.pdf \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\Secondary NTP - T60,T61,T62.pdf | [6 empty] | 472DC-IT | Network | CLOSED |  |  |  | 2025-05-05 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\Primary NTP - T60,T61,T62.pdf \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\Secondary NTP - T60,T61,T62.pdf |  | 1 | Completed & Approved | Closed before june-2025
64 | T63 | 472 | NA |  |  |  | DC-IT | NTP | NTP Functional AT |  |  | Open | [7 empty] | RS Rao |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-07-03 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\NTP FAT & Acceptance - T63.pdf | [6 empty] | 472DC-IT | Network | CLOSED |  |  |  | 2025-07-03 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\NTP FAT & Acceptance - T63.pdf |  | 1 | Completed & Approved | Closed after June
65 | T64 | 472 | NA |  |  |  | DC-IT | Functional AT | DC Network Infra AT |  |  | Open |  |  |  |  | 22-Sep-25: IPMPLS Domain team to submit detailed remarks on raised queries. 08-Jul-2025 - Sandeep will come back by EoD today on extension of Cisco support renewal 01-Jul-25 : Revised FAT documents submission pending (TPA observations to be included) OEM(Cisco) suport is required to show the new test cases, Inputs provided to OEM on 14th May & 30th Jun. OEM onboarding is in progress & LnT Contracts team is coordinating | L&T | RS Rao | RS Rao |  | Open | Open | [9 empty] | 472DC-IT | Network | OPEN | [6 empty] | 1 | Open | Open
66 | T65 | 472 | NA |  |  |  | DR | Servers and Strorage (Deployment and Installations) | Virtulization |  |  | Colosed | [7 empty] | Ravi Kishore |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-05-14 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\DR\Artifact for - T65 | [6 empty] | 472DR | DR | CLOSED |  |  |  | 2025-05-14 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\DR\Artifact for - T65 |  | 1 | Completed & Approved | Closed before june-2025
67 | T66 | 472 | NA |  |  |  | DR | DC (TNOC-DR) | Network Readiness |  |  | Colosed | [7 empty] | Ravi Kishore |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-05-14 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\DR\Artifact for - T66 | [6 empty] | 472DR | DR | CLOSED |  |  |  | 2025-05-14 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\DR\Artifact for - T66 |  | 1 | Completed & Approved | Closed before june-2025
68 | T67 | 472 | NA |  |  |  | DR | Mahbubnagar-DR | Network Readiness |  |  | Colosed | [7 empty] | Ravi Kishore |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-05-14 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\DR\Artifact for -T67 | [6 empty] | 472DR | DR | CLOSED |  |  |  | 2025-05-14 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\DR\Artifact for - T66 |  | 1 | Completed & Approved | Closed before june-2025
69 | T68 | 472 | NA |  |  |  | DR | Design & Documentation | LLD: Approved conditionally with few punch points. Updated LLD to be submitted |  |  | Open |  |  |  |  | Working on additional points shared by Tfiber. |  |  | Ravi Kishore |  | Open | WIP |  |  | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\DR\Artifact for -T68 | [6 empty] | 472DR | DR | OPEN | [6 empty] | 1 | Open | Open
70 | T69 | 472 | NA |  |  |  | DR | Design & Documentation | HLD: Revised solution to submitted |  |  | Open |  |  |  |  | Working on additional points shared by Tfiber. |  |  | Ravi Kishore |  | Open | WIP |  |  | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\DR\Artifact for -T69 | [6 empty] | 472DR | DR | OPEN | [6 empty] | 1 | Open | Open
71 | T70 | 472 | NA |  |  |  | DR | Design & Documentation | DC-DR redunancy Test |  |  | Colosed | [7 empty] | Ravi Kishore |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-05-14 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\DR\Artifact for - T70 | [6 empty] | 472DR | DR | CLOSED |  |  |  | 2025-05-14 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\DR\Artifact for - T70 |  | 1 | Completed & Approved | Closed before june-2025
72 | T71 | 472 | NA |  |  |  | DR | MoM Action | UTM Features (DR FW) |  |  | Open |  |  |  |  | Meeting scheduled with CTRL S to verify the UTM features |  |  | Sarmendra |  | Open | WIP | [9 empty] | 472DR | DR | OPEN | [6 empty] | 1 | Open | Open
73 | T72 | 472 | NA |  |  |  | DR | MoM Action | To configure LACP between L3 Switch and Core Router |  |  | Open |  |  |  |  | 11-Oct-25: CtrlS has to give proposal for procurement for addtional BoQ. IT infra SME need to Re-intiate a mail to get BoQ 22-Sep-25: The existing switch which was placed at DR by CtrlS doesnt have feature on LACP Bundling. CtrlS is planning to relplace the exising switch with LACP supported switch. DC Infra admin need to provide tentative timelines for replacement. 08-Jul-2025 Sandeep will ensure on CTRL-S support and update by EoD 01-Jul-25 : Ticket (SR01301726) raised with CtrlS on 27-Jun, Config & testing to be carried out. This is additional task as per CtrlS and commercials may be involved. LnT Contracts team also talking to CtrlS account team to complete the task. 24-Dec-25 : SR01036770 opened with CtrlS for LACP configuration and it is not O&M activity as per CtrlS ops. team. escalated to LnT Contracts team for supoort. | CtrlS | Venkat | Ravi Kishore |  | Open | WIP | [9 empty] | 472DR | DR | OPEN | [6 empty] | 1 | Open | Open
74 | T73 | 472 | NA |  |  |  | DR | MoM Action | To configure LACP between Core Router and Firewall |  |  | Open |  |  |  |  | 11-Oct-25: CtrlS has to give proposal for procurement for addtional BoQ. IT infra SME need to Re-intiate a mail to get BoQ 22-Sep-25: The existing switch which was placed at DR by CtrlS doesnt have feature on LACP Bundling. CtrlS is planning to relplace the exising switch with LACP supported switch. DC Infra admin need to provide tentative timelines for replacement. 01-Jul-25 : Ticket (SR01301726) raised with CtrlS on 27-Jun, Config & testing to be carried out. This is additional task as per CtrlS and commercials may be involved. LnT Contracts team also talking to CtrlS account team to complete the task. 24-Dec-25 : SR01036770 opened with CtrlS for LACP configuration and it is not O&M activity as per CtrlS ops. team. escalated to LnT Contracts team for supoort. | CtrlS | Venkat | Ravi Kishore |  | Open | WIP | [9 empty] | 472DR | DR | OPEN | [6 empty] | 1 | Open | Open
75 | T74 | 472 | NA |  |  |  | DR | MoM Action | To configure LACP between Firewall and L2 Switch |  |  | Open |  |  |  |  | 11-Oct-25: CtrlS has to give proposal for procurement for addtional BoQ. IT infra SME need to Re-intiate a mail to get BoQ 22-Sep-25: The existing switch which was placed at DR by CtrlS doesnt have feature on LACP Bundling. CtrlS is planning to relplace the exising switch with LACP supported switch. DC Infra admin need to provide tentative timelines for replacement. 01-Jul-25 : Ticket (SR01301726) raised with CtrlS on 27-Jun, Config & testing to be carried out. This is additional task as per CtrlS and commercials may be involved. LnT Contracts team also talking to CtrlS account team to complete the task. 24-Dec-25 : SR01036770 opened with CtrlS for LACP configuration and it is not O&M activity as per CtrlS ops. team. escalated to LnT Contracts team for supoort. | CtrlS | Venkat | Ravi Kishore |  | Open | WIP | [9 empty] | 472DR | DR | OPEN | [6 empty] | 1 | Open | Open
76 | T75 | 472 | NA |  |  |  | DR | MoM Action | To confirm on backups for DR Virtual machines |  |  | Colosed | [7 empty] | Ravi Kishore |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-05-14 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\DR\Artifact for - T75 | [6 empty] | 472DR | DR | CLOSED |  |  |  | 2025-05-14 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\DR\Artifact for - T75 |  | 1 | Completed & Approved | Closed before june-2025
77 | T76 | 472 | NA |  |  |  | DR | MoM Action | Backup storage to 25 TB |  |  | Colosed | [7 empty] | Ravi Kishore |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-05-14 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\DR\Artifact for - T76 | [6 empty] | 472DR | DR | CLOSED |  |  |  | 2025-05-14 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\DR\Artifact for - T76 |  | 1 | Completed & Approved | Closed before june-2025
78 | T77 | 472 | NA |  |  |  | DR | MoM Action | To submit the SOPs for DC-DR switchover, DC-DR failover and failback |  |  | Open |  |  |  |  | Tejas, Nokia, GIS & Ciena MCP documnets are received. Remaining all Applications domains SOP's to be updated. |  |  | Ravi Kishore |  | Open | REOPENED |  |  | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\DR\Artifact for - T77 | [6 empty] | 472DR | DR | OPEN | [6 empty] | 1 | Open | Open
79 | T78 | 472 | NA |  |  |  | DR | MoM Action | to monitor the DR Servers |  |  | Open |  |  |  |  | DR servers monitoring through DR vCentre happening. DR is maintained by CtrlS team as per contract. Feasibility to be checked to integrated through OSS OBM. |  |  | Ravi Kishore |  | Open | WIP |  |  | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\DR\Artifact for - T78 | [6 empty] | 472DR | DR | OPEN | [6 empty] | 1 | Open | Open
80 | T79 | 472 | NA |  |  |  | DR | MoM Action | To confirm that DNS switchover between DC and DR locations should be automatic |  |  | Colosed | [7 empty] | Ravi Kishore |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-05-14 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\DR\Artifact for - T79 | [6 empty] | 472DR | DR | CLOSED |  |  |  | 2025-05-14 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\DR\Artifact for - T79 |  | 1 | Completed & Approved | Closed before june-2025
81 | T80 | 472 | NA |  |  |  | DR | MoM Action | Mahubnagar as NTP |  |  | Colosed | [7 empty] | RS Rao |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-05-05 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\Primary NTP - T60,T61,T62.pdf \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\Secondary NTP - T60,T61,T62.pdf | [6 empty] | 472DR | DR | CLOSED |  |  |  | 2025-05-05 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\Primary NTP - T60,T61,T62.pdf \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\Secondary NTP - T60,T61,T62.pdf |  | 1 | Completed & Approved | Closed before june-2025
82 | T81 | 472 | NA |  |  |  | DR | Configuration | All application to be migrated to implement DR LB configuration |  |  | Open |  |  |  |  | 11-Oct-25: Approved DR HLD document to be shared with T Fiber for further discussion. Noikia app is integrated with DR LB . Balance application migration on DR LB is in Pipeline |  |  | Ravi Kishore |  | Open | WIP | [9 empty] | 472DR | DR | OPEN | [6 empty] | 1 | Open | Open
83 | T82 | 472 | NA |  |  |  | DR | MoM Action | To confirm the applications which support Veem Replication for Reconfiguration |  |  | Colosed | [7 empty] | Ravi Kishore |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-05-14 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\DR\Artifact for - T82 | [6 empty] | 472DR | DR | CLOSED |  |  |  | 2025-05-14 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\DR\Artifact for - T82 |  | 1 | Completed & Approved | Closed before june-2025
84 | T83 | 472 | NA |  |  |  | DWDM | Network Deployment & integration | Zonal Links Integration (12/15) |  |  | Open |  |  |  |  | 20-Sep-25: Nirmal, Jainoor, Gudihatnoor & Bhimni RFE pending due to forest permission 31-July-2025:As per discussion with Ramanaiah sir, need to discuss these points with T Fiber Project team for further action, till that time this point kept on hold Depend on 04 Facilities RFE in Pkg-C Asifabad - Warangal & Karimnagar - Asifabad - Links integrated as per interim plan, actual integration pending Nizamabad - Asifabad - E2E link integration pending 28th-Apr'25: As per Sandeep Sanmani - Forest permission still pending 6/25/2025: Status is same no visibility on forest permission, Target date would be D+21 05-July-25: No progress on the forest permission | T Fiber | Srinivas Jukuri(Project) | Suresh Kumar |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | 472DWDM | DWDM | OPEN | [6 empty] | 1 | Open | Open
85 | T84 | 472 | NA |  |  |  | DWDM | Network Deployment & integration | Nodes Live & Operational (67/71) |  |  | Open |  |  |  |  | 31-July-2025:As per discussion with Ramanaiah sir, need to discuss these points with T Fiber Project team for further action, till that time this point kept on hold Nirmal, Jainoor, Gudihatnoor & Bhimni RFE pending due to forest permission 28th-Apr'25: As per Sandeep Sanmani - Forest permission still pending 15-06-25: No progress on the permission, target - D+15 05-July-25: No progress on the forest permission | T Fiber | Srinivas Jukuri(Project) | Suresh Kumar |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | 472DWDM | DWDM | OPEN | [6 empty] | 1 | Open | Open
86 | T85 | 472 | NA |  |  |  | DWDM | Network Deployment & integration | Zonal Rings readiness with 1+R protection (5/7) |  |  | Open |  |  |  |  | 31-July-2025:As per discussion with Ramanaiah sir, need to discuss these points with T Fiber Project team for further action, till that time this point kept on hold 02 rings depend on 04 Facilities RFE readiness in Pkg-C, which is pending due to forest permission 28th-Apr'25: As per Sandeep Sanmani - Forest permission still pending 6/25/2025: No visibility on forest permission, target date would be D+30 05-July-25: No progress on the forest permission | T Fiber | Srinivas Jukuri(Project) | Suresh Kumar |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | 472DWDM | DWDM | OPEN | [6 empty] | 1 | Open | Open
87 | T86 | 472 | NA |  |  |  | DWDM | Network Deployment & AT Status | Nodal AT (67/71) |  |  | Open |  |  |  |  | 31-July-2025:As per discussion with Ramanaiah sir, need to discuss these points with T Fiber Project team for further action, till that time this point kept on hold Nirmal, Jainoor, Gudihatnoor & Bhimni RFE pending due to forest permission 28th-Apr'25: As per Sandeep Sanmani - Forest permission still pending 15-06-25: No progress on the permission, target - D+15 05-July-25: No progress on the forest permission | T Fiber | Srinivas Jukuri(Project) | Suresh Kumar |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | 472DWDM | DWDM | OPEN | [6 empty] | 1 | Open | Open
88 | T87 | 472 | NA |  |  |  | DWDM | Network Deployment & integration | Mandal Ring Integration through OADM |  |  | Open |  |  |  |  | 31-July-2025:As per discussion with Ramanaiah sir, need to discuss these points with T Fiber Project team for further action, till that time this point kept on hold Mandal services are provisioned (10G) as per integration plan by all packages 6/25/2025: 203 services provisioned out of 270 planned. Remaining can be provisioned as per the requirement | T Fiber | Srinivas Jukuri(Project) | Suresh Kumar |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | 472DWDM | DWDM | OPEN | [6 empty] | 1 | Open | Open
89 | T88 | 472 | NA |  |  |  | DWDM | Network Deployment & AT Status | Zonal Link AT (7/15) |  |  | Open |  |  |  |  | 31-July-2025:As per discussion with Ramanaiah sir, need to discuss these points with T Fiber Project team for further action, till that time this point kept on hold 04 Link AT's approved by T Fiber and 03 Link AT's pending due to letter from Ciena awaited (No impact due to ILA to OADM upgradation) 05 Link AT pending due to high losses in the spans, depend on all packages 02 Links integrated as per interim plan, so not considered for Link AT 20May'25: Declaration letter submitted to T Fiber for 03 links AT approval 25-06-2025: Dependancy on field, no progress. 30-June-2025: As discussed in the meeting, need to arrange meeting with all stakeholders | All Packages |  | Suresh Kumar |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | 472DWDM | DWDM | OPEN |  |  | 20-Sep-25: Mr.Suresh will update the status |  |  |  | 1 | Open | Open
90 | T89 | 472 | NA |  |  |  | DWDM | Design & Documentation | HLD (Revised) with OADM Solution |  |  | Colosed | [7 empty] | Suresh Kumar |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-05-06 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\DWDM\Artefact - T89 | [6 empty] | 472DWDM | DWDM | CLOSED |  |  |  | 2025-05-06 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\DWDM\Artefact - T89 |  | 1 | Completed & Approved | Closed before june-2025
91 | T90 | 472 | NA |  |  |  | DWDM | Design & Documentation | LLD (Revised) with OADM Solution (Ciena) |  |  | Colosed | [7 empty] | Suresh Kumar |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-05-06 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\DWDM\Artefact - T90 | [6 empty] | 472DWDM | DWDM | CLOSED |  |  |  | 2025-05-06 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\DWDM\Artefact - T90 |  | 1 | Completed & Approved | Closed before june-2025
92 | T91 | 472 | NA |  |  |  | DWDM | Design & Documentation | Nodal ATP |  |  | Colosed | [7 empty] | Suresh Kumar |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-05-06 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\DWDM\Artefact - T91 & T92 | [6 empty] | 472DWDM | DWDM | CLOSED |  |  |  | 2025-05-06 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\DWDM\Artefact - T91 & T92 |  | 1 | Completed & Approved | Closed before june-2025
93 | T92 | 472 | NA |  |  |  | DWDM | Design & Documentation | Link ATP |  |  | Colosed | [7 empty] | Suresh Kumar |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-05-06 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\DWDM\Artefact - T91 & T92 | [6 empty] | 472DWDM | DWDM | CLOSED |  |  |  | 2025-05-06 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\DWDM\Artefact - T91 & T92 |  | 1 | Completed & Approved | Closed before june-2025
94 | T93 | 472 | NA |  |  |  | DWDM | Design & Documentation | Ring ATP |  |  | Colosed | [7 empty] | Suresh Kumar |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-05-06 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\DWDM\Artefact - T93 | [6 empty] | 472DWDM | DWDM | CLOSED |  |  |  | 2025-05-06 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\DWDM\Artefact - T93 |  | 1 | Completed & Approved | Closed before june-2025
95 | T94 | 472 | NA |  |  |  | DWDM | Design & Documentation | DWDM EMS (MCP) Functional ATP |  |  | Open |  |  |  |  | 20-Sep-25: MCP FAT document submitted to TPA on XX-XX-XXXX. Meeting need to be scheduled on 22-Sep-25 with TPA to get the clarifications on delay. 13-Sep-25: Response awaited from TPA team 29-August-2025: Spoken with Mr. Bijju, response awaited 26-July-25: FAT document approval pending 08-July-2025: 1. MCP FAT document prepared as per RFP requirements and TPA remarks 2. 100G traffic throughput will be shown during Ring ATP 07-July-2025: 1. SME not aware of MCP FAT Check list, but prepared FAT document and sent to TPA for validation 05-July-2025: Submitted AT document to T Fiber TPA 30-June-2025: target to submit by 2nd July'25, based on OEM reply Revised version to be submitted as per T Fiber remarks on 29th Apr'25 | TPA | Biju | Suresh Kumar |  | Open | WIP | [9 empty] | 472DWDM | DWDM | OPEN |  |  | Pending from TPA |  |  |  | 1 | Open | Open
96 | T95 | 472 | NA |  |  |  | DWDM | Integration with OSS | DWDM Network Alarms Integration |  |  | Colosed | [7 empty] | Suresh Kumar |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-05-06 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\DWDM\Artefact - T95 | [6 empty] | 472DWDM | DWDM | CLOSED |  |  |  | 2025-05-06 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\DWDM\Artefact - T95 |  | 1 | Completed & Approved | Closed before june-2025
97 | T96 | 472 | NA |  |  |  | DWDM | Integration with OSS | Hardware Inventory Integration in HPE OSS |  |  | Colosed | [7 empty] | Suresh Kumar |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-05-06 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\DWDM\Artefact - T96 | [6 empty] | 472DWDM | DWDM | CLOSED |  |  |  | 2025-05-06 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\DWDM\Artefact - T96 |  | 1 | Completed & Approved | Closed before june-2025
98 | T97 | 472 | NA |  |  |  | DWDM | Integration with OSS | DWDM Network Topology |  |  | Open |  |  |  |  | 26-July-2025: HPE conveyed that Topology border unable to make bold or hilight 12-July-2025: Update awaited from HPE 07-July-2025: Topology is visible but border is not highlighted. HP checking for the possibility to impose of border map on topology. Required 02 weeks post confirmation 05-July-2025: In discussion with HPE, required 02 weeks post confirmation, 21st July 30-June-2025: As discussed with Suresh P checking with HPE. Tentative date: 16th July. As discussed in the meeting, call to be arranged along with OSS SME and HP team | HPE | Anand | Suresh Kumar |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | 472DWDM | DWDM | OPEN | [6 empty] | 1 | Open | Open
99 | T98 | 472 | NA |  |  |  | DWDM | Integration with OSS | Auto Ticket & RCA for Fiber Cuts |  |  | Colosed | [7 empty] | Suresh Kumar |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-05-06 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\DWDM\Artefact - T98 | [6 empty] | 472DWDM | DWDM | CLOSED |  |  |  | 2025-05-06 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\DWDM\Artefact - T98 |  | 1 | Completed & Approved | Closed before june-2025
100 | T99 | 472 | NA |  |  |  | DWDM | Integration with OSS | Auto Ticket & RCA for Hardware Failures |  |  | Open | [7 empty] | Suresh Kumar |  |  | COMPLETED & APPROVED | [9 empty] | 472DWDM | DWDM | Open |  |  |  |  | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\DWDM\Artefact - T99 |  | 1 | Completed & Approved | Closed after June
101 | T100 | 472 | NA |  |  |  | DWDM | Integration with OSS | Auto Ticket & RCA for Infra Failures |  |  | Open |  |  |  |  | 20-Sep-25: Required configuration changes was done by HPE team. DWDM team will validate and confirm by 23-Sep-25 13-09-25: Few issues observed, corrected by HP. Validation is in progress 10-08-2025: HP team confirmed cause of failure updated, validation is in progress 26-July-2025: Raised the concerns to HP team, cause of failure yet to update by them, Target date awaited9 12-July-2025: Configuration updated in production and RCA TT's for node down are generating. But having issue in cause of failure, same informed to HP team. Target date - 18-07-25 05-July-2025: Cofiguration in production planned on 8th July'25 30-June-25: WIP with HPE, target date 09-07-25 As discussed in the meeting, call to be arranged along with OSS SME and HP team 15-06-2025: WIP with HPE, target date 30-06-2025 21-05-2025: RCA Yet to be started by HPE, date: 30th June 2025 30APR'25: Node down Auto TT is ok but RCA pending | L&T |  | Suresh Kumar |  |  | COMPLETED & APPROVED | [9 empty] | 472DWDM | DWDM | CLOSED |  |  |  | 2025-09-23 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\DWDM\Artefact 100 |  | 1 | Completed & Approved | Closed after June
102 | T101 | 472 | NA |  |  |  | DWDM | Integration with OSS | Network and service performance monitoring KPIs report in HPE OSS |  |  | Colosed | [7 empty] | Suresh Kumar |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-05-06 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\DWDM\Artefact - T101 | [6 empty] | 472DWDM | DWDM | CLOSED |  |  |  | 2025-05-06 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\DWDM\Artefact - T101 |  | 1 | Completed & Approved | Closed before june-2025
103 | T102 | 472 | NA |  |  |  | DWDM | Integration with OSS | Bandwidth Utilization Data in HPE OSS |  |  | Colosed | [7 empty] | Suresh Kumar |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-05-06 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\DWDM\Artefact - T102 | [6 empty] | 472DWDM | DWDM | CLOSED |  |  |  | 2025-05-06 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\DWDM\Artefact - T102 |  | 1 | Completed & Approved | Closed before june-2025
104 | T103 | 472 | NA |  |  |  | DWDM | Integration with OSS | Service Inventory Data Availibilty in HPE OSS |  |  | Open |  |  |  |  | Post 24.06.25 review and direction, working for a alternate options for NSO. will come back as earliest with closure plan. | NSO | Jayanth | Suresh Kumar |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | 472DWDM | DWDM | OPEN | [6 empty] | 1 | Open | Open
105 | T104 | 472 | NA |  |  |  | DWDM | Integration with OSS | Planned Event Service Impact analysis report |  |  | Open |  |  |  |  | Post 24.06.25 review and direction, working for a alternate options for NSO. will come back as earliest with closure plan. | NSO | Jayanth | Suresh Kumar |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | 472DWDM | DWDM | OPEN | [6 empty] | 1 | Open | Open
106 | T105 | 472 | NA |  |  |  | DWDM | Integration with NSO | 1+1 , 1+0 and 1+R service provisioning testing through NSO |  |  | Open |  |  |  |  | Post 24.06.25 review and direction, working for a alternate options for NSO. will come back as earliest with closure plan. | NSO | Jayanth | Suresh Kumar |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | 472DWDM | DWDM | OPEN | [6 empty] | 1 | Open | Open
107 | T108 | 472 | NA |  |  |  | GIS | Data gathering | Data Gathering for RFS Mandals |  |  | Open | Conflict |  |  |  | 256 Mandal uploaded and AT Completed for 250 Mandals,Ongoing & Approved |  |  | Kaushalendra Kumar |  | Open | Ongoing | Approval Email received from NOC Director & TPA | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T108 | [6 empty] | 472GIS | Applications/Tools | #N/A |  |  |  | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T108 | Ongoing Activity | 1 | Open | Open
108 | T109 | 472 | NA |  |  |  | GIS | Data gathering | Data Upload of RFS Mandals |  |  | Open | Conflict |  |  |  | 256 Mandal uploaded and AT Completed for 250 Mandals,Ongoing & Approved |  |  | Kaushalendra Kumar |  | Open | Ongoing | Approval Email received from NOC Director & TPA | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T109 | [6 empty] | 472GIS | Applications/Tools | #N/A |  |  |  | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T109 | Ongoing Activity | 1 | Open | Open
109 | T110 | 472 | NA |  |  |  | GIS | Basic Readiness | Each Package 5 Mandal (Total-15 Mandal) Upload |  |  | Colosed |  | 1 |  |  | As a PoC, 15 Mandals data uploaded for testing purpose |  |  | Kaushalendra Kumar |  |  | Completed & Approved | Approval Email received from NOC Director & TPA | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T110 | [6 empty] | 472GIS | Applications/Tools | CLOSED |  |  |  | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T110 |  | 1 | Completed & Approved | Closed before june-2025
110 | T111 | 472 | NA |  |  |  | GIS | Deployment | GIS Hardware & Software deployment at DC |  |  | Colosed |  | 1 |  |  | HA Re-Testing Planned with TPA & TFIBER on 2nd June 2025 |  |  | Kaushalendra Kumar |  |  | Completed & Approved | Approval Email received from NOC Director & TPA | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T111 | [6 empty] | 472GIS | Applications/Tools | CLOSED |  |  |  | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T111 |  | 1 | Completed & Approved | Closed before june-2025
111 | T112 | 472 | NA |  |  |  | GIS | Deployment | High Availability & Load Balancer Testing |  |  | Open |  |  |  |  | Awaiting for approval from TFIBER & TPA |  |  | Kaushalendra Kumar |  |  | Completed & Approved | Approved By TFIBER NOC AD | 2025-07-07 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T112 | [6 empty] | 472GIS | Applications/Tools | CLOSED |  |  |  | 2025-07-07 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T112 |  | 1 | Completed & Approved | Closed after June
112 | T113 | 472 | NA |  |  |  | GIS | Deployment | PCs & Licences (G-tech, DI, Geo Media) |  |  | Open |  |  |  |  | Tool & PCs has been installed in NOC GIS room. for Licesnes dependecy on T FIber. During the meeting, the Managing Director of T-Fiber directed that only the minimum number of additional licenses will be procured, and T-Fiber will handle the procurement |  |  | Kaushalendra Kumar |  |  | Completed & Approved |  |  | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T113 | [6 empty] | 472GIS | Applications/Tools | CLOSED |  |  |  | After Jun-25 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T113 |  | 1 | Completed & Approved | Closed after June
113 | T114 | 472 | NA |  |  |  | GIS | Deployment | G-Tech |  |  | Colosed |  | 1 | [5 empty] | Kaushalendra Kumar |  |  | Completed & Approved | Approval Email received from NOC Director & TPA | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T114 | [6 empty] | 472GIS | Applications/Tools | CLOSED |  |  |  | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T114 |  | 1 | Completed & Approved | Closed before june-2025
114 | T115 | 472 | NA |  |  |  | GIS | Deployment | Network Portal |  |  | Colosed |  | 1 |  |  | Network Portal in Production and provided by the approval NoC team but need to demonstarte for Core team |  |  | Kaushalendra Kumar |  |  | Completed & Approved | Approval Email received from NOC Director & TPA | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T115 | [6 empty] | 472GIS | Applications/Tools | CLOSED |  |  |  | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T115 |  | 1 | Completed & Approved | Closed before june-2025
115 | T116 | 472 | NA |  |  |  | GIS | Deployment | Mobile App |  |  | Colosed |  | 1 |  |  | Mobile App in Production and provided by the approval NoC team but need to demonstarte for Core team |  |  | Kaushalendra Kumar |  |  | Completed & Approved | Approval Email received from NOC Director & TPA | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T116 | [6 empty] | 472GIS | Applications/Tools | CLOSED |  |  |  | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T116 |  | 1 | Completed & Approved | Closed before june-2025
116 | T117 | 472 | NA |  |  |  | GIS | DC-DR | Requirement Vs Solution |  |  | Open |  |  |  |  | #N/A |  |  | Kaushalendra Kumar |  |  | Completed & Approved | Completed & Approved by TNOC-AD | 2025-07-09 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T117 | [6 empty] | 472GIS | Applications/Tools | CLOSED |  |  |  | 2025-07-09 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T117 |  | 1 | Completed & Approved | Closed after June
117 | T118 | 472 | NA |  |  |  | GIS | DC-DR | DC-DR Testing |  |  | Open |  |  |  |  | DC-DR Testing completed & Document has been kept on share drive,Awaiting TFIBER Approval |  |  | Kaushalendra Kumar |  |  | Completed & Approved | Completed & Approved by TNOC-AD | 2025-07-09 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T118 | [6 empty] | 472GIS | Applications/Tools | CLOSED |  |  |  | 2025-07-09 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T118 |  | 1 | Completed & Approved | Closed after June
118 | T119 | 472 | NA |  |  |  | GIS | Basic Readiness | Google Map API configuration |  |  | Colosed |  | 1 | [5 empty] | Kaushalendra Kumar |  |  | Completed & Approved | Approval Email received from NOC Director & TPA | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T119 | [6 empty] | 472GIS | Applications/Tools | CLOSED |  |  |  | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T119 |  | 1 | Completed & Approved | Closed before june-2025
119 | T120 | 472 | NA |  |  |  | GIS | Basic Readiness | Fixing of telco Boundaries in GIS |  |  | Colosed |  | 1 | [5 empty] | Kaushalendra Kumar |  |  | Completed & Approved | Approval Email received from NOC Director & TPA | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T120 | [6 empty] | 472GIS | Applications/Tools | CLOSED |  |  |  | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T120 |  | 1 | Completed & Approved | Closed before june-2025
120 | T121 | 472 | NA |  |  |  | GIS | Basic Readiness | Data Model Optimization |  |  | Colosed |  | 1 | [5 empty] | Kaushalendra Kumar |  |  | Completed & Approved | Approval Email received from NOC Director & TPA | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\ | [6 empty] | 472GIS | Applications/Tools | CLOSED |  |  |  | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\ |  | 1 | Completed & Approved | Closed before june-2025
121 | T122 | 472 | NA |  |  |  | GIS | Basic Readiness | ISP/OSP object modelling in tool as per T-Fibre |  |  | Colosed |  | 1 | [5 empty] | Kaushalendra Kumar |  |  | Completed & Approved | Approval Email received from NOC Director & TPA | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T122 | [6 empty] | 472GIS | Applications/Tools | CLOSED |  |  |  | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T122 |  | 1 | Completed & Approved | Closed before june-2025
122 | T123 | 472 | NA |  |  |  | GIS | Basic Readiness | Make & Model deployment against all object as per T-Fibre Project |  |  | Colosed |  | 1 | [5 empty] | Kaushalendra Kumar |  |  | Completed & Approved | Approval Email received from NOC Director & TPA | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T123 | [6 empty] | 472GIS | Applications/Tools | CLOSED |  |  |  | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T123 |  | 1 | Completed & Approved | Closed before june-2025
123 | T124 | 472 | NA |  |  |  | GIS | Basic Readiness | Device (Active/Passive) ( All Type as per T-Fibre Project) & Port Modelling In Tool |  |  | Colosed |  | 1 | [5 empty] | Kaushalendra Kumar |  |  | Completed & Approved | Approval Email received from NOC Director & TPA | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\ | [6 empty] | 472GIS | Applications/Tools | CLOSED |  |  |  | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\ |  | 1 | Completed & Approved | Closed before june-2025
124 | T125 | 472 | NA |  |  |  | GIS | Basic Readiness | Correction In Fttx Network placement rules (GP To GI) |  |  | Colosed |  | 1 | [5 empty] | Kaushalendra Kumar |  |  | Completed & Approved | Approval Email received from NOC Director & TPA | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\ | [6 empty] | 472GIS | Applications/Tools | CLOSED |  |  |  | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\ |  | 1 | Completed & Approved | Closed before june-2025
125 | T126 | 472 | NA |  |  |  | GIS | Basic Readiness | Fine tuning or Enable of Cart feature. ( Pan, Zoom, Vertex, Selection method, ruler Etc.) |  |  | Colosed |  | 1 | [5 empty] | Kaushalendra Kumar |  |  | Completed & Approved | Approval Email received from NOC Director & TPA | 2025-06-02 | D:\T-Fiber Project\Hexagon GIS\Artefacts Of T-NOC Tracker\T126 | [6 empty] | 472GIS | Applications/Tools | CLOSED |  |  |  | 2025-06-02 | D:\T-Fiber Project\Hexagon GIS\Artefacts Of T-NOC Tracker\T126 |  | 1 | Completed & Approved | Closed before june-2025
126 | T127 | 472 | NA |  |  |  | GIS | Basic Readiness | Trace Feature ( Link/Spare/Topology) |  |  | Colosed |  | 1 | [5 empty] | Kaushalendra Kumar |  |  | Completed & Approved | Approval Email received from NOC Director & TPA | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T127 | [6 empty] | 472GIS | Applications/Tools | CLOSED |  |  |  | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T127 |  | 1 | Completed & Approved | Closed before june-2025
127 | T128 | 472 | NA |  |  |  | GIS | Basic Readiness | Reports (Fibre Utilisation, BOQ, Area selection, ISP/OSP Quantify) |  |  | Colosed |  | 1 | [5 empty] | Kaushalendra Kumar |  |  | Completed & Approved | Approval Email received from NOC Director & TPA | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T128 | [6 empty] | 472GIS | Applications/Tools | CLOSED |  |  |  | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T128 |  | 1 | Completed & Approved | Closed before june-2025
128 | T129 | 472 | NA |  |  |  | GIS | Basic Readiness | Document/Image Upload feature |  |  | Colosed |  | 1 | [5 empty] | Kaushalendra Kumar |  |  | Completed & Approved | Approval Email received from NOC Director & TPA | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\ | [6 empty] | 472GIS | Applications/Tools | CLOSED |  |  |  | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\ |  | 1 | Completed & Approved | Closed before june-2025
129 | T130 | 472 | NA |  |  |  | GIS | Basic Readiness | Port level & Fibre stand lever attribute |  |  | Colosed |  | 1 | [5 empty] | Kaushalendra Kumar |  |  | Completed & Approved | Approval Email received from NOC Director & TPA | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T130 | [6 empty] | 472GIS | Applications/Tools | CLOSED |  |  |  | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T130 |  | 1 | Completed & Approved | Closed before june-2025
130 | T131 | 472 | NA |  |  |  | GIS | Basic Readiness | Topology Highlight feature |  |  | Colosed |  | 1 | [5 empty] | Kaushalendra Kumar |  |  | Completed & Approved | Approval Email received from NOC Director & TPA | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T131 | [6 empty] | 472GIS | Applications/Tools | CLOSED |  |  |  | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T131 |  | 1 | Completed & Approved | Closed before june-2025
131 | T132 | 472 | NA |  |  |  | GIS | Basic Readiness | Data Model G-TECH Alignment |  |  | Colosed |  | 1 | [5 empty] | Kaushalendra Kumar |  |  | Completed & Approved | Approval Email received from NOC Director & TPA | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T132 | [6 empty] | 472GIS | Applications/Tools | CLOSED |  |  |  | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T132 |  | 1 | Completed & Approved | Closed before june-2025
132 | T133 | 472 | NA |  |  |  | GIS | Basic Readiness | DI alignment as per new 35 Layer data model |  |  | Colosed |  | 1 | [5 empty] | Kaushalendra Kumar |  |  | Completed & Approved | Approval Email received from NOC Director & TPA | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\ | [6 empty] | 472GIS | Applications/Tools | CLOSED |  |  |  | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\ |  | 1 | Completed & Approved | Closed before june-2025
133 | T134 | 472 | NA |  |  |  | GIS | Basic Readiness | Active to Passive, Active to active connectivity correction |  |  | Colosed |  | 1 | [5 empty] | Kaushalendra Kumar |  |  | Completed & Approved | Approval Email received from NOC Director & TPA | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T134 | [6 empty] | 472GIS | Applications/Tools | CLOSED |  |  |  | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T134 |  | 1 | Completed & Approved | Closed before june-2025
134 | T135 | 472 | NA |  |  |  | GIS | Basic Readiness | DI processing timing optimisation |  |  | Colosed |  | 1 | [5 empty] | Kaushalendra Kumar |  |  | Completed & Approved | Approval Email received from NOC Director & TPA | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\ | [6 empty] | 472GIS | Applications/Tools | CLOSED |  |  |  | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\ |  | 1 | Completed & Approved | Closed before june-2025
135 | T136 | 472 | NA |  |  |  | GIS | Basic Readiness | Rack to Rack Connectivity |  |  | Colosed |  | 1 | [5 empty] | Kaushalendra Kumar |  |  | Completed & Approved | Approval Email received from NOC Director & TPA | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T136 | [6 empty] | 472GIS | Applications/Tools | CLOSED |  |  |  | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T136 |  | 1 | Completed & Approved | Closed before june-2025
136 | T137 | 472 | NA |  |  |  | GIS | Advance Readiness | Graphical Symbology deployment against all object |  |  | Colosed |  | 1 | [5 empty] | Kaushalendra Kumar |  |  | Completed & Approved | Approval Email received from NOC Director & TPA | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T137 | [6 empty] | 472GIS | Applications/Tools | CLOSED |  |  |  | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T137 |  | 1 | Completed & Approved | Closed before june-2025
137 | T138 | 472 | NA |  |  |  | GIS | Advance Readiness | Fixing Of Labelling (Sequencing & Attributes) |  |  | Colosed |  | 1 | [5 empty] | Kaushalendra Kumar |  |  | Completed & Approved | Approval Email received from NOC Director & TPA | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T138 | [6 empty] | 472GIS | Applications/Tools | CLOSED |  |  |  | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T138 |  | 1 | Completed & Approved | Closed before june-2025
138 | T139 | 472 | NA |  |  |  | GIS | Advance Readiness | Object search options to user |  |  | Colosed |  | 1 | [5 empty] | Kaushalendra Kumar |  |  | Completed & Approved | Approval Email received from NOC Director & TPA | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T139 | [6 empty] | 472GIS | Applications/Tools | CLOSED |  |  |  | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T139 |  | 1 | Completed & Approved | Closed before june-2025
139 | T140 | 472 | NA |  |  |  | GIS | Advance Readiness | G-tech to .shp & Kml conversion |  |  | Colosed |  | 1 | [5 empty] | Kaushalendra Kumar |  |  | Completed & Approved | Approval Email received from NOC Director & TPA | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T140 | [6 empty] | 472GIS | Applications/Tools | CLOSED |  |  |  | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T140 |  | 1 | Completed & Approved | Closed before june-2025
140 | T141 | 472 | NA |  |  |  | GIS | Advance Readiness | Plotting & Print Feature |  |  | Colosed |  | 1 | [5 empty] | Kaushalendra Kumar |  |  | Completed & Approved | Approval Email received from NOC Director & TPA | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T141 | [6 empty] | 472GIS | Applications/Tools | CLOSED |  |  |  | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T141 |  | 1 | Completed & Approved | Closed before june-2025
141 | T142 | 472 | NA |  |  |  | GIS | Advance Readiness | 4 More API from Google Map |  |  | Colosed |  | 1 | [5 empty] | Kaushalendra Kumar |  |  | Completed & Approved | Approval Email received from NOC Director & TPA | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T142 | [6 empty] | 472GIS | Applications/Tools | CLOSED |  |  |  | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T142 |  | 1 | Completed & Approved | Closed before june-2025
142 | T143 | 472 | NA |  |  |  | GIS | Advance Readiness | Fibre Utilisation Reports |  |  | Colosed |  | 1 | [5 empty] | Kaushalendra Kumar |  |  | Completed & Approved | Approval Email received from NOC Director & TPA | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T143 | [6 empty] | 472GIS | Applications/Tools | CLOSED |  |  |  | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T143 |  | 1 | Completed & Approved | Closed before june-2025
143 | T144 | 472 | NA |  |  |  | GIS | Advance Readiness | Consolidated reports from GIS |  |  | Colosed |  | 1 | [5 empty] | Kaushalendra Kumar |  |  | Completed & Approved | Approval Email received from NOC Director & TPA | 2025-06-02 | D:\T-Fiber Project\Hexagon GIS\Artefacts Of T-NOC Tracker\T144 | [6 empty] | 472GIS | Applications/Tools | CLOSED |  |  |  | 2025-06-02 | D:\T-Fiber Project\Hexagon GIS\Artefacts Of T-NOC Tracker\T144 |  | 1 | Completed & Approved | Closed before june-2025
144 | T145 | 472 | NA |  |  |  | GIS | Advance Readiness | Link trace Reports |  |  | Colosed |  | 1 | [5 empty] | Kaushalendra Kumar |  |  | Completed & Approved | Approval Email received from NOC Director & TPA | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T145 | [6 empty] | 472GIS | Applications/Tools | CLOSED |  |  |  | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T145 |  | 1 | Completed & Approved | Closed before june-2025
145 | T146 | 472 | NA |  |  |  | GIS | Advance Readiness | Consolidation/Customization of Dashboard feature in G-tech, Network Portal |  |  | Colosed |  | 1 | [5 empty] | Kaushalendra Kumar |  |  | Completed & Approved | Approval Email received from NOC Director & TPA | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T146 | [6 empty] | 472GIS | Applications/Tools | CLOSED |  |  |  | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T146 |  | 1 | Completed & Approved | Closed before june-2025
146 | T147 | 472 | NA |  |  |  | GIS | Advance Readiness | Network data availability in G-Tech & Network portal & Geo media |  |  | Colosed |  | 1 | [5 empty] | Kaushalendra Kumar |  |  | Completed & Approved | Approval Email received from NOC Director & TPA | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T147 | [6 empty] | 472GIS | Applications/Tools | CLOSED |  |  |  | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T147 |  | 1 | Completed & Approved | Closed before june-2025
147 | T148 | 472 | NA |  |  |  | GIS | Advance Readiness | Final Demo to customer |  |  | Colosed |  | 1 | [5 empty] | Kaushalendra Kumar |  |  | Completed & Approved | Approval Email received from NOC Director & TPA | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T148 | [6 empty] | 472GIS | Applications/Tools | CLOSED |  |  |  | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T148 |  | 1 | Completed & Approved | Closed before june-2025
148 | T149 | 472 | NA |  |  |  | GIS | Mobile Applications | Network availability in Mobile application with G-MAP |  |  | Colosed |  | 1 | [5 empty] | Kaushalendra Kumar |  |  | Completed & Approved | Approval Email received from NOC Director & TPA | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T149 | [6 empty] | 472GIS | Applications/Tools | CLOSED |  |  |  | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T149 |  | 1 | Completed & Approved | Closed before june-2025
149 | T150 | 472 | NA |  |  |  | GIS | Mobile Applications | Red line, Red Point Feature deployment in Mobile application |  |  | Colosed |  | 1 | [5 empty] | Kaushalendra Kumar |  |  | Completed & Approved | Approval Email received from NOC Director & TPA | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T150 | [6 empty] | 472GIS | Applications/Tools | CLOSED |  |  |  | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T150 |  | 1 | Completed & Approved | Closed before june-2025
150 | T151 | 472 | NA |  |  |  | GIS | Mobile Applications | JOB creation testing in GIS tool from GIS Mobile app |  |  | Colosed |  | 1 | [5 empty] | Kaushalendra Kumar |  |  | Completed & Approved | Approval Email received from NOC Director & TPA | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T151 | [6 empty] | 472GIS | Applications/Tools | CLOSED |  |  |  | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T151 |  | 1 | Completed & Approved | Closed before june-2025
151 | T152 | 472 | NA |  |  |  | GIS | Design & Documentation | Feasible Points closure of workshop |  |  | Colosed |  | 1 | [5 empty] | Kaushalendra Kumar |  |  | Completed & Approved | Approval Email received from NOC Director & TPA | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T152 | [6 empty] | 472GIS | Applications/Tools | CLOSED |  |  |  | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T152 |  | 1 | Completed & Approved | Closed before june-2025
152 | T153 | 472 | NA |  |  |  | GIS | Resources | Resources onboarding, Licences arrangement, Workstation plan |  |  | Open |  |  |  |  | Resource & PCs has been deployed in NOC GIS room. for Licesnes dependecy on T FIber. |  |  | Kaushalendra Kumar |  |  | Completed & Approved |  |  | Resources and workstations have already been deployed in the NOC GIS Room. Decisions regarding additional licenses need to be made by L&T and TFIBER | [6 empty] | 472GIS | Applications/Tools | CLOSED |  |  |  | After Jun-25 | Artefacts not Required |  | 1 | Completed & Approved | Closed after June
153 | T154 | 472 | NA |  |  |  | GIS | Data gathering | T-NOC Creation in GIS Tool with connectivity |  |  | Colosed |  | 1 | [5 empty] | Kaushalendra Kumar |  |  | Completed & Approved | Approval Email received from NOC Director & TPA | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T154 | [6 empty] | 472GIS | Applications/Tools | CLOSED |  |  |  | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T154 |  | 1 | Completed & Approved | Closed before june-2025
154 | T155 | 472 | NA |  |  |  | GIS | Design & Documentation | SOP Creation |  |  | Colosed |  | 1 | [5 empty] | Kaushalendra Kumar |  |  | Completed & Approved | Approval Email received from NOC Director & TPA | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T155 | [6 empty] | 472GIS | Applications/Tools | CLOSED |  |  |  | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T155 |  | 1 | Completed & Approved | Closed before june-2025
155 | T156 | 472 | NA |  |  |  | GIS | MoM Action | MB kilometers vs UG and arial to path and over all route length to be added in webapplication |  |  | Colosed |  | 1 | [5 empty] | Kaushalendra Kumar |  |  | Completed & Approved | Approval Email received from NOC Director & TPA | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T156 | [6 empty] | 472GIS | Applications/Tools | CLOSED |  |  |  | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T156 |  | 1 | Completed & Approved | Closed before june-2025
156 | T157 | 472 | NA |  |  |  | GIS | MoM Action | 3 Formats of Lat long (DMS, DMM & Mtr) required in Hexagon tool |  |  | Colosed |  | 1 | [5 empty] | Kaushalendra Kumar |  |  | Completed & Approved | Approval Email received from NOC Director & TPA | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T157 | [6 empty] | 472GIS | Applications/Tools | CLOSED |  |  |  | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T157 |  | 1 | Completed & Approved | Closed before june-2025
157 | T158 | 472 | NA |  |  |  | GIS | MoM Action | GIS LLD submitted to T-Fiber on 02.03.2025, to be discussed with T-Fiber |  |  | Open |  |  |  |  | Resubmission done after discussion. Date-19.03.25. queries on LLD with mail dated 25.03.25 |  |  | Kaushalendra Kumar |  |  | Completed & Approved |  |  | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T158 | [6 empty] | 472GIS | Applications/Tools | CLOSED |  |  |  | After Jun-25 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T158 |  | 1 | Completed & Approved | Closed after June
158 | T159 | 472 | NA |  |  |  | GIS | Integration | Physical Device sync-up with OSS System |  |  | Open |  |  |  |  | Integration with OSS Is WIP |  |  | Kaushalendra Kumar |  | Open | WIP |  |  | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T159 | [6 empty] | 472GIS | Applications/Tools | OPEN |  |  |  |  | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T159 | 2025-10-20 | 1 | Open | Open
159 | T160 | 472 | NA |  |  |  | GIS | Integration | Common Span Path |  |  | Open |  |  |  |  | Integration with OSS Is WIP |  |  | Kaushalendra Kumar |  | Open | WIP |  |  | Dependency On Physical Device Syn-up (Integration) & alarm corelation | [6 empty] | 472GIS | Applications/Tools | OPEN |  |  |  |  | Dependency On Physical Device Syn-up (Integration) & alarm corelation | 2025-11-05 | 1 | Open | Open
160 | T161 | 472 | NA |  |  |  | GIS | Integration | Auto feasibility |  |  | Open |  |  |  |  | BSS(knot) has demonstrated the Auto Feasibility feature for single location business cases. If, Customer is expecting Bulk feasibility capabilities, which is not a feature of GIS, required external tool. |  |  | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING |  |  | Multiple demonstrations were provided to showcase auto-feasibility during the GIBB demo | [6 empty] | 472GIS | Applications/Tools | OPEN |  |  |  |  | Multiple demonstrations were provided to showcase auto-feasibility during the GIBB demo |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
161 | T162 | 472 | NA |  |  |  | GPON | Tejas-Design & Documentation | Customer Requirement Document |  |  | Colosed | [7 empty] | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T162 | [6 empty] | 472GPON | GPON | CLOSED |  |  |  | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T162 |  | 1 | Completed & Approved | Closed before june-2025
162 | T163 | 472 | NA |  |  |  | GPON | Tejas-Design & Documentation | HLD |  |  | Colosed | [7 empty] | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T163 Please refer Section-3 in E2E Network HLD | [6 empty] | 472GPON | GPON | CLOSED |  |  |  | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T163 Please refer Section-3 in E2E Network HLD |  | 1 | Completed & Approved | Closed before june-2025
163 | T164 | 472 | NA |  |  |  | GPON | Nokkia-Design & Documentation | LLD for 152 Mandals |  |  | Colosed | [7 empty] | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T164 | [6 empty] | 472GPON | GPON | CLOSED |  |  |  | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T164 |  | 1 | Completed & Approved | Closed before june-2025
164 | T165 | 472 | NA |  |  |  | GPON | Tejas | Latest EMS Integration with OSS (Hold due to CR) |  |  | Colosed | [7 empty] | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T165 | [6 empty] | 472GPON | GPON | CLOSED |  |  |  | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T165 |  | 1 | Completed & Approved | Closed before june-2025
165 | T166 | 472 | NA |  |  |  | GPON | Tejas | * Testing done for new build in T-Fiber test lab . * Plan event for OLTs new SW upgradation in production environment. |  |  | Open |  | Tejas OEM | OLT |  | 13-Oct-25: GPON SME has to provide the breakup for all Pending OLT upgradation activities, need to send a mail to concern packages with respective pending OLT upgradation. 20-Sep-25: All the reachable OLT to EMS are upgraded successfully. And Not reachbale OLTs need to be upgraded, There is a dependecny on All 3 Packages field teams to make reachability to EMS. GPON SME need to submit detailed report on Scope vs upgraded and Pending devices breakup(Package wise). | All Packages | Srinivas Kodali(PKG_A), Venu& Mahesh(PKG B&C) | Sayyad Pasha |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | 472GPON | GPON | OPEN | [6 empty] | 1 | Open | Open
166 | T167 | 472 | NA |  |  |  | GPON | Tejas | TACACS Feature |  |  | Colosed | [7 empty] | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T167 | [6 empty] | 472GPON | GPON | CLOSED |  |  |  | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T372 |  | 1 | Completed & Approved | Closed before june-2025
167 | T168 | 472 | NA |  |  |  | GPON | Tejas | Authentication & Authorization with RAIDUS |  |  | Colosed | [7 empty] | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T168 | [6 empty] | 472GPON | GPON | CLOSED |  |  |  | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T168 |  | 1 | Completed & Approved | Closed before june-2025
168 | T169 | 472 | NA |  |  |  | GPON | Tejas | EMS authentication & Authorization with Alepo |  |  | Colosed | [7 empty] | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T169 | [6 empty] | 472GPON | GPON | CLOSED |  |  |  | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T169 |  | 1 | Completed & Approved | Closed before june-2025
169 | T170 | 472 | NA |  |  |  | GPON | Nokia | Accounting Feature with New build & Logs filteration |  |  | Colosed | [7 empty] | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T170 | [6 empty] | 472GPON | GPON | CLOSED |  |  |  | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T170 |  | 1 | Completed & Approved | Closed before june-2025
170 | T171 | 472 | NA |  |  |  | GPON | Tejas | Accounting Feature with New build & Logs filteration |  |  | Colosed | [7 empty] | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T171 | [6 empty] | 472GPON | GPON | CLOSED |  |  |  | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T170 |  | 1 | Completed & Approved | Closed before june-2025
171 | T172 | 472 | NA |  |  |  | GPON | Tejas | Tejas EMS ATP |  |  | Colosed | [7 empty] | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T172 | [6 empty] | 472GPON | GPON | CLOSED |  |  |  | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T172 |  | 1 | Completed & Approved | Closed before june-2025
172 | T173 | 472 | NA |  |  |  | GPON | Tejas | DC-DR Switchover Activity |  |  | Colosed | [7 empty] | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T173 | [6 empty] | 472GPON | GPON | CLOSED |  |  |  | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T173 |  | 1 | Completed & Approved | Closed before june-2025
173 | T174 | 472 | NA |  |  |  | GPON | Tejas | NBI API availability for BW query Dependent on new OLT build, which supposed to released on 31- March23. |  |  | Colosed | [7 empty] | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T174 | [6 empty] | 472GPON | GPON | CLOSED |  |  |  | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T174 |  | 1 | Completed & Approved | Closed before june-2025
174 | T175 | 472 | NA |  |  |  | GPON | Nokia | CR for Nokia API integration to close BW query and PMS related issues |  |  | Open |  | Nokia OEM | AMS |  | Having dependency on Service Inventory and NSO | NSO | Jayanth | Sayyad Pasha |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | 472GPON | GPON | OPEN | [6 empty] | 1 | Open | Open
175 | T176 | 472 | NA |  |  |  | GPON | Nokia | OLT devices status in OSS is not as per AMS. |  |  | Colosed | [7 empty] | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T176 | [6 empty] | 472GPON | GPON | CLOSED |  |  |  | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T176 |  | 1 | Completed & Approved | Closed before june-2025
176 | T177 | 472 | NA |  |  |  | GPON | Nokia | ONT devices have been recovered and validated as per AMS count. |  |  | Colosed | [7 empty] | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T177 | [6 empty] | 472GPON | GPON | CLOSED |  |  |  | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T177 |  | 1 | Completed & Approved | Closed before june-2025
177 | T178 | 472 | NA |  |  |  | GPON | Nokia | Authentication and authorization have been tested with Nokia devices except CB OLT. |  |  | Colosed | [7 empty] | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T178 | [6 empty] | 472GPON | GPON | CLOSED |  |  |  | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T178 |  | 1 | Completed & Approved | Closed before june-2025
178 | T179 | 472 | NA |  |  |  | GPON | Nokia | Tejas ONT firmware upgradation not happing through Nokia OLT. Joint troubleshooting is required with Tejas and Nokia. |  |  | Colosed | [7 empty] | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T179 | [6 empty] | 472GPON | GPON | CLOSED |  |  |  | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T179 |  | 1 | Completed & Approved | Closed before june-2025
179 | T180 | 472 | NA |  |  |  | GPON | Nokia | Nokia ONT to support NAT, DHCP, both Router and Bridge mode |  |  | Open |  | Nokia OEM | ONT |  | Nokia has provided the SOP, which has been tested and is working as expected. However, Nokia ONTs connected to Tejas OLTs cannot be enabled directly through the Tejas OLT. As discussed with TFiber, we have prepared an SOP for the field team and are currently working on mapping the Nokia ONTs under Tejas OLTs to nearby Nokia OLTs |  |  | Sayyad Pasha |  |  | COMPLETED & APPROVED | [9 empty] | 472GPON | GPON | CLOSED |  |  |  | 2025-09-20 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T180 |  | 1 | Completed & Approved | Closed after June
180 | T181 | 472 | NA |  |  |  | GPON | Nokia | Accounting logs are forwarded to Alepo server, same was reflecting in Alepo server but it was forwarding towards syslog server. |  |  | Colosed | [7 empty] | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T181 | [6 empty] | 472GPON | GPON | CLOSED |  |  |  | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T181 |  | 1 | Completed & Approved | Closed before june-2025
181 | T182 | 472 | NA |  |  |  | GPON | Nokia | Nokia EMS functional ATP to be closed with customer |  |  | Open |  | Nokia OEM | AMS |  | Working with OEM 20-Sep-25: ATP document submitted to TPA, And TPA Shared 12 observations related to RFP compliance.Same has been given to OEM for closure. Nokia team provided clarifications for 10 points and 2 points are WIP. GPON team has to share clarifications of 10 points to TPA and need to confirm timelines for remaining 2 points on 23-Sep-25. | Nokia | Sivakasi | Sayyad Pasha |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | 472GPON | GPON | OPEN | [6 empty] | 1 | Open | Open
182 | T183 | 472 | NA |  |  |  | GPON | Nokia | DC-DR Switchover activity need to plan. |  |  | Colosed | [7 empty] | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T183 | [6 empty] | 472GPON | GPON | CLOSED |  |  |  | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T183 |  | 1 | Completed & Approved | Closed before june-2025
183 | T184 | 472 | NA |  |  |  | GPON | Nokia | Nokia OLTs reachability is pending for DR Servers. |  |  | Colosed | [7 empty] | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T184 | [6 empty] | 472GPON | GPON | CLOSED |  |  |  | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T184 |  | 1 | Completed & Approved | Closed before june-2025
184 | T185 | 472 | NA |  |  |  | IP/MPLS | Service Solution | HSI (High Speed Internet to Household) |  |  | Colosed | [7 empty] | RS Rao |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-05-05 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\House Hold HSI Services Design LLD V1.2 - T185.pdf | [6 empty] | 472IP/MPLS | IPMPLS | CLOSED |  |  |  | 2025-05-05 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\House Hold HSI Services Design LLD V1.2 - T185.pdf |  | 1 | Completed & Approved | Closed before june-2025
185 | T186 | 472 | NA |  |  |  | IP/MPLS | Service Solution | IPTV to Household |  |  | Colosed | [7 empty] | RS Rao |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-05-05 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\House Hold IPTV Services Design LLD V1.2 - T186.pdf | [6 empty] | 472IP/MPLS | IPMPLS | CLOSED |  |  |  | 2025-05-05 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\House Hold IPTV Services Design LLD V1.2 - T186.pdf |  | 1 | Completed & Approved | Closed before june-2025
186 | T187 | 472 | NA |  |  |  | IP/MPLS | Service Solution | VOIP to Household |  |  | Colosed | [7 empty] | RS Rao |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-05-05 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\House Hold VoIP Services Design LLD V1.2 - t187.pdf | [6 empty] | 472IP/MPLS | IPMPLS | CLOSED |  |  |  | 2025-05-05 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\House Hold VoIP Services Design LLD V1.2 - t187.pdf |  | 1 | Completed & Approved | Closed before june-2025
187 | T188 | 472 | NA |  |  |  | IP/MPLS | Service Solution | Internet to GI (Govt. Institution) |  |  | Colosed | [7 empty] | RS Rao |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-05-05 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\T-FIBER T-Net for GI Broadband Service Design LLD V1.1 - T188.pdf | [6 empty] | 472IP/MPLS | IPMPLS | CLOSED |  |  |  | 2025-05-05 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\T-FIBER T-Net for GI Broadband Service Design LLD V1.1 - T188.pdf |  | 1 | Completed & Approved | Closed before june-2025
188 | T189 | 472 | NA |  |  |  | IP/MPLS | Service Solution | CCTV Unicast |  |  | Colosed | [7 empty] | RS Rao |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-05-05 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\Centrailzed CCTV Surveillance Monitoring over T-Fiber Network-Solution Doucment_Initial Draft V1.0 - T189.pdf | [6 empty] | 472IP/MPLS | IPMPLS | CLOSED |  |  |  | 2025-05-05 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\Centrailzed CCTV Surveillance Monitoring over T-Fiber Network-Solution Doucment_Initial Draft V1.0 - T189.pdf |  | 1 | Completed & Approved | Closed before june-2025
189 | T190 | 472 | NA |  |  |  | IP/MPLS | Service Solution | CCTV Multicast |  |  | Colosed | [7 empty] | RS Rao |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-05-05 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\CCTV Multicast Solution LLD V1.2 - T190.pdf | [6 empty] | 472IP/MPLS | IPMPLS | CLOSED |  |  |  | 2025-05-05 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\CCTV Multicast Solution LLD V1.2 - T190.pdf |  | 1 | Completed & Approved | Closed before june-2025
190 | T191 | 472 | NA |  |  |  | IP/MPLS | Service Solution | Cell Tower L2VPN |  |  | Colosed | [7 empty] | RS Rao |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-05-05 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\TFIBER T-CELL Service Design & Solution V4.3 T197, T336, T337, T338.pdf | [6 empty] | 472IP/MPLS | IPMPLS | CLOSED |  |  |  | 2025-05-05 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\TFIBER T-CELL Service Design & Solution V4.3 T197, T336, T337, T338.pdf |  | 1 | Completed & Approved | Closed before june-2025
191 | T192 | 472 | NA |  |  |  | IP/MPLS | Service Solution | Dhanush Telemedicine Application |  |  | Colosed | [7 empty] | RS Rao |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-05-05 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\T-FIBER DHANUSH TELEMEDICINE SOLUTION LLD V1.0 - T192.pdf | [6 empty] | 472IP/MPLS | IPMPLS | CLOSED |  |  |  | 2025-05-05 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\T-FIBER DHANUSH TELEMEDICINE SOLUTION LLD V1.0 - T192.pdf |  | 1 | Completed & Approved | Closed before june-2025
192 | T193 | 472 | NA |  |  |  | IP/MPLS | Service Solution | SDC content to Household and GI |  |  | Open |  |  |  |  | 22-Sep-25: Need to review plan and approve 12-Sep-25 : Peering plan submitted as per discussion on 11-Sep-25 01-Jul-25 : Design document submitted with suggested approaches. Require inputs from TFiber to conduct PoC and finalize service design. | T Fiber | Sanjay | RS Rao |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | 472IP/MPLS | IPMPLS | OPEN | [6 empty] | 1 | Open | Open
193 | T194 | 472 | NA |  |  |  | BSS | Service Catalogue | Incremental Product/ Services finalization in T-Fiber network |  |  | Open |  |  |  |  | 01-Jul-25 : Dependecy on Tfiber in PCN (Product Concept Note) finalisation. Tracked in BSS action item T12 (part of 472 tracker) |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | 472BSS | Applications/Tools | OPEN | [6 empty] | 1 | Open | Open
194 | T195 | 472 | NA |  |  |  | IP/MPLS | Service Provisioning | Service Provisioning PoC for SCCM/NSO - L2, L3 VPN |  |  | Open |  |  |  |  | Post 24.06.25 review and direction, working for a alternate options for NSO. will come back as earliest with closure plan. |  |  | Jayant Madavi |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | 472IP/MPLS | IPMPLS | OPEN | [6 empty] | 1 | Open | Open
195 | T196 | 472 | NA |  |  |  | IP/MPLS | Service Provisioning | Service Provisioning PoC for SCCM/NSO - QoS (all scenarios) |  |  | Open |  |  |  |  | Post 24.06.25 review and direction, working for a alternate options for NSO. will come back as earliest with closure plan. |  |  | Jayant Madavi |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | 472IP/MPLS | IPMPLS | OPEN | [6 empty] | 1 | Open | Open
196 | T197 | 472 | NA |  |  |  | IP/MPLS | Service Provisioning | Service Provisioning PoC for SCCM/NSO - MVPN (all scenarios) |  |  | Open |  |  |  |  | Post 24.06.25 review and direction, working for a alternate options for NSO. will come back as earliest with closure plan. |  |  | Jayant Madavi |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | 472IP/MPLS | IPMPLS | OPEN | [6 empty] | 1 | Open | Open
197 | T198 | 472 | NA |  |  |  | IP/MPLS | Network AT | Simulation and testing network for parameters like network convergence etc |  |  | Open |  |  |  |  | 22-Sep-2025: Need to have discussion on Network AT parameters 8-Jul-2025 - Sandeep will come back by EoD today on extension of Cisco support renewal 01-Jul-25 : OEM(Cisco) suport is required to perform network AT, Inputs provided to OEM. OEM to provide Network AT procedure including all tests and test procedures. OEM onboarding is in progress & LnT Contracts team is coordinating | TPA, T Fiber, L&T | Biju,Sanjay, RS Rao | RS Rao |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | 472IP/MPLS | IPMPLS | OPEN | [6 empty] | 1 | Open | Open
198 | T199 | 472 | NA |  |  |  | IP/MPLS | Design & Documentation | HLD |  |  | Colosed | [7 empty] | RS Rao |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-05-05 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\E2E_Network HLD_Part1_V2.0_ 29.10.2020(Approved) - T199.pdf | [6 empty] | 472IP/MPLS | IPMPLS | CLOSED |  |  |  | 2025-05-05 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\E2E_Network HLD_Part1_V2.0_ 29.10.2020(Approved) - T199.pdf |  | 1 | Completed & Approved | Closed before june-2025
199 | T200 | 472 | NA |  |  |  | IP/MPLS | Design & Documentation | Approved conditionally with few punch points. Updated LLD to be submitted |  |  | Open | [5 empty] | Duplicate |  | RS Rao |  |  | COMPLETED & APPROVED | AD-UT, Tfiber (Sanjay ji) | 2025-08-21 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\IP MPLS Network LLD V1.7 14-Aug-2025.pdf | [6 empty] | 472IP/MPLS | IPMPLS | CLOSED |  |  | Duplicate | 2025-08-21 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\IP MPLS Network LLD V1.7 14-Aug-2025.pdf |  | 1 | Completed & Approved | Closed after June
200 | T201 | 472 | NA |  |  |  | IP/MPLS | OSS | FMS Fault Management System (Device, Link ticketing etc) |  |  | Open |  |  |  |  | 22-Sep-25: Auto ticketing verification is depending on OSS, reqiured configguration or changes done in OSS. Now auto ticket is working atrefatcs to be submitted for Node and Link. 08-Jul-25 : Requirement given to OSS for implementation. FMS parameters given 1. Node down (Router, Switch, DC Network Switches, DWDM, OTN, OADM, OLT, UPS) : Field alarm should be received in NNMi. NNMi has to forward the alarm to OBM, NPS and to TeMiP. UCA has to carryout correlation and accordingly pass the root cause to SM to generate TT. once TT is generated it is assigned to respective District Engineer along with mail. After Fault resolution, TT should be resolved in system with alarm clearance and NoC has to close the TT with RFO. Link down, Protocol down, RSP/Card/PSU down, High Temperature, Latency, Packet Loss, Jitter. End-to-end implementation and demonstration pending in OSS | L&T | Suresh Pawar | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | 472IP/MPLS | IPMPLS | OPEN | CLOSURE REVIEW PENDING | 0 |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
201 | T202 | 472 | NA |  |  |  | IP/MPLS | OSS | PMS Performance Management System (Utilization, Errors etc) |  |  | Open |  |  |  |  | 25-Sep-25: Implementation completed, Need to validate and cofirm 07-Jul-25 : Requirement given to OSS for implementation. PMS parameters given - CPU, Memory, Backplane and Link utilization, CRC errors, Optical power, QoS parameters . End-to-end implementation and demonstration pending in OSS | L&T | Suresh Pawar | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | 472IP/MPLS | IPMPLS | OPEN | COMPLETED | 0 |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
202 | T203 | 472 | NA |  |  |  | IP/MPLS | OSS | Dashboard (Network Parameter Dash Boards) |  |  | Open |  |  |  |  | 25-Sep-25: Implementation completed, Need to validate and cofirm 07-Jul-25 : Requirement given to OSS for implementation. Dash Board required - Top CPU, Memory, Link utilization, Temperature, All Critical alarms . Demonstration pending in OSS | L&T | Suresh Pawar | Suresh Pawar |  | Open | WIP | [9 empty] | 472IP/MPLS | IPMPLS | OPEN | OPEN | 0 |  |  |  |  | 1 | Open | Open
203 | T204 | 472 | NA |  |  |  | IP/MPLS | OSS | Reports (Invetory, Device avability, Link Availability) |  |  | Open |  |  |  |  | 25-Sep-25: Reports are available in UOC, Artefacts to be submitted for clsore 07-Jul-25 : Requirement given to OSS for implementation. Reports required - Node availability, Link availability, Link utilization, Inventory, CPU utilization, Memory Utilization, Latecy. Demonstration pending in OSS | L&T | Suresh Pawar | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | 472IP/MPLS | IPMPLS | OPEN | COMPLETED | 0 |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
204 | T205 | 472 | NA |  |  |  | NSO | Installation | Installation of NSO Applications |  |  | Open |  |  |  |  | Post 24.06.25 review and direction, working for a alternate options for NSO. will come back as earliest with closure plan. |  |  | Jayant Madavi |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | 472NSO | Applications/Tools | OPEN | [6 empty] | 1 | Open | Open
205 | T206 | 472 | NA |  |  |  | NSO | Integration | Integration with Third Party Applications/Nodes |  |  | Open |  |  |  |  | Post 24.06.25 review and direction, working for a alternate options for NSO. will come back as earliest with closure plan. |  |  | Jayant Madavi |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | 472NSO | Applications/Tools | OPEN | [6 empty] | 1 | Open | Open
206 | T207 | 472 | NA |  |  |  | NSO | Integration | OSS |  |  | Open |  |  |  |  | Post 24.06.25 review and direction, working for a alternate options for NSO. will come back as earliest with closure plan. |  |  | Jayant Madavi |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | 472NSO | Applications/Tools | OPEN | [6 empty] | 1 | Open | Open
207 | T208 | 472 | NA |  |  |  | NSO | Integration | BSS |  |  | Open |  |  |  |  | Post 24.06.25 review and direction, working for a alternate options for NSO. will come back as earliest with closure plan. |  |  | Jayant Madavi |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | 472NSO | Applications/Tools | OPEN | [6 empty] | 1 | Open | Open
208 | T209 | 472 | NA |  |  |  | NSO | Integration | Nodes |  |  | Open |  |  |  |  | Post 24.06.25 review and direction, working for a alternate options for NSO. will come back as earliest with closure plan. |  |  | Jayant Madavi |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | 472NSO | Applications/Tools | OPEN | [6 empty] | 1 | Open | Open
209 | T210 | 472 | NA |  |  |  | NSO | Integration | EMS-GPON |  |  | Open |  |  |  |  | Post 24.06.25 review and direction, working for a alternate options for NSO. will come back as earliest with closure plan. |  |  | Jayant Madavi |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | 472NSO | Applications/Tools | OPEN | [6 empty] | 1 | Open | Open
210 | T211 | 472 | NA |  |  |  | NSO | Integration | EMS-DWDM |  |  | Open |  |  |  |  | Post 24.06.25 review and direction, working for a alternate options for NSO. will come back as earliest with closure plan. |  |  | Jayant Madavi |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | 472NSO | Applications/Tools | OPEN | [6 empty] | 1 | Open | Open
211 | T212 | 472 | NA |  |  |  | NSO | Development and unit testing | Service verification and provisioning - IP MPLS |  |  | Open |  |  |  |  | Post 24.06.25 review and direction, working for a alternate options for NSO. will come back as earliest with closure plan. |  |  | Jayant Madavi |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | 472NSO | Applications/Tools | OPEN | [6 empty] | 1 | Open | Open
212 | T213 | 472 | NA |  |  |  | NSO | Development and unit testing | Service verification and activation - GPON Nokia and Tejas |  |  | Open |  |  |  |  | Post 24.06.25 review and direction, working for a alternate options for NSO. will come back as earliest with closure plan. |  |  | Jayant Madavi |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | 472NSO | Applications/Tools | OPEN | [6 empty] | 1 | Open | Open
213 | T214 | 472 | NA |  |  |  | NSO | Development and unit testing | SCCM provisioning request for HSI, IPTV, T-Wire,T-VPN,VoIP,CCTV SDD |  |  | Open |  |  |  |  | Post 24.06.25 review and direction, working for a alternate options for NSO. will come back as earliest with closure plan. |  |  | Jayant Madavi |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | 472NSO | Applications/Tools | OPEN | [6 empty] | 1 | Open | Open
214 | T215 | 472 | NA |  |  |  | NSO | Development and unit testing | NSO module final implementation |  |  | Open |  |  |  |  | Post 24.06.25 review and direction, working for a alternate options for NSO. will come back as earliest with closure plan. |  |  | Jayant Madavi |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | 472NSO | Applications/Tools | OPEN | [6 empty] | 1 | Open | Open
215 | T216 | 472 | NA |  |  |  | NSO | Integration | NSO integration with SCCM |  |  | Open |  |  |  |  | Post 24.06.25 review and direction, working for a alternate options for NSO. will come back as earliest with closure plan. |  |  | Jayant Madavi |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | 472NSO | Applications/Tools | OPEN | [6 empty] | 1 | Open | Open
216 | T217 | 472 | NA |  |  |  | NSO | MoM Action | Cisco NSO to test all the cisco elements including SG350 Horizontal switch to deliver service |  |  | Open |  |  |  |  | Post 24.06.25 review and direction, working for a alternate options for NSO. will come back as earliest with closure plan. |  |  | Jayant Madavi |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | 472NSO | Applications/Tools | OPEN | [6 empty] | 1 | Open | Open
217 | T218 | 472 | NA |  |  |  | NSO | MoM Action | NSO LLD |  |  | Open |  |  |  |  | Post 24.06.25 review and direction, working for a alternate options for NSO. will come back as earliest with closure plan. |  |  | Jayant Madavi |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | 472NSO | Applications/Tools | OPEN | [6 empty] | 1 | Open | Open
218 | T219 | 472 | NA |  |  |  | NSO | MoM Action | Service catalog with product concept note for all services with target requirement date. |  |  | Open |  |  |  |  | Post 24.06.25 review and direction, working for a alternate options for NSO. will come back as earliest with closure plan. |  |  | Jayant Madavi |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | 472NSO | Applications/Tools | OPEN | [6 empty] | 1 | Open | Open
219 | T220 | 472 | NA |  |  |  | NSO | MoM Action | T-Cell Service definition sign off |  |  | Open |  |  |  |  | Post 24.06.25 review and direction, working for a alternate options for NSO. will come back as earliest with closure plan. |  |  | Jayant Madavi |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | 472NSO | Applications/Tools | OPEN | [6 empty] | 1 | Open | Open
220 | T221 | 472 | NA |  |  |  | NSO | MoM Action | MAG/GAC ports reservation feasibility for services booked in BSS with payments made |  |  | Open |  |  |  |  | Post 24.06.25 review and direction, working for a alternate options for NSO. will come back as earliest with closure plan. |  |  | Jayant Madavi |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | 472NSO | Applications/Tools | OPEN | [6 empty] | 1 | Open | Open
221 | T222 | 472 | NA |  |  |  | NSO | MoM Action | Tejas NED readiness |  |  | Open |  |  |  |  | Post 24.06.25 review and direction, working for a alternate options for NSO. will come back as earliest with closure plan. |  |  | Jayant Madavi |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | 472NSO | Applications/Tools | OPEN | [6 empty] | 1 | Open | Open
222 | T223 | 472 | NA |  |  |  | NSO | MoM Action | IPTV tested needs to be finalised for additional configuration for multicast and tested as per lab availability and final sign off |  |  | Open |  |  |  |  | Post 24.06.25 review and direction, working for a alternate options for NSO. will come back as earliest with closure plan. |  |  | Jayant Madavi |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | 472NSO | Applications/Tools | OPEN | [6 empty] | 1 | Open | Open
223 | T224 | 472 | NA |  |  |  | NSO | MoM Action | BSS to provide actual feasibility parameters e.g PE port number(s) from OSS . Right now values are hard-coded . In turn OSS to get these details from GIS. We havent seen an e2e workign scenario on this yet. |  |  | Open |  |  |  |  | Post 24.06.25 review and direction, working for a alternate options for NSO. will come back as earliest with closure plan. |  |  | Jayant Madavi |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | 472NSO | Applications/Tools | OPEN | [6 empty] | 1 | Open | Open
224 | T225 | 472 | NA |  |  |  | NSO | MoM Action | VLAN logic : Vlan logic for HSI-SVLAN has beed provided per zone information. But most of deployments are coming with vlan 256 of PIONEER for any service . This needs to be looked at. VLAN ID should be changed to as per plan shared by Aravindhan. |  |  | Open |  |  |  |  | Post 24.06.25 review and direction, working for a alternate options for NSO. will come back as earliest with closure plan. |  |  | Jayant Madavi |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | 472NSO | Applications/Tools | OPEN | [6 empty] | 1 | Open | Open
225 | T226 | 472 | NA |  | OSS | OSS | OSS | IPMPLS | Alarm & Auto TT |  |  | Open |  |  |  |  | 1. OT Stack upgrade is under discussion 2. Resync stabilization is WIP : Action Plan to submitted by 9th Sept 2025 |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | 472OSS | Applications/Tools | OPEN | COMPLETED | 1. OT Stack upgrade is under discussion 2. Resync stabilization is WIP : Action Plan to submitted by 9th Sept 2025 |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
226 | T227 | 472 | NA |  | OSS | OSS | OSS | Other Applications Integrations with OSS | Create trouble ticket by BSS CRM |  |  | Colosed | [7 empty] | Suresh Pawar |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-05-26 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\OSS\T227 | [6 empty] | 472OSS | Applications/Tools | CLOSED | COMPLETED & APPROVED | 0 |  | 2025-05-26 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\OSS\T227 |  | 1 | Completed & Approved | Closed before june-2025
227 | T228 | 472 | NA |  | OSS | OSS | OSS | Other Applications Integrations with OSS | Creation of technical incident by Helpdesk |  |  | Open |  |  |  |  | 17-05-2025: Under observation. Seek approval from Sivakumar 26-06-2025: closed from OSS end, help desk to start using |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | 472OSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
228 | T229 | 472 | NA |  | OSS | OSS | OSS | DWDM Integration with OSS | DWDM Network Alarms integration has been completed in HPE OSS. However, all alarm counts are not in sync with Ciena MCP to HPE vTeMIP. |  |  | Colosed | [7 empty] | Suresh Pawar |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-05-29 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\OSS\T229 | [6 empty] | 472OSS | Applications/Tools | CLOSED | COMPLETED & APPROVED | 0 |  | 2025-05-29 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\OSS\T229 |  | 1 | Completed & Approved | Closed before june-2025
229 | T230 | 472 | NA |  | OSS | OSS | OSS | DWDM Integration with OSS | Hardware inventory integration has been completed in HPE OSS. |  |  | Colosed | [7 empty] | Suresh Pawar |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-05-26 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\OSS\T230 | [6 empty] | 472OSS | Applications/Tools | CLOSED | COMPLETED & APPROVED | 0 |  | 2025-05-26 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\OSS\T230 |  | 1 | Completed & Approved | Closed before june-2025
230 | T231 | 472 | NA |  | OSS | OSS | OSS | DWDM Integration with OSS | Ciena DWDM Network Topology has been created in HPE OSS topology MAP along with neighbour NE details. Adding the geographical map in the background of HPE OSS is possible with openstreet map.. Not posisble to integarted with GIS map |  |  | Open |  |  |  |  | 09-09-2025: topology available but bordering not feasible |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | 472OSS | Applications/Tools | OPEN | COMPLETED | 09-09-2025: topology available but bordering not feasible |  |  | #N/A |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
231 | T232 | 472 | NA |  | OSS | OSS | OSS | DWDM Integration with OSS | Auto Ticket Generation- Fiber Cut |  |  | Colosed |  |  |  |  | 15-09-2025: Demonstrated in the Demo/UAT call |  |  | Suresh Pawar |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-05-26 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\OSS\T232 | [6 empty] | 472OSS | Applications/Tools | CLOSED | COMPLETED & APPROVED | 15-09-2025: Demonstrated in the Demo/UAT call |  | 2025-05-26 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\OSS\T232 |  | 1 | Completed & Approved | Closed before june-2025
232 | T233 | 472 | NA |  | OSS | OSS | OSS | DWDM Integration with OSS | Auto Ticket Generation- Hardwares Failures |  |  | Open | [7 empty] | Suresh Pawar |  |  | COMPLETED & APPROVED |  |  | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\OSS\T233 | [6 empty] | 472OSS | Applications/Tools | CLOSED | COMPLETED & APPROVED | 0 |  |  | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\OSS\T233 |  | 1 | Completed & Approved | Closed after June
233 | T234 | 472 | NA |  | OSS | OSS | OSS | DWDM Integration with OSS | Auto Ticket Generation- Infra Failure |  |  | Colosed | [7 empty] | Suresh Pawar |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-05-26 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\OSS\T234 | [6 empty] | 472OSS | Applications/Tools | CLOSED | COMPLETED & APPROVED | 0 |  | 2025-05-26 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\OSS\T234 |  | 1 | Completed & Approved | Closed before june-2025
234 | T235 | 472 | NA |  | OSS | OSS | OSS | DWDM Integration with OSS | Network and service performance monitoring KPIs report in HPE OSS |  |  | Colosed | [7 empty] | Suresh Pawar |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-05-26 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\OSS\T235 | [6 empty] | 472OSS | Applications/Tools | CLOSED | COMPLETED & APPROVED | 0 |  | 2025-05-26 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\DWDM\Artefact - T101 |  | 1 | Completed & Approved | Closed before june-2025
235 | T236 | 472 | NA |  | OSS | OSS | OSS | DWDM Integration with OSS | Bandwidth utilization data in HPE OSS is available and under validation. |  |  | Colosed | [7 empty] | Suresh Pawar |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-05-26 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\OSS\T236 | [6 empty] | 472OSS | Applications/Tools | CLOSED | COMPLETED & APPROVED | 0 |  | 2025-05-26 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\OSS\T236 |  | 1 | Completed & Approved | Closed before june-2025
236 | T237 | 472 | NA |  | OSS | OSS | OSS | DWDM Integration with OSS | Service inventory data availability in HPE OSS |  |  | Open |  |  |  |  | 17-05-2025: Dependancy on NSO 26-06-2025: Cisco to be onboarded then it will take ~30 days to complete(timeline is given concidering NSO support available on 1st July) |  |  | Suresh Pawar |  | Open | WIP | [9 empty] | 472OSS | Applications/Tools | OPEN | OPEN | 0 |  |  |  |  | 1 | Open | Open
237 | T238 | 472 | NA |  | OSS | OSS | OSS | DWDM Integration with OSS | For planned event service impact analysis data / report |  |  | Open |  |  |  |  | 17-05-2025: Dependancy on NSO 26-06-2025: Cisco to be onboarded then it will take ~30 days to complete(timeline is given concidering NSO support available on 1st July) |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | 472OSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
238 | T239 | 472 | NA |  | OSS | OSS | OSS | IPMPLS Integration with OSS | FMS (Inventory, Alarm, Auto TT) Ref 226 |  |  | Open |  |  |  |  | 24-05-2025:Working with some operational challenges like frequent NNMi and OBM hung issue, queue increase. |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | 472OSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
239 | T240 | 472 | NA |  | OSS | OSS | OSS | IPMPLS Integration with OSS | PMS reports for IPMPLS domain network elements |  |  | Open |  |  |  |  | 17-05-2025: Data collection rom internal (SME & NOC team) and then OT support is required for NPS to enable all permormance parameters. 24-06-2025: NPS reports available and NOC came back with some observation of wrong data, for which OT has asked evidences which are awaited from NOC |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | 472OSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
240 | T241 | 472 | NA |  | OSS | OSS | OSS | IPMPLS Integration with OSS | Dashboards for IPMPLS Domain |  |  | Open |  |  |  |  | 17-05-2025: OOB dashboards are already available in NNMi, L&T NOC team needs to review and confirm if any descripancy observed. |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | 472OSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
241 | T242 | 472 | NA |  | OSS | OSS | OSS | IPMPLS Integration with OSS | Reports |  |  | Open |  |  |  |  | 24-05-2025: Operational Challenges 26-06-2025: Multiple reports are already available, need clarity if anything is missing from IPMPLS |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | 472OSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
242 | T243 | 472 | NA |  | OSS | OSS | OSS | GPON-NOKIA Integration with OSS | CR for Nokia API integration to close BW query and PMS related issues |  |  | Open |  |  |  |  | 13-Sep-2025: Having dependency on A&O/NSO and service inventory deployment. 29-Aug-2025: Having dependency on A&O/NSO and service inventory deployment. 07-July-2025: L&T Remarks: As per the Tfiber suggestion, this is feasible and will be considered during A&O OEM solution deployemenet. 05-July-2025 : TFiber Comments: Available bandwidth has to be calculated before provisioning service to a customer. Available bandwidth can be achieved either from OSS or from Service Inventory systems- which already have the services provisioned data Internal discussion planned on 07-July-2025 30-June-2025 : To arrange a call with Tfiber for the discussion and conclusion Nokia provided the available upload bandwidth on PON Port but Nokia claiming that devices/AMS does not support to provide the available download bandwidth of a PON Port. This feature is not available with Nokia |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | 472OSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
243 | T244 | 472 | NA |  | OSS | OSS | OSS | Other Applications Integrations with OSS | Fetch trouble ticket status for ticket(s) by BSS CRM |  |  | Colosed | [7 empty] | Suresh Pawar |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-05-26 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\OSS\T244 | [6 empty] | 472OSS | Applications/Tools | CLOSED | COMPLETED & APPROVED | 0 |  | 2025-05-26 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\OSS\T244 |  | 1 | Completed & Approved | Closed before june-2025
244 | T245 | 472 | NA |  | OSS | OSS | OSS | Passive Infra Integration with OSS | Integration with DG - HPE |  |  | Colosed | [7 empty] | Suresh Pawar |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-05-26 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\OSS\T245 | [6 empty] | 472OSS | Applications/Tools | CLOSED | COMPLETED & APPROVED | 0 |  | 2025-05-26 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\OSS\T245 |  | 1 | Completed & Approved | Closed before june-2025
245 | T246 | 472 | NA |  | OSS | OSS | OSS | Passive Infra Integration with OSS | Integration with UPS - HPE |  |  | Colosed | [7 empty] | Suresh Pawar |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-05-26 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\OSS\T246 | [6 empty] | 472OSS | Applications/Tools | CLOSED | COMPLETED & APPROVED | 0 |  | 2025-05-26 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\OSS\T246 |  | 1 | Completed & Approved | Closed before june-2025
246 | T247 | 472 | NA |  | OSS | OSS | OSS | Other Applications Integrations with OSS | Inventory Synch - Physical devices with GIS |  |  | Open |  |  |  |  | 24-05-2025:WIP with HPE 26-06-2025: To be tested post GIS integration |  |  | Suresh Pawar |  | Open | WIP | [9 empty] | 472OSS | Applications/Tools | OPEN | OPEN | 0 |  |  |  |  | 1 | Open | Open
247 | T248 | 472 | NA |  | OSS | OSS | OSS | GPON | Nokia API integration - . PMS ( Chassi OLT ), Inventory, Device Status (ONT ) |  |  | Open |  |  |  |  | 17-05-2025: HPE team will deliver post application upgradation 23-06-2025: for Device status, HPE said the the Nokia alarm format is wrong; post having calls with Nokia HPE reviewing the NBI documentation. 17-07-2025: Solution deplyed for one package, for other 2 package need to raise PE on 22nd July |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | 472OSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
248 | T249 | 472 | NA |  | OSS | OSS | OSS | GPON-NOKIA Integration with OSS | OLT & ONT devices status in OSS is not as per AMS |  |  | Open |  |  |  |  | 06-06-2025: HPE requested a call with Nokia 11-06-2025: Nokia call happened and inputs were shared with HPE 23-06-2025: Post having calls with Nokia one more time last week they have share NBI documents with HPE today which they are reviewing. 22-07-2025: count matching, confirmation awaited from NOC |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | 472OSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
249 | T250 | 472 | NA |  | OSS | OSS | OSS | GPON-NOKIA Integration with OSS | ONT devices have been recovered and validated as per AMS count |  |  | Open |  |  |  |  | 15-06-2025: validation pending from NOC |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | 472OSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
250 | T251 | 472 | NA |  | OSS | OSS | OSS | Other Applications Integrations with OSS | Fetch SLA violation by BSS billing |  |  | Open |  |  |  |  | 26-06-2025: table to exposed with BSS, awating sevice ID from BSS and same needs to implemented in Network | KNOT |  | Suresh Pawar |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | 472OSS | Applications/Tools | OPEN | Not Relevant to OSS | 0 |  |  |  |  | 1 | Open | Open
251 | T252 | 472 | NA |  | OSS | OSS | OSS | Other Applications Integrations with OSS | Circuit performance data to BSS CRM |  |  | Open |  |  |  |  | 26-06-2025: table to exposed with BSS, awating sevice ID from BSS and same needs to implemented in Network |  |  | Suresh Pawar |  | Open | WIP | [9 empty] | 472OSS | Applications/Tools | OPEN | Not Relevant to OSS | 0 |  |  |  |  | 1 | Open | Open
252 | T253 | 472 | NA |  | OSS | OSS | OSS | DWDM | Alarm Sync issue with MCP |  |  | Colosed | [7 empty] | Suresh Pawar |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-05-29 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\OSS\T253 | [6 empty] | 472OSS | Applications/Tools | CLOSED | COMPLETED & APPROVED | 0 |  | 2025-05-29 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\OSS\T253 |  | 1 | Completed & Approved | Closed before june-2025
253 | T254 | 472 | NA |  | OSS | OSS | OSS | GPON | Co-located OLT topology view |  |  | Open |  |  |  |  | 17-05-2025: As per previous joint discussion with TFIBER and HPE team, this is not required.(to be discuss and remove/close) 26-06-2025: Completed, need confirmation from NOC |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | 472OSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
254 | T255 | 472 | NA |  | OSS | OSS | OSS | Other Applications Integrations with OSS | Send SMS communication to SMS gateway |  |  | Open | [7 empty] | Suresh Pawar |  |  | COMPLETED & APPROVED |  |  | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\OSS\T255 | [6 empty] | 472OSS | Applications/Tools | CLOSED | COMPLETED & APPROVED | 0 |  |  | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\OSS\T255 |  | 1 | Completed & Approved | Closed after June
255 | T256 | 472 | NA |  | OSS | OSS | OSS | IPMPLS | EPNM & PI Inventory |  |  | Open |  |  |  |  | 09-09-2025: to show only integrated devices, need take up with HPE to change select query to excluse non SNMP device |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | 472OSS | Applications/Tools | OPEN | COMPLETED | 09-09-2025: to show only integrated devices, need take up with HPE to change select query to excluse non SNMP device |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
256 | T257 | 472 | NA |  | OSS | OSS | OSS | Other Applications Integrations with OSS | Syslog Sync to Syslog Server |  |  | Open |  |  |  |  | 17-06-2025: Support required from Sys-log team/Sarmendra & Ravikishore |  |  | Suresh Pawar |  | Open | WIP | [9 empty] | 472OSS | Applications/Tools | OPEN | OPEN | 0 |  |  |  |  | 1 | Open | Open
257 | T258 | 472 | NA |  | OSS | OSS | OSS | GIS | GIS integration |  |  | Open |  |  |  |  | 17-05-2025: WIP with HPE team |  |  | Suresh Pawar |  | Open | WIP | [9 empty] | 472OSS | Applications/Tools | OPEN | OPEN | 0 |  |  |  |  | 1 | Open | Open
258 | T259 | 472 | NA |  | OSS | OSS | OSS | E2E | TOPOLOGY |  |  | Open |  |  |  |  | 17-05-2025: WIP with HPE team |  |  | Suresh Pawar |  | Open | WIP | [9 empty] | 472OSS | Applications/Tools | OPEN | OPEN | 0 |  |  |  |  | 1 | Open | Open
259 | T260 | 472 | NA |  | OSS | OSS | OSS | E2E | Cross domain RCA corelation |  |  | Open |  |  |  |  | 17-05-2025: WIP with HPE team |  |  | Suresh Pawar |  | Open | WIP | [9 empty] | 472OSS | Applications/Tools | OPEN | OPEN | 0 |  |  |  |  | 1 | Open | Open
260 | T261 | 472 | NA |  | OSS | OSS | OSS | Infra | Data enrichment - Location information PKG A B C, etc |  |  | Open |  |  |  |  | 17-05-2025: GIS Integration with UTM is WIP(OT dependancy) 24-06-2025: OT has shared the API for attributes required by HPE |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | 472OSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
261 | T262 | 472 | NA |  | OSS | OSS | OSS | DC - Active infra Alarm and Auto TT | DC-Active infra Alarm, RCA and Auto TT |  |  | Open |  |  |  |  | 17-05-2025: URL unreachable alarms are there but tickets are not getting generated. OT support required. 26-06-2025: Functionality is delivered,under stabilization. |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | 472OSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
262 | T263 | 472 | NA |  | OSS | OSS | OSS | Documentation - LLD, FAT, HA Testing | OSS Documentation - LLD, FAT, HA Testing |  |  | Open |  |  |  |  | 17-05-2025: OT support is required. 26-06-2025: OT & HPE working on preparing the document concidering the BSOW |  |  | Suresh Pawar |  | Open | WIP | [9 empty] | 472OSS | Applications/Tools | OPEN | OPEN | 0 |  |  |  |  | 1 | Open | Open
263 | T264 | 472 | NA |  | OSS | OSS | OSS | MoM Action | Network Downtime, fault reported to be mapped with BSS to consider during billing process |  |  | Open |  |  |  |  | 26-06-2025: Post NSO integration |  |  | Suresh Pawar |  | Open | WIP | [9 empty] | 472OSS | Applications/Tools | OPEN | Not Relevant to OSS | 0 |  |  |  |  | 1 | Open | Open
264 | T265 | 472 | NA |  | OSS | OSS | OSS | MoM Action | Feasibility Engine |  |  | Open |  |  |  |  | 24-05-2025: WIP with HPE, OT dendancy for data. 26-06-2025: OT has provided necessary data to HPE, HPE to complete remaining development |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | 472OSS | Applications/Tools | OPEN | COMPLETED | API |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
265 | T266 | 472 | NA |  | OSS | OSS | OSS | MoM Action | Commercial engine to be designed along with rules to Budgetory calculation for network and customer feasibilies |  |  | Open |  |  |  |  | 26-06-2025: this needs to be taken care by BSS side |  |  | Suresh Pawar |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | 472OSS | Applications/Tools | OPEN | Not Relevant to OSS | 0 |  |  |  |  | 1 | Open | Open
266 | T267 | 472 | NA |  | OSS | OSS | OSS | MoM Action | Port Block (reservation) against Service ID |  |  | Open |  |  |  |  | DUPLICATE POINT |  |  | Suresh Pawar |  | Open | Duplicate | [9 empty] | 472OSS | Applications/Tools | OPEN | DUPLICATE | 0 |  |  |  |  | 1 | Open | Open
267 | T268 | 472 | NA |  | OSS | OSS | OSS | Design & Documentation | LLD |  |  | Open |  |  |  |  | DUPLICATE POINT |  |  | Suresh Pawar |  | Open | Duplicate | [9 empty] | 472OSS | Applications/Tools | OPEN | DUPLICATE | 0 |  |  |  |  | 1 | Open | Open
268 | T269 | 472 | NA |  | OSS | OSS | OSS | MoM Action | Change management process (eg. planned /Unplanned ) activities to be demonstrated |  |  | Open |  |  |  |  | 17-05-2025: OT Team has to work and deliver 26-06-2025: change managemnt is delivered, NOC team has to confirm |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | 472OSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
269 | T270 | 472 | NA |  | OSS | OSS | OSS | MoM Action | Device status in OSS ciena inventory, details received from Ciena |  |  | Colosed | [7 empty] | Suresh Pawar |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-05-26 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\OSS\T270 | [6 empty] | 472OSS | Applications/Tools | CLOSED | COMPLETED & APPROVED | 0 |  | 2025-05-26 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\OSS\T270 |  | 1 | Completed & Approved | Closed before june-2025
270 | T271 | 472 | NA |  | OSS | OSS | OSS | GPON | ONT & OLT vendor name should be mapped to OSS Inventory & PMS Inventory. |  |  | Open | [7 empty] | Suresh Pawar |  |  | COMPLETED & APPROVED |  |  | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\OSS\T271 | [6 empty] | 472OSS | Applications/Tools | CLOSED | COMPLETED & APPROVED | 0 |  |  | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\OSS\T271 |  | 1 | Completed & Approved | Closed after June
271 | T272 | 472 | NA |  | OSS | OSS | OSS | Design & Documentation | Infra team to maintain the SSL connectivity |  |  | Open |  |  |  |  | 17-05-2025: Dependancy on HPE upgrade and OT PS Team support 23-06-2025: New VM was requested by OT and same is provided. OT will to the testing in TND and confirm for production by 27th June 2025 |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | 472OSS | Applications/Tools | OPEN | COMPLETED | SSL configuartion completed in Service Manager |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
272 | T273 | 472 | NA |  | OSS | OSS | OSS | Deployment and Installations | Deployment process - Process of building network & passive device connectivity to T-NOC through SG350, ONT (One port Voice, 2nd - Data, 3rd - Video & 4th port to T-NOC for SNMP traps) . Along with , and also all other Services to be test and provision in SG350 |  |  | Open |  |  |  |  | 09-09-2025: Needs to be closed along with IPMPLS(RS Rao) & GPON(Sayyad) |  |  | Suresh Pawar |  | Open | Open | [9 empty] | 472OSS | Applications/Tools | OPEN | OPEN | 09-09-2025: Needs to be closed along with IPMPLS(RS Rao) & GPON(Sayyad) |  |  |  |  | 1 | Open | Open
273 | T274 | 472 | NA |  | OSS | OSS | OSS | Development and unit testing | In OSS Script File, both Nokia Primary and Secondary IPs are mentioned, however OSS is considering only the first mentioned IP even if Secondary IP is master. Due to this alarms are not reflecting in OSS. Infra team has to setup Virtual IP. |  |  | Colosed | [7 empty] | Suresh Pawar |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-05-26 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\OSS\T274 | [6 empty] | 472OSS | Applications/Tools | CLOSED | COMPLETED & APPROVED | 0 |  | 2025-05-26 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\OSS\T274 |  | 1 | Completed & Approved | Closed before june-2025
274 | T275 | 472 | NA |  | OSS | OSS | OSS | MoM Action | In OSS management dashboard, Block count should count only Mandal OLTs and not GP OLTs. |  |  | Open | [7 empty] | Suresh Pawar |  |  | COMPLETED & APPROVED |  |  | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\OSS\T275 | [6 empty] | 472OSS | Applications/Tools | CLOSED | COMPLETED & APPROVED | 0 |  |  | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\OSS\T275 |  | 1 | Completed & Approved | Closed after June
275 | T276 | 472 | NA |  | OSS | OSS | OSS | MoM Action | DG Set integration with OSS is in progress for Package A, details for DG set integration with OSS awaited from Package B and C. |  |  | Open |  |  |  |  | 26-06-2025: Functionality is delivered, but system is not stable; same issue is escalated to HPE and OT. 22-07-2025: genset alarms are working now, confirmation required from NOC |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | 472OSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
276 | T277 | 472 | NA |  | OSS | OSS | OSS | MoM Action | UPS and DG Device status, GP Name and LGD code & Block Name and LGD code are not available in the Passive Infra (Non-IT) inventory |  |  | Open |  |  |  |  | 09-09-2025: Status available in NNMi & PowerBI. All other atributes available in UOC |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | 472OSS | Applications/Tools | OPEN | COMPLETED | 09-09-2025: Status available in NNMi & PowerBI. All other atributes available in UOC |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
277 | T278 | 472 | NA |  | OSS | OSS | OSS | Firewall | OSS firewall ports required for Security compliance |  |  | Open |  |  |  |  | 09-09-2025: Security team is already taking care with help of MTR sharma |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | 472OSS | Applications/Tools | OPEN | COMPLETED | 09-09-2025: Security team is already taking care with help of MTR sharma |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
278 | T279 | 472 | NA |  | OSS | OSS | OSS | Security | Security policies to evolve related to DOT/CDOT etc.. from internal and intigration |  |  | Open |  |  |  |  | 26-06-2025: Dependacy on Cross domain delivery |  |  | Suresh Pawar |  | Open | WIP | [9 empty] | 472OSS | Applications/Tools | OPEN | OPEN | 0 |  |  |  |  | 1 | Open | Open
279 | T280 | 472 | NA |  | OSS | OSS | OSS | Correlations | Cross domain Corelation and exact reason for any outage in Network till ONT Port with E2E topology |  |  | Open |  |  |  |  | 17-05-2025: WIP with HPE team |  |  | Suresh Pawar |  | Open | Duplicate | [9 empty] | 472OSS | Applications/Tools | OPEN | DUPLICATE | 0 |  |  |  |  | 1 | Open | Open
280 | T281 | 472 | NA |  | OSS | OSS | OSS | MoM Action | Problem Management report for various recurring outages for the given period like i) one Unique LGD code >5 times in a Month ii) Fiber cut SPAN/Link >2 times in a month iii) Unique LGD code Down for >2 times with Same RFO iv) etc. |  |  | Open | [7 empty] | Suresh Pawar |  | Open | WIP | [9 empty] | 472OSS | Applications/Tools | OPEN | OPEN | 0 |  |  | #N/A |  | 1 | Open | Open
281 | T282 | 472 | NA |  | OSS | OSS | OSS | MoM Action | For ONT Down cases, Some of the Alarms and cause code given by OEM is not matching with RFO provided by field engg., for example incase of Particular ONT goes down at GP level then exact RFO should be available for NOC to correlate with outages due to UPS power or other issue? |  |  | Open |  |  |  |  | 15-09-2025: Demostrated in the Demo/UAT call |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | 472OSS | Applications/Tools | OPEN | COMPLETED | 15-09-2025: Demostrated in the Demo/UAT call |  |  | #VALUE! |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
282 | T283 | 472 | NA |  | OSS | OSS | OSS | Dashboards | Alert Mechanism (event rule) when power supply is through UPS which is running on Battery backup mode then there should be alert in the form of SMS sent to field team so outages can be avoided or minimized proactively. threshold can be configured (TBD) )for given range for Battery backup status i) <50%- - Minor ii) <40%-Major iii) <30% -Critical) |  |  | Open | [7 empty] | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | 472OSS | Applications/Tools | OPEN | COMPLETED | pending |  |  | #VALUE! |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
283 | T284 | 472 | NA |  | OSS | OSS | OSS | Dashboards | Weekly, Monthly E2E Network Availability Trend for each Packages and over all per District, Zone level. |  |  | Open |  |  |  |  | Weekly Availability is not getting calculated hence it is not-feasible |  |  | Suresh Pawar |  | Open | WIP | [9 empty] | 472OSS | Applications/Tools | OPEN | NOT-FEASIBLE | 0 |  |  |  |  | 1 | Open | Open
284 | T285 | 472 | NA |  | OSS | OSS | OSS | Dashboards | District wise Performance report for period of infra, fiber, ISP, config issues etc. |  |  | Open |  |  |  |  | 09-09-2025: user can download reports as on his requirement |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | 472OSS | Applications/Tools | OPEN | COMPLETED | 09-09-2025: user can download reports as on his requirement - TT report |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
285 | T286 | 472 | NA |  | OSS | OSS | OSS | Dashboards | Individual NOC Engineer and shift Lead Performance Measurement for handling the TT's |  |  | Open |  |  |  |  | 17-05-2025: Artefacts needs to be collected from Sivakumar and seek approval. 26-06-2025: Waiting for Sivakumar's approval |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | 472OSS | Applications/Tools | OPEN | COMPLETED | closure |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
286 | T287 | 472 | NA |  | OSS | OSS | OSS | MoM Action | Exact SPAN/Link details must be taken from GIS(Including Lat,Long) for Fiber cut/outage scenario to undserstand fix is permanent or temporarary in nature and impact on Multiple Nodes/GP’s . |  |  | Open |  |  |  |  | 17-05-2025: Common span scenarios solution needs to be finalization pending with L&T and will be finalized based on data coming from GIS integration. 26-06-2025: Dependancy on GIS integration. Expected to be completed by 16th July and then ~30 days needed for Common span |  |  | Suresh Pawar |  | Open | WIP | [9 empty] | 472OSS | Applications/Tools | OPEN | OPEN | 0 |  |  |  |  | 1 | Open | Open
287 | T288 | 472 | NA |  |  | DC-Infrastructure | OSS | MoM Action | Report for Backup Status (success/failure) of all VM (source it from Vcenter Report) |  |  | Open | [7 empty] | Ravi Kishore |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-07-05 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\OSS\Artifact-T288 | [6 empty] | 472OSS | Applications/Tools | CLOSED |  |  |  | 2025-07-05 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\OSS\Artifact-T288 |  | 1 | Completed & Approved | Closed after June
288 | T289 | 472 | NA |  | OSS | OSS | OSS | MoM Action | DC Active infra-Health check-up /Utilization and Resource Availability report.—Hardware and Servers. (Source it from Vcenter to OSS tool) |  |  | Open |  |  |  |  | 26-06-2025: data available in OBM, need confirmation from DC team |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | 472OSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
289 | T290 | 472 | NA |  | OSS | OSS | OSS | MoM Action | IP MPLS node status report to be automated(Zonal / Mandal/GP) along with Alias Name(Like Actual Mandal /GP names) -Feasibility check required if Alias can be updated & fetched by OSS tool |  |  | Open |  |  |  |  | 26-06-2025: IPMPLS node status available in NNMi, need confirmation from NOC |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | 472OSS | Applications/Tools | OPEN | COMPLETED | pending |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
290 | T291 | 472 | NA |  | OSS | OSS | OSS | Dashboards | IP MPLS Node/Link/Port availability & Utilization |  |  | Open |  |  |  |  | 17-05-2025: Utilization is already available. Node and Link availability is WIP. OT Support not available to check port availability, it needs to resume. 26-06-2025: all data available now except Link availability, need confirmation from NOC |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | 472OSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
291 | T292 | 472 | NA |  | OSS | OSS | OSS | MoM Action | Customised dashboard template with available set of fields for different set of users views |  |  | Open |  |  |  |  | 17-05-2025: OOB is available, to be reviewed with NOC |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | 472OSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
292 | T293 | 472 | NA |  | OSS | OSS | OSS | Dashboards | Service VLAN status report from EMS (Nokia and Tejas) |  |  | Open |  |  |  |  | 24-05-2025: Inhouse solution being built by rishik |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | 472OSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
293 | T294 | 472 | NA |  | OSS | OSS | OSS | MoM Action | OSS MTTR report to include additional columns like RFO, Sub RFO, Resolution etc. |  |  | Open | [7 empty] | Suresh Pawar |  |  | COMPLETED & APPROVED |  |  | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\OSS\T294 | [6 empty] | 472OSS | Applications/Tools | CLOSED | COMPLETED & APPROVED | 0 |  |  | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\OSS\T294 |  | 1 | Completed & Approved | Closed after June
294 | T295 | 472 | NA |  | OSS | OSS | OSS | MoM Action | Service Management tool has having duplicate tickets for same node which is impacting availability, outage reports. Issue needs to be fixed. |  |  | Open |  |  |  |  | 12-06-2025: duplicate ticket booking needs to be handle by HPE, HPE working on a script to handle it. 26-06-2025: Script deplyed by HPE, need confirmation from NOC |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | 472OSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
295 | T296 | 472 | NA |  | OSS | OSS | OSS | MoM Action | Service Management dashboard should list planned outages and corelate TT if that is on same device or NW component. |  |  | Open |  |  |  |  | 17-05-2025: OT & NSO support required |  |  | Suresh Pawar |  | Open | WIP | [9 empty] | 472OSS | Applications/Tools | OPEN | OPEN | 0 |  |  |  |  | 1 | Open | Open
296 | T297 | 472 | NA |  |  |  | DC-IT | Servers and Strorage (Deployment and Installations) | VM's Deployment Application Installations |  |  | Open |  |  |  |  | Applications installation completed in the given VM's. Storage/resource Allocation details captured in the TNOC IT Infra Server & Storage-LLD_v_1.5 & DC Inventory master sheet. Artifacts are captured. |  |  | Ravi Kishore |  |  | COMPLETED & APPROVED |  |  | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\DC IT-Infra\Artifact for - T297 | [6 empty] | 472DC-IT | Network | CLOSED |  |  |  |  | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\DC IT-Infra\Artifact for - T297 |  | 1 | Completed & Approved | Closed after June
297 | T298 | 472 | NA |  |  |  | GPON | Tejas-MoM Action | Deployment process - Process of building network & passive device connectivity to T-NOC through SG350, ONT (One port Voice, 2nd - Data, 3rd - Video & 4 th port to T-NOC for SNMP traps) . Along with , and also all other Services to be test and provision in SG350 |  |  | Colosed | [7 empty] | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T298 | [6 empty] | 472GPON | GPON | CLOSED |  |  |  | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T298 |  | 1 | Completed & Approved | Closed before june-2025
298 | T299 | 472 | NA |  | OSS | Security | OSS | Integrating AD so that there is single user ID for all apps and they can integrate better in future if there is a need | Integration testing done for all apps that are ready currently except Alepo. Apps like HP OSS, Cisco ISE and other such applications are already integrated. We can switch IDs to AD anytime |  |  | Open |  |  |  |  | Once AD integration happen for Aleppo this point also will be closed along with T333. |  |  | Sarmendra |  | Open | WIP | [9 empty] | 472OSS | Applications/Tools | OPEN | [6 empty] | 1 | Open | Open
299 | T300 | 472 | NA |  | OSS | Security | OSS | Configuration and best practices | User IDs created. Need to work with users for testing for NOC desktops |  |  | Open |  |  |  |  | Artifacts will be created and submitted on 03 Jul 25 |  |  | Sarmendra |  |  | COMPLETED & APPROVED |  |  | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\NW-Security\T300 | [6 empty] | 472OSS | Applications/Tools | CLOSED |  |  |  |  | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\NW-Security\T300 |  | 1 | Completed & Approved | Closed after June
300 | T301 | 472 | NA |  |  |  | Security & Regulatory Compliance | Configuration | On A-10 -Configuration done on LB side. WAF will be configure with License |  |  | Open |  |  |  |  | A10 AMC not renewed , Awaiting AMC renewal with WAF features |  |  | Sarmendra |  | Open | WIP | [9 empty] | 472Security & Regulatory Compliance | Security | OPEN | [6 empty] | 1 | Open | Open
301 | T302 | 472 | NA |  |  |  | Security & Regulatory Compliance | Functional AT | Will start next week as KT happened this week for all the new resources |  |  | Open |  |  |  |  | KT has been done. |  |  | Sarmendra |  |  | CLOSURE REVIEW PENDING | [9 empty] | 472Security & Regulatory Compliance | Security | OPEN |  |  |  |  | Artefacts to be Submitted |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
302 | T303 | 472 | NA |  | OSS | Security | OSS | Configuration | OSS- Redware LB-There were configuration issues and have been sorted our by having multiple sessions over the past few weeks |  |  | Open |  |  |  |  | Artifact created and will be submitted to customer on 03 Jul 25. |  |  | Sarmendra |  |  | CLOSURE REVIEW PENDING | [9 empty] | 472OSS | Applications/Tools | OPEN |  |  |  |  | Artefacts to be Submitted |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
303 | T304 | 472 | NA |  |  |  | Security & Regulatory Compliance | Functional AT | Radware LB - Will start next week as KT happened this week for all the new resources |  |  | Open |  |  |  |  | KT has been done. |  |  | Sarmendra |  | Open | WIP | [9 empty] | 472Security & Regulatory Compliance | Security | OPEN | [6 empty] | 1 | Open | Open
304 | T305 | 472 | NA |  | OSS | DC-Infrastructure | OSS | Configuration | We have identified memory needed. Need help with space allocation for VM and also need license for a syslog server. ( we can also use Default Linux daemon) Syslog |  |  | Open |  |  |  |  | [17/09/2025] Syslog integration with both Redhat and Windows servers Completed. |  |  | Ravi Kishore |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-09-19 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\OSS\T305 | [6 empty] | 472OSS | Applications/Tools | CLOSED |  |  |  | 2025-09-19 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\OSS\T305 |  | 1 | Completed & Approved | Closed after June
305 | T306 | 472 | NA |  |  |  | Security & Regulatory Compliance | Documentation | Customer has requested a complete Security LLD that states how our security architechture is and how different security products talk to each other |  |  | Open |  |  |  |  | Completed and Review pending. New changes will be incorporated as an addendum to design. |  |  | Sarmendra |  | Open | WIP | [9 empty] | 472Security & Regulatory Compliance | Security | OPEN | [6 empty] | 1 | Open | Open
306 | T307 | 472 | NA |  |  |  | Security & Regulatory Compliance | User Access Rights | Cisco: PKGA-testing in WIP, PKGB&C-will be replicated after PKGA completion GPON: Segregation is done, implementation is WIP DWDM: Segregation is done, implementation is WIP HPE OSS: User to access mapping is done, implementation WIP by hp team Other Apps: Will have meetings this week and sort it out. |  |  | Open |  |  |  |  | #VALUE! |  |  | Sarmendra |  | Open | WIP | [9 empty] | 472Security & Regulatory Compliance | Security | OPEN |  |  |  |  | #VALUE! |  | 1 | Open | Open
307 | T308 | 472 | NA |  |  |  | Security & Regulatory Compliance | IPDR | Developing in-house solution, also exploring with external vendors. 3 vendors declined. |  |  | Open |  |  |  |  | 27.06.25 , IPDR solution operational , pending document will be submitted by 1st week of Jul'25 |  |  | Jayant Madavi |  | Open | WIP | [9 empty] | 472Security & Regulatory Compliance | Security | OPEN | [6 empty] | 1 | Open | Open
308 | T309 | 472 | NA |  |  |  | Security & Regulatory Compliance | Storage | Storage requirement worked out and given to contract team. PO to be issued(Syslog) |  |  | Open |  |  |  |  | 25-Sep-2025: Artefacts to be uploaded, Need to provide current consumption of storage, incremental log will be added to existing storage after adding 18 TB additional storage . | L&T | Ravi Kishore | Sarmendra |  |  | COMPLETED & APPROVED | [9 empty] | 472Security & Regulatory Compliance | Security | CLOSED |  |  |  |  | Artefacts Need to upload |  | 1 | Completed & Approved | Closed after June
309 | T310 | 472 | NA |  |  |  | Security & Regulatory Compliance | NAT | Developed in-house solution, also exploring with external vendors. 3 vendors declined. In-house solution is ready for demo, tested with the sample data.( |  |  | Open |  |  |  |  | 25-Sep-2025: Detailed discussion will be taken up later(Sanjay will brief background against this point) |  |  | Sarmendra |  |  | COMPLETED & APPROVED | [9 empty] | 472Security & Regulatory Compliance | Security | CLOSED |  |  |  |  | Artefacts Need to upload |  | 1 | Completed & Approved | Closed after June
310 | T311 | 472 | NA |  |  |  | Security & Regulatory Compliance | QoS Reporting | QoS Reporting related to all parameters |  |  | Open |  |  |  |  | Completed and Review pending.FAT documents were submitted to TPA , However it has some common observation which will be discussed with TPA team by Mr Sharma. |  |  | Sarmendra |  | Open | WIP | [9 empty] | 472Security & Regulatory Compliance | Security | OPEN | [6 empty] | 1 | Open | Open
311 | T312 | 472 | NA |  |  |  | Security & Regulatory Compliance | Regulatory compliance | SLA Reporting for Cell Tower and GIs |  |  | Colosed | [7 empty] | Siva Kumar |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-05-13 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\T312 | [6 empty] | 472Security & Regulatory Compliance | Security | CLOSED |  |  |  | 2025-05-13 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\T312 |  | 1 | Completed & Approved | Closed before june-2025
312 | T313 | 472 | NA |  |  |  | Security & Regulatory Compliance | Regulatory compliance | Communication made to T-Fiber. Procedure need to be finalized for remote access |  |  | Open | [7 empty] | Sarmendra |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | 472Security & Regulatory Compliance | Security | OPEN | [6 empty] | 1 | Open | Open
313 | T314 | 472 | NA |  |  |  | Security & Regulatory Compliance | External Audit and VAPT | External Audit and VAPT (Tfiber will be arranging a partner for third party audit) |  |  | Open |  |  |  |  | T Fiber to conduct the Audit and VAPT |  |  | Sarmendra |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | 472Security & Regulatory Compliance | Security | OPEN | [6 empty] | 1 | Open | Open
314 | T315 | 472 | NA |  |  | BMS | BMS | Fire and Safety Drill | Certificate and artefacts of last fire & safety drill submitted |  |  | Open | [7 empty] | Sarmendra |  |  | COMPLETED & APPROVED |  |  | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\NW-Security\T315 | [6 empty] | 472BMS | #N/A | CLOSED |  |  |  |  | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\NW-Security\T315 |  | 1 | Completed & Approved | Closed after June
315 | T316 | 472 | NA |  |  |  | Security & Regulatory Compliance | User Traceability | User access traceability |  |  | Open | [7 empty] | Sarmendra |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-05-19 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\NW-Security\T316 | [6 empty] | 472Security & Regulatory Compliance | Security | CLOSED |  |  |  | 2025-05-19 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\NW-Security\T316 |  | 1 | Completed & Approved | Closed after June
316 | T317 | 472 | NA |  | OSS | OSS | OSS | Certifications | ITIL Product certification |  |  | Open | [7 empty] | Suresh Pawar |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-09-12 | \\172.28.9.34\SHARE DRIVE\Artefacts_T-Fiber TNOC Tracker\OSS | [6 empty] | 472OSS | Applications/Tools | CLOSED | COMPLETED & APPROVED | 0 |  | 2025-09-12 | \\172.28.9.34\SHARE DRIVE\Artefacts_T-Fiber TNOC Tracker\OSS |  | 1 | Completed & Approved | Closed after June
317 | T318 | 472 | NA |  |  |  | Security & Regulatory Compliance | Policy Implementation | Network Forensic |  |  | Colosed | [7 empty] | Sarmendra |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-05-19 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\NW-Security\T318 | [6 empty] | 472Security & Regulatory Compliance | Security | CLOSED |  |  |  | 2025-05-19 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\NW-Security\T318 |  | 1 | Completed & Approved | Closed before june-2025
318 | T319 | 472 | NA |  |  |  | Security & Regulatory Compliance | Policy Implementation | Network Hardening |  |  | Open |  |  |  |  | All unauthorised access has been blocked at firwall level. All USB is disables at NOC . All unysed port has been hardened |  |  | Sarmendra |  | Open | WIP | [9 empty] | 472Security & Regulatory Compliance | Security | OPEN | [6 empty] | 1 | Open | Open
319 | T320 | 472 | NA |  |  |  | Security & Regulatory Compliance | Policy Implementation | Network Penetration Test |  |  | Open |  |  |  |  | PT will conducted once Ext audit team arrives |  |  | Sarmendra |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | 472Security & Regulatory Compliance | Security | OPEN | [6 empty] | 1 | Open | Open
320 | T321 | 472 | NA |  |  |  | Security & Regulatory Compliance | MoM Action | Firewall policy compare from DC to DR validation check for redundancy |  |  | Open |  |  |  |  | May be clubed with point T 71 all Policy will be compared with current configuration of firewall and be submitted . |  |  | Sarmendra |  | Open | REOPENED | [9 empty] | 472Security & Regulatory Compliance | Security | OPEN | [6 empty] | 1 | Open | Open
321 | T322 | 472 | NA |  |  |  | Security & Regulatory Compliance | MoM Action | Day 0 attacks for any government departments lifecycle (GIBB to be protected from the day of connection) |  |  | Open |  |  |  |  | will be closed with implementation of URL filtering facilities at IPS |  |  | Sarmendra |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | 472Security & Regulatory Compliance | Security | OPEN | [6 empty] | 1 | Open | Open
322 | T323 | 472 | NA |  |  |  | Security & Regulatory Compliance | Storage | User access logs& Commands to be maintained for 2 years |  |  | Open |  |  |  |  | Completed and approved |  |  | Sarmendra |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-05-19 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\NW-Security\T323 | [6 empty] | 472Security & Regulatory Compliance | Security | CLOSED |  |  |  | 2025-05-19 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\NW-Security\T323 |  | 1 | Completed & Approved | Closed after June
323 | T324 | 472 | NA |  |  |  | Security & Regulatory Compliance | Deployment and Installations | Syslog to maintain for 2 years |  |  | Colosed | [7 empty] | Ravi Kishore |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-05-14 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\Security\T324 | [6 empty] | 472Security & Regulatory Compliance | Security | CLOSED |  |  |  | 2025-05-14 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\Security\T324 |  | 1 | Completed & Approved | Closed before june-2025
324 | T325 | 472 | NA |  |  |  | Security & Regulatory Compliance | Policy Implementation | Organizational Security Policy |  |  | Open |  |  |  |  | Security policy has been made , however same need clarification from customer to incorporate deviation from actual points. |  |  | Sarmendra |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | 472Security & Regulatory Compliance | Security | OPEN | [6 empty] | 1 | Open | Open
325 | T326 | 472 | NA |  |  |  | Security & Regulatory Compliance | Report | IPDR static IP report |  |  | Open | [7 empty] | Sarmendra |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-05-19 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\NW-Security\T326 | [6 empty] | 472Security & Regulatory Compliance | Security | CLOSED |  |  |  | 2025-05-19 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\NW-Security\T326 |  | 1 | Completed & Approved | Closed after June
326 | T327 | 472 | NA |  |  |  | Security & Regulatory Compliance | Report | Syslog NAT report |  |  | Open | [7 empty] | Sarmendra |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-05-19 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\NW-Security\T327 | [6 empty] | 472Security & Regulatory Compliance | Security | CLOSED |  |  |  | 2025-05-19 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\NW-Security\T327 |  | 1 | Completed & Approved | Closed after June
327 | T328 | 472 | NA |  |  |  | Security & Regulatory Compliance | AAA | ISE-Completed, Alepo-Completed for Nokia GPON, Accounting feature demo to be done for Tejas GPON and Ciena DWDM |  |  | Open |  |  |  |  | Confirmation of purchase of ISE. License needed to upgrade for HA |  |  | Sarmendra |  |  | CLOSURE REVIEW PENDING | [9 empty] | 472Security & Regulatory Compliance | Security | OPEN |  |  |  |  | Artefacts to be Submitted |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
328 | T329 | 472 | NA |  |  |  | Security & Regulatory Compliance | MoM Action | Cisco ISE to be integrated with AD for Authentication |  |  | Colosed | [7 empty] | Sarmendra |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-05-19 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\NW-Security\T153 | [6 empty] | 472Security & Regulatory Compliance | Security | CLOSED |  |  |  | 2025-05-19 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\NW-Security\T153 |  | 1 | Completed & Approved | Closed before june-2025
329 | T330 | 472 | NA |  |  |  | Security & Regulatory Compliance | MoM Action | syslog storage requirement for respective OEM devices |  |  | Colosed | [7 empty] | Sarmendra |  |  | COMPLETED & APPROVED | [9 empty] | 472Security & Regulatory Compliance | Security | CLOSED |  |  |  |  | Artefacts Need to upload |  | 1 | Completed & Approved | Closed before june-2025
330 | T331 | 472 | NA |  |  |  | Security & Regulatory Compliance | MoM Action | Tejas OLT to integrate with Alepo AAA Tejas EMS to integrate with Alepo AAA |  |  | Open |  |  |  |  | Alepo AMC Support required for Evidence submission to customer |  |  | Sarmendra |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | 472Security & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
331 | T332 | 472 | NA |  |  |  | Security & Regulatory Compliance | MoM Action | Nokia AMS to integrate with Alepo AAA |  |  | Open | [7 empty] | Sarmendra |  |  | COMPLETED & APPROVED | [9 empty] | 472Security & Regulatory Compliance | Security | CLOSED |  |  |  |  | Artefacts Need to upload |  | 1 | Completed & Approved | Closed after June
332 | T333 | 472 | NA |  |  |  | Security & Regulatory Compliance | MoM Action | Alepo AAA to be integrated with AD |  |  | Open |  |  |  |  | SOW, CR and BOQ Shared for approval and consideration. |  |  | Sarmendra |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | 472Security & Regulatory Compliance | Security | OPEN | [6 empty] | 1 | Open | Open
333 | T334 | 472 | NA |  |  |  | Security & Regulatory Compliance | Functional AT | Cisco Firewall, ISE, IPS/IDS Functional AT |  |  | Open |  |  |  |  | Completed and Review pending. |  |  | Sarmendra |  | Open | WIP | [9 empty] | 472Security & Regulatory Compliance | Security | OPEN | [6 empty] | 1 | Open | Open
334 | T335 | 472 | NA |  |  |  | Security & Regulatory Compliance | Design & Documentation | Security LLD to finalised and submitted to T-Fiber for approval. Customer has requested a complete Security LLD that states how our security architechture is and how different security products talk to each other |  |  | Open |  |  |  |  | Duplicate of point 306 |  |  | Sarmendra |  | Open | WIP | [9 empty] | 472Security & Regulatory Compliance | Security | OPEN | [6 empty] | 1 | Open | Open
335 | T336 | 472 | NA |  |  |  | IP/MPLS | T-Cell Solution Design | Egress QoS policy for ASR907 |  |  | Colosed | [7 empty] | RS Rao |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-05-05 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\TFIBER T-CELL Service Design & Solution V4.3 T197, T336, T337, T338.pdf | [6 empty] | 472IP/MPLS | IPMPLS | CLOSED |  |  |  | 2025-05-05 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\QOS for TFiber Network LLD V2.0 - T339, T340, T341, T342.pdf |  | 1 | Completed & Approved | Closed before june-2025
336 | T337 | 472 | NA |  |  |  | IP/MPLS | T-Cell Solution Design | Egress QoS policy for ASR920 – QoS policy to be applied on Gigabit interfaces instead of on Port Channel (LAG) which is not suitable for CIR application |  |  | Colosed | [7 empty] | RS Rao |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-05-05 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\TFIBER T-CELL Service Design & Solution V4.3 T197, T336, T337, T338.pdf | [6 empty] | 472IP/MPLS | IPMPLS | CLOSED |  |  |  | 2025-05-05 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\TFIBER T-CELL Service Design & Solution V4.3 T197, T336, T337, T338.pdf |  | 1 | Completed & Approved | Closed before june-2025
337 | T338 | 472 | NA |  |  |  | IP/MPLS | T-Cell Solution Design | Additional scenarios for generic Cell tower Solution shared with Cisco, Cisco to check and provide the design |  |  | Colosed | [7 empty] | RS Rao |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-05-05 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\TFIBER T-CELL Service Design & Solution V4.3 T197, T336, T337, T338.pdf | [6 empty] | 472IP/MPLS | IPMPLS | CLOSED |  |  |  | 2025-05-05 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\TFIBER T-CELL Service Design & Solution V4.3 T197, T336, T337, T338.pdf |  | 1 | Completed & Approved | Closed before june-2025
338 | T339 | 472 | NA |  |  |  | IP/MPLS | MPLS Core network QoS | Egress Policy structure and BW as per discussion |  |  | Colosed | [7 empty] | RS Rao |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-05-05 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\QOS for TFiber Network LLD V2.0 - T339, T340, T341, T342.pdf | [6 empty] | 472IP/MPLS | IPMPLS | CLOSED |  |  |  | 2025-05-05 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\QOS for TFiber Network LLD V2.0 - T339, T340, T341, T342.pdf |  | 1 | Completed & Approved | Closed before june-2025
339 | T340 | 472 | NA |  |  |  | IP/MPLS | MPLS Core network QoS | Egress QoS policy for ASR99xx |  |  | Colosed | [7 empty] | RS Rao |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-05-05 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\QOS for TFiber Network LLD V2.0 - T339, T340, T341, T342.pdf | [6 empty] | 472IP/MPLS | IPMPLS | CLOSED |  |  |  | 2025-05-05 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\QOS for TFiber Network LLD V2.0 - T339, T340, T341, T342.pdf |  | 1 | Completed & Approved | Closed before june-2025
340 | T341 | 472 | NA |  |  |  | IP/MPLS | MPLS Core network QoS | Egress QoS policy for ASR907 |  |  | Colosed | [7 empty] | RS Rao |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-05-05 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\QOS for TFiber Network LLD V2.0 - T339, T340, T341, T342.pdf | [6 empty] | 472IP/MPLS | IPMPLS | CLOSED |  |  |  | 2025-05-05 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\QOS for TFiber Network LLD V2.0 - T339, T340, T341, T342.pdf |  | 1 | Completed & Approved | Closed before june-2025
341 | T342 | 472 | NA |  |  |  | IP/MPLS | MPLS Core network QoS | Egress QoS policy for ASR920 |  |  | Colosed | [7 empty] | RS Rao |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-05-05 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\QOS for TFiber Network LLD V2.0 - T339, T340, T341, T342.pdf | [6 empty] | 472IP/MPLS | IPMPLS | CLOSED |  |  |  | 2025-05-05 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\QOS for TFiber Network LLD V2.0 - T339, T340, T341, T342.pdf |  | 1 | Completed & Approved | Closed before june-2025
342 | T343 | 472 | NA |  |  |  | IP/MPLS | Service Solution | Design Document require SDC content to GI |  |  | Open |  |  |  |  | 22-Sep-25: Need to review plan and approve 12-Sep-25 : Peering plan submitted as per discussion on 11-Sep-25 01-Jul-25 : Design document submitted with suggested approaches. Require inputs from TFiber to conduct PoC and finalize service design. | T Fiber | Sanjay | RS Rao |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | 472IP/MPLS | IPMPLS | OPEN | [6 empty] | 1 | Open | Open
343 | T344 | 472 | NA |  |  |  | IP/MPLS | Service Solution | Solution document for GI connectivity (intranet & internet) TVPN |  |  | Open |  |  |  |  | 22-Sep-25:Artefacts to be uploaded 01-Jul-25 : Design document submitted with suggested approaches. Require inputs from TFiber to conduct PoC and finalize service design. | L&T | RS Rao | RS Rao |  |  | COMPLETED & APPROVED | [9 empty] | 472IP/MPLS | IPMPLS | CLOSED |  |  |  | 2025-09-23 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\T-FIBER RYTHUVEDIKA VC L3VPN Solution LLD V1.0.docx |  | 1 | Completed & Approved | Closed after June
344 | T345 | 472 | NA |  |  |  | TNOC-Ops | NOC Operation | OEM Professional services for all products post NOC operationalization |  |  | Open |  |  |  |  | AMC and TAC support provided |  |  | Ahmad |  | Open | Open | [9 empty] | 472TNOC-Ops | Network | OPEN | [6 empty] | 1 | Open | Open
345 | T346 | 472 | NA |  |  |  | BSS | TNOC-Ops | all EMS Devices for provisioning through BSS |  |  | Open |  |  |  |  | BSS will not directly interact with any EMS, it will be via A&O. |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | 472BSS | Applications/Tools | OPEN | [6 empty] | 1 | Open | Open
346 | T347 | 472 | NA |  |  |  | BSS | Functional AT | Lead to Cash, Order to cash & Request to resolution to operate and demonestrate |  |  | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | 472BSS | Applications/Tools | OPEN | [6 empty] | 1 | Open | Open
347 | T348 | 472 | NA | P3 |  |  | TNOC-Ops | NOC Operation | Placement of T-Fiber logo and Telangana State emblem in TNOC reception area |  |  | Open |  |  |  |  | Logo design agreed with customer. Additional places sign boards to be placed as part of CR, give to commercail for quotation. | T Fiber |  | Ahmad |  | Open | Open | [9 empty] | 472TNOC-Ops | Network | OPEN |  |  | Logo |  |  |  | 1 | Open | Open
348 | T349 | 472 | NA |  |  |  | Security & Regulatory Compliance | Design & Documentation | TNOC operational framework with respect to processes (Incident, Problem, Major Event, Change, Version, Security, AAA, Planned Event, SLA Management etc) |  |  | Open |  |  |  |  | Customer has to choose what framework they ned to follow for end to end governance i.e COBIT, COSO, SABSA etc. |  |  | Sarmendra |  | Open | WIP | [9 empty] | 472Security & Regulatory Compliance | Security | OPEN | [6 empty] | 1 | Open | Open
349 | T350 | 472 | NA | P3 |  |  | TNOC-Ops | NOC Operation | Manpower Structure for TNOC Operationalization |  |  | Colosed | [7 empty] | Ahmad |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-05-13 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\T166 | [6 empty] | 472TNOC-Ops | Network | CLOSED |  |  | Manpower | 2025-05-13 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\T166 |  | 1 | Completed & Approved | Closed before june-2025
350 | T351 | 472 | NA |  |  |  | TNOC-Ops | Design & Documentation | Helpdesk Readiness Plan |  |  | Open |  |  |  |  | 1. Soft training completed on 06&07 Sep 2. All Resources will be from L&T only- Resource available to handle current calls 3. updated process document shared, Pending for discussion 4. SOP Submitted for inbound and outbound calls- Discussion Pending 5. Regulatory reports were available(DOT) 6. Integration with OSS and BSS is Pending 7. Based on trainer suggestion, implemented day to day and weekly assestments 8. Neox call Manager functioanlity validated as standlone 9. All Features required for Call Manager completed including Business Helpdesk 10. LLD and RFP Compliance also ready for review |  |  | Siva Kumar |  | Open | WIP | [9 empty] | 472TNOC-Ops | Network | OPEN | [6 empty] | 1 | Open | Open
351 | T352 | 472 | NA |  |  |  | TNOC-Ops | MoM Action | Induction Training program – To be developed and feedback mechanism to be considered, for newly on-boarded resources |  |  | Colosed | [7 empty] | Siva Kumar |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-05-13 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\T166 | [6 empty] | 472TNOC-Ops | Network | CLOSED |  |  |  | 2025-05-13 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\T166 |  | 1 | Completed & Approved | Closed before june-2025
352 | T353 | 472 | NA |  |  |  | TNOC-Ops | Helpdesk | Regulatory Compliance_PMR on QoS |  |  | Colosed | [7 empty] | Siva Kumar |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-05-13 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\T353 | [6 empty] | 472TNOC-Ops | Network | CLOSED |  |  |  | 2025-05-13 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\T353 |  | 1 | Completed & Approved | Closed before june-2025
353 | T354 | 472 | NA | P3 |  |  | TNOC-Ops | NOC Operation | Resource deployment at TNOC |  |  | Colosed | [7 empty] | Ahmad |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-05-13 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\T166 | [6 empty] | 472TNOC-Ops | Network | CLOSED |  |  | Not related to delivery | 2025-05-13 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\T166 |  | 1 | Completed & Approved | Closed before june-2025
354 | T355 | 472 | NA | P3 |  |  | TNOC-Ops | NOC Operation | Interlocking and Interdependencies with resources of package B & C operating at TNOC |  |  | Open | [7 empty] | Ahmad |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-05-26 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\T166 | [6 empty] | 472TNOC-Ops | Network | CLOSED |  |  | Not related to delivery | 2025-05-26 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\T166 |  | 1 | Completed & Approved | Closed after June
355 | T356 | 472 | NA |  |  |  | TNOC-Ops | NOC Operation | OEM Escalation processes for NOC Applications, DBs, IT Infra and Network along with TATs aligned to SLA |  |  | Open | [7 empty] | Siva Kumar |  |  | COMPLETED & APPROVED | ad-ut-tfiber | 2025-07-08 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\TNOC | [6 empty] | 472TNOC-Ops | Network | CLOSED |  |  |  | 2025-07-08 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\TNOC |  | 1 | Completed & Approved | Closed after June
356 | T357 | 472 | NA | P3 |  |  | TNOC-Ops | NOC Operation | Spare for Business continuity - RS&R for NOC and DR elements and assets |  |  | Open |  |  |  |  | List shared with commercial for ordering. WIP |  |  | Ahmad | Dependent on Commercials | Open | WIP | [9 empty] | 472TNOC-Ops | Network | OPEN |  |  | Spares for NOC |  |  |  | 1 | Open | Open
357 | T358 | 472 | NA |  |  |  | TNOC-Ops | Functional AT | Network HOTO and KT from Respective Domain and Packages |  |  | Open |  |  |  | WIP | BSS, NSO and Security SOP training pending. Rest all done |  |  | Siva Kumar |  | Open | WIP | [9 empty] | 472TNOC-Ops | Network | OPEN | [6 empty] | 1 | Open | Open
358 | T359 | 472 | NA |  | OSS | OSS | OSS | NOC Operation | OSS - stability and Operational issues with respect to inventory, ticketing and utilization modules |  |  | Open |  |  |  |  | 26-06-2025: Frequent stability issues are because of NNMi, OBM instability and Vendor asking for upgrade |  |  | Suresh Pawar |  | Open | WIP | [9 empty] | 472OSS | Applications/Tools | OPEN | OPEN | 0 |  |  |  |  | 1 | Open | Open
359 | T360 | 472 | NA | P3 |  |  | TNOC-Ops | NOC Operation | Domain wise training |  |  | Open |  |  |  |  | BSS, NSO and Security SOP training pending. On the job training happening for OSS. Rest all domains done. |  |  | Ahmad |  | Open | Open | [9 empty] | 472TNOC-Ops | Network | OPEN |  |  | Training |  |  |  | 1 | Open | Open
360 | T361 | 472 | NA |  |  |  | TNOC-Ops | Helpdesk | Updated Process document Submission after last Meeting with T Fiber Management |  |  | Colosed | [7 empty] | Siva Kumar |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-05-13 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\T361 | [6 empty] | 472TNOC-Ops | Network | CLOSED |  |  |  | 2025-05-13 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\T361 |  | 1 | Completed & Approved | Closed before june-2025
361 | T362 | 472 | NA |  |  |  | TNOC-Ops | Helpdesk | Categorisation of incoming calls to be detailed and IVR to bilingual(Incoming IVR call flow) |  |  | Colosed | [7 empty] | Siva Kumar |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-05-13 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\T362 | [6 empty] | 472TNOC-Ops | Network | CLOSED |  |  |  | 2025-05-13 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\T362 |  | 1 | Completed & Approved | Closed before june-2025
362 | T363 | 472 | NA |  |  |  | TNOC-Ops | Helpdesk | IVR Recording file required for call landing and Hold time |  |  | Colosed | [7 empty] | Siva Kumar |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-05-13 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\T363 | [6 empty] | 472TNOC-Ops | Network | CLOSED |  |  |  | 2025-05-13 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\T363 |  | 1 | Completed & Approved | Closed before june-2025
363 | T364 | 472 | NA |  |  |  | TNOC-Ops | Helpdesk | Integration with BSS and OSS |  |  | Open |  |  |  | WIP | 11-Sep-25: Basic integration completed with BSS and HPSM(Ticketing). IVR has to be freezed to implement same. As per Neox is one time configuration but Since its ongoing changes will happen in IVR, So it would be configurble as per L&T/T Fiber- Which to be discussed. 360 View also Pending from BSS |  |  | Siva Kumar |  | Open | WIP | [9 empty] | 472TNOC-Ops | Network | OPEN | [6 empty] | 1 | Open | Open
364 | T365 | 472 | NA |  |  |  | TNOC-Ops | Helpdesk | Integration of SMS, E-Mail |  |  | Open |  |  |  | WIP | E-mail & SMS Integration completed. SMS testing pending due to no balance in SMS striker portal. 28 Apri-2025: TFIBER to share SMS GW details to integrate with OSS/BSS. Integration must be configurable without any cost impact to TFIBER. |  |  | Siva Kumar |  | Open | WIP | [9 empty] | 472TNOC-Ops | Network | OPEN | [6 empty] | 1 | Open | Open
365 | T365 | 472 | NA |  |  |  | TNOC-Ops | Helpdesk | Integration of Whatsapp, Chatbot |  |  | Open |  |  |  | WIP | 11-Sep-25: Not Part of RFP and Existing product didn’t support, need to upgrade to Omni based Solution. |  |  | Siva Kumar |  | Open | WIP | [9 empty] | 472TNOC-Ops | Network | OPEN | [6 empty] | 1 | Open | Open
366 | T366 | 472 | NA |  |  |  | TNOC-Ops | Helpdesk | Fancy 4 digit number for Helpdesk or Tollfree number Availability |  |  | Open | [7 empty] | Siva Kumar |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-07-19 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\T366 | [6 empty] | 472TNOC-Ops | Network | CLOSED |  |  |  | 2025-07-19 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\T366 |  | 1 | Completed & Approved | Closed after June
367 | T367 | 472 | NA |  |  |  | TNOC-Ops | Helpdesk | Training for Agents and Helpdesk Manager |  |  | Colosed | [7 empty] | Siva Kumar |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-05-13 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\T367 | [6 empty] | 472TNOC-Ops | Network | CLOSED |  |  |  | 2025-05-13 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\T367 |  | 1 | Completed & Approved | Closed before june-2025
368 | T368 | 472 | NA |  |  |  | TNOC-Ops | Helpdesk | Interface mechanism between T-NOC Helpdesk and District Collector offices for complaints that may be made directly(Walk-in) to District Collector office, provision for a mini-Helpdesk node at each district, provide a facility/ hotline using which an authorised person can log a call / complaint on behalf of the District Collector Office, such mechanism to be similar to the Direct walk-in channel for customer complaints at T-NOC |  |  | Open | [7 empty] | Siva Kumar |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-07-19 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\T368 | [6 empty] | 472TNOC-Ops | Network | CLOSED |  |  |  | 2025-07-19 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\T368 |  | 1 | Completed & Approved | Closed after June
369 | T369 | 472 | NA |  |  |  | TNOC-Ops | Helpdesk | If T-NOC is totally down for some reason like fire, earthquake, lockdown etc….then how Helpdesk will work from DR? |  |  | Open |  |  |  | WIP |  |  |  | Siva Kumar |  | Open | WIP | Not part of RFP | [8 empty] | 472TNOC-Ops | Network | OPEN | [6 empty] | 1 | Open | Open
370 | T370 | 472 | NA |  |  |  | TNOC-Ops | Helpdesk | If all 10 lines are engaged for a longer time. Can the Helpdesk system call back to that missed call? |  |  | Open |  |  |  | WIP | 11-Sep-25: OEM confirmed this feature is not available/feasible Based on CDR record with Agent and Manager Login, Call back can be done manually with CDR or Agent Call report. It will be displayed in queue to agent. But Missed call to be handled by outbound team. Which required complete Set of call Center. If required Helpdesk Manager will review missed call to take action accordingly. |  |  | Siva Kumar |  | Open | WIP | [9 empty] | 472TNOC-Ops | Network | OPEN | [6 empty] | 1 | Open | Open
371 | T371 | 472 | NA |  |  |  | GPON | Nokia | * Testing done for new build in T-Fiber test lab . * Plan event for OLTs new SW upgradation in production environment. |  |  | Open |  | Nokia OEM | OLT |  | All the OLTs reachabled to AMS are upgraded successfully. Having dependecny on PKG-A/B/C field teams to make unreachable OLTs to reachable | All Packages | Srinivas Kodali(PKG_A), Venu& Mahesh(PKG B&C) | Sayyad Pasha |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | 472GPON | GPON | OPEN | [6 empty] | 1 | Open | Open
372 | T372 | 472 | NA |  |  |  | GPON | Nokia | TACACS Feature |  |  | Colosed | [7 empty] | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T372 | [6 empty] | 472GPON | GPON | CLOSED |  |  |  | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T372 |  | 1 | Completed & Approved | Closed before june-2025
373 | T373 | 472 | NA |  |  |  | NSO | Deployment and Installations | HSI (High Speed Internet to Household) implementation |  |  | Open |  |  |  |  | Post 24.06.25 review and direction, working for a alternate options for NSO. will come back as earliest with closure plan. |  |  | Jayant Madavi |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | 472NSO | Applications/Tools | OPEN | [6 empty] | 1 | Open | Open
374 | T374 | 472 | NA |  |  |  | NSO | Deployment and Installations | IPTV to Household implementation |  |  | Open |  |  |  |  | Post 24.06.25 review and direction, working for a alternate options for NSO. will come back as earliest with closure plan. |  |  | Jayant Madavi |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | 472NSO | Applications/Tools | OPEN | [6 empty] | 1 | Open | Open
375 | T375 | 472 | NA |  |  |  | NSO | Deployment and Installations | VOIP to Household implementation |  |  | Open |  |  |  |  | Post 24.06.25 review and direction, working for a alternate options for NSO. will come back as earliest with closure plan. |  |  | Jayant Madavi |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | 472NSO | Applications/Tools | OPEN | [6 empty] | 1 | Open | Open
376 | T376 | 472 | NA |  |  |  | NSO | Deployment and Installations | Internet to GI (Govt. Institution) implementation |  |  | Open |  |  |  |  | Post 24.06.25 review and direction, working for a alternate options for NSO. will come back as earliest with closure plan. |  |  | Jayant Madavi |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | 472NSO | Applications/Tools | OPEN | [6 empty] | 1 | Open | Open
377 | T377 | 472 | NA |  |  |  | NSO | Deployment and Installations | CCTV Unicast implementation |  |  | Open |  |  |  |  | Post 24.06.25 review and direction, working for a alternate options for NSO. will come back as earliest with closure plan. |  |  | Jayant Madavi |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | 472NSO | Applications/Tools | OPEN | [6 empty] | 1 | Open | Open
378 | T378 | 472 | NA |  |  |  | NSO | Deployment and Installations | CCTV Multicast implementation |  |  | Open |  |  |  |  | Post 24.06.25 review and direction, working for a alternate options for NSO. will come back as earliest with closure plan. |  |  | Jayant Madavi |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | 472NSO | Applications/Tools | OPEN | [6 empty] | 1 | Open | Open
379 | T379 | 472 | NA |  |  |  | NSO | Deployment and Installations | Cell Tower L2VPN implementation |  |  | Open |  |  |  |  | Post 24.06.25 review and direction, working for a alternate options for NSO. will come back as earliest with closure plan. |  |  | Jayant Madavi |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | 472NSO | Applications/Tools | OPEN | [6 empty] | 1 | Open | Open
380 | T380 | 472 | NA |  |  |  | NSO | Deployment and Installations | Dhanush Telemedicine Application implementation |  |  | Open |  |  |  |  | Post 24.06.25 review and direction, working for a alternate options for NSO. will come back as earliest with closure plan. |  |  | Jayant Madavi |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | 472NSO | Applications/Tools | OPEN | [6 empty] | 1 | Open | Open
381 | T381 | 472 | NA |  |  |  | NSO | Deployment and Installations | SDC content to Household and GI implementation |  |  | Open |  |  |  |  | Post 24.06.25 review and direction, working for a alternate options for NSO. will come back as earliest with closure plan. |  |  | Jayant Madavi |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | 472NSO | Applications/Tools | OPEN | [6 empty] | 1 | Open | Open
382 | T382 | 472 | NA |  |  |  | BSS | Development and unit testing | EY need to present landing page for suggestion - Design features of web page |  |  | Open | [7 empty] | Manoj Nibrad |  | Open | Open | Approval Email received from NOC Director | 2025-07-16 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\BSS\Artifact_T382 | [6 empty] | 472BSS | Applications/Tools | CLOSED |  |  |  | 2025-07-16 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\BSS\Artifact_T382 |  | 1 | Open | Open
383 | T383 | 472 | NA |  |  |  | DC-IT | Functional AT | Cisco prime infrastructure AT |  |  | Open |  |  |  |  | 22-Sep-25: IPMPLS Domain team to submit detailed remarks on raised queries. 08-Jul-2025 - Sandeep will come back by EoD today on extension of Cisco support renewal 01-Jul-25 : Revised FAT documents submission pending (TPA observations to be included) OEM(Cisco) suport is required to show the new test cases, Inputs provided to OEM on 14th May & 30th Jun. OEM onboarding is in progress & LnT Contracts team is coordinating | L&T | RS Rao | RS Rao |  | Open | Open | [9 empty] | 472DC-IT | Network | OPEN | [6 empty] | 1 | Open | Open
384 | T384 | 472 | NA |  |  |  | IP/MPLS | Security | GCT implementation |  |  | Open |  |  |  |  | Confirmed from IP-MPLS team for GCT implementation. |  |  | Sarmendra |  | Open | WIP | [9 empty] | 472IP/MPLS | IPMPLS | OPEN | [6 empty] | 1 | Open | Open
385 | T385 | 472 | NA |  |  |  | NSO | Design & Documentation | solution document - GI internet solution |  |  | Open | [7 empty] | RS Rao |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-05-05 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\T-FIBER T-Net for GI Broadband Service Design LLD V1.1 - T188.pdf | [6 empty] | 472NSO | Applications/Tools | CLOSED |  |  |  | 2025-05-05 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\T-FIBER T-Net for GI Broadband Service Design LLD V1.1 - T188.pdf |  | 1 | Completed & Approved | Closed after June
386 | T386 | 472 | NA |  |  |  | Security & Regulatory Compliance | Testing | Network audit and certification by ISO certified agency(Tfiber will be arranging a partner for third party audit) |  |  | Open |  |  |  |  | Subject to start of certification process. |  |  | Sarmendra |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | 472Security & Regulatory Compliance | Security | OPEN | [6 empty] | 1 | Open | Open
387 | T387 | 472 | NA |  |  |  | Security & Regulatory Compliance | Regulatory compliance | SLA Reporting for products other than Cell Tower and GIs |  |  | Colosed | [7 empty] | Siva Kumar |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-05-13 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\T387 | [6 empty] | 472Security & Regulatory Compliance | Security | CLOSED |  |  |  | 2025-05-13 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\T387 |  | 1 | Completed & Approved | Closed before june-2025
388 | T388 | 472 | NA |  | OSS | OSS | OSS | Helpdesk | OSS Integration with Helpdesk |  |  | Open |  |  |  |  | 17-05-2025: Artefacts needs to be collected from Sivakumar and seek approval. 26-06-2025: completed from OSS end |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | 472OSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
389 | T389 | 472 | NA |  | OSS | OSS | OSS | OSS | BBNL Report stabilization |  |  | Open | [7 empty] | Suresh Pawar |  |  | COMPLETED & APPROVED |  |  | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\OSS\T389 | [6 empty] | 472OSS | Applications/Tools | CLOSED | COMPLETED & APPROVED | 0 |  |  | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\OSS\T389 |  | 1 | Completed & Approved | Closed after June
390 | T390 | 472 | NA |  | OSS | OSS | OSS | OSS Dashboards | OSS Power BI Dashboard |  |  | Open |  |  |  |  | 09-09-2025: Requested reports are available, if any additional reports needed that can be incorporated |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | 472OSS | Applications/Tools | OPEN | COMPLETED | 09-09-2025: Requested reports are available, if any additional reports needed that can be incorporated |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
391 | T391 | 472 | NA |  | OSS | OSS | OSS | OSS | Auto TT for Genset |  |  | Open |  |  |  |  | 26-06-2025: Confirmation awaited from NOC |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | 472OSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
392 | T392 | 472 | NA |  | OSS | OSS | OSS | OSS | BBNL Status and Availability API integration |  |  | Open | [7 empty] | Suresh Pawar |  |  | COMPLETED & APPROVED |  |  | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\OSS\T392 | [6 empty] | 472OSS | Applications/Tools | CLOSED | COMPLETED & APPROVED | 0 |  |  | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\OSS\T392 |  | 1 | Completed & Approved | Closed after June
393 | 394 | 472 | NA |  |  |  | DC-IT | License | Once excel license for VM |  |  | Open | [7 empty] | Ravi Kishore |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-07-08 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\TNOC\Artifact for - 394 | [6 empty] | 472DC-IT | Network | CLOSED |  |  |  | 2025-07-08 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\TNOC\Artifact for - 394 |  | 1 | Completed & Approved | Closed after June
394 | 395 | 472 | NA |  |  |  | TNOC-Ops | Payments | SMS Gateway recharge |  |  | Open |  |  |  |  | SMS payment pending from Tfiber |  |  | Ahmad |  |  | COMPLETED & APPROVED | ad-ut-tfiber | 2025-07-08 | Not applicable | [6 empty] | 472TNOC-Ops | Network | CLOSED |  |  |  | 2025-07-08 | Artefacts not Required |  | 1 | Completed & Approved | Closed after June
395 | 396 | 472 | NA |  |  |  | TNOC-Ops | AMC | AMC status including HPE/OT |  |  | Open |  |  |  |  | In Place |  |  | Ahmad |  |  | COMPLETED & APPROVED | ad-ut-tfiber | 2025-07-08 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\TNOC | [6 empty] | 472TNOC-Ops | Network | CLOSED |  |  |  | 2025-07-08 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\TNOC |  | 1 | Completed & Approved | Closed after June
396 | 397 | 472 | NA |  |  |  | TNOC-Ops | Security | Access cards - 38 QTY |  |  | Open |  |  |  |  | Access card procured |  |  | Ahmad |  |  | COMPLETED & APPROVED | ad-ut-tfiber | 2025-07-08 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\TNOC | [6 empty] | 472TNOC-Ops | Network | CLOSED |  |  |  | 2025-07-08 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\TNOC |  | 1 | Completed & Approved | Closed after June
397 | 398 | 472 | NA |  |  |  | GPON | Tejas | L&T is asked to submit response against untdertakings for the GPON Tejas issues |  |  | Colosed | [7 empty] | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\Tejas Undertaking | [6 empty] | 472GPON | GPON | CLOSED |  |  |  | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\Tejas Undertaking |  | 1 | Completed & Approved | Closed before june-2025
398 | 399 | 472 | NA |  |  |  | GPON | Tejas | Requested Tejas to enable the TR-069 for T-Fiber deployed elements |  |  | Open |  | Tejas OEM | ONT |  | 20-Sep-25: Artefacts submiited and approved MoM point Not in RFP and L&T confirmed this is not in scope. However, confirmation awaited from OEM on the shared list of parameters |  |  | Sayyad Pasha |  |  | COMPLETED & APPROVED | [9 empty] | 472GPON | GPON | CLOSED |  |  |  | 2025-09-20 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\399 |  | 1 | Completed & Approved | Closed after June
399 | 400 | 472 | NA |  |  |  | GPON | Tejas | Accounting for Tejas OLT and EMS |  |  | Colosed | [7 empty] | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T167 | [6 empty] | 472GPON | GPON | CLOSED |  |  |  | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T167 |  | 1 | Completed & Approved | Closed before june-2025
400 | 401 | 472 | NA |  |  |  | GPON | Tejas | Accounting: All the parameters are not available in service created and Activated log(Including creation/activation of UNI) |  |  | Colosed | [7 empty] | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T167 | [6 empty] | 472GPON | GPON | CLOSED |  |  |  | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T167 |  | 1 | Completed & Approved | Closed before june-2025
401 | 402 | 472 | NA |  |  |  | GPON | Tejas | Accounting: All the parameters are not available in service deactivated and deleted log(Including deactivation/deletion of UNI) |  |  | Colosed | [7 empty] | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T167 | [6 empty] | 472GPON | GPON | CLOSED |  |  |  | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T167 |  | 1 | Completed & Approved | Closed before june-2025
402 | 403 | 472 | NA |  |  |  | GPON | Tejas | Accounting: Log is not available for OLT reboot |  |  | Colosed | [7 empty] | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T167 | [6 empty] | 472GPON | GPON | CLOSED |  |  |  | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T167 |  | 1 | Completed & Approved | Closed before june-2025
403 | 404 | 472 | NA |  |  |  | GPON | Tejas | Accounting: Log is not available for ONT reboot |  |  | Colosed | [7 empty] | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T167 | [6 empty] | 472GPON | GPON | CLOSED |  |  |  | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T167 |  | 1 | Completed & Approved | Closed before june-2025
404 | 405 | 472 | NA |  |  |  | GPON | Tejas | Accounting: Log is not available for the change of OLT location parameter from EMS |  |  | Colosed | [7 empty] | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T167 | [6 empty] | 472GPON | GPON | CLOSED |  |  |  | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T167 |  | 1 | Completed & Approved | Closed before june-2025
405 | 406 | 472 | NA |  |  |  | GPON | Tejas | Enabling TACACS in Tejas OLT |  |  | Colosed | [7 empty] | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T167 | [6 empty] | 472GPON | GPON | CLOSED |  |  |  | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T167 |  | 1 | Completed & Approved | Closed before june-2025
406 | 407 | 472 | NA |  |  |  | GPON | Tejas | CIR/PIR in OLT/EMS |  |  | Open |  | Tejas OEM | EMS/OLT |  | 20-Sep-25: CIR and PIR are different parameters but Tejas OLT considered only CIR not PIR, After combined recent meeting with OEM agreed to provide an alternate solution for config CIR and PIR seperately. Update awaited from OEM Tejas to provide the solution and demo for this issue. Update awaited from OEM | Tejas | Deepak | Sayyad Pasha |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | 472GPON | GPON | OPEN | [6 empty] | 1 | Open | Open
407 | 408 | 472 | NA |  |  |  | GPON | Tejas | Port Description is not available for ONT Eth Ports |  |  | Colosed | [7 empty] | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\ONT Ports description | [6 empty] | 472GPON | GPON | CLOSED |  |  |  | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\ONT Ports description |  | 1 | Completed & Approved | Closed before june-2025
408 | 409 | 472 | NA |  |  |  | GPON | Tejas | Unable to modify the Service Name |  |  | Open | [7 empty] | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-07-03 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\409 | [6 empty] | 472GPON | GPON | CLOSED |  |  |  | 2025-07-03 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\409 |  | 1 | Completed & Approved | Closed after June
409 | 410 | 472 | NA |  |  |  | GPON | Tejas | Special Characters not allowing in User Creation in EMS |  |  | Colosed | [7 empty] | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\Special Characters | [6 empty] | 472GPON | GPON | CLOSED |  |  |  | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\Special Characters |  | 1 | Completed & Approved | Closed before june-2025
410 | 411 | 472 | NA |  |  |  | GPON | Tejas | Unable to add 4th UNI in a service with 1Gb bandwidth |  |  | Colosed | [7 empty] | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\Report of ONT UNI in a Service | [6 empty] | 472GPON | GPON | CLOSED |  |  |  | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\Report of ONT UNI in a Service |  | 1 | Completed & Approved | Closed before june-2025
411 | 412 | 472 | NA |  |  |  | GPON | Tejas | End Customer MAC Address report from EMS |  |  | Colosed | [7 empty] | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\Ens users MAC address report | [6 empty] | 472GPON | GPON | CLOSED |  |  |  | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\Ens users MAC address report |  | 1 | Completed & Approved | Closed before june-2025
412 | 413 | 472 | NA |  |  |  | GPON | Tejas | If Mixed service deleted from EMS and discovered then service type is changing to HIS |  |  | Colosed | [7 empty] | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\Discovery of Mixed Service | [6 empty] | 472GPON | GPON | CLOSED |  |  |  | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\Discovery of Mixed Service |  | 1 | Completed & Approved | Closed before june-2025
413 | 414 | 472 | NA |  |  |  | GPON | Tejas | Live PM monitoring per UNI in EMS service Window |  |  | Open | [7 empty] | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-07-10 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\416 | [6 empty] | 472GPON | GPON | CLOSED |  |  |  | 2025-07-10 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\416 |  | 1 | Completed & Approved | Closed after June
414 | 415 | 472 | NA |  |  |  | GPON | Tejas | Required Consolidated Service invenotry report with ONT UNI details from EMS |  |  | Colosed | [7 empty] | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\Serivce Report | [6 empty] | 472GPON | GPON | CLOSED |  |  |  | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\Serivce Report |  | 1 | Completed & Approved | Closed before june-2025
415 | 416 | 472 | NA |  |  |  | GPON | Tejas | Unable to Enable PM from EMS |  |  | Open | [7 empty] | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-07-07 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\414 | [6 empty] | 472GPON | GPON | CLOSED |  |  |  | 2025-07-07 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\414 |  | 1 | Completed & Approved | Closed after June
416 | 417 | 472 | NA |  |  |  | GPON | Tejas | While creating service profile, maximum bandwidth is not taking 1024000 only considering 1000000 |  |  | Open | [7 empty] | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-TFiber | 2025-07-31 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\417 | [6 empty] | 472GPON | GPON | CLOSED |  |  |  | 2025-07-31 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\417 |  | 1 | Completed & Approved | Closed after June
417 | 418 | 472 | NA |  |  |  | GPON | Tejas | Report of Syslog enabled in OLT |  |  | Colosed | [7 empty] | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\Report of Syslog enabled in Tejas OLTs | [6 empty] | 472GPON | GPON | CLOSED |  |  |  | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\Report of Syslog enabled in Tejas OLTs |  | 1 | Completed & Approved | Closed before june-2025
418 | 419 | 472 | NA |  |  |  | GPON | Tejas | Report of Radius enable in OLT |  |  | Colosed | [7 empty] | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\Report of Radius enabled in Tejas OLTs | [6 empty] | 472GPON | GPON | CLOSED |  |  |  | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\Report of Radius enabled in Tejas OLTs |  | 1 | Completed & Approved | Closed before june-2025
419 | 420 | 472 | NA |  |  |  | GPON | Tejas | OLT (SNMP-V3) status is not updating in EMS |  |  | Colosed | [7 empty] | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T167 | [6 empty] | 472GPON | GPON | CLOSED |  |  |  | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T167 |  | 1 | Completed & Approved | Closed before june-2025
420 | 421 | 472 | NA |  |  |  | GPON | Tejas | ONT status showing as Unexpected |  |  | Colosed | [7 empty] | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\ONT Unexpected State | [6 empty] | 472GPON | GPON | CLOSED |  |  |  | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\ONT Unexpected State |  | 1 | Completed & Approved | Closed before june-2025
421 | 422 | 472 | NA |  |  |  | GPON | Tejas | Unable to add multiple unis while creating mixed service |  |  | Colosed | [7 empty] | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\Create Service with Mulitple UNIs | [6 empty] | 472GPON | GPON | CLOSED |  |  |  | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\Create Service with Mulitple UNIs |  | 1 | Completed & Approved | Closed before june-2025
422 | 423 | 472 | NA |  |  |  | GPON | Tejas | ONT ETH Port status monitoring from OSS |  |  | Colosed | [7 empty] | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\Tejas LAN LOS | [6 empty] | 472GPON | GPON | CLOSED |  |  |  | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\Tejas LAN LOS |  | 1 | Completed & Approved | Closed before june-2025
423 | 424 | 472 | NA |  |  |  | GPON | Tejas | Unable to create service with same vlans on 2 diferent UNI ports |  |  | Colosed | [7 empty] | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\Service Report | [6 empty] | 472GPON | GPON | CLOSED |  |  |  | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\Service Report |  | 1 | Completed & Approved | Closed before june-2025
424 | 425 | 472 | NA |  |  |  | GPON | Tejas | OLT Node not reachable alarm clearance and regeneration |  |  | Open | [7 empty] | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-07-05 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\425 | [6 empty] | 472GPON | GPON | CLOSED |  |  |  | 2025-07-05 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\425 |  | 1 | Completed & Approved | Closed after June
425 | 426 | 472 | NA |  |  |  | GPON | Tejas | Port Description is not available for all ONT UNI Ports |  |  | Colosed | [7 empty] | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\ONT Ports description | [6 empty] | 472GPON | GPON | CLOSED |  |  |  | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\ONT Ports description |  | 1 | Completed & Approved | Closed before june-2025
426 | 427 | 472 | NA |  |  |  | GPON | Tejas | In the Manage ONT Page we need have'(District name Location Name) 'In the Location field |  |  | Colosed | [7 empty] | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\OLT Partition Label in ONT Page | [6 empty] | 472GPON | GPON | CLOSED |  |  |  | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\OLT Partition Label in ONT Page |  | 1 | Completed & Approved | Closed before june-2025
427 | 428 | 472 | NA |  |  |  | GPON | Tejas | Automatically services converting from Active to Conflict - EMS |  |  | Colosed | [7 empty] | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T167 | [6 empty] | 472GPON | GPON | CLOSED |  |  |  | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T167 |  | 1 | Completed & Approved | Closed before june-2025
428 | 429 | 472 | NA |  |  |  | GPON | Tejas | DIAGUSER credentials getting reset after OLT Reboot |  |  | Colosed | [7 empty] | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\DIAGUSER Credentials are Not Resetting | [6 empty] | 472GPON | GPON | CLOSED |  |  |  | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\DIAGUSER Credentials are Not Resetting |  | 1 | Completed & Approved | Closed before june-2025
429 | 430 | 472 | NA |  |  |  | GPON | Tejas | while adding uni in EMS, list of downstream profiles are highlighting in the bottom |  |  | Open | [7 empty] | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-07-05 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\430 | [6 empty] | 472GPON | GPON | CLOSED |  |  |  | 2025-07-05 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\430 |  | 1 | Completed & Approved | Closed after June
430 | 431 | 472 | NA |  |  |  | GPON | Tejas | Unable to add uni without translation in a translation service |  |  | Colosed | [7 empty] | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\Add UNI in Translated Service | [6 empty] | 472GPON | GPON | CLOSED |  |  |  | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\Add UNI in Translated Service |  | 1 | Completed & Approved | Closed before june-2025
431 | 432 | 472 | NA |  |  |  | GPON | Tejas | Nokia ONT ethernet port status is not updating under Tejas OLT | End user services working and not working status unable to monitor |  | Open |  | Tejas OEM | OLT/ONT |  | 13-Sep-2025: Testing is in progress for the ONT ETH status for different 3rd party ONTs under Tejas OLT 30-Aug-2025: Having dependency on both Tejas and Nokia. Also to test and verify the behaviour of the ONT ETH status for different 3rd party ONTs under Tejas OLT 18-Aug-2025 : Tejas updated as below As per ITU-T 988 standard, Section 9.5.1 – Physical path termination point Ethernet UNI, the Operational State attribute indicated whether the ME is capable of performing its function. As this is function of ONU, the operational state of the ONU Ethernet UNI is updated to OLT via AVC indications from the ONU. As per debugging done, the AVC indications are not received from Nokia ONU because of which OLT is not able to update UI about the “Operational State” of the ONU Ethernet port. 08-Aug-2025 : This point has been discussed in the call and TFiber asked to provide the solution. Tejas confirmed that they will check and confirm 02-Aug-2025 : This issue has been discussed with TFiber. When a LAN cable is connected to or removed from the ONT Ethernet port, the operational status is not updating in the OLT. However, the corresponding alarm is being generated and cleared as expected. This matter will be raised during the Tejas call scheduled for 04-Aug-2025 at 4:00 PM. 22-July-2025 : As per Nokia they are having the status update by alarm notification but not with the seperate byte for the status update. Same has been checking with Tejas to get the solution 18-July-2025 : A call scheduled with Nokia on 21-July-2025 to discuss on this issue 11-July-2025 : Also observed that ONT ethernet status is not updating only when Eth port is bridge mode whereas in Route status is updating. Same has been highlighted to Tejas. Working with both Nokia and Tejas for the closure 04-July-2025 : Nokia checking internally on the shared logs 03-July-2025 : Tejas responded that whenever ONT eth status is updating Nokia ONT is not sending the expected OMCI message. In the OMCI message, 3rd byte represents the status of ONT Eth which is not updating. Same has been checking with Nokia 30-June-2025 : Tejas analysing the shared logs on 23-June-2025 and Tejas has to revert with update Nokia ONT ethernet port status is not updating when connected under Tejas OLT however alarms are receiveing on ont eth port. Workaround applied as alarms available for the ONT ETH port status. Nokia has provided the required logs and Tejas is working on the same | Tejas | Deepak | Sayyad Pasha |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | 472GPON | GPON | OPEN | [6 empty] | 1 | Open | Open
432 | 433 | 472 | NA |  |  |  | GPON | Tejas | Tejas ONT Software Upgrade which are connected under Nokia OLT |  |  | Open |  | Tejas OEM | ONT |  | 20-Sep-25: During the ONT software upgradation 11 ONTs got faulty, So GPON Team asked the Tejas team to provided RCA for the 11 ONTs and hold the upgradation activity temporarely. Tejas team provided the RCA 11 ONt Stating that 11 ONTs got faulty not because of upgradation activity . The reason for faulty is 3 ONTs of component and 8 ONTs of Memory corrupted due to multiple reboots. Note: Based on RCA, Now upgradation activity is being taken up(1312 ONTs upgradation completed out of 9530 as on today) 13-Sep-2025: Tejas confirmed that they don't have the 9logs to provide but shared the RCA by verifyting the ONTs at the time of repair 30-Aug2025: Having dependency on Tejas. Asked Tejas to provide the supporting logs. As per Tejas RCA ONT got faulty due to component faulty and memory corruption but these ONTs are working fine before the upgarde activity and only went faulty while performing the upgrade. Tejas have provide the clarity on this to proceed the upgrade for the remaining ONTs 08-Aug-2025 : Tejas provided the below RCA As per analysis, the ONT software upgrade from NOC is not the cause for ONT going down. On 3 ONTs a component was entering faulty state, this has been replaced. Remaining 8 ONTs had a file corruption in memory due to earlier multiple reboot events, this has been resolved by Re-Programming the ONT 02-Aug-2025 : Tejas yet to respond on this issue, same will be raised during the Tejas call scheduled for 04-Aug-2025 at 4:00 PM. 25-July-2025 : Tejas working on the delivered ONTs at their repair center. Tejas yet to share the update on this 14-July-2025 : ONTs delivered at Tejas repair center on 14-July-2025. Same has been communicated to Tejas team to expedite the process and share the RCA 14-July-2025 : ONT still not delivered at Tejas repai center, seems to be courier issue. Informed to concerned team to check and make it to delivier 07-July-2025 : ONTs are intransit to Tejas repair center To provide the contract of RMA on faulty devices replacement or repair 30-June-2025 : Successfully upgraded 600 ONTs in the production environment. All of them came up operational with no issue observed. However, 11 ONTs went unresponsive, and RMA raised for those. 23-June-2025 : RMA raised with Tejas for the ONTs ONTs which are running software version lower than 2.3.5.53 are upgrading locally | L&T |  | Sayyad Pasha |  | Open | WIP | [9 empty] | 472GPON | GPON | OPEN | [6 empty] | 1 | Open | Open
433 | 434 | 472 | NA |  |  |  | GPON | Tejas | Script to change the pasword of DIAGUSER and tejas users |  |  | Colosed | [7 empty] | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\434 | [6 empty] | 472GPON | GPON | CLOSED |  |  |  | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\434 |  | 1 | Completed & Approved | Closed before june-2025
434 | 435 | 472 | NA |  |  |  | GPON | Tejas | Unable to configure downstream profiles to the ONT UNIs -- This option is available in production EMS but not available in latest released EMS |  |  | Colosed | [7 empty] | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T167 | [6 empty] | 472GPON | GPON | CLOSED |  |  |  | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T167 |  | 1 | Completed & Approved | Closed before june-2025
435 | 436 | 472 | NA |  |  |  | GPON | Tejas | MAC address of end device is not reflecting in COLT FDB entries whereas MAC address is available in service level FDB entries |  |  | Colosed | [7 empty] | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T167 | [6 empty] | 472GPON | GPON | CLOSED |  |  |  | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T167 |  | 1 | Completed & Approved | Closed before june-2025
436 | 437 | 472 | NA |  |  |  | GPON | Tejas | Whenever the ONT software is being downloaded to the OLT, the OLT management going down |  |  | Open | [7 empty] | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-TFiber | 2025-07-31 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\437 | [6 empty] | 472GPON | GPON | CLOSED |  |  |  | 2025-07-31 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\437 |  | 1 | Completed & Approved | Closed after June
437 | 438 | 472 | NA |  |  |  | GPON | Tejas | The download bandwidth is not controlled for Nokia ONTs connected to the Tejas OLT |  |  | Colosed | [7 empty] | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T167 | [6 empty] | 472GPON | GPON | CLOSED |  |  |  | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T167 |  | 1 | Completed & Approved | Closed before june-2025
438 | 439 | 472 | NA |  |  |  | GPON | Tejas | Unable to add node in EMS with TACACS user |  |  | Colosed | [7 empty] | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T167 | [6 empty] | 472GPON | GPON | CLOSED |  |  |  | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T167 |  | 1 | Completed & Approved | Closed before june-2025
439 | 440 | 472 | NA |  |  |  | GPON | Tejas | API for ONT creation (Bridge/Route), location name update |  |  | Colosed | [7 empty] | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API | [6 empty] | 472GPON | GPON | CLOSED |  |  |  | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API |  | 1 | Completed & Approved | Closed before june-2025
440 | 441 | 472 | NA |  |  |  | GPON | Tejas | API for GI-BB Service, combo port, mixed service - Bridge Mode with/without translation, including uplink port configuration |  |  | Colosed | [7 empty] | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API | [6 empty] | 472GPON | GPON | CLOSED |  |  |  | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API |  | 1 | Completed & Approved | Closed before june-2025
441 | 442 | 472 | NA |  |  |  | GPON | Tejas | API for GI-BB Service, combo port, mixed service - Route Mode with/without translation, including uplink port configuration |  |  | Open | [7 empty] | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-TFiber | 2025-08-06 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\442 | [6 empty] | 472GPON | GPON | CLOSED |  |  |  | 2025-08-06 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\442 |  | 1 | Completed & Approved | Closed after June
442 | 443 | 472 | NA |  |  |  | GPON | Tejas | API for TDIA Service, combo port, mixed service - Bridge Mode(Tag, Untag) including uplink port configuration |  |  | Colosed | [7 empty] | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API | [6 empty] | 472GPON | GPON | CLOSED |  |  |  | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API |  | 1 | Completed & Approved | Closed before june-2025
443 | 444 | 472 | NA |  |  |  | GPON | Tejas | API for TDIA Service, combo port, mixed service - Route Mode, including uplink port configuration |  |  | Colosed | [7 empty] | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API | [6 empty] | 472GPON | GPON | CLOSED |  |  |  | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API |  | 1 | Completed & Approved | Closed before june-2025
444 | 445 | 472 | NA |  |  |  | GPON | Tejas | API for Household Services, including uplink port configuration |  |  | Colosed | [7 empty] | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API | [6 empty] | 472GPON | GPON | CLOSED |  |  |  | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API |  | 1 | Completed & Approved | Closed before june-2025
445 | 446 | 472 | NA |  |  |  | GPON | Tejas | AP for IPTV services, including uplink port configuration |  |  | Colosed | [7 empty] | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API | [6 empty] | 472GPON | GPON | CLOSED |  |  |  | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API |  | 1 | Completed & Approved | Closed before june-2025
446 | 447 | 472 | NA |  |  |  | GPON | Tejas | API for VOIP services, including uplink port configuration |  |  | Colosed | [7 empty] | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API | [6 empty] | 472GPON | GPON | CLOSED |  |  |  | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API |  | 1 | Completed & Approved | Closed before june-2025
447 | 448 | 472 | NA |  |  |  | GPON | Tejas | API required to provision ONT along with selecting specific UNI port in ONT |  |  | Colosed | [7 empty] | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API | [6 empty] | 472GPON | GPON | CLOSED |  |  |  | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API |  | 1 | Completed & Approved | Closed before june-2025
448 | 449 | 472 | NA |  |  |  | GPON | Tejas | API required to provision ONT with multiple services along with selecting specific UNI port in ONT |  |  | Colosed | [7 empty] | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API | [6 empty] | 472GPON | GPON | CLOSED |  |  |  | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API |  | 1 | Completed & Approved | Closed before june-2025
449 | 450 | 472 | NA |  |  |  | GPON | Tejas | API required to provision ONT with same service on all ports |  |  | Colosed | [7 empty] | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API | [6 empty] | 472GPON | GPON | CLOSED |  |  |  | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API |  | 1 | Completed & Approved | Closed before june-2025
450 | 451 | 472 | NA |  |  |  | GPON | Tejas | API to configure multiple vlans on single ONT UNI Port |  |  | Colosed | [7 empty] | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API | [6 empty] | 472GPON | GPON | CLOSED |  |  |  | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API |  | 1 | Completed & Approved | Closed before june-2025
451 | 452 | 472 | NA |  |  |  | GPON | Tejas | API for the Q&Q services |  |  | Colosed | [7 empty] | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API | [6 empty] | 472GPON | GPON | CLOSED |  |  |  | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API |  | 1 | Completed & Approved | Closed before june-2025
452 | 453 | 472 | NA |  |  |  | GPON | Tejas | Configuration, API for extedning services to enterprise customers for cell towers |  |  | Colosed | [7 empty] | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API | [6 empty] | 472GPON | GPON | CLOSED |  |  |  | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API |  | 1 | Completed & Approved | Closed before june-2025
453 | 454 | 472 | NA |  |  |  | GPON | Tejas | API to configure Rythuvedika, MRO, School Services, CCTV |  |  | Colosed | [7 empty] | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API | [6 empty] | 472GPON | GPON | CLOSED |  |  |  | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API |  | 1 | Completed & Approved | Closed before june-2025
454 | 455 | 472 | NA |  |  |  | GPON | Tejas | API to verify and enable the PM |  |  | Colosed | [7 empty] | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API | [6 empty] | 472GPON | GPON | CLOSED |  |  |  | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API |  | 1 | Completed & Approved | Closed before june-2025
455 | 456 | 472 | NA |  |  |  | GPON | Tejas | API to configure Vlan and Profiles in OLT |  |  | Colosed | [7 empty] | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API | [6 empty] | 472GPON | GPON | CLOSED |  |  |  | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API |  | 1 | Completed & Approved | Closed before june-2025
456 | 457 | 472 | NA |  |  |  | GPON | Tejas | Verification of the services configured by NSO through Playbook(Cisco Tool) |  |  | Colosed | [7 empty] | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API to validate the configured Services | [6 empty] | 472GPON | GPON | CLOSED |  |  |  | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API to validate the configured Services |  | 1 | Completed & Approved | Closed before june-2025
457 | 458 | 472 | NA |  |  |  | GPON | Tejas | API to configure ONT UNI Port as tagged vlan |  |  | Colosed | [7 empty] | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API | [6 empty] | 472GPON | GPON | CLOSED |  |  |  | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API |  | 1 | Completed & Approved | Closed before june-2025
458 | 459 | 472 | NA |  |  |  | GPON | Tejas | API to validate the profiles, vlans available in OLT,ONT |  |  | Colosed | [7 empty] | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API to validate the configured Services | [6 empty] | 472GPON | GPON | CLOSED |  |  |  | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API to validate the configured Services |  | 1 | Completed & Approved | Closed before june-2025
459 | 460 | 472 | NA |  |  |  | GPON | Tejas | API to change the ONT ETH Port to Bridge to Route and Vice versa |  |  | Colosed | [7 empty] | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API | [6 empty] | 472GPON | GPON | CLOSED |  |  |  | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API |  | 1 | Completed & Approved | Closed before june-2025
460 | 461 | 472 | NA |  |  |  | GPON | Tejas | API to suspend/delete the service from a ONT UNI Port |  |  | Colosed | [7 empty] | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API | [6 empty] | 472GPON | GPON | CLOSED |  |  |  | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API |  | 1 | Completed & Approved | Closed before june-2025
461 | 462 | 472 | NA |  |  |  | GPON | Tejas | API to suspend/delete the complete service |  |  | Colosed | [7 empty] | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API | [6 empty] | 472GPON | GPON | CLOSED |  |  |  | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API |  | 1 | Completed & Approved | Closed before june-2025
462 | 463 | 472 | NA |  |  |  | GPON | Tejas | API to modify the service- ONT, UNI Port, bandwidth, vlan, description, unatgged to tag or vice versa., |  |  | Open |  | Tejas OEM | EMS/OLT |  | Having dependency on NSO and BSS | NSO | Jayanth | Sayyad Pasha |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | 472GPON | GPON | OPEN | [6 empty] | 1 | Open | Open
463 | 464 | 472 | NA |  |  |  | GPON | Tejas | API to configure and delete the WAN profiles in WiFi ONT |  |  | Colosed | [7 empty] | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API | [6 empty] | 472GPON | GPON | CLOSED |  |  |  | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API |  | 1 | Completed & Approved | Closed before june-2025
464 | 465 | 472 | NA |  |  |  | GPON | Tejas | API to make PON Port admin up / down |  |  | Colosed | [7 empty] | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API | [6 empty] | 472GPON | GPON | CLOSED |  |  |  | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API |  | 1 | Completed & Approved | Closed before june-2025
465 | 466 | 472 | NA |  |  |  | GPON | Tejas | API to create/delete service Profile |  |  | Colosed | [7 empty] | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API | [6 empty] | 472GPON | GPON | CLOSED |  |  |  | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API |  | 1 | Completed & Approved | Closed before june-2025
466 | 467 | 472 | NA |  |  |  | GPON | Tejas | Required complete API and Template developer document |  |  | Colosed | [7 empty] | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API Document | [6 empty] | 472GPON | GPON | CLOSED |  |  |  | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API Document |  | 1 | Completed & Approved | Closed before june-2025
467 | 468 | 472 | NA |  |  |  | GPON | Nokia | ONT Ethernet Port PM Report |  |  | Colosed | [7 empty] | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\ONT ETH PM Report | [6 empty] | 472GPON | GPON | CLOSED |  |  |  | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\ONT ETH PM Report |  | 1 | Completed & Approved | Closed before june-2025
468 | 469 | 472 | NA |  |  |  | GPON | Nokia | ONT Wifi/Route Mode PM Report |  |  | Colosed | [7 empty] | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\ONT WiFi PM Report | [6 empty] | 472GPON | GPON | CLOSED |  |  |  | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\ONT WiFi PM Report |  | 1 | Completed & Approved | Closed before june-2025
469 | 470 | 472 | NA |  |  |  | GPON | Nokia | PM Report for 24hrs of OLT,ONT,ONT Eth Port(Bridge/Route), Wifi |  |  | Open | [7 empty] | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-TFiber | 2025-07-31 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\470 | [6 empty] | 472GPON | GPON | CLOSED |  |  |  | 2025-07-31 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\470 |  | 1 | Completed & Approved | Closed after June
470 | 471 | 472 | NA |  |  |  | GPON | Nokia | ONT ETH Port status monitoring from OSS |  |  | Colosed | [7 empty] | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\Nokia LAN LOS | [6 empty] | 472GPON | GPON | CLOSED |  |  |  | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\Tejas LAN LOS |  | 1 | Completed & Approved | Closed before june-2025
471 | 472 | 472 | NA |  |  |  | GPON | Nokia | Unable to browse Internet when IPV6 configured in wifi ONT |  |  | Open | [7 empty] | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-TFiber | 2025-07-31 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\472 | [6 empty] | 472GPON | GPON | CLOSED |  |  |  | 2025-07-31 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\472 |  | 1 | Completed & Approved | Closed after June
2428 | T2A | 472 | NA |  |  |  | Security & Regulatory Compliance | Security | Ciena to comply the password policy for MCP and field nodes, though Alepo AAA. |  |  | Open |  |  |  |  | Password managment policy for ciena need to be finalised and to be approved by authority prior implentations |  |  | Sarmendra |  | Open | WIP | [9 empty] | 472Security & Regulatory Compliance | Security | OPEN | [6 empty] | 1 | Open | Open
`

## MOM-Summary (hidden)
Sum of Qty | Column Labels
Row Labels | Closed after June | Closed before june-2025 | Completed but Verification undrer Process | Open | Grand Total
Ahmad | 21 | 18 |  | 9 | 48
Jayant Madavi |  |  | 9 | 47 | 56
Kaushalendra Kumar |  |  | 103 | 44 | 147
Manoj Nibrad |  |  |  | 371 | 371
Ravi Kishore | 4 | 1 | 4 | 6 | 15
RS Rao | 1 | 2 |  |  | 3
S Kodali |  |  |  | 30 | 30
Sarmendra |  |  | 16 | 126 | 142
Sayyad Pasha | 1 | 1 |  | 3 | 5
Siva Kumar | 57 |  |  | 36 | 93
Sivaprasad | 142 | 22 |  | 144 | 308
Srinivas Kommreddy |  |  | 3 |  | 3
Suresh Kumar | 1 |  |  | 2 | 3
Suresh Pawar |  |  | 37 | 15 | 52
TFiber |  |  | 2 |  | 2
Grand Total | 227 | 44 | 174 | 833 | 1278

## MOM-Detailed Sheet (hidden)
Slno | UniqueID | Category | Meeting Date | Priority | Ramana | Ramana-Domain | Domain | Sub-Domain | Action Point | Impact | Priority | Baseline Status | xx | Application | Module | Remarks | Remarks | Organization | Owner | Owner(L&T) | Target Date to Complete | Open | Revised Status (L&T) As on 18-Sep-2025 | Approved BY (TF) | Approval Date(TF) | Link of evidences | R | S | T | U | V | W | X | Tfiber-Cat | Derived Status (L&T) | OSS | OSS Remarks | Ramana Remarks as on 19-Sep-2025 | T Fiber Appoved Date | Artefacts | Target Date | Qty | Ramana-Remarks | Updated on 13-Oct-2025
472 | M1 | MOM | 2023-02-06 |  |  |  | NOC Operationalization | Dashboards | Submit a fortnightly report (Kanban chart) for monitoring all activities in TNOC, including OSS, BSS, NSO, etc. |  | Critical | Open |  | OSS Dashboards |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1 | Completed & Approved | Closed after June
473 | M10 | MOM | 2023-04-03 |  |  |  | GIS | Resource Related | Evaluation of License Sufficiency and Ramp-Up Plan |  | Critical | Open |  | OSS Dashboards |  |  | TFIBER is a critical dependency for closing the GIS licenses |  |  | Kaushalendra Kumar |  | Open | Open | [9 empty] | MOMGIS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
474 | M100 | MOM | 2023-08-01 |  |  |  | Helpdesk | Handbook & SOPs | Call Escalation Recording Process |  | Critical | open |  |  |  | Closed | 25-Sep-25: Artefacts to be uploaded |  |  | Siva Kumar |  |  | COMPLETED & APPROVED | [9 empty] | MOMHelpdesk | Helpdesk (Contact Center) | CLOSED |  |  |  | 2025-09-24 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\M100 |  | 1 | Completed & Approved | Closed after June
475 | M1000 | MOM | 2024-01-25 |  |  |  | WFM |  | Adopt WFM by packages B & C and procure licenses |  | Critical | Open |  |  |  |  | TFIBER is a critical dependency for closing the WFM license |  |  | Kaushalendra Kumar |  | Open | Open | [9 empty] | MOMWFM | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
476 | M1001 | MOM | 2024-01-25 |  |  |  | Field Related |  | Complete implementation of Mandal rings for NoFN PH-1 to declare District Go-Live |  | Critical | Open |  |  |  |  | MR-06 & MR-25 Open due to ROW issue Rest all closed. |  |  | S Kodali |  | Open | Open | [9 empty] | MOMField Related | Field Related issues | OPEN |  |  | Project Team |  | #N/A |  | 1 | Open | Open
477 | M1002 | MOM | 2024-01-25 |  |  |  | Field Related |  | Restore all social welfare and tribal welfare schools to serviceable condition |  | Critical | Open |  |  |  |  | Ongoing process as per priority from clients |  |  | S Kodali |  | Open | Open | [9 empty] | MOMField Related | Field Related issues | OPEN |  |  | Ongoing operations, O&M Team |  | #N/A |  | 1 | Open | Open
478 | M1003 | MOM | 2024-01-25 |  |  |  | Field Related |  | Complete all GI connectivity by March '24 and secure GI payments |  | Critical | Open |  |  |  |  | Completed for |  |  | S Kodali |  | Open | Open | [9 empty] | MOMField Related | Field Related issues | OPEN |  |  | Project Team |  | #N/A |  | 1 | Open | Open
479 | M1004 | MOM | 2024-01-25 |  |  |  | Field Related |  | Focus on top 4 priorities for network readiness |  | Critical | Open | [7 empty] | S Kodali |  | Open | Open | [9 empty] | MOMField Related | Field Related issues | OPEN |  |  | Project Team |  | #N/A |  | 1 | Open | Open
480 | M1005 | MOM | 2024-01-25 |  |  |  | Field Related |  | Make the network ready for service review by State IT&EC Minister |  | Critical | Open | [7 empty] | S Kodali |  | Open | Open | [9 empty] | MOMField Related | Field Related issues | OPEN |  |  | Project Team |  | #N/A |  | 1 | Open | Open
481 | M1006 | MOM | 2024-02-13 |  |  |  | Field Related |  | Issue with status of Sangareddy district E2E completion |  | Critical | Open |  |  |  |  | 9 Mandal E2E completed , 2 WIP , balance 12 Mandal target by Dec'25 2 mandals BER/ ROW permission issue/not feasable |  |  | S Kodali |  | Open | Open | [9 empty] | MOMField Related | Field Related issues | OPEN |  |  | Project Team |  | #N/A |  | 1 | Open | Open
482 | M1007 | MOM | 2024-02-13 |  |  |  | Field Related |  | Status of GP migrations and POP completion |  | Critical | Open |  |  |  |  | 3520 GPs Completed as work front released till date. |  |  | S Kodali |  | Open | Open | [9 empty] | MOMField Related | Field Related issues | OPEN |  |  | Project Team |  | #N/A |  | 1 | Open | Open
483 | M1008 | MOM | 2024-02-13 |  |  |  | Field Related |  | Pending mandals for End-End AT |  | Critical | Open |  |  |  |  | 42 mandals WIP as per work front availability |  |  | S Kodali |  | Open | Open | [9 empty] | MOMField Related | Field Related issues | OPEN |  |  | Project Team |  | #N/A |  | 1 | Open | Open
484 | M1009 | MOM | 2024-02-13 |  |  |  | Security & Regulatory Compliance | Regulatory Compliance | Non-compliance with IP-MAC binding |  | Critical | Open |  |  |  |  | Port winding is possible , however it will cause difficulty with field units. need brainstormig before deployment of Mac binding |  |  | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
485 | M101 | MOM | 2023-08-01 |  |  |  | Helpdesk | User Experience | Missed Call Feature on WhatsApp |  | Critical | open |  |  |  | WIP | 11-Sep-25: Existing product will not Support | L&T | Shiva kumar | Siva Kumar |  | Open | WIP | [9 empty] | MOMHelpdesk | Helpdesk (Contact Center) | OPEN | [6 empty] | 1 | Open | Open
486 | M1010 | MOM | 2024-02-13 |  |  |  | OEM Related |  | Issues with application integration |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMOEM Related | OEM Related Issues | OPEN | [6 empty] | 1 | Open | Open
487 | M1011 | MOM | 2024-02-13 |  |  |  | Security & Regulatory Compliance | Regulatory Compliance | Review of submitted policy documents |  | Critical | Open |  |  |  |  | 02 Policy has been cleared by TPA . Work on balance policy is in process |  |  | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
488 | M1012 | MOM | 2024-02-13 |  |  |  | NOC Operationalization |  | Status of asset management automation |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMNOC Operationalization | Network | OPEN | [6 empty] | 1 | Open | Open
489 | M1013 | MOM | 2024-02-13 |  |  |  | Security & Regulatory Compliance | Compliance | Matter of security for personnel access |  | Critical | Open |  |  |  |  | Request elaborate the point for discussion. Existing mechanism is regulating personnel access at NOC and sensitive places |  |  | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
490 | M1014 | MOM | 2024-02-13 |  |  |  | Security & Regulatory Compliance | Compliance | Incomplete detailing in security report |  | Critical | Open |  |  |  |  | Request elaborate the point for discussion. or any specific criteria need to added or removed |  |  | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
491 | M1015 | MOM | 2024-02-13 |  |  |  | Security & Regulatory Compliance | Regulatory Compliance | Review of SSL for applications |  | Critical | Open |  |  |  |  | All applications owner has been insisted to use SSL for application as per security measures. And it is being ensured that application moving to Producation environment are SSL complied |  |  | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
492 | M1016 | MOM | 2024-02-13 |  |  |  | Security & Regulatory Compliance | Regulatory Compliance | Access control policy |  | Critical | Open |  |  |  |  | ACL policy is defined as per the requested user provided imformation. |  |  | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
493 | M1017 | MOM | 2024-02-13 |  |  |  | Security & Regulatory Compliance | Regulatory Compliance | Concern about remote access management |  | Critical | Open |  |  |  |  | All remote management access is through VPN only . |  |  | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
494 | M1018 | MOM | 2024-02-13 |  |  |  | Security & Regulatory Compliance | Compliance | Inquiry on DMZ details |  | Critical | Open |  |  |  |  | DMZ policy has been shared with team inluitive for verification |  |  | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
495 | M1019 | MOM | 2024-02-13 |  |  |  | Security & Regulatory Compliance | Compliance | Status of leave and potential impacts |  | Critical | Open |  |  |  |  | Point not clear |  |  | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
496 | M102 | MOM | 2023-08-01 |  |  |  | Helpdesk | User Experience | Automated Response for Email Complaints |  | Critical | Open |  |  |  | WIP |  |  |  | Siva Kumar |  | Open | WIP | [9 empty] | MOMHelpdesk | Helpdesk (Contact Center) | OPEN | [6 empty] | 1 | Open | Open
497 | M1020 | MOM | 2024-02-13 |  |  |  | Security & Regulatory Compliance | Compliance | Directive for approval and proper usage of tool services and resources |  | Critical | Open |  |  |  |  | All people has been extended access through RBAC form approved by AD-NoC |  |  | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
498 | M1021 | MOM | 2024-02-13 |  |  |  | Security & Regulatory Compliance | Regulatory Compliance | Requirements for RMC's reporting |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
499 | M1022 | MOM | 2024-02-13 |  |  |  | Security & Regulatory Compliance | Regulatory Compliance | Proposal for security updates bulletin |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
500 | M1023 | MOM | 2024-02-13 |  |  |  | Security & Regulatory Compliance | Regulatory Compliance | Implementation of SOC's best practices |  | Critical | Open |  |  |  |  | SOC's best practices are for SOC includes SIEM,XDR and SOAR integrated Mitre ATT&CKS database. |  |  | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
501 | M1024 | MOM | 2024-02-16 |  |  |  | BSS |  | Ticketing process and tracking |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
502 | M1025 | MOM | 2024-02-16 |  |  |  | BSS |  | Task creation in billing module |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
503 | M1026 | MOM | 2024-02-16 |  |  |  | Helpdesk | Training Module | Recruitment and training of billing officers |  | Critical | open |  |  |  | Closed | 12-Sep-25: its part of Business Helpdesk(T FIber) |  |  | Siva Kumar |  |  | COMPLETED & APPROVED | [9 empty] | MOMHelpdesk | Helpdesk (Contact Center) | CLOSED |  |  |  | 2025-09-24 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\M116,723,1026 |  | 1 | Completed & Approved | Closed after June
504 | M1027 | MOM | 2024-02-16 |  |  |  | BSS |  | Contact synchronization in Lead creation and conversion |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
505 | M1028 | MOM | 2024-02-16 |  |  |  | Security & Regulatory Compliance | Regulatory Compliance | Review of submitted security policy documents |  | Critical | Open |  |  |  |  | Point Duplicated |  |  | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
506 | M1029 | MOM | 2024-02-16 |  |  |  | Security & Regulatory Compliance | Compliance | Asset management and data classification |  | Critical | Open |  |  |  |  | It need DLP solution to tag data as per classification |  |  | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
507 | M103 | MOM | 2023-08-01 |  |  |  | Helpdesk | Resource Related | Helpdesk Manager Availability for 24 Hrs |  | Critical | open |  |  |  | Closed | 24-Sep-25: Existing Lead available during Business Hours, Remaining duration Shift Lead will Manage |  |  | Siva Kumar |  |  | COMPLETED & APPROVED | [9 empty] | MOMHelpdesk | Helpdesk (Contact Center) | CLOSED |  |  |  | 2025-09-24 | Artefacts not Required |  | 1 | Completed & Approved | Closed after June
508 | M1030 | MOM | 2024-02-16 |  |  |  | Security & Regulatory Compliance | Regulatory Compliance | Control of user and visitor access |  | Critical | Open |  |  |  |  | Already physical record is being maintained |  |  | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
509 | M1031 | MOM | 2024-02-16 |  |  |  | Security & Regulatory Compliance | Regulatory Compliance | Concerns about security reporting and compliance |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
510 | M1032 | MOM | 2024-02-16 |  |  |  | Security & Regulatory Compliance | Regulatory Compliance | VPAT implementation and firmware patching |  | Critical | Open |  |  |  |  | VAPT will be conducted by Tfiber . Remediation for sam will be intiated thereafter |  |  | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
511 | M1033 | MOM | 2024-02-16 |  |  |  | Security & Regulatory Compliance | Regulatory Compliance | Compliance to access management policy |  | Critical | Open |  |  |  |  | Access Management policy is as per RBAC approval. |  |  | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
512 | M1034 | MOM | 2024-03-14 |  |  |  | NOC Operationalization | Launch Readiness | Assessing the progress achieved after the Governance meeting held on March 5, 2024. |  | Critical | Open |  |  |  | CLosed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1 | Completed & Approved | Closed after June
513 | M1035 | MOM | 2024-03-14 |  |  |  | BSS |  | Addressing the delays in the End-to-End demonstration of products due to billing/invoice module issues. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
514 | M1036 | MOM | 2024-03-14 |  |  |  | NOC Operationalization | Launch Readiness | Achieving operationalization and readiness of T-NOC. |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMNOC Operationalization | Network | OPEN | [6 empty] | 1 | Open | Open
515 | M1037 | MOM | 2024-03-14 |  |  |  | NOC Operationalization | Launch Readiness | Addressing product gaps and OEM execution delays for the readiness of 5 products. |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMNOC Operationalization | Network | OPEN | [6 empty] | 1 | Open | Open
516 | M1038 | MOM | 2024-03-14 |  |  |  | WFM |  | Ensuring readiness of WFM integration, order fulfillment, service provisioning, and NOC critical points closure. |  | Critical | Open | [7 empty] | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMWFM | Applications/Tools | OPEN | [6 empty] | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
517 | M1039 | MOM | 2024-03-14 |  |  |  | NSO | Service Delivery | Ensuring the service delivery organization is structured for an interim period. |  | Critical | Open | [7 empty] | Jayant Madavi |  | Open | Open | [9 empty] | MOMNSO | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
518 | M104 | MOM | 2023-08-01 |  |  |  | Helpdesk | Handbook & SOPs | Incident categorization to be exhaustive, response timelines to be defined and attached based on incident categorization. |  | Critical | open |  |  |  | Artefacts to be submitted | 24-Sep-25: Updated Document Shared 23-Aug-23 |  |  | Siva Kumar |  |  | COMPLETED & APPROVED | [9 empty] | MOMHelpdesk | Helpdesk (Contact Center) | CLOSED |  |  |  | 2025-09-24 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\M104,105,109,111,113,115,122,123,127,128,130,132,162 |  | 1 | Completed & Approved | Closed after June
519 | M1040 | MOM | 2024-03-14 |  |  |  | Field Related | Network Availibilty | Achieving network availability reports compliance and readiness. |  | Critical | Open |  |  |  |  | closed under O&M scope |  |  | S Kodali |  | Open | Open | [9 empty] | MOMField Related | Field Related issues | OPEN |  |  | O&M Team |  | #N/A |  | 1 | Open | Open
520 | M1041 | MOM | 2024-03-14 |  |  |  | OEM Related | Network Availibilty | Resolving OEM-related gaps and achieving automation roadmap targets. |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMOEM Related | OEM Related Issues | OPEN | [6 empty] | 1 | Open | Open
521 | M1042 | MOM | 2024-03-14 |  |  |  | T&D Environment | Network Availibilty | Establishing a pre-production environment for testing applications before moving to production. |  | NON-Critical | Open |  |  |  |  | [15/09/25] Test Environment is actively used for T&D by Delivery and OEM teams. |  |  | Ravi Kishore |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMT&D Environment | Applications | OPEN |  |  |  |  | #N/A |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
522 | M1043 | MOM | 2024-03-14 |  |  |  | NOC Operationalization | Launch Readiness | L&T to address the delays in demonstrating the End-to-End of the Dark Fiber product. |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMNOC Operationalization | Network | OPEN | [6 empty] | 1 | Open | Open
523 | M1044 | MOM | 2024-03-14 |  |  |  | NOC Operationalization | NOC Readiness | L&T to complete 423 critical points and provide a summary of the status along with action required for balance points. |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1 | Completed & Approved | Closed after June
524 | M1045 | MOM | 2024-03-14 |  |  |  | NOC Operationalization | NOC Readiness | L&T to ensure understanding of the interim T-NOC operationalization plan and work towards readiness. |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMNOC Operationalization | Network | OPEN | [6 empty] | 1 | Open | Open
525 | M1046 | MOM | 2024-03-14 |  |  |  | BSS |  | L&T to be prepared for the next dry run demo and update the order management and quote management statuses. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
526 | M1047 | MOM | 2024-03-14 |  |  |  | NOC Operationalization | NOC Readiness | L&T to provide updates and clarifications on the payment gateway, ticket functionalities, and NSO readiness. |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMNOC Operationalization | Network | OPEN | [6 empty] | 1 | Open | Open
527 | M1048 | MOM | 2024-03-14 |  |  |  | WFM |  | L&T to be prepared for the demonstration of WFM for order fulfillment/service provisioning. |  | Critical | Open | [7 empty] | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMWFM | Applications/Tools | OPEN | [6 empty] | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
528 | M1049 | MOM | 2024-03-14 |  |  |  | T&D Environment |  | L&T to provide details on modules working in pre-production and production environments and seek approvals for transitions. |  | NON-Critical | Open |  |  |  |  | [15/09/25] Test Environment is actively used for T&D by Delivery and OEM teams. |  |  | Ravi Kishore |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMT&D Environment | Applications | OPEN |  |  |  |  | #N/A |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
529 | M105 | MOM | 2023-08-01 |  |  |  | Helpdesk | Handbook & SOPs | Clarity required in the definition of roles and responsibilities of L1 and L2 agents, incident categorization to be handled at L1 level, type of queries, resolution time, escalation matrix to be better defined. |  | Critical | open |  |  |  | Artefacts to be submitted | 24-Sep-25: Updated Document Shared 23-Aug-23 |  |  | Siva Kumar |  |  | COMPLETED & APPROVED | [9 empty] | MOMHelpdesk | Helpdesk (Contact Center) | CLOSED |  |  |  | 2025-09-24 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\M104,105,109,111,113,115,122,123,127,128,130,132,162 |  | 1 | Completed & Approved | Closed after June
530 | M1050 | MOM | 2024-03-14 |  |  |  | NOC Operationalization | Launch Readiness | The demonstration of the End-to-End of one product by 18th March 2024. |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMNOC Operationalization | Network | OPEN | [6 empty] | 1 | Open | Open
531 | M1051 | MOM | 2024-03-14 |  |  |  | NOC Operationalization | Launch Readiness | T0 phase points to be completed by March 2024. |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1 | Completed & Approved | Closed after June
532 | M1052 | MOM | 2024-03-14 |  |  |  | Field Related | District Completion Target | Complete E2E AT Certificate of Rangareddy, Mahbubnagar, Vikarabad & Narayanpet districts by 7th April 2024. |  | NON-Critical | Open | [7 empty] | S Kodali |  | Open | Open | [9 empty] | MOMField Related | Field Related issues | OPEN |  |  | Project Team |  | #N/A |  | 1 | Open | Open
533 | M1053 | MOM | 2024-03-14 |  |  |  | T&D Environment |  | Provide a summary of applications in pre-production & production environments by 16th March 2024. |  | NON-Critical | Open |  |  |  |  | [15/09/25] Test Environment is actively used for T&D by Delivery and OEM teams. NOC submission provided in Tfiber has the T&D application from Oct-Mar2025 |  |  | Ravi Kishore |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMT&D Environment | Applications | OPEN |  |  |  |  | #N/A |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
534 | M1054 | MOM | 2024-03-14 |  |  |  | OEM Related |  | Provide updates on the pre-production environment, OEM gaps, and integration of systems and applications by 16th March 2024. |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMOEM Related | OEM Related Issues | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1 | Completed & Approved | Closed after June
535 | M1055 | MOM | 2024-03-14 |  |  |  | NOC Operationalization | Launch Readiness | Ensure all 5 products are ready by April 2024. |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMNOC Operationalization | Network | OPEN | [6 empty] | 1 | Open | Open
536 | M1056 | MOM | 2024-03-14 |  |  |  | Field Related | Network Availibilty | Achieve 97% Network availability in Gadwal & Wanaparthy from 1st April 2024. |  | NON-Critical | Open |  |  |  |  | closed under O&M scope |  |  | S Kodali |  | Open | Open | [9 empty] | MOMField Related | Field Related issues | OPEN |  |  | O&M Team |  | Artefacts to be uploaded |  | 1 | Open | Open
537 | M1057 | MOM | 2024-03-14 |  |  |  | Field Related | Network Availibilty | Achieve 90% Network availability in Mahbubnagar and Rangareddy for April 2024. |  | NON-Critical | Open |  |  |  |  | closed under O&M scope |  |  | S Kodali |  | Open | Open | [9 empty] | MOMField Related | Field Related issues | OPEN |  |  | O&M Team |  | Artefacts to be uploaded |  | 1 | Open | Open
538 | M1058 | MOM | 2024-03-14 |  |  |  | NOC Operationalization | Network Availibilty | All critical points for T-NOC operationalization to be completed by 30th March 2024. |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMNOC Operationalization | Network | OPEN | [6 empty] | 1 | Open | Open
539 | M1059 | MOM | 2024-06-11 |  |  |  | NOC Operationalization |  | Interim NOC O&M: L&T to complete pending tasks and seek T-Fiber approval for the start of Interim NOC O&M. |  | Critical | Open |  |  |  | NON Critical to be reviewd later | 22-Sep-25: SOPs, Handbook, T0-T6 and interim NOC Plan submitted to the T fiber on XX-XX-XXXX. T Fiber team has shared 65 queries on SOP and Hanbooks. And these 65 points have been incorporated as a different points in this master tracker.(Sub domain as Handbook and SOP). Pending tasks(44 SOP, Opertaions Handbook, Full NOC Readiness plan, NOC all KPI) completed and Interim NOC plan has been Submitted. Artefacts to be uploaded in NAS Interim NOC had started in OCt24 | L&T | Sivaprasad | Sivaprasad |  | Open | Open | [9 empty] | MOMNOC Operationalization | Network | OPEN | [6 empty] | 1 | Open | Open
540 | M106 | MOM | 2023-08-01 |  |  |  | Helpdesk | Mini Helpdesk | Mechanism needed between T-NOC Helpdesk and District Collector offices for complaints that may be made directly to the District Collector office. Provision for a mini-Helpdesk node at each district, with a facility/hotline for an authorized person to log a call/complaint on behalf of the District Collector Office, similar to the direct walk-in channel for customer complaints at T-NOC. |  | NON-Critical | open |  |  |  | Closed | 24-Sep-25: Artefacts to be uploaded |  |  | Siva Kumar |  |  | COMPLETED & APPROVED | [9 empty] | MOMHelpdesk | Helpdesk (Contact Center) | CLOSED |  |  |  | 2025-09-24 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\M106 |  | 1 | Completed & Approved | Closed after June
541 | M1060 | MOM | 2024-06-11 |  |  |  | NOC Operationalization |  | NOC Go-Live: L&T requested recognition of NOC Go-Live status despite manual provisioning; T-Fiber requires full automation for transition from interim to Full NOC. |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMNOC Operationalization | Network | OPEN | [6 empty] | 1 | Open | Open
542 | M1061 | MOM | 2024-06-11 |  |  |  | NOC Operationalization |  | Functional Gaps in NOC Elements: L&T to meet with OEMs to identify scope gaps and evaluate alternate BSS solutions, presenting recommendations within a week. |  | Critical | Open |  |  |  | Closed, Artefacts to be uploaded | 23-Sep-25: Approved Artefacts to be Submitted | L&T | Sivaprasad | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  |  | Artefacts Need to upload |  | 1 | Completed & Approved | Closed after June
543 | M1062 | MOM | 2024-06-11 |  |  |  | NOC Operationalization |  | Time Delays: L&T to comply with RFP and submit timelines for Full NOC readiness. |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMNOC Operationalization | Network | OPEN | [6 empty] | 1 | Open | Open
544 | M1063 | MOM | 2024-06-11 |  |  |  | NOC Operationalization |  | WFM Tool Implementation: L&T to operationalize the WFM tool for Package A within one week. |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMNOC Operationalization | Network | OPEN | [6 empty] | 1 | Open | Open
545 | M1064 | MOM | 2024-06-11 |  |  |  | NOC Operationalization |  | MB and LOA Amendment: L&T to complete MB duct reconciliation; T-Fiber to review data submitted by L&T. |  | Critical | Open |  |  |  | Will be discussed later | 23-Sep-25: NON Critical to be reviewd later | L&T | Sivaprasad | Sivaprasad |  | Open | Open | [9 empty] | MOMNOC Operationalization | Network | OPEN | [6 empty] | 1 | Open | Open
546 | M1065 | MOM | 2024-06-11 |  |  |  | NOC Operationalization |  | Chemical Storage in GP PoPs: L&T to create guidelines for panchayat chemical storage handling. |  | Critical | Open |  |  |  | Will be discussed later | 23-Sep-25: NON Critical to be reviewd later | L&T | Sivaprasad | Sivaprasad |  | Open | Open | [9 empty] | MOMNOC Operationalization | Network | OPEN | [6 empty] | 1 | Open | Open
547 | M1066 | MOM | 2024-06-11 |  |  |  | NOC Operationalization |  | PoP Relocation: L&T to re-offer rates for PoP relocation. |  | Critical | Open |  |  |  | Will be discussed later | 23-Sep-25: NON Critical to be reviewd later | L&T | Sivaprasad | Sivaprasad |  | Open | Open | [9 empty] | MOMNOC Operationalization | Network | OPEN | [6 empty] | 1 | Open | Open
548 | M1067 | MOM | 2024-06-11 |  |  |  | NOC Operationalization |  | Centralized Billing for EB: L&T to submit a proposal for centralized billing. |  | Critical | Open |  |  |  | Will be discussed later | 23-Sep-25: NON Critical to be reviewd later | L&T | Sivaprasad | Sivaprasad |  | Open | Open | [9 empty] | MOMNOC Operationalization | Network | OPEN | [6 empty] | 1 | Open | Open
549 | M1068 | MOM | 2024-06-11 |  |  |  | NOC Operationalization |  | L&T Cash Flow Pressures: L&T to submit invoices as per RFP compliance for payment release. |  | Critical | Open |  |  |  | Will be discussed later | 23-Sep-25: NON Critical to be reviewd later | L&T | Sivaprasad | Sivaprasad |  | Open | Open | [9 empty] | MOMNOC Operationalization | Network | OPEN | [6 empty] | 1 | Open | Open
550 | M1069 | MOM | 2024-06-11 |  |  |  | NOC Operationalization |  | GST Payments: T-Fiber to explore options within regulatory norms to resolve GST payment issues. |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMNOC Operationalization | Network | OPEN | [6 empty] | 1 | Open | Open
551 | M107 | MOM | 2023-08-01 |  |  |  | Helpdesk | Handbook & SOPs | Clarification needed on whether general enquiries are treated as incidents. |  | NON-Critical | open |  |  |  | Artefacts to be submitted | 25-Sep-25 Ans: All business queries will created as lead in BSS |  |  | Siva Kumar |  |  | COMPLETED & APPROVED | [9 empty] | MOMHelpdesk | Helpdesk (Contact Center) | CLOSED |  |  |  | 2025-09-24 | Artefacts not Required |  | 1 | Completed & Approved | Closed after June
552 | M1070 | MOM | 2024-06-11 |  |  |  | NOC Operationalization |  | Interim O&M Payment: L&T to submit supporting documents for payment against Interim O&M. |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1 | Completed & Approved | Closed after June
553 | M1071 | MOM | 2024-06-11 |  |  |  | NOC Operationalization |  | Full NOC Readiness Plan: L&T to submit a comprehensive plan for Full NOC readiness. |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1 | Completed & Approved | Closed after June
554 | M1072 | MOM | 2024-06-11 |  |  |  | NOC Operationalization |  | GI Connectivity: L&T to address slow progress and start NoFN connectivity. |  | Critical | Open |  |  |  | Will be discussed later | 23-Sep-25: NON Critical to be reviewd later | L&T | Sivaprasad | Sivaprasad |  | Open | Open | [9 empty] | MOMNOC Operationalization | Network | OPEN | [6 empty] | 1 | Open | Open
555 | M1073 | MOM | 2024-06-11 |  |  |  | Field Related |  | AT Completion: L&T to complete AT of 10 districts by July 2024, accounting for monsoon season. |  | Critical | Open | [7 empty] | S Kodali |  | Open | Open | [9 empty] | MOMField Related | Field Related issues | OPEN |  |  | Project Team |  | #N/A |  | 1 | Open | Open
556 | M1074 | MOM | 2024-06-11 |  |  |  | Field Related |  | RV – GIs: L&T to identify new partners to connect Rhythu Vedikas. |  | Critical | Open | [7 empty] | S Kodali |  | Open | Open | [9 empty] | MOMField Related | Field Related issues | OPEN |  |  | Project Team |  | #N/A |  | 1 | Open | Open
557 | M1075 | MOM | 2024-06-11 |  |  |  | NOC Operationalization |  | SLA Achievement: L&T to improve O&M availability to meet the target of 97%. |  | Critical | Open |  |  |  |  | 22-Sep-25: MSIs Field team is working on it. Multiple dependencies like fiber rerouting, equipment faults, AT WIP for balance nodes, etc. NOC to support in terms of TT, escalations, reports. |  |  | Ahmad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-22 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\TNOC\M1075 |  | 1 | Completed & Approved | Closed after June
558 | M1076 | MOM | 2024-06-11 |  |  |  | NOC Operationalization |  | The urgency for L&T to demonstrate agreed SOPs are in place for Interim NOC O&M and to submit sample reports. |  | Critical | Open |  |  |  | Artefacts to be submitted | 24-Sep-25: 44 agreed SOP doc submitted and signed off. Artefacts will be uploaded today in NAS |  |  | Siva Kumar |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-24 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\M1076 |  | 1 | Completed & Approved | Closed after June
559 | M1077 | MOM | 2024-06-11 |  |  |  | NOC Operationalization |  | The need for L&T to address the slow progress in GI connectivity and to start NoFN connectivity. |  | Critical | Open |  |  |  | Will be discussed later | 23-Sep-25: NON Critical to be reviewd later | L&T | Sivaprasad | Sivaprasad |  | Open | Open | [9 empty] | MOMNOC Operationalization | Network | OPEN | [6 empty] | 1 | Open | Open
560 | M1078 | MOM | 2024-06-11 |  |  |  | Field Related |  | The expectation for L&T to complete AT for multiple districts by July 2024 and to increase resources to meet targets. |  | Critical | Open | [7 empty] | S Kodali |  | Open | Open | [9 empty] | MOMField Related | Field Related issues | OPEN |  |  | Project Team |  | #N/A |  | 1 | Open | Open
561 | M1079 | MOM | 2024-06-11 |  |  |  | NOC Operationalization |  | The requirement for L&T to resolve issues with OEMs and to consider ready-made BSS solutions to mitigate risks. |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1 | Completed & Approved | Closed after June
562 | M108 | MOM | 2023-08-01 |  |  |  | Helpdesk | Handbook & SOPs | Clarification needed on whether general enquiries are treated as incidents. |  | NON-Critical | open |  |  |  | Artefacts to be submitted | 25-Sep-25 Ans: All business queries will created as lead in BSS |  |  | Siva Kumar |  |  | COMPLETED & APPROVED | [9 empty] | MOMHelpdesk | Helpdesk (Contact Center) | CLOSED |  |  |  | 2025-09-24 | Artefacts not Required |  | 1 | Completed & Approved | Closed after June
563 | M1080 | MOM | 2024-06-11 |  |  |  | NOC Operationalization |  | Asset Management Policy to be drafted and submitted by L&T before 29th June 2024. |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMNOC Operationalization | Network | OPEN | [6 empty] | 1 | Open | Open
564 | M1081 | MOM | 2024-06-11 |  |  |  | Security & Regulatory Compliance | NOC Operationalization | Security Audit of ILL (10G) commissioning to be completed urgently and communicated to DOT prior to service launch. |  | Critical | Open |  |  |  |  | No Provisioning for ILL security. ISP audit will be relevant in this regard. |  |  | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
565 | M1082 | MOM | 2024-06-11 |  |  |  | NOC Operationalization |  | L&T to set up a dedicated security team for the project to resolve all pending security actions. |  | Critical | Open |  |  |  | NON Critical to be reviewd later | 23-Sep-25: NON Critical to be reviewd later | L&T | Sivaprasad | Sivaprasad |  | Open | Open | [9 empty] | MOMNOC Operationalization | Network | OPEN | [6 empty] | 1 | Open | Open
566 | M1083 | MOM | 2024-06-11 |  |  |  | NOC Operationalization |  | L&T to finalize the appointment of a Security SME, with Vikram Khatri being considered for the role. |  | Critical | Open |  |  |  | NON Critical to be reviewd later | 23-Sep-25: NON Critical to be reviewd later | L&T | Sivaprasad | Sivaprasad |  | Open | Open | [9 empty] | MOMNOC Operationalization | Network | OPEN | [6 empty] | 1 | Open | Open
567 | M1084 | MOM | 2024-06-11 |  |  |  | NOC Operationalization |  | L&T to send pre-read material at least one day before the next meeting. |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1 | Completed & Approved | Closed after June
568 | M1085 | MOM | 2024-06-11 |  |  |  | NOC Operationalization |  | Mr. Rajesh Thangavelu, Security in-charge, was absent from the meeting despite specific requests for his presence. |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1 | Completed & Approved | Closed after June
569 | M1086 | MOM | 2024-06-11 |  |  |  | NOC Operationalization |  | No action items from earlier Minutes of Meetings (MOMs) were presented in the RMC Meeting. |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1 | Completed & Approved | Closed after June
570 | M1087 | MOM | 2024-06-11 |  |  |  | NOC Operationalization |  | No formal intimation regarding the exit of the existing Security SME (Mr. Gandhi) by L&T. |  | Critical | Open |  |  |  | NON Critical to be reviewd later | 23-Sep-25: NON Critical to be reviewd later | L&T | Sivaprasad | Sivaprasad |  | Open | Open | [9 empty] | MOMNOC Operationalization | Network | OPEN | [6 empty] | 1 | Open | Open
571 | M1088 | MOM | 2024-06-11 |  |  |  | Security & Regulatory Compliance | NOC Operationalization | Cisco firewall and ISE integration is still pending despite being from the same OEM. |  | Critical | Open |  |  |  |  | Firewall is being integrated with ISE. |  |  | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
572 | M1089 | MOM | 2024-06-11 |  |  |  | NOC Operationalization |  | Address the absence of the central Security resource in future meetings. |  | Critical | Open |  |  |  | NON Critical to be reviewd later | 23-Sep-25: NON Critical to be reviewd later | L&T | Sivaprasad | Sivaprasad |  | Open | Open | [9 empty] | MOMNOC Operationalization | Network | OPEN | [6 empty] | 1 | Open | Open
573 | M109 | MOM | 2023-08-01 |  |  |  | Helpdesk | Handbook & SOPs | Detailed documentation needed on critical, major, minor escalations, and their related thresholds. |  | NON-Critical | open |  |  |  | Closed | 24-Sep-25: Updated Document Shared 23-Aug-23 |  |  | Siva Kumar |  |  | COMPLETED & APPROVED | [9 empty] | MOMHelpdesk | Helpdesk (Contact Center) | CLOSED |  |  |  | 2025-09-24 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\M104,105,109,111,113,115,122,123,127,128,130,132,162 |  | 1 | Completed & Approved | Closed after June
574 | M1090 | MOM | 2024-06-11 |  |  |  | NOC Operationalization |  | Provide closure status of all old action points in a single sheet before the next meeting. |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1 | Completed & Approved | Closed after June
575 | M1091 | MOM | 2024-06-11 |  |  |  | Security & Regulatory Compliance | NOC Operationalization | Complete the scope for Vulnerability Assessment and Penetration Testing as defined and submit the results. |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
576 | M1092 | MOM | 2024-06-11 |  |  |  | Security & Regulatory Compliance | NOC Operationalization | Address the issue of the Cisco firewall and ISE not being integrated. |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
577 | M1093 | MOM | 2024-06-14 |  |  |  | OEM Related |  | All API Documents by HP to be submitted by L&T as soon as possible. |  | Critical | Open |  |  |  | Closed, Artefacts to be uploaded | 23-Sep-25: Approved Artefacts to be Submitted | L&T | Sivaprasad | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMOEM Related | OEM Related Issues | CLOSED |  |  |  |  | Artefacts Need to upload |  | 1 | Completed & Approved | Closed after June
578 | M1094 | MOM | 2024-06-14 |  |  |  | OEM Related |  | BBNL integration solution to be provided by the end of June 2024, with testing beginning from 24th June 2024. |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMOEM Related | OEM Related Issues | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1 | Completed & Approved | Closed after June
579 | M1095 | MOM | 2024-06-14 |  |  |  | OEM Related |  | Alarm enrichment with custom attributes and other new SOW items are in progress, with some attributes completed and others recently given. |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMOEM Related | OEM Related Issues | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1 | Completed & Approved | Closed after June
580 | M1096 | MOM | 2024-06-14 |  |  |  | OEM Related |  | L&T to map documents as per RFP requirements and identify gaps for new SOW internally to their OEMs. |  | Critical | Open |  |  |  | Closed, Artefacts to be uploaded | 23-Sep-25: Approved Artefacts to be Submitted | L&T | Sivaprasad | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMOEM Related | OEM Related Issues | CLOSED |  |  |  |  | Artefacts Need to upload |  | 1 | Completed & Approved | Closed after June
581 | M1097 | MOM | 2024-06-14 |  |  |  | OEM Related |  | HPE to provide Admin user privilege to L&T for filtering after a professional agreement is signed. |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMOEM Related | OEM Related Issues | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1 | Completed & Approved | Closed after June
582 | M1098 | MOM | 2024-06-14 |  |  |  | OEM Related |  | OpenText to share all required documents by 24th June 2024. |  | Critical | Open |  |  |  | Closed, Artefacts to be uploaded | 23-Sep-25: Approved Artefacts to be Submitted | L&T | Sivaprasad | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMOEM Related | OEM Related Issues | CLOSED |  |  |  |  | Artefacts Need to upload |  | 1 | Completed & Approved | Closed after June
583 | M1099 | MOM | 2024-06-14 |  |  |  | OEM Related |  | L&T to demonstrate the correlation engine and event alarm management for all domains. |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMOEM Related | OEM Related Issues | OPEN | [6 empty] | 1 | Open | Open
584 | M11 | MOM | 2023-04-03 |  |  |  | NSO | Functional AT Plan | Use-Cases Testing under NSO |  | Critical | Open |  | OSS Dashboards | [5 empty] | Jayant Madavi |  | Open | Open | [9 empty] | MOMNSO | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
585 | M110 | MOM | 2023-08-01 |  |  |  | Helpdesk | Handbook & SOPs | Feedback Collection Review Mechanism |  | NON-Critical | Open |  |  |  | WIP |  |  |  | Siva Kumar |  | Open | WIP | [9 empty] | MOMHelpdesk | Helpdesk (Contact Center) | OPEN | [6 empty] | 1 | Open | Open
586 | M1100 | MOM | 2024-06-14 |  |  |  | OEM Related |  | External API details provided by L&T are currently not functioning.(BBNL Integration) |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMOEM Related | OEM Related Issues | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1 | Completed & Approved | Closed after June
587 | M1101 | MOM | 2024-06-14 |  |  |  | OEM Related |  | API extension for Alarm Enrichment is not functioning, and inventory API is operational. |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMOEM Related | OEM Related Issues | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1 | Completed & Approved | Closed after June
588 | M1102 | MOM | 2024-06-14 |  |  |  | OEM Related |  | Service impact analysis is not available, and cross-domain RCA is not provided. |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMOEM Related | OEM Related Issues | OPEN | [6 empty] | 1 | Open | Open
589 | M1103 | MOM | 2024-06-14 |  |  |  | OEM Related |  | Alarm forwarding API is not working, and there is a need for service impact and network impact information. |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMOEM Related | OEM Related Issues | OPEN | [6 empty] | 1 | Open | Open
590 | M1104 | MOM | 2024-06-14 |  |  |  | OEM Related |  | There is no topology and zonal view of IPMPLS, and some performance management points are pending validation. |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMOEM Related | OEM Related Issues | OPEN | [6 empty] | 1 | Open | Open
591 | M1105 | MOM | 2024-06-14 |  |  |  | OEM Related |  | L&T to submit all API documents, not just BBNL, and involve T-Fiber for review. |  | Critical | Open |  |  |  | Closed, Artefacts to be uploaded | 23-Sep-25: Approved Artefacts to be Submitted | L&T | Sivaprasad | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMOEM Related | OEM Related Issues | CLOSED |  |  |  |  | Artefacts Need to upload |  | 1 | Completed & Approved | Closed after June
592 | M1106 | MOM | 2024-06-14 |  |  |  | OEM Related |  | L&T to demonstrate functionality and ensure alarm management is in place with the necessary enrichments. |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMOEM Related | OEM Related Issues | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1 | Completed & Approved | Closed after June
593 | M1107 | MOM | 2024-06-14 |  |  |  | OEM Related |  | OpenText to demonstrate the NNMi KPI dashboard and complete the end-to-end demo for threshold values. |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMOEM Related | OEM Related Issues | OPEN | [6 empty] | 1 | Open | Open
594 | M1108 | MOM | 2024-06-14 |  |  |  | OEM Related |  | L&T to define the scope with NSO for the Service Inventory module and ensure it is part of the deliverables. |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMOEM Related | OEM Related Issues | OPEN | [6 empty] | 1 | Open | Open
595 | M1109 | MOM | 2024-06-14 |  |  |  | OEM Related |  | HPE to revisit all alarm scenarios, involve T-Fiber for review, and bring in industry best practices. |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMOEM Related | OEM Related Issues | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1 | Completed & Approved | Closed after June
596 | M111 | MOM | 2023-08-01 |  |  |  | Helpdesk | Handbook & SOPs | Documentation required stating that L2 agents shall make outbound calls to customers. |  | NON-Critical | open |  |  |  | Closed | 24-Sep-25: Updated Document Shared 23-Aug-23 |  |  | Siva Kumar |  |  | COMPLETED & APPROVED | [9 empty] | MOMHelpdesk | Helpdesk (Contact Center) | CLOSED |  |  |  | 2025-09-24 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\M104,105,109,111,113,115,122,123,127,128,130,132,162 |  | 1 | Completed & Approved | Closed after June
597 | M1110 | MOM | 2024-06-14 |  |  |  | OEM Related |  | HPE to review the RFP, compliance documents, solution documents, and HLD document, and offer the system for AT if everything is in compliance. |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMOEM Related | OEM Related Issues | OPEN | [6 empty] | 1 | Open | Open
598 | M1111 | MOM | 2024-06-14 |  |  |  | OEM Related |  | L&T to provide API library access and complete API documents of OpenText to T-Fiber as soon as possible, with follow-up by Director-NOC, T-Fiber. |  | Critical | Open |  |  |  | Closed, Artefacts to be uploaded | 23-Sep-25: Approved Artefacts to be Submitted | L&T | Sivaprasad | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMOEM Related | OEM Related Issues | CLOSED |  |  |  |  | Artefacts Need to upload |  | 1 | Completed & Approved | Closed after June
599 | M1112 | MOM | 2024-06-14 |  |  |  | OEM Related |  | BBNL integration task completion by 30th June 2024, with day-to-day progress monitoring by Director-NOC, T-Fiber. |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMOEM Related | OEM Related Issues | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1 | Completed & Approved | Closed after June
600 | M1113 | MOM | 2024-06-14 |  |  |  | OEM Related |  | OpenText to provide a SMAX proposal with a detailed presentation for potential replacement analysis. |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMOEM Related | OEM Related Issues | OPEN | [6 empty] | 1 | Open | Open
601 | M1114 | MOM | 2024-06-14 |  |  |  | OEM Related |  | L&T to arrange a demo for Server Performance Monitoring and submit all KPI details. |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMOEM Related | OEM Related Issues | OPEN | [6 empty] | 1 | Open | Open
602 | M1115 | MOM | 2024-06-14 |  |  |  | OEM Related |  | OpenText to define custom reports for centralized and customizable service level reporting. |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMOEM Related | OEM Related Issues | OPEN | [6 empty] | 1 | Open | Open
603 | M1116 | MOM | 2024-06-14 |  |  |  | OEM Related |  | OpenText to provide a 7-year direct support commitment and an approval system via email & mobile app. |  | Critical | Open |  |  |  | Closed, Artefacts to be uploaded | 23-Sep-25: Approved Artefacts to be Submitted | L&T | Sivaprasad | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMOEM Related | OEM Related Issues | CLOSED |  |  |  |  | Artefacts Need to upload |  | 1 | Completed & Approved | Closed after June
604 | M1117 | MOM | 2024-06-14 |  |  |  | OEM Related |  | OpenText to provide a list of device models supported for SNMP polling. |  | Critical | Open |  |  |  | Closed, Artefacts to be uploaded | 23-Sep-25: Approved Artefacts to be Submitted | L&T | Sivaprasad | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMOEM Related | OEM Related Issues | CLOSED |  |  |  |  | Artefacts Need to upload |  | 1 | Completed & Approved | Closed after June
605 | M1118 | MOM | 2024-06-14 |  |  |  | OEM Related |  | Full API library of vTemIP is unavailable, affecting self-testing of modules. |  | Critical | Open |  |  |  | Closed, Artefacts to be uploaded | 23-Sep-25: Approved Artefacts to be Submitted | L&T | Sivaprasad | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMOEM Related | OEM Related Issues | CLOSED |  |  |  |  | Artefacts Need to upload |  | 1 | Completed & Approved | Closed after June
606 | M1119 | MOM | 2024-06-14 |  |  |  | OEM Related |  | Product support status from OpenText and incident management issues, including ticket grouping and content filtering. |  | Critical | Open |  |  |  | Closed, Artefacts to be uploaded | 23-Sep-25: Approved Artefacts to be Submitted | L&T | Sivaprasad | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMOEM Related | OEM Related Issues | CLOSED |  |  |  |  | Artefacts Need to upload |  | 1 | Completed & Approved | Closed after June
607 | M112 | MOM | 2023-08-01 |  |  |  | Helpdesk | Handbook & SOPs | Inquiry about how the Helpdesk addresses cases where the number of the person calling differs from the number registered in the BSS database. |  | NON-Critical | open |  |  |  | WIP | 11-Sep-25: BSS Integration |  |  | Siva Kumar |  | Open | WIP | [9 empty] | MOMHelpdesk | Helpdesk (Contact Center) | OPEN | [6 empty] | 1 | Open | Open
608 | M1120 | MOM | 2024-06-14 |  |  |  | OEM Related |  | Unavailability of a consolidated dashboard and cross-domain topology visibility. |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMOEM Related | OEM Related Issues | OPEN | [6 empty] | 1 | Open | Open
609 | M1121 | MOM | 2024-06-14 |  |  |  | OEM Related |  | Instability of OBR and NNMi causing issues in IT event management. |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMOEM Related | OEM Related Issues | OPEN | [6 empty] | 1 | Open | Open
610 | M1122 | MOM | 2024-06-14 |  |  |  | OEM Related |  | Concerns about the pending Network Automation and the process for implementing upgrades. |  | Critical | Open |  |  |  | WIP | DUPLICATE POINT (NOC624) | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMOEM Related | OEM Related Issues | OPEN | [6 empty] | 1 | Open | Open
611 | M1123 | MOM | 2024-06-14 |  |  |  | OEM Related |  | OpenText to check and revert with timelines for API library access. |  | Critical | Open |  |  |  | Closed, Artefacts to be uploaded | 23-Sep-25: Approved Artefacts to be Submitted | L&T | Sivaprasad | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMOEM Related | OEM Related Issues | CLOSED |  |  |  |  | Artefacts Need to upload |  | 1 | Completed & Approved | Closed after June
612 | M1124 | MOM | 2024-06-14 |  |  |  | OEM Related |  | OpenText to revisit the issue of limited ticket visibility in the UI and accommodate more data. |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMOEM Related | OEM Related Issues | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1 | Completed & Approved | Closed after June
613 | M1125 | MOM | 2024-06-14 |  |  |  | OEM Related |  | L&T to establish a product service contract and ensure the operational team is fully engaged. |  | Critical | Open |  |  |  | Closed, Artefacts to be uploaded | 23-Sep-25: Approved Artefacts to be Submitted | L&T | Sivaprasad | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMOEM Related | OEM Related Issues | CLOSED |  |  |  |  | Artefacts Need to upload |  | 1 | Completed & Approved | Closed after June
614 | M1126 | MOM | 2024-06-14 |  |  |  | OEM Related |  | OpenText to provide a solution for Service Level Reporting & availability and to demonstrate WAN-LAN connectivity mapping. |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMOEM Related | OEM Related Issues | OPEN | [6 empty] | 1 | Open | Open
615 | M1127 | MOM | 2024-06-14 |  |  |  | OEM Related |  | L&T to discuss with OpenText about Network Automation for Deployment and configuration check module License. |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMOEM Related | OEM Related Issues | OPEN | [6 empty] | 1 | Open | Open
616 | M1128 | MOM | 2024-06-14 |  |  |  | OEM Related |  | OpenText to deploy a dedicated resource in Hyderabad to close all open points and establish a standard test bed environment. |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMOEM Related | OEM Related Issues | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1 | Completed & Approved | Closed after June
617 | M1129 | MOM | 2024-06-14 |  |  |  | OEM Related |  | All demonstrations should be conducted in the presence of T-Fiber representatives, and product compliance with ITIL Gold level certification needs to be rechecked. |  | Critical | Open |  |  |  | Closed, Artefacts to be uploaded | 23-Sep-25: Approved Artefacts to be Submitted | L&T | Sivaprasad | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMOEM Related | OEM Related Issues | CLOSED |  |  |  |  | Artefacts Need to upload |  | 1 | Completed & Approved | Closed after June
618 | M113 | MOM | 2023-08-01 |  |  |  | Helpdesk | Handbook & SOPs | Clarification needed on the sphere of activity between NOC Technical administrators and Helpdesk agents. |  | NON-Critical | open |  |  |  | Artefacts to be submitted | 24-Sep-25: Updated Document Shared 23-Aug-23 |  |  | Siva Kumar |  |  | COMPLETED & APPROVED | [9 empty] | MOMHelpdesk | Helpdesk (Contact Center) | CLOSED |  |  |  | 2025-09-24 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\M104,105,109,111,113,115,122,123,127,128,130,132,162 |  | 1 | Completed & Approved | Closed after June
619 | M1130 | MOM | 2024-06-28 |  |  |  | Security & Regulatory Compliance | Compliance | L&T Security Teams & Technical Head to resolve login issues for Pkg B & C teams by the end of the next week. |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
620 | M1131 | MOM | 2024-06-28 |  |  |  | OSS | Product | L&T OSS SME to provide updates on the PMS issue with the secondary database after consultation with the OEM. |  | Critical | Open | [7 empty] | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMOSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  | #N/A |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
621 | M1132 | MOM | 2024-06-28 |  |  |  | Security & Regulatory Compliance | Compliance | L&T to work with the vendor to define a solution for integrating AD with Alepo AAA. |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
622 | M1133 | MOM | 2024-06-28 |  |  |  | Security & Regulatory Compliance | Compliance | GPON SME to discuss with OEM and understand the reporting for categorizing users in EMS & AMS systems. |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
623 | M1134 | MOM | 2024-06-28 |  |  |  | Security & Regulatory Compliance | Compliance | L&T Security team & DC infra team to complete the RBAC list updates with domain-wise user information. |  | Critical | Closed | [7 empty] | Sarmendra |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | Artefacts to be Submitted |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
624 | M1135 | MOM | 2024-06-28 |  |  |  | Security & Regulatory Compliance | Compliance | AD not integrating with Alepo AAA. |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
625 | M1136 | MOM | 2024-06-28 |  |  |  | Security & Regulatory Compliance | Compliance | Local users not removed in EMS, AMS, etc., and not verified through AD/Alepo AAA. |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
626 | M1137 | MOM | 2024-06-28 |  |  |  | Security & Regulatory Compliance | Compliance | Cisco EPNM has two separate profiles for a single user after login through TACACS, which needs resolution. |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
627 | M1138 | MOM | 2024-06-28 |  |  |  | Security & Regulatory Compliance | Compliance | L&T does not have HPE Admin access and is missing some OT systems in OSS. |  | Critical | Open | [7 empty] | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN | COMPLETED | 0 |  |  | #N/A |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
628 | M1139 | MOM | 2024-06-28 |  |  |  | Security & Regulatory Compliance | Compliance | ISE HA DC to DR not working due to pending ISE software upgrade. |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
629 | M114 | MOM | 2023-08-01 |  |  |  | Helpdesk | Training | Training for Helpdesk Users and Managers |  | Critical | open |  |  |  | Closed | 24-Sep-25: Artefacts to be uploaded |  |  | Siva Kumar |  |  | COMPLETED & APPROVED | [9 empty] | MOMHelpdesk | Helpdesk (Contact Center) | CLOSED |  |  |  | 2025-09-24 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\M114,722,134 |  | 1 | Completed & Approved | Closed after June
630 | M1140 | MOM | 2024-06-28 |  |  |  | Security & Regulatory Compliance | Compliance | L&T to share user details with Ravi for reconciliation in RBAC worksheets. |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
631 | M1141 | MOM | 2024-06-28 |  |  |  | Security & Regulatory Compliance | Compliance | L&T to ensure all users are domain verified through AD/Alepo AAA and remove local users. |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
632 | M1142 | MOM | 2024-06-28 |  |  |  | Security & Regulatory Compliance | Compliance | L&T to follow a consistent format for user IDs across all domains. |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
633 | M1143 | MOM | 2024-06-28 |  |  |  | Security & Regulatory Compliance | Compliance | L&T OSS SME to initiate communication with OEMs for admin user control access. |  | Critical | Open | [7 empty] | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN | COMPLETED | 0 |  |  | #N/A |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
634 | M1144 | MOM | 2024-06-28 |  |  |  | Security & Regulatory Compliance | Compliance | L&T to prepare a checklist, test user access domain-wise, and create users based on necessary approvals. |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
635 | M1145 | MOM | 2024-06-28 |  |  |  | Security & Regulatory Compliance | Compliance | L&T to rebuild CSM with necessary resources (storage) as a long-term solution. |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
636 | M1146 | MOM | 2024-06-28 |  |  |  | Security & Regulatory Compliance | Compliance | Mark Mr. Sandeep in any escalation emails for pending issues with L&T. |  | Critical | Open |  |  |  |  | Sandeep is marked in mails |  |  | Sarmendra |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | Artefacts to be Submitted |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
637 | M1147 | MOM | 2024-07-12 |  |  |  | OEM Related |  | Cisco confirmed that Airtel uses NSO for IP/MPLS with around 70,000 devices, and Jio uses it for transport management and service provisioning. |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMOEM Related | OEM Related Issues | OPEN | [6 empty] | 1 | Open | Open
638 | M1148 | MOM | 2024-07-12 |  |  |  | OEM Related |  | In T-Fiber, NSO interfaces with EMS for GPON (Nokia & Tejas) and directly with network elements for Cisco IP/MPLS. |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMOEM Related | OEM Related Issues | OPEN | [6 empty] | 1 | Open | Open
639 | M1149 | MOM | 2024-07-12 |  |  |  | OEM Related |  | SVP, T-Fiber requested a comprehensive update on the project's progress, including accomplishments, pending tasks, and future plans. |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMOEM Related | OEM Related Issues | OPEN | [6 empty] | 1 | Open | Open
640 | M115 | MOM | 2023-08-01 |  |  |  | Helpdesk | Handbook & SOPs | Detailed Helpdesk Process Steps |  | Critical | open |  |  |  | Closed | 24-Sep-25: Updated Document Shared 23-Aug-23 |  |  | Siva Kumar |  |  | COMPLETED & APPROVED | [9 empty] | MOMHelpdesk | Helpdesk (Contact Center) | CLOSED |  |  |  | 2025-09-24 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\M104,105,109,111,113,115,122,123,127,128,130,132,162 |  | 1 | Completed & Approved | Closed after June
641 | M1150 | MOM | 2024-07-12 |  |  |  | OEM Related | Cisco | Cisco confirmed that lab licenses are provided free with production licenses and that it is standard practice to set up a pre-production environment. |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMOEM Related | OEM Related Issues | OPEN | [6 empty] | 1 | Open | Open
642 | M1151 | MOM | 2024-07-12 |  |  |  | OEM Related | Cisco | Cisco assured to provide access to the Smartlicenses portal for T-Fiber and to share the full library of APIs for all A&O modules. |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMOEM Related | OEM Related Issues | OPEN | [6 empty] | 1 | Open | Open
643 | M1152 | MOM | 2024-07-12 |  |  |  | OEM Related |  | Technical Support and Operations: |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMOEM Related | OEM Related Issues | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1 | Completed & Approved | Closed after June
644 | M1153 | MOM | 2024-07-12 |  |  |  | OEM Related |  | Discussions were held about the method of operation for NED and product lifecycle management. |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMOEM Related | OEM Related Issues | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1 | Completed & Approved | Closed after June
645 | M1154 | MOM | 2024-07-12 |  |  |  | OEM Related | Cisco | Cisco suggested a gradual handover process with a joint account of L&T and Cisco for a smooth transition. |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMOEM Related | OEM Related Issues | OPEN | [6 empty] | 1 | Open | Open
646 | M1155 | MOM | 2024-07-12 |  |  |  | OEM Related | NSO | Director-P&E, T-Fiber inquired about the system responsible for maintaining the complete inventory within NSO. |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMOEM Related | OEM Related Issues | OPEN | [6 empty] | 1 | Open | Open
647 | M1156 | MOM | 2024-07-12 |  |  |  | OEM Related | Cisco | Cisco mentioned that full orchestration currently requires human intervention, and a service discovery and reconciliation module is needed for full automation. |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMOEM Related | OEM Related Issues | OPEN | [6 empty] | 1 | Open | Open
648 | M1157 | MOM | 2024-07-12 |  |  |  | OEM Related |  | Concerns were raised about customization in the pre-production phase and the need to complete customizations before going live. |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMOEM Related | OEM Related Issues | OPEN | [6 empty] | 1 | Open | Open
649 | M1158 | MOM | 2024-07-12 |  |  |  | OEM Related | Cisco | Cisco emphasized the importance of a change management system for configuration changes and the need for a service audit feature. |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMOEM Related | OEM Related Issues | OPEN | [6 empty] | 1 | Open | Open
650 | M1159 | MOM | 2024-07-12 |  |  |  | OEM Related | Cisco | Cisco to provide all API libraries and hand over NED with knowledge transfers. |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMOEM Related | OEM Related Issues | OPEN | [6 empty] | 1 | Open | Open
651 | M116 | MOM | 2023-08-01 |  |  |  | Helpdesk | Handbook & SOPs | Clarification needed on addressing the subjective nature of "Non-Technical" calls. |  | Critical | open |  |  |  | Closed | 24-Sep-25: It will be Handled by Proposed T fiber Business Helpdesk |  |  | Siva Kumar |  |  | COMPLETED & APPROVED | [9 empty] | MOMHelpdesk | Helpdesk (Contact Center) | CLOSED |  |  |  | 2025-09-24 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\M116,723,1026 |  | 1 | Completed & Approved | Closed after June
652 | M1160 | MOM | 2024-07-12 |  |  |  | OEM Related | OSS | Inventory module and bandwidth manager are still open issues. |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMOEM Related | OEM Related Issues | OPEN | [6 empty] | 1 | Open | Open
653 | M1161 | MOM | 2024-07-12 |  |  |  | OEM Related | OSS | L&T to provide lifecycle processes and how change management and customization are done post-production. |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMOEM Related | OEM Related Issues | OPEN | [6 empty] | 1 | Open | Open
654 | M1162 | MOM | 2024-07-12 |  |  |  | OEM Related | NSO | Cisco to provide E2E topology feasibility, including bandwidth management using NSO. |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMOEM Related | OEM Related Issues | OPEN | [6 empty] | 1 | Open | Open
655 | M1163 | MOM | 2024-07-12 |  |  |  | OEM Related |  | Director-P&E, T-Fiber asked for the deployment of the system in a pre-production environment for thorough testing. |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMOEM Related | OEM Related Issues | OPEN | [6 empty] | 1 | Open | Open
656 | M1164 | MOM | 2024-07-12 |  |  |  | OEM Related |  | SVP, T-Fiber requested access to all modules within the pre-production environment, along with necessary licenses. |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMOEM Related | OEM Related Issues | OPEN | [6 empty] | 1 | Open | Open
657 | M1165 | MOM | 2024-07-12 |  |  |  | OEM Related |  | Director-P&E, T-Fiber emphasized the importance of the system being modular and raised concerns about functionality without BSS. |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMOEM Related | OEM Related Issues | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1 | Completed & Approved | Closed after June
658 | M1166 | MOM | 2024-07-15 |  |  |  | OEM Related |  | L&T to inform T-Fiber and provide details once solution support is fully deployed. |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMOEM Related | OEM Related Issues | OPEN | [6 empty] | 1 | Open | Open
659 | M1167 | MOM | 2024-07-15 |  |  |  | OEM Related |  | L&T to focus on solution reports and resolve operational issues related to UTM. |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMOEM Related | OEM Related Issues | OPEN | [6 empty] | 1 | Open | Open
660 | M1168 | MOM | 2024-07-15 |  |  |  | OEM Related |  | HPE to consider features not possible for alternative solutions. |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMOEM Related | OEM Related Issues | OPEN | [6 empty] | 1 | Open | Open
661 | M1169 | MOM | 2024-07-15 |  |  |  | OEM Related |  | L&T to provide automation in the purge-auto termination process without manual intervention. |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMOEM Related | OEM Related Issues | OPEN | [6 empty] | 1 | Open | Open
662 | M117 | MOM | 2023-08-01 |  |  |  | Helpdesk | Handbook & SOPs | Assumptions for Estimated Calls per Day |  | Critical | open |  |  |  | Closed | 24-Sep-25: Artefacts to be uploaded |  |  | Siva Kumar |  |  | COMPLETED & APPROVED | [9 empty] | MOMHelpdesk | Helpdesk (Contact Center) | CLOSED |  |  |  | 2025-09-24 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\M117,126,728 |  | 1 | Completed & Approved | Closed after June
663 | M1170 | MOM | 2024-07-15 |  |  |  | OEM Related |  | L&T to ensure GIS is the master source for passive infra and it should be a permanent solution. |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMOEM Related | OEM Related Issues | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1 | Completed & Approved | Closed after June
664 | M1171 | MOM | 2024-07-15 |  |  |  | OEM Related |  | L&T to provide all relevant data to facilitate customization requirements for business. |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMOEM Related | OEM Related Issues | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1 | Completed & Approved | Closed after June
665 | M1172 | MOM | 2024-07-15 |  |  |  | OEM Related |  | L&T assured that technical support would be available for the long term and operational training would continue until the complete delivery of the contract. |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMOEM Related | OEM Related Issues | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1 | Completed & Approved | Closed after June
666 | M1173 | MOM | 2024-07-15 |  |  |  | OEM Related |  | L&T to demonstrate all points, including completed points, to ensure transparency on solutions implemented. |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMOEM Related | OEM Related Issues | OPEN | [6 empty] | 1 | Open | Open
667 | M1174 | MOM | 2024-07-15 |  |  |  | OEM Related |  | L&T to prioritize tasks to support business along with T-Fiber to maintain efficient and effective operational workflows. |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMOEM Related | OEM Related Issues | OPEN | [6 empty] | 1 | Open | Open
668 | M1175 | MOM | 2024-07-15 |  |  |  | OEM Related |  | L&T and HPE to provide timelines for operational, delivery, and technical support, as well as a plan for out-of-the-box features. |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMOEM Related | OEM Related Issues | OPEN | [6 empty] | 1 | Open | Open
669 | M1176 | MOM | 2024-07-15 |  |  |  | OEM Related |  | L&T to provide updated LLD document and ensure that all Licenses are provided to T-Fiber as they are an asset of T-Fiber. |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMOEM Related | OEM Related Issues | OPEN | [6 empty] | 1 | Open | Open
670 | M1177 | MOM | 2024-07-15 |  |  |  | OEM Related |  | L&T to submit customize reports and ensure that all open HP APIs should be made available to L&T and T-Fiber. |  | Critical | Open |  |  |  | Closed, Artefacts to be uploaded | 23-Sep-25: Approved Artefacts to be Submitted | L&T | Sivaprasad | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMOEM Related | OEM Related Issues | CLOSED |  |  |  |  | Artefacts Need to upload |  | 1 | Completed & Approved | Closed after June
671 | M1178 | MOM | 2024-07-15 |  |  |  | OEM Related |  | L&T to ensure that the pre-production environment is set up and additional infrastructure needs are met. |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMOEM Related | OEM Related Issues | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1 | Completed & Approved | Closed after June
672 | M1179 | MOM | 2024-07-15 |  |  |  | OEM Related |  | Director-P&E, T-Fiber emphasized the importance of delivering services and suggested scheduling calls to ensure delivery is on track. |  | Critical | Open |  |  |  | Closed, Artefacts to be uploaded | 23-Sep-25: Approved Artefacts to be Submitted | L&T | Sivaprasad | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMOEM Related | OEM Related Issues | CLOSED |  |  |  |  | Artefacts Need to upload |  | 1 | Completed & Approved | Closed after June
673 | M118 | MOM | 2023-08-01 |  |  |  | Helpdesk | Handbook & SOPs | Readiness of Helpdesk to report on compliances and responsiveness and calculate penalties. |  | Critical | open |  |  |  | Artefacts to be submitted | 24-Sep-25:Artefacts to be submitted |  |  | Siva Kumar |  | Open | Open | [9 empty] | MOMHelpdesk | Helpdesk (Contact Center) | OPEN |  |  |  | 2025-09-24 |  |  | 1 | Open | Open
674 | M1180 | MOM | 2024-07-15 |  |  |  | OEM Related |  | Director-P&E, T-Fiber requested an out-of-box demo as per the pre-bid agreement. |  | Critical | Open |  |  |  | Closed, Artefacts to be uploaded | 23-Sep-25: Approved Artefacts to be Submitted | L&T | Sivaprasad | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMOEM Related | OEM Related Issues | CLOSED |  |  |  |  | Artefacts Need to upload |  | 1 | Completed & Approved | Closed after June
675 | M1181 | MOM | 2024-07-15 |  |  |  | OEM Related |  | A detailed discussion is required for DR with all stakeholders, including HPE, OT, and CTRL S, for a comprehensive approach. |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMOEM Related | OEM Related Issues | OPEN | [6 empty] | 1 | Open | Open
676 | M1182 | MOM | 2024-07-22 |  |  |  | T&D Environment |  | MD, T-Fiber emphasized the necessity of a pre-production setup and directed L&T to submit an infrastructure proposal. |  | NON-Critical | Open |  |  |  |  | 11-Oct-25: T Fiber requested to submit reference document Historically the L&T submitted proposal was not approved. Need to work for the final setup |  |  | Ravi Kishore |  | Open | Open | [9 empty] | MOMT&D Environment | Applications | OPEN | [6 empty] | 1 | Open | Open
677 | M1183 | MOM | 2024-07-22 |  |  |  | OEM Related |  | MD, T-Fiber asked L&T to work with the OEM for a higher license count for the Work Force Management Tool (WFM) and to explore features of government tools for comparison. |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMOEM Related | OEM Related Issues | OPEN | [6 empty] | 1 | Open | Open
678 | M1184 | MOM | 2024-07-22 |  |  |  | OEM Related | All OEM's | Concerns were raised about the delay in onboarding OEMs like OpenText, HP, and Cisco. |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMOEM Related | OEM Related Issues | OPEN | [6 empty] | 1 | Open | Open
679 | M1185 | MOM | 2024-07-22 |  |  |  | OEM Related |  | Concerns were raised about the lack of response from Nokia on Hybrid mode solutioning. |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMOEM Related | OEM Related Issues | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1 | Completed & Approved | Closed after June
680 | M1186 | MOM | 2024-12-09 |  |  |  | NOC Operationalization |  | Principal Consultant to be added in WA groups (only NOC , Service Delivery, Project Delivery , and Technology wise group along with OEMs) |  | Critical | Closed |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1 | Completed & Approved | Closed before june-2025
681 | M1187 | MOM | 2024-12-09 |  |  |  | OEM Related |  | OEM wise physical meeting to be called |  | Critical | Closed |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMOEM Related | OEM Related Issues | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1 | Completed & Approved | Closed before june-2025
682 | M1188 | MOM | 2024-12-09 |  |  |  | Helpdesk |  | Helpdesk LLD/HLD to be discussed in detailed |  | Critical | Open |  |  |  | WIP |  |  |  | Siva Kumar |  | Open | WIP | [9 empty] | MOMHelpdesk | Helpdesk (Contact Center) | OPEN | [6 empty] | 1 | Open | Open
683 | M1189 | MOM | 2024-12-09 |  |  |  | NOC Operationalization |  | Only one Issue Tracker to be maintained to track whatever is discussed during current week review |  | Critical | Closed |  |  |  | NON Critical to be reviewd later | 23-Sep-25: NON Critical to be reviewd later | L&T | Sivaprasad | Sivaprasad |  | Open | Open | [9 empty] | MOMNOC Operationalization | Network | OPEN | [6 empty] | 1 | Open | Open
684 | M119 | MOM | 2023-08-01 |  |  |  | Helpdesk | Handbook & SOPs | Live Intrusion of Calls |  | Critical | open |  |  |  | Closed | 24-Sep-25: Artfcats to be uploaded 11-Sep-25: Feature Available, Shall be demonstrated |  |  | Siva Kumar |  |  | COMPLETED & APPROVED | [9 empty] | MOMHelpdesk | Helpdesk (Contact Center) | CLOSED |  |  |  | 2025-09-24 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\M119,733 |  | 1 | Completed & Approved | Closed after June
685 | M1190 | MOM | 2024-12-09 | P3 |  |  | NOC Operationalization |  | Share NOC Dec24 roaster |  | Critical | Closed |  |  |  |  | Roaster shared |  |  | Ahmad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  | Daily oprational task | 2025-09-24 | "\\172.28.9.23\TNOC_Roaster Plan |  | 1 | Completed & Approved | Closed before june-2025
686 | M1191 | MOM | 2024-12-09 |  |  |  | NOC Operationalization |  | OSS to be discussed on 10Dec24 or today |  | Critical | Closed |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1 | Completed & Approved | Closed before june-2025
687 | M1192 | MOM | 2024-12-09 |  |  |  | NOC Operationalization |  | Send all presentations to Principal Consultant |  | Critical | Closed |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1 | Completed & Approved | Closed before june-2025
688 | M1193 | MOM | 2024-12-09 |  | OSS | OSS | OSS | NOC Operationalization | Change Mgmt. system to be made up, currently its manual on mails/excel |  | Critical | Open | [7 empty] | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMOSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  | #N/A |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
689 | M1194 | MOM | 2024-12-09 |  |  |  | BSS |  | Aravindham have personal challenges, can come on MS Team. Request him to come for 2 day for physical meeting |  | Critical | Closed | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN | [6 empty] | 1 | Open | Open
690 | M1195 | MOM | 2024-12-09 |  |  |  | NSO | Service provisioning | IP Schema to discussed |  | Critical | Closed | [7 empty] | Jayant Madavi |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMNSO | Applications/Tools | OPEN |  |  |  |  | Artefacts to be uploaded |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
691 | M1196 | MOM | 2024-12-09 |  |  |  | NOC Operationalization |  | Current PRIORITY discussion to be done for : NOC Review, OSS, DC-Infra, Call Centre HLD/LLD, IP MPLS. Balance to be communicated during the sessions |  | NON-Critical | Closed |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1 | Completed & Approved | Closed before june-2025
692 | M1197 | MOM | 2024-12-09 | P3 |  |  | NOC Operationalization |  | Different kinds of reports to be discussed : Daily reports/dashboards, Capacity reports for all nodes/links (like ISP Util, Capacities utilization, licenses , availability reports for PCK-A/B/C technology wise, etc.) |  | Critical | Closed |  |  |  |  | Discussed and reports sent to Principal COnsultant |  |  | Ahmad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  | Covered in OSS | 2025-09-19 | Artefacts not Required |  | 1 | Completed & Approved | Closed before june-2025
693 | M1198 | MOM | 2024-12-09 |  | OSS | OSS | OSS | BBNL | CDOT integration with NMS is highest priority. The team should be actively engaged with teams and visit sites. |  | Critical | Closed | [7 empty] | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMOSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
694 | M1199 | MOM | 2024-12-09 | P3 |  |  | NOC Operationalization |  | Principal Consultant meeting with NOC L3s |  | Critical | Closed |  |  |  |  | Meeting was done |  |  | Ahmad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  | Not related to delivery | 2025-09-19 | Artefacts not Required |  | 1 | Completed & Approved | Closed before june-2025
695 | M12 | MOM | 2023-04-03 |  |  |  | T&D Environment | T&D Environment | Test Lab Setup Equipments and Plan |  | NON-Critical | Open |  |  |  |  | 11-Oct-25: T Fiber requested to submit reference document Historically the L&T submitted proposal was not approved. Need to work for the final setup |  |  | Ravi Kishore |  | Open | Open | [9 empty] | MOMT&D Environment | Applications | OPEN | [6 empty] | 1 | Open | Open
696 | M120 | MOM | 2023-08-01 |  |  |  | Helpdesk | Handbook & SOPs | Duration of Call Measurement |  | Critical | open |  |  |  | Closed | 24-Sep-25: Artfcats to be uploaded 11-Sep-25: Feature Available, Shall be demonstrated |  |  | Siva Kumar |  |  | COMPLETED & APPROVED | [9 empty] | MOMHelpdesk | Helpdesk (Contact Center) | CLOSED |  |  |  | 2025-09-24 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\M120,129 |  | 1 | Completed & Approved | Closed after June
697 | M1200 | MOM | 2024-12-09 |  |  |  | NOC Operationalization |  | NOC 2.0 Mission : 30th April - All systems should be live. BSS KNOT(phase1) should be ready by 15th March OSS should be ready by Jan end NSO should be ready by mid-March |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMNOC Operationalization | Network | OPEN | [6 empty] | 1 | Open | Open
698 | M1201 | MOM | 2024-12-09 |  |  |  | NOC Operationalization |  | L&T should recommend systems that should be procured for better efficiencies. A tendering process may be taken up as suitable by TFIBER. |  | Critical | Closed |  |  |  | Siva prasad to getback on same | 23-Sep-25: NON Critical to be reviewd later | L&T | Sivaprasad | Sivaprasad |  | Open | Open | [9 empty] | MOMNOC Operationalization | Network | OPEN | [6 empty] | 1 | Open | Open
699 | M1202 | MOM | 2024-12-09 |  |  |  | NOC Operationalization |  | Map of technology vis-à-vis OEM vis-à-vis issues |  | Critical | Closed |  |  |  | Closed, Artefacts to be uploaded | 23-Sep-25: Approved Artefacts to be Submitted | L&T | Sivaprasad | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  |  | Artefacts Need to upload |  | 1 | Completed & Approved | Closed before june-2025
700 | M1203 | MOM | 2024-12-09 | P3 |  |  | NOC Operationalization |  | Passive Infra-Additional capacity needed in the NOC |  | Critical | Closed |  |  |  |  | TFiber team had to share this as per future plan. DC Passive deployed capacity is already as per RFP and AT completed |  |  | Ahmad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  | No clarity on requirment | 2025-09-19 | Artefacts not Required |  | 1 | Completed & Approved | Closed before june-2025
701 | M1204 | MOM | 2024-12-09 | P3 |  |  | NOC Operationalization |  | CCTV to be configured on Principal Consultant office and laptop. L&T to come up with solution |  | Critical | Closed |  |  |  |  | Discussed with TFiber later on, not needed |  |  | Ahmad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  | Not related to delivery | 2025-09-19 | Artefacts not Required |  | 1 | Completed & Approved | Closed before june-2025
702 | M1205 | MOM | 2024-12-09 |  |  |  | NOC Operationalization |  | Test labs and staging environment, currently project equipment's (routers, GPON, etc.) are being used |  | Critical | Closed |  |  |  | TO be reviewed | 23-Sep-25: NON Critical to be reviewd later | L&T | Sivaprasad | Sivaprasad |  | Open | Open | [9 empty] | MOMNOC Operationalization | Network | OPEN | [6 empty] | 1 | Open | Open
703 | M1206 | MOM | 2024-12-09 |  |  |  | DC-IT | NOC Operationalization | HLD and LLD documents to be revised for DC Infra |  | NON-Critical | Open |  |  |  |  | Work in progress |  |  | Ravi Kishore |  | Open | Open | [9 empty] | MOMDC-IT | Network | OPEN | [6 empty] | 1 | Open | Open
704 | M1207 | MOM | 2024-12-10 |  |  |  | BSS |  | One call with BSS and NSO SME to be done tomorrow morning |  | Critical | Closed | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN | [6 empty] | 1 | Open | Open
705 | M1208 | MOM | 2024-12-10 |  |  |  | OEM Related |  | Tejas : TR069 feature to be enabled for TFIBER network |  | NON-Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMOEM Related | OEM Related Issues | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1 | Completed & Approved | Closed after June
706 | M1209 | MOM | 2024-12-10 |  |  |  | OEM Related |  | One resource from Tejas to be placed at TNOC for sorting out Tejas related issues |  | Critical | Closed |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMOEM Related | OEM Related Issues | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1 | Completed & Approved | Closed before june-2025
707 | M121 | MOM | 2023-08-01 |  |  |  | Helpdesk | Handbook & SOPs | Exceptions in IVR User Response |  | Critical | open |  |  |  | Closed | 24-Sep-25: Approved and shall be closed |  |  | Siva Kumar |  |  | COMPLETED & APPROVED | [9 empty] | MOMHelpdesk | Helpdesk (Contact Center) | CLOSED |  |  |  | 2025-09-24 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\M121,170,99,726 |  | 1 | Completed & Approved | Closed after June
708 | M1210 | MOM | 2024-12-10 |  |  |  | NOC Operationalization |  | Tejas: Pending API to be given on priority |  | Critical | Closed | [7 empty] | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API | [6 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API |  | 1 | Completed & Approved | Closed before june-2025
709 | M1211 | MOM | 2024-12-10 |  |  |  | NOC Operationalization |  | Make one WhatsApp group for Tejas only (LTTS, TFIBER, Tejas) |  | Critical | Closed |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1 | Completed & Approved | Closed before june-2025
710 | M1212 | MOM | 2024-12-10 |  |  |  | NOC Operationalization |  | Suggested one format for SME tasks tracking Each SME to update that tracker putting all critical/major/minor tasks/issues listed in this. To be updated on daily basis with dates |  | Critical | Closed |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1 | Completed & Approved | Closed before june-2025
711 | M1213 | MOM | 2024-12-10 |  |  |  | NSO | Service provisioning | 27 services NSO licenses details to be shared with Principal Consultant |  | Critical | Closed | [7 empty] | Jayant Madavi |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMNSO | Applications/Tools | OPEN |  |  |  |  | Artefacts to be uploaded |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
712 | M1214 | MOM | 2024-12-10 |  |  |  | NSO | Service provisioning | NSO VMs details for T&D to be shared with Principal Consultant along with issue details (what support needed from Cisco) |  | Critical | Closed | [7 empty] | Jayant Madavi |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMNSO | Applications/Tools | OPEN |  |  |  |  | Artefacts to be uploaded |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
713 | M1215 | MOM | 2024-12-10 |  |  |  | NSO | Service provisioning | Trial licenses will be given as stop gap arrangement for NSO T&D setup. VM details to be shared with Ravindra (MAC id , etc.) by LTTS |  | Critical | Closed | [7 empty] | Jayant Madavi |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMNSO | Applications/Tools | OPEN |  |  |  |  | Artefacts to be uploaded |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
714 | M1216 | MOM | 2024-12-10 |  |  |  | OEM Related | Cisco EPNM | License issue for EPNM and ISE to be resolved |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMOEM Related | OEM Related Issues | OPEN | [6 empty] | 1 | Open | Open
715 | M1217 | MOM | 2024-12-10 |  |  |  | NOC Operationalization |  | One resource from Tejas to be placed at TNOC for sorting out Tejas related issues |  | Critical | Closed |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1 | Completed & Approved | Closed before june-2025
716 | M1218 | MOM | 2024-12-10 |  |  |  | NSO | Service provisioning | Agreed SOW for NSO to be shared |  | Critical | Closed | [7 empty] | Jayant Madavi |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMNSO | Applications/Tools | OPEN |  |  |  |  | Artefacts to be uploaded |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
717 | M1219 | MOM | 2024-12-10 |  |  |  | NSO | Service provisioning | SOW for Cisco NSO - by when quotation will be closed by Cisco? Cisco to revert back with quotation timelines, probably tomorrow, also with TAT for implementation |  | Critical | Open | [7 empty] | Jayant Madavi |  | Open | Open | [9 empty] | MOMNSO | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
718 | M122 | MOM | 2023-08-01 |  |  |  | Helpdesk | Handbook & SOPs | The unit of measurement is required for all Key Performance Indicator (KPI) parameters. |  | Critical | open |  |  |  | Closed | 24-Sep-25: Updated Document Shared 23-Aug-23 |  |  | Siva Kumar |  |  | COMPLETED & APPROVED | [9 empty] | MOMHelpdesk | Helpdesk (Contact Center) | CLOSED |  |  |  | 2025-09-24 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\M104,105,109,111,113,115,122,123,127,128,130,132,162 |  | 1 | Completed & Approved | Closed after June
719 | M1220 | MOM | 2024-12-10 |  |  |  | NOC Operationalization |  | Make one WhatsApp group for NSO only (LTTS, TFIBER, OEM) |  | Critical | Closed |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1 | Completed & Approved | Closed before june-2025
720 | M1221 | MOM | 2024-12-10 |  |  |  | NSO | Service provisioning | Dark Fiber as a service |  | Critical | Closed | [7 empty] | Jayant Madavi |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMNSO | Applications/Tools | OPEN |  |  |  |  | Artefacts to be uploaded |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
721 | M1222 | MOM | 2024-12-10 |  |  |  | NSO | Service provisioning | List down all services which are needed for launch (As per LTTS understanding). During 2PM workshop tomorrow KNOT, Aravindham, Ashish, Ravindra Cisco, TFIBER will be there on call |  | Critical | Closed | [7 empty] | Jayant Madavi |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMNSO | Applications/Tools | OPEN |  |  |  |  | Artefacts to be uploaded |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
722 | M1223 | MOM | 2024-12-10 |  |  |  | OEM Related |  | SG350 switch EOS/EOL: GP all OK. Mandal/Zonal level have some discrepancy like less ports compared to current version or at least match to RFP |  | NON-Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMOEM Related | OEM Related Issues | OPEN | [6 empty] | 1 | Open | Open
723 | M1224 | MOM | 2024-12-10 |  |  |  | NOC Operationalization |  | Make other WhatsApp group for Cisco other domains (apart from NSO). Make Ravindar Admin to add other Cisco team members. (LTTS except NSO, TF, Cisco) |  | Critical | Closed |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1 | Completed & Approved | Closed before june-2025
724 | M1225 | MOM | 2024-12-10 |  |  |  | OEM Related | Cisco | SG350 switch: EOSale/EOL/LDOHWS (Last date of HW support which is Oct2026. Till LDOHWS that RMA will be given with new CBS model. Post that support will stop. Mail request to be send to Cisco to extend support. |  | NON-Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMOEM Related | OEM Related Issues | OPEN | [6 empty] | 1 | Open | Open
725 | M1226 | MOM | 2024-12-10 |  |  |  | OEM Related |  | EPNM license upgraded, in smart account licenses are not working. Its issue with PKG-A only (PKG-B/C had procured separately 5.x so they don’t have this issue, while LTTS procured 2.x as per Ravindra) |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMOEM Related | OEM Related Issues | OPEN | [6 empty] | 1 | Open | Open
726 | M1227 | MOM | 2024-12-10 |  |  |  | BSS |  | Is our network integrated with Aadhar servers, GST? LTTS confirmed it is not integrated |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
727 | M1228 | MOM | 2024-12-10 |  |  |  | NOC Operationalization |  | Agreement status for all OEM to be shared |  | Critical | Closed |  |  |  | Closed, Artefacts to be uploaded | 23-Sep-25: Approved Artefacts to be Submitted | L&T | Sivaprasad | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  |  | Artefacts Need to upload |  | 1 | Completed & Approved | Closed before june-2025
728 | M1229 | MOM | 2024-12-10 |  | OSS | OSS | OSS | BBNL | BBNL - API : is top priority. Each day update to be sent to Principal Consultant |  | Critical | Closed | [7 empty] | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMOSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
729 | M123 | MOM | 2023-08-01 |  |  |  | Helpdesk | Handbook & SOPs | Sample Methods for KPI Calculations |  | Critical | open |  |  |  | Closed | 24-Sep-25: Updated Document Shared 23-Aug-23 |  |  | Siva Kumar |  |  | COMPLETED & APPROVED | [9 empty] | MOMHelpdesk | Helpdesk (Contact Center) | CLOSED |  |  |  | 2025-09-24 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\M104,105,109,111,113,115,122,123,127,128,130,132,162 |  | 1 | Completed & Approved | Closed after June
730 | M1230 | MOM | 2024-12-10 |  | OSS | OSS | OSS | BBNL | Tomorrow 3 PM. will call Rupa Maan and Akhilesh Gupta Sir for BBNL API |  | Critical | Closed | [7 empty] | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMOSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
731 | M1231 | MOM | 2024-12-10 |  |  |  | OEM Related |  | Principal Consultant Room Dashboard - Excel sheet sent, to discuss and finetune. Discussed. Need this report through OSS, to be added in HPE/OT scope once they are onboarded - discuss jointly with TFIBER along with OEM |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMOEM Related | OEM Related Issues | OPEN | [6 empty] | 1 | Open | Open
732 | M1232 | MOM | 2024-12-10 |  |  |  | NOC Operationalization |  | All inhouse automation : LLD to be made by SME and handover to Ops & TFIBER team |  | NON-Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMNOC Operationalization | Network | OPEN | [6 empty] | 1 | Open | Open
733 | M1233 | MOM | 2024-12-10 |  |  |  | OEM Related |  | OSS out of Scope: 1. Service Topology 2. Retail Services (5Mn), 3. Services & Service KPI Monitoring. As per SOR this is not there. This is for Principal Consultant information |  | Critical | Closed |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMOEM Related | OEM Related Issues | OPEN | [6 empty] | 1 | Open | Open
734 | M1234 | MOM | 2024-12-10 |  |  |  | OEM Related |  | Share all OSS documents (RFP points, LLD, FRS, etc.) |  | Critical | Closed |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMOEM Related | OEM Related Issues | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1 | Completed & Approved | Closed before june-2025
735 | M1235 | MOM | 2024-12-10 |  |  |  | NOC Operationalization |  | Make P1/P2/P3 list for all pending tasks for all domain P1: 25% P2 : 30% P3 : 45% And then list of some additional ask if needed like new HW or software required. |  | Critical | Closed |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1 | Completed & Approved | Closed before june-2025
736 | M1236 | MOM | 2024-12-10 |  | OSS | OSS | OSS | BBNL | Manoj: Complete BBNL ask tasks will be completed by 12 Dec24 (only GP and Block Node status API pending). Sanjay: Uptime gap ~7% to be addressed. For this, HPE support needed. Then only we can go to BBNL for closure. Alarm re-synchronization issue - need HPE support. Interim solution implemented (1 Hr). Same for Inventory. |  | Critical | Open | [7 empty] | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMOSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
737 | M1237 | MOM | 2024-12-10 |  |  |  | OEM Related |  | Bottomline for OSS: Engagement with HPE and OT to start to get all OSS open/pending tasks done |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMOEM Related | OEM Related Issues | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1 | Completed & Approved | Closed after June
738 | M1238 | MOM | 2024-12-10 |  |  |  | OEM Related | All OEM's | Priority engagement with HPE/OT/Cisco/Aleppo needed to meet Apr25 target. Current payment/cash flow issues hindering this right now |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMOEM Related | OEM Related Issues | OPEN | [6 empty] | 1 | Open | Open
739 | M1239 | MOM | 2024-12-10 |  |  |  | NOC Operationalization |  | Pending AT for all Application and DC systems to be shared by tomorrow |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMNOC Operationalization | Network | OPEN | [6 empty] | 1 | Open | Open
740 | M124 | MOM | 2023-08-01 |  |  |  | Helpdesk | Handbook & SOPs | Inquiry into how Customer Satisfaction (CSAT) is measured and whether there is a mechanism for transactional feedback. |  | Critical | Open |  |  |  | WIP |  |  |  | Siva Kumar |  | Open | WIP | [9 empty] | MOMHelpdesk | Helpdesk (Contact Center) | OPEN | [6 empty] | 1 | Open | Open
741 | M1240 | MOM | 2024-12-10 | P3 |  |  | NOC Operationalization |  | Major nodes/links utilization report to be shared (Deployed V/s Utilized) by tomorrow |  | Critical | Closed |  |  |  |  | Report shared |  |  | Ahmad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  | Covered in OSS | 2025-09-19 | Artefacts not Required |  | 1 | Completed & Approved | Closed before june-2025
742 | M1241 | MOM | 2024-12-10 |  |  |  | NOC Operationalization |  | Did anyone visited DR Ctrl-S location at Mumbai? No, except of earlier L&T Delivery Head Principal Consultant: Will plan visit to this location in future |  | Critical | Open |  |  |  | Will be discussed later | 23-Sep-25: NON Critical to be reviewd later | L&T | Sivaprasad | Sivaprasad |  | Open | Open | [9 empty] | MOMNOC Operationalization | Network | OPEN | [6 empty] | 1 | Open | Open
743 | M1242 | MOM | 2024-12-10 | P3 |  |  | NOC Operationalization |  | Send Cluster wise utilization report for DC infra |  | Critical | Closed |  |  |  |  | Report shared |  |  | Ahmad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  | Daily oprational task | 2025-09-19 | Artefacts not Required |  | 1 | Completed & Approved | Closed before june-2025
744 | M1243 | MOM | 2024-12-10 | P3 |  |  | NOC Operationalization |  | Login in OSS, BSS, ticketing, NSO and to share all links with Principal Consultant |  | Critical | Closed |  |  |  |  | Login ID made and link shared |  |  | Ahmad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  | Not related to delivery | 2025-09-19 | Artefacts not Required |  | 1 | Completed & Approved | Closed before june-2025
745 | M1244 | MOM | 2024-12-10 |  |  |  | OEM Related | Neox | Neox team to be called for meeting |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMOEM Related | OEM Related Issues | OPEN | [6 empty] | 1 | Open | Open
746 | M1245 | MOM | 2024-12-10 | P3 |  |  | NOC Operationalization |  | Access to NAS server to be provided to Principal Consultant to get access to HLD / LLD / reports. |  | NON-Critical | Closed |  |  |  |  | Access given |  |  | Ahmad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  | Not related to delivery | 2025-09-19 | Artefacts not Required |  | 1 | Completed & Approved | Closed before june-2025
747 | M1246 | MOM | 2024-12-10 | P3 |  |  | NOC Operationalization |  | Dashboards samples were shared by the Principal Consultant, a brief discussions carried on how critical data to be presented |  | Critical | Closed |  |  |  |  | Report shared as per Principal Consultant review |  |  | Ahmad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  | Covered in OSS | 2025-09-19 | Artefacts not Required |  | 1 | Completed & Approved | Closed before june-2025
748 | M1247 | MOM | 2024-12-11 |  |  |  | IP/MPLS | NOC Operationalization | Actual implemented IP MPLS ring details needed. |  | Critical | Closed |  |  |  |  | RIng details shared | L&T |  | RS Rao |  |  | COMPLETED & APPROVED | [9 empty] | MOMIP/MPLS | IPMPLS | CLOSED |  |  |  | After Jun-25 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\Link topology of PKG A B C updated as on 05082025.xlsx |  | 1 | Completed & Approved | Closed before june-2025
749 | M1248 | MOM | 2024-12-11 |  |  |  | NOC Operationalization |  | Share Test Setup proposal which was sent to TFIBER by LTTS. |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1 | Completed & Approved | Closed after June
750 | M1249 | MOM | 2024-12-11 | P3 |  |  | NOC Operationalization |  | What is total scope of the project V/S implementation. And then total equipment procured Vs installed Vs Available in field and at DC |  | Critical | Closed |  |  |  |  | Report shared |  |  | Ahmad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  | Covered in OSS | 2025-09-19 | Artefacts not Required |  | 1 | Completed & Approved | Closed before june-2025
751 | M125 | MOM | 2023-08-01 |  |  |  | Helpdesk | Handbook & SOPs | Expression of First Call Resolution (FCR) as a percentage |  | Critical | Open |  |  |  | WIP |  |  |  | Siva Kumar |  | Open | WIP | [9 empty] | MOMHelpdesk | Helpdesk (Contact Center) | OPEN | [6 empty] | 1 | Open | Open
752 | M1250 | MOM | 2024-12-11 |  |  |  | OEM Related | HPSM | In Asset Manager deployed inventory status is available. WH equipment data also available for PKG-B & C. |  | Critical | Closed |  |  |  | to be discussed later | 23-Sep-25: NON Critical to be reviewd later | L&T | Sivaprasad | Sivaprasad |  | Open | Open | [9 empty] | MOMOEM Related | OEM Related Issues | OPEN | [6 empty] | 1 | Open | Open
753 | M1251 | MOM | 2024-12-11 | P3 |  |  | NOC Operationalization |  | Tomorrow Field Project team discussion is scheduled (Different Packages , Different Slots, Need OSS and NOC team) |  | Critical | Closed |  |  |  |  | Meetin conducted |  |  | Ahmad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  | Not related to delivery | 2025-09-19 | Artefacts not Required |  | 1 | Completed & Approved | Closed before june-2025
754 | M1252 | MOM | 2024-12-11 | P3 |  |  | NOC Operationalization |  | Inventory, down, nodes/links with aging, team deployed in field to be shown to them |  | Critical | Closed |  |  |  |  | Data shown especially DWDM, Mandal, GP and UPS |  |  | Ahmad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  | Covered in OSS | 2025-09-19 | Artefacts not Required |  | 1 | Completed & Approved | Closed before june-2025
755 | M1253 | MOM | 2024-12-11 |  | OSS | OSS | OSS | BBNL | Make a Focused WhatsApp group for BBNL |  | Critical | Closed | [7 empty] | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMOSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
756 | M1254 | MOM | 2024-12-11 |  |  |  | IP/MPLS | NOC Operationalization | Holistic IP planning for all service type to be done based on discussion in near future |  | Critical | Closed | [5 empty] | L&T |  | RS Rao |  |  | COMPLETED & APPROVED | [9 empty] | MOMIP/MPLS | IPMPLS | CLOSED |  |  |  | After Jun-25 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\TFiber IP Plan Details.zip |  | 1 | Completed & Approved | Closed before june-2025
757 | M1255 | MOM | 2024-12-11 |  |  |  | NOC Operationalization |  | Official mail to IPNIC from TFIBER MD office for additional IPs to be sent |  | Critical | Open | [7 empty] | TFiber |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMNOC Operationalization | Network | OPEN |  |  |  |  | Artefacts to be uploaded |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
758 | M1256 | MOM | 2024-12-11 |  |  |  | NOC Operationalization |  | For all equipment's, need confirmation mail/letter from all OEMs for IPv4 and IPv6 dual stack implementation compliance |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMNOC Operationalization | Network | OPEN | [6 empty] | 1 | Open | Open
759 | M1257 | MOM | 2024-12-11 |  |  |  | NOC Operationalization |  | A consistent process of design review to acceptance of artefact is missing. Requested Principal Consultant to agree process to set a design authority |  | Critical | Closed | [7 empty] | TFiber |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMNOC Operationalization | Network | OPEN |  |  |  |  | Artefacts to be uploaded |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
760 | M1258 | MOM | 2024-12-11 |  |  |  | BSS |  | Capture Aadhar integration need in our requirement doc / soln/SOW for BSS/NSO. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
761 | M1259 | MOM | 2024-12-11 |  |  |  | NOC Operationalization |  | What BSS & NSO does? Can you make flow of processes/data/provisioning/delivery etc. across BSS, NSO, OSS, EMS, Billing, Helpdesk |  | Critical | Closed |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMNOC Operationalization | Network | OPEN | [6 empty] | 1 | Open | Open
762 | M126 | MOM | 2023-08-01 |  |  |  | Helpdesk | Handbook & SOPs | Review of Agent Utilization Formula |  | Critical | open |  |  |  | Closed | 25-Sep-25: Artefacts to be uploaded |  |  | Siva Kumar |  |  | COMPLETED & APPROVED | [9 empty] | MOMHelpdesk | Helpdesk (Contact Center) | CLOSED |  |  |  | 2025-09-24 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\M117,126,728 |  | 1 | Completed & Approved | Closed after June
763 | M1260 | MOM | 2024-12-11 |  |  |  | NOC Operationalization |  | What all services are automated and what is not automated list to be provided |  | Critical | Closed |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMNOC Operationalization | Network | OPEN | [6 empty] | 1 | Open | Open
764 | M1261 | MOM | 2024-12-11 |  |  |  | BSS |  | Business flow discussed like existing telecom operator customer mgmt. case study . BSS Workout sheet made by Principal Consultant will be sent to you, and will discuss in detailed along with KNOT, TFIBER, TFIBER business/finance team when Aravindhan comes over to HYD at TFIBER office |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN | [6 empty] | 1 | Open | Open
765 | M1262 | MOM | 2024-12-13 | P3 |  |  | NOC Operationalization |  | Make Node Availability as per today's format as suggested by Principal Consultant |  | Critical | Closed |  |  |  |  | Report shared as per Principal Consultant review |  |  | Ahmad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  | Covered in OSS | 2025-09-19 | Artefacts not Required |  | 1 | Completed & Approved | Closed before june-2025
766 | M1263 | MOM | 2024-12-13 | P3 |  |  | NOC Operationalization |  | All nodes/applications AMC details to be shared |  | Critical | Closed |  |  |  |  | AMC status shared |  |  | Ahmad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  | Infrastructure | 2025-09-24 | \\172.28.9.23\tnocreports\AMC |  | 1 | Completed & Approved | Closed before june-2025
767 | M1264 | MOM | 2024-12-31 | P3 |  |  | NOC Operationalization |  | Network alarms to be reduced, currently 90K alarms |  | Critical | Closed |  |  |  |  | Report shared. Field related alarms exists as per field anamolies |  |  | Ahmad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  | Covered in OSS | 2025-09-19 | Artefacts not Required |  | 1 | Completed & Approved | Closed before june-2025
768 | M1265 | MOM | 2025-02-14 |  |  |  | NOC Operationalization |  | Go-live plan discussion and action items to be tracked and closed |  | Critical | Closed |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMNOC Operationalization | Network | OPEN | [6 empty] | 1 | Open | Open
769 | M1266 | MOM | 2025-02-14 | P3 |  |  | NOC Operationalization |  | One-to-one meeting with complete TNOC resources to be completed |  | Critical | Open |  |  |  |  | Scheduled as per Principal Consultant availability |  |  | Ahmad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  | Not related to delivery | 2025-09-19 | Artefacts not Required |  | 1 | Completed & Approved | Closed after June
770 | M1267 | MOM | 2025-02-14 |  |  |  | OEM Related | Nokia | All APIs to be taken from Nokia |  | Critical | Open |  |  |  | Closed, Artefacts to be uploaded | 23-Sep-25: Approved Artefacts to be Submitted | L&T | Sivaprasad | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMOEM Related | OEM Related Issues | CLOSED |  |  |  |  | Artefacts Need to upload |  | 1 | Completed & Approved | Closed after June
771 | M1268 | MOM | 2025-02-14 |  |  |  | NOC Operationalization |  | Undertaking from L&T is needed for all In-House software |  | Critical | Open |  |  |  | Closed, Artefacts to be uploaded | 23-Sep-25: Approved Artefacts to be Submitted | L&T | Sivaprasad | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  |  | Artefacts Need to upload |  | 1 | Completed & Approved | Closed after June
772 | M1269 | MOM | 2025-02-14 | P3 |  |  | NOC Operationalization |  | PKG-A WH inventory data to be uploaded in Asset Manager |  | Critical | Open |  |  |  |  | Done |  |  | Ahmad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  | Covered in OSS | 2025-09-19 | Artefacts not Required |  | 1 | Completed & Approved | Closed after June
773 | M127 | MOM | 2023-08-01 |  |  |  | Helpdesk | Handbook & SOPs | Customer-Specific SLA Flows |  | Critical | open |  |  |  | Closed | 24-Sep-25: Updated Document Shared 23-Aug-23 |  |  | Siva Kumar |  |  | COMPLETED & APPROVED | [9 empty] | MOMHelpdesk | Helpdesk (Contact Center) | CLOSED |  |  |  | 2025-09-24 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\M104,105,109,111,113,115,122,123,127,128,130,132,162 |  | 1 | Completed & Approved | Closed after June
774 | M1270 | MOM | 2025-02-14 |  |  |  | Helpdesk | Handbook & SOPs | Helpdesk IVR: after selecting any number (apart from configured 1/2/3), call is getting disconnected. This need to be corrected |  | Critical | open |  |  |  | Closed | 24-Sep-25: Artefacts to be uploaded |  |  | Siva Kumar |  |  | COMPLETED & APPROVED | [9 empty] | MOMHelpdesk | Helpdesk (Contact Center) | CLOSED |  |  |  | 2025-09-24 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\M1270 |  | 1 | Completed & Approved | Closed after June
775 | M1271 | MOM | 2025-04-03 |  |  |  | NOC Operationalization |  | One slide to be presented showing status of work capturing: a. Status (last week actions), b) Issues, c) Achievements d) Plan for Next week. Only major points to be mentioned |  | Critical | Closed |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1 | Completed & Approved | Closed before june-2025
776 | M1272 | MOM | 2025-04-03 |  |  |  | NOC Operationalization |  | Review slides to capture: 1. Tech/SME/OEM wise update 2. Domain Status - one slide for each domain 3. HLD/LLD/FAT update 4. Detailed HLD/LLD/FAT open points list: 20-30 points 5. Other important points (NOC also like DWDM losses, infra issues at ZOnal/mandal, etc.) 6. 742 Tracker, MoM update |  | NON-Critical | Closed |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1 | Completed & Approved | Closed before june-2025
777 | M1273 | MOM | 2025-04-03 |  |  |  | NOC Operationalization |  | Aggressive followups with TPA to be done by L&T SMEs. Post 2-3 followups, then come to Principal Consultant for support alongwith TPA |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1 | Completed & Approved | Closed after June
778 | M1274 | MOM | 2025-04-03 |  |  |  | GIS | User Experience | GIS: Make a PPT for operationalisation of GIS Ops & updation. This will be shared to PKG-B & C |  | Critical | Open | Conflict | Gtech | [5 empty] | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMGIS | Applications/Tools | OPEN | [6 empty] | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
779 | M1275 | MOM | 2025-04-03 |  |  |  | NOC Operationalization |  | Incorporate MoM points in HLD/LLD documents |  | NON-Critical | Closed |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMNOC Operationalization | Network | OPEN | [6 empty] | 1 | Open | Open
780 | M1276 | MOM | 2025-04-03 |  |  |  | NOC Operationalization |  | Make proper justification for A&O for Tfiber MD approval. Shpw project plan. Show previous delivered systems like IPDR, BBNL solution which his made solely by L&T inhouse team. Include Support system/mechanism to Tfiber during 7 years and post L&T exit project |  | Critical | Closed |  |  |  | Closed, Artefacts to be uploaded | 23-Sep-25: Approved Artefacts to be Submitted | L&T | Sivaprasad | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  |  | Artefacts Need to upload |  | 1 | Completed & Approved | Closed before june-2025
781 | M1277 | MOM | 2025-04-03 |  |  |  | NSO | Service provisioning | GI-BB Demo to be shown to Principal Consultant on 15th April2025 |  | Critical | Closed | [7 empty] | Jayant Madavi |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMNSO | Applications/Tools | OPEN |  |  |  |  | Artefacts to be uploaded |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
782 | M1278 | MOM | 2025-04-03 |  |  |  | NOC Operationalization |  | Every Thursday 11 AM review meeting to be planned with Principal Consultant on NOC project |  | Critical | Closed |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1 | Completed & Approved | Closed before june-2025
783 | M128 | MOM | 2023-08-01 |  |  |  | Helpdesk | Handbook & SOPs | Exhaustive List of General Enquiries |  | Critical | open |  |  |  | Closed | 24-Sep-25: Updated Document Shared 23-Aug-23 |  |  | Siva Kumar |  |  | COMPLETED & APPROVED | [9 empty] | MOMHelpdesk | Helpdesk (Contact Center) | CLOSED |  |  |  | 2025-09-24 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\M104,105,109,111,113,115,122,123,127,128,130,132,162 |  | 1 | Completed & Approved | Closed after June
784 | M129 | MOM | 2023-08-01 |  |  |  | Helpdesk | Handbook & SOPs | DoT KPIs Coverage in KPI Section |  | Critical | open |  |  |  | Closed | 24-Sep-25: Artfcats to be uploaded 11-Sep-25: Feature Available, Shall be demonstrated |  |  | Siva Kumar |  |  | COMPLETED & APPROVED | [9 empty] | MOMHelpdesk | Helpdesk (Contact Center) | CLOSED |  |  |  | 2025-09-24 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\M120,129 |  | 1 | Completed & Approved | Closed after June
785 | M13 | MOM | 2023-04-03 |  | OSS | OSS | OSS | Functional AT Plan | Quality test report submission for DWDM & IPMPLS each zonal path. |  | Critical | Open |  | OSS Dashboards | [5 empty] | Suresh Pawar |  | Open | Open | [9 empty] | MOMOSS | Applications/Tools | OPEN | OPEN | 0 |  |  | #N/A |  | 1 | Open | Open
786 | M130 | MOM | 2023-08-01 |  |  |  | Helpdesk | Handbook & SOPs | FAQs Based on Case Studies |  | Critical | open |  |  |  | Closed | 24-Sep-25: Updated Document Shared 23-Aug-23 |  |  | Siva Kumar |  |  | COMPLETED & APPROVED | [9 empty] | MOMHelpdesk | Helpdesk (Contact Center) | CLOSED |  |  |  | 2025-09-24 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\M104,105,109,111,113,115,122,123,127,128,130,132,162 |  | 1 | Completed & Approved | Closed after June
787 | M131 | MOM | 2023-08-01 |  |  |  | Helpdesk | Handbook & SOPs | Request to differentiate between registered users and registered numbers using examples. |  | Critical | Open |  |  |  | WIP | 11-Sep-25: BSS Integration to be completed |  |  | Siva Kumar |  | Open | WIP | [9 empty] | MOMHelpdesk | Helpdesk (Contact Center) | OPEN | [6 empty] | 1 | Open | Open
788 | M132 | MOM | 2023-08-01 |  |  |  | Helpdesk | Handbook & SOPs | the roles and responsibilities of NOC and Field Personnel be separate according to the RASCI matrix |  | Critical | open |  |  |  | Closed | 24-Sep-25: Updated Document Shared 23-Aug-23 |  |  | Siva Kumar |  |  | COMPLETED & APPROVED | [9 empty] | MOMHelpdesk | Helpdesk (Contact Center) | CLOSED |  |  |  | 2025-09-24 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\M104,105,109,111,113,115,122,123,127,128,130,132,162 |  | 1 | Completed & Approved | Closed after June
789 | M133 | MOM | 2023-08-01 |  |  |  | Helpdesk | Handbook & SOPs | Inclusion of Master and Child Service Level Agreement (SLA) monitoring; if any SLA is breached, a proper escalation matrix should be available for speedy escalation and resolution of the issue. |  | Critical | open |  |  |  | WIP |  |  |  | Siva Kumar |  | Open | WIP | [9 empty] | MOMHelpdesk | Helpdesk (Contact Center) | OPEN | [6 empty] | 1 | Open | Open
790 | M134 | MOM | 2023-08-01 |  |  |  | Helpdesk | Training | Training for Call Transferring |  | Critical | open |  |  |  | Closed | 24-Sep-25: Trianing completed, Artefacts to be uploaded |  |  | Siva Kumar |  |  | COMPLETED & APPROVED | [9 empty] | MOMHelpdesk | Helpdesk (Contact Center) | CLOSED |  |  |  | 2025-09-24 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\M114,722,134 |  | 1 | Completed & Approved | Closed after June
791 | M135 | MOM | 2023-08-01 |  |  |  | Helpdesk | User Experience | Proactive Intimation of Planned Downtime |  | Critical | open |  |  |  | WIP | 24-Sep-25: Part of Neox integration with BSS/OSS | L&T | Manoj & Shiva kumar | Siva Kumar |  | Open | WIP | [9 empty] | MOMHelpdesk | Helpdesk (Contact Center) | OPEN | [6 empty] | 1 | Open | Open
792 | M136 | MOM | 2023-08-23 |  |  |  | BSS | Notification Template | comprehensive list of event notification scenarios and implementation plan. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
793 | M137 | MOM | 2023-08-23 |  |  |  | BSS | Improvement | Complete User Group creation |  | Critical | Closed | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN | [6 empty] | 1 | Open | Open
794 | M138 | MOM | 2023-08-23 |  |  |  | BSS | Improvement | customizable columns |  | Critical | Closed | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN | [6 empty] | 1 | Open | Open
795 | M139 | MOM | 2023-08-23 |  |  |  | BSS | Dashboards | Summary of Leads |  | NON-Critical | Closed | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN | [6 empty] | 1 | Open | Open
796 | M14 | MOM | 2023-04-16 |  | OSS | OSS | OSS | Full NOC Readiness | Secretary, DoT enquired to show the MTTR through against individual TT in the OSS |  | Critical | Open |  | OSS Dashboards | [5 empty] | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMOSS | Applications/Tools | OPEN | CLOSURE REVIEW PENDING | 0 |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
797 | M140 | MOM | 2023-08-23 |  |  |  | BSS | Improvement | Advance Search options |  | NON-Critical | Open |  |  |  |  | It is available OOB |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN | [6 empty] | 1 | Open | Open
798 | M141 | MOM | 2023-08-23 |  |  |  | BSS | Resource Related | Structure & Composition of Service Delivery group |  | NON-Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
799 | M142 | MOM | 2023-08-23 |  |  |  | BSS | Resource Related | Roles & Responsibility of Service Delivery group |  | NON-Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
800 | M143 | MOM | 2023-08-23 |  |  |  | BSS | User Experience | Notification with status changes from Opportunity - RFO - RFS – Order |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
801 | M144 | MOM | 2023-08-23 |  |  |  | BSS | Handbook & SOPs | Process for Data Integrity of Bulk upload |  | NON-Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
802 | M145 | MOM | 2023-08-23 |  | OSS | OSS | OSS | Manual Feasibility Plan | Plan for manual feasibility in the OSS |  | NON-Critical | Open | [7 empty] | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMOSS | Applications/Tools | OPEN | CLOSURE REVIEW PENDING | 0 |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
803 | M146 | MOM | 2023-08-23 |  |  |  | BSS | Dashboards | Summary before Feasibility Result |  | NON-Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
804 | M147 | MOM | 2023-08-23 |  |  |  | BSS | Manual Feasibility Plan | Order Fulfilment - Exception Scenarios |  | NON-Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
805 | M148 | MOM | 2023-08-23 |  |  |  | BSS | Action points | Ensure that site editing is restricted |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
806 | M149 | MOM | 2023-08-23 |  |  |  | BSS | Data Upload | Entire network POI/ PoP status, including 12751 GPs, 1 NOC, all zones, districts & Mandal nodes, is available in the CRM database |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
807 | M15 | MOM | 2023-04-16 |  | OSS | OSS | OSS | Full NOC Readiness | Secretary, DoT advised to show more KPIs, Video wall extension is required |  | Critical | Open |  | OSS Dashboards | [5 empty] | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMOSS | Applications/Tools | OPEN | COMPLETED | All power BI dashboards, SM MTTR Dashboards |  |  | #N/A |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
808 | M150 | MOM | 2023-08-23 |  |  |  | BSS | CSP User Experience | Telugu Subtitles in CSP |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
809 | M151 | MOM | 2023-08-23 |  |  |  | BSS | CSP User Experience | Google Location Pickup |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
810 | M152 | MOM | 2023-08-23 |  |  |  | BSS | CSP User Experience | Lat/Long coordinates and LGD codes should be removed from the search bar. |  | Critical | Closed | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN | [6 empty] | 1 | Open | Open
811 | M153 | MOM | 2023-08-23 |  |  |  | BSS | CSP User Experience | Check Residential" should be changed with a more appropriate term. |  | NON-Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
812 | M154 | MOM | 2023-08-23 |  |  |  | BSS | CSP User Experience | Introduce a "Thank You" page after a lead is submitted, displaying the lead number. This lead number could be useful for Helpdesk also. |  | NON-Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
813 | M155 | MOM | 2023-08-23 |  |  |  | BSS | CSP User Experience | The term "External" should be replaced with "Internal." |  | NON-Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
814 | M156 | MOM | 2023-08-23 |  |  |  | BSS | CSP User Experience | "Value-Add Partners" Tab |  | NON-Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
815 | M157 | MOM | 2023-08-23 |  |  |  | BSS | CSP User Experience | Landing Page Content |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
816 | M158 | MOM | 2023-08-23 |  |  |  | BSS | CSP User Experience | The term "Last Miles" should be changed to "Partners. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
817 | M159 | MOM | 2023-08-23 |  |  |  | BSS | CSP User Experience | The "Government/Cell Tower/Enterprise" tab should have a dropdown for various services & information. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
818 | M16 | MOM | 2023-04-19 |  |  |  | GIS | Functional AT Plan | Loading Sample Data and Internal Quality Test Report Submission |  | NON-Critical | Open |  | OSS Dashboards | [5 empty] | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMGIS | Applications/Tools | OPEN | [6 empty] | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
819 | M160 | MOM | 2023-08-23 |  |  |  | BSS | CSP User Experience | Chatbot Feature |  | NON-Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
820 | M161 | MOM | 2023-08-23 |  |  |  | BSS | CSP User Experience | Leads Summary for B2B Partner |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
821 | M162 | MOM | 2023-08-31 |  |  |  | BSS | User Experience | CRM should be in IST Times |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
822 | M163 | MOM | 2023-08-31 |  |  |  | BSS | User Experience | User Group training for administrator to Add/Modify the user access in CSP and CRM |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
823 | M164 | MOM | 2023-08-31 |  |  |  | BSS | Billing Related | SSL Certificate implementation |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
824 | M165 | MOM | 2023-08-31 |  |  |  | BSS | User Experience | Corporate Number for WhatsApp |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
825 | M166 | MOM | 2023-09-08 |  |  |  | BSS | Handbook & SOPs | Order Fulfilment Process |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
826 | M167 | MOM | 2023-09-08 |  |  |  | BSS | Handbook & SOPs | Service Delivery Process |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
827 | M168 | MOM | 2023-09-08 |  |  |  | BSS | Handbook & SOPs | Service Delivery Team Resource and responsibilities & relationship with other packages |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
828 | M169 | MOM | 2023-09-08 |  |  |  | BSS | Handbook & SOPs | Clearly define user system mapping with specific process steps with documentation for clarity |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
829 | M17 | MOM | 2023-05-18 |  |  |  | GIS | Functional AT Plan | Basic GIS Tool UAT for TPA |  | Critical | Open |  | OSS Dashboards |  |  | The ATP was submitted, discussed with the TPA, and all feedback was incorporated. The revised ATP has also been sent |  |  | Kaushalendra Kumar |  | Open | Open | [9 empty] | MOMGIS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
830 | M170 | MOM | 2023-09-08 |  |  |  | Helpdesk | User Experience | Change in IVRS Welcome Message |  | Critical | open |  |  |  | Closed | 24-Sep-25: Approved and shall be closed 11-Sep-25: Changed and operational Now |  |  | Siva Kumar |  |  | COMPLETED & APPROVED | [9 empty] | MOMHelpdesk | Helpdesk (Contact Center) | CLOSED |  |  |  | 2025-09-24 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\M121,170,99,726 |  | 1 | Completed & Approved | Closed after June
831 | M171 | MOM | 2023-09-08 |  |  |  | Helpdesk | Resource Related | Other package involvement |  | Critical | open |  |  |  | Closed | 24-Sep-25: Artefacts to be submitted 11-Sep-25: Clarified as its only L&T Manpower |  |  | Siva Kumar |  |  | COMPLETED & APPROVED | [9 empty] | MOMHelpdesk | Helpdesk (Contact Center) | CLOSED |  |  |  | 2025-09-24 | Artefacts Need to upload |  | 1 | Completed & Approved | Closed after June
832 | M172 | MOM | 2023-09-12 | P3 |  |  | NOC Operationalization | Handbook & SOPs | SOPs Submission |  | Critical | Closed |  |  |  |  | Agreed SOPs are submitted and agreed with TFiber |  |  | Ahmad | 2025-09-20 |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  | Documentation | 2025-09-24 | \\172.28.9.23\tnocreports\Approved Process and SOP_ T Fiber\SOP |  | 1 | Completed & Approved | Closed before june-2025
833 | M173 | MOM | 2023-09-12 |  |  |  | NOC Operationalization | OEM's Details | Submit details on OEM alignment, warranty, AMC, and engagement status for go-live and post-go-live phases, location-wise & application-wise, to Director-Contracts, T-Fiber |  | Critical | Open | [7 empty] | Ahmad |  | Open | Open | [9 empty] | MOMNOC Operationalization | Network | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
834 | M174 | MOM | 2023-09-12 |  |  |  | Helpdesk | Improvement | Streamlining of Helpdesk and Ticketing system |  | Critical | open |  |  |  | WIP | 11-Sep-25: Same has been Submitted |  |  | Siva Kumar |  | Open | WIP | [9 empty] | MOMHelpdesk | Helpdesk (Contact Center) | OPEN | [6 empty] | 1 | Open | Open
835 | M175 | MOM | 2023-09-12 | P3 |  |  | NOC Operationalization | Dashboards | Dashboards for each element of the Video Wall, specifying manual or automatic clarity |  | Critical | Completed |  |  |  |  | Curently Video wall is displaying dashboards as per agreement with TFiber |  |  | Ahmad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  | Covered in OSS | 2025-09-19 | Artefacts not Required |  | 1 | Completed & Approved | Closed after June
836 | M176 | MOM | 2023-09-12 | P3 |  |  | NOC Operationalization | Resource Related | T-NOC Resource details and deployment with Roles and Responsibilities |  | Critical | Completed |  |  |  |  | TNOC resource is deployed as per RFP. Manpower report is shared on weekly basis. |  |  | Ahmad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  | Not related to delivery | 2025-09-24 | \\172.28.9.23\tnocreports\TNOC Manpower_CVs\NOC Resources Details & Roles |  | 1 | Completed & Approved | Closed after June
837 | M177 | MOM | 2023-09-12 |  |  |  | Security & Regulatory Compliance | Patch update | Engagements with vendors for Patch Delivery and Testing |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
838 | M178 | MOM | 2023-09-12 |  |  |  | NOC Operationalization | Dashboards | SLA Monitoring and Network Performance Statistics |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMNOC Operationalization | Network | OPEN | [6 empty] | 1 | Open | Open
839 | M179 | MOM | 2023-09-12 |  |  |  | NOC Operationalization | O&M Strategy | Spares Management |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMNOC Operationalization | Network | OPEN | [6 empty] | 1 | Open | Open
840 | M18 | MOM | 2023-05-18 |  | OSS | OSS | OSS | Integration | IP MPLS auto trouble tickets |  | Critical | Open |  | OSS Dashboards |  |  | 09-09-2025: Stabilization needed |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMOSS | Applications/Tools | OPEN | COMPLETED | 09-09-2025: Stabilization needed |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
841 | M180 | MOM | 2023-09-12 |  |  |  | NOC Operationalization | O&M Strategy | Repair and Replacement process |  | Critical | Completed |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1 | Completed & Approved | Closed after June
842 | M181 | MOM | 2023-09-12 |  |  |  | BSS | Dynamic Feature | Overall capability to support the creation of innovative new products and seamless customer experience |  | NON-Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
843 | M182 | MOM | 2023-09-22 |  |  |  | NSO | Service provisioning | NSO provisioning is happening through EMS and asked for the list of provisioning/monitoring features being limited or constrained due to any interoperability issues in a multi-vendor eco-system. |  | Critical | Open | [7 empty] | Jayant Madavi |  | Open | Open | [9 empty] | MOMNSO | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
844 | M183 | MOM | 2023-09-22 |  | OSS | OSS | OSS | Service provisioning | Role of OSS in Service Provisioning |  | Critical | Open | [7 empty] | Suresh Pawar |  | Open | WIP | [9 empty] | MOMOSS | Applications/Tools | OPEN | OPEN | 0 |  |  | #N/A |  | 1 | Open | Open
845 | M184 | MOM | 2023-09-22 |  |  |  | NOC Operationalization | O&M Strategy | Redundancy Plan for NSO and OSS |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMNOC Operationalization | Network | OPEN | [6 empty] | 1 | Open | Open
846 | M185 | MOM | 2023-09-22 |  |  |  | NOC Operationalization | O&M Strategy | Limitations in OSS and NSO Scalability for post go live |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMNOC Operationalization | Network | OPEN | [6 empty] | 1 | Open | Open
847 | M186 | MOM | 2023-09-22 |  |  |  | BSS | Dynamic Feature | Enhance BSS to allow flexibility in creating, modifying, adding, and deleting product categories |  | NON-Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
848 | M187 | MOM | 2023-09-22 |  |  |  | NSO | Handbook & SOPs | Train in-house L&T resources in NSO and NEDs for reduced dependency on Cisco. |  | Critical | Open | [7 empty] | Jayant Madavi |  | Open | Open | [9 empty] | MOMNSO | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
849 | M188 | MOM | 2023-09-22 |  |  |  | BSS | Notification Template | Notification Template Flexibility |  | NON-Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
850 | M189 | MOM | 2023-09-22 |  |  |  | BSS | Notification Template | CP to be changed to CP-TFGCLT |  | NON-Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
851 | M19 | MOM | 2023-05-18 |  |  |  | BSS | Resource Related | Inter-Dependence Matrix and Resource Identification |  | Critical | Open |  | OSS Dashboards | [5 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
852 | M190 | MOM | 2023-09-22 |  |  |  | BSS | CSP User Experience | Ensure that only the logos of the Government of Telangana and T-Fiber are used in the CSP. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
853 | M191 | MOM | 2023-09-22 |  |  |  | BSS | Billing Related | CAF detailed analysis related to TRAI |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
854 | M192 | MOM | 2023-09-22 |  |  |  | BSS | CSP User Experience | Clearly mention on the Landing Page that services are currently extended only for Rural Telangana; Capture and store leads for requests from Urban Telangana. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
855 | M193 | MOM | 2023-09-22 |  |  |  | BSS | CSP User Experience | User guides such as "May I help you", Chatbots, Videos |  | NON-Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
856 | M194 | MOM | 2023-09-22 |  |  |  | BSS | CSP User Experience | Definitions of terminologies to be available on mouseover |  | NON-Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
857 | M195 | MOM | 2023-09-22 |  |  |  | DR | O&M Strategy | a brief note on what is required to be delivered by CtrlS for DR |  | NON-Critical | Open |  |  |  |  | Work in progress |  |  | Ravi Kishore |  | Open | Open | [9 empty] | MOMDR | DR | OPEN | [6 empty] | 1 | Open | Open
858 | M196 | MOM | 2023-09-22 |  |  |  | DR | Functional AT Plan | Share the test results of DR systems with T-Fiber. |  | NON-Critical | Open |  |  |  |  | Work in progress |  |  | Ravi Kishore |  | Open | Open | [9 empty] | MOMDR | DR | OPEN | [6 empty] | 1 | Open | Open
859 | M197 | MOM | 2023-09-22 |  |  |  | BSS | Integration | WFM-SMS Gateway integration |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
860 | M198 | MOM | 2023-09-22 |  |  |  | BSS | CSP User Experience | L&T, to update the Landing Page to cater to all specified segments such as Pin code, Address, Lat-Long, or address pulling from Google API is required |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
861 | M199 | MOM | 2023-09-22 |  |  |  | BSS | Notification Template | Replace "Re-confirm" with "View" in the notification template. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
862 | M2 | MOM | 2023-02-06 | P3 |  |  | NOC Operationalization | Handbook & SOPs | T-Fiber requested the inclusion of Protocol Manager and Regulatory roles in the TNOC organization chart. Also, emphasized clear demarcation and mapping of resources with names, roles, and responsibilities |  | Critical | Completed |  | OSS Dashboards |  |  | NOC resources details is shared on weekly basis. Roles of NOC is as per RFP. |  |  | Ahmad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  | Not related to delivery | 2025-09-19 | Artefacts not Required |  | 1 | Completed & Approved | Closed after June
863 | M20 | MOM | 2023-05-18 |  |  |  | BSS | Full NOC Readiness | Roadmap for Network Service Order Fulfilment and Service Assurance |  | Critical | Open |  | OSS Dashboards | [5 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
864 | M200 | MOM | 2023-09-22 |  |  |  | BSS | Notification Template | Ensure that SMS includes a link to the CSP. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
865 | M201 | MOM | 2023-09-22 |  |  |  | BSS | Functional AT Plan | Perform testing of negative scenarios to identify and address any issues or vulnerabilities |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
866 | M202 | MOM | 2023-09-22 |  |  |  | BSS | CSP User Experience | Validate all mandatory fields and associated asterisks to ensure completeness and accuracy of data entry |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
867 | M203 | MOM | 2023-09-22 |  |  |  | BSS | Billing Related | Establish a mechanism to confirm the synchronization between the current account and the payment portal. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
868 | M204 | MOM | 2023-09-22 |  |  |  | BSS | CSP User Experience | Display Progress in CSP Post-Order |  | NON-Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
869 | M205 | MOM | 2023-09-22 |  |  |  | BSS | CSP User Experience | User-Friendly Product Naming |  | NON-Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
870 | M206 | MOM | 2023-09-22 |  |  |  | BSS | Action points | Address and resolve issues related to using the backspace key on the webpage, ensuring smooth navigation to the previous page. |  | NON-Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
871 | M207 | MOM | 2023-09-22 |  |  |  | BSS | Billing Related | Payments and policies : BSS billing module should have various frameworks of full payment, part payment, advance payment, based on customer credit worthiness , based on discount policy etc. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
872 | M208 | MOM | 2023-09-22 |  |  |  | BSS | CSP User Experience | Time Duration of OTP need to be fixed with timer |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
873 | M209 | MOM | 2023-09-22 |  |  |  | BSS | CSP User Experience | Implement 'Request to Re-send OTP' |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
874 | M21 | MOM | 2023-06-01 |  |  |  | GIS | User Experience | Google Map availability in Geo Media Tool with real time navigation |  | Critical | Open |  | OSS Dashboards |  |  | Google Map availability in Geo Media Tool, Hexagon clarified that Google Map feature is not available in Geo Media as it is a client based independent tool which can be installed in client PCs; however, end users can use OSM and/or Bing maps along with Geo media |  |  | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMGIS | Applications/Tools | OPEN | [6 empty] | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
875 | M210 | MOM | 2023-09-22 |  |  |  | BSS | Billing Related | Implement a system to generate a revised Proforma Invoice with the latest date if the ordering process is stopped and resumed. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
876 | M211 | MOM | 2023-09-22 |  |  |  | BSS | CSP User Experience | Configure the CSP portal to display only orders relevant to the specific customer, enhancing user experience and clarity. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
877 | M212 | MOM | 2023-09-22 |  |  |  | BSS | Service provisioning | Reservation of Bandwidth at Provisioning |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
878 | M213 | MOM | 2023-09-22 |  |  |  | BSS | CSP User Experience | Customer Care should in bold |  | NON-Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
879 | M214 | MOM | 2023-09-22 |  |  |  | BSS | Billing Related | Align Order Confirmation with Payment Receipt |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
880 | M215 | MOM | 2023-09-22 |  |  |  | BSS | Improvement | Improve 'Pick Order' Button and Placeholder |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
881 | M216 | MOM | 2023-09-22 |  |  |  | BSS | Billing Related | Implement Alerts for CAF Approval and Payment |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
882 | M217 | MOM | 2023-09-22 |  |  |  | BSS | Improvement | Customer Dashboards with visible website name for branding |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
883 | M218 | MOM | 2023-09-22 |  |  |  | BSS | User Experience | Make Site ID More Relevant for Order Selection |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
884 | M219 | MOM | 2023-09-22 |  |  |  | BSS | Improvement | Display Opportunity ID and Order ID Differently columns |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
885 | M22 | MOM | 2023-06-01 |  |  |  | GIS | User Experience | Fixed Topology Nomenclature |  | Critical | Open |  | OSS Dashboards | [5 empty] | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMGIS | Applications/Tools | OPEN | [6 empty] | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
886 | M220 | MOM | 2023-09-22 |  |  |  | BSS | Action points | Address Missing Scroll Bar in Some Pages |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
887 | M221 | MOM | 2023-09-22 |  |  |  | BSS | Billing Related | Incorporate a partial payment option for larger or priority accounts, allowing T-Fiber to decide on a case-by-case basis, along with an approval matrix. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
888 | M222 | MOM | 2023-09-22 |  |  |  | BSS | Action points | Rectify the issue with the 'Show Password' option to ensure its proper functionality |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
889 | M223 | MOM | 2023-09-22 |  |  |  | BSS | Billing Related | Mandate the selection of the payment window (half-yearly or annually) during the ordering process, making it clear to the customer, rather than defaulting to monthly. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
890 | M224 | MOM | 2023-09-22 |  |  |  | BSS | Improvement | Modify the order submission process to collect secondary phone numbers and email IDs, as required. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
891 | M225 | MOM | 2023-09-22 |  |  |  | BSS | Billing Related | Implement a restriction to prevent order placement without the completion of payment, ensuring a secure and controlled ordering process. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
892 | M226 | MOM | 2023-09-22 |  |  |  | BSS | Improvement | Standardize colour coding across all UX/UI elements for consistency and a unified visual experience. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
893 | M227 | MOM | 2023-09-22 |  |  |  | BSS | Improvement | Allow users to refresh and continue after prolonged inactivity, enhancing the user experience and preventing disruptions |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
894 | M228 | MOM | 2023-09-22 |  |  |  | BSS | Improvement | Welcome Message Placement |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
895 | M229 | MOM | 2023-09-22 |  |  |  | BSS | Improvement | Introduce a flashing indicator for orders to attract attention and improve visibility. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
896 | M23 | MOM | 2023-06-01 |  |  |  | GIS | User Experience | Character size in G-Tech |  | Critical | Open |  | OSS Dashboards | [5 empty] | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMGIS | Applications/Tools | OPEN | [6 empty] | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
897 | M230 | MOM | 2023-09-22 |  |  |  | BSS | User Experience | Add a visual indication for users to select the service under the Create Order page. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
898 | M231 | MOM | 2023-09-22 |  |  |  | BSS | Action points | Investigate and address the issue where no details are displayed upon clicking on "Customer Premises Equipment." |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
899 | M232 | MOM | 2023-09-22 |  |  |  | BSS | Improvement | Rephrase the error message that appears when clicking on the Remove button under Create Order Step 3 for better clarity. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
900 | M233 | MOM | 2023-09-22 |  |  |  | BSS | Improvement | Display Recurring Charge Frequency in Order Summary |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
901 | M234 | MOM | 2023-09-22 |  |  |  | BSS | User Experience | Display Instructions for CAF Download |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
902 | M235 | MOM | 2023-09-22 |  |  |  | BSS | User Experience | Indicate File Type and Size at Confirmation Stage |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
903 | M236 | MOM | 2023-09-22 |  |  |  | BSS | User Experience | Implement Preview Option for Uploaded Documents |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
904 | M237 | MOM | 2023-09-22 |  |  |  | BSS | Improvement | Emphasize the purpose of the "Edit Proceed" button for user understanding and clarity. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
905 | M238 | MOM | 2023-09-22 |  |  |  | BSS | Action points | Resolve Issues with "Edit Proceed" Button |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
906 | M239 | MOM | 2023-09-22 |  |  |  | BSS | Improvement | Digitally Sign Proforma Invoice |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
907 | M24 | MOM | 2023-06-01 |  |  |  | GIS | User Experience | Searching for location accuracy in G-Tech with pinpoint accuracy |  | Critical | Open |  | OSS Dashboards | [5 empty] | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMGIS | Applications/Tools | OPEN | [6 empty] | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
908 | M240 | MOM | 2023-09-26 |  |  |  | NOC Operationalization | Handbook & SOPs | Provide clarification on the status of HOTO (Handover to Operations) and Knowledge Transfer. |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1 | Completed & Approved | Closed after June
909 | M241 | MOM | 2023-09-26 |  |  |  | NOC Operationalization | Functional AT Plan | Systems functional Acceptance Tests Plan yet |  | Critical | Completed |  |  |  | WIP | FAT documents shared, Tracker & updates are sent on periodic basis | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMNOC Operationalization | Network | OPEN | [6 empty] | 1 | Open | Open
910 | M242 | MOM | 2023-09-26 |  |  |  | NOC Operationalization | Full NOC Readiness | Launch Road Map |  | Critical | Completed |  |  |  | WIP | 12 NOC points, 472 Tracker is being tracked with timelines and updates / reiew happening on regular basis | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMNOC Operationalization | Network | OPEN | [6 empty] | 1 | Open | Open
911 | M243 | MOM | 2023-09-26 |  |  |  | T&D Environment | T&D Environment | Provide details on the completion status of test and development of systems. |  | NON-Critical | Open |  |  |  |  | [15/09/25] Test Environment is actively used for T&D by Delivery and OEM teams. NOC submission provided in Tfiber has the T&D application from Oct-Mar2025 |  |  | Ravi Kishore |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMT&D Environment | Applications | OPEN |  |  |  |  | #N/A |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
912 | M244 | MOM | 2023-09-26 |  |  |  | NOC Operationalization | Full NOC Readiness | Provide assurance that comprehensive solutions and designs will be within the specified list, considering anything beyond as a change request. |  | Critical | Open |  |  |  | Will be discussed later | 23-Sep-25: NON Critical to be reviewd later | L&T | Sivaprasad | Sivaprasad |  | Open | Open | [9 empty] | MOMNOC Operationalization | Network | OPEN | [6 empty] | 1 | Open | Open
913 | M245 | MOM | 2023-09-26 |  |  |  | WFM | WFM Application | Clarify the distinction between smart app and WFM. |  | Critical | Open | [7 empty] | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMWFM | Applications/Tools | OPEN | [6 empty] | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
914 | M246 | MOM | 2023-09-26 |  |  |  | NSO | Service provisioning | IP Pool analysis with clearly define the ownership structure of IPs, specifying whether it's co-ownership or complete ownership by the OEM. |  | NON-Critical | Open | [7 empty] | Jayant Madavi |  | Open | Open | [9 empty] | MOMNSO | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
915 | M247 | MOM | 2023-09-26 |  |  |  | T&D Environment | T&D Environment | Clarify constraints related to infra upgradation for testing & development. |  | NON-Critical | Open |  |  |  |  | 11-Oct-25: Need to list out requirement of T&D for all Domains. [15/09/25] It was decided to setup T&D using existing infra in DC in the interim |  |  | Ravi Kishore |  | Open | WIP | [9 empty] | MOMT&D Environment | Applications | OPEN | [6 empty] | 1 | Open | Open
916 | M248 | MOM | 2023-09-26 |  |  |  | NOC Operationalization | Full NOC Readiness | Consider RFP, technical bid, and solutions for understanding the requirements of a staging system after go-live. |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMNOC Operationalization | Network | OPEN | [6 empty] | 1 | Open | Open
917 | M249 | MOM | 2023-09-26 |  |  |  | NOC Operationalization | OEM's Details | Provide all OEMs' test cases & certificates for T-Fiber network testing |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMNOC Operationalization | Network | OPEN | [6 empty] | 1 | Open | Open
918 | M25 | MOM | 2023-06-01 |  |  |  | GIS | User Experience | Self-address auto-population in G-Tech |  | Critical | Open |  | OSS Dashboards |  |  | Duplicate with Point- 80 |  |  | Kaushalendra Kumar |  | Open | Duplicate | [9 empty] | MOMGIS | Applications/Tools | #N/A |  |  |  |  | #N/A |  | 1 | Open | Open
919 | M250 | MOM | 2023-10-11 |  |  |  | NOC Operationalization | Full NOC Readiness | Full NOC to be ready by 10th Nov'23 |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1 | Completed & Approved | Closed after June
920 | M251 | MOM | 2023-10-11 |  |  |  | BSS | Resource Related | BSS Expert onboarding |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
921 | M252 | MOM | 2023-10-11 |  |  |  | Security & Regulatory Compliance | Functional AT Plan | Share scope and test plans of the External Audit. |  | Critical | Open |  |  |  |  | External audit is done by 3rd party broughtin by TFiber |  |  | Sarmendra |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | Artefacts to be Submitted |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
922 | M253 | MOM | 2023-10-11 |  |  |  | Security & Regulatory Compliance | Physical Execution | Physical User access : Button is used for exit and still L&T have to finalise vendor |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
923 | M254 | MOM | 2023-10-11 |  |  |  | Security & Regulatory Compliance | Dashboards | QoS reporting- Breakdown between automated and manual aspects |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
924 | M255 | MOM | 2023-10-18 |  |  |  | BSS | CSP User Experience | Back Button to be available in the Payment Screen. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
925 | M256 | MOM | 2023-10-18 |  |  |  | BSS | CSP User Experience | Guidelines to be available to the user in the CAF upload stage, what to upload in CAF upload stage is not clear. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
926 | M257 | MOM | 2023-10-18 |  |  |  | BSS | CSP User Experience | Add a disclaimer for “Subject to Verification of CAF”, with notification trigger |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
927 | M258 | MOM | 2023-10-18 |  |  |  | BSS | CSP User Experience | Unable to view offline payment transactions uploaded |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
928 | M259 | MOM | 2023-10-18 |  |  |  | BSS | CSP User Experience | Mandatory sections of the CAF to be highlighted. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
929 | M26 | MOM | 2023-06-01 |  |  |  | GIS | User Experience | GPON Fiber Termination plan adherence |  | Critical | Open |  | Gtech | [5 empty] | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMGIS | Applications/Tools | OPEN | [6 empty] | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
930 | M260 | MOM | 2023-10-18 |  |  |  | BSS | CSP User Experience | Notifications for ticket via SMS and Email not received. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
931 | M261 | MOM | 2023-10-18 |  |  |  | BSS | CSP User Experience | Received a Pop-up for incorrect entry of OTP despite entering the correct OTP |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
932 | M262 | MOM | 2023-10-18 |  |  |  | BSS | CSP User Experience | Raised single ticket in CSP, however 3 distinct tickets are visible in CSP with same narration of issue, notification or alerts not received for any of these tickets. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
933 | M263 | MOM | 2023-10-18 |  |  |  | BSS | CSP User Experience | tickets raised are visible at the department level only, is this possible to be made available Departmental user wise? |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
934 | M264 | MOM | 2023-10-18 |  |  |  | BSS | CSP User Experience | Searching by Order ID is case sensitive. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
935 | M265 | MOM | 2023-10-18 |  |  |  | BSS | CSP User Experience | Receiving the “Pending Feasibility” confirmation message, then receiving result as “Feasible” |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
936 | M266 | MOM | 2023-10-18 |  |  |  | BSS | CSP User Experience | How does BSS handle dismantled GPs if there is no real-time sync between GIS-OSS |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
937 | M267 | MOM | 2023-10-18 |  |  |  | BSS | CSP User Experience | Cygnet product name showing in the top of the tab, to be removed. |  | NON-Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
938 | M268 | MOM | 2023-10-18 |  |  |  | BSS | CSP User Experience | GP names are not aligned to government list |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
939 | M269 | MOM | 2023-10-18 |  |  |  | BSS | CSP User Experience | Plot number to be renamed as Plot / House no |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
940 | M27 | MOM | 2023-06-07 |  |  |  | GIS | Handbook & SOPs | Approval mechanism for object changes/deletion |  | Critical | Open |  | Gtech |  |  | Duplicate with Point- 81 |  |  | Kaushalendra Kumar |  | Open | Duplicate | [9 empty] | MOMGIS | Applications/Tools | #N/A |  |  |  |  | #N/A |  | 1 | Open | Open
941 | M270 | MOM | 2023-10-18 |  |  |  | BSS | CSP User Experience | In case of Manual Provisioning, is there a stage for Validation? |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
942 | M271 | MOM | 2023-10-18 |  |  |  | BSS | CSP User Experience | Unable to enter the OTP, Unable to close the Pop-up window for OTP, require either a “Close” button OR closing the Pop-up should be allowed by clicking outside the Pop-up. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
943 | M272 | MOM | 2023-10-18 |  |  |  | BSS | CSP User Experience | Unable to go back to Home Screen |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
944 | M273 | MOM | 2023-10-18 |  |  |  | BSS | CSP User Experience | In Landing Page, number of GPs is mentioned as 12,751, this number to be validated. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
945 | M274 | MOM | 2023-10-18 |  |  |  | BSS | CSP User Experience | Back Button required in Create Order and Order Summary screens |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
946 | M275 | MOM | 2023-10-18 |  |  |  | BSS | CSP User Experience | What is the purpose of displaying segment as G2G in CAF ? |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
947 | M276 | MOM | 2023-10-18 |  |  |  | BSS | CSP User Experience | How does a GI customer know the Site ID to be entered. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
948 | M277 | MOM | 2023-10-18 |  |  |  | BSS | CSP User Experience | Payment is showing as Net banking for all transactions, including offline transactions. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
949 | M278 | MOM | 2023-10-18 |  |  |  | BSS | CSP User Experience | Unable to see Order Summary just before Payment. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
950 | M279 | MOM | 2023-10-18 |  |  |  | BSS | CSP User Experience | Notification of Success / Failure to be available on Order Submission. |  | NON-Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
951 | M28 | MOM | 2023-06-07 |  |  |  | GIS | Handbook & SOPs | Change Management Log/User Log history |  | Critical | Open |  | Gtech |  |  | Duplicate with Point- 82 |  |  | Kaushalendra Kumar |  | Open | Duplicate | [9 empty] | MOMGIS | Applications/Tools | #N/A |  |  |  |  | #N/A |  | 1 | Open | Open
952 | M280 | MOM | 2023-10-18 |  |  |  | BSS | CSP User Experience | In Payment Screen, add a disclaimer that “Payment details are subject to verification for offline payments” to cover for the scenario of wrong / incorrect Payment ID provided by the user. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
953 | M281 | MOM | 2023-10-18 |  |  |  | BSS | CSP User Experience | Is a location added in CSP visible in the CRM as a lead? |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
954 | M282 | MOM | 2023-10-18 |  |  |  | BSS | CSP User Experience | While adding a new location using the map, searching by name is working (example- Jagtial), however searching by Lat-Long is not working. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
955 | M283 | MOM | 2023-10-18 |  |  |  | BSS | CSP User Experience | Added a location, but GP name is not getting populated, how is this address added in the CRM, received a pop-up alert for location confirmation, but this location is not added to the list. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
956 | M284 | MOM | 2023-10-18 |  |  |  | BSS | CSP User Experience | Product Selection screen did not display “Last Mile Connectivity” with no view to scroll right, either restrict the size of the location name or display all columns in a single page. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
957 | M285 | MOM | 2023-10-18 |  |  |  | BSS | CSP User Experience | Email notifications not being triggered for a few actions where events are not configured |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
958 | M286 | MOM | 2023-10-18 |  |  |  | BSS | CSP User Experience | Received order confirmation, but no notifications received for payment, no notification on save order. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
959 | M287 | MOM | 2023-10-18 |  |  |  | BSS | CSP User Experience | What is the Transaction number? |  | NON-Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
960 | M288 | MOM | 2023-10-18 |  |  |  | BSS | CSP User Experience | While adding a new address, selected a gram panchayat, changed Lat-Long, provided address details, successfully added these details, but the address for GP name is not seen, to be shown. |  | NON-Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
961 | M289 | MOM | 2023-10-19 |  |  |  | NOC Operationalization | Interim NOC | Provide a list of points that need to be available for the Network Launch targeted for November 30th, 2023. Identify the points that will be included in the roadmap and specify the timelines for their implementation |  | Critical | Completed |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1 | Completed & Approved | Closed after June
962 | M29 | MOM | 2023-06-07 |  |  |  | GIS | Handbook & SOPs | Data Validation Rules document |  | Critical | Open |  | Gtech | [5 empty] | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMGIS | Applications/Tools | OPEN | [6 empty] | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
963 | M290 | MOM | 2023-10-19 |  |  |  | NOC Operationalization | Interim NOC | explain their approach for handling Operations and Maintenance (O&M) to meet the SLAs (Service Level Agreements) and provide process documents for features that are currently unavailable. |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1 | Completed & Approved | Closed after June
964 | M291 | MOM | 2023-10-19 |  |  |  | NOC Operationalization | Interim NOC | To clarify how they plan to transition the O&M responsibilities and data once the currently unavailable features are made available. |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1 | Completed & Approved | Closed after June
965 | M292 | MOM | 2023-10-19 |  |  |  | NOC Operationalization | Interim NOC | Evidence from L&T on the timelines for fulfilling the feature gaps |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1 | Completed & Approved | Closed after June
966 | M293 | MOM | 2023-10-19 |  |  |  | BSS | GeM Integration | GeM integration with BSS: the point may be deferred for 6 months, with timeline to be added by L&T for next review, L&T to issue a Note (Note 1) recording this statement. |  | NON-Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
967 | M294 | MOM | 2023-10-19 |  |  |  | GPON | Interim NOC | Request a Note (Note 2) from L&T addressing the impact of the unavailability of NBI API availability for BW query Dependent on new OLT build for GI deployment and how NOC operations will be managed in the interim period until the required features are developed and integrated with seamless transition. |  | Critical | Open |  | Nokia OEM | AMS |  | Duplicate point of 472 - T175 | Duplicate |  | Sayyad Pasha |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | MOMGPON | GPON | OPEN |  |  | Duplicate |  | #VALUE! |  | 1 | Open | Open
968 | M295 | MOM | 2023-10-19 |  |  |  | GPON | Integration | Point No. 175: CR for Nokia API integration to resolve BW query and PMS-related issues. 1. Note 2 should also cover Point No. 175. 2. Set a target completion date of November 20th '23 for this activity. |  | Critical | Open |  | Nokia OEM | AMS |  | Duplicate point of 472 - T175 | Duplicate |  | Sayyad Pasha |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | MOMGPON | GPON | OPEN |  |  | Duplicate |  | #N/A |  | 1 | Open | Open
969 | M296 | MOM | 2023-10-19 |  |  |  | GPON | Upgradation | Point No. 179: Troubleshooting required with Tejas and Nokia for Tejas ONT firmware upgrade issue. 1. Technical Head from L&T to seek support from L&T-Contracts team and aim for implementation within 15-20 days from the resolution of the issue. 2. L&T to submit the agreed Scope between L&T and NOC OEMs (primarily OSS, BSS, NSO) by October 24th '23. 3.Request a Note (Note 3) outlining the interim/final solution and an undertaking co-signed by Package Owners to be submitted by October 26th '23. 4.Target completion of Point No. 179 by November 20th '23. |  | Critical | Open | [7 empty] | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T179 | [6 empty] | MOMGPON | GPON | CLOSED |  |  |  | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T179 |  | 1 | Completed & Approved | Closed after June
970 | M297 | MOM | 2023-10-19 |  |  |  | GPON | Upgradation | Point No. 180: Nokia ONT to support NAT, DHCP in both Router and Bridge modes. 1. Instruct L&T to identify the number of ONTs in the warehouse and send them to the Nokia Warehouse immediately for upgrade. 2. Coordinate with Package B&C for similar actions. 3.Note 4 on the mitigation and deployment plan for remediation, along with the timelines, testing to be part of the method of deployment. |  | Critical | Open |  | Nokia OEM | ONT |  | Duplicate point of 472 - T180 | Duplicate |  | Sayyad Pasha |  | Open | Duplicate | [9 empty] | MOMGPON | GPON | CLOSED |  |  | Duplicate |  | Artefacts not Required |  | 1 | Open | Open
971 | M298 | MOM | 2023-10-19 |  |  |  | IP/MPLS | Service Solution | Point No. 186: IPTV to Household ,Point No. 190: CCTV Multicast ,Point No. 193: SDC content to Household and GI ,Point No. 194: Incremental Product/ Services finalization in T-Fiber network,Point No. 197: Service Provisioning PoC for SCCM/NSO - MVPN (all scenarios) ,Point No. 198: Simulation and testing network for parameters like network convergence etc & Point No. 344: CCTV Solution - solution to start PoC with DC connectivity at Cyberabad location as receiver and Sircilla NVR as source. To respond with relevant evidence on how the scope is contracted between L&T and its NOC OEMs, how L&T will implement the Network AT given the Launch date of 30th November ’23. |  | Critical | Open |  |  |  |  | 25-Sep-25: Aretfacts to be uploaded for closure All updated in 472 tracker 186, 190 - Closed 344 - CCTV PoC completed. 193 - Plan re-submitted on 12-Sep-25 198 - Pending, OEM dependancy 197 - NSO point | L&T | RS Rao | RS Rao |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-05-05 | T186 - \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\House Hold VoIP Services Design LLD V1.2 - t187.pdf T190 - \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\CCTV Multicast Solution LLD V1.2 - T190.pdf T344 - | [6 empty] | MOMIP/MPLS | IPMPLS | CLOSED |  |  |  | 2025-05-05 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\House Hold VoIP Services Design LLD V1.2 - t187.pdf |  | 1 | Completed & Approved | Closed after June
972 | M299 | MOM | 2023-10-19 |  |  |  | NSO | Design features | Point No. 221: MAG/GAC ports reservation feasibility for services booked in BSS with payments made. - BSS-SME, L&T to seek clarity on port reservation as a business requirement and the time period required for reservation. - Head Telecom Networks, L&T to record the statement that the port reservation is not a blocker for Network Launch. - Request a Note (Note 5) documenting the statement made by Head Telecom Networks. - L&T to make a decision on the period of port reservation considering the scope of NOC O&M for 7 years. |  | Critical | Open | [7 empty] | Jayant Madavi |  | Open | Open | [9 empty] | MOMNSO | Applications/Tools | OPEN |  |  |  |  | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\CCTV Multicast Solution LLD V1.2 - T190.pdf |  | 1 | Open | Open
973 | M3 | MOM | 2023-03-27 |  |  |  | NOC Operationalization | Full NOC Readiness | Present a plan on how digital processes and tools will be used for GI connectivity provisioning, customer acceptance, and O&M functions |  | Critical | Open |  | OSS Dashboards |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMNOC Operationalization | Network | OPEN |  |  |  |  | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\CCTV Multicast Solution LLD V1.2 - T190.pdf |  | 1 | Open | Open
974 | M30 | MOM | 2023-06-07 |  |  |  | GIS | User Experience | Show duct length, Cable length, chambers, and joint closures in a Mandal |  | NON-Critical | Open |  | Gtech | [5 empty] | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMGIS | Applications/Tools | OPEN | [6 empty] | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
975 | M300 | MOM | 2023-10-19 |  |  |  | NSO | Development & Unit Testing | Point No. 223: IPTV tested needs to be finalised for additional configuration for multicast and tested as per lab availability and final sign off Technical Head, L&T to get the solution sign-off from T-Fiber for additional IPTV configuration and testing. - Target implementation date set for November 15th '23. - Request a Note (Note 6) recording the statement that this point is not a blocker for Network Launch. |  | Critical | Open | [7 empty] | Jayant Madavi |  | Open | Open | [9 empty] | MOMNSO | Applications/Tools | OPEN |  |  |  |  | #VALUE! |  | 1 | Open | Open
976 | M301 | MOM | 2023-10-19 |  | OSS | OSS | New BSS | Integration | Point No. 251: Fetch SLA violation by BSS billing & Point No. 252 Circuit performance data to BSS CRM L&T to provide an outline of the interim solution before the Service Inventory solution from HP is in place. - Ensure no impact on operations during the interim period. - L&T proposes interim measures such as manual computation of downtime, manual SLA performance management, etc. - Request an Undertaking (Note 7) confirming that the interim solution will have no cost impact to T-Fiber. - Timelines for interim milestones and emphasize the need to plan for the final deliverables and a seamless transition. - Segment Head, L&T to provide clear confirmation by the 1st week of November '23. |  | Critical | Open | [7 empty] | Suresh Pawar |  | Open | WIP | [9 empty] | MOMNew BSS | #N/A | OPEN | Not Relevant to OSS | 0 |  |  | #VALUE! |  | 1 | Open | Open
977 | M302 | MOM | 2023-10-19 |  | OSS | OSS | New BSS | Integration | Point No. 264: Network Downtime, fault reported to be mapped with BSS to consider during billing process & Point No. 265: Feasibility Engine & Point No. 266: Commercial engine to be designed along with rules to Budgetary calculation for network and customer feasibilities L&T to submit the SOW agreed between L&T and HP by EoD 19th October ’23. |  | Critical | Open | [7 empty] | Suresh Pawar |  | Open | WIP | [9 empty] | MOMNew BSS | #N/A | OPEN | Not Relevant to OSS | 0 |  |  | #VALUE! |  | 1 | Open | Open
978 | M303 | MOM | 2023-10-19 |  | OSS | OSS | OSS | Development & Unit Testing | Point No. 267: Port Block against Service ID ( Note 5) |  | Critical | Open |  |  |  |  | Additional Scope (This is not give to HPE/OT) |  |  | Suresh Pawar |  | Open | Open | [9 empty] | MOMOSS | Applications/Tools | OPEN | Additional scope | 0 |  |  |  |  | 1 | Open | Open
979 | M304 | MOM | 2023-10-19 |  | OSS | OSS | OSS | Design & Documentation | Point No. 272: Infra team to maintain the SSH connectivity • Security-SME, L&T to submit the design document for SSH. |  | Critical | Open | [7 empty] | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMOSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
980 | M305 | MOM | 2023-10-19 |  | OSS | OSS | OSS | Dashboards | Point No. 280: Cross domain Corelation and exact reason for any outage in Network till ONT Port with E2E topology is targeted for closure by November 15th '23. |  | Critical | Open | [7 empty] | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMOSS | Applications/Tools | OPEN | COMPLETED | Pending |  |  | #N/A |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
981 | M306 | MOM | 2023-10-19 |  | OSS | OSS | OSS | Dashboards | Point No. 282: For ONT Down cases, Some of the Alarms and cause code given by OEM is not matching with RFO provided by field engineer with target date as 25th October ’23. |  | Critical | Open |  |  |  |  | 15-09-2025: Demostrated in the Demo/UAT call |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMOSS | Applications/Tools | OPEN | COMPLETED | 15-09-2025: Demostrated in the Demo/UAT call |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
982 | M307 | MOM | 2023-10-19 |  | OSS | OSS | OSS | Dashboards | Point No. 283: Alert Mechanism (event rule) when power supply is through UPS which is running on Battery backup mode then there should be alert in the form of SMS sent to field team so outages can be avoided or minimized proactively. target date is 15th November ’23. |  | Critical | Open |  |  |  |  | 09-09-2025: It can be enabled based on customer confirmation |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMOSS | Applications/Tools | OPEN | COMPLETED | Pending |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
983 | M308 | MOM | 2023-10-19 |  | OSS | OSS | OSS | Dashboards | Point No. 290: IP MPLS node status report to be automated (Zonal / Mandal/GP) along with Alias Name (Like Actual Mandal /GP names) -Feasibility check required if Alias can be updated & fetched by OSS tool will be informed |  | Critical | Open | [7 empty] | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMOSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
984 | M309 | MOM | 2023-10-19 |  | OSS | OSS | OSS | Dashboards | Point No. 292: Customised dashboard template with available set of fields for different set of user views by 20th Oct'23 |  | Critical | Open | [7 empty] | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMOSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
985 | M31 | MOM | 2023-06-07 |  |  |  | GIS | User Experience | Correct Actual Measure Length and Loop length in BOQ |  | NON-Critical | Open |  | Gtech | [5 empty] | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMGIS | Applications/Tools | OPEN | [6 empty] | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
986 | M310 | MOM | 2023-10-19 |  | OSS | OSS | OSS | Dashboards | Point No. 294: OSS MTTR report to include additional columns like RFO, Sub RFO, Resolution etc. By 20th Oct'23 |  | Critical | Open | [7 empty] | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMOSS | Applications/Tools | OPEN | CLOSURE REVIEW PENDING | 0 |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
987 | M311 | MOM | 2023-10-19 |  | OSS | OSS | OSS | Dashboards | Point No. 296: Service Management dashboard should list planned outages and corelate TT if that is on same device or NW component by 20th Oct'23 |  | Critical | Open | [7 empty] | Suresh Pawar |  | Open | WIP | [9 empty] | MOMOSS | Applications/Tools | OPEN | OPEN | 0 |  |  | #N/A |  | 1 | Open | Open
988 | M312 | MOM | 2023-10-19 |  |  |  | Security & Regulatory Compliance | Regulatory Compliance | Point No. 308: IPDR - Developing in-house solution, also exploring with external vendors. to obtain clarity from the Regulator on the requirements, along with the industry best practices. • VP-Program, T-Fiber asked L&T to revert on the next steps by 26th October ’23. |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #VALUE! |  | 1 | Open | Open
989 | M313 | MOM | 2023-10-19 |  |  |  | Security & Regulatory Compliance | Regulatory Compliance | Point No. 312: SLA Reporting for Cell Tower and GIs • Head Telecom Networks, L&T mentioned that two approaches are under consideration, solution approach to be finalised, target for completion is 30th November ’23. |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
990 | M314 | MOM | 2023-10-19 |  | OSS | OSS | OSS | Resource Related | SVP, T-Fiber emphasized the importance of L&T establishing its own resources for the HPE related tasks and they should not rely solely on one individual. |  | Critical | Open |  |  |  |  | 09-09-2025: Taken support from vigility Team |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMOSS | Applications/Tools | OPEN | COMPLETED | 09-09-2025: Taken support from vigility Team |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
991 | M315 | MOM | 2023-10-19 |  |  |  | Security & Regulatory Compliance | User Traceability | Point No. 316: User Traceability,targeted for closure by 15th November ’23. this point to be included in the SOPs for NOC. |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
992 | M316 | MOM | 2023-10-19 |  |  |  | Security & Regulatory Compliance | Policy Implementation | Point No. 318: Policy Implementation – Network Forensics the process for tracing all incidents including security incidents is yet to be put in place, targeted for 15th November ’23. |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
993 | M317 | MOM | 2023-10-19 |  |  |  | Security & Regulatory Compliance | Report | Point no. 326: IPDR static IP report SVP, T-Fiber asked for the Regulatory aspects to be discovered by 26th October ’23. |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
994 | M318 | MOM | 2023-10-19 |  |  |  | Security & Regulatory Compliance | Design features | Point No. 333: Alepo AAA to be integrated with AD SVP, T-Fiber asked for an SOP to be defined for this. • SVP, T-Fiber asked for a note (Note 8) recording this statement. |  | Critical | Open |  |  |  |  | This is Security point |  |  | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
995 | M319 | MOM | 2023-10-19 |  |  |  | NSO | Design & Documentation | Point No. 343: SDC content to GI – Design document required. Head Telecom Networks, L&T to update on the next steps by 26th October ’23. |  | NON-Critical | Open | [7 empty] | Jayant Madavi |  | Open | Open | [9 empty] | MOMNSO | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
996 | M32 | MOM | 2023-06-07 |  |  |  | GIS | Handbook & SOPs | Detailed validation document |  | NON-Critical | Open |  | Gtech | [5 empty] | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMGIS | Applications/Tools | OPEN | [6 empty] | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
997 | M320 | MOM | 2023-10-19 |  |  |  | Helpdesk | Demo | Assistant Director-P&E, T-Fiber asked L&T to submit the Helpdesk Compliance report along with a summary with respect to RFP by 23rd October’23 and the Demonstration on Helpdesk NEOX to be scheduled after the compliance report submission. |  | Critical | open |  |  |  | WIP | 11-Sep-25: Same has been Submitted | L&T | Shiva kumar | Siva Kumar |  | Open | WIP | [9 empty] | MOMHelpdesk | Helpdesk (Contact Center) | OPEN | [6 empty] | 1 | Open | Open
998 | M321 | MOM | 2023-10-19 |  |  |  | BSS | Development & Unit Testing | Point No. 16: Development and Unit Testing - Service Assurance and trouble tickets To be linked with the points in follow-up with HP for completion by March ’24, with clarity on next steps by 1st week of November. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
999 | M322 | MOM | 2023-10-19 |  |  |  | DR | DNS Switchover | Point No. 79: to confirm that DNS switchover between DC and DR locations should be automatic • Chief Delivery Officer, LTTS updated that this in follow-up with Cisco and CtrlS, next update by 26th October ’23. |  | NON-Critical | Closed |  |  |  |  | [15/09/25] Completed |  |  | Ravi Kishore |  |  | COMPLETED & APPROVED | AD-UT-Tfiber |  | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\DR\Artifact for - T79 | [6 empty] | MOMDR | DR | CLOSED |  |  |  |  | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\DR\Artifact for - T79 |  | 1 | Completed & Approved | Closed before june-2025
1000 | M323 | MOM | 2023-10-19 |  |  |  | DWDM | Integration with OSS | Point No. 103: DWDM-OSS integration - Service Inventory Data Availability in HPE OSS & Point No. 237: DWDM-OSS integration - Service inventory data availability in HPE OSS • Technical Head, L&T updated that this is targeted for closure by 15th November ’23. |  | Critical | Open |  |  |  |  | Duplicate Already covered in 472-points, Ref Point No. 103 & 237 |  |  | Suresh Kumar |  | Open | Duplicate | [9 empty] | MOMDWDM | DWDM | #N/A |  |  | Duplicate |  |  |  | 1 | Open | Open
1001 | M324 | MOM | 2023-10-19 |  |  |  | DWDM | Integration with OSS | Point No. 104 – DWDM-OSS integration: Planned Event Service Impact analysis report & Point No. 238: DWDM-OSS integration: For planned event service impact analysis data / report SVP, T-Fiber asked for the SOP that shall be put in place by L&T until the Service Inventory solution from HP is in place |  | Critical | Open |  |  |  |  | Duplicate Already covered in 472-points, Ref Point No. 104& 238 |  |  | Suresh Kumar |  | Open | Duplicate | [9 empty] | MOMDWDM | DWDM | #N/A |  |  | Duplicate |  |  |  | 1 | Open | Open
1002 | M325 | MOM | 2023-10-19 |  | OSS | OSS | OSS | Integration | Point No. 231: Ciena DWDM Network Topology has been created in HPE OSS topology MAP along with neighbour NE details. SVP, T-Fiber suggested that this requirement may be revisited later. |  | Critical | Open | [7 empty] | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMOSS | Applications/Tools | OPEN | CLOSURE REVIEW PENDING | 0 |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1003 | M326 | MOM | 2023-10-19 |  | OSS | OSS | OSS | Design Features | Point No. 259: OSS E2E Topology it will be completed by 30th December’23 |  | Critical | Open |  |  |  |  | This point is already covered under point no. 584. and Point no. 633 under 472 tracker column |  |  | Suresh Pawar |  | Open | Duplicate | [9 empty] | MOMOSS | Applications/Tools | OPEN | DUPLICATE | This point is already covered under point no. 584. and Point no. 633 under 472 tracker column |  |  | #N/A |  | 1 | Open | Open
1004 | M327 | MOM | 2023-10-19 |  | OSS | OSS | OSS | Dashboards | Point No. 275: In OSS management dashboard, Block count should count only Mandal OLTs and not GP OLTs target date as 30th December ’23. |  | Critical | Open | [7 empty] | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMOSS | Applications/Tools | OPEN | CLOSURE REVIEW PENDING | 0 |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1005 | M328 | MOM | 2023-10-19 |  | OSS | OSS | OSS | Design Features | Point No. 281: Problem Management report for various recurring outages for the given period target date as 30th December ’23 |  | Critical | Open | [7 empty] | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMOSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1006 | M329 | MOM | 2023-10-19 |  | OSS | OSS | OSS | Design Features | Point No. 287: Exact SPAN/Link details must be taken from GIS (Including Lat, Long) for Fiber cut/outage scenario to understand fix is permanent or temporary in nature and impact on Multiple Nodes/GP’s. |  | Critical | Open | [7 empty] | Suresh Pawar |  | Open | Not Feasible | [9 empty] | MOMOSS | Applications/Tools | #N/A | OPEN | 0 |  |  | #N/A |  | 1 | Open | Open
1007 | M33 | MOM | 2023-06-07 |  |  |  | GIS | User Experience | Hyperlink real images to GPs and Mandals |  | Critical | Open |  | Gtech | [5 empty] | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMGIS | Applications/Tools | OPEN | [6 empty] | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1008 | M330 | MOM | 2023-10-19 |  | OSS | OSS | OSS | Dashboards | Point No. 288: Report for Backup Status (success/failure) of all VM (source it from Vcenter Report) L&T to conclude discussions with HP to obtain the target date. |  | Critical | Open |  |  |  |  | 09-09-2025: managed at vmware(comvault) by DCInfra Team |  |  | Suresh Pawar |  | Open | Not Feasible | [9 empty] | MOMOSS | Applications/Tools | #N/A | NOT-FEASIBLE | 09-09-2025: managed at vmware(comvault) by DCInfra Team |  |  | #N/A |  | 1 | Open | Open
1009 | M331 | MOM | 2023-10-19 |  | OSS | OSS | OSS | Dashboards | Point No. 289: DC Active infra-Health check-up /Utilization and Resource Availability report L&T to conclude discussions with HP to obtain the target date. |  | Critical | Open | [7 empty] | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMOSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1010 | M332 | MOM | 2023-10-19 |  | OSS | OSS | OSS | Dashboards | Point No. 293: Service VLAN status report from EMS (Nokia and Tejas) Technical Head, L&T to conclude discussions to obtain the target date. |  | Critical | Open |  |  |  |  | It will be available from intranet portal |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMOSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  | #N/A |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1011 | M333 | MOM | 2023-11-03 |  |  |  | BSS | Service provisioning | UD,SD Peramaters to be captured. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1012 | M334 | MOM | 2023-11-03 |  |  |  | NSO | Service provisioning | NSo inventory manager funtionality to check. |  | Critical | Open | [7 empty] | Jayant Madavi |  | Open | Open | [9 empty] | MOMNSO | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1013 | M335 | MOM | 2023-11-03 |  |  |  | BSS | Service provisioning | UD perameters for product based to be prepared. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1014 | M336 | MOM | 2023-11-03 |  |  |  | BSS | Service provisioning | Ashish to comeback with Design plan for Inventory Manager at NSO |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1015 | M337 | MOM | 2023-11-03 |  |  |  | BSS | Service provisioning | Arvindam to comeback with product wise UD perameters |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1016 | M338 | MOM | 2023-11-03 |  |  |  | BSS | Service provisioning | Additional information for VRF, VLAN , Inner vlan etc to capture in Master DB |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1017 | M339 | MOM | 2023-11-03 |  |  |  | BSS | Service provisioning | As per Cisco LLD All 28 types of L2, L3 models to be mapped aginest products |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1018 | M34 | MOM | 2023-06-07 |  |  |  | GIS | Installation | 100TB storage for LIDAR survey data |  | Critical | Open | Conflict | Gtech | [5 empty] | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMGIS | Applications/Tools | OPEN | [6 empty] | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1019 | M340 | MOM | 2023-11-03 |  |  |  | BSS | Service Codes | GL code to be mapped based on subtype GI under sub type Central & State |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1020 | M341 | MOM | 2023-11-03 |  |  |  | BSS | Service Codes | Define the Code for Circuit type , Customer type , customer service type etc in single format |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1021 | M342 | MOM | 2023-11-03 |  |  |  | BSS | Service Codes | Define design plan for House hold services in GPON Level |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1022 | M343 | MOM | 2023-11-03 |  |  |  | BSS | Service Codes | Define Household plan for provisioning as per the GPON plan design |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1023 | M344 | MOM | 2023-11-03 |  |  |  | BSS | Service Codes | OSS Method of distance from GIS need to comeback with plan |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1024 | M345 | MOM | 2023-11-03 |  |  |  | BSS | Service Codes | Aravindam to update on previous meetings updates to be updated in next in continuous meetings |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1025 | M346 | MOM | 2023-11-17 |  |  |  | Helpdesk | Demo | Neox helpdesk Demo : |  | Critical | Open |  |  |  | WIP |  |  |  | Siva Kumar |  | Open | WIP | [9 empty] | MOMHelpdesk | Helpdesk (Contact Center) | OPEN | [6 empty] | 1 | Open | Open
1026 | M347 | MOM | 2023-11-17 |  |  |  | Helpdesk | Compliance | Neox Compliance confirmation : |  | Critical | open |  |  |  | WIP | 11-Sep-25: Same has been Submitted | L&T | Shiva kumar | Siva Kumar |  | Open | WIP | [9 empty] | MOMHelpdesk | Helpdesk (Contact Center) | OPEN | [6 empty] | 1 | Open | Open
1027 | M348 | MOM | 2023-11-17 |  |  |  | NOC Operationalization | Action Points | 370 points out of which 24 points which are already covered in 370 : Praveen to share indicating the reference of 24 points by |  | Critical | Closed |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1 | Completed & Approved | Closed before june-2025
1028 | M349 | MOM | 2023-11-17 |  |  |  | NOC Operationalization | Action Points | 196 points closure along with artefacts : |  | Critical | Closed |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1 | Completed & Approved | Closed before june-2025
1029 | M35 | MOM | 2023-06-07 |  |  |  | GIS | Training | Hands-on Training on GIS tool |  | NON-Critical | Open |  | Gtech | [5 empty] | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMGIS | Applications/Tools | OPEN | [6 empty] | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1030 | M350 | MOM | 2023-11-17 | P3 |  |  | NOC Operationalization | Documentation | Revised Organization structure : |  | Critical | Completed |  |  |  |  | NOC structure and manpower details shared |  |  | Ahmad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  | Not related to delivery | 2025-09-19 | Artefacts not Required |  | 1 | Completed & Approved | Closed after June
1031 | M351 | MOM | 2023-11-17 |  |  |  | BSS | Demo | Second Dry Run (details to be shared later) : week starting |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1032 | M352 | MOM | 2023-11-17 |  |  |  | NOC Operationalization | Documentation | Artefacts storage link : |  | Critical | Completed |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1 | Completed & Approved | Closed after June
1033 | M353 | MOM | 2023-11-17 |  |  |  | Security & Regulatory Compliance | Regulatory Compliance | Security Assessment Review Meeting : week starting |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1034 | M354 | MOM | 2023-11-17 |  |  |  | NOC Operationalization | Resource Related | HP & Cisco OEM teams onboarding from 20th November'23. |  | Critical | Closed |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1 | Completed & Approved | Closed before june-2025
1035 | M355 | MOM | 2023-11-17 |  |  |  | NOC Operationalization | Documentation | Letter from all OEMs apart from Cisco & HP to be submitted by 22nd November'23 |  | Critical | Open |  |  |  | Closed, Artefacts to be uploaded | 23-Sep-25: Approved Artefacts to be Submitted | L&T | Sivaprasad | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  |  | Artefacts Need to upload |  | 1 | Completed & Approved | Closed after June
1036 | M356 | MOM | 2023-11-17 |  |  |  | NOC Operationalization | Documentation | Letter from from Cisco & HP to be submitted by 24th November'23 |  | Critical | Open |  |  |  | Closed, Artefacts to be uploaded | 23-Sep-25: Approved Artefacts to be Submitted | L&T | Sivaprasad | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  |  | Artefacts Need to upload |  | 1 | Completed & Approved | Closed after June
1037 | M357 | MOM | 2023-11-17 |  |  |  | NOC Operationalization | Documentation | Letter of confirmation for closure of issues with Tejas & Nokia on or before 30th November’23 |  | Critical | Open |  |  |  | Closed, Artefacts to be uploaded | 23-Sep-25: Approved Artefacts to be Submitted | L&T | Sivaprasad | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  |  | Artefacts Need to upload |  | 1 | Completed & Approved | Closed after June
1038 | M358 | MOM | 2023-11-17 |  |  |  | NOC Operationalization | Meeting | Date for All OEMs Meeting |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1 | Completed & Approved | Closed after June
1039 | M359 | MOM | 2023-11-17 |  |  |  | BSS | Resource Related | BSS-SME visit & extended stay for backlog clearance and sharing agenda prior to visit |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1040 | M36 | MOM | 2023-06-07 |  |  |  | GIS | Dashboards | Discuss and Develop Dashboard for GIS tool |  | NON-Critical | Open |  | Gtech | [5 empty] | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMGIS | Applications/Tools | OPEN | [6 empty] | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1041 | M360 | MOM | 2023-11-17 |  |  |  | NOC Operationalization | Documentation | Revert pending on 8 Notes(Undertaking) |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1 | Completed & Approved | Closed after June
1042 | M361 | MOM | 2023-11-17 |  |  |  | Helpdesk | Resource Related | Dimensioning of Helpdesk calls |  | Critical | open |  |  |  | Closed | 24-Sep-25: Approved and shall be closed 11-Sep-25: Changed and operational Now |  |  | Siva Kumar |  |  | COMPLETED & APPROVED | [9 empty] | MOMHelpdesk | Helpdesk (Contact Center) | CLOSED |  |  |  | 2025-09-24 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\M117,126,728 |  | 1 | Completed & Approved | Closed after June
1043 | M362 | MOM | 2023-11-17 | P3 |  |  | NOC Operationalization | Documentation | Revert on 26 SOPS & O&M Handbook |  | Critical | Open |  |  |  |  | SOP agreed and signed off. O&M Handbook WIP |  |  | Ahmad | 2025-10-07 | Open | Open | [9 empty] | MOMNOC Operationalization | Network | OPEN |  |  | Documentation |  | #N/A |  | 1 | Open | Open
1044 | M363 | MOM | 2023-11-17 | P3 |  |  | NOC Operationalization | Documentation | Measurable KPI for individual TNOC team |  | Critical | Completed |  |  |  |  | NOC role KRA and KPI submitted to TFiber |  |  | Ahmad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  | Not related to delivery | 2025-09-24 | \\172.28.9.23\tnocreports\TNOC Manpower_CVs\NOC Resources Details & Roles |  | 1 | Completed & Approved | Closed after June
1045 | M364 | MOM | 2023-11-17 | P3 |  |  | NOC Operationalization | Resource Related | Service delivery & Service assurance Manager |  | Critical | Completed |  |  |  |  | Not part of RFP. Service Provisioning is being done by NOC team |  |  | Ahmad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  | Not related to delivery | 2025-09-19 | Artefacts not Required |  | 1 | Completed & Approved | Closed after June
1046 | M365 | MOM | 2023-11-17 | P3 |  |  | NOC Operationalization | Resource Related | Plan for Manpower augmentation to handle Infra Alarm in TNOC & field to finalize O&M |  | Critical | Completed |  |  |  |  | NOC manpower is deputed as per RFP and manpower report is shared with TFiber on weekly basis |  |  | Ahmad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  | Not related to delivery | 2025-09-19 | Artefacts not Required |  | 1 | Completed & Approved | Closed after June
1047 | M366 | MOM | 2023-11-17 |  |  |  | BSS | Dry Run | BSS product system readiness for usage |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1048 | M367 | MOM | 2023-11-17 |  |  |  | NOC Operationalization | Resource Related | Additional resources for fast tracking of project |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1 | Completed & Approved | Closed after June
1049 | M368 | MOM | 2023-11-28 |  |  |  | NOC Operationalization | Meeting | L&T to communicate with OEMs and arrange a meeting on behalf of T-Fiber. 1. To seek evidence from L&T on the commitment from respective OEMs of BSS, OSS, NSO, GIS, GPON on closure of gaps identified so far, related to the operationalization of various systems along with firm dates for delivery from respective OEMs for the same. 2. L&T to provide a plan on how the NOC O&M will be handled with SOPs where relevant in the interim period. 3. How L&T transitions the systems from the interim to the final state without any business impact while ensuring data integrity. |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1 | Completed & Approved | Closed after June
1050 | M369 | MOM | 2023-11-28 |  |  |  | Security & Regulatory Compliance | Regulatory Compliance | Fast-track track closure of Regulatory and security requirements along with SLA monitoring for the immediate start of Business related to Cell Tower, GI BB, GI ILL & VPN service delivery. |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1051 | M37 | MOM | 2023-06-07 |  |  |  | GIS | User Experience | New validation Logic to be incorporated in DI tool - if Depth is zero and construction method is HDD/OT, Protection is required |  | NON-Critical | Open |  | Gtech | [5 empty] | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMGIS | Applications/Tools | OPEN | [6 empty] | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1052 | M370 | MOM | 2023-11-28 |  |  |  | NOC Operationalization | Demo | L&T to prepare and execute the next DRY run effectively. |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1 | Completed & Approved | Closed after June
1053 | M371 | MOM | 2023-11-28 |  |  |  | NOC Operationalization | Documentation | L&T to develop a comprehensive presentation on product readiness and NOC operationalization schedule. |  | Critical | Completed |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1 | Completed & Approved | Closed after June
1054 | M372 | MOM | 2023-12-12 |  |  |  | Security & Regulatory Compliance | RMC meeting | Submit Acceptable Usage Policy document with suggested changes |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1055 | M373 | MOM | 2023-12-12 |  |  |  | Security & Regulatory Compliance | RMC meeting | Complete the configuration of CA signed SSL certificate |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1056 | M374 | MOM | 2023-12-12 |  |  |  | Security & Regulatory Compliance | RMC meeting | Concur with T-Fiber for annual external VAPT testing |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1057 | M375 | MOM | 2023-12-12 |  |  |  | Security & Regulatory Compliance | RMC meeting | Submit Vulnerability Management Policy |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1058 | M376 | MOM | 2023-12-12 |  |  |  | Security & Regulatory Compliance | RMC meeting | List and share the Security Policy documents and SOPS |  | Critical | Open |  |  |  |  | Docs List is shared |  |  | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1059 | M377 | MOM | 2023-12-12 |  |  |  | Security & Regulatory Compliance | RMC meeting | Upload all RMC MoMs to the shared folder and share access |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1060 | M378 | MOM | 2023-12-12 |  |  |  | Security & Regulatory Compliance | RMC meeting | Submit Asset Management policy |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1061 | M379 | MOM | 2023-12-12 |  |  |  | Security & Regulatory Compliance | RMC meeting | Submit onboarding/offboarding policy |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1062 | M38 | MOM | 2023-06-15 |  |  |  | BSS | Resource Related | Billing Expert onboarding |  | Critical | Open |  | Billing | [5 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1063 | M380 | MOM | 2023-12-12 |  |  |  | Security & Regulatory Compliance | RMC meeting | Submit scope of work for External VAPT |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1064 | M381 | MOM | 2023-12-12 |  |  |  | Security & Regulatory Compliance | RMC meeting | Collect Cryptography encryption model document from all OEMs |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1065 | M382 | MOM | 2023-12-12 |  |  |  | Security & Regulatory Compliance | RMC meeting | Submit the revised undertaking for Tejas - Alepo and Nokia |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1066 | M383 | MOM | 2023-12-12 |  |  |  | Security & Regulatory Compliance | RMC meeting | Provide compliance documents for all applications and devices |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1067 | M384 | MOM | 2023-12-12 |  |  |  | Security & Regulatory Compliance | RMC meeting | Submit document on Privilege management |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1068 | M385 | MOM | 2023-12-12 |  |  |  | Security & Regulatory Compliance | RMC meeting | Submit password management policy |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1069 | M386 | MOM | 2023-12-12 |  |  |  | Security & Regulatory Compliance | RMC meeting | Submit artefacts for all banners |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1070 | M387 | MOM | 2023-12-12 |  |  |  | Security & Regulatory Compliance | RMC meeting | Submit internal/external, Trusted, untrusted zone checklist |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1071 | M388 | MOM | 2023-12-12 |  |  |  | Security & Regulatory Compliance | RMC meeting | Submit internal network policies details |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1072 | M389 | MOM | 2023-12-12 |  |  |  | Security & Regulatory Compliance | RMC meeting | Submit SSL implementation report for all APIs |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1073 | M39 | MOM | 2023-06-15 |  |  |  | BSS | Handbook & SOPs | State of maturity of all Business process flows mentioned in the HLD |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1074 | M390 | MOM | 2023-12-12 |  |  |  | Security & Regulatory Compliance | RMC meeting | Submit Acceptable Usage Policy |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1075 | M391 | MOM | 2023-12-12 |  |  |  | Security & Regulatory Compliance | RMC meeting | Submit Security endpoints list of Infra, workstations |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1076 | M392 | MOM | 2023-12-12 |  |  |  | Security & Regulatory Compliance | RMC meeting | Submit SOP for security policies |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1077 | M393 | MOM | 2023-12-12 |  |  |  | Security & Regulatory Compliance | RMC meeting | Submit DR reports for all Applications |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1078 | M394 | MOM | 2023-12-12 |  |  |  | Security & Regulatory Compliance | RMC meeting | Submit attendance list for security awareness trainings |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1079 | M395 | MOM | 2023-12-12 |  |  |  | Security & Regulatory Compliance | RMC meeting | Finalize backup duration and frequency, and provide utilization report |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1080 | M396 | MOM | 2023-12-12 |  |  |  | Security & Regulatory Compliance | RMC meeting | Submit a report capturing online and offline storage status |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1081 | M397 | MOM | 2023-12-12 |  |  |  | Security & Regulatory Compliance | RMC meeting | Finalize Technology Risk Management checklist |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1082 | M398 | MOM | 2023-12-12 |  |  |  | Security & Regulatory Compliance | RMC meeting | Further audit and VAPT by Allied Boston |  | Critical | Open |  |  |  |  | Audit done by Allied Boston |  |  | Sarmendra |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | Artefacts to be Submitted |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1083 | M399 | MOM | 2023-12-15 |  |  |  | WFM | Mobile Application | Arrange a demonstration of WFM Tool for field operations |  | Critical | Open |  |  |  |  | Duplicate with Point- 235 |  |  | Kaushalendra Kumar |  | Open | Duplicate | [9 empty] | MOMWFM | Applications/Tools | #N/A |  |  |  |  | #N/A |  | 1 | Open | Open
1084 | M4 | MOM | 2023-03-27 |  |  |  | BSS | Service provisioning | BSS-based provisioning for regularizing 3000 GI through NOC BSS, with scalability to 30,000 GIs. |  | Critical | Open |  | OSS Dashboards | [5 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1085 | M40 | MOM | 2023-06-19 |  |  |  | GIS | User Experience | Download active port connectivity details |  | Critical | Open | Conflict | Gtech |  |  | Link Trace Report Download |  |  | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMGIS | Applications/Tools | OPEN | [6 empty] | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1086 | M400 | MOM | 2023-12-15 |  |  |  | WFM | Mobile Application | Clarity on GPS tracking availability and battery consumption |  | Critical | Open | [7 empty] | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMWFM | Applications/Tools | OPEN | [6 empty] | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1087 | M401 | MOM | 2023-12-15 |  |  |  | WFM | Mobile Application | WFM Mobile App Features: L&T to provide clarity on GPS tracking availability, polling frequency, photo upload feature, file size limitations, and supported Android and iOS versions. |  | Critical | Open | [7 empty] | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMWFM | Applications/Tools | OPEN | [6 empty] | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1088 | M402 | MOM | 2023-12-15 |  |  |  | WFM | Mobile Application | Clarify on photo upload feature and impact on mobile phone memory |  | NON-Critical | Open | [7 empty] | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMWFM | Applications/Tools | OPEN | [6 empty] | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1089 | M403 | MOM | 2023-12-15 |  |  |  | WFM | Mobile Application | Clarity on offline data storage feature availability |  | NON-Critical | Open |  |  |  |  | 11-7-2025:- Offline data, such as images and documents, can be uploaded either from the mobile gallery or directly using the camera. To support the storage of LIDAR survey data and GIS images, an 80 TB NAS storage system has already been deployed at the NOC Data Center |  |  | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMWFM | Applications/Tools | OPEN | [6 empty] | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1090 | M404 | MOM | 2023-12-15 |  |  |  | WFM | Mobile Application | Clarity on file size limitations during upload |  | NON-Critical | Open | [7 empty] | Kaushalendra Kumar |  | Open | Open | [9 empty] | MOMWFM | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1091 | M405 | MOM | 2023-12-15 |  |  |  | WFM | Mobile Application | The urgency for L&T to demonstrate the WFM tool for field operations and to provide detailed information on its features and capabilities. |  | NON-Critical | Open | [7 empty] | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMWFM | Applications/Tools | OPEN | [6 empty] | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1092 | M406 | MOM | 2023-12-15 |  |  |  | WFM | Mobile Application | Clarify the usage differences between GIS and WFM mobile apps |  | NON-Critical | Open | [7 empty] | Kaushalendra Kumar |  | Open | Open | [9 empty] | MOMWFM | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1093 | M407 | MOM | 2023-12-15 |  |  |  | WFM | Mobile Application | Security Assurance: L&T to provide the NDA signed with M/S Lepton, assure API security, and share the contract copy. |  | NON-Critical | Open | [7 empty] | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMWFM | Applications/Tools | OPEN | [6 empty] | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1094 | M408 | MOM | 2023-12-15 |  |  |  | WFM | Mobile Application | Geo-fencing: L&T to explain how geo-fencing shall work for a fiber route and how it will be assigned for Mandal and GP locations. |  | Critical | Open | [7 empty] | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMWFM | Applications/Tools | OPEN | [6 empty] | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1095 | M409 | MOM | 2023-12-15 |  |  |  | WFM | Mobile Application | Ticket Allocation: L&T to start manual ticket allocation and freeze the process for node and link ticket allocation. |  | Critical | Open | [7 empty] | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMWFM | Applications/Tools | OPEN | [6 empty] | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1096 | M41 | MOM | 2023-06-19 |  |  |  | GIS | User Experience | Real-time sync of topology details from OSS |  | Critical | Open |  | Gtech | [5 empty] | Kaushalendra Kumar |  | Open | WIP | [9 empty] | MOMGIS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1097 | M410 | MOM | 2023-12-15 |  |  |  | WFM | Mobile Application | Ticket Allocation: L&T to start manual ticket allocation and freeze the process for node and link ticket allocation. |  | NON-Critical | Open | [7 empty] | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMWFM | Applications/Tools | OPEN | [6 empty] | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1098 | M411 | MOM | 2023-12-15 |  |  |  | WFM | Mobile Application | Use of document forms from the Operations Handbook by the WFM app |  | Critical | Open | [7 empty] | Kaushalendra Kumar |  | Open | Open | [9 empty] | MOMWFM | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1099 | M412 | MOM | 2023-12-15 |  |  |  | WFM | Mobile Application | Summary Dashboards/Management Reports: L&T to provide inputs based on Operations best practices for weekly/monthly management reports from the WFM package. |  | Critical | Open | [7 empty] | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMWFM | Applications/Tools | OPEN | [6 empty] | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1100 | M413 | MOM | 2023-12-19 |  |  |  | WFM | Mobile Application | WFM Tool Demonstration: L&T to arrange a demonstration of the WFM tool usage for field operations soon. |  | Critical | Open | [7 empty] | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMWFM | Applications/Tools | OPEN | [6 empty] | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1101 | M414 | MOM | 2023-12-19 |  |  |  | BSS | Improvement | Investigate and expedite the issue on slowness of BSS Test Environment |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1102 | M415 | MOM | 2023-12-19 |  |  |  | BSS | Dashboards | Explore web-based Analytic tools for performance benchmarking |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1103 | M416 | MOM | 2023-12-19 |  |  |  | BSS | Compliance | Review the status of points with "No Change" status and obtain T-Fiber's consensus before rendering items as "Closed". |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1104 | M417 | MOM | 2023-12-19 |  |  |  | BSS | Improvement | Verify the feature allowing multiple locations per customer |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1105 | M418 | MOM | 2023-12-19 |  |  |  | BSS | Improvement | Cross-reference user experience feedback with related points |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1106 | M419 | MOM | 2023-12-19 |  |  |  | BSS | SMS Integration | Implement notification of SMS dispatch in the CSP and provision of a link in SMS to the CSP page allowing T-Fiber user to Approve or Reject |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1107 | M42 | MOM | 2023-06-19 |  |  |  | GIS | User Experience | automate active connectivity within site with logical link name populated from OSS |  | Critical | Open |  | Gtech |  |  | Based on discussions with the OSS and GIS teams, integration is not feasible, and automation of connectivity cannot be implemented, 11th July 2025, a discussion is needed with Siva Sir to explore in-house solution possibilities. |  |  | Kaushalendra Kumar |  | Open | Not Feasible | [9 empty] | MOMGIS | Applications/Tools | #N/A |  |  |  |  | #N/A |  | 1 | Open | Open
1108 | M420 | MOM | 2023-12-19 |  |  |  | BSS | Product Demo | Provide a demo to showcase product catalogue configurability |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1109 | M421 | MOM | 2023-12-19 |  |  |  | BSS | Product Demo | Provide a demo of Backend Validation and share a document with the steps for validation |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1110 | M422 | MOM | 2023-12-19 |  |  |  | BSS | Product Demo | Address the delay in data load due to system limitation in the production instance |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1111 | M423 | MOM | 2023-12-19 |  |  |  | BSS | Product Demo | Define a benchmark for page loading, login, browsing, and payment scenarios |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1112 | M424 | MOM | 2023-12-19 |  |  |  | BSS | Product Demo | Review the status of Point no. 52 from Dry Run 1 with a demo |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1113 | M425 | MOM | 2023-12-19 |  |  |  | BSS | Product Demo | Ensure uniform colour coding across the website |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1114 | M426 | MOM | 2023-12-19 |  |  |  | BSS | Product Demo | Address the change of website heading for customer dashboards prior to moving into production |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1115 | M427 | MOM | 2023-12-19 |  |  |  | BSS | Product Demo | Arrange for a demo of current products since significant time has passed since the Dry Run |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1116 | M428 | MOM | 2023-12-19 |  |  |  | BSS | Product Demo | Show the flows of Dark Fiber with BSS and WFM |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1117 | M429 | MOM | 2023-12-19 |  |  |  | BSS | Product Demo | Hold discussions for T-Cell product integration with respective OEMs |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1118 | M43 | MOM | 2023-06-19 |  |  |  | GIS | Functional AT Plan | TPA to validate active-active connectivity |  | Critical | Open | Conflict | Gtech | [5 empty] | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMGIS | Applications/Tools | OPEN | [6 empty] | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1119 | M430 | MOM | 2023-12-19 |  |  |  | BSS | Product Demo | Complete T-Cell, T-VPN, and GI-ILL |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1120 | M431 | MOM | 2023-12-19 |  |  |  | BSS | Product Demo | Address delay in support for enabling newer products |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1121 | M432 | MOM | 2023-12-19 |  |  |  | BSS | Product Demo | Complete T-Cell, T-VPN and GI-ILL on priority before impending visit to NOC by Hon’ Minister |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1122 | M433 | MOM | 2023-12-19 |  |  |  | BSS | Product Demo | Include headers and check across pages in the CSP |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1123 | M434 | MOM | 2023-12-19 |  |  |  | BSS | Product Demo | Start working on the CSP for listed schools |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1124 | M435 | MOM | 2023-12-19 |  |  |  | BSS | Product Demo | Clarify scenario where GP location is feasible, whereas the feasibility of end customer location is yet to be ascertained |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1125 | M436 | MOM | 2023-12-19 |  |  |  | BSS | Product Demo | Include feasibility logic for S1, and S2 splitters |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1126 | M437 | MOM | 2023-12-19 |  |  |  | BSS | Product Demo | Present the logic for Bandwidth feasibility in the backhaul, network capacity planning to be progressively provisioned, and operationalised |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1127 | M438 | MOM | 2023-12-19 |  |  |  | BSS | Improvement | Address immediate need for NSO inventory to be part of the final solution for feasibility |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1128 | M439 | MOM | 2023-12-19 |  |  |  | BSS | Resource Related | Ask Segment Head, L&T to discuss with EVP, T-Fiber on the adequacy of NMS works resources |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN | [6 empty] | 1 | Open | Open
1129 | M44 | MOM | 2023-06-19 |  |  |  | GIS | User Experience | Add card/module/slot level details |  | Critical | Open |  | Gtech |  |  | Duplicate with Point- 90 |  |  | Kaushalendra Kumar |  | Open | Duplicate | [9 empty] | MOMGIS | Applications/Tools | #N/A |  |  |  |  | #N/A |  | 1 | Open | Open
1130 | M440 | MOM | 2023-12-19 |  |  |  | BSS | Improvement | Clarify that Repository Module for Uploading of MSA, CAF form and other documents of a particular customer is in CRM, not in CSP |  | NON-Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1131 | M441 | MOM | 2023-12-19 |  |  |  | BSS | Integration | Incorporate advanced features in the CSP's WhatsApp Integration |  | NON-Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1132 | M442 | MOM | 2023-12-19 |  |  |  | BSS | User Experience | On-board an internal UI/UX resource and engage them with T-Fiber |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1133 | M443 | MOM | 2023-12-28 |  |  |  | BSS | Product Demo | Complete T-VPN and T-DILL |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1134 | M444 | MOM | 2023-12-28 |  |  |  | BSS | Product Demo | Complete basic products by |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1135 | M445 | MOM | 2023-12-28 |  |  |  | BSS | Product Demo | Complete GI-BB, T-Cell, Dark Fiber |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1136 | M446 | MOM | 2023-12-28 |  | OSS | OSS | OSS | HPSM | Remove duplicate TroubleTicket issue |  | Critical | Open | [7 empty] | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMOSS | Applications/Tools | OPEN | CLOSURE REVIEW PENDING | 0 |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1137 | M447 | MOM | 2023-12-28 |  |  |  | Security & Regulatory Compliance | Regulatory Compliance | Finalize scope of external audit in consultation with T-Fiber |  | Critical | Open |  |  |  |  | Audit done by Allied Boston |  |  | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1138 | M448 | MOM | 2023-12-28 |  |  |  | Security & Regulatory Compliance | Regulatory Compliance | Conduct external audit |  | Critical | Open |  |  |  |  | Audit done by Allied Boston |  |  | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1139 | M449 | MOM | 2023-12-28 |  |  |  | Helpdesk | Training | Improve maturity of Helpdesk to handle incoming calls |  | Critical | Open |  |  |  | Closed | 24-Sep-25: Approved and shall be closed |  |  | Siva Kumar |  |  | COMPLETED & APPROVED | [9 empty] | MOMHelpdesk | Helpdesk (Contact Center) | CLOSED |  |  |  | 2025-09-24 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\M114,722,134 |  | 1 | Completed & Approved | Closed after June
1140 | M45 | MOM | 2023-06-19 |  |  |  | GIS | User Experience | Ensure Topology name uniqueness |  | Critical | Open | Conflict | Gtech |  |  | Duplicate with Point- 128 |  |  | Kaushalendra Kumar |  | Open | Duplicate | [9 empty] | MOMGIS | Applications/Tools | #N/A |  |  |  |  | #N/A |  | 1 | Open | Open
1141 | M450 | MOM | 2023-12-28 |  | OSS | OSS | OSS | HPSM | Freeze the process for node ticket allocation |  | Critical | Open | [7 empty] | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMOSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1142 | M451 | MOM | 2023-12-28 |  |  |  | NOC Operationalization | Action Points | Cover all requirements from workshops, RFP, and discussions in the roadmap |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1 | Completed & Approved | Closed after June
1143 | M452 | MOM | 2023-12-28 |  | OSS | OSS | OSS | Action Points | Generate SLA reports automatically from NOC |  | Critical | Open | [7 empty] | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMOSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  | #N/A |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1144 | M453 | MOM | 2023-12-28 |  |  |  | NOC Operationalization | Action Points | Submit a Roadmap covering all requirements raised in all Workshops, the RFP requirements, the 396-point Worksheet maintained by L&T, and all the discussions |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1 | Completed & Approved | Closed after June
1145 | M454 | MOM | 2023-12-28 |  |  |  | NOC Operationalization | Action Points | Explore templates from BBNL NOC for invoice settlement |  | Critical | Open |  |  |  | Will be discussed later | 23-Sep-25: NON Critical to be reviewd later | L&T | Sivaprasad | Sivaprasad |  | Open | Open | [9 empty] | MOMNOC Operationalization | Network | OPEN | [6 empty] | 1 | Open | Open
1146 | M455 | MOM | 2023-12-28 |  | OSS | OSS | OSS | HPSM | Ensure cross-domain RCA, SIA, Helpdesk and Network Service Topology are in place |  | Critical | Open |  |  |  |  | Inhouse solution |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMOSS | Applications/Tools | OPEN | COMPLETED | Pending |  |  | #N/A |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1147 | M456 | MOM | 2023-12-28 |  |  |  | NOC Operationalization | Action Points | Deliver NOC before the end of T3 |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMNOC Operationalization | Network | OPEN | [6 empty] | 1 | Open | Open
1148 | M457 | MOM | 2024-01-04 |  | OSS | OSS | OSS | HPSM | Implement ticket tracking with OSS Service Manager |  | Critical | Open | [7 empty] | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMOSS | Applications/Tools | OPEN | CLOSURE REVIEW PENDING | 0 |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1149 | M458 | MOM | 2024-01-04 |  |  |  | BSS | Product category | Complete T-DILL & T-VPN |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1150 | M459 | MOM | 2024-01-04 |  |  |  | BSS | Product category | Discuss network design for T-DILL with AD-P&E, T-Fiber & IPMPLS-SME |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1151 | M46 | MOM | 2023-06-19 |  |  |  | GIS | User Experience | BoQ feature to download passive/active devices separately |  | Critical | Open | Conflict | Gtech | [5 empty] | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMGIS | Applications/Tools | OPEN | [6 empty] | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1152 | M460 | MOM | 2024-01-04 |  |  |  | NSO | Service Solution | Submit a plan for the completion of the 28 services, along with dependencies |  | Critical | Open | [7 empty] | Jayant Madavi |  | Open | Open | [9 empty] | MOMNSO | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1153 | M461 | MOM | 2024-01-04 |  |  |  | BSS | Product category | Conduct a product discussion audit |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1154 | M462 | MOM | 2024-01-04 |  |  |  | BSS | Product category | Submit evidence on commitment from OEMs for integration of various systems with BSS |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1155 | M463 | MOM | 2024-01-04 |  |  |  | NSO | Service Solution | Submit a road map for the completion of the 28 services and all variants |  | Critical | Open | [7 empty] | Jayant Madavi |  | Open | Open | [9 empty] | MOMNSO | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1156 | M464 | MOM | 2024-01-04 |  |  |  | NSO | Service Solution | Initiate daily meetings and share progress updates |  | Critical | Open | [7 empty] | Jayant Madavi |  | Open | Open | [9 empty] | MOMNSO | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1157 | M465 | MOM | 2024-01-04 |  |  |  | BSS | Product category | Finalize network design and initiate the implementation of Mandal-to-Mandal and Mandal-to-GP dark fiber process |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1158 | M466 | MOM | 2024-01-04 |  |  |  | BSS | Product category | Prepare for mock audit regarding bill desk integration and prepare a road map for the dry run of T-DILL & T-VPN |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1159 | M467 | MOM | 2024-01-04 |  |  |  | BSS | Product category | Finalize details of services of T3 & T4 |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1160 | M468 | MOM | 2024-01-04 |  | OSS | OSS | OSS | Service Solution | Resolve discrepancies in readiness status of Fault Management, Network Performance Management Security Management, Regulatory Compliances, Service Delivery- Feasibility, DR readiness, and Technical Helpdesk |  | Critical | Open | [7 empty] | Suresh Pawar |  | Open | WIP | [9 empty] | MOMOSS | Applications/Tools | OPEN | OPEN | 0 |  |  | #N/A |  | 1 | Open | Open
1161 | M469 | MOM | 2024-01-04 |  |  |  | NOC Operationalization | O&M Strategy | Achieve readiness of all 'T0' NOC functions |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1 | Completed & Approved | Closed after June
1162 | M47 | MOM | 2023-06-19 |  |  |  | GIS | User Experience | Bulk Feasibility closure case reports from GIS |  | Critical | Open |  | Gtech |  |  | To fulfill this requirement, an external feasibility application or tool is needed, as it cannot be achieved within the GIS application, 11 July 2025:- TFIBER is not agreed, asked to take with L&T upper management |  |  | Kaushalendra Kumar |  | Open | Open | [9 empty] | MOMGIS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1163 | M470 | MOM | 2024-01-04 |  |  |  | NOC Operationalization | O&M Strategy | Submit details of remaining services of T3 & T4 |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMNOC Operationalization | Network | OPEN | [6 empty] | 1 | Open | Open
1164 | M471 | MOM | 2024-01-04 |  |  |  | NOC Operationalization | O&M Strategy | Start daily meetings and share progress updates |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1 | Completed & Approved | Closed after June
1165 | M472 | MOM | 2024-01-04 |  |  |  | BSS | Product category | Ensure all 29 BSNL locations are loaded for lead to order presentation |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1166 | M473 | MOM | 2024-01-04 |  |  |  | BSS | Product category | Submit confirmation responses along with product notes on all raised points |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1167 | M474 | MOM | 2024-01-05 |  |  |  | BSS | Product category | Review and finalize the Unique ID code convention for various attributes |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1168 | M475 | MOM | 2024-01-05 |  |  |  | BSS | Product category | Provide demo on Circuit ID generation process and integrate it in BSS |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1169 | M476 | MOM | 2024-01-05 |  |  |  | NSO | Service provisioning | Revisit current Circuit ID logic in NSO and define new naming convention |  | Critical | Open | [7 empty] | Jayant Madavi |  | Open | Open | [9 empty] | MOMNSO | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1170 | M477 | MOM | 2024-01-05 |  |  |  | NSO | Service provisioning | Ensure GUI interface to initiate the order from NSO directly |  | Critical | Open | [7 empty] | Jayant Madavi |  | Open | Open | [9 empty] | MOMNSO | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1171 | M478 | MOM | 2024-01-05 |  |  |  | NSO | Service provisioning | Make A&O independent of BSS for generating Circuit ID |  | Critical | Open | [7 empty] | Jayant Madavi |  | Open | Open | [9 empty] | MOMNSO | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1172 | M479 | MOM | 2024-01-05 |  |  |  | NSO | Service provisioning | Circuit ID should distinguish origin system if a new front-end system is introduced |  | Critical | Open | [7 empty] | Jayant Madavi |  | Open | Open | [9 empty] | MOMNSO | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1173 | M48 | MOM | 2023-06-19 |  |  |  | GIS | User Experience | Route path identification through Google |  | Critical | Open | Conflict | Gtech | [5 empty] | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMGIS | Applications/Tools | OPEN | [6 empty] | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1174 | M480 | MOM | 2024-01-05 |  |  |  | NSO | Service provisioning | Ensure Circuit ID isn't limited to 6/8 digits; it should follow the industry-recommended approach |  | Critical | Open | [7 empty] | Jayant Madavi |  | Open | Open | [9 empty] | MOMNSO | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1175 | M481 | MOM | 2024-01-05 |  |  |  | BSS | Product category | Provide option to add new Customer ID during onboarding a new customer |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1176 | M482 | MOM | 2024-01-05 |  |  |  | BSS | Product category | Proceed with Payment approach Option 3 including one-time and recurring invoice generation |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1177 | M483 | MOM | 2024-01-05 |  |  |  | BSS | Product category | If purchase order and CAF are already loaded in the CRM and mapped with customer account, the CAF generation and approval process should be skipped |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1178 | M484 | MOM | 2024-01-05 |  |  |  | BSS | Billing Related | L&T and NMSworks to conduct a detailed training session on operational activities of the Billing module post invoice generation |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN | [6 empty] | 1 | Open | Open
1179 | M485 | MOM | 2024-01-05 |  |  |  | BSS | Integration | Offer option to perform manual assignment and auto-assignment of Task Tickets |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1180 | M486 | MOM | 2024-01-05 |  |  |  | BSS | Dry Run | Demonstrate the complete Buyer and Seller journey |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1181 | M487 | MOM | 2024-01-05 |  |  |  | BSS | Design & Documentation | Ensure workflows/activities carried outside the BSS system are captured and mapped in BSS process flows |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1182 | M488 | MOM | 2024-01-05 |  |  |  | BSS | Billing Related | Introduce new column in the invoice template to distinguish billing items as ONE TIME or RECURRING |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1183 | M489 | MOM | 2024-01-05 |  |  |  | BSS | Billing Related | Review the solution of automatic QR code generation integration with Clear Tax or any other third party portal |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1184 | M49 | MOM | 2023-06-19 |  |  |  | GIS | User Experience | Network portal search functionality for objects |  | Critical | Open |  | Gtech | [5 empty] | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMGIS | Applications/Tools | OPEN | [6 empty] | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1185 | M490 | MOM | 2024-01-05 |  |  |  | BSS | Billing Related | Pending changes suggested by the Finance Director should be incorporated into the invoice template |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1186 | M491 | MOM | 2024-01-05 |  |  |  | BSS | Billing Related | Onboard Pioneer and start generating bills |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1187 | M492 | MOM | 2024-01-05 |  |  |  | BSS | Billing Related | Provide a detailed approach on how BSS is integrated with Bill Desk |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1188 | M493 | MOM | 2024-01-05 |  |  |  | BSS | Billing Related | Finalize bill desk integration-related final solution documents covering aspects suggested by Assistant Director-P&E, T-Fiber |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1189 | M494 | MOM | 2024-01-05 |  |  |  | BSS | Billing Related | Pending discussions from October’23 regarding bill desk integration should be completed |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1190 | M495 | MOM | 2024-01-05 |  |  |  | BSS | Design Features | Schedule a separate session with OEMs regarding Ticketing process through OSS/BSS referring to the current design template |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1191 | M496 | MOM | 2024-01-18 |  |  |  | BSS | Design Features | Finalize the Unique ID code convention for various attributes |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1192 | M497 | MOM | 2024-01-18 |  |  |  | BSS | Design Features | Integrate Circuit ID generation process in BSS |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1193 | M498 | MOM | 2024-01-18 |  |  |  | BSS | Design Features | Discuss and define a new naming convention for Circuit ID |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1194 | M499 | MOM | 2024-01-18 |  |  |  | BSS | Design Features | Review direct order through GUI interface |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1195 | M5 | MOM | 2023-03-27 |  |  |  | NSO | Full NOC Readiness | variance in L2 & L3, requiring time to understand along with NSO & OSS SMEs |  | Critical | Open |  | OSS Dashboards | [5 empty] | Jayant Madavi |  | Open | Open | [9 empty] | MOMNSO | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1196 | M50 | MOM | 2023-06-19 |  |  |  | GIS | User Experience | GIS function for bulk feasibility report |  | Critical | Open |  | Gtech |  |  | To fulfill this requirement, an external feasibility application or tool is needed, as it cannot be achieved within the GIS application,11 July 2025:- TFIBER is not agreed, asked to take with L&T upper management |  |  | Kaushalendra Kumar |  | Open | Open | [9 empty] | MOMGIS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1197 | M500 | MOM | 2024-01-18 |  |  |  | BSS | Design Features | Make dependency of A&O for generating Circuit ID independent of BSS |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1198 | M501 | MOM | 2024-01-18 |  |  |  | BSS | Design Features | Circuit ID should distinguish the origin if a new front-end system is introduced |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1199 | M502 | MOM | 2024-01-18 |  |  |  | BSS | Design Features | Include option to introduce new Customer ID when onboarding a new customer |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1200 | M503 | MOM | 2024-01-18 |  |  |  | BSS | Design Features | Transition from Excel-based format to live data for Lit-up and other relevant data |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1201 | M504 | MOM | 2024-01-18 |  |  |  | BSS | Design Features | Capture whether the network is linear or ring based |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1202 | M505 | MOM | 2024-01-18 |  |  |  | BSS | Design Features | Review and finalize the definition of 'Ready for Service' |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1203 | M506 | MOM | 2024-01-18 |  |  |  | BSS | Design Features | Implement user access control for converting from RFO to RFS in BSS |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1204 | M507 | MOM | 2024-01-18 |  |  |  | BSS | Design Features | Use terms from the industry library for representing 'Ready for Service', etc. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1205 | M508 | MOM | 2024-01-18 |  |  |  | BSS | Design Features | Retry the implementation of the Mandal-to-Mandal and Mandal-to-GP dark fiber process |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1206 | M509 | MOM | 2024-01-18 |  |  |  | BSS | Design Features | Integrate with GIS for live data capturing for feasibility check |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1207 | M51 | MOM | 2023-06-19 |  |  |  | GIS | User Experience | building logic / intelligence to populate the relevant information in the BoQ, presently available as a dump. |  | Critical | Open | Conflict | Gtech | [5 empty] | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMGIS | Applications/Tools | OPEN | [6 empty] | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1208 | M510 | MOM | 2024-01-18 |  |  |  | BSS | Design Features | Correct and finalize the changes suggested in the Lead page |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1209 | M511 | MOM | 2024-01-18 |  |  |  | BSS | Design Features | Enable communication to customers via Quote Tab in system |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1210 | M512 | MOM | 2024-01-18 |  |  |  | BSS | Design Features | Review Service order Form and related attributes |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1211 | M513 | MOM | 2024-01-18 |  |  |  | BSS | Design Features | Implement immediate Dark Fiber service for Mandal to GP and Mandal to Mandal |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1212 | M514 | MOM | 2024-01-18 |  |  |  | BSS | Design Features | Bring the approach for Bulk Feasibility into use |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1213 | M515 | MOM | 2024-01-18 |  |  |  | BSS | Design Features | Confirm the list of personnel who will be part of BSS operations |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1214 | M516 | MOM | 2024-01-18 |  |  |  | BSS | Design Features | Solve the issue of Document repository not being tagged with the order number |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1215 | M517 | MOM | 2024-01-18 |  |  |  | BSS | Design Features | Present a lead to order and GIS integration way forward for BSNL locations |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1216 | M518 | MOM | 2024-01-18 |  |  |  | BSS | Design Features | Confirm the timeline for GI-BB |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1217 | M519 | MOM | 2024-01-18 |  |  |  | BSS | Design Features | Confirm the timeline for T-Cell |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1218 | M52 | MOM | 2023-06-19 |  |  |  | GIS | Integration | GIS integration with WFM tool |  | Critical | Open |  | Gtech | [5 empty] | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMGIS | Applications/Tools | OPEN | [6 empty] | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1219 | M520 | MOM | 2024-01-18 |  |  |  | BSS | Design Features | Discuss with T-Fiber regarding Route Mode and Bridge Mode for Internet Leased Line product |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1220 | M521 | MOM | 2024-01-24 |  |  |  | NSO | O&M Strategy | Complete basic six products and field O&M |  | Critical | Open | [7 empty] | Jayant Madavi |  | Open | Open | [9 empty] | MOMNSO | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1221 | M522 | MOM | 2024-01-24 |  |  |  | BSS | Design & Documentation | Complete delivery of 24 variant products |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1222 | M523 | MOM | 2024-01-24 |  |  |  | BSS | Design & Documentation | Submit documentation for each of 6 products with respect to flow, regulatory, connectivity to other elements signed off with T-Fiber |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1223 | M524 | MOM | 2024-01-24 |  |  |  | NOC Operationalization | Design & Documentation | Provide final timeline for all conditional approvals & workshop tracker and detailed scope document |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1 | Completed & Approved | Closed after June
1224 | M525 | MOM | 2024-01-24 |  | OSS | OSS | OSS | Design Features | Present the readiness of service inventory module |  | Critical | Open |  |  |  |  | Inhouse solution |  |  | Suresh Pawar |  | Open | WIP | [9 empty] | MOMOSS | Applications/Tools | OPEN | OPEN | 0 |  |  | #N/A |  | 1 | Open | Open
1225 | M526 | MOM | 2024-01-24 |  |  |  | NOC Operationalization | Design & Documentation | Share detailed scope document and conditional approvals & workshops tracker |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1 | Completed & Approved | Closed after June
1226 | M527 | MOM | 2024-01-24 |  |  |  | Helpdesk | Helpdesk | Obtain T-Fiber's review in the next two days and submit revised Helpdesk SOPs |  | Critical | open |  |  |  | Closed | 24-Sep-25: Artefcts to be submiited for closure 11-Sep-25: Same has been Submitted |  |  | Siva Kumar |  |  | COMPLETED & APPROVED | [9 empty] | MOMHelpdesk | Helpdesk (Contact Center) | CLOSED |  |  |  | 2025-09-24 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\M1076 |  | 1 | Completed & Approved | Closed after June
1227 | M528 | MOM | 2024-01-24 |  |  |  | NOC Operationalization | O&M Strategy | Discuss and revert all pending points with MD(I/C), T-Fiber, and T-Fiber Operations Team |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1 | Completed & Approved | Closed after June
1228 | M529 | MOM | 2024-01-24 |  |  |  | NSO | Design Features | Provide road map detailing how the 6 products will move from manual process to automation |  | Critical | Open | [7 empty] | Jayant Madavi |  | Open | Open | [9 empty] | MOMNSO | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1229 | M53 | MOM | 2023-06-19 |  |  |  | GIS | User Experience | Automation of active connectivity |  | Critical | Open |  | Gtech |  |  | Duplicate with Point- 145 |  |  | Kaushalendra Kumar |  | Open | Duplicate | [9 empty] | MOMGIS | Applications/Tools | #N/A |  |  |  |  | #N/A |  | 1 | Open | Open
1230 | M530 | MOM | 2024-01-24 |  |  |  | NSO | Design Features | Share a plan about how 6 products Dark Fiber, GI-BB, T-Cell, T-VPN, T-Dill will move from manual process to automation |  | Critical | Open | [7 empty] | Jayant Madavi |  | Open | Open | [9 empty] | MOMNSO | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1231 | M531 | MOM | 2024-01-24 |  |  |  | BSS | Design Features | Finalize the readiness of all modules, including ticketing, Helpdesk, full automation, and WFM |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1232 | M532 | MOM | 2024-01-24 |  |  |  | GIS | Design Features | Discuss internally and provide a feasible response about leading the GIS data update process |  | Critical | Open | [7 empty] | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMGIS | Applications/Tools | OPEN | [6 empty] | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1233 | M533 | MOM | 2024-01-24 |  |  |  | Helpdesk | Design Features | Arrange Helpdesk toll-free (1800-XXX-XX) number |  | Critical | Open |  |  |  |  | 11-09-2025: Same as T366(472) Closed |  |  | Siva Kumar |  |  | COMPLETED & APPROVED | Yes | 2025-07-19 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\T366 | [6 empty] | MOMHelpdesk | Helpdesk (Contact Center) | CLOSED |  |  |  | 2025-07-19 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\T366 |  | 1 | Completed & Approved | Closed after June
1234 | M534 | MOM | 2024-01-24 |  |  |  | Helpdesk | Design Features | Share finalized notification readiness of SMS, WhatsApp & Email formats for T-Fiber customers |  | Critical | Open |  |  |  | WIP |  |  |  | Siva Kumar |  | Open | WIP | [9 empty] | MOMHelpdesk | Helpdesk (Contact Center) | OPEN | [6 empty] | 1 | Open | Open
1235 | M535 | MOM | 2024-01-24 |  |  |  | Helpdesk | Helpdesk | Arrange a demonstration of Helpdesk and IVR functions flow |  | Critical | open |  |  |  | Closed | 23-Sep-25: Demo completed shall be closed 11-Sep-25: Complied, Part of Interim NOC KPI |  |  | Siva Kumar |  |  | COMPLETED & APPROVED | [9 empty] | MOMHelpdesk | Helpdesk (Contact Center) | CLOSED |  |  |  | 2025-09-24 | Artefacts not Required |  | 1 | Completed & Approved | Closed after June
1236 | M536 | MOM | 2024-01-24 |  |  |  | Security & Regulatory Compliance | Compliance | Ensure L&T meets all regulatory compliance for poducts and provide NOC operationalisation |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1237 | M537 | MOM | 2024-01-25 |  |  |  | WFM | WFM Application | Complete the WFM-OSS integration |  | Critical | Open | [7 empty] | Kaushalendra Kumar |  | Open | WIP | [9 empty] | MOMWFM | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1238 | M538 | MOM | 2024-01-25 |  |  |  | WFM | WFM Application | Understand use cases of WFM integration with BSS |  | Critical | Open | [7 empty] | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMWFM | Applications/Tools | OPEN | [6 empty] | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1239 | M539 | MOM | 2024-01-25 |  |  |  | OSS | WFM Application | Define authorization of PoP RFS criteria for approval |  | Critical | Open |  |  |  |  | Not a WFM Point 11th July 2025:-this point needs to be discussed with Siva Sir to explore the possibility of accommodating the feature in the respective application, as it is not related to WFM |  |  | Suresh Pawar |  | Open | Shifted to OSS | [9 empty] | MOMOSS | Applications/Tools | #N/A | #N/A | #N/A |  |  | #N/A |  | 1 | Open | Open
1240 | M54 | MOM | 2023-06-19 |  |  |  | GIS | Integration | Sync issue error alerts in OSS and GIS |  | Critical | Open |  | Gtech | [5 empty] | Kaushalendra Kumar |  | Open | WIP | [9 empty] | MOMGIS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1241 | M540 | MOM | 2024-01-25 |  |  |  | WFM | WFM Application | Complete Fault Management and Trouble Ticketing assignment (OSS to WFM) |  | Critical | Open |  |  |  |  | DWDM Completed |  |  | Kaushalendra Kumar |  | Open | WIP | [9 empty] | MOMWFM | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1242 | M541 | MOM | 2024-01-25 |  |  |  | WFM | WFM Application | Distinguish between the use of GIS mobile app and WFM mobile app |  | Critical | Open | [7 empty] | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMWFM | Applications/Tools | OPEN | [6 empty] | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1243 | M542 | MOM | 2024-01-25 |  |  |  | WFM | WFM Application | Submit the NDA signed between L&T and M/S Lepton |  | Critical | Open | [7 empty] | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMWFM | Applications/Tools | OPEN | [6 empty] | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1244 | M543 | MOM | 2024-01-25 |  |  |  | WFM | WFM Application | Submit sample reports and dashboards of WFM package |  | Critical | Open | [7 empty] | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMWFM | Applications/Tools | OPEN | [6 empty] | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1245 | M544 | MOM | 2024-01-25 |  |  |  | WFM | WFM Application | Verify proposed solution for WFM |  | Critical | Open | [7 empty] | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMWFM | Applications/Tools | OPEN | [6 empty] | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1246 | M545 | MOM | 2024-01-25 |  |  |  | WFM | WFM Application | Dry run and operationalize three routes for testing WFM with actual data |  | Critical | Open | [7 empty] | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMWFM | Applications/Tools | OPEN | [6 empty] | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1247 | M546 | MOM | 2024-01-25 |  |  |  | WFM | WFM Application | Conduct weekly training sessions for patrollers on WFM app |  | Critical | Open |  |  |  |  | Completed on 100 Licenced Users, three months weekly training provide to PKG-A, Training given to PKG-B & C also |  |  | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMWFM | Applications/Tools | OPEN | [6 empty] | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1248 | M547 | MOM | 2024-01-25 |  |  |  | WFM | WFM Application | Check and confirm the watermarking feature on photos taken by field users |  | Critical | Open | [7 empty] | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMWFM | Applications/Tools | OPEN | [6 empty] | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1249 | M548 | MOM | 2024-02-13 |  |  |  | Security & Regulatory Compliance | RMC meeting | Implement IP-MAC binding to prevent IP spoofing |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1250 | M549 | MOM | 2024-02-13 |  |  |  | Security & Regulatory Compliance | RMC meeting | Ensure the standardization of usernames across applications |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1251 | M55 | MOM | 2023-06-22 |  |  |  | Security & Regulatory Compliance | Audit | Scope submission for external audit |  | Critical | Open |  |  |  |  | Audit done by Allied Boston. And further external audit to be done by TFiber vendor |  |  | Sarmendra |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | Artefacts to be Submitted |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1252 | M550 | MOM | 2024-02-13 |  |  |  | Security & Regulatory Compliance | RMC meeting | Obtain T-Fiber's review and approval for policy documents |  | Critical | Open |  |  |  |  | As process this is being followed. Mails being sent for approvals. This point is adhered |  |  | Sarmendra |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | Artefacts to be Submitted |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1253 | M551 | MOM | 2024-02-13 |  |  |  | BSS | Product | Work on implementing the guidelines for Dark Fiber from T-Fiber and GIS team |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1254 | M552 | MOM | 2024-02-13 |  |  |  | BSS | Product | Get clarity on integration rules and timeline for activating 'Ready for Order' and 'Ready for Service' statuses |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1255 | M553 | MOM | 2024-02-13 |  |  |  | BSS | Product | Implement user access control for converting from RFO to RFS |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1256 | M554 | MOM | 2024-02-13 |  |  |  | BSS | Product | Populate data fields automatically while feeding site information |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1257 | M555 | MOM | 2024-02-13 |  |  |  | BSS | Product | Submit a document explaining reformatted guidelines for service |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1258 | M556 | MOM | 2024-02-13 |  |  |  | Security & Regulatory Compliance | RMC meeting | Initiate the implementation of Mandal-to-Mandal and Mandal-to-GP dark fiber process |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1259 | M557 | MOM | 2024-02-13 |  |  |  | GIS | Feasibility | Introduce the approach for Bulk Feasibility |  | Critical | Open |  |  |  |  | To fulfill this requirement, an external feasibility application or tool is needed, as it cannot be achieved within the GIS application, 11 July 2025:- TFIBER is not agreed, asked to take with L&T upper management |  |  | Kaushalendra Kumar |  | Open | Open | [9 empty] | MOMGIS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1260 | M558 | MOM | 2024-02-13 |  |  |  | BSS |  | Capture and demonstrate BSS integration with Bill Desk |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1261 | M559 | MOM | 2024-02-13 |  |  |  | BSS |  | Ensure all 29 BSNL locations are loaded for lead to order presentation |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1262 | M56 | MOM | 2023-06-22 |  |  |  | Security & Regulatory Compliance | Audit | External agency Audit with certification |  | Critical | Open |  |  |  |  | Audit done by Allied Boston. And further external audit to be done by TFiber vendor |  |  | Sarmendra |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | Artefacts to be Submitted |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1263 | M560 | MOM | 2024-02-13 |  |  |  | Security & Regulatory Compliance | RMC meeting | Finalize GI-BB timeline |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1264 | M561 | MOM | 2024-02-13 |  |  |  | Security & Regulatory Compliance | RMC meeting | Finalize T-Cell timeline |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1265 | M562 | MOM | 2024-02-13 |  |  |  | Security & Regulatory Compliance | RMC meeting | Make user access control to convert from RFO to RFS |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1266 | M563 | MOM | 2024-02-13 |  |  |  | Security & Regulatory Compliance | RMC meeting | Revisit the actual requirements of SSL certifications and implementation policies |  | Critical | Open |  |  |  |  | Duplicate point. Hence clsoing this point |  |  | Sarmendra |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | Artefacts to be Submitted |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1267 | M564 | MOM | 2024-02-13 |  |  |  | Security & Regulatory Compliance | RMC meeting | Submit a document with details on implementing the suggested process changes |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1268 | M565 | MOM | 2024-02-13 |  |  |  | Security & Regulatory Compliance | RMC meeting | Develop a standard training program followed by quizzes for improving security |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1269 | M566 | MOM | 2024-02-13 |  |  |  | Security & Regulatory Compliance | RMC meeting | Start a weekly security bulletin |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1270 | M567 | MOM | 2024-02-13 |  |  |  | Security & Regulatory Compliance | RMC meeting | Study the best practices of the State Security Operations Center and implement them |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1271 | M568 | MOM | 2024-02-14 |  |  |  | NSO | Service provisioning | Resolve issues with the NSO features |  | Critical | Open | [7 empty] | Jayant Madavi |  | Open | Open | [9 empty] | MOMNSO | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1272 | M569 | MOM | 2024-02-14 |  |  |  | NSO | Service provisioning | Fast track the making of the pre-production environment |  | Critical | Open | [7 empty] | Jayant Madavi |  | Open | Open | [9 empty] | MOMNSO | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1273 | M57 | MOM | 2023-06-22 |  |  |  | Security & Regulatory Compliance | Audit | external auditor to be government empanelled (MeitY / STQC). |  | Critical | Open |  |  |  |  | Audit done by Allied Boston. And further external audit to be done by TFiber vendor |  |  | Sarmendra |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | Artefacts to be Submitted |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1274 | M570 | MOM | 2024-02-14 |  |  |  | NSO | Service provisioning | Upload government orders in the BSS |  | Critical | Open | [7 empty] | Jayant Madavi |  | Open | Open | [9 empty] | MOMNSO | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1275 | M571 | MOM | 2024-02-14 |  |  |  | NSO | Service provisioning | Re-initiate the daily cadence calls |  | Critical | Open | [7 empty] | Jayant Madavi |  | Open | Open | [9 empty] | MOMNSO | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1276 | M572 | MOM | 2024-02-14 |  |  |  | NSO | Service provisioning | Make all products for the government and cellular business segments ready by |  | Critical | Open | [7 empty] | Jayant Madavi |  | Open | Open | [9 empty] | MOMNSO | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1277 | M573 | MOM | 2024-02-14 |  |  |  | BSS | Dry Run | Finish all Dry runs |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1278 | M574 | MOM | 2024-02-14 |  |  |  | NSO | Service provisioning | Work parallelly on household business products |  | Critical | Open | [7 empty] | Jayant Madavi |  | Open | Open | [9 empty] | MOMNSO | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1279 | M575 | MOM | 2024-02-14 |  |  |  | NSO | Service provisioning | Onboard all L&T SMEs and involve OEMs for 15th March'24 target |  | Critical | Open | [7 empty] | Jayant Madavi |  | Open | Open | [9 empty] | MOMNSO | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1280 | M576 | MOM | 2024-02-14 |  |  |  | Helpdesk | Helpdesk | Ensure helpdesk is ready by |  | Critical | Open |  |  |  | WIP |  |  |  | Siva Kumar |  | Open | WIP | [9 empty] | MOMHelpdesk | Helpdesk (Contact Center) | OPEN | [6 empty] | 1 | Open | Open
1281 | M577 | MOM | 2024-02-14 |  |  |  | NOC Operationalization | O&M Strategy | Provide daily updates on the progress made in NOC by |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1 | Completed & Approved | Closed after June
1282 | M578 | MOM | 2024-02-14 |  |  |  | NOC Operationalization | O&M Strategy | Resolve all issues |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1 | Completed & Approved | Closed after June
1283 | M579 | MOM | 2024-02-14 |  |  |  | NOC Operationalization | O&M Strategy | Establish two distinct setup—one for live operations, another for pre-production |  | Critical | Completed |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1 | Completed & Approved | Closed after June
1284 | M58 | MOM | 2023-06-22 |  |  |  | Security & Regulatory Compliance | Audit | simulation of attacks on the network and hardening of applications in the NOC |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1285 | M580 | MOM | 2024-02-14 |  |  |  | NOC Operationalization | O&M Strategy | Share all related details for pre-production setup to Director-NOC, T-Fiber |  | Critical | Completed |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1 | Completed & Approved | Closed after June
1286 | M581 | MOM | 2024-02-16 |  |  |  | BSS | O&M Strategy | Implement ticket tracking with OSS Service Manager |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1287 | M582 | MOM | 2024-02-16 |  |  |  | BSS | GIS | Address challenge in BSS-GIS integration |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1288 | M583 | MOM | 2024-02-16 |  |  |  | BSS | GIS | Ensure collection of required / optional parameters at each step |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1289 | M584 | MOM | 2024-02-16 |  |  |  | BSS | CRM | Reconsider requirement for document collection in CAF approval stage |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1290 | M585 | MOM | 2024-02-16 |  |  |  | BSS | CRM | Introduce 'Manual reference ID' attribute in service order form |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1291 | M586 | MOM | 2024-02-16 |  |  |  | BSS | CRM | Enable option to close or update work order status manually |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1292 | M587 | MOM | 2024-02-16 |  |  |  | BSS | CRM | Alter selections or drop-down options in Lead, Opportunity, and Service Order page |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1293 | M588 | MOM | 2024-02-16 |  |  |  | BSS | CRM | Renaming certain attributes in the Opportunity Screen |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1294 | M589 | MOM | 2024-02-16 |  |  |  | BSS | CRM | Rename 'Normal Loss' attribute to 'Optical Loss' in service order form |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1295 | M59 | MOM | 2023-06-22 |  |  |  | WFM | Mobile Application | Mobile App supported in Android & IOS |  | Critical | Open | [7 empty] | Kaushalendra Kumar |  | Open | Open | [9 empty] | MOMWFM | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1296 | M590 | MOM | 2024-02-16 |  |  |  | BSS | CRM | Add multiple reference documents received from customer in service order |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1297 | M591 | MOM | 2024-02-16 |  |  |  | BSS | BSS | Display order count bar chart in the Dashboard |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1298 | M592 | MOM | 2024-02-16 |  |  |  | BSS | BSS | Issues observed in the generated CAF to be resolved |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1299 | M593 | MOM | 2024-02-16 |  |  |  | BSS | GIS | Automatically populate Site FDMS name post-GIS integration |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1300 | M594 | MOM | 2024-02-16 |  |  |  | BSS | BSS | Limit 'retry' options in BSS until process failure |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1301 | M595 | MOM | 2024-02-16 |  |  |  | BSS | WFM Application | Ensure multiple tasks tied to single work order are visible in WFM |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1302 | M596 | MOM | 2024-02-16 |  |  |  | BSS | WFM Application | Make manual acceptance function available in BSS for WFM |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1303 | M597 | MOM | 2024-02-16 |  |  |  | BSS | NSO | Resolve configuration issues to operationalize Product Catalogue module |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1304 | M598 | MOM | 2024-02-16 |  |  |  | BSS | BSS | Physical survey and customer signoff to be included in the next step |  | NON-Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1305 | M599 | MOM | 2024-02-16 |  |  |  | BSS | WFM Application | Feedback on WFM stages to be given in the next meeting |  | NON-Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1306 | M6 | MOM | 2023-03-27 |  |  |  | NOC Operationalization | Handbook & SOPs | Clear accountability and responsibility of SMEs, along with an presented RASCI matrix |  | Critical | Completed |  | NSO |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1 | Completed & Approved | Closed after June
1307 | M60 | MOM | 2023-06-28 |  |  |  | NOC Operationalization | Handbook & SOPs | Classification of Procedures and processes from ITIL and eTOM |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1 | Completed & Approved | Closed after June
1308 | M600 | MOM | 2024-02-16 |  |  |  | BSS | WFM Application | Generate customer signoff through WFM and create separate tabs for storing OTDR traces and customer signoff |  | NON-Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1309 | M601 | MOM | 2023-07-03 |  |  |  | Security & Regulatory Compliance | Internal Audit | Security Audit |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1310 | M602 | MOM | 2023-07-03 |  |  |  | Security & Regulatory Compliance | Internal Security | Acceptable Usage of information |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1311 | M603 | MOM | 2023-07-03 |  |  |  | Security & Regulatory Compliance | Safety | ERT and mock drills |  | Critical | Open |  |  |  |  | Mock drills, safety briefing and training is done |  |  | Srinivas Kommreddy |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | Artefacts to be uploaded |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1312 | M604 | MOM | 2023-07-03 |  |  |  | Security & Regulatory Compliance | Internal Security | Gate pass for materials |  | Critical | Open |  |  |  |  | Gate pass process in place at TNOC |  |  | Srinivas Kommreddy |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | Artefacts to be uploaded |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1313 | M605 | MOM | 2023-07-03 |  |  |  | Security & Regulatory Compliance | Internal Security | VAPT |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1314 | M606 | MOM | 2023-07-03 |  |  |  | Security & Regulatory Compliance | Internal Security | Security Incident management |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1315 | M607 | MOM | 2023-07-03 |  |  |  | Security & Regulatory Compliance | Safety | Training |  | Critical | Open |  |  |  |  | Mock drills, safety briefing and training is done |  |  | Srinivas Kommreddy |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | Artefacts to be uploaded |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1316 | M608 | MOM | 2023-07-03 |  |  |  | Security & Regulatory Compliance | Internal Security | Assest Management |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1317 | M609 | MOM | 2023-07-03 |  |  |  | Security & Regulatory Compliance | Internal Security | Crytography |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1318 | M61 | MOM | 2023-06-28 |  |  |  | NOC Operationalization | Resource Related | L&T with ITIL or eTOM certifications |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMNOC Operationalization | Network | OPEN | [6 empty] | 1 | Open | Open
1319 | M610 | MOM | 2023-07-03 |  |  |  | Security & Regulatory Compliance | Internal Security | Access control |  | Critical | Open |  |  |  |  | Physical access control in place at TNOC. FOr system Access control, this is duplicate point |  |  | Sarmendra |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | Artefacts to be Submitted |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1320 | M611 | MOM | 2023-07-04 | P3 |  |  | NOC Operationalization | Operational Handbook | Incorporate changes into the proposed operational framework as per T-Fiber's review, including adding a Vision and Mission statement, identifying additional relevant processes, updating the organisation structure, and correcting inconsistencies in the documentation of processes. |  | Critical | Open |  |  |  |  | SOPs approved, have flow diagrams |  |  | Ahmad | 2025-09-20 |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  | Documentation | 2025-09-24 | \\172.28.9.23\tnocreports\Approved Process and SOP_ T Fiber\SOP |  | 1 | Completed & Approved | Closed after June
1321 | M612 | MOM | 2023-07-04 |  |  |  | NOC Operationalization | Operational Handbook | Detail flow charts of the processes into SOPs. |  | Critical | Open |  |  |  | Artefacts to be submitted | 24-Sep-25: Updated Document Shared 23-Aug-23 |  |  | Siva Kumar |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-24 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\M104,105,109,111,113,115,122,123,127,128,130,132,162 |  | 1 | Completed & Approved | Closed after June
1322 | M613 | MOM | 2023-07-04 |  | OSS | OSS | OSS | O&M Strategy | Justify the use of the implemented HPSM tool as best suited to ITIL compliant processes. |  | Critical | Open | [7 empty] | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | AD-UT-Tfiber | 2025-09-12 | \\172.28.9.34\SHARE DRIVE\Artefacts_T-Fiber TNOC Tracker\OSS | [6 empty] | MOMOSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1323 | M614 | MOM | 2023-07-04 |  |  |  | NOC Operationalization | O&M Strategy | Revert on the segregation of current, interim, and final organisation structure along with the timelines in which these should be applicable. |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1 | Completed & Approved | Closed after June
1324 | M615 | MOM | 2023-07-04 |  |  |  | NOC Operationalization | Hiddencove suggestions | Include the processes recommended by the external auditor (Hiddencove) such as Handover deployment to Operation process, Service Request Process, Configuration Management, Asset Management, Critical Event Management, Site Access Management, Handover Deployment to Operations Process (Transition Process). |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMNOC Operationalization | Network | OPEN | [6 empty] | 1 | Open | Open
1325 | M616 | MOM | 2023-07-04 |  |  |  | NOC Operationalization | O&M Strategy | Include a Continuous Improvement framework covering the process of identification/initiation of the areas for continuous improvement on a regular basis. Standard frameworks like KAIZEN Or PDCA are suggested. |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1 | Completed & Approved | Closed after June
1326 | M617 | MOM | 2023-07-04 | P3 |  |  | NOC Operationalization | Escalation Matrix | Include aspects like document processes, RASCI & Escalation Matrix in NOC Operational Framework. |  | Critical | Open | [7 empty] | Ahmad | 2025-10-07 | Open | Open | [9 empty] | MOMNOC Operationalization | Network | OPEN |  |  | Documentation |  | #N/A |  | 1 | Open | Open
1327 | M618 | MOM | 2023-07-04 |  |  |  | NOC Operationalization | O&M Strategy | Highlight the processes that will be implemented and ready by 15th August ’23 and provide a roadmap of which module will be ready by when. |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1 | Completed & Approved | Closed after June
1328 | M619 | MOM | 2023-07-04 | P3 |  |  | NOC Operationalization | Escalation Matrix | Define clear roles and responsibilities related to L1, L2 & L3 with an appropriate number of resources which should be according to the fault rates. |  | Critical | Open |  |  |  |  | 24-Sep-25: Updated Document Shared 23-Aug-23 |  |  | Ahmad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  | Not related to delivery | 2025-09-24 | \\172.28.9.23\tnocreports\TNOC Manpower_CVs\NOC Resources Details & Roles |  | 1 | Completed & Approved | Closed after June
1329 | M62 | MOM | 2023-06-28 | P3 |  |  | NOC Operationalization | Handbook & SOPs | All KPIs details submission |  | Critical | Completed |  |  |  |  | NOC KPI report for submitted and signed for Oct24 to Dec24. Jan to March25 KPI submitted but sign-off pending with TFiber |  |  | Ahmad | 2025-09-20 |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  | Documentation | 2025-09-24 | \\172.28.9.23\tnocreports\Monthly KPI Reports\FY 24-25\NOV-24\Interim NOC KPI for Signoff_ NOV-24 |  | 1 | Completed & Approved | Closed after June
1330 | M620 | MOM | 2023-07-04 |  |  |  | NOC Operationalization | GIS | Ensure the coverage of GIS operations as part of a single integrated picture of NOC, Field including handovers to/from Field and NOC. |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1 | Completed & Approved | Closed after June
1331 | M621 | MOM | 2023-07-04 |  |  |  | Helpdesk | Helpdesk | Evaluate the readiness of the current Helpdesk to start taking calls for GI and validate the sufficiency of the Helpdesk based on the fault rate, waiting time for each agent etc. by 15th July'23 |  | Critical | open |  |  |  | Closed | 24-Sep-25: Approved and shall be closed 11-Sep-25: Changed and operational Now |  |  | Siva Kumar |  |  | COMPLETED & APPROVED | [9 empty] | MOMHelpdesk | Helpdesk (Contact Center) | CLOSED |  |  |  | 2025-09-24 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\M117,126,728 |  | 1 | Completed & Approved | Closed after June
1332 | M622 | MOM | 2023-07-04 | P3 |  |  | NOC Operationalization | O&M Strategy | Submission of the proposed TNOC Operational Framework document on 9th July ’23 for review. |  | Critical | Open |  |  |  |  | 223-Sep-25: Artefacts uploded |  |  | Ahmad | 2025-10-07 |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  | Documentation | 2025-09-22 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\TNOC\M622 |  | 1 | Completed & Approved | Closed after June
1333 | M623 | MOM | 2023-07-04 |  |  |  | NOC Operationalization | O&M Strategy | Next review on Operational Framework by 11th July ’23. |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1 | Completed & Approved | Closed after June
1334 | M624 | MOM | 2023-07-04 |  |  |  | NOC Operationalization | O&M Strategy | Develop a process and framework for order fulfillment, ensuring that all applications and tools are ready for production. |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMNOC Operationalization | Network | OPEN | [6 empty] | 1 | Open | Open
1335 | M625 | MOM | 2023-07-04 |  |  |  | NOC Operationalization | O&M Strategy | Prepare a more comprehensive plan for product catalog and infrastructure management and maintenance. |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMNOC Operationalization | Network | OPEN | [6 empty] | 1 | Open | Open
1336 | M626 | MOM | 2023-07-04 |  |  |  | NOC Operationalization | O&M Strategy | Develop a comprehensive plan for improving network service management and address any issues related to MPLS-related resources. |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMNOC Operationalization | Network | OPEN | [6 empty] | 1 | Open | Open
1337 | M627 | MOM | 2023-07-04 |  |  |  | NOC Operationalization | Dry Run | Schedule the first dry run for the NOC Operationalization for 24th July '23. |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1 | Completed & Approved | Closed after June
1338 | M628 | MOM | 2023-07-04 |  |  |  | WFM | Mobile Application | Develop and present mobile applications that are functional and meet the needs and preferences of users by 15th August '23. |  | Critical | Open | [7 empty] | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMWFM | Applications/Tools | OPEN | [6 empty] | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1339 | M629 | MOM | 2023-07-04 |  |  |  | NOC Operationalization |  | The Tools Assigned the Operation to be ready and deployed by 9th July '23. |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMNOC Operationalization | Network | OPEN | [6 empty] | 1 | Open | Open
1340 | M63 | MOM | 2023-06-28 |  |  |  | NOC Operationalization | Handbook & SOPs | The difference between problem and issue management. |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1 | Completed & Approved | Closed after June
1341 | M630 | MOM | 2023-07-04 |  |  |  | NOC Operationalization |  | HLD & LLD Approval: L&T to expedite closure of pending points with daily discussions, aiming for 6th April '23. |  | NON-Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMNOC Operationalization | Network | OPEN | [6 empty] | 1 | Open | Open
1342 | M631 | MOM | 2023-07-04 |  |  |  | BSS | T-Cell Launch | Cell Tower Launch: CRM-based demo by L&T with manual NSO loop and GIS by 27th March '23. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1343 | M632 | MOM | 2023-07-04 |  |  |  | BSS | T-Cell Launch | Dependencies for Cell Tower Launch: L&T to address payment gateway integration, product catalog sign-off, and E2E flows with T-Fiber approval. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1344 | M633 | MOM | 2023-07-04 |  |  |  | BSS | T-Cell Launch | GIS Feasibility for Cell Tower: L&T to present an alternative solution within 2 to 3 days and document risks and mitigation for seamless migration. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1345 | M634 | MOM | 2023-07-04 |  |  |  | GIS | GIS Completion | GIS OEM - Hexagon: L&T to ensure GIS readiness within 2 to 4 weeks for service provisioning automation. |  | Critical | Open | [7 empty] | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMGIS | Applications/Tools | OPEN | [6 empty] | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1346 | M635 | MOM | 2023-07-04 |  |  |  | OEM Related | Security | Cisco Firewall Limitation: L&T to demonstrate GI Internet workflow by 5th April '23 and confirm support for full capacity of 30 thousand institutions. |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMOEM Related | OEM Related Issues | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1 | Completed & Approved | Closed after June
1347 | M636 | MOM | 2023-07-04 |  |  |  | PM Tool Issue | PM Tool Issue | Digital Process for GI Connectivity: L&T to present a plan for digital process and tools usage by 5th April '23, with the possibility of presenting earlier in Cadence calls. |  | NON-Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMPM Tool Issue | Applications | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1 | Completed & Approved | Closed after June
1348 | M637 | MOM | 2023-07-04 |  |  |  | BSS | BSS | BSS Cadence Calls: L&T to initiate and lead the required Cadence calls to meet project timelines. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1349 | M638 | MOM | 2023-07-04 |  |  |  | NOC Operationalization | Resource Augmentation | IPMPLS SME Resignation: L&T to address the resignation and retention of the IPMPLS SME. |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1 | Completed & Approved | Closed after June
1350 | M639 | MOM | 2023-07-04 |  |  |  | NOC Operationalization | Communication Matrix | Project SPOC: Mr. Anthony from L&T to coordinate across all domains to deliver the project. |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1 | Completed & Approved | Closed after June
1351 | M64 | MOM | 2023-06-28 |  |  |  | NOC Operationalization | Handbook & SOPs | Establish a configuration management system to monitor all changes in NOC operations |  | Critical | Completed |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMNOC Operationalization | Network | OPEN | [6 empty] | 1 | Open | Open
1352 | M640 | MOM | 2023-07-04 |  |  |  | NOC Operationalization | Service Solution | T-NOC Operationalisation Plan: L&T to present a phased plan on 27th March '23 for minimal readiness by 5th April, stage 2 by 20th April, and stage 3 by 30th April, with the entire T-NOC operational by 30th April and launch by 15th May '23. |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMNOC Operationalization | Network | OPEN | [6 empty] | 1 | Open | Open
1353 | M641 | MOM | 2023-07-04 |  |  |  | Field Related | Resource Augmentation | Resource Deployment for District Delivery: L&T to ramp up resources to meet the delivery target of five and a half districts by 7th April '23. |  | Critical | Open | [7 empty] | S Kodali |  | Open | Open | [9 empty] | MOMField Related | Field Related issues | OPEN |  |  | Project Team |  | Artefacts to be uploaded |  | 1 | Open | Open
1354 | M642 | MOM | 2023-07-04 |  |  |  | Field Related | Zonal Path connectivity | Zonal Path Completion: L&T to complete Medak to Mahbubnagar Zonal path by 31st March and AT by 15th April '23; AT of other completed zonal paths by 31st March '23. |  | Critical | Open | [7 empty] | S Kodali |  | Open | Open | [9 empty] | MOMField Related | Field Related issues | OPEN |  |  | Project Team |  | #N/A |  | 1 | Open | Open
1355 | M643 | MOM | 2023-07-05 |  |  |  | GIS | GIS Completion | Evaluate the current readiness status of the GIS tool and address the pending issues. |  | Critical | Open | [7 empty] | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMGIS | Applications/Tools | OPEN | [6 empty] | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1356 | M644 | MOM | 2023-07-05 |  |  |  | BSS | BSS | Ensure that the product being developed meets all the discussed and agreed-upon requirements and features. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1357 | M645 | MOM | 2023-07-05 |  |  |  | BSS | Dry Run | Complete the BSS Demo according to the feedback points received and demonstrate progress on the same by the first week of May. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1358 | M646 | MOM | 2023-07-05 |  |  |  | NOC Operationalization | NOC Operationalization | Develop and present a comprehensive proposal for improving the appearance of T-NOC. |  | Critical | Open |  |  |  |  | TNOC passive infra delivered, AT done |  |  | Ahmad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  | Need clarity | 2025-09-19 | Artefacts not Required |  | 1 | Completed & Approved | Closed after June
1359 | M647 | MOM | 2023-07-05 |  |  |  | GIS | GIS Completion | Submit revise plan for Complete GIS Tool (Basic) Readiness by 30th April’23, GIS Tool (Advanced) Readiness by 31st May’23, and GIS Tool (Integration) Readiness by 30th June’23. |  | Critical | Open | [7 empty] | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMGIS | Applications/Tools | OPEN | [6 empty] | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1360 | M648 | MOM | 2023-07-05 |  |  |  | GIS | GIS Completion | Submit responses on concerns of the number of GIS licences for data upload and readiness of current helpdesk to start taking calls for GI. |  | Critical | Open |  |  |  |  | TFIBER is a critical dependency for closing the GIS licenses |  |  | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMGIS | Applications/Tools | OPEN | [6 empty] | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1361 | M649 | MOM | 2023-07-05 | P3 |  |  | NOC Operationalization | Operational Framework | Identify and rectify inconsistencies in the document processes presented in the NOC's Operational Framework. |  | Critical | Open | [7 empty] | Ahmad | 2025-10-07 | Open | Open | [9 empty] | MOMNOC Operationalization | Network | OPEN |  |  | Documentation |  | #N/A |  | 1 | Open | Open
1362 | M65 | MOM | 2023-06-28 | P3 |  |  | NOC Operationalization | Handbook & SOPs | Create an archival policy for documentation storage, including retrieval systems, access matrix, and policies |  | Critical | Open | [7 empty] | Ahmad | 2025-10-07 | Open | Open | [9 empty] | MOMNOC Operationalization | Network | OPEN |  |  | Documentation |  | #N/A |  | 1 | Open | Open
1363 | M650 | MOM | 2023-07-05 |  |  |  | BSS | Dry Run | Provide BSS Demo with actual auto-feasibility check by 6th April. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1364 | M651 | MOM | 2023-07-05 |  |  |  | BSS | Dry Run | Present a clear day-wise plan for BSS readiness by 30th September 2023 for full-fledged production with automated GIS. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1365 | M652 | MOM | 2023-07-05 |  |  |  | Field Related | Full NOC Readiness | Complete the connection of 589 Mandals by 1st week of June, with an expectation of minimum 3 hours and maximum of 5 hours for each Mandal. |  | Critical | Open | [7 empty] | S Kodali |  | Open | Open | [9 empty] | MOMField Related | Field Related issues | OPEN |  |  | Project Team |  | #N/A |  | 1 | Open | Open
1366 | M653 | MOM | 2023-07-05 |  |  |  | NOC Operationalization | Full NOC Readiness | Highlight the processes that will be implemented and ready by 15th August ’23 and provide a roadmap of which module will be ready by when during the meeting on 4th July'23. |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMNOC Operationalization | Network | OPEN | [6 empty] | 1 | Open | Open
1367 | M654 | MOM | 2023-07-05 |  |  |  | Security & Regulatory Compliance | Full NOC Readiness | Still update on the perceived firewall limitation issue is pending , asked on 3rd April'24 |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1368 | M655 | MOM | 2023-07-05 |  |  |  | BSS | WFM Application | Submit internal E2E Project Plan on 31st March’23 as committed for review. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1369 | M656 | MOM | 2023-07-05 |  |  |  | BSS | Dry Run | BSS Demo on 6th April’23 must provide order feasibility. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1370 | M657 | MOM | 2023-07-05 |  |  |  | NOC Operationalization | Operational Framework | Ensure that all references to processes from ITIL and eTOM are clearly explained and utilized in the operational framework. |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1 | Completed & Approved | Closed after June
1371 | M658 | MOM | 2023-07-05 | P3 |  |  | NOC Operationalization | Escalation Matrix | Implement a robust RASCI & Escalation Matrix in the NOC Operational Framework. |  | Critical | Open | [7 empty] | Ahmad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  | Not related to delivery | 2025-09-19 | Artefacts not Required |  | 1 | Completed & Approved | Closed after June
1372 | M659 | MOM | 2023-07-05 |  |  |  | GIS | GIS Completion | Integrate the processes recommended by the external auditor into the process flow of GIS readiness. |  | Critical | Open |  |  |  |  | GIS SOP |  |  | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMGIS | Applications/Tools | OPEN | [6 empty] | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1373 | M66 | MOM | 2023-06-28 | P3 |  |  | NOC Operationalization | Handbook & SOPs | Define categories of problems along with a resolution approach plan |  | Critical | Open | [7 empty] | Ahmad | 2025-10-07 | Open | Open | [9 empty] | MOMNOC Operationalization | Network | OPEN |  |  | Documentation |  | #N/A |  | 1 | Open | Open
1374 | M660 | MOM | 2023-07-05 |  |  |  | BSS | GIS | Perform manual feasibility checking until the GIS tool is ready and data is uploaded into the tool. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1375 | M661 | MOM | 2023-07-05 |  |  |  | BSS | GI Demo | Showcase the GI demo by the end of May. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1376 | M662 | MOM | 2023-07-05 |  |  |  | GIS | GIS Completion | Improve coordination with GIS, OEMs, and explore the possibility of developing a new GIS OEM to deliver the requirements of T-Fiber. |  | Critical | Open | [7 empty] | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMGIS | Applications/Tools | OPEN | [6 empty] | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1377 | M663 | MOM | 2023-07-05 |  |  |  | Helpdesk | Helpdesk | Take the performance measurement processes into consideration for measuring the performance of the identified Helpdesk resources. |  | Critical | Open |  |  |  | Closed | 24-Sep-25: Approved and shall be closed |  |  | Siva Kumar |  |  | COMPLETED & APPROVED | [9 empty] | MOMHelpdesk | Helpdesk (Contact Center) | CLOSED |  |  |  | 2025-09-24 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\M114,722,134 |  | 1 | Completed & Approved | Closed after June
1378 | M664 | MOM | 2023-07-05 |  |  |  | BSS | CRM | Handle more professionally the field activity portion of the CRM flow. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1379 | M665 | MOM | 2023-07-05 |  |  |  | NSO | NSO | Arrive at feasible alternatives to handle situations such as NSO provisioning timeouts, submit alternative approaches in such scenarios and revert with exact steps taken to achieve this. |  | Critical | Open | [7 empty] | Jayant Madavi |  | Open | Open | [9 empty] | MOMNSO | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1380 | M666 | MOM | 2023-07-05 |  |  |  | NOC Operationalization | Daily Meetings | Officially commence up the daily stand-up call on 16th June ’23, with the call to be held routinely from this date. |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1 | Completed & Approved | Closed after June
1381 | M667 | MOM | 2023-07-05 |  |  |  | BSS | Dry Run | BSS Demo on 6th April ’23 to provide order feasibility. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1382 | M668 | MOM | 2023-07-05 |  |  |  | NOC Operationalization | Operational Framework | Review of the Operational Framework by 11th July ’23. |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1 | Completed & Approved | Closed after June
1383 | M669 | MOM | 2023-07-05 |  |  |  | BSS | T-Cell Launch | Showcase the demo for T-Cell on 6th April ’23. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1384 | M67 | MOM | 2023-06-28 |  |  |  | NOC Operationalization | Handbook & SOPs | Adopt a continuous improvement framework such as DMAIC and Kaizen for process improvement |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1 | Completed & Approved | Closed after June
1385 | M670 | MOM | 2023-07-05 |  |  |  | BSS | Billing Related | Auto-approval of the Invoice by Finance users. |  | NON-Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1386 | M671 | MOM | 2023-07-05 |  |  |  | Helpdesk | Helpdesk | Make Helpdesk operational by 15th July ’23. |  | Critical | Open |  |  |  | WIP |  |  |  | Siva Kumar |  | Open | WIP | [9 empty] | MOMHelpdesk | Helpdesk (Contact Center) | OPEN | [6 empty] | 1 | Open | Open
1387 | M672 | MOM | 2023-07-21 |  |  |  | BSS | BSS | BSS Readiness Confirmation: L&T to review and update overall readiness for E2E NOC by EOD 8th September '23, including confirmation on launch deliverables and interim launch processes . |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1388 | M673 | MOM | 2023-07-21 |  |  |  | BSS | Dry Run | BSS Demo Observations: L&T to address observations from the BSS Demo on 24th July '23 and action items from the meeting with Director-Finance, T-Fiber . |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1389 | M674 | MOM | 2023-07-21 |  |  |  | WFM |  | WFM Integration: L&T commenced WFM integration and will arrange a demonstration for field operations . |  | Critical | Open | [7 empty] | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMWFM | Applications/Tools | OPEN | [6 empty] | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1390 | M675 | MOM | 2023-07-21 |  |  |  | BSS | NSO | Static IP and UI/UX Changes: Ready for demonstration by L&T . |  | NON-Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1391 | M676 | MOM | 2023-07-21 |  |  |  | Security & Regulatory Compliance | Compliance | Security and Compliance: L&T to address critical security-related activities for launch and regulatory compliances with specific target dates . |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1392 | M677 | MOM | 2023-07-21 |  |  |  | BSS | Billing Related | Payment Gateway Completion: If SSL Certificate is provided by 11th September '23, L&T to complete the payment gateway by 30th September '23 . |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1393 | M678 | MOM | 2023-07-21 |  |  |  | BSS | Dry Run | BSS E2E Demo: Chief Delivery Officer, L&T proposed to have the E2E BSS Demo on 4th July '23, with features to be confirmed by 1st July '23 . |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1394 | M679 | MOM | 2023-07-21 |  |  |  | WFM |  | Mobile App & WFM: SVP, T-Fiber requested clarity on the number of mobile apps and urged L&T to freeze the scope in consultation with MSI B and C. Demo with M/S Lepton scheduled for 21st June '23 . |  | Critical | Open | [7 empty] | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMWFM | Applications/Tools | OPEN | [6 empty] | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1395 | M68 | MOM | 2023-07-04 | P3 |  |  | NOC Operationalization | Handbook & SOPs | RASCI & Escalation Matrix in NOC Operational Framework |  | Critical | Closed |  |  |  |  | OEM, vendor , Field/NOC escalation matrix available. This is a point in 472 tracker as well and this point is approved by TFiber |  |  | Ahmad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  | Not related to delivery | 2025-09-19 | Artefacts not Required |  | 1 | Completed & Approved | Closed before june-2025
1396 | M680 | MOM | 2023-07-21 |  |  |  | NSO | NSO related | NSO Competency Plan: L&T to put in place an NSO competency plan . |  | Critical | Open | [7 empty] | Jayant Madavi |  | Open | Open | [9 empty] | MOMNSO | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1397 | M681 | MOM | 2023-07-21 |  |  |  | T&D Environment | Testing Environment | Separation of T&D and Production Environments: L&T to provide a plan addressing the requirement for separate environments . |  | NON-Critical | Open |  |  |  |  | [15/09/2025] Clusters are segregated for Production vis-à-vis pre-production |  |  | Ravi Kishore |  |  | COMPLETED & APPROVED | [9 empty] | MOMT&D Environment | Applications | CLOSED |  |  |  |  | Artefacts Need to upload |  | 1 | Completed & Approved | Closed after June
1398 | M682 | MOM | 2023-07-21 |  |  |  | BSS | Testing Environment | Onboarding of Billing Specialist: L&T to update on the onboarding process for a long-term Billing Specialist . |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1399 | M683 | MOM | 2023-07-21 |  |  |  | BSS | Billing Related | Closure of CRM Billing Process and Invoice Format: L&T to close action items regarding CRM Billing Process and Invoice format . |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1400 | M684 | MOM | 2023-07-21 |  |  |  | BSS | Action Points | BSS Roadmap Progress: L&T to demonstrate completed points for closure and include related test cases . |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1401 | M685 | MOM | 2023-07-21 |  |  |  | BSS | Dry Run | Next BSS Demo for Cell Tower: L&T to confirm the date of the next BSS Demo for Cell Tower by 21st August '23 . |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1402 | M686 | MOM | 2023-07-21 |  |  |  | BSS | Action Points | User Groups Demonstration: L&T to showcase the demonstration on user groups along with the demo for Cell Tower . |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1403 | M687 | MOM | 2023-07-21 |  |  |  | BSS | Action Points | Next BSS Demo Schedule: Scheduled for 23rd August '23, to include RFS/RFO status, notification templates, UI/UX validation, and exception scenarios . |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1404 | M688 | MOM | 2023-07-21 |  |  |  | BSS | Regulatory Compliance | Regulatory Reports Review: L&T to identify available reports in BSS as Ready/WIP by 21st August '23 and review with T-Fiber for approval . |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1405 | M689 | MOM | 2023-07-26 |  |  |  | WFM |  | Finalise and share the scope of work (SOW) for Work Force Management solution implementation with M/S Lepton. |  | Critical | Open | [7 empty] | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMWFM | Applications/Tools | OPEN | [6 empty] | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1406 | M69 | MOM | 2023-07-04 | P3 |  |  | NOC Operationalization | Handbook & SOPs | clear definition of roles and responsibilities related to L1, L2 & L3 with number of resources which should be according to the fault rates. |  | Critical | Completed |  |  |  |  | NOC manpower report is shared on weekly basis. Manpower is as per RFP count. KRA is also submitted for L1/L2/L3 roles |  |  | Ahmad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  | Not related to delivery | 2025-09-24 | \\172.28.9.23\tnocreports\TNOC Manpower_CVs\NOC Resources Details & Roles |  | 1 | Completed & Approved | Closed after June
1407 | M690 | MOM | 2023-07-26 |  |  |  | WFM |  | Support for translation to Telugu to be checked with M/S Lepton. |  | Critical | Open |  |  |  |  | Duplicate with Point- 177 |  |  | Kaushalendra Kumar |  | Open | Duplicate | [9 empty] | MOMWFM | Applications/Tools | #N/A |  |  |  |  | #N/A |  | 1 | Open | Open
1408 | M691 | MOM | 2023-07-26 |  |  |  | WFM |  | Clarity on the term “As-is solution to be deployed” under Order Management is to be provided. |  | Critical | Open | [7 empty] | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMWFM | Applications/Tools | OPEN | [6 empty] | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1409 | M692 | MOM | 2023-07-26 |  |  |  | WFM |  | Support for Barcode scanning as well as QR code scanning to be checked with M/S Lepton. |  | Critical | Open | [7 empty] | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMWFM | Applications/Tools | OPEN | [6 empty] | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1410 | M693 | MOM | 2023-07-26 |  |  |  | BSS | Dry Run | Preparation for a dry run of BSS to include WFM. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1411 | M694 | MOM | 2023-07-26 |  |  |  | WFM |  | Receive clarification on the support for re-assignment of workflow in case a Field Technician is on leave. |  | Critical | Open |  |  |  |  | Manager has to reassign TT to different FE |  |  | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMWFM | Applications/Tools | OPEN | [6 empty] | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1412 | M695 | MOM | 2023-07-26 |  |  |  | WFM |  | Verify processes for recording of timelocks of patrol routes. |  | Critical | Open | [7 empty] | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMWFM | Applications/Tools | OPEN | [6 empty] | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1413 | M696 | MOM | 2023-07-26 |  |  |  | WFM |  | Improve the clarity, definition, and availability of existing filters in WFM dashboards. |  | Critical | Open |  |  |  |  | Duplicate with Point- 186 |  |  | Kaushalendra Kumar |  | Open | Duplicate | [9 empty] | MOMWFM | Applications/Tools | #N/A |  |  |  |  | #N/A |  | 1 | Open | Open
1414 | M697 | MOM | 2023-07-26 |  |  |  | WFM |  | Video upload support. |  | Critical | Open |  |  |  |  | Duplicate with Point- 187 |  |  | Kaushalendra Kumar |  | Open | Duplicate | [9 empty] | MOMWFM | Applications/Tools | #N/A |  |  |  |  | #N/A |  | 1 | Open | Open
1415 | M698 | MOM | 2023-07-26 |  |  |  | WFM |  | Support for Workforce Management productivity statistics mentioned that this shall fall under the customisation scope. |  | Critical | Open |  |  |  |  | Duplicate with Point- 188 |  |  | Kaushalendra Kumar |  | Open | Duplicate | [9 empty] | MOMWFM | Applications/Tools | #N/A |  |  |  |  | #N/A |  | 1 | Open | Open
1416 | M699 | MOM | 2023-07-26 |  |  |  | WFM |  | Coordination required with NOC, Operations, and Projects team of 3 MSIs for the WFM Demo of 3 Packages including BSS-SME- L&T. |  | Critical | Open | [7 empty] | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMWFM | Applications/Tools | OPEN | [6 empty] | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1417 | M7 | MOM | 2023-04-03 |  |  |  | NOC Operationalization | Full NOC Readiness | Request for submission of Test Reports, outcomes, and documentation on a common server for continuous testing and monitoring. (Shared Folder) |  | Critical | Completed |  | OSS Dashboards |  | Artefacts to be submitted | 24-Sep-25: All Field and Interim NOC KPIs, reports, forms are available in shared folder.Artefacts will be uploaded today in NAS |  |  | Siva Kumar |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-24 | \\172.28.9.23\tnocreports |  | 1 | Completed & Approved | Closed after June
1418 | M70 | MOM | 2023-07-04 | P3 |  |  | NOC Operationalization | Audit | Checklist for issue handling and first level troubleshooting |  | Critical | Completed |  |  |  |  | Checklist available with Helpdesk |  |  | Ahmad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  | Daily oprational task | 2025-09-19 | Artefacts not Required |  | 1 | Completed & Approved | Closed after June
1419 | M700 | MOM | 2023-07-26 |  |  |  | WFM |  | Asses if NOC Work Force Management is handled by the proposed WFM tool |  | Critical | Open |  |  |  |  | Duplicate with Point- 189 |  |  | Kaushalendra Kumar |  | Open | Duplicate | [9 empty] | MOMWFM | Applications/Tools | #N/A |  |  |  |  | #N/A |  | 1 | Open | Open
1420 | M701 | MOM | 2023-07-26 |  |  |  | WFM |  | Samples or actual reports and dashboards based on operational processes to be presented by 28th July’23. |  | Critical | Open |  |  |  |  | Duplicate with Point- 207 |  |  | Kaushalendra Kumar |  | Open | Duplicate | [9 empty] | MOMWFM | Applications/Tools | #N/A |  |  |  |  | #N/A |  | 1 | Open | Open
1421 | M702 | MOM | 2023-07-26 |  |  |  | WFM |  | Assessment to ensure that planned Event Manpower assignment is covered by the WFM solution. |  | Critical | Open |  |  |  |  | Duplicate with Point- 190 |  |  | Kaushalendra Kumar |  | Open | Duplicate | [9 empty] | MOMWFM | Applications/Tools | #N/A |  |  |  |  | #N/A |  | 1 | Open | Open
1422 | M703 | MOM | 2023-07-26 |  |  |  | WFM |  | Assessment about whether the proposed WFM solution supports field personnel to schedule appointments with end customers. |  | Critical | Open |  |  |  |  | Duplicate with Point- 194 |  |  | Kaushalendra Kumar |  | Open | Duplicate | [9 empty] | MOMWFM | Applications/Tools | #N/A |  |  |  |  | #N/A |  | 1 | Open | Open
1423 | M704 | MOM | 2023-07-26 |  |  |  | WFM |  | Ensure the licenses for WFM are perpetual. |  | Critical | Open |  |  |  |  | Duplicate with Point- 196 |  |  | Kaushalendra Kumar |  | Open | Duplicate | [9 empty] | MOMWFM | Applications/Tools | #N/A |  |  |  |  | #N/A |  | 1 | Open | Open
1424 | M705 | MOM | 2023-07-26 |  |  |  | NOC Operationalization | Launch Readiness | Assessment and redistribution of support because of the launch date approaching on 15th August. |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1 | Completed & Approved | Closed after June
1425 | M706 | MOM | 2023-08-01 |  |  |  | GIS | Launch Readiness | Each MSI needs to commit to the target for Mandal upload in the GIS tool for business readiness. |  | Critical | Open | [7 empty] | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMGIS | Applications/Tools | OPEN | [6 empty] | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1426 | M707 | MOM | 2023-08-01 |  |  |  | GIS | Launch Readiness | Commit target dates for GIS Data Upload for each package. |  | Critical | Open | [7 empty] | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMGIS | Applications/Tools | OPEN | [6 empty] | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1427 | M708 | MOM | 2023-08-01 |  |  |  | GIS | Launch Readiness | Package A needs to provide a day by day Mandal upload action plan to meet the committed target dates. |  | Critical | Open | [7 empty] | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMGIS | Applications/Tools | OPEN | [6 empty] | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1428 | M709 | MOM | 2023-08-01 |  |  |  | GIS | Launch Readiness | Packages B and C are expected to submit a proposal to hasten data upload in consultation with GIS-SME, Pkg-A. |  | Critical | Open | [7 empty] | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMGIS | Applications/Tools | OPEN | [6 empty] | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1429 | M71 | MOM | 2023-07-04 |  |  |  | NOC Operationalization | Audit | Latency/Jitter & Backbone packet loss SLAs |  | Critical | Completed |  |  |  | WIP | Report & SLA compliance is shared on monhtly basis | L&T | Manoj | Siva Kumar |  | Open | WIP | [9 empty] | MOMNOC Operationalization | Network | OPEN | [6 empty] | 1 | Open | Open
1430 | M710 | MOM | 2023-08-01 |  |  |  | Field Related | Launch Readiness | MSIs to prioritise a district-wise approach over a scattered approach. |  | Critical | Open | [7 empty] | S Kodali |  | Open | Open | [9 empty] | MOMField Related | Field Related issues | OPEN |  |  | Project Team |  | #N/A |  | 1 | Open | Open
1431 | M711 | MOM | 2023-08-01 |  |  |  | Field Related | Mandal Rings | The status of Mandal Rings completion i.e. GIS uploading done, splicing pending, attribute updating is pending. |  | NON-Critical | Open |  |  |  |  | completed for 110 Mandals and balance in progress with mandal readiness by acitive & passive |  |  | S Kodali |  | Open | Open | [9 empty] | MOMField Related | Field Related issues | OPEN |  |  | Project Team |  | #N/A |  | 1 | Open | Open
1432 | M712 | MOM | 2023-08-01 |  |  |  | GIS | Launch Readiness | The current committed dates for GIS Data Upload are not meeting the expectations of T-Fiber. |  | Critical | Open | [7 empty] | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMGIS | Applications/Tools | OPEN | [6 empty] | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1433 | M713 | MOM | 2023-08-01 |  |  |  | Helpdesk | Launch Readiness | Complete Helpdesk integration with OSS and BSS. |  | Critical | Open |  |  |  | WIP |  |  |  | Siva Kumar |  | Open | WIP | [9 empty] | MOMHelpdesk | Helpdesk (Contact Center) | OPEN | [6 empty] | 1 | Open | Open
1434 | M714 | MOM | 2023-08-01 |  |  |  | BSS | Launch Readiness | Set up SMS based alerting. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1435 | M715 | MOM | 2023-08-01 |  |  |  | Helpdesk | Launch Readiness | Handle 150-160 calls per day in Helpdesk. |  | Critical | open |  |  |  | Closed | 24-Sep-25: Approved and shall be closed 11-Sep-25: Changed and operational Now |  |  | Siva Kumar |  |  | COMPLETED & APPROVED | [9 empty] | MOMHelpdesk | Helpdesk (Contact Center) | CLOSED |  |  |  | 2025-09-24 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\M117,126,728 |  | 1 | Completed & Approved | Closed after June
1436 | M716 | MOM | 2023-08-01 |  |  |  | Helpdesk | Launch Readiness | Ensure that Helpdesk SLAs from the RFP are met. |  | Critical | open |  |  |  | WIP |  |  |  | Siva Kumar |  | Open | WIP | [9 empty] | MOMHelpdesk | Helpdesk (Contact Center) | OPEN | [6 empty] | 1 | Open | Open
1437 | M717 | MOM | 2023-08-01 |  | OSS | OSS | OSS | Launch Readiness | Deploy the Knowledge Management module in HPSM. |  | Critical | Open | [7 empty] | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMOSS | Applications/Tools | OPEN | CLOSURE REVIEW PENDING | 0 |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1438 | M718 | MOM | 2023-08-01 |  |  |  | Helpdesk | Launch Readiness | Make the number for reaching Helpdesk toll-free. |  | Critical | Open |  |  |  |  | 11-09-2025: Same as T366(472) Closed |  |  | Siva Kumar |  |  | COMPLETED & APPROVED | Yes | 2025-07-19 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\T366 | [6 empty] | MOMHelpdesk | Helpdesk (Contact Center) | CLOSED |  |  |  | 2025-07-19 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\T366 |  | 1 | Completed & Approved | Closed after June
1439 | M719 | MOM | 2023-08-01 |  |  |  | BSS | Launch Readiness | Create and finalize multiple channels of communication to the Helpdesk such as SMS, WhatsApp, and email. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1440 | M72 | MOM | 2023-07-04 | P3 |  |  | NOC Operationalization | Handbook & SOPs | service management of configuration |  | Critical | Open | [7 empty] | Ahmad | 2025-10-07 | Open | Open | [9 empty] | MOMNOC Operationalization | Network | OPEN |  |  | Documentation |  | #N/A |  | 1 | Open | Open
1441 | M720 | MOM | 2023-08-01 |  | OSS | OSS | OSS | Launch Readiness | Define incident categorisation. |  | Critical | Open | [7 empty] | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMOSS | Applications/Tools | OPEN | CLOSURE REVIEW PENDING | 0 |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1442 | M721 | MOM | 2023-08-01 |  |  |  | Helpdesk | Launch Readiness | Specify features of Helpdesk not presently available for future deployment. |  | Critical | Open |  |  |  | WIP |  |  |  | Siva Kumar |  | Open | WIP | [9 empty] | MOMHelpdesk | Helpdesk (Contact Center) | OPEN | [6 empty] | 1 | Open | Open
1443 | M722 | MOM | 2023-08-01 |  |  |  | Helpdesk | Launch Readiness | Training for Helpdesk users and managers for call center response and management. |  | Critical | open |  |  |  | Closed | 24-Sep:25: Artefacts to sbumitted |  |  | Siva Kumar |  |  | COMPLETED & APPROVED | [9 empty] | MOMHelpdesk | Helpdesk (Contact Center) | CLOSED |  |  |  | 2025-09-24 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\M114,722,134 |  | 1 | Completed & Approved | Closed after June
1444 | M723 | MOM | 2023-08-01 |  |  |  | Helpdesk | Launch Readiness | Set up a mechanism for non-technical call handling improvement. |  | Critical | open |  |  |  | Closed | 25-Sep-25: aretfacts to be sumitted for closure 11-Sep-25: Established Business Helpdesk Setup at T Fiber office |  |  | Siva Kumar |  |  | COMPLETED & APPROVED | [9 empty] | MOMHelpdesk | Helpdesk (Contact Center) | CLOSED |  |  |  | 2025-09-24 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\M116,723,1026 |  | 1 | Completed & Approved | Closed after June
1445 | M724 | MOM | 2023-08-01 |  |  |  | Helpdesk | Launch Readiness | Get readiness of Helpdesk and Business to accept issues with order login. |  | Critical | open |  |  |  | Closed | 25-Sep-25: aretfacts to be sumitted for closure 11-Sep-25: Established Business Helpdesk Setup at T Fiber office |  |  | Siva Kumar |  |  | COMPLETED & APPROVED | [9 empty] | MOMHelpdesk | Helpdesk (Contact Center) | CLOSED |  |  |  | 2025-09-24 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\M724 |  | 1 | Completed & Approved | Closed after June
1446 | M725 | MOM | 2023-08-01 |  |  |  | Helpdesk | Launch Readiness | Determine how to handle calls originating from different packages given the shared Helpdesk agents. |  | Critical | open |  |  |  | Closed | 24-Sep-25: IVR Flows made ready Accordingly |  |  | Siva Kumar |  |  | COMPLETED & APPROVED | [9 empty] | MOMHelpdesk | Helpdesk (Contact Center) | CLOSED |  |  |  | 2025-09-24 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\M725,735 |  | 1 | Completed & Approved | Closed after June
1447 | M726 | MOM | 2023-08-01 |  |  |  | Helpdesk | Launch Readiness | Problems with not supporting Telugu language in IVR and Helpdesk. |  | Critical | open |  |  |  | Closed | 24-Sep-25: Now its in 3 Languages |  |  | Siva Kumar |  |  | COMPLETED & APPROVED | [9 empty] | MOMHelpdesk | Helpdesk (Contact Center) | CLOSED |  |  |  | 2025-09-24 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\M121,170,99,726 |  | 1 | Completed & Approved | Closed after June
1448 | M727 | MOM | 2023-08-01 |  |  |  | Helpdesk | Launch Readiness | Unclear about support for integration with WhatsApp. |  | Critical | open |  |  |  | WIP | 11-Se-25:This Prouct Not Support |  |  | Siva Kumar |  | Open | WIP | [9 empty] | MOMHelpdesk | Helpdesk (Contact Center) | OPEN | [6 empty] | 1 | Open | Open
1449 | M728 | MOM | 2023-08-01 |  |  |  | Helpdesk | Resource Augmentation | Confirm if the current load handled by Helpdesk is sufficient. |  | Critical | open |  |  |  | Closed | 24-Sep-25: Artefcats to be submitted 11-Sep-25: Data Shared |  |  | Siva Kumar |  |  | COMPLETED & APPROVED | [9 empty] | MOMHelpdesk | Helpdesk (Contact Center) | CLOSED |  |  |  | 2025-09-24 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\M117,126,728 |  | 1 | Completed & Approved | Closed after June
1450 | M729 | MOM | 2023-08-01 |  |  |  | Helpdesk | Launch Readiness | Concern over non-availability of Helpdesk Manager between 10 PM – 6 AM and how emergencies are handled during this time. |  | Critical | open |  |  |  | Closed | 24-Sep-25: Existing Lead available during Business Hours, Remaining duration Shift Lead will Manage |  |  | Siva Kumar |  |  | COMPLETED & APPROVED | [9 empty] | MOMHelpdesk | Helpdesk (Contact Center) | CLOSED |  |  |  | 2025-09-24 | Artefacts not Required |  | 1 | Completed & Approved | Closed after June
1451 | M73 | MOM | 2023-07-26 |  |  |  | WFM | User Experience | Support for translation to Telugu |  | Critical | Open |  |  |  |  | As per OEM this point is not feasible 11 July 2025:- A follow-up discussion with the OEM is required to assess feasibility. If it is found to be unfeasible, a call should be arranged with Sanjay Sir along with the OEM team & artefacts needs to submit |  |  | Kaushalendra Kumar |  | Open | Not Feasible | [9 empty] | MOMWFM | Applications/Tools | #N/A |  |  |  |  | #N/A |  | 1 | Open | Open
1452 | M730 | MOM | 2023-08-01 |  |  |  | NOC Operationalization | Launch Readiness | The relationship between people and functions as realised by RASCI matrix needs improvement. |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1 | Completed & Approved | Closed after June
1453 | M731 | MOM | 2023-08-01 |  |  |  | Helpdesk | Launch Readiness | Differentiate between registered users and registered numbers. |  | Critical | Open |  |  |  | WIP | 11-Sep-25: BSS Integration to be completed |  |  | Siva Kumar |  | Open | WIP | [9 empty] | MOMHelpdesk | Helpdesk (Contact Center) | OPEN | [6 empty] | 1 | Open | Open
1454 | M732 | MOM | 2023-08-01 |  |  |  | Helpdesk | Launch Readiness | Resolve confusion over the categorisation of incoming queries. |  | Critical | open |  |  |  | WIP |  |  |  | Siva Kumar |  | Open | WIP | [9 empty] | MOMHelpdesk | Helpdesk (Contact Center) | OPEN | [6 empty] | 1 | Open | Open
1455 | M733 | MOM | 2023-08-01 |  |  |  | Helpdesk |  | Check how the Call management system can support live intrusion of calls for instant feedback. |  | Critical | open |  |  |  | Artefacts to be submitted | 24-Sep-25:Artefacts to be submitted 11-Sep-25: Feature is available, Shall be demonstrated |  |  | Siva Kumar |  |  | COMPLETED & APPROVED | [9 empty] | MOMHelpdesk | Helpdesk (Contact Center) | CLOSED |  |  |  | 2025-09-24 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\M119,733 |  | 1 | Completed & Approved | Closed after June
1456 | M734 | MOM | 2023-08-01 |  |  |  | Helpdesk |  | Define how readiness of Helpdesk to report on compliances and responsiveness and penalties calculation. |  | Critical | open |  |  |  | WIP |  |  |  | Siva Kumar |  | Open | WIP | [9 empty] | MOMHelpdesk | Helpdesk (Contact Center) | OPEN | [6 empty] | 1 | Open | Open
1457 | M735 | MOM | 2023-08-04 |  |  |  | Helpdesk |  | Determine how the Helpdesk to NOC and Field is going to be integrated with the operational framework when they currently lack synergy. |  | Critical | open |  |  |  | WIP | 11-Sep-25: IVR Flows are aligned accordingly, Post Approval and Implementation we can meet expectations |  |  | Siva Kumar |  |  | COMPLETED & APPROVED | [9 empty] | MOMHelpdesk | Helpdesk (Contact Center) | CLOSED |  |  |  | 2025-09-24 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\M725,735 |  | 1 | Completed & Approved | Closed after June
1458 | M736 | MOM | 2023-08-04 |  |  |  | Helpdesk |  | Concern over Toll-free levels availability for the Helpdesk. |  | Critical | Open |  |  |  | WIP |  |  |  | Siva Kumar |  | Open | WIP | [9 empty] | MOMHelpdesk | Helpdesk (Contact Center) | OPEN | [6 empty] | 1 | Open | Open
1459 | M737 | MOM | 2023-08-18 |  |  |  | BSS | NSO | BSS Readiness and Demo: L&T to demonstrate Static IP and UI/UX changes, with WFM integration not part of the demonstration. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1460 | M738 | MOM | 2023-08-18 |  |  |  | WFM | WFM Application | WFM Tool Usage Demonstration: L&T to arrange a demonstration of WFM tool usage for field operations soon. |  | Critical | Open |  |  |  |  | Duplicate with Point- 235 |  |  | Kaushalendra Kumar |  | Open | Duplicate | [9 empty] | MOMWFM | Applications/Tools | #N/A |  |  |  |  | #N/A |  | 1 | Open | Open
1461 | M739 | MOM | 2023-08-18 |  |  |  | BSS | Billing Related | Payment Gateway Completion: L&T to complete the payment gateway by 30th September '23 if SSL Certificate is provided by 11th September '23. |  | Critical | Open |  |  |  |  | DUPLICATE POINT (M739) |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1462 | M74 | MOM | 2023-07-26 |  |  |  | WFM | Handbook & SOPs | Scope of Order Processing and Service Ticket Management |  | Critical | Open | [7 empty] | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMWFM | Applications/Tools | OPEN | [6 empty] | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1463 | M740 | MOM | 2023-08-18 |  |  |  | Security & Regulatory Compliance | Compliance | Security Related Activities: L&T to address various security and compliance sub-activities with specific target dates. |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1464 | M741 | MOM | 2023-08-18 |  |  |  | BSS | BSS | BSS Integration with Lepton WFM: L&T to complete the demo of BSS Integration with Lepton WFM by 25th August '23. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1465 | M742 | MOM | 2023-08-18 |  |  |  | BSS | NSO | NSO Competency Plan: L&T to put in place an NSO competency plan. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1466 | M743 | MOM | 2023-08-18 |  |  |  | BSS | T&D Environment | Separation of T&D and Production Environments: L&T to provide a plan addressing the requirement for separate environments. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1467 | M744 | MOM | 2023-08-18 |  |  |  | BSS | Resource Augmentation | Onboarding of Billing Specialist: L&T to update on the onboarding process for a long-term Billing Specialist. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1468 | M745 | MOM | 2023-08-18 |  |  |  | BSS | Billing Related | Closure of CRM Billing Process and Invoice Format: L&T to close action items regarding CRM Billing Process and Invoice format. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1469 | M746 | MOM | 2023-08-18 |  |  |  | BSS | T&D Environment | BSS Roadmap Progress: L&T to demonstrate completed points for closure and include related test cases. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1470 | M747 | MOM | 2023-08-18 |  |  |  | BSS | Dry Run | Next BSS Demo for Cell Tower: L&T to confirm the date of the next BSS Demo for Cell Tower by 21st August '23. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1471 | M748 | MOM | 2023-08-18 |  |  |  | BSS | Dry Run | User Groups Demonstration: L&T to showcase the demonstration on user groups along with the demo for Cell Tower. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1472 | M749 | MOM | 2023-08-18 |  |  |  | BSS | Dry Run | Next BSS Demo Schedule: Scheduled for 23rd August '23, to include RFS/RFO status, notification templates, UI/UX validation, and exception scenarios. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1473 | M75 | MOM | 2023-07-26 |  |  |  | WFM | Handbook & SOPs | Document references in SOW to be shared |  | Critical | Open | [7 empty] | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMWFM | Applications/Tools | OPEN | [6 empty] | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1474 | M750 | MOM | 2023-08-18 |  |  |  | BSS | Regulatory Compliance | Regulatory Reports Review: L&T to identify available reports in BSS as Ready/WIP by 21st August '23 and review with T-Fiber for approval. |  | Critical | Open |  |  |  |  | DUPLICATE POINT (M688) |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1475 | M751 | MOM | 2023-08-18 |  |  |  | BSS |  | Dedication of Time to T-Fiber Project: Chief Delivery Officer, L&T to confirm dedicating 2 days a week to the T-Fiber Project in Hyderabad leading up to the Network Launch. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1476 | M752 | MOM | 2023-08-23 |  |  |  | BSS |  | Review of alert and notification templates and implementation. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1477 | M753 | MOM | 2023-08-23 |  |  |  | BSS |  | Lead data presentation for Airtel and GI_BB customers. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1478 | M754 | MOM | 2023-08-23 |  |  |  | BSS |  | Walkthrough of Ready for Service (RFS) Process. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1479 | M755 | MOM | 2023-08-23 |  |  |  | BSS |  | Identifying and addressing challenges for user experience in CRM. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1480 | M756 | MOM | 2023-08-23 |  |  |  | BSS |  | Development of BSS demo of CSP. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1481 | M757 | MOM | 2023-08-23 |  |  |  | BSS |  | Analysis of the issue impacting BSS demo. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1482 | M758 | MOM | 2023-08-23 |  |  |  | NOC Operationalization |  | Fixing issues with OSS - BSS integration. |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMNOC Operationalization | Network | OPEN | [6 empty] | 1 | Open | Open
1483 | M759 | MOM | 2023-08-23 |  |  |  | BSS |  | Establish a comprehensive list of event notification scenarios and implementation plan. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1484 | M76 | MOM | 2023-07-26 |  |  |  | WFM | User Experience | WFM tool's own Google Map |  | Critical | Open | [7 empty] | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMWFM | Applications/Tools | OPEN | [6 empty] | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1485 | M760 | MOM | 2023-08-23 |  |  |  | BSS |  | Identify and create more user groups according to the business and workflow requirements. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1486 | M761 | MOM | 2023-08-23 |  |  |  | BSS |  | Resolve discrepancies with manual updates for RFO and RFS status. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1487 | M762 | MOM | 2023-08-23 |  |  |  | WFM |  | Respond to the query of WFM integration. |  | Critical | Open | [7 empty] | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMWFM | Applications/Tools | OPEN | [6 empty] | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1488 | M763 | MOM | 2023-08-23 |  |  |  | BSS |  | Improve user experience for better data accuracy. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1489 | M764 | MOM | 2023-08-23 |  |  |  | BSS |  | Ensure the BSS-Lead, L&T and Head Telecom Practice, L&T to discuss and create more user groups according to the business and workflow requirements. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1490 | M765 | MOM | 2023-08-23 |  |  |  | BSS |  | Introduce a status/bucket "Renewal" for orders that need further work / rectification. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1491 | M766 | MOM | 2023-08-23 |  |  |  | BSS |  | Ensure that the entire network POI/ PoP status including 12751 GPs, 1 NOC, all zones, districts & Mandal nodes should be available in CRM database. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1492 | M767 | MOM | 2023-08-23 |  |  |  | BSS |  | Address observations made in the CSP by L&T and implement changes. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1493 | M768 | MOM | 2023-08-23 |  |  |  | BSS | T-Cell Launch | Propose the next date for T-Cell Demo. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1494 | M769 | MOM | 2023-08-31 |  |  |  | NOC Operationalization |  | L&T to review NOC readiness and demonstrate service excellence for launch; separate meeting for 360 View presentation on 31st August '23. |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMNOC Operationalization | Network | OPEN | [6 empty] | 1 | Open | Open
1495 | M77 | MOM | 2023-07-26 |  |  |  | WFM | Improvement | Support for Re-assignment of workflow in case of leave |  | Critical | Open | [7 empty] | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMWFM | Applications/Tools | OPEN | [6 empty] | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1496 | M770 | MOM | 2023-08-31 |  |  |  | NOC Operationalization | Launch Readiness | Implement IST in SCCM and confirm BSS readiness for live customers like Airtel by 31st August '23. |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMNOC Operationalization | Network | OPEN | [6 empty] | 1 | Open | Open
1497 | M771 | MOM | 2023-08-31 |  |  |  | NOC Operationalization | NOC Operationalization | Data cleanup before Airtel onboarding and present GI migration approach from trial to production. |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1 | Completed & Approved | Closed after June
1498 | M772 | MOM | 2023-08-31 |  | OSS | Security & OSS | All Domain | WhatsApp | List pending action items from T-Fiber; SSL certificate and WhatsApp Integration expected closure in 2-3 days. |  | NON-Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMAll Domain | Applications/Tools | OPEN | [6 empty] | 1 | Open | Open
1499 | M773 | MOM | 2023-08-31 |  |  |  | BSS |  | Share status updates on BSS action items by 1st September '23. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1500 | M774 | MOM | 2023-08-31 |  |  |  | WFM |  | Schedule WFM integration with BSS demo for 15th September '23. |  | Critical | Open | [7 empty] | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMWFM | Applications/Tools | OPEN | [6 empty] | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1501 | M775 | MOM | 2023-09-08 |  |  |  | Field Related | GI Connectivity | Rectification and progress of GI Connectivity. |  | NON-Critical | Open |  |  |  |  | Maintainance in progress for go Live districts |  |  | S Kodali |  | Open | Open | [9 empty] | MOMField Related | Field Related issues | OPEN |  |  | O&M Team |  | #N/A |  | 1 | Open | Open
1502 | M776 | MOM | 2023-09-08 |  |  |  | NOC Operationalization | Launch Readiness | Completion of Pause-Mechanism and QOS Visibility part of the committed deliverables. |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMNOC Operationalization | Network | OPEN | [6 empty] | 1 | Open | Open
1503 | M777 | MOM | 2023-09-08 |  |  |  | NOC Operationalization | Launch Readiness | Reviewing readiness for launch, readiness of O&M Approach, and readiness of NOC from a multiple perspectives. |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMNOC Operationalization | Network | OPEN | [6 empty] | 1 | Open | Open
1504 | M778 | MOM | 2023-09-08 |  |  |  | NOC Operationalization |  | Submissio of module wise Functional Acceptance Test Plan. |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMNOC Operationalization | Network | OPEN | [6 empty] | 1 | Open | Open
1505 | M779 | MOM | 2023-09-08 |  |  |  | NOC Operationalization | Launch Readiness | Implementation and readiness in order for Interim Launch from NOC to field level. |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1 | Completed & Approved | Closed after June
1506 | M78 | MOM | 2023-07-26 |  |  |  | WFM | Improvement | Support for pre-defined routes |  | Critical | Open | [7 empty] | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMWFM | Applications/Tools | OPEN | [6 empty] | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1507 | M780 | MOM | 2023-09-08 |  |  |  | Security & Regulatory Compliance | NOC Operationalization | Establishing a security system including hardware, IT Infra, and Applications security certifications. |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1508 | M781 | MOM | 2023-09-08 |  |  |  | NOC Operationalization |  | Submit report capturing the number of test cases and their status. |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMNOC Operationalization | Network | OPEN | [6 empty] | 1 | Open | Open
1509 | M782 | MOM | 2023-09-08 |  |  |  | NOC Operationalization | Launch Readiness | Include more sample sites in the 2nd Dry Run by the end of September' 23. |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1 | Completed & Approved | Closed after June
1510 | M783 | MOM | 2023-09-08 |  |  |  | NOC Operationalization | Launch Readiness | Review and finalize the process design related to Service Delivery linked to manpower. |  | Critical | Open |  |  |  | Closed, Artefacts to be uploaded | 23-Sep-25: Approved Artefacts to be Submitted | L&T | Sivaprasad | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  |  | Artefacts Need to upload |  | 1 | Completed & Approved | Closed after June
1511 | M784 | MOM | 2023-09-08 |  |  |  | NOC Operationalization |  | LLD (Revised) with OADM Solution (Ciena) |  | NON-Critical | Open | [7 empty] | Suresh Kumar |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  |  | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\DWDM\Artefact - T90 |  | 1 | Completed & Approved | Closed after June
1512 | M785 | MOM | 2023-09-08 |  |  |  | T&D Environment | Testing Environment | BSS T&D license to be accessible by 30/6/23. It will be moved to a production environment afterward. |  | NON-Critical | Open |  |  |  |  | [15/09/2025] KNOT BSS T&D is setup |  |  | Ravi Kishore |  |  | COMPLETED & APPROVED | [9 empty] | MOMT&D Environment | Applications | CLOSED |  |  |  |  | Artefacts Need to upload |  | 1 | Completed & Approved | Closed after June
1513 | M786 | MOM | 2023-09-08 |  |  |  | NOC Operationalization | Launch Readiness | The readiness of E2E NOC will be reviewed and updated by 8th Sep ‘23. |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1 | Completed & Approved | Closed after June
1514 | M787 | MOM | 2023-09-08 |  |  |  | NOC Operationalization | Launch Readiness | The status of pending deliverables that were committed for delivery by 15th August ’23 has not been mentioned to have been met by specific dates. |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1 | Completed & Approved | Closed after June
1515 | M788 | MOM | 2023-09-08 |  |  |  | NOC Operationalization | Launch Readiness | T-NOC Readiness Confirmation: EVP, T-Fiber requested confirmation on launch deliverables and interim launch processes by EOD 8th September '23. |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1 | Completed & Approved | Closed after June
1516 | M789 | MOM | 2023-09-08 |  |  |  | NOC Operationalization |  | Review of Pending Activities: Director-P&E, T-Fiber to review and update the status of 92 pending activities related to the 15th August '23 deliverables. |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1 | Completed & Approved | Closed after June
1517 | M79 | MOM | 2023-07-26 |  |  |  | WFM | User Experience | Support for recording timeclocks of patrol routes |  | Critical | Open | [7 empty] | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMWFM | Applications/Tools | OPEN | [6 empty] | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1518 | M790 | MOM | 2023-09-08 |  |  |  | NOC Operationalization |  | Revised LLD for DWDM: Technical Head, L&T submitted the revised LLD for approval. |  | NON-Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1 | Completed & Approved | Closed after June
1519 | M791 | MOM | 2023-09-08 |  |  |  | Security & Regulatory Compliance | Compliance | Risk Assessment: VP-Program emphasized the need for a Risk register with a responsible SPOC and response plan. |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1520 | M792 | MOM | 2023-09-08 |  |  |  | BSS |  | Payment Gateway Completion: L&T to complete the payment gateway by 30th September '23 if SSL Certificate is provided by 11th September '23. |  | Critical | Open |  |  |  |  | DUPLICATE POINT (M739) |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1521 | M793 | MOM | 2023-09-08 |  |  |  | Security & Regulatory Compliance | Compliance | Security Related Activities: Director-P&E, T-Fiber stressed the importance of security activities for launch and regulatory compliances. |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1522 | M794 | MOM | 2023-09-08 |  |  |  | Security & Regulatory Compliance | Compliance | Security and Compliance Sub-Activities: L&T to address various security and compliance sub-activities with specific target dates ranging from 31st August to 15th September '23. |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1523 | M795 | MOM | 2023-09-08 |  |  |  | Security & Regulatory Compliance | Compliance | Alepo AAA and TACACS Integration: Alepo to test integration with Nokia and Ciena nodes on TACACS with supporting artefacts of testing. |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1524 | M796 | MOM | 2023-09-08 |  |  |  | Security & Regulatory Compliance | Compliance | OSS Firewall Ports: L&T to address OSS firewall ports required for security compliance. |  | Critical | Open | [7 empty] | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN | COMPLETED | 0 |  |  | #N/A |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1525 | M797 | MOM | 2023-09-08 |  |  |  | Security & Regulatory Compliance | Compliance | Security LLD: Customer requested a complete Security LLD that outlines the security architecture and interactions between security products. |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1526 | M798 | MOM | 2023-09-08 |  |  |  | Security & Regulatory Compliance | Compliance | External Audit and VAPT: L&T to conduct external audits and vulnerability assessments for applications and network elements. |  | Critical | Open |  |  |  |  | Audit done by Allied Boston. And further external audit to be done by TFiber vendor |  |  | Sarmendra |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | Artefacts to be Submitted |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1527 | M799 | MOM | 2023-09-12 |  |  |  | WFM |  | L&T is to submit a proposal to T-Fiber on the scope to be showcased in the proposed WFM-BSS demonstration. |  | Critical | Open | [7 empty] | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMWFM | Applications/Tools | OPEN | [6 empty] | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1528 | M8 | MOM | 2023-04-03 |  |  |  | NOC Operationalization | Full NOC Readiness | All Test Plans to be submitted to TPA in coordination with Package B&C; reviewed by Assistant Director Technical, T-Fiber. |  | Critical | Open |  | OSS Dashboards |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1 | Completed & Approved | Closed after June
1529 | M80 | MOM | 2023-07-26 |  |  |  | WFM | User Experience | Support for Barcode and QR code scanning |  | Critical | Open | [7 empty] | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMWFM | Applications/Tools | OPEN | [6 empty] | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1530 | M800 | MOM | 2023-09-12 |  |  |  | WFM |  | L&T is to identify a product owner for WFM. |  | Critical | Open | [7 empty] | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMWFM | Applications/Tools | OPEN | [6 empty] | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1531 | M801 | MOM | 2023-09-22 |  |  |  | NOC Operationalization | Launch Readiness | Overcoming technical issues hampering the setup for the 1st Dry Run. |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1 | Completed & Approved | Closed after June
1532 | M802 | MOM | 2023-09-22 |  |  |  | NOC Operationalization | Launch Readiness | Reviewing the setup for 1st Dry Run observed by the EVP, T-Fiber. |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1 | Completed & Approved | Closed after June
1533 | M803 | MOM | 2023-09-22 |  |  |  | NOC Operationalization | Launch Readiness | Gaining clarity on roles and functionalities of NSO and OSS. |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMNOC Operationalization | Network | OPEN | [6 empty] | 1 | Open | Open
1534 | M804 | MOM | 2023-09-22 |  |  |  | BSS |  | Overcoming technical issues observed in CSP and CRM. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1535 | M805 | MOM | 2023-09-22 |  |  |  | BSS |  | Reviewing processes of order booking to be communicated more simply and effectively to the end users. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1536 | M806 | MOM | 2023-09-22 |  |  |  | NOC Operationalization |  | L&T to identify provisioning/monitoring features limited because of interoperability issues in a multi-vendor eco-system. |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMNOC Operationalization | Network | OPEN | [6 empty] | 1 | Open | Open
1537 | M807 | MOM | 2023-09-22 |  |  |  | NOC Operationalization |  | L&T to articulate how NSO and OSS are complementing each other and their roles in service provisioning. |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMNOC Operationalization | Network | OPEN | [6 empty] | 1 | Open | Open
1538 | M808 | MOM | 2023-09-22 |  |  |  | NOC Operationalization |  | L&T to provide the redundancy plan if entire DC were to go down and the backup measures if NSO were to fail. |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMNOC Operationalization | Network | OPEN | [6 empty] | 1 | Open | Open
1539 | M809 | MOM | 2023-09-22 |  |  |  | NOC Operationalization |  | L&T to work towards a system that is foolproof, automated, futuristic, and provides seamless service experience for end users. |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMNOC Operationalization | Network | OPEN | [6 empty] | 1 | Open | Open
1540 | M81 | MOM | 2023-07-26 |  |  |  | WFM | Handbook & SOPs | Confirmation of SOW addressing Packages B and C |  | Critical | Open | [7 empty] | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMWFM | Applications/Tools | OPEN | [6 empty] | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1541 | M810 | MOM | 2023-09-22 |  |  |  | NOC Operationalization | Dry Run | L&T to propose the date for the 2nd Dry Run inclusive of Internet Leased Line, P2P, and P2MP flavors of service. |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1 | Completed & Approved | Closed after June
1542 | M811 | MOM | 2023-09-22 |  |  |  | NOC Operationalization | Dry Run | L&T to confirm target date for E2E BSS Demo. |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMNOC Operationalization | Network | OPEN | [6 empty] | 1 | Open | Open
1543 | M812 | MOM | 2023-09-22 |  |  |  | NOC Operationalization | Dry Run | L&T to consider the creation of a template for tracking observations. |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1 | Completed & Approved | Closed after June
1544 | M813 | MOM | 2023-09-22 |  |  |  | NOC Operationalization | NSO | Provision of training for L&T pool of resources in NSO and development of NEDs. |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMNOC Operationalization | Network | OPEN | [6 empty] | 1 | Open | Open
1545 | M814 | MOM | 2023-09-22 |  |  |  | NOC Operationalization |  | L&T to create a timetable displaying the percentage of progress on activities week-wise and fortnight-wise. |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1 | Completed & Approved | Closed after June
1546 | M815 | MOM | 2023-09-22 |  |  |  | NOC Operationalization |  | L&T to confirm the features ready for showcase in the E2E Demo by 25th September’23. |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1 | Completed & Approved | Closed after June
1547 | M816 | MOM | 2023-09-22 |  |  |  | NOC Operationalization |  | Target the 2nd Dry Run on 30th September ’23 with more ONTs, covering GI BB, Point to point, dedicated ILL & Dark fiber by end of L&T. |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1 | Completed & Approved | Closed after June
1548 | M817 | MOM | 2024-09-26 |  |  |  | T&D Environment | AT Process | Defining and aligning with the acceptance criteria for each system in the NOC. |  | NON-Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMT&D Environment | Applications | OPEN | [6 empty] | 1 | Open | Open
1549 | M818 | MOM | 2023-09-26 |  |  |  | Helpdesk |  | Inclusion of Helpdesk and other missing items as per the RFP and solution in the Build. |  | Critical | Open |  |  |  | Closed | 24-Sep-25: Approved and shall be closed, Accordingly Helpdesk LLD Aligning |  |  | Siva Kumar |  |  | COMPLETED & APPROVED | [9 empty] | MOMHelpdesk | Helpdesk (Contact Center) | CLOSED |  |  |  | 2025-09-24 | Artefacts not Required |  | 1 | Completed & Approved | Closed after June
1550 | M819 | MOM | 2023-09-26 |  |  |  | T&D Environment | T&D Environment | Implementation of Test and Development environment. |  | NON-Critical | Open |  |  |  |  | [15/09/2025] Clusters are segregated for Production vis-à-vis pre-production |  |  | Ravi Kishore |  |  | COMPLETED & APPROVED | [9 empty] | MOMT&D Environment | Applications | CLOSED |  |  |  |  | Artefacts Need to upload |  | 1 | Completed & Approved | Closed after June
1551 | M82 | MOM | 2023-07-26 |  |  |  | WFM | User Experience | Clear definition and availability of existing filters in WFM dashboards |  | Critical | Open |  |  |  |  | 11-7-2025:- The dashboard and report filter options should be showcased during the WFM application demonstration. |  |  | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMWFM | Applications/Tools | OPEN | [6 empty] | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1552 | M820 | MOM | 2023-09-26 |  |  |  | T&D Environment | T&D Environment | Discussion on the requirements for Test Lab/Staging environment. |  | NON-Critical | Open |  |  |  |  | [15/09/2025] Interim T&D is setup, finalised option detailing pending |  |  | Ravi Kishore |  |  | COMPLETED & APPROVED | [9 empty] | MOMT&D Environment | Applications | CLOSED |  |  |  |  | Artefacts Need to upload |  | 1 | Completed & Approved | Closed after June
1553 | M821 | MOM | 2023-10-18 |  |  |  | BSS | CSP Testing | Adding a back button on the payment screen. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1554 | M822 | MOM | 2023-10-18 |  |  |  | BSS | CSP Testing | Providing guidelines for the CAF upload stage and adding a disclaimer for "Subject to Verification of CAF." |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1555 | M823 | MOM | 2023-10-18 |  |  |  | BSS | CSP Testing | Ensuring offline payment transactions are viewable and mandatory sections of the CAF are highlighted. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1556 | M824 | MOM | 2023-10-18 |  |  |  | BSS | CSP Testing | Addressing issues with ticket creation, notification, and enquiry handling in the CSP. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1557 | M825 | MOM | 2023-10-18 |  |  |  | BSS | CSP Testing | Clarifying the bulk upload of leads and the feasibility of integrating such a feature in the CSP. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1558 | M826 | MOM | 2023-10-18 |  |  |  | BSS | CSP Testing | Resolving user interface issues such as incorrect OTP entry pop-ups, case sensitivity in order ID searches, and real-time synchronization between GIS-OSS for feasibility checks. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1559 | M827 | MOM | 2023-10-18 |  |  |  | BSS | CSP Testing | Removing unnecessary elements from the UI, aligning GP names with government lists, and modifying the sequence of address fields. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1560 | M828 | MOM | 2023-10-18 |  |  |  | BSS | CSP Testing | Integrating Google API for auto-populating details based on service location selection. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1561 | M829 | MOM | 2023-10-18 |  |  |  | BSS | CSP Testing | Ensuring proper display and functionality of various screens within the CSP, including payment and order summary screens. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1562 | M83 | MOM | 2023-07-26 |  |  |  | WFM | User Experience | Upload of video |  | Critical | Open |  |  |  |  | As per OEM this point is not feasible 11 July 2025:- A follow-up discussion with the OEM is required to assess feasibility. If it is found to be unfeasible, a call should be arranged with Sanjay Sir along with the OEM team & artefacts needs to submit |  |  | Kaushalendra Kumar |  | Open | Not Feasible | [9 empty] | MOMWFM | Applications/Tools | #N/A |  |  |  |  | #N/A |  | 1 | Open | Open
1563 | M830 | MOM | 2023-10-18 |  |  |  | BSS | CSP Testing | Configuring event-based email notifications for actions within the CSP. |  | NON-Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1564 | M831 | MOM | 2023-10-19 |  |  |  | IPDR | Regulatory Compliance | Clarity from the Regulator on IPDR requirements to be obtained by L&T: Discussion on industry best practices and regulatory aspects to be concluded by 26th October '23. |  | Critical | Open | [7 empty] | Jayant Madavi |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMIPDR | Applications/Tools | OPEN |  |  |  |  | Artefacts to be uploaded |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1565 | M832 | MOM | 2023-11-03 |  |  |  | NSO | Service Delivery | UD,SD Peramaters to be captured. |  | Critical | Open | [7 empty] | Jayant Madavi |  | Open | Open | [9 empty] | MOMNSO | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1566 | M833 | MOM | 2023-11-03 |  |  |  | NSO | Service Delivery | NSo inventory manager funtionality to check. |  | Critical | Open | [7 empty] | Jayant Madavi |  | Open | Open | [9 empty] | MOMNSO | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1567 | M834 | MOM | 2023-11-03 |  |  |  | NSO | Service Delivery | UD perameters for product based to be prepared. |  | Critical | Open | [7 empty] | Jayant Madavi |  | Open | Open | [9 empty] | MOMNSO | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1568 | M835 | MOM | 2023-11-03 |  |  |  | NSO | Service Delivery | Ashish to comeback with Design plan for Inventory Manager at NSO |  | Critical | Open | [7 empty] | Jayant Madavi |  | Open | Open | [9 empty] | MOMNSO | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1569 | M836 | MOM | 2023-11-03 |  |  |  | NSO | Service Delivery | Arvindam to comeback with product wise UD perameters |  | Critical | Open | [7 empty] | Jayant Madavi |  | Open | Open | [9 empty] | MOMNSO | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1570 | M837 | MOM | 2023-11-03 |  |  |  | NSO | Service Delivery | Additional information for VRF, VLAN , Inner vlan etc to capture in Master DB |  | Critical | Open | [7 empty] | Jayant Madavi |  | Open | Open | [9 empty] | MOMNSO | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1571 | M838 | MOM | 2023-11-03 |  |  |  | NSO | Service Delivery | As per Cisco LLD All 28 types of L2, L3 models to be mapped aginest products |  | Critical | Open | [7 empty] | Jayant Madavi |  | Open | Open | [9 empty] | MOMNSO | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1572 | M839 | MOM | 2023-11-03 |  |  |  | NSO | Service Delivery | GL code to be mapped based on subtype GI under sub type Central & State |  | Critical | Open | [7 empty] | Jayant Madavi |  | Open | Open | [9 empty] | MOMNSO | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1573 | M84 | MOM | 2023-07-26 |  |  |  | WFM | Dashboards | Support for Workforce Management productivity statistics |  | Critical | Open |  |  |  |  | 11-7-2025:- Various reports should be demonstrated during the WFM application demo to showcase its capabilities. |  |  | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMWFM | Applications/Tools | OPEN | [6 empty] | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1574 | M840 | MOM | 2023-11-03 |  |  |  | NSO | Service Delivery | Definbe the Code for Circuit type , Customer type , customer service type etc in single format |  | Critical | Open | [7 empty] | Jayant Madavi |  | Open | Open | [9 empty] | MOMNSO | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1575 | M841 | MOM | 2023-11-03 |  |  |  | NSO | Service Delivery | Define design plan for House hold services in GPON Level |  | Critical | Open | [7 empty] | Jayant Madavi |  | Open | Open | [9 empty] | MOMNSO | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1576 | M842 | MOM | 2023-11-03 |  |  |  | NSO | Service Delivery | Define Household plan for provisioning as per the GPON plan design |  | Critical | Open | [7 empty] | Jayant Madavi |  | Open | Open | [9 empty] | MOMNSO | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1577 | M843 | MOM | 2023-11-03 |  |  |  | NSO | Service Delivery | OSS Method of distance from GIS need to comeback with plan |  | Critical | Open | [7 empty] | Jayant Madavi |  | Open | Open | [9 empty] | MOMNSO | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1578 | M844 | MOM | 2023-11-03 |  |  |  | NSO | Service Delivery | Aravindam to update on previous meetings updates to be updated in next in continuous meetings |  | Critical | Open | [7 empty] | Jayant Madavi |  | Open | Open | [9 empty] | MOMNSO | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1579 | M845 | MOM | 2023-11-17 |  |  |  | Helpdesk |  | Neox Helpdesk Demo: Scheduled for either 23rd or 24th November. |  | Critical | Open |  |  |  | WIP |  |  |  | Siva Kumar |  | Open | WIP | [9 empty] | MOMHelpdesk | Helpdesk (Contact Center) | OPEN | [6 empty] | 1 | Open | Open
1580 | M846 | MOM | 2023-11-17 |  |  |  | Helpdesk |  | Neox Compliance Confirmation: Closed on 17th November. |  | Critical | open |  |  |  | WIP | 11-Sep-25 Same has been Submitted |  |  | Siva Kumar |  | Open | WIP | [9 empty] | MOMHelpdesk | Helpdesk (Contact Center) | OPEN | [6 empty] | 1 | Open | Open
1581 | M847 | MOM | 2023-11-17 |  |  |  | Helpdesk |  | Reference for 24 Points: Praveen to share the reference of 24 points by 20th November. |  | Critical | open |  |  |  | WIP |  |  |  | Siva Kumar |  | Open | WIP | [9 empty] | MOMHelpdesk | Helpdesk (Contact Center) | OPEN | [6 empty] | 1 | Open | Open
1582 | M848 | MOM | 2023-11-17 |  |  |  | OEM Related | GPON | Closure of Issues with Tejas & Nokia: Letter of confirmation for closure to be submitted on or before 30th November ’23. |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMOEM Related | OEM Related Issues | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1 | Completed & Approved | Closed after June
1583 | M849 | MOM | 2023-11-17 |  |  |  | OEM Related | GPON | OEM Teams Onboarding: HP & Cisco OEM teams to be onboarded from 20th November '23. |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMOEM Related | OEM Related Issues | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1 | Completed & Approved | Closed after June
1584 | M85 | MOM | 2023-07-26 |  |  |  | WFM | Improvement | Check if NOC Workforce Management is handled by the proposed WFM tool |  | Critical | Open |  |  |  |  | The WFM application is designed to manage field force operations, task assignments, and service delivery. Separate licenses & functionally & user role will be required for managing NOC resources. 11 July 2025:- A note needs to be sent to Sanjay Sir outlining the benefits, potential duplication of work, and any associated drawbacks. |  |  | Kaushalendra Kumar |  | Open | Open | [9 empty] | MOMWFM | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1585 | M850 | MOM | 2023-11-17 |  |  |  | OEM Related |  | Letters from OEMs: Letters from all OEMs, excluding Cisco & HP, to be submitted by 22nd November '23. Letters from Cisco & HP to be submitted by 24th November '23. |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMOEM Related | OEM Related Issues | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1 | Completed & Approved | Closed after June
1586 | M851 | MOM | 2023-11-28 |  |  |  | Security & Regulatory Compliance | Compliance | Regulatory and Security Requirements: L&T to fast-track the closure of regulatory and security requirements, along with SLA monitoring for the immediate start of business services. |  | Critical | Open |  |  |  |  | Duplicate point. Hence clsoing this point |  |  | Sarmendra |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | Artefacts to be Submitted |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1587 | M852 | MOM | 2023-12-12 |  |  |  | NOC Operationalization |  | Submit updated Acceptable Usage Policy |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMNOC Operationalization | Network | OPEN | [6 empty] | 1 | Open | Open
1588 | M853 | MOM | 2023-12-12 |  |  |  | Security & Regulatory Compliance | Compliance | Complete configuration of CA signed SSL certificate for all web-based applications |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1589 | M854 | MOM | 2023-12-12 |  |  |  | Security & Regulatory Compliance | Compliance | Obtain T-Fiber’s approval for annual external VAPT testing |  | Critical | Open |  |  |  |  | Audit done by Allied Boston. And further external audit to be done by TFiber vendor |  |  | Sarmendra |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | Artefacts to be Submitted |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1590 | M855 | MOM | 2023-12-12 |  |  |  | Security & Regulatory Compliance | Compliance | Submit Vulnerability Management Policy as part of Patch Management Policy |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1591 | M856 | MOM | 2023-12-12 |  |  |  | Security & Regulatory Compliance | Compliance | Submit a list of Security Policy documents and all SOPs, Checklist |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1592 | M857 | MOM | 2023-12-12 |  |  |  | Security & Regulatory Compliance | Compliance | Deliver security policy documents and SOPs for launch |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1593 | M858 | MOM | 2023-12-12 |  |  |  | Security & Regulatory Compliance | Compliance | Upload RMC MoMs to shared folder and grant access to T-Fiber |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1594 | M859 | MOM | 2023-12-12 |  |  |  | Security & Regulatory Compliance | Compliance | Provide comments against each sub-point in Internal Audit Report |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1595 | M86 | MOM | 2023-07-26 |  |  |  | WFM | Improvement | Coverage of Planned Event Manpower assignment by WFM solution |  | Critical | Open |  |  |  |  | OT System Dependency |  |  | Kaushalendra Kumar |  | Open | Open | [9 empty] | MOMWFM | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1596 | M860 | MOM | 2023-12-12 |  |  |  | Security & Regulatory Compliance | Compliance | Submit Asset Management policy |  | Critical | Open |  |  |  |  | Duplicate point. Hence clsoing this point |  |  | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1597 | M861 | MOM | 2023-12-12 |  |  |  | Security & Regulatory Compliance | Compliance | Submit onboarding/offboarding policy |  | Critical | Open |  |  |  |  | Duplicate point. Hence clsoing this point |  |  | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1598 | M862 | MOM | 2023-12-12 |  |  |  | Security & Regulatory Compliance | Compliance | Report on the management of physical and environmental security |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1599 | M863 | MOM | 2023-12-12 |  |  |  | Security & Regulatory Compliance | Compliance | Provide review of work scope for External VAPT prior |  | Critical | Open | [7 empty] | Sarmendra |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | Artefacts to be Submitted |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1600 | M864 | MOM | 2023-12-12 |  |  |  | Security & Regulatory Compliance | Compliance | Close Vulnerability & patch management after audit document is finalized |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1601 | M865 | MOM | 2023-12-12 |  |  |  | Security & Regulatory Compliance | Compliance | Submit Cryptography encryption model document |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1602 | M866 | MOM | 2023-12-12 |  |  |  | OEM Related | Tejas Related | Submit updated undertakings for Tejas - Alepo and Nokia |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMOEM Related | OEM Related Issues | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1 | Completed & Approved | Closed after June
1603 | M867 | MOM | 2023-12-12 |  |  |  | Security & Regulatory Compliance | Compliance | Provide compliance with supporting documents for all applications & devices |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1604 | M868 | MOM | 2023-12-12 |  |  |  | Security & Regulatory Compliance | Compliance | Submit document on Privilege management |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1605 | M869 | MOM | 2023-12-12 |  |  |  | Security & Regulatory Compliance | Compliance | Submit a password management policy for the entire Network |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1606 | M87 | MOM | 2023-07-26 |  |  |  | WFM | Handbook & SOPs | Overall fitment of WFM in E2E applications architecture with integration touchpoints highlighted, along with the WFM flows |  | Critical | Open | [7 empty] | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMWFM | Applications/Tools | OPEN | [6 empty] | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1607 | M870 | MOM | 2023-12-12 |  |  |  | Security & Regulatory Compliance | Compliance | Disable all Remote access |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1608 | M871 | MOM | 2023-12-12 |  |  |  | Security & Regulatory Compliance | Compliance | Submit artefacts for all banners |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1609 | M872 | MOM | 2023-12-12 |  |  |  | Security & Regulatory Compliance | Compliance | Submit checklist of internal/external, Trusted, untrusted zones |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1610 | M873 | MOM | 2023-12-12 |  |  |  | Security & Regulatory Compliance | Compliance | Submit details of the policies for DMZ and internet-facing interfaces |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1611 | M874 | MOM | 2023-12-12 |  |  |  | Security & Regulatory Compliance | Compliance | Re-audit of Section 4.8 with the response captured in 4 sub-points |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1612 | M875 | MOM | 2023-12-12 |  |  |  | Security & Regulatory Compliance | Compliance | Submit list of APIs for all applications with risk information & conduct detailed audit on API security |  | Critical | Open | [7 empty] | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1613 | M876 | MOM | 2023-12-12 |  |  |  | Security & Regulatory Compliance | Compliance | Submit Security Endpoints List of Infrastructure, Workstations, etc. |  | Critical | Open |  |  |  |  | Completed . Also Screenshot has been taken during security audit . |  |  | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1614 | M877 | MOM | 2023-12-12 |  |  |  | Security & Regulatory Compliance | Compliance | Provide a list of applications generating Syslog, not generating syslog |  | Critical | Open |  |  |  |  | integration of application with syslog is still undergoing will; be submitted soon. |  |  | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1615 | M878 | MOM | 2023-12-12 |  |  |  | Security & Regulatory Compliance | Compliance | Submit DR reports for all Applications that have been tested for DC-DR switchover |  | Critical | Open |  |  |  |  | DC-dr failover will be shown during FATS for Application |  |  | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1616 | M879 | MOM | 2023-12-12 |  |  |  | Security & Regulatory Compliance | Compliance | Submit attendance list for security awareness trainings, ensure all NOC resources attend |  | Critical | Open |  |  |  |  | Last training conducted on 23 May25, and mail sent |  |  | Sarmendra |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | Artefacts to be Submitted |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1617 | M88 | MOM | 2023-07-26 |  |  |  | WFM | Handbook & SOPs | Clarity required on the scope of WFM under Phase-2 and sharing of Phase-1 & 2 scope with T-Fiber |  | Critical | Open |  |  |  |  | BSS Integration was on phase-II however it has integrated in phase-I |  |  | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMWFM | Applications/Tools | OPEN | [6 empty] | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1618 | M880 | MOM | 2023-12-12 |  |  |  | Security & Regulatory Compliance | Compliance | Finalise the duration and frequency of backup, provide storage utilisation report weekly, provide config backup details of all routers/switches/devices, submit weekly report capturing online & offline storage status |  | Critical | Open |  |  |  |  | The point is already under discussion and duration of back up has been already mentioned as per ISO 27001 Data retention policy. Custoimer mat tailor it as per their requirement |  |  | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1619 | M881 | MOM | 2023-12-15 |  |  |  | WFM |  | WFM Tool Demonstration: L&T to arrange a demonstration of the WFM tool usage for field operations soon. |  | Critical | Open | [7 empty] | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMWFM | Applications/Tools | OPEN | [6 empty] | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1620 | M882 | MOM | 2023-12-15 |  |  |  | WFM |  | WFM Mobile App Features: L&T to provide clarity on GPS tracking availability, polling frequency, photo upload feature, file size limitations, and supported Android and iOS versions. |  | Critical | Open | [7 empty] | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMWFM | Applications/Tools | OPEN | [6 empty] | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1621 | M883 | MOM | 2023-12-15 |  |  |  | WFM |  | Offline Data Storage: L&T to address the lack of offline data storage feature in the mobile application. |  | Critical | Open |  |  |  |  | 11-7-2025:- Offline data, such as images and documents, can be uploaded either from the mobile gallery or directly using the camera. To support the storage of LIDAR survey data and GIS images, an 80 TB NAS storage system has already been deployed at the NOC Data Center |  |  | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMWFM | Applications/Tools | OPEN | [6 empty] | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1622 | M884 | MOM | 2023-12-15 |  |  |  | WFM |  | Workflow Simulation: L&T to simulate a fiber cut and explain the workflow for clearing the fault and updating GIS. |  | Critical | Open | [7 empty] | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMWFM | Applications/Tools | OPEN | [6 empty] | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1623 | M885 | MOM | 2023-12-15 |  |  |  | WFM |  | Security Assurance: L&T to provide the NDA signed with M/S Lepton, assure API security, and share the contract copy. |  | Critical | Open | [7 empty] | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMWFM | Applications/Tools | OPEN | [6 empty] | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1624 | M886 | MOM | 2023-12-15 |  |  |  | GIS | GIS Related | Geo-fencing: L&T to explain how geo-fencing shall work for a fiber route and how it will be assigned for Mandal and GP locations. |  | Critical | Open | [7 empty] | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMGIS | Applications/Tools | OPEN | [6 empty] | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1625 | M887 | MOM | 2023-12-15 |  |  |  | WFM | GIS Completion | Ticket Allocation: L&T to start manual ticket allocation and freeze the process for node and link ticket allocation. |  | Critical | Open | [7 empty] | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMWFM | Applications/Tools | OPEN | [6 empty] | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1626 | M888 | MOM | 2023-12-15 | P3 |  |  | NOC Operationalization | Operational Handbook | Operations Handbook: L&T to share document forms from the Operations Handbook to be used by the WFM app. |  | Critical | Open | [7 empty] | Ahmad | 2025-10-07 | Open | Open | [9 empty] | MOMNOC Operationalization | Network | OPEN |  |  | Documentation |  | #N/A |  | 1 | Open | Open
1627 | M889 | MOM | 2023-12-15 |  |  |  | WFM |  | Summary Dashboards/Management Reports: L&T to provide inputs based on Operations best practices for weekly/monthly management reports from the WFM package. |  | Critical | Open | [7 empty] | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMWFM | Applications/Tools | OPEN | [6 empty] | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1628 | M89 | MOM | 2023-07-26 |  |  |  | WFM | Integration | Integration with Material Management systems, ERP systems, and On-Demand dashboards to be covered in Phase-2 |  | Critical | Open |  |  |  |  | For GI service delivery, the ONT inventory management feature has been given into the WFM application & integration completed between web & mobile also with BSS . application supports ONT authentication and inventory tracking. Additionally, various dashboards have been provided within the WFM application to enhance monitoring and management capabilities |  |  | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMWFM | Applications/Tools | OPEN | [6 empty] | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1629 | M890 | MOM | 2023-12-15 |  |  |  | WFM |  | The urgency for L&T to demonstrate the WFM tool for field operations and to provide detailed information on its features and capabilities. |  | Critical | Open | [7 empty] | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMWFM | Applications/Tools | OPEN | [6 empty] | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1630 | M891 | MOM | 2023-12-15 |  |  |  | WFM |  | The necessity for L&T to address the absence of offline data storage in the mobile application and to simulate a fiber cut workflow. |  | Critical | Open |  |  |  |  | Duplicate with Point- 237 |  |  | Kaushalendra Kumar |  | Open | Duplicate | [9 empty] | MOMWFM | Applications/Tools | #N/A |  |  |  |  | #N/A |  | 1 | Open | Open
1631 | M892 | MOM | 2023-12-15 |  |  |  | WFM |  | The requirement for L&T to assure security in the WFM package, including API security and geo-fencing capabilities. |  | Critical | Open | [7 empty] | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMWFM | Applications/Tools | OPEN | [6 empty] | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1632 | M893 | MOM | 2023-12-15 |  |  |  | WFM |  | The expectation for L&T to provide comprehensive management reports and dashboards to support process improvements and operational efficiency. |  | Critical | Open | [7 empty] | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMWFM | Applications/Tools | OPEN | [6 empty] | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1633 | M894 | MOM | 2023-12-19 |  |  |  | BSS |  | BSS Test Environment: VP-Program, T-Fiber requested BSS-SME, L&T to investigate and expedite the resolution of the slowness in the BSS Test Environment. |  | NON-Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1634 | M895 | MOM | 2023-12-19 |  |  |  | BSS |  | Performance Benchmarking Tools: BSS-SME, L&T to explore web-based analytic tools for performance benchmarking. |  | NON-Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1635 | M896 | MOM | 2023-12-19 |  |  |  | BSS |  | Status of Action Items: VP-Program, T-Fiber emphasized that action items marked as "Completed" should only be rendered "Closed" upon concurrence from T-Fiber. |  | NON-Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1636 | M897 | MOM | 2023-12-19 |  |  |  | BSS |  | SMS and CSP Integration: BSS-SME, L&T to implement SMS dispatch notification in CSP and include a link to the CSP page for T-Fiber USER to Approve or Reject. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1637 | M898 | MOM | 2023-12-19 |  |  |  | BSS |  | Product Catalogue Demo: SVP, T-Fiber requested a demo to showcase the configurable product catalogue feature. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1638 | M899 | MOM | 2023-12-19 |  |  |  | BSS |  | Backend Validation Demo: Director-P&E, T-Fiber asked for a demo of Backend Validation and a document with validation steps. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1639 | M9 | MOM | 2023-04-03 |  |  |  | NOC Operationalization | Full NOC Readiness | Demonstration of Repository Module |  | Critical | Open |  | Helpdesk |  | Closed | 24-Sep-25: Approved and shall be closed, its NAS Created in NOC for all Domains documentaton |  |  | Siva Kumar |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-24 | \\172.28.9.23\tnocreports |  | 1 | Completed & Approved | Closed after June
1640 | M90 | MOM | 2023-07-26 |  |  |  | WFM | Improvement | Proposed WFM solution support field personnel to schedule appointments with end customers |  | Critical | Open |  |  |  |  | Customer appointment is being handled by BSS and FE appointment by WFM |  |  | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMWFM | Applications/Tools | OPEN | [6 empty] | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1641 | M900 | MOM | 2023-12-19 |  |  |  | BSS |  | Page Load Benchmark: Director-P&E, T-Fiber requested a benchmark for page loading to be defined. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1642 | M901 | MOM | 2023-12-19 |  |  |  | BSS |  | Payment Gateway Integration: BSS-SME, L&T confirmed integration is completed with a test account. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1643 | M902 | MOM | 2023-12-19 |  |  |  | BSS |  | BSS E2E Demo: Chief Delivery Officer, L&T proposed to have the E2E BSS Demo on 4th July '23, with features to be confirmed by 1st July '23. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1644 | M903 | MOM | 2023-12-19 |  |  |  | WFM |  | Mobile App & WFM: SVP, T-Fiber requested clarity on the number of mobile apps and urged L&T to freeze the scope in consultation with MSI B and C. Demo with M/S Lepton scheduled for 21st June '23. |  | Critical | Open |  |  |  |  | Duplicate with Point- 214 |  |  | Kaushalendra Kumar |  | Open | Duplicate | [9 empty] | MOMWFM | Applications/Tools | #N/A |  |  |  |  | #N/A |  | 1 | Open | Open
1645 | M904 | MOM | 2023-12-19 |  |  |  | GIS | GIS Completion | BSS-SME, L&T to ensure Dark Fiber with BSS and WFM flows can be shown by 30th December '23. |  | Critical | Open |  |  |  |  | Pending with BSS Team |  |  | Kaushalendra Kumar |  | Open | Open | [9 empty] | MOMGIS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1646 | M905 | MOM | 2023-12-19 |  |  |  | NOC Operationalization | Launch Readiness | T-Cell, T-VPN, and GI-ILL Completion: SVP, T-Fiber called for these to be completed on priority before the visit by Hon’ Minister. |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMNOC Operationalization | Network | OPEN | [6 empty] | 1 | Open | Open
1647 | M906 | MOM | 2023-12-19 |  |  |  | GIS | Feasibility Logic | Feasibility Logic: SVP, T-Fiber asked for the feasibility logic to include S1, S2 splitters and to be demonstrated in the next demo. |  | Critical | Open |  |  |  |  | Dependency On OSS Splitter View has been given to OSS team |  |  | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMGIS | Applications/Tools | OPEN | [6 empty] | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1648 | M907 | MOM | 2023-12-19 |  |  |  | OSS | Feasibility Logic | Bandwidth Feasibility Logic: Director-P&E, T-Fiber requested the logic for Bandwidth feasibility in the backhaul to be provisioned and operationalised immediately. |  | Critical | Open |  |  |  |  | This point not related to GIS,11th July 2025:- As discussed with Sanjay Sir, this points need to be move to the OSS team. |  |  | Suresh Pawar |  | Open | Shifted to OSS | [9 empty] | MOMOSS | Applications/Tools | #N/A | #N/A | #N/A |  |  | #N/A |  | 1 | Open | Open
1649 | M908 | MOM | 2023-12-19 |  |  |  | BSS | Resource Augmentation | NMS Works Resources: SVP, T-Fiber requested a discussion with EVP, T-Fiber on the adequacy of NMS works resources. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN | [6 empty] | 1 | Open | Open
1650 | M909 | MOM | 2023-12-19 |  |  |  | BSS | BSS | Repository Module for Document Upload: BSS-SME, L&T to ensure the module is available in CRM and discussed with OEM. |  | NON-Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN | [6 empty] | 1 | Open | Open
1651 | M91 | MOM | 2023-07-26 |  |  |  | WFM | Handbook & SOPs | Finalization of Operational Processes linked to WFM workflows |  | Critical | Open | [7 empty] | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMWFM | Applications/Tools | OPEN | [6 empty] | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1652 | M910 | MOM | 2023-12-19 |  |  |  | BSS | WhatsApp | WhatsApp Integration: BSS-SME, L&T to incorporate advanced features into WhatsApp Integration with CSP. |  | NON-Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN | [6 empty] | 1 | Open | Open
1653 | M911 | MOM | 2023-12-19 |  |  |  | BSS |  | UI/UX Resource: BSS-SME, L&T updated that an internal UI/UX resource has been onboarded. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1654 | M912 | MOM | 2023-12-19 |  |  |  | BSS |  | Discussions on the BSS roadmap, including the status of action items from the dry run and CSP testing exercise. |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1655 | M913 | MOM | 2023-12-19 |  |  |  | Field Related | District Completion Target | The urgency for STL to complete E2E for additional districts by 07th April '23 and the need to resolve issues impacting project progress. |  | NON-Critical | Open | [7 empty] | S Kodali |  | Open | Open | [9 empty] | MOMField Related | Field Related issues | OPEN |  |  | Project Team |  | #N/A |  | 1 | Open | Open
1656 | M914 | MOM | 2023-12-19 |  |  |  | NOC Operationalization |  | The necessity for STL to complete T-NOC Operationalization by 6th April 2023 to begin commercialization. |  | Critical | Open | [7 empty] | Ahmad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  | Not related to delivery | 2025-09-22 | Artefacts not Required |  | 1 | Completed & Approved | Closed after June
1657 | M915 | MOM | 2023-12-19 |  |  |  | Field Related | Resource Augmentation | The requirement for STL to address resource productivity issues and ensure sufficient resources for project completion. |  | NON-Critical | Open | [7 empty] | S Kodali |  | Open | Open | [9 empty] | MOMField Related | Field Related issues | OPEN |  |  | Project Team |  | #N/A |  | 1 | Open | Open
1658 | M916 | MOM | 2023-12-19 |  |  |  | Field Related | Payment Related | The need for T-Fiber to expedite payment processes and for STL to provide a senior resource to orchestrate project completion efforts. |  | NON-Critical | Open | [7 empty] | S Kodali |  | Open | Open | [9 empty] | MOMField Related | Field Related issues | OPEN |  |  | Project Team |  | #N/A |  | 1 | Open | Open
1659 | M917 | MOM | 2023-12-19 |  |  |  | NOC Operationalization |  | The presentation of a comprehensive T-NOC operationalisation plan by STL, with clear phases and readiness stages. |  | Critical | Open | [7 empty] | Ahmad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  | Not related to delivery | 2025-09-22 | Artefacts not Required |  | 1 | Completed & Approved | Closed after June
1660 | M918 | MOM | 2023-12-19 |  |  |  | Field Related | Zonal Path connectivity | The completion of zonal paths and the delivery of districts within the committed timelines. |  | NON-Critical | Open | [7 empty] | S Kodali |  | Open | Open | [9 empty] | MOMField Related | Field Related issues | OPEN |  |  | Project Team |  | #N/A |  | 1 | Open | Open
1661 | M919 | MOM | 2023-12-28 |  |  |  | NOC Operationalization | Launch Readiness | Achieve T-VPN and T-DILL completion by 31st Jan '24; confirm Dark Fiber P2P link target date later. |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMNOC Operationalization | Network | OPEN | [6 empty] | 1 | Open | Open
1662 | M92 | MOM | 2023-07-26 |  |  |  | WFM | Resource Related | Perpetual licenses for WFM |  | Critical | Open |  |  |  |  | TFIBER is a critical dependency for closing the WFM license |  |  | Kaushalendra Kumar |  | Open | Open | [9 empty] | MOMWFM | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1663 | M920 | MOM | 2023-12-28 |  |  |  | NOC Operationalization | Launch Readiness | Ensure basic products are available by end of April '24; complete all 28 products within 2 months beyond April '24. |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMNOC Operationalization | Network | OPEN | [6 empty] | 1 | Open | Open
1664 | M921 | MOM | 2023-12-28 |  |  |  | NSO | Service Delivery | Develop Service Delivery – Provisioning through OSS module; address potential failures and industry best practices. |  | Critical | Open | [7 empty] | Jayant Madavi |  | Open | Open | [9 empty] | MOMNSO | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1665 | M922 | MOM | 2023-12-28 |  |  |  | OEM Related | Service Delivery | Manual KPI for service assurance due to lack of OEM confirmation; address concerns about NSO and OSS use. |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMOEM Related | OEM Related Issues | OPEN | [6 empty] | 1 | Open | Open
1666 | M923 | MOM | 2023-12-28 |  |  |  | OEM Related |  | Align L&T and OEM with product vision and delivery cadence; consider product development strategy. |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMOEM Related | OEM Related Issues | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1 | Completed & Approved | Closed after June
1667 | M924 | MOM | 2023-12-28 |  |  |  | NSO | Resource Augmentation | NSO resource available from 3rd January '24; ensure readiness to operate remotely and train L&T resources. |  | Critical | Open | [7 empty] | Jayant Madavi |  | Open | Open | [9 empty] | MOMNSO | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1668 | M925 | MOM | 2023-12-28 |  |  |  | NOC Operationalization | Launch Readiness | Conduct Dry Run for 3 Products (GI-BB, T-CELL, Dark Fiber) on 5th January '24 with BSS & WFM; share date soon. |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMNOC Operationalization | Network | OPEN | [6 empty] | 1 | Open | Open
1669 | M926 | MOM | 2023-12-28 |  |  |  | NOC Operationalization | Communication Matrix | Initiate daily meetings with T-Fiber; share progress updates daily. |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1 | Completed & Approved | Closed after June
1670 | M927 | MOM | 2023-12-28 |  |  |  | NOC Operationalization | O&M Related | Start daily uptime report immediately; resolve duplicate TroubleTicket issue within the week. |  | Critical | Open |  |  |  | Closed | 24-Sep-25: Approved and shall be closed |  |  | Siva Kumar |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-24 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\M927 |  | 1 | Completed & Approved | Closed after June
1671 | M928 | MOM | 2023-12-28 |  |  |  | Security & Regulatory Compliance | Compliance | Clarify NOC resource roles and seating; discuss and fix scope for external audit by 3rd Jan '24; conduct External Audit by 31st January '24. |  | Critical | Open |  |  |  |  | Audit done by Allied Boston. And further external audit to be done by TFiber vendor. Scope has been submitted to customer for external Audit. NOC teams role and KRA shared with TFiber |  |  | Sarmendra |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | Artefacts to be Submitted |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1672 | M929 | MOM | 2023-12-28 |  |  |  | Helpdesk |  | Address maturity of the Helpdesk; clarify integration aspects and ensure Helpdesk is ready to handle calls. |  | Critical | Open |  |  |  | WIP |  |  |  | Siva Kumar |  | Open | WIP | [9 empty] | MOMHelpdesk | Helpdesk (Contact Center) | OPEN | [6 empty] | 1 | Open | Open
1673 | M93 | MOM | 2023-07-26 |  |  |  | WFM | Handbook & SOPs | To check for potential overlapping functions between proposed WFM app and GIS O&M app, and accordingly streamline the Operational process |  | Critical | Open | [7 empty] | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMWFM | Applications/Tools | OPEN | [6 empty] | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1674 | M930 | MOM | 2023-12-28 |  |  |  | NOC Operationalization | Launch Readiness | Cover all requirements in the roadmap with completion dates; explore standard templates for SLA reports to settle invoices with BBNL. |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1 | Completed & Approved | Closed after June
1675 | M931 | MOM | 2023-12-28 |  |  |  | NOC Operationalization | O&M Related | Provide clarity on Alarm Correlation, cross-domain RCA, SIA, Helpdesk design, Network and Service Topology. |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMNOC Operationalization | Network | OPEN | [6 empty] | 1 | Open | Open
1676 | M932 | MOM | 2023-12-28 |  |  |  | NOC Operationalization | Launch Readiness | Deliver NOC before the end of T3 as mandated by EVP, T-Fiber. |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1 | Completed & Approved | Closed after June
1677 | M933 | MOM | 2024-01-05 |  |  |  | BSS | BSS | BSS readiness |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1678 | M934 | MOM | 2024-01-05 |  |  |  | BSS | Product category | Unique ID – Naming Convention |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1679 | M935 | MOM | 2024-01-05 |  |  |  | NSO | Service provisioning | GUI Interface for NSO |  | Critical | Open | [7 empty] | Jayant Madavi |  | Open | Open | [9 empty] | MOMNSO | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1680 | M936 | MOM | 2024-01-05 |  |  |  | BSS | Billing Related | Payment Approach & Integration |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1681 | M937 | MOM | 2024-01-05 |  |  |  | BSS | Billing Related | Invoice Template |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1682 | M938 | MOM | 2024-01-05 |  |  |  | BSS | Billing Related | Integration of Bill Desk & Other Points |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1683 | M939 | MOM | 2024-01-18 |  |  |  | BSS | Product category | BSS progress session for Dark Fiber |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1684 | M94 | MOM | 2023-07-26 |  |  |  | WFM | Improvement | Manual overwrite of data |  | Critical | Open |  |  |  |  | 11-7-2025:-WFM does not allow any manual data overwrite scenarios |  |  | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMWFM | Applications/Tools | OPEN | [6 empty] | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1685 | M940 | MOM | 2024-01-18 |  |  |  | OSS | Integration | Integrate live data for location feasibility |  | Critical | Open |  | Gtech |  |  | This point not related to GIS,External Feasibility Tool is required ,11th July 2025:- As discussed with Sanjay Sir, this points need to be move to the OSS team. |  |  | Suresh Pawar |  | Open | Shifted to OSS | [9 empty] | MOMOSS | Applications/Tools | #N/A | #N/A | #N/A |  |  | #N/A |  | 1 | Open | Open
1686 | M941 | MOM | 2024-01-18 |  |  |  | OSS | Integration | Review and align ‘Ready for Service’ nomenclature |  | Critical | Open |  | Gtech |  |  | This point not related to GIS, 11th July 2025:-this point needs to be discussed with Siva Sir to explore the possibility of accommodating the feature in the respective application, as it is not related to GIS |  |  | Suresh Pawar |  | Open | Shifted to OSS | [9 empty] | MOMOSS | Applications/Tools | #N/A | #N/A | #N/A |  |  | #N/A |  | 1 | Open | Open
1687 | M942 | MOM | 2024-01-18 |  |  |  | BSS | CRM | Implement auto-population of fields in CRM |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1688 | M943 | MOM | 2024-01-18 |  |  |  | BSS |  | Implement user access control for RFO to RFS conversion |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1689 | M944 | MOM | 2024-01-18 |  |  |  | BSS | GIS | Integrate BSS with GIS for distance calculation |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1690 | M945 | MOM | 2024-01-18 |  |  |  | BSS |  | Provide updates and roadmap for Lead/Opportunity/Order conversion process |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1691 | M946 | MOM | 2024-01-18 |  |  |  | BSS |  | Implement Mandal to GP and Mandal to Mandal Dark fiber service |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1692 | M947 | MOM | 2024-01-18 |  |  |  | BSS |  | Clarify the list of individuals involved in BSS operations |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1693 | M948 | MOM | 2024-01-18 |  |  |  | BSS |  | Resolve document upload feature with order tagging |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1694 | M949 | MOM | 2024-01-18 |  |  |  | BSS |  | Prepare for soft launch in accordance with management's direction |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1695 | M95 | MOM | 2023-07-26 |  |  |  | WFM | User Experience | Verification process for checking whether the field technician has gone to the required location or not. |  | Critical | Open | [7 empty] | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMWFM | Applications/Tools | OPEN | [6 empty] | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1696 | M950 | MOM | 2024-01-18 |  |  |  | BSS |  | Upload BSNL locations for demonstration and discuss GIS integration and document repository issues |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1697 | M951 | MOM | 2024-01-18 |  |  |  | BSS |  | Confirm timeline for GI-BB and T-Cell |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1698 | M952 | MOM | 2024-01-18 |  |  |  | BSS |  | Discuss Route and Bridge Mode for Internet Leased Line product |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1699 | M953 | MOM | 2024-01-24 |  |  |  | NOC Operationalization |  | NOC Readiness Review |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1 | Completed & Approved | Closed after June
1700 | M954 | MOM | 2024-01-24 |  |  |  | NOC Operationalization |  | Ensure full delivery of NOC including field O&M and basic six products |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1 | Completed & Approved | Closed after June
1701 | M955 | MOM | 2024-01-24 |  |  |  | NOC Operationalization |  | Confirm readiness of all NOC modules including ticketing, Helpdesk and WFM |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMNOC Operationalization | Network | OPEN | [6 empty] | 1 | Open | Open
1702 | M956 | MOM | 2024-01-24 |  |  |  | NOC Operationalization |  | Deliver service inventory module |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMNOC Operationalization | Network | OPEN | [6 empty] | 1 | Open | Open
1703 | M957 | MOM | 2024-01-24 |  |  |  | NOC Operationalization |  | Create a tracker sheet for conditional approvals and workshop points |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMNOC Operationalization | Network | OPEN | [6 empty] | 1 | Open | Open
1704 | M958 | MOM | 2024-01-24 |  |  |  | NOC Operationalization |  | Submit detailed plan for module-wise readiness |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1 | Completed & Approved | Closed after June
1705 | M959 | MOM | 2024-01-24 |  |  |  | NOC Operationalization |  | Present documentation for automation of 6 products |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMNOC Operationalization | Network | OPEN | [6 empty] | 1 | Open | Open
1706 | M96 | MOM | 2023-08-01 |  |  |  | Helpdesk | User Experience | Toll Free-Number |  | NON-Critical | Open |  |  |  |  | 11-09-2025: Same as T366(472) Closed |  |  | Siva Kumar |  |  | COMPLETED & APPROVED | Yes | 2025-07-19 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\T366 | [6 empty] | MOMHelpdesk | Helpdesk (Contact Center) | CLOSED |  |  |  | 2025-07-19 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\T366 |  | 1 | Completed & Approved | Closed after June
1707 | M960 | MOM | 2024-01-24 |  |  |  | NOC Operationalization |  | Submit package for NOC readiness, roadmaps, and sheets |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1 | Completed & Approved | Closed after June
1708 | M961 | MOM | 2024-01-24 |  |  |  | NOC Operationalization |  | Engage OEMs till end-to-end stabilization of services |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1 | Completed & Approved | Closed after June
1709 | M962 | MOM | 2024-01-24 |  |  |  | NOC Operationalization |  | Discuss pending points and close the final scope with T-Fiber |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1 | Completed & Approved | Closed after June
1710 | M963 | MOM | 2024-01-24 |  |  |  | NOC Operationalization |  | Share a business continuity plan for 6 manual to automated product transitions |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMNOC Operationalization | Network | OPEN | [6 empty] | 1 | Open | Open
1711 | M964 | MOM | 2024-01-24 |  |  |  | NOC Operationalization |  | Present NOC pre-production testing and environment plan |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1 | Completed & Approved | Closed after June
1712 | M965 | MOM | 2024-01-24 |  |  |  | NOC Operationalization |  | Confirm list of BSS operation team members |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1 | Completed & Approved | Closed after June
1713 | M966 | MOM | 2024-01-24 |  |  |  | WFM | NOC Operationalization | Update the GIS data and confirm its operation SOP |  | Critical | Open | [7 empty] | Kaushalendra Kumar |  | Open | Open | [9 empty] | MOMWFM | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1714 | M967 | MOM | 2024-01-24 |  |  |  | NOC Operationalization |  | Deploy senior resource for managing T-Fiber helpdesk |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMNOC Operationalization | Network | OPEN | [6 empty] | 1 | Open | Open
1715 | M968 | MOM | 2024-01-24 |  |  |  | NOC Operationalization |  | Separate helpdesk and call center desk with transition plan |  | Critical | Open |  |  |  | WIP | Only technical helpdesk in scope which is operational | T Fiber | Sanjay | Siva Kumar |  | Open | WIP | [9 empty] | MOMNOC Operationalization | Network | OPEN | [6 empty] | 1 | Open | Open
1716 | M969 | MOM | 2024-01-24 |  |  |  | NOC Operationalization |  | Arrange toll-free number and update on notification formats readiness |  | Critical | Open |  |  |  | WIP |  |  |  | Siva Kumar |  | Open | WIP | [9 empty] | MOMNOC Operationalization | Network | OPEN | [6 empty] | 1 | Open | Open
1717 | M97 | MOM | 2023-08-01 |  |  |  | Helpdesk | User Experience | Different communication channels such as SMS, WhatsApp, Email |  | Critical | open |  |  |  | WIP | 11- Sep-25: SMS and E-mail Integrated and Whatsapp existing Product will not support |  |  | Siva Kumar |  | Open | WIP | [9 empty] | MOMHelpdesk | Helpdesk (Contact Center) | OPEN | [6 empty] | 1 | Open | Open
1718 | M970 | MOM | 2024-01-24 |  |  |  | NOC Operationalization |  | Integrate WhatsApp for customer communication through calls with IVR |  | Critical | Open |  |  |  | WIP |  |  |  | Siva Kumar |  | Open | WIP | [9 empty] | MOMNOC Operationalization | Network | OPEN | [6 empty] | 1 | Open | Open
1719 | M971 | MOM | 2024-01-24 |  |  |  | NOC Operationalization |  | Provide updates on NOC progress and ensure commitment dates are met |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1 | Completed & Approved | Closed after June
1720 | M972 | MOM | 2024-01-24 |  |  |  | NOC Operationalization |  | Deploy stable standard product for IPDR |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1 | Completed & Approved | Closed after June
1721 | M973 | MOM | 2024-01-24 |  |  |  | NOC Operationalization |  | Ensure pre-scheduled meetings occur without SMEs absence |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1 | Completed & Approved | Closed after June
1722 | M974 | MOM | 2024-01-24 |  |  |  | NOC Operationalization |  | Prepare NOC for review by the State IT&EC Minister and PS-ITE&C |  | Critical | Open |  |  |  | Closed | 24-Sep-25: Closed, Meeting completed |  |  | Siva Kumar |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-24 | Artefacts not Required |  | 1 | Completed & Approved | Closed after June
1723 | M975 | MOM | 2024-01-24 |  |  |  | NOC Operationalization |  | Project Review with 3 MSIs |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1 | Completed & Approved | Closed after June
1724 | M976 | MOM | 2024-01-24 | P3 |  |  | NOC Operationalization |  | Resource mobilization and network availability |  | Critical | Open |  |  |  |  | NOC resources available, availability report being shared |  |  | Ahmad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  | Not related to delivery | 2025-09-19 | Artefacts not Required |  | 1 | Completed & Approved | Closed after June
1725 | M977 | MOM | 2024-01-24 |  |  |  | NOC Operationalization |  | Adoption of WFM by packages B & C |  | Critical | Open |  |  |  | WIP |  | L&T | Sivaprasad | Sivaprasad |  | Open | WIP | [9 empty] | MOMNOC Operationalization | Network | OPEN | [6 empty] | 1 | Open | Open
1726 | M978 | MOM | 2024-01-24 |  |  |  | Field Related |  | Implementation of Mandal rings of NoFN PH-1 |  | NON-Critical | Open | [7 empty] | S Kodali |  | Open | Open | [9 empty] | MOMField Related | Field Related issues | OPEN |  |  | Project Team |  | #N/A |  | 1 | Open | Open
1727 | M979 | MOM | 2024-01-24 |  |  |  | NOC Operationalization |  | Restoration of social welfare and tribal welfare schools to service |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1 | Completed & Approved | Closed after June
1728 | M98 | MOM | 2023-08-01 |  |  |  | Helpdesk | Dashboards | Categorization of Incoming Queries |  | Critical | open |  |  |  | WIP | 11- Sep-25: Available in Neox Application |  |  | Siva Kumar |  | Open | WIP | [9 empty] | MOMHelpdesk | Helpdesk (Contact Center) | OPEN | [6 empty] | 1 | Open | Open
1729 | M980 | MOM | 2024-01-24 |  |  |  | Field Related |  | Complete all GI connectivity before March '24 |  | Critical | Open | [7 empty] | S Kodali |  | Open | Open | [9 empty] | MOMField Related | Field Related issues | OPEN |  |  | Project Team |  | Artefacts to be uploaded |  | 1 | Open | Open
1730 | M981 | MOM | 2024-01-24 |  |  |  | NOC Operationalization |  | Focus on top 4 network readiness priorities |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1 | Completed & Approved | Closed after June
1731 | M982 | MOM | 2024-01-25 |  |  |  | WFM | NOC Operationalization | WFM Patrolling App Demo |  | Critical | Open | [7 empty] | Kaushalendra Kumar |  | Open | Open | [9 empty] | MOMWFM | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1732 | M983 | MOM | 2024-01-25 |  |  |  | WFM | NOC Operationalization | Complete WFM-OSS integration |  | Critical | Open | [7 empty] | Kaushalendra Kumar |  | Open | Open | [9 empty] | MOMWFM | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1733 | M984 | MOM | 2024-01-25 |  |  |  | NOC Operationalization |  | Submit solution document for PoP RFS |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1 | Completed & Approved | Closed after June
1734 | M985 | MOM | 2024-01-25 |  |  |  | WFM | NOC Operationalization | Understand use cases of WFM integration with BSS |  | Critical | Open | [7 empty] | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMWFM | Applications/Tools | OPEN | [6 empty] | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1735 | M986 | MOM | 2024-01-25 |  | OSS | OSS | OSS |  | Complete Fault Management and Trouble Ticketing |  | Critical | Open | [7 empty] | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMOSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1736 | M987 | MOM | 2024-01-25 |  |  |  | WFM | NOC Operationalization | Clarify GIS vs WFM mobile app usage |  | Critical | Open | [7 empty] | Kaushalendra Kumar |  | Open | Open | [9 empty] | MOMWFM | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1737 | M988 | MOM | 2024-01-25 |  |  |  | WFM | NOC Operationalization | Submit the NDA signed between L&T and M/S Lepton |  | Critical | Open | [7 empty] | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMWFM | Applications/Tools | OPEN | [6 empty] | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1738 | M989 | MOM | 2024-01-25 |  |  |  | Security & Regulatory Compliance | NOC Operationalization | Ensure API security measures |  | Critical | Open |  |  |  |  | Applicationer has been asked to collect from Developers |  |  | Sarmendra |  | Open | Open | [9 empty] | MOMSecurity & Regulatory Compliance | Security | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1739 | M99 | MOM | 2023-08-01 |  |  |  | Helpdesk | User Experience | Bilingual IVR |  | Critical | open |  |  |  | CLosed | 24-Sep-25: Now its in 3 Languages |  |  | Siva Kumar |  |  | COMPLETED & APPROVED | [9 empty] | MOMHelpdesk | Helpdesk (Contact Center) | CLOSED |  |  |  | 2025-09-24 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\M121,170,99,726 |  | 1 | Completed & Approved | Closed after June
1740 | M990 | MOM | 2024-01-25 |  | OSS | OSS | OSS |  | Submit sample dashboards/reports |  | Critical | Open | [7 empty] | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMOSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1741 | M991 | MOM | 2024-01-25 | P3 |  |  | NOC Operationalization |  | Provide Operations Handbook document forms |  | Critical | Open | [7 empty] | Ahmad | 2025-10-07 | Open | Open | [9 empty] | MOMNOC Operationalization | Network | OPEN |  |  | Documentation |  | #N/A |  | 1 | Open | Open
1742 | M992 | MOM | 2024-01-25 |  |  |  | NOC Operationalization |  | Clarify attendance watermarking feature |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1 | Completed & Approved | Closed after June
1743 | M993 | MOM | 2024-01-25 |  |  |  | NOC Operationalization |  | Schedule weekly training for patrollers |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1 | Completed & Approved | Closed after June
1744 | M994 | MOM | 2024-01-25 |  |  |  | NOC Operationalization |  | Update on previous MoM action items |  | Critical | Open |  |  |  | Closed | 23-Sep-25: Approved shall be closed |  |  | Sivaprasad |  |  | COMPLETED & APPROVED | [9 empty] | MOMNOC Operationalization | Network | CLOSED |  |  |  | 2025-09-23 | Artefacts not Required |  | 1 | Completed & Approved | Closed after June
1745 | M995 | MOM | 2024-01-25 |  |  |  | BSS |  | Continue defining logic for Dark Fiber and GI-BB products |  | Critical | Open | [7 empty] | Manoj Nibrad |  | Open | Open | [9 empty] | MOMBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1746 | M996 | MOM | 2024-01-25 |  |  |  | WFM | NOC Operationalization | Dry run and operationalize three routes for testing WFM with actual data |  | Critical | Open | [7 empty] | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | MOMWFM | Applications/Tools | OPEN | [6 empty] | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1747 | M997 | MOM | 2024-01-25 |  |  |  | Field Related |  | Improve resource mobilization & achieve 65% network availability |  | NON-Critical | Open | [7 empty] | S Kodali |  | Open | Open | [9 empty] | MOMField Related | Field Related issues | OPEN |  |  | Project Team |  | #N/A |  | 1 | Open | Open
1748 | M998 | MOM | 2024-01-25 |  |  |  | Field Related |  | Engage partners for O&M resources augmentation and ensure active spares availability |  | NON-Critical | Open | [7 empty] | S Kodali |  | Open | Open | [9 empty] | MOMField Related | Field Related issues | OPEN |  |  | O&M Team |  | #N/A |  | 1 | Open | Open
1749 | M999 | MOM | 2024-01-25 |  |  |  | Field Related |  | Deploy committed resources and achieve network availability |  | NON-Critical | Open | [7 empty] | S Kodali |  | Open | Open | [9 empty] | MOMField Related | Field Related issues | OPEN |  |  | O&M Team |  | #N/A |  | 1 | Open | Open
`

## NOC-Summary (hidden)
Sum of Qty | Column Labels
Row Labels | Closed after June | Completed but Verification undrer Process | Open | Grand Total
Jayant Madavi |  | 4 | 25 | 29
Kaushalendra Kumar |  | 17 | 1 | 18
Manoj Nibrad |  |  | 133 | 133
Sayyad Pasha | 10 |  | 40 | 50
Siva Kumar | 5 |  | 20 | 25
Suresh Pawar |  | 248 | 175 | 423
Grand Total | 15 | 269 | 394 | 678

## NOC-Detailed sheet (hidden)
Slno | UniqueID | Category | Meeting Date | Priority | Ramana | Ramana-Domain | Domain | Sub-Domain | Action Point | Impact | Priority | Baseline Status | xx | Application | Module | Remarks | Remarks | Organization | Owner | Owner(L&T) | Target Date to Complete | Open | Revised Status (L&T) As on 18-Sep-2025 | Approved BY (TF) | Approval Date(TF) | Link of evidences | R | S | T | U | V | W | X | Tfiber-Cat | Derived Status (L&T) | OSS | OSS Remarks | Ramana Remarks as on 19-Sep-2025 | T Fiber Appoved Date | Artefacts | Target Date | Qty | Ramana-Remarks | Updated on 13-Oct-2025
1750 | NOC1 | NOC | NA |  | OSS | OSS | OSS | DC | DC Active Infra uptime & SLA Daily |  | Critical |  |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCOSS | Applications/Tools | OPEN | OPEN | 0 |  |  | #N/A |  | 1 | Open | Open
1751 | NOC10 | NOC | NA |  | OSS | OSS | OSS | DC | DC Passive infra uptime & SLA Weekly |  | Critical |  |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCOSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  | #N/A |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1752 | NOC100 | NOC | NA |  |  |  | GPON | OSS | Governenmnet Institutions ( GI ) links delivery. Preparation and publishing of KPI Daily |  | Critical | OPEN |  | NNMI | NPS |  | OPEN-DEPENDENT |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCGPON | Applications/Tools | OPEN | OPEN-DEPENDENT | 0 |  |  | #N/A |  | 1 | Open | Open
1753 | NOC101 | NOC | NA |  |  |  | GPON | OSS | Governenmnet Institutions ( GI ) links delivery. Preparation and publishing of KPI Weekly |  | Critical | OPEN |  | NNMI | NPS |  | OPEN-DEPENDENT |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCGPON | Applications/Tools | OPEN | OPEN-DEPENDENT | 0 |  |  | #N/A |  | 1 | Open | Open
1754 | NOC102 | NOC | NA |  |  |  | GPON | OSS | Governenmnet Institutions ( GI ) links delivery. Preparation and publishing of KPI Monthly |  | Critical | OPEN |  | NNMI | NPS |  | OPEN-DEPENDENT |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCGPON | Applications/Tools | OPEN | OPEN-DEPENDENT | 0 |  |  | #N/A |  | 1 | Open | Open
1755 | NOC103 | NOC | NA |  |  |  | GPON | OSS | Governenmnet Institutions ( GI ) links delivery. Preparation and publishing of KPI (Selective from and to dates) |  | Critical | OPEN |  | NNMI | NPS |  | OPEN-DEPENDENT |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCGPON | Applications/Tools | OPEN | OPEN-DEPENDENT | 0 |  |  | #N/A |  | 1 | Open | Open
1756 | NOC104 | NOC | NA |  |  |  | GPON | OSS | Published GP Network uptime (like, total scope, litup count and availability according to the category) Daily |  | Critical | COMPLETED |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCGPON | Applications/Tools | OPEN | CLOSURE REVIEW PENDING | 0 |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1757 | NOC105 | NOC | NA |  |  |  | GPON | OSS | Published GP Network uptime (like, total scope, litup count and availability according to the category) Weekly |  | Critical | OPEN |  | HPSM | Incident Management |  | 26-Sep-2025: GPON , DWDM, Routers, switches and UPS we can take monthly and Daily reports from UOC. For UPS, Routers and switches we can take hourly, weekly, monthly on demand and any selective period basis from NNMI. L&T conveyed that, As per the agreed scope of work between L&T, TFiber, HP and OT this hourly and weekly granuality not given in the scope, also availability based on alarm. As per the confirmation from Manoj L&T, The existing tool can only give daily and monthly reports only. Apart from that the system doesn't have capabilities to generate other reports. Vigility need to co-ordinate with OEM and confirm the feasibility. |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCGPON | Applications/Tools | OPEN | NOT-FEASIBLE | 26-Sep-2025: GPON , DWDM, Routers, switches and UPS we can take monthly and Daily reports from UOC. For UPS, Routers and switches we can take hourly, weekly, monthly on demand and any selective period basis from NNMI. L&T conveyed that, As per the agreed scope of work between L&T, TFiber, HP and OT this hourly and weekly granuality not given in the scope, also availability based on alarm. As per the confirmation from Manoj L&T, The existing tool can only give daily and monthly reports only. Apart from that the system doesn't have capabilities to generate other reports. Vigility need to co-ordinate with OEM and confirm the feasibility. |  |  |  |  | 1 | Open | Open
1758 | NOC106 | NOC | NA |  |  |  | GPON | OSS | Published GP Network uptime (like, total scope, litup count and availability according to the category) Monthly |  | Critical | COMPLETED |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCGPON | Applications/Tools | OPEN | CLOSURE REVIEW PENDING | 0 |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1759 | NOC107 | NOC | NA |  |  |  | GPON | OSS | Published GP Network uptime (like, total scope, litup count and availability according to the category) (Selective from and to dates) |  | Critical | COMPLETED |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCGPON | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1760 | NOC108 | NOC | NA |  |  |  | GPON | OSS | Publishing Package wise and District wise GP Network uptime and GP TT resolution MTTR dashboard Daily |  | Critical | COMPLETED |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCGPON | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1761 | NOC109 | NOC | NA |  |  |  | GPON | OSS | Publishing Package wise and District wise GP Network uptime and GP TT resolution MTTR dashboard Weekly |  | Critical | COMPLETED |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCGPON | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1762 | NOC11 | NOC | NA |  | OSS | OSS | OSS | DC | DC Passive infra uptime & SLA Monthly |  | Critical |  |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCOSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  | #N/A |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1763 | NOC110 | NOC | NA |  |  |  | GPON | OSS | Publishing Package wise and District wise GP Network uptime and GP TT resolution MTTR dashboard Monthly |  | Critical | COMPLETED |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCGPON | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1764 | NOC111 | NOC | NA |  |  |  | GPON | OSS | Publishing Package wise and District wise GP Network uptime and GP TT resolution MTTR dashboard (Selective from and to dates) |  | Critical | OPEN |  | HPSM | Incident Management |  | Availability is available in UOC for Daily and monthly only. MTTR Report is available from SM on Daily , Weekly, monthly and customized period. Dashboards made available as per requirements against MTTR |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCGPON | Applications/Tools | OPEN | WIP | Availability is available in UOC for Daily and monthly only. MTTR Report is available from SM on Daily , Weekly, monthly and customized period. Dashboards made available as per requirements against MTTR |  |  | #N/A |  | 1 | Open | Open
1765 | NOC112 | NOC | NA |  |  |  | GPON | OSS | Published Mandal Network uptime (like, total scope, litup count and availability according to the category) Hourly |  | Critical | OPEN |  | HPSM | Incident Management |  | Availability is available in UOC for Daily and monthly only. |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCGPON | Applications/Tools | OPEN | NOT-FEASIBLE | Availability is available in UOC for Daily and monthly only. |  |  | #N/A |  | 1 | Open | Open
1766 | NOC113 | NOC | NA |  |  |  | GPON | OSS | Published Mandal Network uptime (like, total scope, litup count and availability according to the category) Daily |  | Critical | COMPLETED |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCGPON | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1767 | NOC114 | NOC | NA |  |  |  | GPON | OSS | Published Mandal Network uptime (like, total scope, litup count and availability according to the category) Weekly |  | Critical | OPEN |  | HPSM | Incident Management |  | Additional Scope (Total scope value is not possible to display in HPSM) |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCGPON | Applications/Tools | OPEN | NOT-FEASIBLE | 0 |  |  | #N/A |  | 1 | Open | Open
1768 | NOC115 | NOC | NA |  |  |  | GPON | OSS | Published Mandal Network uptime (like, total scope, litup count and availability according to the category) Monthly |  | Critical | COMPLETED |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCGPON | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1769 | NOC116 | NOC | NA |  |  |  | GPON | OSS | Published Mandal Network uptime (like, total scope, litup count and availability according to the category) (Selective from and to dates) |  | Critical | COMPLETED |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCGPON | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1770 | NOC117 | NOC | NA |  |  |  | GPON | OSS | Publishing Package wise and district wise Mandal Network uptime and Mandal TT resolution MTTR dashboard Daily |  | Critical | COMPLETED |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCGPON | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1771 | NOC118 | NOC | NA |  |  |  | GPON | OSS | Publishing Package wise and district wise Mandal Network uptime and Mandal TT resolution MTTR dashboard Weekly |  | Critical | COMPLETED |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCGPON | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1772 | NOC119 | NOC | NA |  |  |  | GPON | OSS | Publishing Package wise and district wise Mandal Network uptime and Mandal TT resolution MTTR dashboard Monthly |  | Critical | COMPLETED |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCGPON | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1773 | NOC12 | NOC | NA |  | OSS | OSS | OSS | DC | DC Passive infra uptime & SLA (Selective from and to dates) |  | Critical |  |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCOSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  | #N/A |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1774 | NOC120 | NOC | NA |  |  |  | GPON | OSS | Publishing Package wise and district wise Mandal Network uptime and Mandal TT resolution MTTR dashboard (Selective from and to dates) |  | Critical | OPEN |  | HPSM | Incident Management |  | Uptime and MMTR are two separate reports. |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCGPON | Applications/Tools | OPEN | WIP | 0 |  |  | #N/A |  | 1 | Open | Open
1775 | NOC121 | NOC | NA |  | OSS | OSS | All Domain | OSS | Based on DFR, prepare and publishing domain wise Ticketing dashboard Hourly |  | Critical | COMPLETED |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCAll Domain | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1776 | NOC122 | NOC | NA |  | OSS | OSS | All Domain | OSS | Based on DFR, prepare and publishing domain wise Ticketing dashboard Daily |  | Critical | COMPLETED |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCAll Domain | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1777 | NOC123 | NOC | NA |  | OSS | OSS | All Domain | OSS | Based on DFR, prepare and publishing domain wise Ticketing dashboard Weekly |  | Critical | COMPLETED |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCAll Domain | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1778 | NOC124 | NOC | NA |  | OSS | OSS | All Domain | OSS | Based on DFR, prepare and publishing domain wise Ticketing dashboard Monthly |  | Critical | COMPLETED |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCAll Domain | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1779 | NOC125 | NOC | NA |  | OSS | OSS | All Domain | OSS | Based on DFR, prepare and publishing domain wise Ticketing dashboard (Selective from and to dates) |  | Critical | COMPLETED |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCAll Domain | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1780 | NOC126 | NOC | NA |  | OSS | OSS | All Domain | OSS | Publishing of total field network devices dashboard Daily |  | Critical | COMPLETED |  | OSS Dashboards | UTM |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCAll Domain | Applications/Tools | OPEN | COMPLETED | Power BI DB - Device status will be live in the dashboard |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1781 | NOC127 | NOC | NA |  | OSS | OSS | All Domain | OSS | Publishing of total field network devices dashboard Weekly |  | Critical | NOT_FEASIBLE |  | OSS Dashboards | UTM |  |  |  |  | Suresh Pawar |  | Open | Not Feasible | [9 empty] | NOCAll Domain | Applications/Tools | #N/A | NOT-FEASIBLE | 0 |  |  | #N/A |  | 1 | Open | Open
1782 | NOC128 | NOC | NA |  | OSS | OSS | All Domain | OSS | Publishing of total field network devices dashboard Monthly |  | Critical | COMPLETED |  | OSS Dashboards | UTM |  | Device status will be live in the dashboard |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCAll Domain | Applications/Tools | OPEN | COMPLETED | Device status will be live in the dashboard |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1783 | NOC129 | NOC | NA |  | OSS | OSS | All Domain | OSS | Publishing of total field network devices dashboard (Selective from and to dates) |  | Critical | NOT_FEASIBLE |  | OSS Dashboards | UTM |  |  |  |  | Suresh Pawar |  | Open | Not Feasible | [9 empty] | NOCAll Domain | Applications/Tools | #N/A | NOT-FEASIBLE | 0 |  |  | #N/A |  | 1 | Open | Open
1784 | NOC13 | NOC | NA |  | OSS | OSS | OSS | DC | DC Network link uptime & SLA Daily |  | Critical |  |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCOSS | Applications/Tools | OPEN | OPEN | 0 |  |  | #N/A |  | 1 | Open | Open
1785 | NOC130 | NOC | NA |  | OSS | OSS | OSS | Field Passive Infra | Preparion and publishing Field Passive Infra Devices Uptime dashboard (Zone,Mandal,GP wise) Daily |  | Critical | COMPLETED |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCOSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1786 | NOC131 | NOC | NA |  | OSS | OSS | OSS | Field Passive Infra | Preparion and publishing Field Passive Infra Devices Uptime dashboard (Zone,Mandal,GP wise) Weekly |  | Critical | NOT_FEASIBLE |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  | Open | Not Feasible | [9 empty] | NOCOSS | Applications/Tools | #N/A | NOT-FEASIBLE | 0 |  |  | #N/A |  | 1 | Open | Open
1787 | NOC132 | NOC | NA |  | OSS | OSS | OSS | Field Passive Infra | Preparion and publishing Field Passive Infra Devices Uptime dashboard (Zone,Mandal,GP wise) Monthly |  | Critical | COMPLETED |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCOSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1788 | NOC133 | NOC | NA |  | OSS | OSS | OSS | Field Passive Infra | Preparion and publishing Field Passive Infra Devices Uptime dashboard (Zone,Mandal,GP wise) (Selective from and to dates) |  | Critical | COMPLETED |  | NNMI | NPS |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCOSS | Applications/Tools | OPEN | COMPLETED | available-weekly in NPS not in UOC |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1789 | NOC134 | NOC | NA |  | OSS | OSS | OSS | Planned Events | Publishing Planned Events dashboard of all the packages(like , PE applied,Success,cancelation etc) Daily |  | Critical | COMPLETED |  | NNMI | NPS |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCOSS | Applications/Tools | OPEN | COMPLETED | there is no dashboard |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1790 | NOC135 | NOC | NA |  | OSS | OSS | OSS | Planned Events | Publishing Planned Events dashboard of all the packages(like , PE applied,Success,cancelation etc) Weekly |  | Critical | COMPLETED |  | NNMI | NPS |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCOSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1791 | NOC136 | NOC | NA |  | OSS | OSS | OSS | Planned Events | Publishing Planned Events dashboard of all the packages(like , PE applied,Success,cancelation etc) Monthly |  | Critical | COMPLETED |  | NNMI | NPS |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCOSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1792 | NOC137 | NOC | NA |  | OSS | OSS | OSS | Planned Events | Publishing Planned Events dashboard of all the packages(like , PE applied,Success,cancelation etc) (Selective from and to dates) |  | Critical | COMPLETED |  | NNMI | NPS |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCOSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1793 | NOC138 | NOC | NA |  | OSS | OSS | OSS | DC IT Active Infra | Preparation and publishing of all DC IT devices availability dashboard Daily |  | NON-Critical |  |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCOSS | Applications/Tools | OPEN | OPEN | 0 |  |  | #N/A |  | 1 | Open | Open
1794 | NOC139 | NOC | NA |  | OSS | OSS | OSS | DC IT Active Infra | Preparation and publishing of all DC IT devices availability dashboard Weekly |  | NON-Critical |  |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCOSS | Applications/Tools | OPEN | OPEN | 0 |  |  | #N/A |  | 1 | Open | Open
1795 | NOC14 | NOC | NA |  | OSS | OSS | OSS | DC | DC Network link uptime & SLA Weekly |  | Critical |  |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCOSS | Applications/Tools | OPEN | OPEN | 0 |  |  | #N/A |  | 1 | Open | Open
1796 | NOC140 | NOC | NA |  | OSS | OSS | OSS | DC IT Active Infra | Preparation and publishing of all DC IT devices availability dashboard Monthly |  | NON-Critical |  |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCOSS | Applications/Tools | OPEN | OPEN | 0 |  |  | #N/A |  | 1 | Open | Open
1797 | NOC141 | NOC | NA |  | OSS | OSS | OSS | DC IT Active Infra | Preparation and publishing of all DC IT devices availability dashboard (Selective from and to dates) |  | NON-Critical |  |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCOSS | Applications/Tools | OPEN | OPEN | 0 |  |  | #N/A |  | 1 | Open | Open
1798 | NOC142 | NOC | NA |  |  |  | DC Passive Infra | OSS | Preparation and publishing of all DC Non IT devices availability dashboard Daily |  | NON-Critical |  |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCDC Passive Infra | Applications/Tools | OPEN | OPEN | 0 |  |  | #N/A |  | 1 | Open | Open
1799 | NOC143 | NOC | NA |  |  |  | DC Passive Infra | OSS | Preparation and publishing of all DC Non IT devices availability dashboard Weekly |  | NON-Critical |  |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCDC Passive Infra | Applications/Tools | OPEN | OPEN | 0 |  |  | #N/A |  | 1 | Open | Open
1800 | NOC144 | NOC | NA |  |  |  | DC Passive Infra | OSS | Preparation and publishing of all DC Non IT devices availability dashboard Monthly |  | NON-Critical |  |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCDC Passive Infra | Applications/Tools | OPEN | OPEN | 0 |  |  | #N/A |  | 1 | Open | Open
1801 | NOC145 | NOC | NA |  |  |  | DC Passive Infra | OSS | Preparation and publishing of all DC Non IT devices availability dashboard (Selective from and to dates) |  | NON-Critical |  |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCDC Passive Infra | Applications/Tools | OPEN | OPEN | 0 |  |  | #N/A |  | 1 | Open | Open
1802 | NOC146 | NOC | NA |  | OSS | OSS | OSS | OSS | Preparation and publishing of all application availability dashboard Daily |  | Critical | COMPLETED |  | OSS Dashboards | UOC |  | 09-09-2025: Sitescope based application URL monitoring |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCOSS | Applications/Tools | OPEN | COMPLETED | 09-09-2025: Sitescope based application URL monitoring |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1803 | NOC147 | NOC | NA |  | OSS | OSS | OSS | OSS | Preparation and publishing of all application availability dashboard Weekly |  | Critical | COMPLETED |  | OSS Dashboards | UOC |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCOSS | Applications/Tools | OPEN | COMPLETED | sitescope |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1804 | NOC148 | NOC | NA |  | OSS | OSS | OSS | OSS | Preparation and publishing of all application availability dashboard Monthly |  | Critical | COMPLETED |  | OSS Dashboards | UOC |  | 09-09-2025: Sitescope based application URL monitoring |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCOSS | Applications/Tools | OPEN | COMPLETED | 09-09-2025: Sitescope based application URL monitoring |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1805 | NOC149 | NOC | NA |  | OSS | OSS | OSS | OSS | Preparation and publishing of all application availability dashboard (Selective from and to dates) |  | Critical | COMPLETED |  | OSS Dashboards | UOC |  | 09-09-2025: Sitescope based application URL availability monitoring |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCOSS | Applications/Tools | OPEN | COMPLETED | 09-09-2025: Sitescope based application URL availability monitoring |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1806 | NOC15 | NOC | NA |  | OSS | OSS | OSS | DC | DC Network link uptime & SLA Monthly |  | Critical |  |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCOSS | Applications/Tools | OPEN | OPEN | 0 |  |  | #N/A |  | 1 | Open | Open
1807 | NOC150 | NOC | NA |  | OSS | OSS | OSS | OSS | Service assurance & Dashboards |  | Critical |  |  | OSS Dashboards | HPE Telco Unified OSS Console |  | Power Bi |  |  | Suresh Pawar |  | Open | WIP | [9 empty] | NOCOSS | Applications/Tools | OPEN | OPEN | 0 |  |  | #N/A |  | 1 | Open | Open
1808 | NOC151 | NOC | NA |  | OSS | OSS | OSS | OSS | Network Service Assurance Dashboards |  | Critical |  |  | OSS Dashboards | HPE Telco Unified OSS Console |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCOSS | Applications/Tools | OPEN | COMPLETED | dashboard is not there |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1809 | NOC152 | NOC | NA |  | OSS | OSS | OSS | OSS | Business Service Assurance Dashboards |  | Critical |  |  | OSS Dashboards | HPE Telco Unified OSS Console |  |  |  |  | Suresh Pawar |  | Open | WIP | [9 empty] | NOCOSS | Applications/Tools | OPEN | OPEN | 0 |  |  | #N/A |  | 1 | Open | Open
1810 | NOC153 | NOC | NA |  | OSS | OSS | OSS | OSS | Customer Service Dashboards |  | Critical |  |  | OSS Dashboards | HPE Telco Unified OSS Console |  | It will be available in BSS |  |  | Suresh Pawar |  | Open | WIP | [9 empty] | NOCOSS | Applications/Tools | OPEN | OPEN | 0 |  |  | #N/A |  | 1 | Open | Open
1811 | NOC154 | NOC | NA |  | OSS | OSS | OSS | OSS | Security Assurance Dashboard |  | Critical |  |  | OSS Dashboards | HPE Telco Unified OSS Console |  | It will be available in BSS |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCOSS | Applications/Tools | OPEN | COMPLETED | MTTR Reports for all domain including customer tickets |  |  | #N/A |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1812 | NOC155 | NOC | NA |  | OSS | OSS | OSS | OSS | Service Inventory |  | Critical |  |  | OSS Dashboards | HPE Telco Unified OSS Console |  | Inhouse solution |  |  | Suresh Pawar |  | Open | WIP | [9 empty] | NOCOSS | Applications/Tools | OPEN | OPEN | 0 |  |  | #N/A |  | 1 | Open | Open
1813 | NOC156 | NOC | NA |  | OSS | OSS | OSS | OSS | Service Monitoring |  | Critical |  |  | OSS Dashboards | HPE Telco Unified OSS Console |  |  |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCOSS | Applications/Tools | OPEN | OPEN | 0 |  |  | #N/A |  | 1 | Open | Open
1814 | NOC157 | NOC | NA |  | OSS | OSS | New BSS | OSS | OSS Intigration for POC Locations LCO,RMSO & MSO |  | Critical | OPEN |  | HPSM | Incident Management |  | Aditional Scope for OT/HPE |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCNew BSS | #N/A | OPEN | Not Relevant to OSS | 0 |  |  | #N/A |  | 1 | Open | Open
1815 | NOC158 | NOC | NA |  | OSS | OSS | New BSS | OSS | OSS Intigration for Live LCO , RMSO & MSO |  | Critical | OPEN |  | HPSM | Incident Management |  | Aditional Scope for OT/HPE |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCNew BSS | #N/A | OPEN | Not Relevant to OSS | 0 |  |  | #N/A |  | 1 | Open | Open
1816 | NOC159 | NOC | NA |  | OSS | OSS | OSS | OSS | Video customer inventory , Internet customer inventory , Bandwidth allocation inventory count etc., |  | Critical | OPEN |  | HPSM | Incident Management |  | Aditional Scope for OT/HPE |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCOSS | Applications/Tools | OPEN | OPEN | 0 |  |  | #N/A |  | 1 | Open | Open
1817 | NOC16 | NOC | NA |  | OSS | OSS | OSS | DC | DC Network link uptime & SLA (Selective from and to dates) |  | Critical |  |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCOSS | Applications/Tools | OPEN | OPEN | 0 |  |  | #N/A |  | 1 | Open | Open
1818 | NOC160 | NOC | NA |  |  |  | DC Passive Infra | OSS | Preparation and publishing of all DC passive infra(Internal, OEM) PM dashboard Daily |  | NON-Critical |  |  | OSS Dashboards | UOC |  |  |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCDC Passive Infra | Applications/Tools | OPEN | OPEN | 0 |  |  | #N/A |  | 1 | Open | Open
1819 | NOC161 | NOC | NA |  |  |  | DC Passive Infra | OSS | Preparation and publishing of all DC passive infra(Internal, OEM) PM dashboard Weekly |  | NON-Critical |  |  | OSS Dashboards | UOC |  |  |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCDC Passive Infra | Applications/Tools | OPEN | OPEN | 0 |  |  | #N/A |  | 1 | Open | Open
1820 | NOC162 | NOC | NA |  |  |  | DC Passive Infra | OSS | Preparation and publishing of all DC passive infra(Internal, OEM) PM dashboard Monthly |  | NON-Critical |  |  | OSS Dashboards | UOC |  |  |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCDC Passive Infra | Applications/Tools | OPEN | OPEN | 0 |  |  | #N/A |  | 1 | Open | Open
1821 | NOC163 | NOC | NA |  |  |  | DC Passive Infra | OSS | Preparation and publishing of all DC passive infra(Internal, OEM) PM dashboard (Selective from and to dates) |  | NON-Critical |  |  | OSS Dashboards | UOC |  |  |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCDC Passive Infra | Applications/Tools | OPEN | OPEN | 0 |  |  | #N/A |  | 1 | Open | Open
1822 | NOC164 | NOC | NA |  | OSS | OSS | OSS | NOC | Preparation and publishing of all devices, application, software AMC dashboard Daily |  | Critical |  |  | OSS Dashboards | Asset Manager |  | Report is available in Asset manager |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCOSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1823 | NOC165 | NOC | NA |  | OSS | OSS | OSS | NOC | Preparation and publishing of all devices, application, software AMC dashboard Weekly |  | Critical |  |  | OSS Dashboards | Asset Manager |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCOSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  | #N/A |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1824 | NOC166 | NOC | NA |  | OSS | OSS | OSS | NOC | Preparation and publishing of all devices, application, software AMC dashboard Monthly |  | Critical |  |  | OSS Dashboards | Asset Manager |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCOSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  | #N/A |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1825 | NOC167 | NOC | NA |  | OSS | OSS | OSS | NOC | Preparation and publishing of all devices, application, software AMC dashboard (Selective from and to dates) |  | Critical |  |  | OSS Dashboards | Asset Manager |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCOSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  | #N/A |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1826 | NOC168 | NOC | NA |  | OSS | OSS | OSS | NOC | Publishing of all major events in Tnoc dashboard Daily |  | Critical |  |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCOSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  | #N/A |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1827 | NOC169 | NOC | NA |  | OSS | OSS | OSS | NOC | Publishing of all major events in Tnoc dashboard Weekly |  | Critical |  |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCOSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  | #N/A |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1828 | NOC17 | NOC | NA |  |  |  | BSS | Service Provisioning | configure of GI services and tracking and publishing data Daily |  | Critical | OPEN |  | BSS | CRM |  | It will be available in NSO and BSS |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1829 | NOC170 | NOC | NA |  | OSS | OSS | OSS | NOC | Publishing of all major events in Tnoc dashboard Monthly |  | Critical |  |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCOSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  | #N/A |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1830 | NOC171 | NOC | NA |  | OSS | OSS | OSS | NOC | Publishing of all major events in Tnoc dashboard (Selective from and to dates) |  | Critical |  |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCOSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  | #N/A |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1831 | NOC172 | NOC | NA |  | OSS | OSS | OSS | BBNL Reports | Publishing of BBNL dashboard Daily |  | Critical | COMPLETED |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCOSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1832 | NOC173 | NOC | NA |  | OSS | OSS | OSS | BBNL Reports | Publishing of BBNL dashboard Weekly |  | Critical | NOT_FEASIBLE |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  | Open | Not Feasible | [9 empty] | NOCOSS | Applications/Tools | #N/A | Not Required to BBNL | 11-Oct-25: BBNL do not ask weekly hence it is not delivered |  |  | #N/A |  | 1 | Open | Open
1833 | NOC174 | NOC | NA |  | OSS | OSS | OSS | BBNL Reports | Publishing of BBNL dashboard Monthly |  | Critical | COMPLETED |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCOSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1834 | NOC175 | NOC | NA |  | OSS | OSS | OSS | BBNL Reports | Publishing of BBNL dashboard (Selective from and to dates) |  | Critical | NOT_FEASIBLE |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  | Open | Not Feasible | [9 empty] | NOCOSS | Applications/Tools | #N/A | Not Required to BBNL | 11-Oct-25: BBNL do not ask Selective from and to dates hence it is not delivered |  |  | #N/A |  | 1 | Open | Open
1835 | NOC176 | NOC | NA |  | OSS | OSS | OSS | Field Passive Infra | Publishing of Field Passive infra total devices dashboard Daily |  | Critical | COMPLETED |  | NNMI | NNMI |  | 09-09-2025: Inventory Dashboard visible for live data which is refreshing 6 times a day. |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCOSS | Applications/Tools | OPEN | COMPLETED | 09-09-2025: Inventory Dashboard visible for live data which is refreshing 6 times a day. |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1836 | NOC177 | NOC | NA |  | OSS | OSS | OSS | Field Passive Infra | Publishing of Field Passive infra total devices dashboard Weekly |  | Critical | NOT_FEASIBLE |  | NNMI | NNMI |  |  |  |  | Suresh Pawar |  | Open | Not Feasible | [9 empty] | NOCOSS | Applications/Tools | #N/A | NOT-FEASIBLE | 0 |  |  | #N/A |  | 1 | Open | Open
1837 | NOC178 | NOC | NA |  | OSS | OSS | OSS | Field Passive Infra | Publishing of Field Passive infra total devices dashboard Monthly |  | Critical | COMPLETED |  | NNMI | NNMI |  | Live report is available in UOC |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCOSS | Applications/Tools | OPEN | COMPLETED | Live report is available in UOC |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1838 | NOC179 | NOC | NA |  | OSS | OSS | OSS | Field Passive Infra | Publishing of Field Passive infra total devices dashboard (Selective from and to dates) |  | Critical | COMPLETED |  | NNMI | NNMI |  | Live report is available in UOC |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCOSS | Applications/Tools | OPEN | COMPLETED | Live report is available in UOC |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1839 | NOC18 | NOC | NA |  |  |  | BSS | Service Provisioning | configure of GI services and tracking and publishing data Weekly |  | Critical | OPEN |  | BSS | CRM |  | It will be available in NSO and BSS |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1840 | NOC180 | NOC | NA |  |  |  | DWDM | OSS | Published Zonal Network uptime (like, total scope, litup count and availability according to the category) Daily |  | Critical | COMPLETED |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCDWDM | Applications/Tools | OPEN | CLOSURE REVIEW PENDING | 0 |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1841 | NOC181 | NOC | NA |  |  |  | DWDM | OSS | Published Zonal Network uptime (like, total scope, litup count and availability according to the category) Weekly |  | Critical | OPEN |  | HPSM | Incident Management |  | Uptime and MMTR are two separate reports. |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCDWDM | Applications/Tools | OPEN | OPEN | 0 |  |  | #N/A |  | 1 | Open | Open
1842 | NOC182 | NOC | NA |  |  |  | DWDM | OSS | Published Zonal Network uptime (like, total scope, litup count and availability according to the category) Monthly |  | Critical | COMPLETED |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCDWDM | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1843 | NOC183 | NOC | NA |  |  |  | DWDM | OSS | Published Zonal Network uptime (like, total scope, litup count and availability according to the category) (Selective from and to dates) |  | Critical | COMPLETED |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCDWDM | Applications/Tools | OPEN | CLOSURE REVIEW PENDING | 0 |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1844 | NOC184 | NOC | NA |  |  |  | DWDM | OSS | Publishing Package wise , district wise and node wise (like DWDM,OADM) Zonal Network uptime and Mandal TT resolution MTTR dashboard Daily |  | Critical | COMPLETED |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCDWDM | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1845 | NOC185 | NOC | NA |  |  |  | DWDM | OSS | Publishing Package wise , district wise and node wise (like DWDM,OADM) Zonal Network uptime and Mandal TT resolution MTTR dashboard Weekly |  | Critical | COMPLETED |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCDWDM | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1846 | NOC186 | NOC | NA |  |  |  | DWDM | OSS | Publishing Package wise , district wise and node wise (like DWDM,OADM) Zonal Network uptime and Mandal TT resolution MTTR dashboard Monthly |  | Critical | COMPLETED |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCDWDM | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1847 | NOC187 | NOC | NA |  |  |  | DWDM | OSS | Publishing Package wise , district wise and node wise (like DWDM,OADM) Zonal Network uptime and Mandal TT resolution MTTR dashboard (Selective from and to dates) |  | Critical | OPEN |  | HPSM | Incident Management |  | Uptime and MMTR are two separate reports. |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCDWDM | Applications/Tools | OPEN | WIP | 0 |  |  | #N/A |  | 1 | Open | Open
1848 | NOC188 | NOC | NA |  |  |  | DWDM | OSS | Preparation and publishing of Zonal link summary , uptime and MTTR dashboard Daily |  | Critical | COMPLETED |  | HPSM | Incident Management |  | 11-09-2025: Uptime/Availability and MTTR is available for daily and monthly |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCDWDM | Applications/Tools | OPEN | COMPLETED | 11-09-2025: Uptime/Availability and MTTR is available for daily and monthly |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1849 | NOC189 | NOC | NA |  |  |  | DWDM | OSS | Preparation and publishing of Zonal link summary , uptime and MTTR dashboard Weekly |  | Critical | OPEN |  | HPSM | Incident Management |  | 11-09-2025: Uptime/Availability and MTTR is available for daily and monthly |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCDWDM | Applications/Tools | OPEN | WIP | 11-09-2025: Uptime/Availability and MTTR is available for daily and monthly |  |  | #N/A |  | 1 | Open | Open
1850 | NOC19 | NOC | NA |  |  |  | BSS | Service Provisioning | configure of GI services and tracking and publishing data Monthly |  | Critical | OPEN |  | BSS | CRM |  | It will be available in NSO and BSS |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1851 | NOC190 | NOC | NA |  |  |  | DWDM | OSS | Preparation and publishing of Zonal link summary , uptime and MTTR dashboard Monthly |  | Critical | OPEN |  | HPSM | Incident Management |  | 11-09-2025: Uptime/Availability and MTTR is available for daily and monthly |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCDWDM | Applications/Tools | OPEN | WIP | 11-09-2025: Uptime/Availability and MTTR is available for daily and monthly |  |  | #N/A |  | 1 | Open | Open
1852 | NOC191 | NOC | NA |  |  |  | DWDM | OSS | Preparation and publishing of Zonal link summary , uptime and MTTR dashboard (Selective from and to dates) |  | Critical | OPEN |  | HPSM | Incident Management |  | Uptime and MMTR are two separate reports. |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCDWDM | Applications/Tools | OPEN | WIP | 0 |  |  | #N/A |  | 1 | Open | Open
1853 | NOC192 | NOC | NA |  |  |  | DWDM | OSS | Preparing and publishing Zonal Link Fiber MTTR dashboard Daily |  | Critical | OPEN |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCDWDM | Applications/Tools | OPEN | WIP | 0 |  |  | #N/A |  | 1 | Open | Open
1854 | NOC193 | NOC | NA |  |  |  | DWDM | OSS | Preparing and publishing Zonal Link Fiber MTTR dashboard Weekly |  | Critical | OPEN |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCDWDM | Applications/Tools | OPEN | WIP | 0 |  |  | #N/A |  | 1 | Open | Open
1855 | NOC194 | NOC | NA |  |  |  | DWDM | OSS | Preparing and publishing Zonal Link Fiber MTTR dashboard Monthly |  | Critical | OPEN |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCDWDM | Applications/Tools | OPEN | WIP | 0 |  |  | #N/A |  | 1 | Open | Open
1856 | NOC195 | NOC | NA |  |  |  | DWDM | OSS | Preparing and publishing Zonal Link Fiber MTTR dashboard (Selective from and to dates) |  | Critical | OPEN |  | HPSM | Incident Management |  | Uptime and MMTR are two separate reports. |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCDWDM | Applications/Tools | OPEN | WIP | 0 |  |  | #N/A |  | 1 | Open | Open
1857 | NOC196 | NOC | NA |  |  |  | DWDM | OSS | Preparation and publishing dashboard for major events happened in network Hourly |  | Critical | OPEN |  | HPSM | Incident Management |  | Option is Availale in UOC (FAS) to check major alarms |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCDWDM | Applications/Tools | OPEN | COMPLETED | Option is Availale in UOC (FAS) to check major alarms |  |  | #N/A |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1858 | NOC197 | NOC | NA |  |  |  | DWDM | OSS | Preparation and publishing dashboard for major events happened in network Daily |  | Critical | COMPLETED |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCDWDM | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1859 | NOC198 | NOC | NA |  |  |  | DWDM | OSS | Preparation and publishing dashboard for major events happened in network Weekly |  | Critical | COMPLETED |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCDWDM | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1860 | NOC199 | NOC | NA |  |  |  | DWDM | OSS | Preparation and publishing dashboard for major events happened in network Monthly |  | Critical | COMPLETED |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCDWDM | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1861 | NOC2 | NOC | NA |  | OSS | OSS | OSS | DC | DC Active Infra uptime & SLA Weekly |  | Critical |  |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCOSS | Applications/Tools | OPEN | OPEN | 0 |  |  | #N/A |  | 1 | Open | Open
1862 | NOC20 | NOC | NA |  |  |  | BSS | Service Provisioning | configure of GI services and tracking and publishing data (Selective from and to dates) |  | Critical | OPEN |  | BSS | CRM |  | It will be available in NSO and BSS |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
1863 | NOC200 | NOC | NA |  |  |  | DWDM | OSS | Preparation and publishing dashboard for major events happened in network (Selective from and to dates) |  | Critical | COMPLETED |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCDWDM | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1864 | NOC201 | NOC | NA |  |  |  | DWDM | OSS | Preparation and publishing of all DC DWDM devices availability dashboard Daily |  | Critical | COMPLETED |  | OSS Dashboards | UOC |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCDWDM | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1865 | NOC202 | NOC | NA |  |  |  | DWDM | OSS | Preparation and publishing of all DC DWDM devices availability dashboard Weekly |  | Critical | NOT_FEASIBLE |  | OSS Dashboards | UOC |  |  |  |  | Suresh Pawar |  | Open | Not Feasible | [9 empty] | NOCDWDM | Applications/Tools | #N/A | NOT-FEASIBLE | 0 |  |  | #N/A |  | 1 | Open | Open
1866 | NOC203 | NOC | NA |  |  |  | DWDM | OSS | Preparation and publishing of all DC DWDM devices availability dashboard Monthly |  | Critical | COMPLETED |  | OSS Dashboards | UOC |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCDWDM | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1867 | NOC204 | NOC | NA |  |  |  | DWDM | OSS | Preparation and publishing of all DC DWDM devices availability dashboard (Selective from and to dates) |  | Critical | COMPLETED |  | OSS Dashboards | UOC |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCDWDM | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1868 | NOC205 | NOC | NA |  |  |  | DWDM | OSS | T-NOC Report : Zonal Links DWDM DFR Status as on 15-May-2025 Action to be taken on Top Most Priority Daily |  | Critical | COMPLETED |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCDWDM | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1869 | NOC206 | NOC | NA |  |  |  | DWDM | OSS | T-NOC Report : Zonal Links DWDM DFR Status as on 15-May-2025 Action to be taken on Top Most Priority Weekly |  | Critical | COMPLETED |  | HPSM | Incident Management |  | 09-09-2025: Ticket data based on Service Manager |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCDWDM | Applications/Tools | OPEN | COMPLETED | 09-09-2025: Ticket data based on Service Manager |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1870 | NOC207 | NOC | NA |  |  |  | DWDM | OSS | T-NOC Report : Zonal Links DWDM DFR Status as on 15-May-2025 Action to be taken on Top Most Priority Monthly |  | Critical | COMPLETED |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCDWDM | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1871 | NOC208 | NOC | NA |  |  |  | DWDM | OSS | T-NOC Report : Zonal Links DWDM DFR Status as on 15-May-2025 Action to be taken on Top Most Priority (Selective from and to dates) |  | Critical | COMPLETED |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCDWDM | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1872 | NOC209 | NOC | NA |  |  |  | DWDM | OSS | Zonal High Received Span Losses with TT for PKG_A Daily |  | Critical | OPEN |  | OSS Dashboards | UOC |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCDWDM | Applications/Tools | OPEN | COMPLETED | 0 |  |  | #N/A |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1873 | NOC21 | NOC | NA |  | OSS | OSS | OSS | Service Assurance | Monitoring,tracking of field details, Tracking of GI services form and prepare Service assurance dashboard Hourly |  | NON-Critical | OPEN |  | HPSM | Incident Management |  | OPEN-DEPENDENT |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCOSS | Applications/Tools | OPEN | OPEN-DEPENDENT | 0 |  |  | #N/A |  | 1 | Open | Open
1874 | NOC210 | NOC | NA |  |  |  | DWDM | OSS | Zonal High Received Span Losses with TT for PKG_A Weekly |  | Critical | OPEN |  | OSS Dashboards | UOC |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCDWDM | Applications/Tools | OPEN | COMPLETED | 0 |  |  | #N/A |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1875 | NOC211 | NOC | NA |  |  |  | DWDM | OSS | Zonal High Received Span Losses with TT for PKG_A Monthly |  | Critical | OPEN |  | OSS Dashboards | UOC |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCDWDM | Applications/Tools | OPEN | COMPLETED | 0 |  |  | #N/A |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1876 | NOC212 | NOC | NA |  |  |  | DWDM | OSS | Zonal High Received Span Losses with TT for PKG_A (Selective from and to dates) |  | Critical | OPEN |  | OSS Dashboards | UOC |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCDWDM | Applications/Tools | OPEN | COMPLETED | 0 |  |  | #N/A |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1877 | NOC213 | NOC | NA |  |  |  | DWDM | OSS | Zonal High Received Span Losses with TT for PKG_B Daily |  | Critical | OPEN |  | OSS Dashboards | UOC |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCDWDM | Applications/Tools | OPEN | COMPLETED | 0 |  |  | #N/A |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1878 | NOC214 | NOC | NA |  |  |  | DWDM | OSS | Zonal High Received Span Losses with TT for PKG_B Weekly |  | Critical | OPEN |  | OSS Dashboards | UOC |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCDWDM | Applications/Tools | OPEN | COMPLETED | 0 |  |  | #N/A |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1879 | NOC215 | NOC | NA |  |  |  | DWDM | OSS | Zonal High Received Span Losses with TT for PKG_B Monthly |  | Critical | OPEN |  | OSS Dashboards | UOC |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCDWDM | Applications/Tools | OPEN | COMPLETED | 0 |  |  | #N/A |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1880 | NOC216 | NOC | NA |  |  |  | DWDM | OSS | Zonal High Received Span Losses with TT for PKG_B (Selective from and to dates) |  | Critical | OPEN |  | OSS Dashboards | UOC |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCDWDM | Applications/Tools | OPEN | COMPLETED | 0 |  |  | #N/A |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1881 | NOC217 | NOC | NA |  |  |  | DWDM | OSS | Zonal High Received Span Losses with TT for PKG_C Daily |  | Critical | OPEN |  | OSS Dashboards | UOC |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCDWDM | Applications/Tools | OPEN | COMPLETED | 0 |  |  | #N/A |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1882 | NOC218 | NOC | NA |  |  |  | DWDM | OSS | Zonal High Received Span Losses with TT for PKG_C Weekly |  | Critical | OPEN |  | OSS Dashboards | UOC |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCDWDM | Applications/Tools | OPEN | COMPLETED | 0 |  |  | #N/A |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1883 | NOC219 | NOC | NA |  |  |  | DWDM | OSS | Zonal High Received Span Losses with TT for PKG_C Monthly |  | Critical | OPEN |  | OSS Dashboards | UOC |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCDWDM | Applications/Tools | OPEN | COMPLETED | 0 |  |  | #N/A |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1884 | NOC22 | NOC | NA |  | OSS | OSS | OSS | Service Assurance | Monitoring,tracking of field details, Tracking of GI services form and prepare Service assurance dashboard Daily |  | NON-Critical | OPEN |  | HPSM | Incident Management |  | OPEN-DEPENDENT |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCOSS | Applications/Tools | OPEN | OPEN-DEPENDENT | 0 |  |  | #N/A |  | 1 | Open | Open
1885 | NOC220 | NOC | NA |  |  |  | DWDM | OSS | Zonal High Received Span Losses with TT for PKG_C (Selective from and to dates) |  | Critical | OPEN |  | OSS Dashboards | UOC |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCDWDM | Applications/Tools | OPEN | COMPLETED | 0 |  |  | #N/A |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1886 | NOC221 | NOC | NA |  | OSS | OSS | OSS | GPON/IPMPLS | Monitoring and published of Dark Fiber and TSWAN KPI Daily |  | Critical | OPEN |  | HPSM | Incident Management |  | OPEN-DEPENDENT |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCOSS | Applications/Tools | OPEN | OPEN-DEPENDENT | 0 |  |  | #N/A |  | 1 | Open | Open
1887 | NOC222 | NOC | NA |  | OSS | OSS | OSS | GPON/IPMPLS | Monitoring and published of Dark Fiber and TSWAN KPI Weekly |  | Critical | OPEN |  | HPSM | Incident Management |  | OPEN-DEPENDENT |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCOSS | Applications/Tools | OPEN | OPEN-DEPENDENT | 0 |  |  | #N/A |  | 1 | Open | Open
1888 | NOC223 | NOC | NA |  | OSS | OSS | OSS | GPON/IPMPLS | Monitoring and published of Dark Fiber and TSWAN KPI Monthly |  | Critical | OPEN |  | HPSM | Incident Management |  | OPEN-DEPENDENT |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCOSS | Applications/Tools | OPEN | OPEN-DEPENDENT | 0 |  |  | #N/A |  | 1 | Open | Open
1889 | NOC224 | NOC | NA |  | OSS | OSS | OSS | GPON/IPMPLS | Monitoring and published of Dark Fiber and TSWAN KPI (Selective from and to dates) |  | Critical | OPEN |  | HPSM | Incident Management |  | OPEN-DEPENDENT |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCOSS | Applications/Tools | OPEN | OPEN-DEPENDENT | 0 |  |  | #N/A |  | 1 | Open | Open
1890 | NOC225 | NOC | NA |  |  |  | IP/MPLS | OSS | Preparation and publishing of GP to GP and GP to Mandal link summary , uptime and MTTR dashboard Hourly |  | Critical | OPEN |  | HPSM | Incident Management |  | 11-09-2025: Uptime/Availability and MTTR is available for daily and monthly |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCIP/MPLS | Applications/Tools | OPEN | WIP | 11-09-2025: Uptime/Availability and MTTR is available for daily and monthly |  |  | #N/A |  | 1 | Open | Open
1891 | NOC226 | NOC | NA |  |  |  | IP/MPLS | OSS | Preparation and publishing of GP to GP and GP to Mandal link summary , uptime and MTTR dashboard Daily |  | Critical | COMPLETED |  | HPSM | Incident Management |  | 11-09-2025: Uptime/Availability and MTTR is available for daily and monthly |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCIP/MPLS | Applications/Tools | OPEN | COMPLETED | 11-09-2025: Uptime/Availability and MTTR is available for daily and monthly |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1892 | NOC227 | NOC | NA |  |  |  | IP/MPLS | OSS | Preparation and publishing of GP to GP and GP to Mandal link summary , uptime and MTTR dashboard Weekly |  | Critical | COMPLETED |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCIP/MPLS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1893 | NOC228 | NOC | NA |  |  |  | IP/MPLS | OSS | Preparation and publishing of GP to GP and GP to Mandal link summary , uptime and MTTR dashboard Monthly |  | Critical | OPEN |  | HPSM | Incident Management |  | 11-09-2025: Uptime/Availability and MTTR is available for daily and monthly |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCIP/MPLS | Applications/Tools | OPEN | WIP | 11-09-2025: Uptime/Availability and MTTR is available for daily and monthly |  |  | #N/A |  | 1 | Open | Open
1894 | NOC229 | NOC | NA |  |  |  | IP/MPLS | OSS | Preparation and publishing of GP to GP and GP to Mandal link summary , uptime and MTTR dashboard (Selective from and to dates) |  | Critical | OPEN |  | HPSM | Incident Management |  | 11-09-2025: Uptime/Availability and MTTR is available for daily and monthly |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCIP/MPLS | Applications/Tools | OPEN | WIP | 11-09-2025: Uptime/Availability and MTTR is available for daily and monthly |  |  | #N/A |  | 1 | Open | Open
1895 | NOC23 | NOC | NA |  | OSS | OSS | OSS | Service Assurance | Monitoring,tracking of field details, Tracking of GI services form and prepare Service assurance dashboard Weekly |  | NON-Critical | OPEN |  | HPSM | Incident Management |  | OPEN-DEPENDENT |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCOSS | Applications/Tools | OPEN | OPEN-DEPENDENT | 0 |  |  | #N/A |  | 1 | Open | Open
1896 | NOC230 | NOC | NA |  |  |  | IP/MPLS | OSS | Preparation and publishing of Mandal to Mandal and Mandal to Zonal link summary , uptime and MTTR dashboard Daily |  | Critical | COMPLETED |  | HPSM | Incident Management |  | 11-09-2025: Uptime/Availability and MTTR is available for daily and monthly |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCIP/MPLS | Applications/Tools | OPEN | COMPLETED | 11-09-2025: Uptime/Availability and MTTR is available for daily and monthly |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1897 | NOC231 | NOC | NA |  |  |  | IP/MPLS | OSS | Preparation and publishing of Mandal to Mandal and Mandal to Zonal link summary , uptime and MTTR dashboard Weekly |  | Critical | OPEN |  | HPSM | Incident Management |  | 11-09-2025: Uptime/Availability and MTTR is available for daily and monthly |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCIP/MPLS | Applications/Tools | OPEN | WIP | 11-09-2025: Uptime/Availability and MTTR is available for daily and monthly |  |  | #N/A |  | 1 | Open | Open
1898 | NOC232 | NOC | NA |  |  |  | IP/MPLS | OSS | Preparation and publishing of Mandal to Mandal and Mandal to Zonal link summary , uptime and MTTR dashboard Monthly |  | Critical | OPEN |  | HPSM | Incident Management |  | 11-09-2025: Uptime/Availability and MTTR is available for daily and monthly |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCIP/MPLS | Applications/Tools | OPEN | WIP | 11-09-2025: Uptime/Availability and MTTR is available for daily and monthly |  |  | #N/A |  | 1 | Open | Open
1899 | NOC233 | NOC | NA |  |  |  | IP/MPLS | OSS | Preparation and publishing of Mandal to Mandal and Mandal to Zonal link summary , uptime and MTTR dashboard (Selective from and to dates) |  | Critical | OPEN |  | HPSM | Incident Management |  | 11-09-2025: Uptime/Availability and MTTR is available for daily and monthly |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCIP/MPLS | Applications/Tools | OPEN | WIP | 11-09-2025: Uptime/Availability and MTTR is available for daily and monthly |  |  | #N/A |  | 1 | Open | Open
1900 | NOC234 | NOC | NA |  |  |  | IP/MPLS | OSS | High priority link like Tfiber ring monitoring and publishing KPI Hourly |  | Critical | OPEN |  | HPSM | Incident Management |  | Manually group needs to form in the NNMi and from that group it can be monitored. Venkatesh is giving KT to Operation team |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCIP/MPLS | Applications/Tools | OPEN | COMPLETED | Manually group needs to form in the NNMi and from that group it can be monitored. Venkatesh is giving KT to Operation team |  |  | #N/A |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1901 | NOC235 | NOC | NA |  |  |  | IP/MPLS | OSS | High priority link like Tfiber ring monitoring and publishing KPI Daily |  | Critical | COMPLETED |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCIP/MPLS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1902 | NOC236 | NOC | NA |  |  |  | IP/MPLS | OSS | High priority link like Tfiber ring monitoring and publishing KPI Weekly |  | Critical | OPEN |  | HPSM | Incident Management |  | Manually group needs to form in the NNMi and from that group it can be monitored. Venkatesh is giving KT to Operation team |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCIP/MPLS | Applications/Tools | OPEN | COMPLETED | Manually group needs to form in the NNMi and from that group it can be monitored. Venkatesh is giving KT to Operation team |  |  | #N/A |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1903 | NOC237 | NOC | NA |  |  |  | IP/MPLS | OSS | High priority link like Tfiber ring monitoring and publishing KPI Monthly |  | Critical | COMPLETED |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCIP/MPLS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1904 | NOC238 | NOC | NA |  |  |  | IP/MPLS | OSS | High priority link like Tfiber ring monitoring and publishing KPI (Selective from and to dates) |  | Critical | COMPLETED |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCIP/MPLS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1905 | NOC239 | NOC | NA |  |  |  | IP/MPLS | OSS | Enteprise Services Delivery ( Aitel Towers, Airtel LWEsite, pioneer etc ) Monitoring, preparation KPI like Service Up reports Hourly |  | Critical | OPEN |  | HPSM | Incident Management |  | OPEN-DEPENDENT |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCIP/MPLS | Applications/Tools | OPEN | OPEN-DEPENDENT | 0 |  |  | #N/A |  | 1 | Open | Open
1906 | NOC24 | NOC | NA |  | OSS | OSS | OSS | Service Assurance | Monitoring,tracking of field details, Tracking of GI services form and prepare Service assurance dashboard Monthly |  | NON-Critical | OPEN |  | HPSM | Incident Management |  | OPEN-DEPENDENT |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCOSS | Applications/Tools | OPEN | OPEN-DEPENDENT | 0 |  |  | #N/A |  | 1 | Open | Open
1907 | NOC240 | NOC | NA |  |  |  | IP/MPLS | OSS | Enteprise Services Delivery ( Aitel Towers, Airtel LWEsite, pioneer etc ) Monitoring, preparation KPI like Service Up reports Daily |  | Critical | OPEN |  | HPSM | Incident Management |  | OPEN-DEPENDENT |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCIP/MPLS | Applications/Tools | OPEN | OPEN-DEPENDENT | 0 |  |  | #N/A |  | 1 | Open | Open
1908 | NOC241 | NOC | NA |  |  |  | IP/MPLS | OSS | Enteprise Services Delivery ( Aitel Towers, Airtel LWEsite, pioneer etc ) Monitoring, preparation KPI like Service Up reports Weekly |  | Critical | OPEN |  | HPSM | Incident Management |  | OPEN-DEPENDENT |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCIP/MPLS | Applications/Tools | OPEN | OPEN-DEPENDENT | 0 |  |  | #N/A |  | 1 | Open | Open
1909 | NOC242 | NOC | NA |  |  |  | IP/MPLS | OSS | Enteprise Services Delivery ( Aitel Towers, Airtel LWEsite, pioneer etc ) Monitoring, preparation KPI like Service Up reports Monthly |  | Critical | OPEN |  | HPSM | Incident Management |  | OPEN-DEPENDENT |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCIP/MPLS | Applications/Tools | OPEN | OPEN-DEPENDENT | 0 |  |  | #N/A |  | 1 | Open | Open
1910 | NOC243 | NOC | NA |  |  |  | IP/MPLS | OSS | Enteprise Services Delivery ( Aitel Towers, Airtel LWEsite, pioneer etc ) Monitoring, preparation KPI like Service Up reports (Selective from and to dates) |  | Critical | OPEN |  | HPSM | Incident Management |  | OPEN-DEPENDENT |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCIP/MPLS | Applications/Tools | OPEN | OPEN-DEPENDENT | 0 |  |  | #N/A |  | 1 | Open | Open
1911 | NOC244 | NOC | NA |  |  |  | IP/MPLS | OSS | Preparation and publishing of Enterprise Customer Service KPIs like availability, packet drops, latency, jitter & bandwidth utilization Daily |  | Critical | COMPLETED |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCIP/MPLS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1912 | NOC245 | NOC | NA |  |  |  | IP/MPLS | OSS | Preparation and publishing of Enterprise Customer Service KPIs like availability, packet drops, latency, jitter & bandwidth utilization Weekly |  | Critical | COMPLETED |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCIP/MPLS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1913 | NOC246 | NOC | NA |  |  |  | IP/MPLS | OSS | Preparation and publishing of Enterprise Customer Service KPIs like availability, packet drops, latency, jitter & bandwidth utilization Monthly |  | Critical | COMPLETED |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCIP/MPLS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1914 | NOC247 | NOC | NA |  |  |  | IP/MPLS | OSS | Preparation and publishing of Enterprise Customer Service KPIs like availability, packet drops, latency, jitter & bandwidth utilization (Selective from and to dates) |  | Critical | COMPLETED |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCIP/MPLS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1915 | NOC248 | NOC | NA |  |  |  | IP/MPLS | OSS | Preparation and publishing of all DC MPLS Network devices availability dashboard Daily |  | Critical | COMPLETED |  | NNMI | NPS |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCIP/MPLS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1916 | NOC249 | NOC | NA |  |  |  | IP/MPLS | OSS | Preparation and publishing of all DC MPLS Network devices availability dashboard Weekly |  | Critical | NOT_FEASIBLE |  | NNMI | NPS |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCIP/MPLS | Applications/Tools | #N/A | COMPLETED | available- hourly & weekly in NPS |  |  | #N/A |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1917 | NOC25 | NOC | NA |  | OSS | OSS | OSS | Service Assurance | Monitoring,tracking of field details, Tracking of GI services form and prepare Service assurance dashboard(Selective from and to dates) |  | NON-Critical | OPEN |  | HPSM | Incident Management |  | OPEN-DEPENDENT |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCOSS | Applications/Tools | OPEN | OPEN-DEPENDENT | 0 |  |  | #N/A |  | 1 | Open | Open
1918 | NOC250 | NOC | NA |  |  |  | IP/MPLS | OSS | Preparation and publishing of all DC MPLS Network devices availability dashboard Monthly |  | Critical | COMPLETED |  | NNMI | NPS |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCIP/MPLS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1919 | NOC251 | NOC | NA |  |  |  | IP/MPLS | OSS | Preparation and publishing of all DC MPLS Network devices availability dashboard (Selective from and to dates) |  | Critical | COMPLETED |  | NNMI | NPS |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCIP/MPLS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1920 | NOC252 | NOC | NA |  |  |  | IP/MPLS | OSS | Prepartion and publishing of Core link availability and utilization dashboard Hourly |  | Critical | COMPLETED |  | HPSM | Incident Management |  | Link Group can be created in NNMi and monitor for only IPMPLS links |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCIP/MPLS | Applications/Tools | OPEN | COMPLETED | Link Group can be created in NNMi and monitor for only IPMPLS links |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1921 | NOC253 | NOC | NA |  |  |  | IP/MPLS | OSS | Prepartion and publishing of Core link availability and utilization dashboard Daily |  | Critical | COMPLETED |  | NNMI | NPS |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCIP/MPLS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1922 | NOC254 | NOC | NA |  |  |  | IP/MPLS | OSS | Prepartion and publishing of Core link availability and utilization dashboard Weekly |  | Critical | COMPLETED |  | NNMI | NPS |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCIP/MPLS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1923 | NOC255 | NOC | NA |  |  |  | IP/MPLS | OSS | Prepartion and publishing of Core link availability and utilization dashboard Monthly |  | Critical | COMPLETED |  | NNMI | NPS |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCIP/MPLS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1924 | NOC256 | NOC | NA |  |  |  | IP/MPLS | OSS | Prepartion and publishing of Core link availability and utilization dashboard (Selective from and to dates) |  | Critical | COMPLETED |  | NNMI | NPS |  | Link Group can be created in NNMi and monitor for only IPMPLS links |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCIP/MPLS | Applications/Tools | OPEN | COMPLETED | Link Group can be created in NNMi and monitor for only IPMPLS links |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1925 | NOC257 | NOC | NA |  |  |  | IP/MPLS | OSS | Package A Low RX Optical Power Levels in IPMPLS Network Daily |  | Critical | OPEN |  | NNMI | NNMI |  | 09-09-2025: Need confirmation from OT for "Low RX Optical Power Levels" KPI |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCIP/MPLS | Applications/Tools | OPEN | OPEN | 09-09-2025: Need confirmation from OT for "Low RX Optical Power Levels" KPI |  |  | #N/A |  | 1 | Open | Open
1926 | NOC258 | NOC | NA |  |  |  | IP/MPLS | OSS | Package A Low RX Optical Power Levels in IPMPLS Network Weekly |  | Critical | OPEN |  | NNMI | NNMI |  |  |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCIP/MPLS | Applications/Tools | OPEN | OPEN | 0 |  |  | #N/A |  | 1 | Open | Open
1927 | NOC259 | NOC | NA |  |  |  | IP/MPLS | OSS | Package A Low RX Optical Power Levels in IPMPLS Network Monthly |  | Critical | OPEN |  | NNMI | NNMI |  | 09-09-2025: Need confirmation from OT for "Low RX Optical Power Levels" KPI |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCIP/MPLS | Applications/Tools | OPEN | OPEN | 09-09-2025: Need confirmation from OT for "Low RX Optical Power Levels" KPI |  |  | #N/A |  | 1 | Open | Open
1928 | NOC26 | NOC | NA |  | OSS | OSS | OSS | Service Monitoring | Monitoring,tracking service details, Tracking of GI services uptime Service assurance dashboard Daily |  | Critical | OPEN |  | HPSM | Incident Management |  | OPEN-DEPENDENT |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCOSS | Applications/Tools | OPEN | OPEN-DEPENDENT | 0 |  |  | #N/A |  | 1 | Open | Open
1929 | NOC260 | NOC | NA |  |  |  | IP/MPLS | OSS | Package A Low RX Optical Power Levels in IPMPLS Network (Selective from and to dates) |  | Critical | OPEN |  | NNMI | NNMI |  | 09-09-2025: Need confirmation from OT for "Low RX Optical Power Levels" KPI |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCIP/MPLS | Applications/Tools | OPEN | OPEN | 09-09-2025: Need confirmation from OT for "Low RX Optical Power Levels" KPI |  |  | #N/A |  | 1 | Open | Open
1930 | NOC261 | NOC | NA |  |  |  | IP/MPLS | OSS | Package B Low RX Optical Power Levels in IPMPLS Network Daily |  | Critical | OPEN |  | NNMI | NNMI |  | 09-09-2025: Need confirmation from OT for "Low RX Optical Power Levels" KPI |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCIP/MPLS | Applications/Tools | OPEN | OPEN | 09-09-2025: Need confirmation from OT for "Low RX Optical Power Levels" KPI |  |  | #N/A |  | 1 | Open | Open
1931 | NOC262 | NOC | NA |  |  |  | IP/MPLS | OSS | Package B Low RX Optical Power Levels in IPMPLS Network Weekly |  | Critical | OPEN |  | NNMI | NNMI |  |  |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCIP/MPLS | Applications/Tools | OPEN | OPEN | 0 |  |  | #N/A |  | 1 | Open | Open
1932 | NOC263 | NOC | NA |  |  |  | IP/MPLS | OSS | Package B Low RX Optical Power Levels in IPMPLS Network Monthly |  | Critical | OPEN |  | NNMI | NNMI |  | 09-09-2025: Need confirmation from OT for "Low RX Optical Power Levels" KPI |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCIP/MPLS | Applications/Tools | OPEN | OPEN | 09-09-2025: Need confirmation from OT for "Low RX Optical Power Levels" KPI |  |  | #N/A |  | 1 | Open | Open
1933 | NOC264 | NOC | NA |  |  |  | IP/MPLS | OSS | Package B Low RX Optical Power Levels in IPMPLS Network (Selective from and to dates) |  | Critical | OPEN |  | NNMI | NNMI |  | 09-09-2025: Need confirmation from OT for "Low RX Optical Power Levels" KPI |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCIP/MPLS | Applications/Tools | OPEN | OPEN | 09-09-2025: Need confirmation from OT for "Low RX Optical Power Levels" KPI |  |  | #N/A |  | 1 | Open | Open
1934 | NOC265 | NOC | NA |  |  |  | IP/MPLS | OSS | Package C Low RX Optical Power Levels in IPMPLS Network Daily |  | Critical | OPEN |  | NNMI | NNMI |  | 09-09-2025: Need confirmation from OT for "Low RX Optical Power Levels" KPI |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCIP/MPLS | Applications/Tools | OPEN | OPEN | 09-09-2025: Need confirmation from OT for "Low RX Optical Power Levels" KPI |  |  | #N/A |  | 1 | Open | Open
1935 | NOC266 | NOC | NA |  |  |  | IP/MPLS | OSS | Package C Low RX Optical Power Levels in IPMPLS Network Weekly |  | Critical | OPEN |  | NNMI | NNMI |  |  |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCIP/MPLS | Applications/Tools | OPEN | OPEN | 0 |  |  | #N/A |  | 1 | Open | Open
1936 | NOC267 | NOC | NA |  |  |  | IP/MPLS | OSS | Package C Low RX Optical Power Levels in IPMPLS Network Monthly |  | Critical | OPEN |  | NNMI | NNMI |  | 09-09-2025: Need confirmation from OT for "Low RX Optical Power Levels" KPI |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCIP/MPLS | Applications/Tools | OPEN | OPEN | 09-09-2025: Need confirmation from OT for "Low RX Optical Power Levels" KPI |  |  | #N/A |  | 1 | Open | Open
1937 | NOC268 | NOC | NA |  |  |  | IP/MPLS | OSS | Package C Low RX Optical Power Levels in IPMPLS Network (Selective from and to dates) |  | Critical | OPEN |  | NNMI | NNMI |  | 09-09-2025: Need confirmation from OT for "Low RX Optical Power Levels" KPI |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCIP/MPLS | Applications/Tools | OPEN | OPEN | 09-09-2025: Need confirmation from OT for "Low RX Optical Power Levels" KPI |  |  | #N/A |  | 1 | Open | Open
1938 | NOC269 | NOC | NA |  |  |  | IP/MPLS | OSS | Mandal Link Down + GP Link Down DFR Daily |  | Critical | COMPLETED |  | HPSM | Incident Management |  | 09-09-2025: Need confirmation from OT for "Low RX Optical Power Levels" KPI |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCIP/MPLS | Applications/Tools | OPEN | COMPLETED | 09-09-2025: Need confirmation from OT for "Low RX Optical Power Levels" KPI |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1939 | NOC27 | NOC | NA |  | OSS | OSS | OSS | Service Monitoring | Monitoring,tracking service details, Tracking of GI services uptime Service assurance dashboard Weekly |  | Critical | OPEN |  | HPSM | Incident Management |  | OPEN-DEPENDENT |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCOSS | Applications/Tools | OPEN | OPEN-DEPENDENT | 0 |  |  | #N/A |  | 1 | Open | Open
1940 | NOC270 | NOC | NA |  |  |  | IP/MPLS | OSS | Mandal Link Down + GP Link Down DFR Weekly |  | Critical | COMPLETED |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCIP/MPLS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1941 | NOC271 | NOC | NA |  |  |  | IP/MPLS | OSS | Mandal Link Down + GP Link Down DFR Monthly |  | Critical | COMPLETED |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCIP/MPLS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1942 | NOC272 | NOC | NA |  |  |  | IP/MPLS | OSS | Mandal Link Down + GP Link Down DFR (Selective from and to dates) |  | Critical | COMPLETED |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCIP/MPLS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1943 | NOC273 | NOC | NA |  | OSS | OSS | All Domain | OSS | All Domain RMA Tracker //Daily Daily//Domain And package wise Filtering |  | Critical | COMPLETED |  | HPSM | Incident Management |  | Direct integration with OEM portal is not in scope, however manual ticket can be created in service manager using 'RMA_TAC' category and monitor the status and progress |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCAll Domain | Applications/Tools | OPEN | COMPLETED | Direct integration with OEM portal is not in scope, however manual ticket can be created in service manager using 'RMA_TAC' category and monitor the status and progress |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1944 | NOC274 | NOC | NA |  | OSS | OSS | All Domain | OSS | All Domain RMA Tracker //Daily Weekly Domain and package Wise Filtering |  | Critical | COMPLETED |  | HPSM | Incident Management |  | Direct integration with OEM portal is not in scope, however manual ticket can be created in service manager using 'RMA_TAC' category and monitor the status and progress |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCAll Domain | Applications/Tools | OPEN | COMPLETED | Direct integration with OEM portal is not in scope, however manual ticket can be created in service manager using 'RMA_TAC' category and monitor the status and progress |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1945 | NOC275 | NOC | NA |  | OSS | OSS | All Domain | OSS | All Domain RMA Tracker //Daily Monthly Domain and package Wise Filtering |  | Critical | COMPLETED |  | HPSM | Incident Management |  | Direct integration with OEM portal is not in scope, however manual ticket can be created in service manager using 'RMA_TAC' category and monitor the status and progress |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCAll Domain | Applications/Tools | OPEN | COMPLETED | Direct integration with OEM portal is not in scope, however manual ticket can be created in service manager using 'RMA_TAC' category and monitor the status and progress |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1946 | NOC276 | NOC | NA |  | OSS | OSS | All Domain | OSS | All OEM_TAC Cases Tracker Daily Domain and package Wise Filtering |  | Critical | COMPLETED |  | HPSM | Incident Management |  | Direct integration with OEM portal is not in scope, however manual ticket can be created in service manager using 'RMA_TAC' category and monitor the status and progress |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCAll Domain | Applications/Tools | OPEN | COMPLETED | Direct integration with OEM portal is not in scope, however manual ticket can be created in service manager using 'RMA_TAC' category and monitor the status and progress |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1947 | NOC277 | NOC | NA |  | OSS | OSS | All Domain | OSS | All OEM_TAC Cases Tracker Weekly Domain and package Wise Filtering |  | Critical | COMPLETED |  | HPSM | Incident Management |  | Direct integration with OEM portal is not in scope, however manual ticket can be created in service manager using 'RMA_TAC' category and monitor the status and progress |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCAll Domain | Applications/Tools | OPEN | COMPLETED | Direct integration with OEM portal is not in scope, however manual ticket can be created in service manager using 'RMA_TAC' category and monitor the status and progress |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1948 | NOC278 | NOC | NA |  | OSS | OSS | All Domain | OSS | All OEM_TAC Cases Tracker Monthly Domain and package Wise Filtering |  | Critical | COMPLETED |  | HPSM | Incident Management |  | Direct integration with OEM portal is not in scope, however manual ticket can be created in service manager using 'RMA_TAC' category and monitor the status and progress |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCAll Domain | Applications/Tools | OPEN | COMPLETED | Direct integration with OEM portal is not in scope, however manual ticket can be created in service manager using 'RMA_TAC' category and monitor the status and progress |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1949 | NOC279 | NOC | NA |  | OSS | OSS | All Domain | OSS | All OEM_TAC Cases Tracker (Selective from and to dates) Domain and package Wise Filtering |  | Critical | COMPLETED |  | HPSM | Incident Management |  | Direct integration with OEM portal is not in scope, however manual ticket can be created in service manager using 'RMA_TAC' category and monitor the status and progress |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCAll Domain | Applications/Tools | OPEN | COMPLETED | Direct integration with OEM portal is not in scope, however manual ticket can be created in service manager using 'RMA_TAC' category and monitor the status and progress |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1950 | NOC28 | NOC | NA |  | OSS | OSS | OSS | Service Monitoring | Monitoring,tracking service details, Tracking of GI services uptime Service assurance dashboard Monthly |  | Critical | OPEN |  | HPSM | Incident Management |  | OPEN-DEPENDENT |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCOSS | Applications/Tools | OPEN | OPEN-DEPENDENT | 0 |  |  | #N/A |  | 1 | Open | Open
1951 | NOC280 | NOC | NA |  | OSS | OSS | All Domain | OSS | All Sites Infra OPEN TTs details for HRT(High Temparature) Alarm Daily |  | Critical | COMPLETED |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCAll Domain | Applications/Tools | OPEN | COMPLETED | need to check |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1952 | NOC281 | NOC | NA |  | OSS | OSS | All Domain | OSS | All Sites Infra OPEN TTs details for HRT(High Temparature) Alarm Weekly |  | Critical | COMPLETED |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCAll Domain | Applications/Tools | OPEN | COMPLETED | need to check |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1953 | NOC282 | NOC | NA |  | OSS | OSS | All Domain | OSS | All Sites Infra OPEN TTs details for HRT(High Temparature) Alarm Monthly |  | Critical | COMPLETED |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCAll Domain | Applications/Tools | OPEN | COMPLETED | need to check |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1954 | NOC283 | NOC | NA |  | OSS | OSS | All Domain | OSS | All Sites Infra OPEN TTs details for HRT(High Tempararure) Alarm (Selective from and to dates) |  | Critical | COMPLETED |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCAll Domain | Applications/Tools | OPEN | COMPLETED | need to check |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1955 | NOC284 | NOC | NA |  | OSS | OSS | OSS | Field Passive Infra | Field Passive Infra :: Package Wise District Level Visibility Status Daily |  | Critical | COMPLETED |  | NNMI | NNMI |  | 09-09-2025: live status will be available |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCOSS | Applications/Tools | OPEN | COMPLETED | 09-09-2025: live status will be available |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1956 | NOC285 | NOC | NA |  | OSS | OSS | OSS | Field Passive Infra | Field Passive Infra :: Package Wise District Level Visibility Status Weekly |  | Critical | NOT_FEASIBLE |  | NNMI | NNMI |  |  |  |  | Suresh Pawar |  | Open | Not Feasible | [9 empty] | NOCOSS | Applications/Tools | #N/A | NOT-FEASIBLE | 0 |  |  | #N/A |  | 1 | Open | Open
1957 | NOC286 | NOC | NA |  | OSS | OSS | OSS | Field Passive Infra | Field Passive Infra :: Package Wise District Level Visibility Status Monthly |  | Critical | NOT_FEASIBLE |  | NNMI | NNMI |  |  |  |  | Suresh Pawar |  | Open | Not Feasible | [9 empty] | NOCOSS | Applications/Tools | #N/A | NOT-FEASIBLE | 0 |  |  | #N/A |  | 1 | Open | Open
1958 | NOC287 | NOC | NA |  | OSS | OSS | OSS | Field Passive Infra | Field Passive Infra :: Package Wise District Level Visibility Status (Selective from and to dates) |  | Critical | NOT_FEASIBLE |  | NNMI | NNMI |  |  |  |  | Suresh Pawar |  | Open | Not Feasible | [9 empty] | NOCOSS | Applications/Tools | #N/A | NOT-FEASIBLE | avaiable in NNMI , assign to someone from oSSteam |  |  | #N/A |  | 1 | Open | Open
1959 | NOC288 | NOC | NA |  | OSS | OSS | OSS | Field Passive Infra | NNMI :: Integration Status with Reachability Daily |  | Critical | COMPLETED |  | NNMI | NNMI |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCOSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1960 | NOC289 | NOC | NA |  | OSS | OSS | OSS | Field Passive Infra | NNMI :: Integration Status with Reachability Weekly |  | Critical | COMPLETED |  | NNMI | NNMI |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCOSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1961 | NOC29 | NOC | NA |  | OSS | OSS | OSS | Service Monitoring | Monitoring,tracking service details, Tracking of GI services uptime Service assurance dashboard (Selective from and to dates) |  | Critical | OPEN |  | HPSM | Incident Management |  | OPEN-DEPENDENT |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCOSS | Applications/Tools | OPEN | OPEN-DEPENDENT | 0 |  |  | #N/A |  | 1 | Open | Open
1962 | NOC290 | NOC | NA |  | OSS | OSS | OSS | Field Passive Infra | NNMI :: Integration Status with Reachability Monthly |  | Critical | COMPLETED |  | NNMI | NNMI |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCOSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1963 | NOC291 | NOC | NA |  | OSS | OSS | OSS | Field Passive Infra | NNMI :: Integration Status with Reachability (Selective from and to dates) |  | Critical | COMPLETED |  | NNMI | NNMI |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCOSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1964 | NOC292 | NOC | NA |  | OSS | OSS | OSS | Field Passive Infra | PKG -A :: Open TTs for O&M GP for UPS Daily |  | Critical | COMPLETED |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCOSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1965 | NOC293 | NOC | NA |  | OSS | OSS | OSS | Field Passive Infra | PKG -A :: Open TTs for O&M GP for UPS Weekly |  | Critical | COMPLETED |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCOSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1966 | NOC294 | NOC | NA |  | OSS | OSS | OSS | Field Passive Infra | PKG -A :: Open TTs for O&M GP for UPS Monthly |  | Critical | COMPLETED |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCOSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1967 | NOC295 | NOC | NA |  | OSS | OSS | OSS | Field Passive Infra | PKG -A :: Open TTs for O&M GP for UPS (Selective from and to dates) |  | Critical | COMPLETED |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCOSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1968 | NOC296 | NOC | NA |  | OSS | OSS | OSS | Field Passive Infra | PKG -B :: Open TTs for O&M GP for UPS Daily |  | Critical | COMPLETED |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCOSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1969 | NOC297 | NOC | NA |  | OSS | OSS | OSS | Field Passive Infra | PKG -B :: Open TTs for O&M GP for UPS Weekly |  | Critical | COMPLETED |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCOSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1970 | NOC298 | NOC | NA |  | OSS | OSS | OSS | Field Passive Infra | PKG -B :: Open TTs for O&M GP for UPS Monthly |  | Critical | COMPLETED |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCOSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1971 | NOC299 | NOC | NA |  | OSS | OSS | OSS | Field Passive Infra | PKG -B :: Open TTs for O&M GP for UPS (Selective from and to dates) |  | Critical | COMPLETED |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCOSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1972 | NOC3 | NOC | NA |  | OSS | OSS | OSS | DC | DC Active Infra uptime & SLA Monthly |  | Critical |  |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCOSS | Applications/Tools | OPEN | OPEN | 0 |  |  | #N/A |  | 1 | Open | Open
1973 | NOC30 | NOC | NA |  |  |  | Helpdesk | OSS | Service Delivery & Service Assurance Dash Board Daily |  | Critical | COMPLETED |  | HPSM | Incident Management |  | 11-09-2025: BSS will display all delivery data as well as service ticket informations in the CRM portal. OSS will maintain only technical information. |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCHelpdesk | Applications/Tools | OPEN | COMPLETED | 11-09-2025: BSS will display all delivery data as well as service ticket informations in the CRM portal. OSS will maintain only technical information. |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1974 | NOC300 | NOC | NA |  | OSS | OSS | OSS | Field Passive Infra | PKG -C :: Open TTs for O&M GP for UPS Daily |  | Critical | COMPLETED |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCOSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1975 | NOC301 | NOC | NA |  | OSS | OSS | OSS | Field Passive Infra | PKG -C :: Open TTs for O&M GP for UPS Weekly |  | Critical | COMPLETED |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCOSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1976 | NOC302 | NOC | NA |  | OSS | OSS | OSS | Field Passive Infra | PKG -C :: Open TTs for O&M GP for UPS Monthly |  | Critical | COMPLETED |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCOSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1977 | NOC303 | NOC | NA |  | OSS | OSS | OSS | Field Passive Infra | PKG -C :: Open TTs for O&M GP for UPS (Selective from and to dates) |  | Critical | COMPLETED |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCOSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1978 | NOC304 | NOC | NA |  | OSS | OSS | OSS | Field Passive Infra | SNMP issues _ Report Daily |  | Critical | COMPLETED |  | NNMI | NNMI |  | 09-09-2025: Live status will be available |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCOSS | Applications/Tools | OPEN | COMPLETED | 09-09-2025: Live status will be available |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1979 | NOC305 | NOC | NA |  | OSS | OSS | OSS | Field Passive Infra | SNMP issues _ Report Weekly |  | Critical | NOT_FEASIBLE |  | NNMI | NNMI |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCOSS | Applications/Tools | #N/A | COMPLETED | 0 |  |  | #N/A |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1980 | NOC306 | NOC | NA |  | OSS | OSS | OSS | Field Passive Infra | SNMP issues _ Report Monthly |  | Critical | NOT_FEASIBLE |  | NNMI | NNMI |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCOSS | Applications/Tools | #N/A | COMPLETED | 0 |  |  | #N/A |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1981 | NOC307 | NOC | NA |  | OSS | OSS | OSS | Field Passive Infra | SNMP issues _ Report (Selective from and to dates) |  | Critical | NOT_FEASIBLE |  | NNMI | NNMI |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCOSS | Applications/Tools | #N/A | COMPLETED | 0 |  |  | #N/A |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1982 | NOC308 | NOC | NA |  | OSS | OSS | OSS | Field Passive Infra | Mandal EB & Zonal DG Running report Daily |  | Critical | OPEN |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCOSS | Applications/Tools | OPEN | NOT-FEASIBLE | 0 |  |  | #N/A |  | 1 | Open | Open
1983 | NOC309 | NOC | NA |  | OSS | OSS | OSS | Field Passive Infra | Mandal EB & Zonal DG Running report Weekly |  | Critical | OPEN |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCOSS | Applications/Tools | OPEN | NOT-FEASIBLE | 0 |  |  | #N/A |  | 1 | Open | Open
1984 | NOC31 | NOC | NA |  |  |  | Helpdesk | OSS | Service Delivery & Service Assurance Dash Board Weekly |  | Critical | COMPLETED |  | HPSM | Incident Management |  | 11-09-2025: BSS will display all delivery data as well as service ticket informations in the CRM portal. OSS will maintain only technical information. |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCHelpdesk | Applications/Tools | OPEN | COMPLETED | 11-09-2025: BSS will display all delivery data as well as service ticket informations in the CRM portal. OSS will maintain only technical information. |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1985 | NOC310 | NOC | NA |  | OSS | OSS | OSS | Field Passive Infra | Mandal EB & Zonal DG Running report Monthly |  | Critical | OPEN |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCOSS | Applications/Tools | OPEN | NOT-FEASIBLE | 0 |  |  | #N/A |  | 1 | Open | Open
1986 | NOC311 | NOC | NA |  | OSS | OSS | OSS | Field Passive Infra | Mandal EB & Zonal DG Running report (Selective from and to dates) |  | Critical | OPEN |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCOSS | Applications/Tools | OPEN | OPEN | 0 |  |  | #N/A |  | 1 | Open | Open
1987 | NOC312 | NOC | NA |  | OSS | OSS | OSS | Field Passive Infra | DG Running status NNMi Logs Daily |  | Critical | COMPLETED |  | NNMI | NNMI |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCOSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1988 | NOC313 | NOC | NA |  | OSS | OSS | OSS | Field Passive Infra | DG Running status NNMi Logs Weekly |  | Critical | COMPLETED |  | NNMI | NNMI |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCOSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1989 | NOC314 | NOC | NA |  | OSS | OSS | OSS | Field Passive Infra | DG Running status NNMi Logs Monthly |  | Critical | COMPLETED |  | NNMI | NNMI |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCOSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1990 | NOC315 | NOC | NA |  | OSS | OSS | OSS | Field Passive Infra | DG Running status NNMi Logs (Selective from and to dates) |  | Critical | COMPLETED |  | NNMI | NNMI |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCOSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1991 | NOC316 | NOC | NA |  | OSS | OSS | OSS | Service Monitoring | Customised Dashboard as per Department/Service/Locations, etc.. Daily |  | Critical | COMPLETED |  | HPSM | Incident Management |  | 09-09-2025: Only Availability |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCOSS | Applications/Tools | OPEN | COMPLETED | 09-09-2025: Only Availability |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1992 | NOC317 | NOC | NA |  | OSS | OSS | OSS | Service Monitoring | Customised Dashboard as per Department/Service/Locations, etc..Weekly |  | Critical | NOT_FEASIBLE |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  | Open | Not Feasible | [9 empty] | NOCOSS | Applications/Tools | #N/A | NOT-FEASIBLE | 0 |  |  | #N/A |  | 1 | Open | Open
1993 | NOC318 | NOC | NA |  | OSS | OSS | OSS | Service Monitoring | Customised Dashboard as per Department/Service/Locations, etc..Monthly |  | Critical | NOT_FEASIBLE |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  | Open | Not Feasible | [9 empty] | NOCOSS | Applications/Tools | #N/A | NOT-FEASIBLE | 0 |  |  | #N/A |  | 1 | Open | Open
1994 | NOC319 | NOC | NA |  | OSS | OSS | OSS | Service Monitoring | Customised Dashboard as per Department/Service/Locations, etc..Selective Dates |  | Critical | NOT_FEASIBLE |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  | Open | Not Feasible | [9 empty] | NOCOSS | Applications/Tools | #N/A | NOT-FEASIBLE | 0 |  |  | #N/A |  | 1 | Open | Open
1995 | NOC32 | NOC | NA |  |  |  | Helpdesk | OSS | Service Delivery & Service Assurance Dash Board Monthly |  | Critical | COMPLETED |  | HPSM | Incident Management |  | 11-09-2025: BSS will display all delivery data as well as service ticket informations in the CRM portal. OSS will maintain only technical information. |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCHelpdesk | Applications/Tools | OPEN | COMPLETED | 11-09-2025: BSS will display all delivery data as well as service ticket informations in the CRM portal. OSS will maintain only technical information. |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1996 | NOC320 | NOC | NA |  | OSS | OSS | OSS | Service Monitoring | T-NOC Report :: GI Sites SD SA Report Daily |  | Critical | COMPLETED |  | HPSM | Incident Management |  | 09-09-2025: SD report to be collected from BSS. Ticketing & utilization report is available in OSS. |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCOSS | Applications/Tools | OPEN | COMPLETED | 09-09-2025: SD report to be collected from BSS. Ticketing & utilization report is available in OSS. |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1997 | NOC321 | NOC | NA |  | OSS | OSS | OSS | Service Monitoring | T-NOC Report :: GI Sites SD SA Report Weekly |  | Critical | NOT_FEASIBLE |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  | Open | Not Feasible | [9 empty] | NOCOSS | Applications/Tools | #N/A | NOT-FEASIBLE | 0 |  |  | #N/A |  | 1 | Open | Open
1998 | NOC322 | NOC | NA |  | OSS | OSS | OSS | Service Monitoring | T-NOC Report :: GI Sites SD SA Report Monthly |  | Critical | COMPLETED |  | HPSM | Incident Management |  | 09-09-2025: SD report to be collected from BSS. Ticketing & utilization report is available in OSS. |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCOSS | Applications/Tools | OPEN | COMPLETED | 09-09-2025: SD report to be collected from BSS. Ticketing & utilization report is available in OSS. |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
1999 | NOC323 | NOC | NA |  | OSS | OSS | OSS | Service Monitoring | T-NOC Report :: GI Sites SD SA Report (Selective from and to dates) |  | Critical | COMPLETED |  | HPSM | Incident Management |  | 09-09-2025: SD report to be collected from BSS. Ticketing & utilization report is available in OSS. |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCOSS | Applications/Tools | OPEN | COMPLETED | 09-09-2025: SD report to be collected from BSS. Ticketing & utilization report is available in OSS. |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
2000 | NOC324 | NOC | NA |  | OSS | OSS | OSS | Service Monitoring | List of GI with bandwidth Utilization Details Daily |  | Critical | COMPLETED |  | OSS Dashboards | PMS(UOC) |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCOSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
2001 | NOC325 | NOC | NA |  | OSS | OSS | OSS | Service Monitoring | List of GI with bandwidth Utilization Details Weekly |  | Critical | NOT_FEASIBLE |  | OSS Dashboards | PMS(UOC) |  |  |  |  | Suresh Pawar |  | Open | Not Feasible | [9 empty] | NOCOSS | Applications/Tools | #N/A | NOT-FEASIBLE | 0 |  |  | #N/A |  | 1 | Open | Open
2002 | NOC326 | NOC | NA |  | OSS | OSS | OSS | Service Monitoring | List of GI with bandwidth Utilization Details Monthly |  | Critical | COMPLETED |  | OSS Dashboards | PMS(UOC) |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCOSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
2003 | NOC327 | NOC | NA |  | OSS | OSS | OSS | Service Monitoring | List of GI with bandwidth Utilization Details (Selective from and to dates) |  | Critical | NOT_FEASIBLE |  | OSS Dashboards | PMS(UOC) |  |  |  |  | Suresh Pawar |  | Open | Not Feasible | [9 empty] | NOCOSS | Applications/Tools | #N/A | NOT-FEASIBLE | 0 |  |  | #N/A |  | 1 | Open | Open
2004 | NOC328 | NOC | NA |  | OSS | OSS | OSS | Service Monitoring | T-NOC :: Status Summary of Bandwidth Utilization & Non Utilization of WIFI Routers in GB & ONTs Status Daily |  | Critical | COMPLETED |  | OSS Dashboards | PMS(UOC) |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCOSS | Applications/Tools | OPEN | COMPLETED | ont bw |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
2005 | NOC329 | NOC | NA |  | OSS | OSS | OSS | Service Monitoring | T-NOC :: Status Summary of Bandwidth Utilization & Non Utilization of WIFI Routers in GB & ONTs Status Weekly |  | Critical | NOT_FEASIBLE |  | OSS Dashboards | PMS(UOC) |  |  |  |  | Suresh Pawar |  | Open | Not Feasible | [9 empty] | NOCOSS | Applications/Tools | #N/A | NOT-FEASIBLE | 0 |  |  | #N/A |  | 1 | Open | Open
2006 | NOC33 | NOC | NA |  |  |  | Helpdesk | OSS | Service Delivery & Service Assurance Dash Board (Selective from and to dates) |  | Critical | COMPLETED |  | HPSM | Incident Management |  | 11-09-2025: BSS will display all delivery data as well as service ticket informations in the CRM portal. OSS will maintain only technical information. |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCHelpdesk | Applications/Tools | OPEN | COMPLETED | 11-09-2025: BSS will display all delivery data as well as service ticket informations in the CRM portal. OSS will maintain only technical information. |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
2007 | NOC330 | NOC | NA |  | OSS | OSS | OSS | Service Monitoring | T-NOC :: Status Summary of Bandwidth Utilization & Non Utilization of WIFI Routers in GB & ONTs Status Monthly |  | Critical | COMPLETED |  | OSS Dashboards | PMS(UOC) |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCOSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
2008 | NOC331 | NOC | NA |  | OSS | OSS | OSS | Service Monitoring | T-NOC :: Status Summary of Bandwidth Utilization & Non Utilization of WIFI Routers in GB & ONTs Status (Selective from and to dates) |  | Critical | NOT_FEASIBLE |  | OSS Dashboards | PMS(UOC) |  |  |  |  | Suresh Pawar |  | Open | Not Feasible | [9 empty] | NOCOSS | Applications/Tools | #N/A | NOT-FEASIBLE | 0 |  |  | #N/A |  | 1 | Open | Open
2009 | NOC332 | NOC | NA |  | OSS | OSS | New BSS | Service Monitoring | Request for FTTH Connection Details Sheet for T-Fiber Daily |  | Critical | OPEN |  | OSS Dashboards | PMS(UOC) |  | Not Relevent to OSS, It should come from BSS |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCNew BSS | #N/A | OPEN | Not Relevant to OSS | 0 |  |  | #N/A |  | 1 | Open | Open
2010 | NOC333 | NOC | NA |  | OSS | OSS | New BSS | Service Monitoring | Request for FTTH Connection Details Sheet for T-Fiber Weekly |  | Critical | OPEN |  | OSS Dashboards | PMS(UOC) |  | Not Relevent to OSS, It should come from BSS |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCNew BSS | #N/A | OPEN | Not Relevant to OSS | 0 |  |  | #N/A |  | 1 | Open | Open
2011 | NOC334 | NOC | NA |  | OSS | OSS | New BSS | Service Monitoring | Request for FTTH Connection Details Sheet for T-Fiber Monthly |  | Critical | OPEN |  | OSS Dashboards | PMS(UOC) |  | Not Relevent to OSS, It should come from BSS |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCNew BSS | #N/A | OPEN | Not Relevant to OSS | 0 |  |  | #N/A |  | 1 | Open | Open
2012 | NOC335 | NOC | NA |  | OSS | OSS | New BSS | Service Monitoring | Request for FTTH Connection Details Sheet for T-Fiber (Selective from and to dates) |  | Critical | OPEN |  | OSS Dashboards | PMS(UOC) |  | Not Relevent to OSS, It should come from BSS |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCNew BSS | #N/A | OPEN | Not Relevant to OSS | 0 |  |  | #N/A |  | 1 | Open | Open
2013 | NOC336 | NOC | NA |  | OSS | OSS | New BSS | Service Monitoring | Service Delivery & Service Assurance Dash Board (Signed Forms) Daily |  | Critical | OPEN |  | HPSM | Incident Management |  | Aditional Scope for OT/HPE |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCNew BSS | #N/A | OPEN | Not Relevant to OSS | 0 |  |  | #N/A |  | 1 | Open | Open
2014 | NOC337 | NOC | NA |  | OSS | OSS | New BSS | Service Monitoring | Service Delivery & Service Assurance Dash Board (Signed Forms) Weekly |  | Critical | OPEN |  | HPSM | Incident Management |  | Aditional Scope for OT/HPE |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCNew BSS | #N/A | OPEN | Not Relevant to OSS | 0 |  |  | #N/A |  | 1 | Open | Open
2015 | NOC338 | NOC | NA |  | OSS | OSS | New BSS | Service Monitoring | Service Delivery & Service Assurance Dash Board (Signed Forms) Monthly |  | Critical | OPEN |  | HPSM | Incident Management |  | Aditional Scope for OT/HPE |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCNew BSS | #N/A | OPEN | Not Relevant to OSS | 0 |  |  | #N/A |  | 1 | Open | Open
2016 | NOC339 | NOC | NA |  | OSS | OSS | New BSS | Service Monitoring | Service Delivery & Service Assurance Dash Board (Signed Forms) (Selective from and to dates) |  | Critical | OPEN |  | HPSM | Incident Management |  | Aditional Scope for OT/HPE |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCNew BSS | #N/A | OPEN | Not Relevant to OSS | 0 |  |  | #N/A |  | 1 | Open | Open
2017 | NOC34 | NOC | NA |  |  |  | Helpdesk | OSS | Incident Reporting and Field Assignment(Any failure/incident on any part of the network infrastructure or its facilities shall be communicated immediately to Helpdesk by Network Monitoring team/ field representative / end user giving details of the incident/fault/problem.) Daily |  | Critical |  |  | HPSM | Incident Management |  | 09-09-2025: Integration with WFM is in place to give live trigger to FE and SMS/email integration also in place to give notification to configured escallation matrix |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCHelpdesk | Applications/Tools | OPEN | NOT-FEASIBLE | 09-09-2025: Integration with WFM is in place to give live trigger to FE and SMS/email integration also in place to give notification to configured escallation matrix |  |  | #VALUE! |  | 1 | Open | Open
2018 | NOC340 | NOC | NA |  | OSS | OSS | All Domain | OSS | PE Mapping with MTTR report Daily |  | Critical | OPEN |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCAll Domain | Applications/Tools | OPEN | WIP | 0 |  |  | #N/A |  | 1 | Open | Open
2019 | NOC341 | NOC | NA |  | OSS | OSS | All Domain | OSS | PE Mapping with MTTR report Weekly |  | Critical | OPEN |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCAll Domain | Applications/Tools | OPEN | WIP | 0 |  |  | #N/A |  | 1 | Open | Open
2020 | NOC342 | NOC | NA |  | OSS | OSS | All Domain | OSS | PE Mapping with MTTR report Monthly |  | Critical | OPEN |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCAll Domain | Applications/Tools | OPEN | WIP | 0 |  |  | #N/A |  | 1 | Open | Open
2021 | NOC343 | NOC | NA |  | OSS | OSS | All Domain | OSS | PE Mapping with MTTR report (Selective from and to dates) |  | Critical | NOT_FEASIBLE |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCAll Domain | Applications/Tools | #N/A | COMPLETED | 0 |  |  | #N/A |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
2022 | NOC344 | NOC | NA |  |  |  | BSS | Service Delivery | GI GP Wifi HH Delivery Status Daily |  | Critical | OPEN |  | BSS | CRM |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
2023 | NOC345 | NOC | NA |  |  |  | BSS | Service Delivery | GI GP Wifi HH Delivery Status Weekly |  | Critical | OPEN |  | BSS | CRM |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
2024 | NOC346 | NOC | NA |  |  |  | BSS | Service Delivery | GI GP Wifi HH Delivery Status Monthly |  | Critical | OPEN |  | BSS | CRM |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
2025 | NOC347 | NOC | NA |  |  |  | BSS | Service Delivery | GI GP Wifi HH Delivery Status (Selective from and to dates) |  | Critical | OPEN |  | BSS | CRM |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
2026 | NOC348 | NOC | NA |  |  |  | BSS | Service Delivery | Service IDs for all GI Locatinos Daily |  | Critical | OPEN |  | BSS | CRM |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
2027 | NOC349 | NOC | NA |  |  |  | BSS | Service Delivery | Service IDs for all GI Locatinos Weekly |  | Critical | OPEN |  | BSS | CRM |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
2028 | NOC35 | NOC | NA |  |  |  | Helpdesk | OSS | Incident Reporting and Field Assignment(Any failure/incident on any part of the network infrastructure or its facilities shall be communicated immediately to Helpdesk by Network Monitoring team/ field representative / end user giving details of the incident/fault/problem.) Weekly |  | Critical |  |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCHelpdesk | Applications/Tools | OPEN | COMPLETED | 0 |  |  | #VALUE! |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
2029 | NOC350 | NOC | NA |  |  |  | BSS | Service Delivery | Service IDs for all GI Locatinos Monthly |  | Critical | OPEN |  | BSS | CRM |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
2030 | NOC351 | NOC | NA |  |  |  | BSS | Service Delivery | Service IDs for all GI Locatinos (Selective from and to dates) |  | Critical | OPEN |  | BSS | CRM |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
2031 | NOC352 | NOC | NA |  |  |  | BSS | Service Delivery | Household Delivery Status Report Daily |  | Critical | OPEN |  | BSS | CRM |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
2032 | NOC353 | NOC | NA |  |  |  | BSS | Service Delivery | Household Delivery Status Report Weekly |  | Critical | OPEN |  | BSS | CRM |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
2033 | NOC354 | NOC | NA |  |  |  | BSS | Service Delivery | Household Delivery Status Report Monthly |  | Critical | OPEN |  | BSS | CRM |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
2034 | NOC355 | NOC | NA |  |  |  | BSS | Service Delivery | Household Delivery Status Report (Selective from and to dates) |  | Critical | OPEN |  | BSS | CRM |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
2035 | NOC356 | NOC | NA |  | OSS | OSS | All Domain | OSS | Alarm seviority(Critical/major/Minor)(Domain wise Filter) Daily |  | Critical | COMPLETED |  | OSS Dashboards | VTemip |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCAll Domain | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
2036 | NOC357 | NOC | NA |  | OSS | OSS | All Domain | OSS | Alarm seviority(Critical/major/Minor)(Domain wise Filter) Weekly |  | Critical | COMPLETED |  | OSS Dashboards | VTemip |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCAll Domain | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
2037 | NOC358 | NOC | NA |  | OSS | OSS | All Domain | OSS | Alarm seviority(Critical/major/Minor)(Domain wise Filter) Monthly |  | Critical | COMPLETED |  | OSS Dashboards | VTemip |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCAll Domain | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
2038 | NOC359 | NOC | NA |  | OSS | OSS | All Domain | OSS | Alarm seviority(Critical/major/Minor)(Domain wise Filter) (Selective from and to dates) |  | Critical | COMPLETED |  | OSS Dashboards | VTemip |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCAll Domain | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
2039 | NOC36 | NOC | NA |  |  |  | Helpdesk | OSS | Incident Reporting and Field Assignment(Any failure/incident on any part of the network infrastructure or its facilities shall be communicated immediately to Helpdesk by Network Monitoring team/ field representative / end user giving details of the incident/fault/problem.) Monthly |  | Critical |  |  | HPSM | Incident Management |  | 09-09-2025: Integration with WFM is in place to give live trigger to FE and SMS/email integration also in place to give notification to configured escallation matrix |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCHelpdesk | Applications/Tools | OPEN | NOT-FEASIBLE | 09-09-2025: Integration with WFM is in place to give live trigger to FE and SMS/email integration also in place to give notification to configured escallation matrix |  |  | #VALUE! |  | 1 | Open | Open
2040 | NOC360 | NOC | NA |  | OSS | OSS | All Domain | OSS | Inventory Dashboard and Report(Domain wise Filter) Daily |  | Critical | COMPLETED |  | OSS Dashboards | UTM |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCAll Domain | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
2041 | NOC361 | NOC | NA |  | OSS | OSS | All Domain | OSS | Inventory Dashboard and Report(Domain wise Filter) Weekly |  | Critical | NOT_FEASIBLE |  | OSS Dashboards | UTM |  |  |  |  | Suresh Pawar |  | Open | Not Feasible | [9 empty] | NOCAll Domain | Applications/Tools | #N/A | NOT-FEASIBLE | 0 |  |  | #N/A |  | 1 | Open | Open
2042 | NOC362 | NOC | NA |  | OSS | OSS | All Domain | OSS | Inventory Dashboard and Report(Domain wise Filter) Monthly |  | Critical | NOT_FEASIBLE |  | OSS Dashboards | UTM |  |  |  |  | Suresh Pawar |  | Open | Not Feasible | [9 empty] | NOCAll Domain | Applications/Tools | #N/A | NOT-FEASIBLE | 0 |  |  | #N/A |  | 1 | Open | Open
2043 | NOC363 | NOC | NA |  | OSS | OSS | All Domain | OSS | Inventory Dashboard and Report(Domain wise Filter) (Selective from and to dates) |  | Critical | NOT_FEASIBLE |  | OSS Dashboards | UTM |  |  |  |  | Suresh Pawar |  | Open | Not Feasible | [9 empty] | NOCAll Domain | Applications/Tools | #N/A | NOT-FEASIBLE | 0 |  |  | #N/A |  | 1 | Open | Open
2044 | NOC364 | NOC | NA |  | OSS | OSS | All Domain | OSS | Correlation within Domain and cross domain Daily |  | Critical |  |  | OSS Dashboards | UCA |  |  |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCAll Domain | Applications/Tools | OPEN | OPEN | 0 |  |  | #N/A |  | 1 | Open | Open
2045 | NOC365 | NOC | NA |  | OSS | OSS | All Domain | OSS | Correlation within Domain and cross domain Weekly |  | Critical | DUPLICATE POINT |  | OSS Dashboards | UCA |  | DUPLICATE POINT |  |  | Suresh Pawar |  | Open | WIP | [9 empty] | NOCAll Domain | Applications/Tools | OPEN | OPEN | 0 |  |  | #N/A |  | 1 | Open | Open
2046 | NOC366 | NOC | NA |  | OSS | OSS | All Domain | OSS | Correlation within Domain and cross domain Monthly |  | Critical |  |  | OSS Dashboards | UCA |  |  |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCAll Domain | Applications/Tools | OPEN | OPEN | 0 |  |  | #N/A |  | 1 | Open | Open
2047 | NOC367 | NOC | NA |  | OSS | OSS | All Domain | OSS | Correlation within Domain and cross domain (Selective from and to dates) |  | Critical |  |  | OSS Dashboards | UCA |  |  |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCAll Domain | Applications/Tools | OPEN | OPEN | 0 |  |  | #N/A |  | 1 | Open | Open
2048 | NOC368 | NOC | NA |  | OSS | OSS | OSS | DC IT Active Infra | Service Monitoring of All DC Elements(DC WAN, Leaf, Spine and Service riding on these Network and Servers) Daily |  | Critical |  |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCOSS | Applications/Tools | OPEN | OPEN | 0 |  |  | #N/A |  | 1 | Open | Open
2049 | NOC369 | NOC | NA |  | OSS | OSS | OSS | DC IT Active Infra | Service Monitoring of All DC Elements(DC WAN, Leaf, Spine and Service riding on these Network and Servers) Weekly |  | Critical |  |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCOSS | Applications/Tools | OPEN | OPEN | 0 |  |  | #N/A |  | 1 | Open | Open
2050 | NOC37 | NOC | NA |  |  |  | Helpdesk | OSS | Incident Reporting and Field Assignment(Any failure/incident on any part of the network infrastructure or its facilities shall be communicated immediately to Helpdesk by Network Monitoring team/ field representative / end user giving details of the incident/fault/problem.) (Selective from and to dates) |  | Critical |  |  | HPSM | Incident Management |  | 09-09-2025: Integration with WFM is in place to give live trigger to FE and SMS/email integration also in place to give notification to configured escallation matrix |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCHelpdesk | Applications/Tools | OPEN | NOT-FEASIBLE | 09-09-2025: Integration with WFM is in place to give live trigger to FE and SMS/email integration also in place to give notification to configured escallation matrix |  |  | #VALUE! |  | 1 | Open | Open
2051 | NOC370 | NOC | NA |  | OSS | OSS | OSS | DC IT Active Infra | Service Monitoring of All DC Elements(DC WAN, Leaf, Spine and Service riding on these Network and Servers) Monthly |  | Critical |  |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCOSS | Applications/Tools | OPEN | OPEN | 0 |  |  | #N/A |  | 1 | Open | Open
2052 | NOC371 | NOC | NA |  | OSS | OSS | OSS | DC IT Active Infra | Service Monitoring of All DC Elements(DC WAN, Leaf, Spine and Service riding on these Network and Servers) (Selective from and to dates) |  | Critical |  |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCOSS | Applications/Tools | OPEN | OPEN | 0 |  |  | #N/A |  | 1 | Open | Open
2053 | NOC372 | NOC | NA |  | OSS | OSS | All Domain | OSS | Interface Utilisation(>80%) Hourly |  | Critical | COMPLETED |  | NNMI | NPS |  | 09-09-2025: Threshold limits needs tobe enabled and on that threshold limit the alarms to be generated and that alarm should qualify for ticket generation as per requirement |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCAll Domain | Applications/Tools | OPEN | COMPLETED | 09-09-2025: Threshold limits needs tobe enabled and on that threshold limit the alarms to be generated and that alarm should qualify for ticket generation as per requirement-need to check with govind |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
2054 | NOC373 | NOC | NA |  | OSS | OSS | All Domain | OSS | Interface Utilisation(>80%) Daily |  | Critical | COMPLETED |  | NNMI | NPS |  | 09-09-2025: Threshold limits needs tobe enabled and on that threshold limit the alarms to be generated and that alarm should qualify for ticket generation as per requirement |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCAll Domain | Applications/Tools | OPEN | COMPLETED | 09-09-2025: Threshold limits needs tobe enabled and on that threshold limit the alarms to be generated and that alarm should qualify for ticket generation as per requirement |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
2055 | NOC374 | NOC | NA |  | OSS | OSS | All Domain | OSS | Interface Utilisation(>80%) Weekly |  | Critical | COMPLETED |  | NNMI | NPS |  | 09-09-2025: Threshold limits needs tobe enabled and on that threshold limit the alarms to be generated and that alarm should qualify for ticket generation as per requirement |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCAll Domain | Applications/Tools | OPEN | COMPLETED | 09-09-2025: Threshold limits needs tobe enabled and on that threshold limit the alarms to be generated and that alarm should qualify for ticket generation as per requirement |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
2056 | NOC375 | NOC | NA |  | OSS | OSS | All Domain | OSS | Interface Utilisation(>80%) Monthly |  | Critical | COMPLETED |  | NNMI | NPS |  | 09-09-2025: Threshold limits needs tobe enabled and on that threshold limit the alarms to be generated and that alarm should qualify for ticket generation as per requirement |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCAll Domain | Applications/Tools | OPEN | COMPLETED | 09-09-2025: Threshold limits needs tobe enabled and on that threshold limit the alarms to be generated and that alarm should qualify for ticket generation as per requirement |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
2057 | NOC376 | NOC | NA |  | OSS | OSS | All Domain | OSS | Interface Utilisation(% of Utilisation configurable) |  | Critical | COMPLETED |  | NNMI | NPS |  | 09-09-2025: Threshold limits needs tobe enabled and on that threshold limit the alarms to be generated and that alarm should qualify for ticket generation as per requirement |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCAll Domain | Applications/Tools | OPEN | COMPLETED | 09-09-2025: Threshold limits needs tobe enabled and on that threshold limit the alarms to be generated and that alarm should qualify for ticket generation as per requirement |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
2058 | NOC377 | NOC | NA |  | OSS | OSS | All Domain | OSS | Interface Utilisation(Polling Duration configurable) |  | Critical | COMPLETED |  | NNMI | NPS |  | 09-09-2025: Threshold limits needs tobe enabled and on that threshold limit the alarms to be generated and that alarm should qualify for ticket generation as per requirement |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCAll Domain | Applications/Tools | OPEN | COMPLETED | 09-09-2025: Threshold limits needs tobe enabled and on that threshold limit the alarms to be generated and that alarm should qualify for ticket generation as per requirement |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
2059 | NOC378 | NOC | NA |  | OSS | OSS | All Domain | OSS | Interface Utilisation(>80%) (Selective from and to dates) |  | Critical | COMPLETED |  | NNMI | NPS |  | 09-09-2025: Threshold limits needs tobe enabled and on that threshold limit the alarms to be generated and that alarm should qualify for ticket generation as per requirement |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCAll Domain | Applications/Tools | OPEN | COMPLETED | 09-09-2025: Threshold limits needs tobe enabled and on that threshold limit the alarms to be generated and that alarm should qualify for ticket generation as per requirement |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
2060 | NOC379 | NOC | NA |  | OSS | OSS | All Domain | OSS | CPU/RAM(>80%) Daily |  | Critical | COMPLETED |  | NNMI | NPS |  | 09-09-2025: Threshold limits needs tobe enabled and on that threshold limit the alarms to be generated and that alarm should qualify for ticket generation as per requirement |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCAll Domain | Applications/Tools | OPEN | COMPLETED | 09-09-2025: Threshold limits needs tobe enabled and on that threshold limit the alarms to be generated and that alarm should qualify for ticket generation as per requirement |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
2061 | NOC38 | NOC | NA |  |  |  | Helpdesk | Help Desk | Help Desk managing and publishing KPI like Total I/O call, answereed call withing time frame etc. Hourly |  | NON-Critical |  |  | Helpdesk | Dial center | CLosed | 24-Sep-25: Option available to Choose Dates, daily, Weekly and Monthly But not Direct as Daily, Weekly, Monthly |  |  | Siva Kumar |  |  | COMPLETED & APPROVED | [9 empty] | NOCHelpdesk | Applications/Tools | CLOSED |  |  |  | 2025-09-24 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\NOC38,39,40,41,42 |  | 1 | Completed & Approved | Closed after June
2062 | NOC380 | NOC | NA |  | OSS | OSS | All Domain | OSS | CPU/RAM(>80%) Weekly |  | Critical | COMPLETED |  | NNMI | NPS |  | 09-09-2025: Threshold limits needs tobe enabled and on that threshold limit the alarms to be generated and that alarm should qualify for ticket generation as per requirement |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCAll Domain | Applications/Tools | OPEN | COMPLETED | 09-09-2025: Threshold limits needs tobe enabled and on that threshold limit the alarms to be generated and that alarm should qualify for ticket generation as per requirement |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
2063 | NOC381 | NOC | NA |  | OSS | OSS | All Domain | OSS | CPU/RAM(>80%) Monthly |  | Critical | COMPLETED |  | NNMI | NPS |  | 09-09-2025: Threshold limits needs tobe enabled and on that threshold limit the alarms to be generated and that alarm should qualify for ticket generation as per requirement |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCAll Domain | Applications/Tools | OPEN | COMPLETED | 09-09-2025: Threshold limits needs tobe enabled and on that threshold limit the alarms to be generated and that alarm should qualify for ticket generation as per requirement |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
2064 | NOC382 | NOC | NA |  | OSS | OSS | All Domain | OSS | CPU/RAM(% of Utilisation configurable) |  | Critical | COMPLETED |  | NNMI | NPS |  | 09-09-2025: Threshold limits needs tobe enabled and on that threshold limit the alarms to be generated and that alarm should qualify for ticket generation as per requirement |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCAll Domain | Applications/Tools | OPEN | COMPLETED | 09-09-2025: Threshold limits needs tobe enabled and on that threshold limit the alarms to be generated and that alarm should qualify for ticket generation as per requirement |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
2065 | NOC383 | NOC | NA |  | OSS | OSS | All Domain | OSS | CPU/RAM(Polling Duration configurable) |  | Critical | COMPLETED |  | NNMI | NPS |  | 09-09-2025: Threshold limits needs tobe enabled and on that threshold limit the alarms to be generated and that alarm should qualify for ticket generation as per requirement |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCAll Domain | Applications/Tools | OPEN | COMPLETED | 09-09-2025: Threshold limits needs tobe enabled and on that threshold limit the alarms to be generated and that alarm should qualify for ticket generation as per requirement |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
2066 | NOC384 | NOC | NA |  | OSS | OSS | All Domain | OSS | CPU/RAM(>80%) (Selective from and to dates) |  | Critical | COMPLETED |  | NNMI | NPS |  | 09-09-2025: Threshold limits needs tobe enabled and on that threshold limit the alarms to be generated and that alarm should qualify for ticket generation as per requirement |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCAll Domain | Applications/Tools | OPEN | COMPLETED | 09-09-2025: Threshold limits needs tobe enabled and on that threshold limit the alarms to be generated and that alarm should qualify for ticket generation as per requirement |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
2067 | NOC385 | NOC | NA |  | OSS | OSS | All Domain | OSS | Incident/Alarm Notifciation via SMS, E-mail and Call, Whatsapp as per escalation Matrix (Selective from and to dates) |  | Critical | COMPLETED |  | HPSM | Incident Management |  | 09-09-2025: SMS & EMAIL is integrated. Whatsapp & Call not feasible |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCAll Domain | Applications/Tools | OPEN | COMPLETED | 09-09-2025: SMS & EMAIL is integrated. Whatsapp & Call not feasible-earlier it was present as there was no credit it was stopped |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
2068 | NOC386 | NOC | NA |  | OSS | OSS | All Domain | OSS | Node(POP) wise Availability Daily |  | Critical | COMPLETED |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCAll Domain | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
2069 | NOC387 | NOC | NA |  | OSS | OSS | All Domain | OSS | Node(POP) wise Availability Weekly |  | Critical | NOT_FEASIBLE |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  | Open | Not Feasible | [9 empty] | NOCAll Domain | Applications/Tools | #N/A | NOT-FEASIBLE | 0 |  |  | #N/A |  | 1 | Open | Open
2070 | NOC388 | NOC | NA |  | OSS | OSS | All Domain | OSS | Node(POP) wise Availability Monthly |  | Critical | COMPLETED |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCAll Domain | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
2071 | NOC389 | NOC | NA |  | OSS | OSS | All Domain | OSS | Node(POP) wise Availability (Selective from and to dates) |  | Critical | NOT_FEASIBLE |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  | Open | Not Feasible | [9 empty] | NOCAll Domain | Applications/Tools | #N/A | NOT-FEASIBLE | 0 |  |  | #N/A |  | 1 | Open | Open
2072 | NOC39 | NOC | NA |  |  |  | Helpdesk | Help Desk | Help Desk managing and publishing KPI like Total I/O call, answereed call withing time frame etc. Daily |  | NON-Critical |  |  | Helpdesk | Dial center | CLosed | 24-Sep-25: Option available to Choose Dates, daily, Weekly and Monthly But not Direct as Daily, Weekly, Monthly |  |  | Siva Kumar |  |  | COMPLETED & APPROVED | [9 empty] | NOCHelpdesk | Applications/Tools | CLOSED |  |  |  | 2025-09-24 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\NOC38,39,40,41,42 |  | 1 | Completed & Approved | Closed after June
2073 | NOC390 | NOC | NA |  | OSS | OSS | All Domain | OSS | Equipment wise Availability Daily |  | Critical | COMPLETED |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCAll Domain | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
2074 | NOC391 | NOC | NA |  | OSS | OSS | All Domain | OSS | Equipment wise Availability Weekly |  | Critical | NOT_FEASIBLE |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  | Open | Not Feasible | [9 empty] | NOCAll Domain | Applications/Tools | #N/A | NOT-FEASIBLE | 0 |  |  | #N/A |  | 1 | Open | Open
2075 | NOC392 | NOC | NA |  | OSS | OSS | All Domain | OSS | Equipment wise Availability Monthly |  | Critical | COMPLETED |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCAll Domain | Applications/Tools | OPEN | COMPLETED | for DWDN no monthly report inUOC |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
2076 | NOC393 | NOC | NA |  | OSS | OSS | All Domain | OSS | Equipment wise Availability (Selective from and to dates) |  | Critical | NOT_FEASIBLE |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  | Open | Not Feasible | [9 empty] | NOCAll Domain | Applications/Tools | #N/A | NOT-FEASIBLE | 0 |  |  | #N/A |  | 1 | Open | Open
2077 | NOC394 | NOC | NA |  | OSS | OSS | All Domain | OSS | Link wise Uptime Daily |  | Critical | COMPLETED |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCAll Domain | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
2078 | NOC395 | NOC | NA |  | OSS | OSS | All Domain | OSS | Link wise Uptime Weekly |  | Critical | NOT_FEASIBLE |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  | Open | Not Feasible | [9 empty] | NOCAll Domain | Applications/Tools | #N/A | NOT-FEASIBLE | 0 |  |  | #N/A |  | 1 | Open | Open
2079 | NOC396 | NOC | NA |  | OSS | OSS | All Domain | OSS | Link wise Uptime Monthly |  | Critical | COMPLETED |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCAll Domain | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
2080 | NOC397 | NOC | NA |  | OSS | OSS | All Domain | OSS | Link wise Uptime (Selective from and to dates) |  | Critical | NOT_FEASIBLE |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  | Open | Not Feasible | [9 empty] | NOCAll Domain | Applications/Tools | #N/A | NOT-FEASIBLE | 0 |  |  | #N/A |  | 1 | Open | Open
2081 | NOC398 | NOC | NA |  | OSS | OSS | All Domain | OSS | Link wise MTTR Daily |  | Critical | OPEN |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCAll Domain | Applications/Tools | OPEN | WIP | 0 |  |  | #N/A |  | 1 | Open | Open
2082 | NOC399 | NOC | NA |  | OSS | OSS | All Domain | OSS | Link wise MTTR Weekly |  | Critical | OPEN |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCAll Domain | Applications/Tools | OPEN | WIP | 0 |  |  | #N/A |  | 1 | Open | Open
2083 | NOC4 | NOC | NA |  | OSS | OSS | OSS | DC | DC Active Infra uptime & SLA Custom(Selective from and to dates) |  | Critical |  |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCOSS | Applications/Tools | OPEN | OPEN | 0 |  |  | #N/A |  | 1 | Open | Open
2084 | NOC40 | NOC | NA |  |  |  | Helpdesk | Help Desk | Help Desk managing and publishing KPI like Total I/O call, answereed call withing time frame etc. Weekly |  | NON-Critical |  |  | Helpdesk | Dial center | CLosed | 24-Sep-25: Option available to Choose Dates, daily, Weekly and Monthly But not Direct as Daily, Weekly, Monthly |  |  | Siva Kumar |  |  | COMPLETED & APPROVED | [9 empty] | NOCHelpdesk | Applications/Tools | CLOSED |  |  |  | 2025-09-24 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\NOC38,39,40,41,42 |  | 1 | Completed & Approved | Closed after June
2085 | NOC400 | NOC | NA |  | OSS | OSS | All Domain | OSS | Link wise MTTR Monthly |  | Critical | OPEN |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCAll Domain | Applications/Tools | OPEN | WIP | 0 |  |  | #N/A |  | 1 | Open | Open
2086 | NOC401 | NOC | NA |  | OSS | OSS | All Domain | OSS | Link wise MTTR (Selective from and to dates) |  | Critical | NOT_FEASIBLE |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCAll Domain | Applications/Tools | #N/A | COMPLETED | 0 |  |  | #N/A |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
2087 | NOC402 | NOC | NA |  | OSS | OSS | OSS | DC and Field IPMPLS | IPSLA Daily(Packet Drops, Latency, Jitter, ect..) |  | Critical | COMPLETED |  | NNMI | NPS |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCOSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
2088 | NOC403 | NOC | NA |  | OSS | OSS | OSS | DC and Field IPMPLS | IPSLA Weekly(Packet drops, latency, jitter, etc..) |  | Critical | COMPLETED |  | NNMI | NPS |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCOSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
2089 | NOC404 | NOC | NA |  | OSS | OSS | OSS | DC and Field IPMPLS | IPSLA Monthly (Packet drops, latency, jitter, etc..) |  | Critical | COMPLETED |  | NNMI | NPS |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCOSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
2090 | NOC405 | NOC | NA |  | OSS | OSS | OSS | DC and Field IPMPLS | IPSLA (Selective from and to dates)(Packet drops, latency, jitter, etc..) |  | Critical | COMPLETED |  | NNMI | NPS |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCOSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
2091 | NOC406 | NOC | NA |  | OSS | OSS | OSS | DC and Field IPMPLS | IPSLA (Packet drops to be configurable and existing >1% to be reported in Dashboard |  | Critical | COMPLETED |  | NNMI | NPS |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCOSS | Applications/Tools | OPEN | COMPLETED | To be checked |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
2092 | NOC407 | NOC | NA |  | OSS | OSS | OSS | DC and Field IPMPLS | IPSLA (Latency to be configurable and existing >10ms to be reported in Dashboard |  | Critical | COMPLETED |  | NNMI | NPS |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCOSS | Applications/Tools | OPEN | COMPLETED | To be checked |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
2093 | NOC408 | NOC | NA |  | OSS | OSS | OSS | DC and Field IPMPLS | IPSLA (Jitter to be configurable and existing >30ms to be reported in Dashboard |  | Critical | COMPLETED |  | NNMI | NPS |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCOSS | Applications/Tools | OPEN | COMPLETED | To be checked |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
2094 | NOC409 | NOC | NA |  | OSS | OSS | OSS | DC and Field IPMPLS | Traffic Utilisation covering All QoS Partameters Daily |  | Critical | OPEN |  | NNMI | NPS |  | 09-09-2025: Need to discuss with OT |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCOSS | Applications/Tools | OPEN | OPEN | 09-09-2025: Need to discuss with OT |  |  | #N/A |  | 1 | Open | Open
2095 | NOC41 | NOC | NA |  |  |  | Helpdesk | Help Desk | Help Desk managing and publishing KPI like Total I/O call, answereed call withing time frame etc. Monthly |  | NON-Critical |  |  | Helpdesk | Dial center | CLosed | 24-Sep-25: Option available to Choose Dates, daily, Weekly and Monthly But not Direct as Daily, Weekly, Monthly |  |  | Siva Kumar |  |  | COMPLETED & APPROVED | [9 empty] | NOCHelpdesk | Applications/Tools | CLOSED |  |  |  | 2025-09-24 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\NOC38,39,40,41,42 |  | 1 | Completed & Approved | Closed after June
2096 | NOC410 | NOC | NA |  | OSS | OSS | OSS | DC and Field IPMPLS | Traffic Utilisation covering All QoS Partameters Weekly |  | Critical | OPEN |  | NNMI | NPS |  | 09-09-2025: Need to discuss with OT |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCOSS | Applications/Tools | OPEN | OPEN | 09-09-2025: Need to discuss with OT |  |  | #N/A |  | 1 | Open | Open
2097 | NOC411 | NOC | NA |  | OSS | OSS | OSS | DC and Field IPMPLS | Traffic Utilisation covering All QoS Partameters Monthly |  | Critical | OPEN |  | NNMI | NPS |  | 09-09-2025: Need to discuss with OT |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCOSS | Applications/Tools | OPEN | OPEN | 09-09-2025: Need to discuss with OT |  |  | #N/A |  | 1 | Open | Open
2098 | NOC412 | NOC | NA |  | OSS | OSS | OSS | DC and Field IPMPLS | Traffic Utilisation covering All QoS Partameters (Selective from and to dates) |  | Critical | OPEN |  | NNMI | NPS |  | 09-09-2025: Need to discuss with OT |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCOSS | Applications/Tools | OPEN | OPEN | 09-09-2025: Need to discuss with OT |  |  | #N/A |  | 1 | Open | Open
2099 | NOC413 | NOC | NA |  | OSS | OSS | OSS | BBNL Reports | Block and GP Status Daily |  | Critical | COMPLETED |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCOSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
2100 | NOC414 | NOC | NA |  | OSS | OSS | OSS | BBNL Reports | Block and GP Status Weekly |  | Critical | NOT_FEASIBLE |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  | Open | Not Feasible | [9 empty] | NOCOSS | Applications/Tools | #N/A | Not Required to BBNL | 11-Oct-25: BBNL do not ask weekly hence it is not delivered |  |  | #N/A |  | 1 | Open | Open
2101 | NOC415 | NOC | NA |  | OSS | OSS | OSS | BBNL Reports | Block and GP Status Monthly |  | Critical | COMPLETED |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCOSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
2102 | NOC416 | NOC | NA |  | OSS | OSS | OSS | BBNL Reports | Block and GP Status (Selective from and to dates) |  | Critical | NOT_FEASIBLE |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  | Open | Not Feasible | [9 empty] | NOCOSS | Applications/Tools | #N/A | Not Required to BBNL | 11-Oct-25: BBNL do not ask Selective from and to dates hence it is not delivered |  |  | #N/A |  | 1 | Open | Open
2103 | NOC417 | NOC | NA |  | OSS | OSS | OSS | BBNL Reports | Block and GP Availability Daily |  | Critical | COMPLETED |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCOSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
2104 | NOC418 | NOC | NA |  | OSS | OSS | OSS | BBNL Reports | Block and GP Availability Weekly |  | Critical | NOT_FEASIBLE |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  | Open | Not Feasible | [9 empty] | NOCOSS | Applications/Tools | #N/A | Not Required to BBNL | 11-Oct-25: BBNL do not ask weekly hence it is not delivered |  |  | #N/A |  | 1 | Open | Open
2105 | NOC419 | NOC | NA |  | OSS | OSS | OSS | BBNL Reports | Block and GP Availability Monthly |  | Critical | COMPLETED |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCOSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
2106 | NOC42 | NOC | NA |  |  |  | Helpdesk | Help Desk | Help Desk managing and publishing KPI like Total I/O call, answereed call withing time frame etc. (Selective from and to dates) |  | NON-Critical |  |  | Helpdesk | Dial center | CLosed | 24-Sep-25: Option available to Choose Dates, daily, Weekly and Monthly But not Direct as Daily, Weekly, Monthly |  |  | Siva Kumar |  |  | COMPLETED & APPROVED | [9 empty] | NOCHelpdesk | Applications/Tools | CLOSED |  |  |  | 2025-09-24 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\NOC38,39,40,41,42 |  | 1 | Completed & Approved | Closed after June
2107 | NOC420 | NOC | NA |  | OSS | OSS | OSS | BBNL Reports | Block and GP Availability (Selective from and to dates) |  | Critical | NOT_FEASIBLE |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  | Open | Not Feasible | [9 empty] | NOCOSS | Applications/Tools | #N/A | Not Required to BBNL | 11-Oct-25: BBNL do not ask Selective from and to dates hence it is not delivered |  |  | #N/A |  | 1 | Open | Open
2108 | NOC421 | NOC | NA |  |  |  | New BSS | BBNL Reports | FTTH Connections and their utilisation(Including Household) Daily |  | Critical | OPEN |  | BSS | CRM |  |  |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCNew BSS | #N/A | OPEN | Not Relevant to OSS | 0 |  |  | #N/A |  | 1 | Open | Open
2109 | NOC422 | NOC | NA |  |  |  | New BSS | BBNL Reports | FTTH Connections and their utilisation(Including Household) Weekly |  | Critical | OPEN |  | BSS | CRM |  |  |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCNew BSS | #N/A | OPEN | Not Relevant to OSS | 0 |  |  | #N/A |  | 1 | Open | Open
2110 | NOC423 | NOC | NA |  |  |  | New BSS | BBNL Reports | FTTH Connections and their utilisation(Including Household) Monthly |  | Critical | OPEN |  | BSS | CRM |  |  |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCNew BSS | #N/A | OPEN | Not Relevant to OSS | 0 |  |  | #N/A |  | 1 | Open | Open
2111 | NOC424 | NOC | NA |  |  |  | New BSS | BBNL Reports | FTTH Connections and their utilisation(Including Household) (Selective from and to dates) |  | Critical | OPEN |  | BSS | CRM |  |  |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCNew BSS | #N/A | OPEN | Not Relevant to OSS | 0 |  |  | #N/A |  | 1 | Open | Open
2112 | NOC425 | NOC | NA |  |  |  | BSS | Regulatory Compliance | Customer connections Daily |  | Critical | OPEN |  | BSS | CRM |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
2113 | NOC426 | NOC | NA |  |  |  | BSS | Regulatory Compliance | Customer connections Weekly |  | Critical | OPEN |  | BSS | CRM |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
2114 | NOC427 | NOC | NA |  |  |  | BSS | Regulatory Compliance | Customer connections Monthly |  | Critical | OPEN |  | BSS | CRM |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
2115 | NOC428 | NOC | NA |  |  |  | BSS | Regulatory Compliance | Customer connections (Selective from and to dates) |  | Critical | OPEN |  | BSS | CRM |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
2116 | NOC429 | NOC | NA |  |  |  | BSS | Regulatory Compliance | Billing Daily |  | Critical | OPEN |  | BSS | Billing |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
2117 | NOC43 | NOC | NA |  | OSS | OSS | OSS | Service Assurance | Raised Proactive and reactive TT for all service deliverable sites and troubleshoot, escalation to field, follow up with field and resolve the issue Hourly |  | Critical | COMPLETED |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCOSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
2118 | NOC430 | NOC | NA |  |  |  | BSS | Regulatory Compliance | Billing Weekly |  | Critical | OPEN |  | BSS | Billing |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
2119 | NOC431 | NOC | NA |  |  |  | BSS | Regulatory Compliance | Billing Monthly |  | Critical | OPEN |  | BSS | Billing |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
2120 | NOC432 | NOC | NA |  |  |  | BSS | Regulatory Compliance | Billing (Selective from and to dates) |  | Critical | OPEN |  | BSS | Billing |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
2121 | NOC433 | NOC | NA |  |  |  | BSS | Regulatory Compliance | Waiver Daily |  | Critical | OPEN |  | BSS | Billing |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
2122 | NOC434 | NOC | NA |  |  |  | BSS | Regulatory Compliance | Waiver Weekly |  | Critical | OPEN |  | BSS | Billing |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
2123 | NOC435 | NOC | NA |  |  |  | BSS | Regulatory Compliance | Waiver Monthly |  | Critical | OPEN |  | BSS | Billing |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
2124 | NOC436 | NOC | NA |  |  |  | BSS | Regulatory Compliance | Waiver (Selective from and to dates) |  | Critical | OPEN |  | BSS | Billing |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
2125 | NOC437 | NOC | NA |  |  |  | IPDR | Regulatory | Customer data logs(Session with MAC) Daily |  | Critical |  |  | IPDR | IPDR |  |  |  |  | Jayant Madavi |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCIPDR | Applications/Tools | OPEN |  |  |  |  | Artefacts to be uploaded |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
2126 | NOC438 | NOC | NA |  |  |  | IPDR | Regulatory | Customer data logs(Session with MAC) Weekly |  | Critical |  |  | IPDR | IPDR |  |  |  |  | Jayant Madavi |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCIPDR | Applications/Tools | OPEN |  |  |  |  | Artefacts to be uploaded |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
2127 | NOC439 | NOC | NA |  |  |  | IPDR | Regulatory | Customer data logs(Session with MAC) Monthly |  | Critical |  |  | IPDR | IPDR |  |  |  |  | Jayant Madavi |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCIPDR | Applications/Tools | OPEN |  |  |  |  | Artefacts to be uploaded |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
2128 | NOC44 | NOC | NA |  | OSS | OSS | OSS | Service Assurance | Raised Proactive and reactive TT for all service deliverable sites and troubleshoot, escalation to field, follow up with field and resolve the issue Daily |  | Critical | COMPLETED |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCOSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
2129 | NOC440 | NOC | NA |  |  |  | IPDR | Regulatory | Customer data logs(Session with MAC) (Selective from and to dates) |  | Critical |  |  | IPDR | IPDR |  |  |  |  | Jayant Madavi |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCIPDR | Applications/Tools | OPEN |  |  |  |  | Artefacts to be uploaded |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
2130 | NOC441 | NOC | NA |  |  |  | BSS | Regulatory Compliance | Service Delivery TAT Dashboard and Reporting Daily |  | Critical | OPEN |  | BSS | CRM |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
2131 | NOC442 | NOC | NA |  |  |  | BSS | Regulatory Compliance | Service Delivery TAT Dashboard and Reporting Weekly |  | Critical | OPEN |  | BSS | CRM |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
2132 | NOC443 | NOC | NA |  |  |  | BSS | Regulatory Compliance | Service Delivery TAT Dashboard and Reporting Monthly |  | Critical | OPEN |  | BSS | CRM |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
2133 | NOC444 | NOC | NA |  |  |  | BSS | Regulatory Compliance | Service Delivery TAT Dashboard and Reporting (Selective from and to dates) |  | Critical | OPEN |  | BSS | CRM |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
2134 | NOC445 | NOC | NA |  | OSS | OSS | OSS | Service Monitoring | VLAN |  | Critical | OPEN |  | HPSM | Service Inventory |  | OPEN-DEPENDENT |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCOSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  | #N/A |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
2135 | NOC446 | NOC | NA |  | OSS | OSS | OSS | Service Monitoring | ONT Downlink Port(Service segregation 4- UPS, 1-4 for Services) |  | Critical | NOT_FEASIBLE |  | HPSM | Service Inventory |  |  |  |  | Suresh Pawar |  | Open | Not Feasible | [9 empty] | NOCOSS | Applications/Tools | #N/A | NOT-FEASIBLE | 0 |  |  | #N/A |  | 1 | Open | Open
2136 | NOC447 | NOC | NA |  | OSS | OSS | OSS | Service Monitoring | Service ID Mapping for UPS and Customer services |  | Critical | OPEN |  | HPSM | Service Inventory |  | OPEN-DEPENDENT |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCOSS | Applications/Tools | OPEN | OPEN-DEPENDENT | 0 |  |  | #N/A |  | 1 | Open | Open
2137 | NOC448 | NOC | NA |  |  |  | NSO | Service Provisioning | Service Provision using NSO Daily |  | Critical |  |  | NSO | SCCM |  |  |  |  | Jayant Madavi |  | Open | Open | [9 empty] | NOCNSO | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
2138 | NOC449 | NOC | NA |  |  |  | NSO | Service Provisioning | Service template configuration |  | Critical |  |  | NSO | SCCM |  |  |  |  | Jayant Madavi |  | Open | Open | [9 empty] | NOCNSO | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
2139 | NOC45 | NOC | NA |  | OSS | OSS | OSS | Service Assurance | Raised Proactive and reactive TT for all service deliverable sites and troubleshoot, escalation to field, follow up with field and resolve the issue Weekly |  | Critical | COMPLETED |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCOSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
2140 | NOC450 | NOC | NA |  |  |  | BSS | Service Provisioning | ILL(G2G) Daily |  | Critical | OPEN |  | BSS | CRM |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
2141 | NOC451 | NOC | NA |  |  |  | BSS | Service Provisioning | ILL(G2G) with QoS Daily |  | Critical | OPEN |  | BSS | CRM |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
2142 | NOC452 | NOC | NA |  |  |  | BSS | Service Provisioning | ILL(G2G) with QoS Weekly |  | Critical | COMPLETED |  | BSS | CRM |  | 09-09-2025: If IPMPLS Node interface for customer link then possible |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN | [6 empty] | 1 | Open | Open
2143 | NOC453 | NOC | NA |  |  |  | BSS | Service Provisioning | ILL(G2G) with QoS Monthly |  | Critical | OPEN |  | BSS | CRM |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
2144 | NOC454 | NOC | NA |  |  |  | BSS | Service Provisioning | ILL(G2G) with QoS (Selective from and to dates) |  | Critical | OPEN |  | BSS | CRM |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
2145 | NOC455 | NOC | NA |  |  |  | BSS | Service Provisioning | GI BB(G2G) Direct Bandwidth Daily |  | Critical | OPEN |  | BSS | CRM |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
2146 | NOC456 | NOC | NA |  |  |  | BSS | Service Provisioning | GI BB(G2G) Direct Bandwidth Weekly |  | Critical | COMPLETED |  | BSS | CRM |  | 09-09-2025: If IPMPLS Node interface for customer link then possible |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN | [6 empty] | 1 | Open | Open
2147 | NOC457 | NOC | NA |  |  |  | BSS | Service Provisioning | GI BB(G2G) Direct Bandwidth Monthly |  | Critical | OPEN |  | BSS | CRM |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
2148 | NOC458 | NOC | NA |  |  |  | BSS | Service Provisioning | GI BB(G2G) Direct Bandwidth (Selective from and to dates) |  | Critical | OPEN |  | BSS | CRM |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
2149 | NOC459 | NOC | NA |  |  |  | BSS | Service Provisioning | GI BB(G2G) Bandidth with QoS filtered Daily |  | Critical | OPEN |  | BSS | CRM |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
2150 | NOC46 | NOC | NA |  | OSS | OSS | OSS | Service Assurance | Raised Proactive and reactive TT for all service deliverable sites and troubleshoot, escalation to field, follow up with field and resolve the issue Monthly |  | Critical | COMPLETED |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCOSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
2151 | NOC460 | NOC | NA |  |  |  | BSS | Service Provisioning | GI BB(G2G) Bandidth with QoS filtered Weekly |  | Critical | COMPLETED |  | BSS | CRM |  | 09-09-2025: If IPMPLS Node interface for customer link then possible |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN | [6 empty] | 1 | Open | Open
2152 | NOC461 | NOC | NA |  |  |  | BSS | Service Provisioning | GI BB(G2G) Bandidth with QoS filtered Monthly |  | Critical | OPEN |  | BSS | CRM |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
2153 | NOC462 | NOC | NA |  |  |  | BSS | Service Provisioning | GI BB(G2G) Bandidth with QoS filtered (Selective from and to dates) |  | Critical | OPEN |  | BSS | CRM |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
2154 | NOC463 | NOC | NA |  |  |  | BSS | Service Provisioning | Dark Fiber Daily |  | Critical | OPEN |  | BSS | CRM |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
2155 | NOC464 | NOC | NA |  |  |  | BSS | Service Provisioning | Dark Fiber Weekly |  | Critical | OPEN |  | BSS | CRM |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
2156 | NOC465 | NOC | NA |  |  |  | BSS | Service Provisioning | Dark Fiber Monthly |  | Critical | OPEN |  | BSS | CRM |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
2157 | NOC466 | NOC | NA |  |  |  | BSS | Service Provisioning | Dark Fiber (Selective from and to dates) |  | Critical | OPEN |  | BSS | CRM |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
2158 | NOC467 | NOC | NA |  |  |  | BSS | Service Provisioning | Household(G2C) Daily |  | Critical | OPEN |  | BSS | CRM |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
2159 | NOC468 | NOC | NA |  |  |  | BSS | Service Provisioning | Household(G2C) Weekly |  | Critical | OPEN |  | BSS | CRM |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
2160 | NOC469 | NOC | NA |  |  |  | BSS | Service Provisioning | Household(G2C) Monthly |  | Critical | OPEN |  | BSS | CRM |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
2161 | NOC47 | NOC | NA |  | OSS | OSS | OSS | Service Assurance | Raised Proactive and reactive TT for all service deliverable sites and troubleshoot, escalation to field, follow up with field and resolve the issue (Selective from and to dates) |  | Critical | COMPLETED |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCOSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
2162 | NOC470 | NOC | NA |  |  |  | BSS | Service Provisioning | Household(G2C) (Selective from and to dates) |  | Critical | OPEN |  | BSS | CRM |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
2163 | NOC471 | NOC | NA |  |  |  | BSS | Service Provisioning | VPN(B2B) Daily |  | Critical | OPEN |  | BSS | CRM |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
2164 | NOC472 | NOC | NA |  |  |  | BSS | Service Provisioning | VPN(B2B) Weekly |  | Critical | OPEN |  | BSS | CRM |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
2165 | NOC473 | NOC | NA |  |  |  | BSS | Service Provisioning | VPN(B2B) Monthly |  | Critical | OPEN |  | BSS | CRM |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
2166 | NOC474 | NOC | NA |  |  |  | BSS | Service Provisioning | VPN(B2B) (Selective from and to dates) |  | Critical | OPEN |  | BSS | CRM |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
2167 | NOC475 | NOC | NA |  |  |  | BSS | Service Provisioning | VPN(B2B)with filtered QoS Daily |  | Critical | OPEN |  | BSS | CRM |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
2168 | NOC476 | NOC | NA |  |  |  | BSS | Service Provisioning | VPN(B2B)with filtered QoS Weekly |  | Critical | OPEN |  | BSS | CRM |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
2169 | NOC477 | NOC | NA |  |  |  | BSS | Service Provisioning | VPN(B2B)with filtered QoS Monthly |  | Critical | OPEN |  | BSS | CRM |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
2170 | NOC478 | NOC | NA |  |  |  | BSS | Service Provisioning | VPN(B2B)with filtered QoS (Selective from and to dates) |  | Critical | OPEN |  | BSS | CRM |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
2171 | NOC479 | NOC | NA |  |  |  | BSS | Service Provisioning | Enterprise(B2B) Daily |  | Critical | OPEN |  | BSS | CRM |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
2172 | NOC48 | NOC | NA |  |  |  | GPON | OSS | Summary Status of complete 424 Mandal OLTs ( Blocks ) of PKG-ABC Daily |  | Critical | COMPLETED |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCGPON | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
2173 | NOC480 | NOC | NA |  |  |  | BSS | Service Provisioning | Enterprise(B2B) Weekly |  | Critical | OPEN |  | BSS | CRM |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
2174 | NOC481 | NOC | NA |  |  |  | BSS | Service Provisioning | Enterprise(B2B) Monthly |  | Critical | OPEN |  | BSS | CRM |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
2175 | NOC482 | NOC | NA |  |  |  | BSS | Service Provisioning | Enterprise(B2B) (Selective from and to dates) |  | Critical | OPEN |  | BSS | CRM |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
2176 | NOC483 | NOC | NA |  |  |  | BSS | Service Provisioning | Enterprise(B2B) with filtered QoS Daily |  | Critical | OPEN |  | BSS | CRM |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
2177 | NOC484 | NOC | NA |  |  |  | BSS | Service Provisioning | Enterprise(B2B) with filtered QoS Weekly |  | Critical | OPEN |  | BSS | CRM |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
2178 | NOC485 | NOC | NA |  |  |  | BSS | Service Provisioning | Enterprise(B2B) with filtered QoS Monthly |  | Critical | OPEN |  | BSS | CRM |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
2179 | NOC486 | NOC | NA |  |  |  | BSS | Service Provisioning | Enterprise(B2B) with filtered QoS (Selective from and to dates) |  | Critical | OPEN |  | BSS | CRM |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
2180 | NOC487 | NOC | NA |  |  |  | BSS | Service Provisioning | Partner(B2B2C) Daily |  | Critical | COMPLETED |  | BSS | CRM |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN | [6 empty] | 1 | Open | Open
2181 | NOC488 | NOC | NA |  |  |  | BSS | Service Provisioning | Partner(B2B2C) Weekly |  | Critical | COMPLETED |  | BSS | CRM |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN | [6 empty] | 1 | Open | Open
2182 | NOC489 | NOC | NA |  |  |  | BSS | Service Provisioning | Partner(B2B2C) Monthly |  | Critical | COMPLETED |  | BSS | CRM |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN | [6 empty] | 1 | Open | Open
2183 | NOC49 | NOC | NA |  |  |  | GPON | OSS | Summary Status of complete 424 Mandal OLTs ( Blocks ) of PKG-ABC Weekly |  | Critical | NOT_FEASIBLE |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  | Open | Not Feasible | [9 empty] | NOCGPON | Applications/Tools | #N/A | NOT-FEASIBLE | Live data -bothUOC and POWErbi |  |  | #N/A |  | 1 | Open | Open
2184 | NOC490 | NOC | NA |  |  |  | BSS | Service Provisioning | Partner(B2B2C) (Selective from and to dates) |  | Critical | COMPLETED |  | BSS | CRM |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN | [6 empty] | 1 | Open | Open
2185 | NOC491 | NOC | NA |  |  |  | BSS | Service Provisioning | Partner(B2B2C) with Filtered QoS Daily |  | Critical | OPEN |  | BSS | CRM |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
2186 | NOC492 | NOC | NA |  |  |  | BSS | Service Provisioning | Partner(B2B2C) with Filtered QoS Weekly |  | Critical | OPEN |  | BSS | CRM |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
2187 | NOC493 | NOC | NA |  |  |  | BSS | Service Provisioning | Partner(B2B2C) with Filtered QoS Monthly |  | Critical | OPEN |  | BSS | CRM |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
2188 | NOC494 | NOC | NA |  |  |  | BSS | Service Provisioning | Partner(B2B2C) with Filtered QoS (Selective from and to dates) |  | Critical | OPEN |  | BSS | CRM |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
2189 | NOC495 | NOC | NA |  |  |  | BSS | Service Provisioning | T-cell (P2MP) Daily |  | Critical | OPEN |  | BSS | CRM |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
2190 | NOC496 | NOC | NA |  |  |  | BSS | Service Provisioning | T-cell (P2MP) Weekly |  | Critical | OPEN |  | BSS | CRM |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
2191 | NOC497 | NOC | NA |  |  |  | BSS | Service Provisioning | T-cell (P2MP) Monthly |  | Critical | OPEN |  | BSS | CRM |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
2192 | NOC498 | NOC | NA |  |  |  | BSS | Service Provisioning | T-cell (P2MP) (Selective from and to dates) |  | Critical | OPEN |  | BSS | CRM |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
2193 | NOC499 | NOC | NA |  |  |  | BSS | Service Provisioning | T-cell P2MP with Filtered QoS Daily |  | Critical | OPEN |  | BSS | CRM |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
2194 | NOC5 | NOC | NA |  | OSS | OSS | OSS | DC | DC Applications uptime & SLA Daily |  | Critical |  |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCOSS | Applications/Tools | OPEN | OPEN | 0 |  |  | #N/A |  | 1 | Open | Open
2195 | NOC50 | NOC | NA |  |  |  | GPON | OSS | Summary Status of complete 424 Mandal OLTs ( Blocks ) of PKG-ABC Monthly |  | Critical | COMPLETED |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCGPON | Applications/Tools | OPEN | COMPLETED | only Live data |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
2196 | NOC500 | NOC | NA |  |  |  | BSS | Service Provisioning | T-cell P2MP with Filtered QoS Weekly |  | Critical | OPEN |  | BSS | CRM |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
2197 | NOC501 | NOC | NA |  |  |  | BSS | Service Provisioning | T-cell P2MP with Filtered QoS Monthly |  | Critical | OPEN |  | BSS | CRM |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
2198 | NOC502 | NOC | NA |  |  |  | BSS | Service Provisioning | T-cell P2MP with Filtered QoS (Selective from and to dates) |  | Critical | OPEN |  | BSS | CRM |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
2199 | NOC503 | NOC | NA |  |  |  | BSS | Service Provisioning | T-cell (P2P) Daily |  | Critical | OPEN |  | BSS | CRM |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
2200 | NOC504 | NOC | NA |  |  |  | BSS | Service Provisioning | T-cell (P2P) Weekly |  | Critical | OPEN |  | BSS | CRM |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
2201 | NOC505 | NOC | NA |  |  |  | BSS | Service Provisioning | T-cell (P2P) Monthly |  | Critical | OPEN |  | BSS | CRM |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
2202 | NOC506 | NOC | NA |  |  |  | BSS | Service Provisioning | T-cell (P2P) (Selective from and to dates) |  | Critical | OPEN |  | BSS | CRM |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
2203 | NOC507 | NOC | NA |  |  |  | BSS | Service Provisioning | T-cell P2P with Filtered QoS Daily |  | Critical | OPEN |  | BSS | CRM |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
2204 | NOC508 | NOC | NA |  |  |  | BSS | Service Provisioning | T-cell P2P with Filtered QoS Weekly |  | Critical | OPEN |  | BSS | CRM |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
2205 | NOC509 | NOC | NA |  |  |  | BSS | Service Provisioning | T-cell P2P with Filtered QoS Monthly |  | Critical | OPEN |  | BSS | CRM |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
2206 | NOC51 | NOC | NA |  |  |  | GPON | OSS | Summary Status of complete 424 Mandal OLTs ( Blocks ) of PKG-ABC (Selective from and to dates) |  | Critical | COMPLETED |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCGPON | Applications/Tools | OPEN | COMPLETED | Live data |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
2207 | NOC510 | NOC | NA |  |  |  | BSS | Service Provisioning | T-cell P2P with Filtered QoS (Selective from and to dates) |  | Critical | OPEN |  | BSS | CRM |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
2208 | NOC511 | NOC | NA |  | OSS | OSS | OSS and NSO | Service Provisioning | Bandwidth Feasibility for New Provisioning, Exising configured bandwidth to be made available at OSS Daily |  | Critical | OPEN |  | OSS and NSO | Service Inventory, SCCM |  | 14-09-2025: We can get this report from BSS by downloading services provisioned for the perticular week |  |  | Jayant Madavi |  | Open | WIP | [9 empty] | NOCOSS and NSO | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
2209 | NOC512 | NOC | NA |  | OSS | OSS | OSS and NSO | Service Provisioning | Bandwidth Feasibility for New Provisioning, Exising configured bandwidth to be made available at OSS Weekly |  | Critical | OPEN |  | OSS and NSO | Service Inventory, SCCM |  | 14-09-2025: We can get this report from BSS by downloading services provisioned for the perticular week |  |  | Jayant Madavi |  | Open | WIP | [9 empty] | NOCOSS and NSO | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
2210 | NOC513 | NOC | NA |  | OSS | OSS | OSS and NSO | Service Provisioning | Bandwidth Feasibility for New Provisioning, Exising configured bandwidth to be made available at OSS Monthly |  | Critical | OPEN |  | OSS and NSO | Service Inventory, SCCM |  | 14-09-2025: We can get this report from BSS by downloading services provisioned for the perticular month |  |  | Jayant Madavi |  | Open | WIP | [9 empty] | NOCOSS and NSO | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
2211 | NOC514 | NOC | NA |  | OSS | OSS | OSS and NSO | Service Provisioning | Bandwidth Feasibility for New Provisioning, Exising configured bandwidth to be made available at OSS (Selective from and to dates) |  | Critical | OPEN |  | OSS and NSO | Service Inventory, SCCM |  | 14-09-2025: We can get this report from BSS by downloading services provisioned for the selected period |  |  | Jayant Madavi |  | Open | WIP | [9 empty] | NOCOSS and NSO | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
2212 | NOC515 | NOC | NA |  | OSS | OSS | OSS | Service Provisioning | Capacity augmentationn based on Feasible/NON- Feasible status count and required bandwidth Daily |  | Critical | COMPLETED |  | OSS | Service Inventory, UTM |  | 09-09-2025: Desired output will be shown through BSS but actual data is fetching from the OSS (UTM +GIS). |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCOSS | Applications/Tools | OPEN | COMPLETED | 09-09-2025: Desired output will be shown through BSS but actual data is fetching from the OSS (UTM +GIS). |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
2213 | NOC516 | NOC | NA |  | OSS | OSS | OSS | Service Provisioning | Capacity augmentationn based on Feasible/NON- Feasible status count and required bandwidth Weekly |  | Critical | NOT_FEASIBLE |  | OSS | Service Inventory, UTM |  |  |  |  | Suresh Pawar |  | Open | Not Feasible | [9 empty] | NOCOSS | Applications/Tools | #N/A | NOT-FEASIBLE | 0 |  |  | #N/A |  | 1 | Open | Open
2214 | NOC517 | NOC | NA |  | OSS | OSS | OSS | Service Provisioning | Capacity augmentationn based on Feasible/NON- Feasible status count and required bandwidth Monthly |  | Critical | COMPLETED |  | OSS | Service Inventory, UTM |  | 09-09-2025: Desired output will be shown through BSS but actual data is fetching from the OSS (UTM +GIS). |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCOSS | Applications/Tools | OPEN | COMPLETED | 09-09-2025: Desired output will be shown through BSS but actual data is fetching from the OSS (UTM +GIS). |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
2215 | NOC518 | NOC | NA |  | OSS | OSS | OSS | Service Provisioning | Capacity augmentationn based on Feasible/NON- Feasible status count and required bandwidth (Selective from and to dates) |  | Critical | COMPLETED |  | OSS | Service Inventory, UTM |  | 09-09-2025: Desired output will be shown through BSS but actual data is fetching from the OSS (UTM +GIS). |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCOSS | Applications/Tools | OPEN | COMPLETED | 09-09-2025: Desired output will be shown through BSS but actual data is fetching from the OSS (UTM +GIS). |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
2216 | NOC519 | NOC | NA |  |  |  | WFM | WFM | User level view for Number of tasks assigned/resolved/closed Daily |  | Critical |  |  | WFM | Corrective |  | Development Completed & Reports are available |  |  | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCWFM | Applications/Tools | OPEN | [6 empty] | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
2217 | NOC52 | NOC | NA |  |  |  | GPON | OSS | Summary of Lit-up GPs Status_8894 as on 14-05-2025_4PM(Revised) Daily |  | Critical | COMPLETED |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCGPON | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
2218 | NOC520 | NOC | NA |  |  |  | WFM | WFM | User level view for Number of tasks assigned/resolved/closed Weekly |  | Critical |  |  | WFM | Incident Management |  | Development Completed & Reports are available |  |  | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCWFM | Applications/Tools | OPEN | [6 empty] | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
2219 | NOC521 | NOC | NA |  |  |  | WFM | WFM | User level view for Number of tasks assigned/resolved/closed Monthly |  | Critical |  |  | WFM | Incident Management |  | Development Completed & Reports are available |  |  | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCWFM | Applications/Tools | OPEN | [6 empty] | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
2220 | NOC522 | NOC | NA |  |  |  | WFM | WFM | User level view for Number of tasks assigned/resolved/closed (Selective from and to dates) |  | Critical |  |  | WFM | Smart track |  | Development Completed & Reports are available |  |  | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCWFM | Applications/Tools | OPEN | [6 empty] | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
2221 | NOC523 | NOC | NA |  |  |  | WFM | WFM | Management Dashboard Patroller Daily |  | Critical |  |  | WFM | Smart track |  | The development is complete and can be demonstrated through three methods: reports, dashboards, and single-click interaction on the map |  |  | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCWFM | Applications/Tools | OPEN | [6 empty] | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
2222 | NOC524 | NOC | NA |  |  |  | WFM | WFM | Management Dashboard Patroller Weekly |  | Critical |  |  | WFM | Smart track |  | The development is complete and can be demonstrated through three methods: reports, dashboards, and single-click interaction on the map |  |  | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCWFM | Applications/Tools | OPEN | [6 empty] | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
2223 | NOC525 | NOC | NA |  |  |  | WFM | WFM | Management Dashboard Patroller Monthly |  | Critical |  |  | WFM | Smart track |  | The development is complete and can be demonstrated through three methods: reports, dashboards, and single-click interaction on the map |  |  | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCWFM | Applications/Tools | OPEN | [6 empty] | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
2224 | NOC526 | NOC | NA |  |  |  | WFM | WFM | Management Dashboard Patroller (Selective from and to dates) |  | Critical |  |  | WFM | Smart track |  | The development is complete and can be demonstrated through three methods: reports, dashboards, and single-click interaction on the map |  |  | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCWFM | Applications/Tools | OPEN | [6 empty] | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
2225 | NOC527 | NOC | NA |  |  |  | WFM | WFM | Management Dashboard FRT Daily |  | Critical |  |  | WFM | Smart track |  | The development is complete and can be demonstrated through three methods: reports, dashboards, and single-click interaction on the map |  |  | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCWFM | Applications/Tools | OPEN | [6 empty] | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
2226 | NOC528 | NOC | NA |  |  |  | WFM | WFM | Management Dashboard FRT Weekly |  | Critical |  |  | WFM | Smart track |  | The development is complete and can be demonstrated through three methods: reports, dashboards, and single-click interaction on the map |  |  | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCWFM | Applications/Tools | OPEN | [6 empty] | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
2227 | NOC529 | NOC | NA |  |  |  | WFM | WFM | Management Dashboard FRT Monthly |  | Critical |  |  | WFM | Smart track |  | The development is complete and can be demonstrated through three methods: reports, dashboards, and single-click interaction on the map |  |  | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCWFM | Applications/Tools | OPEN | [6 empty] | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
2228 | NOC53 | NOC | NA |  |  |  | GPON | OSS | Summary of Lit-up GPs Status_8894 as on 14-05-2025_4PM(Revised) Weekly |  | Critical | NOT_FEASIBLE |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  | Open | Not Feasible | [9 empty] | NOCGPON | Applications/Tools | #N/A | NOT-FEASIBLE | 0 |  |  | #N/A |  | 1 | Open | Open
2229 | NOC530 | NOC | NA |  |  |  | WFM | WFM | Management Dashboard FRT (Selective from and to dates) |  | Critical |  |  | WFM | Smart track |  | The development is complete and can be demonstrated through three methods: reports, dashboards, and single-click interaction on the map |  |  | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCWFM | Applications/Tools | OPEN | [6 empty] | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
2230 | NOC531 | NOC | NA |  |  |  | WFM | WFM | Management Dashboard Engineers Daily |  | Critical |  |  | WFM | Smart track |  | The development is complete and can be demonstrated through three methods: reports, dashboards, and single-click interaction on the map |  |  | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCWFM | Applications/Tools | OPEN | [6 empty] | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
2231 | NOC532 | NOC | NA |  |  |  | WFM | WFM | Management Dashboard Engineers Weekly |  | Critical |  |  | WFM | Smart track |  | The development is complete and can be demonstrated through three methods: reports, dashboards, and single-click interaction on the map |  |  | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCWFM | Applications/Tools | OPEN | [6 empty] | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
2232 | NOC533 | NOC | NA |  |  |  | WFM | WFM | Management Dashboard Engineers Monthly |  | Critical |  |  | WFM | Smart track |  | The development is complete and can be demonstrated through three methods: reports, dashboards, and single-click interaction on the map |  |  | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCWFM | Applications/Tools | OPEN | [6 empty] | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
2233 | NOC534 | NOC | NA |  |  |  | WFM | WFM | Management Dashboard Engineers (Selective from and to dates) |  | Critical |  |  | WFM | Smart track |  | The development is complete and can be demonstrated through three methods: reports, dashboards, and single-click interaction on the map |  |  | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCWFM | Applications/Tools | OPEN | [6 empty] | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
2234 | NOC535 | NOC | NA |  |  |  | Helpdesk | BSS | Integration to be Aligned with Approved IVR flow(All Customers) Daily |  | NON-Critical |  |  | BSS | CRM | WIP | IVR Flows Submitted for Approval |  |  | Siva Kumar |  | Open | WIP | [9 empty] | NOCHelpdesk | Applications/Tools | OPEN | [6 empty] | 1 | Open | Open
2235 | NOC536 | NOC | NA |  |  |  | Helpdesk | BSS | Integration to be Aligned with Approved IVR flow(All Customers) Weekly |  | NON-Critical |  |  | BSS | CRM | WIP | IVR Flows Submitted for Approval |  |  | Siva Kumar |  | Open | WIP | [9 empty] | NOCHelpdesk | Applications/Tools | OPEN | [6 empty] | 1 | Open | Open
2236 | NOC537 | NOC | NA |  |  |  | Helpdesk | BSS | Integration to be Aligned with Approved IVR flow(All Customers) Monthly |  | NON-Critical |  |  | BSS | CRM | WIP | IVR Flows Submitted for Approval |  |  | Siva Kumar |  | Open | WIP | [9 empty] | NOCHelpdesk | Applications/Tools | OPEN | [6 empty] | 1 | Open | Open
2237 | NOC538 | NOC | NA |  |  |  | Helpdesk | BSS | Integration to be Aligned with Approved IVR flow(All Customers) (Selective from and to dates) |  | NON-Critical |  |  | BSS | CRM | WIP | IVR Flows Submitted for Approval |  |  | Siva Kumar |  | Open | WIP | [9 empty] | NOCHelpdesk | Applications/Tools | OPEN | [6 empty] | 1 | Open | Open
2238 | NOC539 | NOC | NA |  |  |  | Helpdesk | BSS | Integration to be Aligned with Approved IVR flow(All Enterprise) Daily |  | NON-Critical |  |  | BSS | CRM | WIP | IVR Flows Submitted for Approval |  |  | Siva Kumar |  | Open | WIP | [9 empty] | NOCHelpdesk | Applications/Tools | OPEN | [6 empty] | 1 | Open | Open
2239 | NOC54 | NOC | NA |  |  |  | GPON | OSS | Summary of Lit-up GPs Status_8894 as on 14-05-2025_4PM(Revised) Monthly |  | Critical | NOT_FEASIBLE |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  | Open | Not Feasible | [9 empty] | NOCGPON | Applications/Tools | #N/A | NOT-FEASIBLE | 0 |  |  | #N/A |  | 1 | Open | Open
2240 | NOC540 | NOC | NA |  |  |  | Helpdesk | BSS | Integration to be Aligned with Approved IVR flow(All Enterprise) Weekly |  | NON-Critical |  |  | BSS | CRM | WIP | IVR Flows Submitted for Approval |  |  | Siva Kumar |  | Open | WIP | [9 empty] | NOCHelpdesk | Applications/Tools | OPEN | [6 empty] | 1 | Open | Open
2241 | NOC541 | NOC | NA |  |  |  | Helpdesk | BSS | Integration to be Aligned with Approved IVR flow(All Enterprise) Monthly |  | NON-Critical |  |  | BSS | CRM | WIP | IVR Flows Submitted for Approval |  |  | Siva Kumar |  | Open | WIP | [9 empty] | NOCHelpdesk | Applications/Tools | OPEN | [6 empty] | 1 | Open | Open
2242 | NOC542 | NOC | NA |  |  |  | Helpdesk | BSS | Integration to be Aligned with Approved IVR flow(All Enterprise) (Selective from and to dates) |  | NON-Critical |  |  | BSS | CRM | WIP | IVR Flows Submitted for Approval |  |  | Siva Kumar |  | Open | WIP | [9 empty] | NOCHelpdesk | Applications/Tools | OPEN | [6 empty] | 1 | Open | Open
2243 | NOC543 | NOC | NA |  |  |  | Helpdesk | BSS | Integration to be Aligned with Approved IVR flow(All Partners) Daily |  | NON-Critical |  |  | BSS | CRM | WIP | IVR Flows Submitted for Approval |  |  | Siva Kumar |  | Open | WIP | [9 empty] | NOCHelpdesk | Applications/Tools | OPEN | [6 empty] | 1 | Open | Open
2244 | NOC544 | NOC | NA |  |  |  | Helpdesk | BSS | Integration to be Aligned with Approved IVR flow(All Partners) Weekly |  | NON-Critical |  |  | BSS | CRM | WIP | IVR Flows Submitted for Approval |  |  | Siva Kumar |  | Open | WIP | [9 empty] | NOCHelpdesk | Applications/Tools | OPEN | [6 empty] | 1 | Open | Open
2245 | NOC545 | NOC | NA |  |  |  | Helpdesk | BSS | Integration to be Aligned with Approved IVR flow(All Partners) Monthly |  | NON-Critical |  |  | BSS | CRM | WIP | IVR Flows Submitted for Approval |  |  | Siva Kumar |  | Open | WIP | [9 empty] | NOCHelpdesk | Applications/Tools | OPEN | [6 empty] | 1 | Open | Open
2246 | NOC546 | NOC | NA |  |  |  | Helpdesk | BSS | Integration to be Aligned with Approved IVR flow(All Partners) (Selective from and to dates) |  | NON-Critical |  |  | BSS | CRM | WIP | IVR Flows Submitted for Approval |  |  | Siva Kumar |  | Open | WIP | [9 empty] | NOCHelpdesk | Applications/Tools | OPEN | [6 empty] | 1 | Open | Open
2247 | NOC547 | NOC | NA |  |  |  | Helpdesk | OSS | Integration to be Aligned with Approved IVR flow(MSI) Daily |  | NON-Critical |  |  | HPSM | Incident Management | WIP | IVR Flows Submitted for Approval |  |  | Siva Kumar |  | Open | WIP | [9 empty] | NOCHelpdesk | Applications/Tools | OPEN | [6 empty] | 1 | Open | Open
2248 | NOC548 | NOC | NA |  |  |  | Helpdesk | OSS | Integration to be Aligned with Approved IVR flow(MSI) Weekly |  | NON-Critical |  |  | HPSM | Incident Management | WIP | IVR Flows Submitted for Approval |  |  | Siva Kumar |  | Open | WIP | [9 empty] | NOCHelpdesk | Applications/Tools | OPEN | [6 empty] | 1 | Open | Open
2249 | NOC549 | NOC | NA |  |  |  | Helpdesk | OSS | Integration to be Aligned with Approved IVR flow(MSI) Monthly |  | NON-Critical |  |  | HPSM | Incident Management | WIP | IVR Flows Submitted for Approval |  |  | Siva Kumar |  | Open | WIP | [9 empty] | NOCHelpdesk | Applications/Tools | OPEN | [6 empty] | 1 | Open | Open
2250 | NOC55 | NOC | NA |  |  |  | GPON | OSS | Summary of Lit-up GPs Status_8894 as on 14-05-2025_4PM(Revised) (Selective from and to dates) |  | Critical | NOT_FEASIBLE |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  | Open | Not Feasible | [9 empty] | NOCGPON | Applications/Tools | #N/A | NOT-FEASIBLE | 0 |  |  | #N/A |  | 1 | Open | Open
2251 | NOC550 | NOC | NA |  |  |  | Helpdesk | OSS | Integration to be Aligned with Approved IVR flow(MSI) (Selective from and to dates) |  | NON-Critical |  |  | HPSM | Incident Management | WIP | IVR Flows Submitted for Approval |  |  | Siva Kumar |  | Open | WIP | [9 empty] | NOCHelpdesk | Applications/Tools | OPEN | [6 empty] | 1 | Open | Open
2252 | NOC551 | NOC | NA |  |  |  | Helpdesk | OSS | Integration to be Aligned with Approved IVR flow(NOC) Daily |  | NON-Critical |  |  | HPSM | Incident Management | WIP | IVR Flows Submitted for Approval |  |  | Siva Kumar |  | Open | WIP | [9 empty] | NOCHelpdesk | Applications/Tools | OPEN | [6 empty] | 1 | Open | Open
2253 | NOC552 | NOC | NA |  |  |  | Helpdesk | OSS | Integration to be Aligned with Approved IVR flow(NOC) Weekly |  | NON-Critical |  |  | HPSM | Incident Management | WIP | IVR Flows Submitted for Approval |  |  | Siva Kumar |  | Open | WIP | [9 empty] | NOCHelpdesk | Applications/Tools | OPEN | [6 empty] | 1 | Open | Open
2254 | NOC553 | NOC | NA |  |  |  | Helpdesk | OSS | Integration to be Aligned with Approved IVR flow(NOC) Monthly |  | NON-Critical |  |  | HPSM | Incident Management | WIP | IVR Flows Submitted for Approval |  |  | Siva Kumar |  | Open | WIP | [9 empty] | NOCHelpdesk | Applications/Tools | OPEN | [6 empty] | 1 | Open | Open
2255 | NOC554 | NOC | NA |  |  |  | Helpdesk | OSS | Integration to be Aligned with Approved IVR flow(NOC) (Selective from and to dates) |  | NON-Critical |  |  | HPSM | Incident Management | WIP | IVR Flows Submitted for Approval |  |  | Siva Kumar |  | Open | WIP | [9 empty] | NOCHelpdesk | Applications/Tools | OPEN | [6 empty] | 1 | Open | Open
2256 | NOC555 | NOC | NA |  |  |  | NSO | Service Provisioning | VLAN Planning |  | Critical | OPEN |  | NSO | SCCM/Playbook |  |  |  |  | Jayant Madavi |  | Open | Open | [9 empty] | NOCNSO | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
2257 | NOC556 | NOC | NA |  |  |  | NSO | Service Provisioning | IPV4 and IPV6 Planning |  | Critical | OPEN |  | NSO | SCCM/Playbook |  |  |  |  | Jayant Madavi |  | Open | Open | [9 empty] | NOCNSO | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
2258 | NOC557 | NOC | NA |  |  |  | BSS | Service Provisioning | Migration of Existing customers provision via BSS-NSO |  | Critical | OPEN |  | BSS, NSO | CRM, SCCM |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
2259 | NOC558 | NOC | NA |  | OSS | OSS | All Domain | OSS | TT should not be generated for planned event window and Affected CI |  | Critical | OPEN |  | HPSM | Change Management |  |  |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCAll Domain | Applications/Tools | OPEN | OPEN | 0 |  |  | #N/A |  | 1 | Open | Open
2260 | NOC559 | NOC | NA |  | OSS | OSS | All Domain | OSS | Planned event to be rejected/Postponed incase another side Ring is open |  | Critical | COMPLETED |  | HPSM | Change Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCAll Domain | Applications/Tools | OPEN | COMPLETED | consider SS from mail |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
2261 | NOC56 | NOC | NA |  |  |  | GPON | OSS | T-NOC Report :: Summary of O&M Cluster OLTs status Daily |  | Critical | COMPLETED |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCGPON | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
2262 | NOC560 | NOC | NA |  |  |  | WFM | WFM | Field Remarks like ETR, RFO updation pending against Open Task |  | Critical |  |  | WFM | Smart track |  |  |  |  | Kaushalendra Kumar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCWFM | Applications/Tools | OPEN | [6 empty] | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
2263 | NOC561 | NOC | NA |  |  |  | WFM | WFM | Field team working without events and as a part of corrective actions at Passive |  | Critical |  |  | WFM | Smart track |  | 11-7-2025:- SM & WFM Intigration is WIP |  |  | Kaushalendra Kumar |  | Open | WIP | [9 empty] | NOCWFM | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
2264 | NOC562 | NOC | NA |  | OSS | OSS&WFM | OSS | OSS | Auto Escalation Matrix |  | Critical |  |  | HPSM | Incident Management |  | 09-09-2025: its configurable item and can be modified on demand |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCOSS | Applications/Tools | OPEN | COMPLETED | 09-09-2025: its configurable item and can be modified on demand |  |  | Artefacts to be uploaded |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
2265 | NOC563 | NOC | NA |  | OSS | OSS | All Domain | OSS | Configutable paramters for SLA |  | Critical | COMPLETED |  | NNMI | NPS |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCAll Domain | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
2266 | NOC564 | NOC | NA |  |  |  | GPON | GPON | Requested Tejas to enable the TR-069 for T-Fiber deployed elements |  | Critical |  |  | Tejas OEM | ONT |  | Duplicate point of 472 - 399 | Duplicate |  | Sayyad Pasha |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | NOCGPON | Applications/Tools | OPEN |  |  | Duplicate |  |  |  | 1 | Open | Open
2267 | NOC565 | NOC | NA |  |  |  | GPON | GPON | CIR/PIR in OLT/EMS |  | Critical |  |  | Tejas OEM | EMS/OLT |  | Duplicate point of 472 - 407 | Duplicate |  | Sayyad Pasha |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | NOCGPON | Applications/Tools | OPEN |  |  | Duplicate |  |  |  | 1 | Open | Open
2268 | NOC566 | NOC | NA |  |  |  | GPON | GPON | Unable to modify the Service Name |  | Critical |  |  | Tejas OEM | EMS |  |  |  |  | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-07-03 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\409 | [6 empty] | NOCGPON | Applications/Tools | CLOSED |  |  |  | 2025-07-03 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\409 |  | 1 | Completed & Approved | Closed after June
2269 | NOC567 | NOC | NA |  |  |  | GPON | GPON | Live PM monitoring per UNI in EMS service Window |  | Critical |  |  | Tejas OEM | EMS |  |  |  |  | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-07-10 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\416 | [6 empty] | NOCGPON | Applications/Tools | CLOSED |  |  |  | 2025-07-10 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\416 |  | 1 | Completed & Approved | Closed after June
2270 | NOC568 | NOC | NA |  |  |  | GPON | GPON | Unable to Enable PM from EMS |  | Critical |  |  | Tejas OEM | EMS |  |  |  |  | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-07-07 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\414 | [6 empty] | NOCGPON | Applications/Tools | CLOSED |  |  |  | 2025-07-07 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\414 |  | 1 | Completed & Approved | Closed after June
2271 | NOC569 | NOC | NA |  |  |  | GPON | GPON | While creating service profile, maximum bandwidth is not taking 1024000 only considering 1000000 |  | Critical |  |  | Tejas OEM | EMS |  |  |  |  | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-07-31 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\417 | [6 empty] | NOCGPON | Applications/Tools | CLOSED |  |  |  | 2025-07-31 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\417 |  | 1 | Completed & Approved | Closed after June
2272 | NOC57 | NOC | NA |  |  |  | GPON | OSS | T-NOC Report :: Summary of O&M Cluster OLTs status Weekly |  | Critical | NOT_FEASIBLE |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  | Open | Not Feasible | [9 empty] | NOCGPON | Applications/Tools | #N/A | NOT-FEASIBLE | 0 |  |  | #N/A |  | 1 | Open | Open
2273 | NOC570 | NOC | NA |  |  |  | GPON | GPON | OLT Node not reachable alarm clearance and regeneration |  | Critical |  |  | Tejas OEM | EMS |  |  |  |  | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-07-05 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\425 | [6 empty] | NOCGPON | Applications/Tools | CLOSED |  |  |  | 2025-07-05 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\425 |  | 1 | Completed & Approved | Closed after June
2274 | NOC571 | NOC | NA |  |  |  | GPON | GPON | while adding uni in EMS, list of downstream profiles are highlighting in the bottom |  | Critical |  |  | Tejas OEM | EMS |  |  |  |  | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-07-05 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\430 | [6 empty] | NOCGPON | Applications/Tools | CLOSED |  |  |  | 2025-07-05 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\430 |  | 1 | Completed & Approved | Closed after June
2275 | NOC572 | NOC | NA |  |  |  | GPON | GPON | Nokia ONT ethernet port status is not updating |  | Critical |  |  | Tejas OEM | ONT |  | Duplicate point of 472 - 432 | Duplicate |  | Sayyad Pasha |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | NOCGPON | Applications/Tools | OPEN |  |  | Duplicate |  |  |  | 1 | Open | Open
2276 | NOC573 | NOC | NA |  |  |  | GPON | GPON | Tejas ONT Software Upgrade which are connected under Nokia OLT |  | Critical |  |  | Tejas OEM | ONT |  | Duplicate point of 472 - 433 | Duplicate |  | Sayyad Pasha |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | NOCGPON | Applications/Tools | OPEN |  |  | Duplicate |  |  |  | 1 | Open | Open
2277 | NOC574 | NOC | NA |  |  |  | GPON | GPON | API for GI-BB Service, combo port, mixed service - Route Mode with/without translation, including uplink port configuration |  | Critical |  |  | Tejas OEM | EMS |  |  |  |  | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-08-06 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\442 | [6 empty] | NOCGPON | Applications/Tools | CLOSED |  |  |  | 2025-08-06 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\442 |  | 1 | Completed & Approved | Closed after June
2278 | NOC575 | NOC | NA |  |  |  | GPON | GPON | API for TDIA Service, combo port, mixed service - Route Mode with/without translation, including uplink port configuration |  | Critical |  |  | Tejas OEM | EMS |  |  |  |  | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API | [6 empty] | NOCGPON | Applications/Tools | CLOSED |  |  |  | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API |  | 1 | Completed & Approved | Closed after June
2279 | NOC576 | NOC | NA |  |  |  | GPON | GPON | API to restirct/block the PON port to a specific customer |  | Critical |  |  | Tejas OEM | EMS |  | OEM confirmed API will be made availble in next release of EMS on March-2026 | Tejas & Nokia | Deepak and Sivakasi | Sayyad Pasha |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | NOCGPON | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
2280 | NOC577 | NOC | NA |  |  |  | GPON | GPON | API to modify the service- ONT, UNI Port, bandwidth, vlan, description, unatgged to tag or vice versa., |  | Critical |  |  | Tejas OEM | EMS |  | Duplicate point of 472 - 463 | Duplicate |  | Sayyad Pasha |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | NOCGPON | Applications/Tools | OPEN |  |  | Duplicate |  |  |  | 1 | Open | Open
2281 | NOC578 | NOC | NA |  |  |  | GPON | GPON | PIR not working in route mode |  | Critical |  |  | Tejas OEM | OLT |  | Duplicate point of 472 - 407 | Duplicate |  | Sayyad Pasha |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | NOCGPON | Applications/Tools | OPEN |  |  | Duplicate |  | #N/A |  | 1 | Open | Open
2282 | NOC579 | NOC | NA |  |  |  | GPON | GPON | Nokia ONT/3rd party ONT under Tejas OLT Remote access for WAN port |  | Critical |  |  | Tejas OEM | OLT/ONT |  | OEM confirmed this feature is not available 20-Sep-25: T Fiber team asked to arrange meeting with Tejas, Nokia OEM | Tejas & Nokia | Deepak and Sivakasi | Sayyad Pasha |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | NOCGPON | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
2283 | NOC58 | NOC | NA |  |  |  | GPON | OSS | T-NOC Report :: Summary of O&M Cluster OLTs status Monthly |  | Critical | NOT_FEASIBLE |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  | Open | Not Feasible | [9 empty] | NOCGPON | Applications/Tools | #N/A | NOT-FEASIBLE | 0 |  |  | #N/A |  | 1 | Open | Open
2284 | NOC580 | NOC | NA |  |  |  | GPON | GPON | Unable to browse Internet when IPV6 configured in wifi ONT |  | Critical |  |  | Nokia OEM | AMS |  |  |  |  | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-07-31 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\472 | [6 empty] | NOCGPON | Applications/Tools | CLOSED |  |  |  | 2025-07-31 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\472 |  | 1 | Completed & Approved | Closed after June
2285 | NOC581 | NOC | NA |  |  |  | GPON | GPON | Hybrid Mode of the G-240G-E ONT |  | Critical |  |  | Nokia OEM | ONT |  | Duplicate point of 472 - T180 | Duplicate |  | Sayyad Pasha |  | Open | Duplicate | [9 empty] | NOCGPON | Applications/Tools | CLOSED |  |  | Duplicate |  | Artefacts not Required |  | 1 | Open | Open
2286 | NOC582 | NOC | NA |  |  |  | GPON | GPON | Nokia ONT under Nokia OLT Remote access for WAN port |  | Critical |  |  | Nokia OEM | OLT/ONT |  | OEM confirmed this feature is not available 20-Sep-25: T Fiber team asked to arrange meeting with Tejas, Nokia OEM | Tejas & Nokia | Deepak and Sivakasi | Sayyad Pasha |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | NOCGPON | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
2287 | NOC583 | NOC | NA |  |  |  | GPON | GPON | Tejas ONT/3rd party ONT under Nokia OLT Remote access for WAN port |  | Critical |  |  | Nokia OEM | OLT/ONT |  | OEM confirmed this feature is not available 20-Sep-25: T Fiber team asked to arrange meeting with Tejas, Nokia OEM | Tejas & Nokia | Deepak and Sivakasi | Sayyad Pasha |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | NOCGPON | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
2288 | NOC584 | NOC | NA |  |  |  | GPON | GPON | Nokia ONT under Tejas OLT Remote access for WAN port |  | Critical |  |  | Nokia OEM | OLT/ONT |  | OEM confirmed this feature is not available 20-Sep-25: T Fiber team asked to arrange meeting with Tejas, Nokia OEM | Tejas & Nokia | Deepak and Sivakasi | Sayyad Pasha |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | NOCGPON | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
2289 | NOC585 | NOC | NA |  |  |  | GPON | GPON | ONT cosumed count is showing wrong in license page |  | Critical |  |  | Nokia OEM | AMS |  | To resolve this issue, AMS to be upgraded and plan of action is awaited from OEM 20-Sep-25: Licensing conumption quantity not showing in Nokia AMS for discovered ONTs.Nokia OEM informed to address this issue Nokia AMS software need to be upgraded. As requested by Nokia team required pre-requsuits shared with Nokia OEM.yet to receive upgradation plan from Nokia Team. | Tejas & Nokia | Deepak and Sivakasi | Sayyad Pasha |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | NOCGPON | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
2290 | NOC586 | NOC | NA |  |  |  | GPON | GPON | API and Template for ILL Service - Bridge Mode, including uplink port configuration |  | Critical |  |  | Nokia OEM | AMS |  | OEM confirmed API/Template is not available for uplink port configuration | Nokia & NSO | Sivakasi & Jayath | Sayyad Pasha |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | NOCGPON | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
2291 | NOC587 | NOC | NA |  |  |  | GPON | GPON | API and Template for ILL Service - Route Mode, including uplink port configuration |  | Critical |  |  | Nokia OEM | AMS |  | OEM confirmed API/Template is not available for uplink port configuration | Nokia & NSO | Sivakasi & Jayath | Sayyad Pasha |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | NOCGPON | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
2292 | NOC588 | NOC | NA |  |  |  | GPON | GPON | API and Template for Household Services, including uplink port configuration |  | Critical |  |  | Nokia OEM | AMS |  | OEM confirmed API/Template is not available for uplink port configuration | Nokia & NSO | Sivakasi & Jayath | Sayyad Pasha |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | NOCGPON | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
2293 | NOC589 | NOC | NA |  |  |  | GPON | GPON | API and Template for IPTV services, including uplink port configuration |  | Critical |  |  | Nokia OEM | AMS |  | OEM confirmed API/Template is not available for uplink port configuration | Nokia & NSO | Sivakasi & Jayath | Sayyad Pasha |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | NOCGPON | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
2294 | NOC59 | NOC | NA |  |  |  | GPON | OSS | T-NOC Report :: Summary of O&M Cluster OLTs status (Selective from and to dates) |  | Critical | NOT_FEASIBLE |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  | Open | Not Feasible | [9 empty] | NOCGPON | Applications/Tools | #N/A | NOT-FEASIBLE | 0 |  |  | #N/A |  | 1 | Open | Open
2295 | NOC590 | NOC | NA |  |  |  | GPON | GPON | API, Template and configuration for VOIP services, including uplink port configuration |  | Critical |  |  | Nokia OEM | AMS |  | OEM confirmed API/Template is not available for uplink port configuration | Nokia & NSO | Sivakasi & Jayath | Sayyad Pasha |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | NOCGPON | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
2296 | NOC591 | NOC | NA |  |  |  | GPON | GPON | API and Template for GI-BB Service - Bridge Mode, including uplink port configuration |  | Critical |  |  | Nokia OEM | AMS |  | OEM confirmed API/Template is not available for uplink port configuration | Nokia & NSO | Sivakasi & Jayath | Sayyad Pasha |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | NOCGPON | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
2297 | NOC592 | NOC | NA |  |  |  | GPON | GPON | API and Template for GI-BB Service - Route Mode, including uplink port configuration |  | Critical |  |  | Nokia OEM | AMS |  | OEM confirmed API/Template is not available for uplink port configuration | Nokia & NSO | Sivakasi & Jayath | Sayyad Pasha |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | NOCGPON | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
2298 | NOC593 | NOC | NA |  |  |  | GPON | GPON | API to fetch the configured services in AMS, including uplink port configuration |  | Critical |  |  | Nokia OEM | AMS |  | OEM confirmed API/Template is not available for uplink port configuration | Nokia & NSO | Sivakasi & Jayath | Sayyad Pasha |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | NOCGPON | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
2299 | NOC594 | NOC | NA |  |  |  | GPON | GPON | Configuration, API and Template for applying QOS for the different types of services |  | Critical |  |  | Nokia OEM | AMS |  | API has to share by OEM | Nokia & NSO | Sivakasi & Jayath | Sayyad Pasha |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | NOCGPON | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
2300 | NOC595 | NOC | NA |  |  |  | GPON | GPON | API and Template required to provision ONT along with selecting specific UNI port in ONT |  | Critical |  |  | Nokia OEM | AMS |  | API has to share by OEM | Nokia & NSO | Sivakasi & Jayath | Sayyad Pasha |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | NOCGPON | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
2301 | NOC596 | NOC | NA |  |  |  | GPON | GPON | API and Template required to provision ONT with multiple services along with selecting specific UNI port in ONT |  | Critical |  |  | Nokia OEM | AMS |  | API has to share by OEM | Nokia & NSO | Sivakasi & Jayath | Sayyad Pasha |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | NOCGPON | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
2302 | NOC597 | NOC | NA |  |  |  | GPON | GPON | API and Template required to provision ONT with same service on all ports |  | Critical |  |  | Nokia OEM | AMS |  | API has to share by OEM | Nokia & NSO | Sivakasi & Jayath | Sayyad Pasha |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | NOCGPON | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
2303 | NOC598 | NOC | NA |  |  |  | GPON | GPON | API and Template to configure multiple vlans on single ONT UNI Port |  | Critical |  |  | Nokia OEM | AMS |  | API has to share by OEM | Nokia & NSO | Sivakasi & Jayath | Sayyad Pasha |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | NOCGPON | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
2304 | NOC599 | NOC | NA |  |  |  | GPON | GPON | Configuration, API and Template for extedning services to enterprise customers |  | Critical |  |  | Nokia OEM | AMS |  | API has to share by OEM | Nokia & NSO | Sivakasi & Jayath | Sayyad Pasha |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | NOCGPON | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
2305 | NOC6 | NOC | NA |  | OSS | OSS | OSS | DC | DC Applications uptime & SLA Weekly |  | Critical |  |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCOSS | Applications/Tools | OPEN | OPEN | 0 |  |  | #N/A |  | 1 | Open | Open
2306 | NOC60 | NOC | NA |  |  |  | GPON | OSS | Router UP - OLT Down cases Daily |  | Critical | COMPLETED |  | NNMI | NNMI |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCGPON | Applications/Tools | OPEN | COMPLETED | To be updated by Manoj |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
2307 | NOC600 | NOC | NA |  |  |  | GPON | GPON | API and Template to verify and enable the PM |  | Critical |  |  | Nokia OEM | AMS |  | API has to share by OEM | Nokia & NSO | Sivakasi & Jayath | Sayyad Pasha |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | NOCGPON | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
2308 | NOC601 | NOC | NA |  |  |  | GPON | GPON | API and Template to configure Vlan and Profiles in OLT |  | Critical |  |  | Nokia OEM | AMS |  | API has to share by OEM | Nokia & NSO | Sivakasi & Jayath | Sayyad Pasha |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | NOCGPON | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
2309 | NOC602 | NOC | NA |  |  |  | GPON | GPON | Required complete API and Template developer document |  | Critical |  |  | Nokia OEM | AMS |  | OEM shared the document of APC template creation but required document for the API attributes | Nokia & NSO | Sivakasi & Jayath | Sayyad Pasha |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | NOCGPON | Applications/Tools | OPEN |  |  |  |  | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API Document |  | 1 | Open | Open
2310 | NOC603 | NOC | NA |  |  |  | GPON | GPON | API and Template to validate the profiles, vlans available in OLT,ONT |  | Critical |  |  | Nokia OEM | AMS |  | API has to share by OEM | Nokia & NSO | Sivakasi & Jayath | Sayyad Pasha |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | NOCGPON | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
2311 | NOC604 | NOC | NA |  |  |  | GPON | GPON | API and Template to restirct/block the PON port to a specific customer |  | Critical |  |  | Nokia OEM | AMS |  | API has to share by OEM | Nokia & NSO | Sivakasi & Jayath | Sayyad Pasha |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | NOCGPON | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
2312 | NOC605 | NOC | NA |  |  |  | GPON | GPON | API and Template to modify the service- ONT, UNI Port, bandwidth, vlan, description, unatgged to tag or vice versa., |  | Critical |  |  | Nokia OEM | AMS |  | API has to share by OEM | Nokia & NSO | Sivakasi & Jayath | Sayyad Pasha |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | NOCGPON | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
2313 | NOC606 | NOC | NA |  |  |  | GPON | GPON | API and Template to configure,modify,suspend,delete the WAN profiles in WiFi ONT |  | Critical |  |  | Nokia OEM | AMS |  | OEM confirmed API/Template is not available | Nokia & NSO | Sivakasi & Jayath | Sayyad Pasha |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | NOCGPON | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
2314 | NOC607 | NOC | NA |  |  |  | GPON | GPON | Verification of the service provisioning templates which are prepared for the different types of services |  | Critical |  |  | Nokia OEM | AMS |  | API has to share by OEM | Nokia & NSO | Sivakasi & Jayath | Sayyad Pasha |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | NOCGPON | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
2315 | NOC608 | NOC | NA |  |  |  | GPON | GPON | Verification of the services configured by NSO through Playbook(Cisco Tool) |  | Critical |  |  | Nokia OEM | AMS |  | API has to share by OEM | Nokia & NSO | Sivakasi & Jayath | Sayyad Pasha |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | NOCGPON | Applications/Tools | OPEN |  |  |  |  | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API to validate the configured Services |  | 1 | Open | Open
2316 | NOC609 | NOC | NA |  |  |  | GPON | GPON | Mapping bandiwdth profiles per vlan in a ONT UNI | 20-Sep-25: As per Nokia OEM, Mapping BW profiles per service BW on ONT Interface.Meeting to be arranged with Nokia OEM | Critical |  |  | Nokia OEM | OLT/ONT |  | Update awaited from OEM | Nokia & NSO | Sivakasi & Jayath | Sayyad Pasha |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | NOCGPON | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
2317 | NOC61 | NOC | NA |  |  |  | GPON | OSS | Router UP - OLT Down cases Weekly |  | Critical | COMPLETED |  | NNMI | NNMI |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCGPON | Applications/Tools | OPEN | COMPLETED | To be updated by Manoj |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
2318 | NOC610 | NOC | NA |  |  |  | GPON | GPON | NOKIA ONT is not supporting for bandwidth Rate Limit configuration On ONT LAN Ethernet port (UNI) when connected under Tejas OLT | 20-Sep-25:Guidelines have to share with all 3 packages to deploy balance scope as Tejas OLT- Tejas ONT and Nokia OLT-Nokia ONT | Critical |  |  | Nokia OEM | ONT |  | OEM confirmed Rate Limit is not supported by Nokia ONTs | Nokia & NSO | Sivakasi & Jayath | Sayyad Pasha |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | NOCGPON | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
2319 | NOC611 | NOC | NA |  |  |  | GPON | GPON | PM Report for 24hrs of OLT,ONT,ONT Eth Port(Bridge/Route), Wifi |  | Critical |  |  | Nokia OEM | AMS |  |  |  |  | Sayyad Pasha |  |  | COMPLETED & APPROVED | AD-UT-Tfiber | 2025-07-31 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\470 | [6 empty] | NOCGPON | Applications/Tools | CLOSED |  |  |  | 2025-07-31 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\470 |  | 1 | Completed & Approved | Closed after June
2320 | NOC612 | NOC | NA |  |  |  | GPON | GPON | Nokia ONT ethernet port status is not updating |  | Critical | DUPLICATE POINT (NOC572) |  | Nokia OEM | OLT/ONT |  | Duplicate point of 472 - 432 | Duplicate |  | Sayyad Pasha |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | NOCGPON | Applications/Tools | OPEN |  |  | Duplicate |  |  |  | 1 | Open | Open
2321 | NOC613 | NOC | NA |  |  |  | GPON | GPON | Unable to provide available download bandwidth of PON Port for Nokia devices (Nokia BW Query) |  | Critical |  |  | Nokia OEM | AMS |  | Duplicate point of 472 - T175 | Duplicate |  | Sayyad Pasha |  | Open | DEPENDENCY(Client/Ext.) | [9 empty] | NOCGPON | Applications/Tools | OPEN |  |  | Duplicate |  | #N/A |  | 1 | Open | Open
2322 | NOC614 | NOC | NA |  | OSS | OSS | All Domain | OSS | EOL and EOS Through inventory Dashboard-Weekly |  | Critical | COMPLETED |  | HPSM | Asset Manager |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCAll Domain | Applications/Tools | OPEN | COMPLETED | we dont have dashboard only report is available |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
2323 | NOC615 | NOC | NA |  | OSS | OSS | All Domain | OSS | EOL and EOS Through inventory Dashboard-Monthly |  | Critical | COMPLETED |  | HPSM | Asset Manager |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCAll Domain | Applications/Tools | OPEN | COMPLETED | we dont have dashboard only report is available |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
2324 | NOC616 | NOC | NA |  | OSS | OSS | All Domain | OSS | Infra Server Url Services Intigration |  | Critical | COMPLETED |  | HPSM | Site scope |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCAll Domain | Applications/Tools | OPEN | CLOSURE REVIEW PENDING | 0 |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
2325 | NOC617 | NOC | NA |  | OSS | OSS | All Domain | OSS | Infra Server Url Services Monitoring |  | Critical | COMPLETED |  | HPSM | Site scope |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCAll Domain | Applications/Tools | OPEN | CLOSURE REVIEW PENDING | 0 |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
2326 | NOC618 | NOC | NA |  | OSS | OSS | All Domain | OSS | Infra Server Url Services Reporting |  | Critical | COMPLETED |  | HPSM | Site scope |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCAll Domain | Applications/Tools | OPEN | CLOSURE REVIEW PENDING | 0 |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
2327 | NOC619 | NOC | NA |  | OSS | OSS | All Domain | OSS | real-time information |  | Critical | COMPLETED |  | HPSM | Site scope |  | 09-09-2025: Ticket, status, Inventory, Alarms, etc are available in real time |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCAll Domain | Applications/Tools | OPEN | COMPLETED | 09-09-2025: Ticket, status, Inventory, Alarms, etc are available in real time |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
2328 | NOC62 | NOC | NA |  |  |  | GPON | OSS | Router UP - OLT Down cases Monthly |  | Critical | COMPLETED |  | NNMI | NNMI |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCGPON | Applications/Tools | OPEN | COMPLETED | To be updated by Manoj |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
2329 | NOC620 | NOC | NA |  | OSS | OSS | All Domain | OSS | Health of the Performance for Traffic |  | Critical | COMPLETED |  | HPSM | NNM iSPI |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCAll Domain | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
2330 | NOC621 | NOC | NA |  | OSS | OSS | All Domain | OSS | Analyze Flow Packets |  | Critical | COMPLETED |  | HPSM | NNM iSPI |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCAll Domain | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
2331 | NOC622 | NOC | NA |  | OSS | OSS | All Domain | OSS | Performance for Traffic Maps |  | Critical | COMPLETED |  | HPSM | NNM iSPI |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCAll Domain | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
2332 | NOC623 | NOC | NA |  |  |  | NSO | NSO | NSO Intigration for POC Locations LCO,RMSO & MSO |  | Critical |  |  | NSO | SCCM/Playbook |  |  |  |  | Jayant Madavi |  | Open | Open | [9 empty] | NOCNSO | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
2333 | NOC624 | NOC | NA |  |  |  | NSO | NSO | Video customer inventory , Internet customer inventory , Bandwidth allocation inventory count etc., |  | Critical |  |  | NSO | SCCM/Playbook |  |  |  |  | Jayant Madavi |  | Open | Open | [9 empty] | NOCNSO | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
2334 | NOC625 | NOC | NA |  |  |  | NSO | NSO | NSO Intigration for Live Locations LCO,RMSO & MSO |  | Critical |  |  | NSO | SCCM/Playbook |  |  |  |  | Jayant Madavi |  | Open | Open | [9 empty] | NOCNSO | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
2335 | NOC626 | NOC | NA |  |  |  | NSO | NSO | Video customer inventory , Internet customer inventory , Bandwidth allocation inventory count etc., |  | Critical | DUPLICATE POINT (NOC624) |  | NSO | SCCM/Playbook |  |  |  |  | Jayant Madavi |  | Open | Open | [9 empty] | NOCNSO | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
2336 | NOC627 | NOC | NA |  |  |  | BSS | BSS | TFiber BSS to be integrated with Partners SMS & BSS (LCO, RMSO & MSO etc..) for POC Locations |  | Critical | OPEN |  | KNOT | CRM |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
2337 | NOC628 | NOC | NA |  |  |  | BSS | BSS | After completion of POC Same solution shall be implemented for All Household of Telangana (TFiber BSS to be integrated with all other Partners SMS & BSS for Live (LCO , RMSO & MSO etc..)) |  | Critical | OPEN |  | KNOT | CRM |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
2338 | NOC629 | NOC | NA |  |  |  | BSS | BSS | New Customer order HouseHolds |  | Critical | OPEN |  | KNOT | CRM |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
2339 | NOC63 | NOC | NA |  |  |  | GPON | OSS | Router UP - OLT Down cases (Selective from and to dates) |  | Critical | COMPLETED |  | NNMI | NNMI |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCGPON | Applications/Tools | OPEN | COMPLETED | To be updated by Manoj |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
2340 | NOC630 | NOC | NA |  |  |  | BSS | BSS | Existing customer alignment for order |  | Critical | OPEN |  | KNOT | CRM |  | DUPLICATE POINT (NOC630) |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
2341 | NOC631 | NOC | NA |  |  |  | BSS | BSS | Customer service ID allocation |  | Critical | OPEN |  | KNOT | CRM |  | DUPLICATE POINT (NOC631) |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
2342 | NOC632 | NOC | NA |  |  |  | BSS | BSS | Activation & Deactivation update to BSS |  | Critical | OPEN |  | KNOT | CRM |  | DUPLICATE POINT (NOC632) |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
2343 | NOC633 | NOC | NA |  |  |  | BSS | BSS | New customer package & billing |  | Critical | OPEN |  | KNOT | Billing |  | DUPLICATE POINT (NOC633) |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
2344 | NOC634 | NOC | NA |  |  |  | BSS | BSS | Existing customer renewal & package modification update |  | Critical | OPEN |  | KNOT | Billing |  | DUPLICATE POINT (NOC634) |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
2345 | NOC635 | NOC | NA |  |  |  | BSS | BSS | Customer address change intigration |  | Critical | OPEN |  | KNOT | Billing |  | DUPLICATE POINT (NOC635) |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
2346 | NOC636 | NOC | NA |  |  |  | BSS | BSS | Customer Discount update to BSS |  | Critical | OPEN |  | KNOT | Billing |  | DUPLICATE POINT (NOC636) |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
2347 | NOC637 | NOC | NA |  |  |  | BSS | BSS | Partner Dashboard Number of customers through TFiber |  | Critical | OPEN |  | BSS | CRM |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
2348 | NOC638 | NOC | NA |  |  |  | BSS | BSS | Partner Dashboard Uptime SLA customers through TFiber |  | Critical | OPEN |  | HPSM | Incident Management |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
2349 | NOC639 | NOC | NA |  |  |  | BSS | BSS | Partner Dashboard Access |  | Critical | OPEN |  | BSS | CRM |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
2350 | NOC64 | NOC | NA |  |  |  | GPON | OSS | ONTs down more than 8 hrs. list Daily |  | Critical | COMPLETED |  | OSS Dashboards | UOC |  | 09-09-2025: Aging Report available, Stabilization Required |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCGPON | Applications/Tools | OPEN | COMPLETED | 09-09-2025: Aging Report available, Stabilization Required |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
2351 | NOC640 | NOC | NA |  |  |  | BSS | BSS | TFiber BSS to be Implemented for all GI of Telangana |  | Critical | OPEN |  | KNOT | CRM |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
2352 | NOC641 | NOC | NA |  |  |  | BSS | BSS | After completion of POC Same solution shall be implemented for All Government Institutions of Telangana (TFiber BSS to be Utilized for go Live ) |  | Critical | OPEN |  | KNOT | CRM |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
2353 | NOC642 | NOC | NA |  |  |  | BSS | BSS | New Customer order GI |  | Critical | OPEN |  | KNOT | CRM |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
2354 | NOC643 | NOC | NA |  |  |  | BSS | BSS | Existing customer alignment for order |  | Critical | DUPLICATE POINT (NOC630) |  | KNOT | CRM |  | DUPLICATE POINT (NOC630) |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
2355 | NOC644 | NOC | NA |  |  |  | BSS | BSS | Customer service ID allocation |  | Critical | DUPLICATE POINT (NOC631) |  | KNOT | CRM |  | DUPLICATE POINT (NOC631) |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
2356 | NOC645 | NOC | NA |  |  |  | BSS | BSS | Activation & Deactivation update to BSS |  | Critical | DUPLICATE POINT (NOC632) |  | KNOT | CRM |  | DUPLICATE POINT (NOC632) |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
2357 | NOC646 | NOC | NA |  |  |  | BSS | BSS | New customer package & billing |  | Critical | DUPLICATE POINT (NOC633) |  | KNOT | Billing |  | DUPLICATE POINT (NOC633) |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
2358 | NOC647 | NOC | NA |  |  |  | BSS | BSS | Existing customer renewal & package modification update |  | Critical | DUPLICATE POINT (NOC634) |  | KNOT | Billing |  | DUPLICATE POINT (NOC634) |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
2359 | NOC648 | NOC | NA |  |  |  | BSS | BSS | Customer address change intigration |  | Critical | DUPLICATE POINT (NOC635) |  | KNOT | Billing |  | DUPLICATE POINT (NOC635) |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
2360 | NOC649 | NOC | NA |  |  |  | BSS | BSS | Customer Discount update to BSS |  | Critical | DUPLICATE POINT (NOC636) |  | KNOT | Billing |  | DUPLICATE POINT (NOC636) |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
2361 | NOC65 | NOC | NA |  |  |  | GPON | OSS | ONTs down more than 8 hrs. list Weekly |  | Critical | COMPLETED |  | OSS Dashboards | UOC |  | 09-09-2025: Aging Report available, Stabilization Required |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCGPON | Applications/Tools | OPEN | COMPLETED | 09-09-2025: Aging Report available, Stabilization Required |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
2362 | NOC650 | NOC | NA |  |  |  | BSS | BSS | Customer Dashboard Number of customers through TFiber |  | Critical | OPEN |  | BSS | CRM |  | DUPLICATE POINT (NOC650) |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
2363 | NOC651 | NOC | NA |  |  |  | BSS | BSS | Customer Dashboard Uptime SLA customers through TFiber |  | Critical | OPEN |  | HPSM | Incident Management |  | DUPLICATE POINT (NOC651) |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
2364 | NOC652 | NOC | NA |  |  |  | BSS | BSS | Customer Dashboard Access |  | Critical | OPEN |  | BSS | CRM |  | DUPLICATE POINT (NOC652) |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
2365 | NOC653 | NOC | NA |  |  |  | BSS | BSS | TFiber BSS to be Implemented for all Enterprice P2p & P2MP services in Telangana |  | Critical | OPEN |  | KNOT | CRM |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
2366 | NOC654 | NOC | NA |  |  |  | BSS | BSS | After completion of POC Same solution shall be implemented for All Enterprice P2p & P2MP services in Telangana (TFiber BSS to be Utilized for go Live ) |  | Critical | OPEN |  | KNOT | CRM |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
2367 | NOC655 | NOC | NA |  |  |  | BSS | BSS | New Customer order Enterprice |  | Critical | OPEN |  | KNOT | CRM |  |  |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
2368 | NOC656 | NOC | NA |  |  |  | BSS | BSS | Existing customer alignment for order |  | Critical | DUPLICATE POINT (NOC630) |  | KNOT | CRM |  | DUPLICATE POINT (NOC630) |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
2369 | NOC657 | NOC | NA |  |  |  | BSS | BSS | Customer service ID allocation |  | Critical | DUPLICATE POINT (NOC631) |  | KNOT | CRM |  | DUPLICATE POINT (NOC631) |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
2370 | NOC658 | NOC | NA |  |  |  | BSS | BSS | Activation & Deactivation update to BSS |  | Critical | DUPLICATE POINT (NOC632) |  | KNOT | CRM |  | DUPLICATE POINT (NOC632) |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
2371 | NOC659 | NOC | NA |  |  |  | BSS | BSS | New customer package & billing |  | Critical | DUPLICATE POINT (NOC633) |  | KNOT | Billing |  | DUPLICATE POINT (NOC633) |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
2372 | NOC66 | NOC | NA |  |  |  | GPON | OSS | ONTs down more than 8 hrs. list Monthly |  | Critical | COMPLETED |  | OSS Dashboards | UOC |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCGPON | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
2373 | NOC660 | NOC | NA |  |  |  | BSS | BSS | Existing customer renewal & package modification update |  | Critical | DUPLICATE POINT (NOC634) |  | KNOT | Billing |  | DUPLICATE POINT (NOC634) |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
2374 | NOC661 | NOC | NA |  |  |  | BSS | BSS | Customer address change intigration |  | Critical | DUPLICATE POINT (NOC635) |  | KNOT | Billing |  | DUPLICATE POINT (NOC635) |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
2375 | NOC662 | NOC | NA |  |  |  | BSS | BSS | Customer Discount update to BSS |  | Critical | DUPLICATE POINT (NOC636) |  | KNOT | Billing |  | DUPLICATE POINT (NOC636) |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
2376 | NOC663 | NOC | NA |  |  |  | BSS | BSS | Customer Dashboard Number of customers through TFiber |  | NON-Critical | DUPLICATE POINT (NOC650) |  | BSS | CRM |  | DUPLICATE POINT (NOC650) |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
2377 | NOC664 | NOC | NA |  |  |  | BSS | BSS | Customer Dashboard Uptime SLA customers through TFiber |  | NON-Critical | DUPLICATE POINT (NOC651) |  | HPSM | Incident Management |  | DUPLICATE POINT (NOC651) |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
2378 | NOC665 | NOC | NA |  |  |  | BSS | BSS | Customer Dashboard Access |  | NON-Critical | DUPLICATE POINT (NOC652) |  | BSS | CRM |  | DUPLICATE POINT (NOC652) |  |  | Manoj Nibrad |  | Open | Open | [9 empty] | NOCBSS | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
2379 | NOC666 | NOC | NA |  |  |  | NSO | Service Solutions | GI-BB |  | Critical |  |  | NSO | SCCM/Playbook |  |  |  |  | Jayant Madavi |  | Open | Open | [9 empty] | NOCNSO | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
2380 | NOC667 | NOC | NA |  |  |  | NSO | Service Solutions | T-CELL |  | Critical |  |  | NSO | SCCM/Playbook |  |  |  |  | Jayant Madavi |  | Open | Open | [9 empty] | NOCNSO | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
2381 | NOC668 | NOC | NA |  |  |  | NSO | Service Solutions | HH Triple Play (Internet, IPTV, VoIP) |  | Critical |  |  | NSO | SCCM/Playbook |  |  |  |  | Jayant Madavi |  | Open | Open | [9 empty] | NOCNSO | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
2382 | NOC669 | NOC | NA |  |  |  | NSO | Service Solutions | CCTV Unicast |  | Critical |  |  | NSO | SCCM/Playbook |  |  |  |  | Jayant Madavi |  | Open | Open | [9 empty] | NOCNSO | Applications/Tools | OPEN |  |  |  |  | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\Centrailzed CCTV Surveillance Monitoring over T-Fiber Network-Solution Doucment_Initial Draft V1.0 - T189.pdf |  | 1 | Open | Open
2383 | NOC67 | NOC | NA |  |  |  | GPON | OSS | ONTs down more than 8 hrs. list (Selective from and to dates) |  | Critical | COMPLETED |  | OSS Dashboards | UOC |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCGPON | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
2384 | NOC670 | NOC | NA |  |  |  | NSO | Service Solutions | CCTV Multicast |  | Critical |  |  | NSO | SCCM/Playbook |  |  |  |  | Jayant Madavi |  | Open | Open | [9 empty] | NOCNSO | Applications/Tools | OPEN |  |  |  |  | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\CCTV Multicast Solution LLD V1.2 - T190.pdf |  | 1 | Open | Open
2385 | NOC671 | NOC | NA |  |  |  | NSO | Service Solutions | T-DIA (ILL) |  | Critical |  |  | NSO | SCCM/Playbook |  |  |  |  | Jayant Madavi |  | Open | Open | [9 empty] | NOCNSO | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
2386 | NOC672 | NOC | NA |  |  |  | NSO | Service Solutions | L2VPN |  | Critical |  |  | NSO | SCCM/Playbook |  |  |  |  | Jayant Madavi |  | Open | Open | [9 empty] | NOCNSO | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
2387 | NOC673 | NOC | NA |  |  |  | NSO | Service Solutions | L3VPN |  | Critical |  |  | NSO | SCCM/Playbook |  |  |  |  | Jayant Madavi |  | Open | Open | [9 empty] | NOCNSO | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
2388 | NOC674 | NOC | NA |  |  |  | NSO | Service Solutions | TVPN - Rythu Vedika |  | Critical |  |  | NSO | SCCM/Playbook |  |  |  |  | Jayant Madavi |  | Open | Open | [9 empty] | NOCNSO | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
2389 | NOC675 | NOC | NA |  |  |  | NSO | Service Solutions | TVPN - DHQ to SHQ Connectivity |  | Critical |  |  | NSO | SCCM/Playbook |  |  |  |  | Jayant Madavi |  | Open | Open | [9 empty] | NOCNSO | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
2390 | NOC676 | NOC | NA |  |  |  | NSO | Service Solutions | TVPN - MRO Office Connectivity |  | Critical |  |  | NSO | SCCM/Playbook |  |  |  |  | Jayant Madavi |  | Open | Open | [9 empty] | NOCNSO | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
2391 | NOC677 | NOC | NA |  |  |  | NSO | Service Solutions | SDC/TSWAN integration |  | Critical |  |  | NSO | SCCM/Playbook |  |  |  |  | Jayant Madavi |  | Open | Open | [9 empty] | NOCNSO | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
2392 | NOC678 | NOC | NA |  |  |  | NSO | Service Solutions | TSP NNI |  | Critical |  |  | NSO | SCCM/Playbook |  |  |  |  | Jayant Madavi |  | Open | Open | [9 empty] | NOCNSO | Applications/Tools | OPEN |  |  |  |  | #N/A |  | 1 | Open | Open
2393 | NOC68 | NOC | NA |  |  |  | GPON | OSS | Mandal OLT down more than 6 hrs. list Daily |  | Critical | COMPLETED |  | OSS Dashboards | UOC |  | 09-09-2025: Aging Report available, Stabilization Required |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCGPON | Applications/Tools | OPEN | COMPLETED | 09-09-2025: Aging Report available, Stabilization Required -real time data |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
2394 | NOC69 | NOC | NA |  |  |  | GPON | OSS | Mandal OLT down more than 6 hrs. list Weekly |  | Critical | COMPLETED |  | OSS Dashboards | UOC |  | 09-09-2025: Aging Report available, Stabilization Required |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCGPON | Applications/Tools | OPEN | COMPLETED | 09-09-2025: Aging Report available, Stabilization Required |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
2395 | NOC7 | NOC | NA |  | OSS | OSS | OSS | DC | DC Applications uptime & SLA Monthly |  | Critical |  |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCOSS | Applications/Tools | OPEN | OPEN | 0 |  |  | #N/A |  | 1 | Open | Open
2396 | NOC70 | NOC | NA |  |  |  | GPON | OSS | Mandal OLT down more than 6 hrs. list Monthly |  | Critical | COMPLETED |  | OSS Dashboards | UOC |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCGPON | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
2397 | NOC71 | NOC | NA |  |  |  | GPON | OSS | Mandal OLT down more than 6 hrs. list (Selective from and to dates) |  | Critical | COMPLETED |  | OSS Dashboards | UOC |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCGPON | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
2398 | NOC72 | NOC | NA |  |  |  | GPON | OSS | HH_PM Utilization Dump _PKGA_PKGC Daily |  | NON-Critical | COMPLETED |  | NNMI | NPS |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCGPON | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
2399 | NOC73 | NOC | NA |  |  |  | GPON | OSS | HH_PM Utilization Dump _PKGA_PKGC Weekly |  | NON-Critical | NOT_FEASIBLE |  | NNMI | NPS |  |  |  |  | Suresh Pawar |  | Open | Not Feasible | [9 empty] | NOCGPON | Applications/Tools | #N/A | NOT-FEASIBLE | 0 |  |  | #N/A |  | 1 | Open | Open
2400 | NOC74 | NOC | NA |  |  |  | GPON | OSS | HH_PM Utilization Dump _PKGA_PKGC Monthly |  | NON-Critical | COMPLETED |  | NNMI | NPS |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCGPON | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
2401 | NOC75 | NOC | NA |  |  |  | GPON | OSS | HH_PM Utilization Dump _PKGA_PKGC (Selective from and to dates) |  | NON-Critical | NOT_FEASIBLE |  | NNMI | NPS |  |  |  |  | Suresh Pawar |  | Open | Not Feasible | [9 empty] | NOCGPON | Applications/Tools | #N/A | NOT-FEASIBLE | 0 |  |  | #N/A |  | 1 | Open | Open
2402 | NOC76 | NOC | NA |  |  |  | GPON | OSS | Summary of Lit-up GPs Status_8895 Daily |  | NON-Critical | DUPLICATE POINT |  | HPSM | Incident Management |  | DUPLICATE POINT |  |  | Suresh Pawar |  | Open | Duplicate | [9 empty] | NOCGPON | Applications/Tools | OPEN | DUPLICATE | 0 |  |  | Artefacts to be uploaded |  | 1 | Open | Open
2403 | NOC77 | NOC | NA |  |  |  | GPON | OSS | Summary of Lit-up GPs Status_8895 Weekly |  | NON-Critical | DUPLICATE POINT |  | HPSM | Incident Management |  | DUPLICATE POINT |  |  | Suresh Pawar |  | Open | Duplicate | [9 empty] | NOCGPON | Applications/Tools | OPEN | DUPLICATE | 0 |  |  | Artefacts to be uploaded |  | 1 | Open | Open
2404 | NOC78 | NOC | NA |  |  |  | GPON | OSS | Summary of Lit-up GPs Status_8895 Monthly |  | NON-Critical | DUPLICATE POINT |  | HPSM | Incident Management |  | DUPLICATE POINT |  |  | Suresh Pawar |  | Open | Duplicate | [9 empty] | NOCGPON | Applications/Tools | OPEN | DUPLICATE | 0 |  |  | Artefacts to be uploaded |  | 1 | Open | Open
2405 | NOC79 | NOC | NA |  |  |  | GPON | OSS | Summary of Lit-up GPs Status_8895 (Selective from and to dates) |  | Critical | DUPLICATE POINT |  | HPSM | Incident Management |  | DUPLICATE POINT |  |  | Suresh Pawar |  | Open | Duplicate | [9 empty] | NOCGPON | Applications/Tools | OPEN | DUPLICATE | 0 |  |  | Artefacts to be uploaded |  | 1 | Open | Open
2406 | NOC8 | NOC | NA |  | OSS | OSS | OSS | DC | DC Applications uptime & SLA (Selective from and to dates) |  | Critical |  |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  | Open | Open | [9 empty] | NOCOSS | Applications/Tools | OPEN | OPEN | 0 |  |  | #N/A |  | 1 | Open | Open
2407 | NOC80 | NOC | NA |  |  |  | GPON | OSS | GPON OLT TT trend dashboard Daily |  | Critical | COMPLETED |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCGPON | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
2408 | NOC81 | NOC | NA |  |  |  | GPON | OSS | GPON OLT TT trend dashboard Weekly |  | Critical | COMPLETED |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCGPON | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
2409 | NOC82 | NOC | NA |  |  |  | GPON | OSS | GPON OLT TT trend dashboard Monthly |  | Critical | COMPLETED |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCGPON | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
2410 | NOC83 | NOC | NA |  |  |  | GPON | OSS | GPON OLT TT trend dashboard (Selective from and to dates) |  | Critical | COMPLETED |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCGPON | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
2411 | NOC84 | NOC | NA |  |  |  | GPON | OSS | GPON ONT TT trend dashboard Daily |  | Critical | COMPLETED |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCGPON | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
2412 | NOC85 | NOC | NA |  |  |  | GPON | OSS | GPON ONT TT trend dashboard Weekly |  | Critical | COMPLETED |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCGPON | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
2413 | NOC86 | NOC | NA |  |  |  | GPON | OSS | GPON ONT TT trend dashboard Monthly |  | Critical | COMPLETED |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCGPON | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
2414 | NOC87 | NOC | NA |  |  |  | GPON | OSS | GPON ONT TT trend dashboard (Selective from and to dates) |  | Critical | COMPLETED |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCGPON | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
2415 | NOC88 | NOC | NA |  |  |  | GPON | OSS | POP uptime_ GP Mandal and Zonal Daily |  | Critical | COMPLETED |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCGPON | Applications/Tools | OPEN | COMPLETED | availablity |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
2416 | NOC89 | NOC | NA |  |  |  | GPON | OSS | POP uptime_ GP Mandal and Zonal Weekly |  | Critical | NOT_FEASIBLE |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  | Open | Not Feasible | [9 empty] | NOCGPON | Applications/Tools | #N/A | NOT-FEASIBLE | 0 |  |  | #N/A |  | 1 | Open | Open
2417 | NOC9 | NOC | NA |  | OSS | OSS | OSS | DC | DC Passive infra uptime & SLA Daily |  | Critical |  |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCOSS | Applications/Tools | OPEN | COMPLETED | 0 |  |  | #N/A |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
2418 | NOC90 | NOC | NA |  |  |  | GPON | OSS | POP uptime_ GP Mandal and Zonal Monthly |  | Critical | COMPLETED |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCGPON | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
2419 | NOC91 | NOC | NA |  |  |  | GPON | OSS | POP uptime_ GP Mandal and Zonal (Selective from and to dates) |  | Critical | NOT_FEASIBLE |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  | Open | Not Feasible | [9 empty] | NOCGPON | Applications/Tools | #N/A | NOT-FEASIBLE | 0 |  |  | #N/A |  | 1 | Open | Open
2420 | NOC92 | NOC | NA |  |  |  | GPON | OSS | Weekly BW utilization Supporting data Daily |  | NON-Critical | COMPLETED |  | OSS Dashboards | PMS(UOC) |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCGPON | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
2421 | NOC93 | NOC | NA |  |  |  | GPON | OSS | Weekly BW utilization Supporting data Weekly |  | NON-Critical | NOT_FEASIBLE |  | OSS Dashboards | PMS(UOC) |  |  |  |  | Suresh Pawar |  | Open | Not Feasible | [9 empty] | NOCGPON | Applications/Tools | #N/A | NOT-FEASIBLE | 0 |  |  | #N/A |  | 1 | Open | Open
2422 | NOC94 | NOC | NA |  |  |  | GPON | OSS | Weekly BW utilization Supporting data Monthly |  | NON-Critical | COMPLETED |  | OSS Dashboards | PMS(UOC) |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCGPON | Applications/Tools | OPEN | COMPLETED | 0 |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
2423 | NOC95 | NOC | NA |  |  |  | GPON | OSS | Weekly BW utilization Supporting data (Selective from and to dates) |  | NON-Critical | NOT_FEASIBLE |  | OSS Dashboards | PMS(UOC) |  |  |  |  | Suresh Pawar |  | Open | Not Feasible | [9 empty] | NOCGPON | Applications/Tools | #N/A | NOT-FEASIBLE | 0 |  |  | #N/A |  | 1 | Open | Open
2424 | NOC96 | NOC | NA |  |  |  | GPON | OSS | T-NOC Report :: Migrated & Duplicated GPs still available both Tejas EMS & Nokia AMS Daily |  | NON-Critical | COMPLETED |  | HPSM | Incident Management |  | 09-09-2025: It has to handle manuaaly by downloading report |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCGPON | Applications/Tools | OPEN | COMPLETED | 09-09-2025: It has to handle manuaaly by downloading report |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
2425 | NOC97 | NOC | NA |  |  |  | GPON | OSS | T-NOC Report :: Migrated & Duplicated GPs still available both Tejas EMS & Nokia AMS Weekly |  | NON-Critical | NOT_FEASIBLE |  | HPSM | Incident Management |  |  |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCGPON | Applications/Tools | #N/A | COMPLETED | 0 |  |  | #N/A |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
2426 | NOC98 | NOC | NA |  |  |  | GPON | OSS | T-NOC Report :: Migrated & Duplicated GPs still available both Tejas EMS & Nokia AMS Monthly |  | NON-Critical | COMPLETED |  | HPSM | Incident Management |  | 09-09-2025: It has to handle manuaaly by downloading report |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCGPON | Applications/Tools | OPEN | COMPLETED | 09-09-2025: It has to handle manuaaly by downloading report |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
2427 | NOC99 | NOC | NA |  |  |  | GPON | OSS | T-NOC Report :: Migrated & Duplicated GPs still available both Tejas EMS & Nokia AMS (Selective from and to dates) |  | NON-Critical | COMPLETED |  | HPSM | Incident Management |  | 09-09-2025: It has to handle manuaaly by downloading report |  |  | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | [9 empty] | NOCGPON | Applications/Tools | OPEN | COMPLETED | 09-09-2025: It has to handle manuaaly by downloading report |  |  |  |  | 1 | Completed but Verification undrer Process | Completed but Verification undrer Process
`

## 472-Summary (hidden)
Sum of Qty | Column Labels
Row Labels | Closed after June | Closed before june-2025 | Completed but Verification undrer Process | Open | Grand Total
Ahmad | 4 | 2 |  | 4 | 10
Jayant Madavi |  |  |  | 34 | 34
Kaushalendra Kumar | 6 | 43 | 1 | 4 | 54
Manoj Nibrad |  |  |  | 24 | 24
Ravi Kishore | 4 | 20 |  | 12 | 36
RS Rao | 5 | 20 |  | 7 | 32
Sarmendra | 10 | 3 | 6 | 38 | 57
Sayyad Pasha | 12 | 81 |  | 8 | 101
Siva Kumar | 3 | 8 |  | 7 | 18
Suresh Kumar | 2 | 11 |  | 12 | 25
Suresh Pawar | 8 | 13 | 38 | 22 | 81
Grand Total | 54 | 201 | 45 | 172 | 472

## GIS and WFM (hidden)
Sl. No. | Domain | MOM/ Reference | Area Of Points | Severity by TFIBER | Date | Action Items | Status | Dependency | Planned Completion Date | Remarks
1 | GIS | 472 | 472 | Critical | Date Not Available | Data Gathering for RFS Mandals | Ongoing | All The Package Owners | N/A | 256 Mandal uploaded and AT Completed for 250 Mandals,Ongoing & Approved
2 | GIS | 472 | 472 | Critical | Date Not Available | Data Upload of RFS Mandals | Ongoing | All The Package Owners | N/A | 256 Mandal uploaded and AT Completed for 250 Mandals,Ongoing & Approved
3 | GIS | 472 | 472 | Critical | Date Not Available | Each Package 5 Mandal (Total-15 Mandal) Upload | Completed & Approved | L&T:- Kaushal | N/A | As a PoC, 15 Mandals data uploaded for testing purpose
4 | GIS | 472 | 472 | Critical | Date Not Available | GIS Hardware & Software deployment at DC | Completed & Approved | L&T:- Kaushal | N/A | HA Re-Testing Planned with TPA & TFIBER on 2nd June 2025
5 | GIS | 472 | 472 | Critical | Date Not Available | High Availability & Load Balancer Testing | Completed & Approved | L&T:- Kaushal | N/A | Awaiting for approval from TFIBER & TPA
6 | GIS | 472 | 472 | Critical | Date Not Available | PCs & Licences (G-tech, DI, Geo Media) | Completed | L&T Kaushal & T-FIBER | N/A | Tool & PCs has been installed in NOC GIS room. for Licesnes dependecy on T FIber. During the meeting, the Managing Director of T-Fiber directed that only the minimum number of additional licenses will be procured, and T-Fiber will handle the procurement
7 | GIS | 472 | 472 | Critical | Date Not Available | G-Tech | Completed & Approved | L&T:- Kaushal | N/A
8 | GIS | 472 | 472 | Critical | Date Not Available | Network Portal | Completed & Approved | L&T:- Kaushal | N/A | Network Portal in Production and provided by the approval NoC team but need to demonstarte for Core team
9 | GIS | 472 | 472 | Critical | Date Not Available | Mobile App | Completed & Approved | L&T:- Kaushal | N/A | Mobile App in Production and provided by the approval NoC team but need to demonstarte for Core team
10 | GIS | 472 | 472 | Critical | Date Not Available | DC-DR Requirement Vs Solution | Completed & Approved | L&T:- Kaushal | N/A | DC-DR Testing completed & Document has been kept on share drive,Awaiting TFIBER Approval
11 | GIS | 472 | 472 | Critical | Date Not Available | DC-DR Testing | Completed & Approved | L&T:- Kaushal | N/A | DC-DR Testing completed & Document has been kept on share drive,Awaiting TFIBER Approval
12 | GIS | 472 | 472 | Critical | Date Not Available | Google Map API configuration | Completed & Approved | L&T:- Kaushal | N/A
13 | GIS | 472 | 472 | Critical | Date Not Available | Fixing of telco Boundaries in GIS | Completed & Approved | L&T:- Kaushal | N/A
14 | GIS | 472 | 472 | Critical | Date Not Available | Data Model Optimization | Completed & Approved | L&T:- Kaushal | N/A
15 | GIS | 472 | 472 | Critical | Date Not Available | ISP/OSP object modelling in tool as per T-Fibre | Completed & Approved | L&T:- Kaushal | N/A
16 | GIS | 472 | 472 | Critical | Date Not Available | Make & Model deployment against all object as per T-Fibre Project | Completed & Approved | L&T:- Kaushal | N/A
17 | GIS | 472 | 472 | Critical | Date Not Available | Device (Active/Passive) ( All Type as per T-Fibre Project) & Port Modelling In Tool | Completed & Approved | L&T:- Kaushal | N/A
18 | GIS | 472 | 472 | Critical | Date Not Available | Correction In Fttx Network placement rules (GP To GI) | Completed & Approved | L&T:- Kaushal | N/A
19 | GIS | 472 | 472 | Critical | Date Not Available | Fine tuning or Enable of Cart feature. ( Pan, Zoom, Vertex, Selection method, ruler Etc.) | Completed & Approved | L&T:- Kaushal | N/A
20 | GIS | 472 | 472 | Critical | Date Not Available | Trace Feature ( Link/Spare/Topology) | Completed & Approved | L&T:- Kaushal | N/A
21 | GIS | 472 | 472 | Critical | Date Not Available | Reports (Fibre Utilisation, BOQ, Area selection, ISP/OSP Quantify) | Completed & Approved | L&T:- Kaushal | N/A
22 | GIS | 472 | 472 | Critical | Date Not Available | Document/Image Upload feature | Completed & Approved | L&T:- Kaushal | N/A
23 | GIS | 472 | 472 | Critical | Date Not Available | Port level & Fibre stand lever attribute | Completed & Approved | L&T:- Kaushal | N/A
24 | GIS | 472 | 472 | Critical | Date Not Available | Topology Highlight feature | Completed & Approved | L&T:- Kaushal | N/A
25 | GIS | 472 | 472 | Critical | Date Not Available | Data Model G-TECH Alignment | Completed & Approved | L&T:- Kaushal | N/A
26 | GIS | 472 | 472 | Critical | Date Not Available | DI alignment as per new 35 Layer data model | Completed & Approved | L&T:- Kaushal | N/A
27 | GIS | 472 | 472 | Critical | Date Not Available | Active to Passive, Active to active connectivity correction | Completed & Approved | L&T:- Kaushal | N/A
28 | GIS | 472 | 472 | Critical | Date Not Available | DI processing timing optimisation | Completed & Approved | L&T:- Kaushal | N/A
29 | GIS | 472 | 472 | Critical | Date Not Available | Rack to Rack Connectivity | Completed & Approved | L&T:- Kaushal | N/A
30 | GIS | 472 | 472 | Critical | Date Not Available | Graphical Symbology deployment against all object | Completed & Approved | L&T:- Kaushal | N/A
31 | GIS | 472 | 472 | Critical | Date Not Available | Fixing Of Labelling (Sequencing & Attributes) | Completed & Approved | L&T:- Kaushal | N/A
32 | GIS | 472 | 472 | Critical | Date Not Available | Object search options to user | Completed & Approved | L&T:- Kaushal | N/A
33 | GIS | 472 | 472 | Critical | Date Not Available | G-tech to .shp & Kml conversion | Completed & Approved | L&T:- Kaushal | N/A
34 | GIS | 472 | 472 | Critical | Date Not Available | Plotting & Print Feature | Completed & Approved | L&T:- Kaushal | N/A
35 | GIS | 472 | 472 | Critical | Date Not Available | 4 More API from Google Map | Completed & Approved | L&T:- Kaushal | N/A
36 | GIS | 472 | 472 | Critical | Date Not Available | Fibre Utilisation Reports | Completed & Approved | L&T:- Kaushal | N/A
37 | GIS | 472 | 472 | Critical | Date Not Available | Consolidated reports from GIS | Completed & Approved | L&T:- Kaushal | N/A
38 | GIS | 472 | 472 | Critical | Date Not Available | Link trace Reports | Completed & Approved | L&T:- Kaushal | N/A
39 | GIS | 472 | 472 | Critical | Date Not Available | Consolidation/Customization of Dashboard feature in G-tech, Network Portal | Completed & Approved | L&T:- Kaushal | N/A
40 | GIS | 472 | 472 | Critical | Date Not Available | Network data availability in G-Tech & Network portal & Geo media | Completed & Approved | L&T:- Kaushal | N/A
41 | GIS | 472 | 472 | Critical | Date Not Available | Final Demo to customer | Completed & Approved | L&T:- Kaushal | N/A
42 | GIS | 472 | 472 | NON-Critical | Date Not Available | Network availability in Mobile application with G-MAP | Completed & Approved | L&T:- Kaushal | N/A
43 | GIS | 472 | 472 | NON-Critical | Date Not Available | Red line, Red Point Feature deployment in Mobile application | Completed & Approved | L&T:- Kaushal | N/A
44 | GIS | 472 | 472 | NON-Critical | Date Not Available | JOB creation testing in GIS tool from GIS Mobile app | Completed & Approved | L&T:- Kaushal | N/A
45 | GIS | 472 | 472 | Critical | Date Not Available | Feasible Points closure of workshop | Completed & Approved | L&T:- Kaushal | N/A
46 | GIS | 472 | 472 | Critical | Date Not Available | T-NOC Creation in GIS Tool with connectivity | Completed & Approved | L&T:- Kaushal | N/A
47 | GIS | 472 | 472 | Critical | Date Not Available | SOP Creation | Completed & Approved | L&T:- Kaushal | N/A
48 | GIS | 472 | 472 | Critical | Date Not Available | Auto feasibility | Completed | L&T Kaushal & T-FIBER | N/A | BSS(knot) has demonstrated the Auto Feasibility feature for single location business cases. If, Customer is expecting Bulk feasibility capabilities, which is not a feature of GIS, required external tool.
49 | GIS | 472 | 472 | Critical | Date Not Available | MB kilometers vs UG and arial to path and over all route length to be added in webapplication | Completed & Approved | L&T:- Kaushal | N/A
50 | GIS | 472 | 472 | Critical | Date Not Available | 3 Formats of Lat long (DMS, DMM & Mtr) required in Hexagon tool | Completed & Approved | L&T:- Kaushal | N/A
51 | GIS | 472 | 472 | Critical | Date Not Available | Resources onboarding, Licences arrangement, Workstation plan | Completed | L&T Kaushal & T-FIBER | N/A | Resource & PCs has been deployed in NOC GIS room. for Licesnes dependecy on T FIber.
52 | GIS | 472 | 472 | Critical | Date Not Available | Physical Device sync-up with OSS System | WIP | OEM (Hexagon) Alignment Required | 2025-10-20 | Integration with OSS Is WIP
53 | GIS | 472 | 472 | NON-Critical | Date Not Available | Common Span Path | WIP | OEM (Hexagon) Alignment Required | 2025-11-05 | Integration with OSS Is WIP
54 | GIS | 472 | 472 | Critical | Date Not Available | GIS LLD submitted to T-Fiber on 02.03.2025, to be discussed with T-Fiber | Completed | L&T Kaushal & T-FIBER | N/A | Resubmission done after discussion. Date-19.03.25. queries on LLD with mail dated 25.03.25
55 | GIS | 472 | 472 | Severity Not Available | Date Not Available | GIS integration | Duplicate Points | No One | N/A | This is a general statement; the instigation scenario has already been addressed elsewhere (Duplicate with Points 52 & 53)
56 | GIS | 472 | 472 | Severity Not Available | Date Not Available | Exact SPAN/Link details must be taken from GIS(Including Lat,Long) for Fiber cut/outage scenario to undserstand fix is permanent or temporarary in nature and impact on Multiple Nodes/GP’s . | Duplicate Points | No One | N/A | The point has been addressed under Common Span Integration. Span and Link are confirmed to be in order. However, providing latitude and longitude for the cut location is not feasible due to the absence of the RFMS solution, Duplicate with Point 53
57 | GIS | 472 | 472 | Severity Not Available | Date Not Available | Inventory Synch - Physical devices with GIS | Duplicate Points | No One | N/A | This point has been covered under physical device sync-up point, Duplicate with Point 52
58 | GIS | 472 | 472 | Severity Not Available | Date Not Available | Ciena DWDM Network Topology has been created in HPE OSS topology MAP along with neighbour NE details. Adding the geographical map in the background of HPE OSS is possible with openstreet map.. Not posisble to integarted with GIS map | Shifted to OSS | OSS Team | N/A | Three types of data sharing options have been provided to OSS: Shapefile (.shp), KML format, WMS services, The HP team needs to assess the feasibility of integrating these options. No action pending from GIS 25 July 2025:- HP team has confirmed that their product does not support this functionality,According to the HP team, the new version is expected to be released in 2026
59 | GIS | Project Plan (L&T) | MOM | Severity Not Available | Date Not Available | GIS Integration and Common Span Data details | Duplicate Points | No One | N/A | The point has been addressed under Common Span Integration, Duplicate with Point 53
60 | GIS | Project Plan (L&T) | MOM | Severity Not Available | Date Not Available | UTM integration with GIS | Duplicate Points | No One | N/A | This point has been covered under physical device sync-up point, Duplicate with Point 52
61 | GIS | MOM | MOM | Severity Not Available | Date Not Available | Point No. 287: Exact SPAN/Link details must be taken from GIS (Including Lat, Long) for Fiber cut/outage scenario to understand fix is permanent or temporary in nature and impact on Multiple Nodes/GP’s. | Duplicate Points | No One | N/A | The point has been addressed under Common Span Integration. Span and Link are confirmed to be in order. However, providing latitude and longitude for the cut location is not feasible due to the absence of the RFMS solution Duplicate with Point 56
62 | GIS | T0-T5 | T0-T5 | Severity Not Available | Date Not Available | GIS Operations Resources | Completed | L&T Kaushal & T-FIBER | N/A | GIS operational resources have been deployed and are functioning from the NOC GIS Room
63 | GIS | T0-T5 | T0-T5 | Severity Not Available | Date Not Available | GI planning through GIS Bulk feasibility using new BSS with OSS API for GIS (P2) | Patrial Completed | L&T Management & TFIBER | N/A | GI planning using GeoMedia has been demonstrated, and the relevant documentation has been submitted.Auto feasibility of single location has been demonstrated with new BSS system , However, bulk feasibility requires an external application as this is not functionality of GIS system
64 | WFM | NOC Team | NOC | Critical | Date Not Available | User level view for Number of tasks assigned/resolved/closed Daily | Completed | L&T Kaushal & T-FIBER | N/A | Development Completed & Reports are available
65 | WFM | NOC Team | NOC | Critical | Date Not Available | User level view for Number of tasks assigned/resolved/closed Weekly | Completed | L&T Kaushal & T-FIBER | N/A | Development Completed & Reports are available
66 | WFM | NOC Team | NOC | Critical | Date Not Available | User level view for Number of tasks assigned/resolved/closed Monthly | Completed | L&T Kaushal & T-FIBER | N/A | Development Completed & Reports are available
67 | WFM | NOC Team | NOC | Critical | Date Not Available | User level view for Number of tasks assigned/resolved/closed (Selective from and to dates) | Completed | L&T Kaushal & T-FIBER | N/A | Development Completed & Reports are available
68 | WFM | NOC Team | NOC | Critical | Date Not Available | Management Dashboard Patroller Daily | Completed | L&T Kaushal & T-FIBER | N/A | The development is complete and can be demonstrated through three methods: reports, dashboards, and single-click interaction on the map
69 | WFM | NOC Team | NOC | Critical | Date Not Available | Management Dashboard Patroller Weekly | Completed | L&T Kaushal & T-FIBER | N/A | The development is complete and can be demonstrated through three methods: reports, dashboards, and single-click interaction on the map
70 | WFM | NOC Team | NOC | Critical | Date Not Available | Management Dashboard Patroller Monthly | Completed | L&T Kaushal & T-FIBER | N/A | The development is complete and can be demonstrated through three methods: reports, dashboards, and single-click interaction on the map
71 | WFM | NOC Team | NOC | Critical | Date Not Available | Management Dashboard Patroller (Selective from and to dates) | Completed | L&T Kaushal & T-FIBER | N/A | The development is complete and can be demonstrated through three methods: reports, dashboards, and single-click interaction on the map
72 | WFM | NOC Team | NOC | Critical | Date Not Available | Management Dashboard FRT Daily | Completed | L&T Kaushal & T-FIBER | N/A | The development is complete and can be demonstrated through three methods: reports, dashboards, and single-click interaction on the map
73 | WFM | NOC Team | NOC | Critical | Date Not Available | Management Dashboard FRT Weekly | Completed | L&T Kaushal & T-FIBER | N/A | The development is complete and can be demonstrated through three methods: reports, dashboards, and single-click interaction on the map
74 | WFM | NOC Team | NOC | Critical | Date Not Available | Management Dashboard FRT Monthly | Completed | L&T Kaushal & T-FIBER | N/A | The development is complete and can be demonstrated through three methods: reports, dashboards, and single-click interaction on the map
75 | WFM | NOC Team | NOC | Critical | Date Not Available | Management Dashboard FRT (Selective from and to dates) | Completed | L&T Kaushal & T-FIBER | N/A | The development is complete and can be demonstrated through three methods: reports, dashboards, and single-click interaction on the map
76 | WFM | NOC Team | NOC | Critical | Date Not Available | Management Dashboard Engineers Daily | Completed | L&T Kaushal & T-FIBER | N/A | The development is complete and can be demonstrated through three methods: reports, dashboards, and single-click interaction on the map
77 | WFM | NOC Team | NOC | Critical | Date Not Available | Management Dashboard Engineers Weekly | Completed | L&T Kaushal & T-FIBER | N/A | The development is complete and can be demonstrated through three methods: reports, dashboards, and single-click interaction on the map
78 | WFM | NOC Team | NOC | Critical | Date Not Available | Management Dashboard Engineers Monthly | Completed | L&T Kaushal & T-FIBER | N/A | The development is complete and can be demonstrated through three methods: reports, dashboards, and single-click interaction on the map
79 | WFM | NOC Team | NOC | Critical | Date Not Available | Management Dashboard Engineers (Selective from and to dates) | Completed | L&T Kaushal & T-FIBER | N/A | The development is complete and can be demonstrated through three methods: reports, dashboards, and single-click interaction on the map
80 | GIS | Feedback and Observations (from T-Fiber) | MOM | Severity Not Available | 2023-06-01 | Self-address to be auto-populated in G-Tech, eg - Refer OLA, Uber Apps. | Not Feasible | No One | N/A | The GTECH application does not support this functionality. However, this feature is available in the mobile application, where the user's current location is automatically displayed on the map., 11 July 2025:- A follow-up discussion with the OEM is required to assess feasibility. If it is found to be unfeasible, a call should be arranged with Sanjay Sir along with the OEM team & artefacts needs to submit
81 | GIS | Feedback and Observations (from T-Fiber) | MOM | Severity Not Available | 2023-06-01 | Approval mechanism to be made available for any object changes/deletion. | Completed | L&T Kaushal & T-FIBER | N/A | Approval Mechanism has been incorporated in SOP, any operational changes will not be incorporated based upon direct information received from field, it will be through mail approval from Mandal/District & Zonal in charge, drastic change will be done after approval of O&M head.
82 | GIS | Feedback and Observations (from T-Fiber) | MOM | Critical | 2023-06-01 | Change Management Log /User Log history to be developed and made available in Hexagon Tool. | Completed | L&T Kaushal & T-FIBER | N/A | User log History feature has been deployed in production.
83 | GIS | Feedback and Observations (from T-Fiber) | MOM | Severity Not Available | 2023-06-01 | Data Validation Rules document to be submitted to T-Fiber. | Completed | L&T Kaushal & T-FIBER | N/A | Data Validation Document (DI) logic & user manual has been shared to all MSI, TPA along with T-FIBER representatives.
84 | GIS | Feedback and Observations (from T-Fiber) | MOM | Severity Not Available | 2023-06-01 | Actual Measure Length and Loop length to be corrected in BOQ. | Completed | L&T Kaushal & T-FIBER | N/A
85 | GIS | Tool Features | MOM | Severity Not Available | 2023-06-07 | Document/Image Hyperlink feature | Completed | L&T Kaushal & T-FIBER | N/A | Demo has been provided to TFIBER Core Team
86 | GIS | Tool Features | MOM | Severity Not Available | 2023-06-07 | Validation documents | Completed | L&T Kaushal & T-FIBER | N/A
87 | GIS | Feedback and Observations (from TPA) | MOM | NON-Critical | 2023-06-07 | New validation Logic to be incorporated in DI tool - if Depth is zero and construction method is HDD/OT, Protection is required | Completed | L&T Kaushal & T-FIBER | N/A
88 | GIS | Feedback and Observations (from TCIL) | MOM | Severity Not Available | 2023-06-07 | As Time and Efforts are being expended for formation of splicing, in case there are further changes to validation rules, responsibility to be assigned for any further changes to be done to the data already uploaded in the GIS tool. | Completed | L&T Kaushal & T-FIBER | N/A | Splicing automated 60%
89 | GIS | Tool Features | MOM | Severity Not Available | 2023-06-19 | BoQ Feature for active elements and infra | Completed | L&T Kaushal & T-FIBER | N/A | Demo has been provided to TFIBER Core Team
90 | GIS | Feedback and Observations (from T-Fiber) | MOM | Critical | 2023-06-19 | Director, P&E, T-Fiber asked for feature to add card level, module level, slot level detail , L&T responded that addition of card / module / slot is not supported, feature is available to add port level detail. | Completed | L&T Kaushal & T-FIBER | N/A
91 | GIS | Feedback and Observations (from T-Fiber) | MOM | Severity Not Available | 2023-06-19 | Both OSS and GIS should throw error if any sync issues related to data. | WIP | OEM (Hexagon) Alignment Required | 2025-10-30 | Solution is WIP full & delta sync reports will be available in this solution.
92 | GIS | Demonstration of GIS Modules (Network Portal, IGD Dashboards & GIS Mobile Application) | MOM | Severity Not Available | 2025-01-24 | Since the Network Portal allows attribute editing, TFIBER expressed concerns about the data security & safely of granting edit rights to field users. The GIS SME and Hexagon team responded that they would provide a separate URL with view-only rights for field users. This point was closed by creating a separate URL (http://172.28.30.15/Nwportal2) for users with view-only access only for field users. | Completed | L&T Kaushal & T-FIBER | N/A
93 | GIS | Demonstration of GIS Modules (Network Portal, IGD Dashboards & GIS Mobile Application) | MOM | Severity Not Available | 2025-01-24 | TFIBER inquired about the possibility of exporting the entire Mandal data through the NW Portal. Hexagon and L&T explained that this is not possible through the NW Portal, but the option is available in GTECH | Completed | L&T Kaushal & T-FIBER | N/A
94 | GIS | Demonstration of GIS Modules (Network Portal, IGD Dashboards & GIS Mobile Application) | MOM | Severity Not Available | 2025-01-24 | TFIBER inquired about the authentication of Redline and Red points raised by the field team and whether there is an approval process within the application. The GIS/WFM SME and Hexagon team explained that this option is not available in the application. However, the approval process can be followed offline through email communication from the GIS user to the respective district/Mandal Manager. TFIBER requested that the names of the GIS operation leads from each package, who will follow this practice and take responsibility for correct input in GIS, be provided. | Completed | L&T Kaushal & T-FIBER | N/A
95 | GIS | Application | MOM | Severity Not Available | 2020-09-01 | Application deployment in DR | Completed | L&T Kaushal & T-FIBER | N/A
96 | GIS | Data set for assessment | MOM | Severity Not Available | 2020-09-01 | Mission Bhagiratha water routes small data set for assessment | Completed | L&T Kaushal & T-FIBER | N/A | MB section duct data is being captured during the data mandal wise uploads in G/Tech. And the duct not laid sections will be mapped at the time of reconciliation of mission Bhagiratha ducts as per the provided guidelines.
97 | GIS | GIS(Integration) | MOM | Severity Not Available | 2023-04-04 | Approach Finalisation between cross domain (OSS,BSS) OEMs | Completed | L&T Kaushal & T-FIBER | N/A
98 | GIS | GIS(Integration) | MOM | Severity Not Available | 2023-04-04 | Integration Deployment as per Project Requirements | WIP | OEM (Hexagon) Alignment Required | 2025-11-05
99 | GIS | GIS(Integration) | MOM | Severity Not Available | 2023-04-04 | Integration Testing | WIP | OEM (Hexagon) Alignment Required | 2025-11-10
100 | GIS | Network data Migration in GIS | MOM | Severity Not Available | 2023-04-04 | Fixing of Validation Errors | Completed | L&T Kaushal & T-FIBER | N/A
101 | GIS | GIS Related | MOM | Severity Not Available | 2023-01-09 | Bulk splicing for T-Joints & straight,FDMS termination, Active to passive possibilitys | Completed | L&T Kaushal & T-FIBER | N/A | All possible Automation has been completed
102 | GIS | GIS Related | MOM | Severity Not Available | 2023-01-09 | OSM Scale visibility needs to correct | Completed | L&T Kaushal & T-FIBER | N/A | OSM Removed & Google Map integrated
103 | GIS | GIS Related | MOM | Severity Not Available | 2023-01-09 | Geopolitical boundaries should differentiate by different colours | Completed | L&T Kaushal & T-FIBER | N/A
104 | GIS | GIS Related | MOM | Severity Not Available | 2023-01-09 | All data model objects should be present in default legend | Completed | L&T Kaushal & T-FIBER | N/A
105 | GIS | GIS Related | MOM | Severity Not Available | 2023-01-09 | All data model objects should be present in default Create new feature functionalities | Completed | L&T Kaushal & T-FIBER | N/A
106 | GIS | GIS Related | MOM | Severity Not Available | 2020-12-26 | Creation of GIS to HP NMS integration web service | Deferred | No One | N/A | 11-07-2025:- Required To send email to Sanjay sir (Differed Point)
107 | GIS | GIS Related | MOM | Severity Not Available | 2023-05-23 | 1. Error validation count should be shown in black instead of red color after resolving/fixing the issues ( Hexagon Needs to check feasibility) | Completed | L&T Kaushal & T-FIBER | N/A
108 | GIS | GIS Related | MOM | Severity Not Available | 2023-05-23 | 2. If Geo political boundaries changed, there is a possibility to change in GIS also ( asked by T-FIBER) :- L&T/HEAXGON:- Yes It possible as Geopolitical layer still present/ Manual changes also allowed. | Completed | L&T Kaushal & T-FIBER | N/A
109 | GIS | GIS Related | MOM | Severity Not Available | 2023-05-23 | 3. Background Google map ( Image tilers and detail of images was showing) :- L&T:- Needs to check with Google, ( It is permanent or temporary showing ) | Completed | L&T Kaushal & T-FIBER | N/A | As discussed with Google it will auto adjust on the Zoom in zoom out
110 | GIS | GIS Related | MOM | Severity Not Available | 2023-05-23 | 5. OFC Cable overlapping with buildings ,need to incorporated as P2 Error L&T :- L&T:- Logic incorporated and deployed in production | Completed | L&T Kaushal & T-FIBER | N/A
111 | GIS | GIS Related | MOM | Severity Not Available | 2023-05-23 | 6. Symbology finalization required from MSIs :- L&T:- As it was not part of basic tool readiness, however development is underway. | Completed | L&T Kaushal & T-FIBER | N/A
112 | GIS | GIS Related | MOM | Severity Not Available | 2023-05-23 | 7. Log required of not uploaded object. L&T :- Logic incorporated and deployed in production, log will be present in Mandal data folder, additional logic incorporated if loop length is less that 0 DI will throw error, In GHANPUR MANDAL Loop length was 0 for one loop | Completed | L&T Kaushal & T-FIBER | N/A
113 | GIS | GIS Related | MOM | Severity Not Available | 2023-05-23 | 8. New Logic required in G-TECH, per path type 48F Cable L&T:- Logic incorporated and deployed in production, below are logic If Path type not contains any “+” , cable should be 48 size or more If Path type contains one “+” symbol , cable should be 96 size or more If Path type contains two “+” symbol , cable should be 144 size or more If Path type contains three to five “+” symbol , cable should be 288 size. | Completed | L&T Kaushal & T-FIBER | N/A
114 | GIS | GIS Related | MOM | Severity Not Available | 2023-05-23 | 9. Missing splicing on joints by DI Log required L&T:- Logic incorporated and deployed in production | Completed | L&T Kaushal & T-FIBER | N/A
115 | GIS | GIS Related | MOM | Severity Not Available | 2023-05-23 | 10. Common centralized storage required in NOC to create data (LIDAR Survey & GIS Documents/Images) repository, minimum 200 TB capacity required, L&T :- Will discuss internally and update | Completed | L&T Kaushal & T-FIBER | N/A
116 | GIS | GIS Related | MOM | Severity Not Available | 2023-05-23 | 11. BOQ Pole count repetition, Cable length will be total length only (as Existing Logic), all line feature in length in Mtr & Point feature counts ( It has fixed and deployed in production) | Completed | L&T Kaushal & T-FIBER | N/A
117 | GIS | Advance Readiness | MOM | Severity Not Available | 2023-05-25 | Map Ruler feature in Mtr. Cm & Km | Completed | L&T Kaushal & T-FIBER | N/A
118 | GIS | Advance Readiness | MOM | Severity Not Available | 2023-05-25 | Required Custom commands on tool ribbon instead of Landy process | Completed | L&T Kaushal & T-FIBER | N/A
119 | GIS | Advance Readiness | MOM | Severity Not Available | 2023-05-25 | By look Chainage type & Depth profile on Map | Completed | L&T Kaushal & T-FIBER | N/A
120 | GIS | GIS Related | MOM | Severity Not Available | Date Not Available | FIBER SIZE VS Common path ex 96F= GPR1+MAR2 | Completed | L&T Kaushal & T-FIBER | N/A | It can be analysed from BOQ report
121 | GIS | GIS Related | MOM | Severity Not Available | Date Not Available | LGD Code search option | Completed | L&T Kaushal & T-FIBER | N/A
122 | GIS | GIS Related | MOM | Severity Not Available | Date Not Available | ZOOMING VS Text visibility | Completed | L&T Kaushal & T-FIBER | N/A
123 | GIS | GIS Related | During Review | Severity Not Available | Date Not Available | Exporting data to other formats in Web application (kmz, shp) | Not Feasible | No One | N/A | This feature is not feasible within the web application. However, it is already available in GTECH and has been demonstrated, 11 July 2025:- A follow-up discussion with the OEM is required to assess feasibility. If it is found to be unfeasible, a call should be arranged with Sanjay Sir along with the OEM team & artefacts needs to submit
124 | GIS | Resource Related | MOM | Critical | 2023-04-03 | Evaluation of License Sufficiency and Ramp-Up Plan | Pending | L&T Management & TFIBER | _ | TFIBER is a critical dependency for closing the GIS licenses
125 | GIS | Functional AT Plan | MOM | NON-Critical | 2023-04-19 | Loading Sample Data and Internal Quality Test Report Submission | Completed | L&T Kaushal & T-FIBER | N/A
126 | GIS | Functional AT Plan | MOM | Critical | 2023-05-18 | Basic GIS Tool UAT for TPA | Pending | TFIBER & TPA | _ | The ATP was submitted, discussed with the TPA, and all feedback was incorporated. The revised ATP has also been sent
127 | GIS | User Experience | MOM | Critical | 2023-06-01 | Google Map availability in Geo Media Tool, Hexagon clarified that Google Map feature is not available in Geo Media as it is a client based independent tool which can be installed in client PCs; however, end users can use OSM and/or Bing maps along with Geo media | Completed | L&T Kaushal & T-FIBER | N/A | Google Map availability in Geo Media Tool, Hexagon clarified that Google Map feature is not available in Geo Media as it is a client based independent tool which can be installed in client PCs; however, end users can use OSM and/or Bing maps along with Geo media
128 | GIS | User Experience | MOM | Critical | 2023-06-01 | Fixed Topology Nomenclature | Completed | L&T Kaushal & T-FIBER | N/A
129 | GIS | User Experience | MOM | Critical | 2023-06-01 | Character size in G-Tech | Completed | L&T Kaushal & T-FIBER | N/A
130 | GIS | User Experience | MOM | Critical | 2023-06-01 | Searching for location accuracy in G-Tech with pinpoint accuracy | Completed | L&T Kaushal & T-FIBER | N/A
131 | GIS | User Experience | MOM | Critical | 2023-06-01 | Self-address auto-population in G-Tech | Duplicate Points | No One | N/A | Duplicate with Point- 80
132 | GIS | User Experience | MOM | Critical | 2023-06-01 | GPON Fiber Termination plan adherence | Completed | L&T Kaushal & T-FIBER | N/A
133 | GIS | Handbook & SOPs | MOM | Critical | 2023-06-07 | Approval mechanism for object changes/deletion | Duplicate Points | No One | N/A | Duplicate with Point- 81
134 | GIS | Handbook & SOPs | MOM | Critical | 2023-06-07 | Change Management Log/User Log history | Duplicate Points | No One | N/A | Duplicate with Point- 82
135 | GIS | Handbook & SOPs | MOM | Critical | 2023-06-07 | Data Validation Rules document | Completed | L&T Kaushal & T-FIBER | N/A
136 | GIS | User Experience | MOM | NON-Critical | 2023-06-07 | Show duct length, Cable length, chambers, and joint closures in a Mandal | Completed | L&T Kaushal & T-FIBER | N/A
137 | GIS | User Experience | MOM | NON-Critical | 2023-06-07 | Correct Actual Measure Length and Loop length in BOQ | Completed | L&T Kaushal & T-FIBER | N/A
138 | GIS | Handbook & SOPs | MOM | NON-Critical | 2023-06-07 | Detailed validation document | Completed | L&T Kaushal & T-FIBER | N/A
139 | GIS | User Experience | MOM | Critical | 2023-06-07 | Hyperlink real images to GPs and Mandals | Completed | L&T Kaushal & T-FIBER | N/A
140 | GIS | Installation | MOM | Critical | 2023-06-07 | 100TB storage for LIDAR survey data | Completed | L&T Kaushal & T-FIBER | N/A
141 | GIS | Training | MOM | NON-Critical | 2023-06-07 | Hands-on Training on GIS tool | Completed | L&T Kaushal & T-FIBER | N/A
142 | GIS | Dashboards | MOM | NON-Critical | 2023-06-07 | Discuss and Develop Dashboard for GIS tool | Completed | L&T Kaushal & T-FIBER | N/A
143 | GIS | User Experience | MOM | Critical | 2023-06-19 | Download active port connectivity details | Completed | L&T Kaushal & T-FIBER | N/A | Link Trace Report Download
144 | GIS | User Experience | MOM | Critical | 2023-06-19 | Real-time sync of topology details from OSS | WIP | OEM (Hexagon) Alignment Required | 2025-10-20
145 | GIS | User Experience | MOM | Critical | 2023-06-19 | automate active connectivity within site with logical link name populated from OSS | Not Feasible | No One | N/A | Based on discussions with the OSS and GIS teams, integration is not feasible, and automation of connectivity cannot be implemented, 11th July 2025, a discussion is needed with Siva Sir to explore in-house solution possibilities.
146 | GIS | Functional AT Plan | MOM | Critical | 2023-06-19 | TPA to validate active-active connectivity | Completed | L&T Kaushal & T-FIBER | N/A
147 | GIS | User Experience | MOM | Critical | 2023-06-19 | Add card/module/slot level details | Duplicate Points | No One | N/A | Duplicate with Point- 90
148 | GIS | User Experience | MOM | Critical | 2023-06-19 | Ensure Topology name uniqueness | Duplicate Points | No One | N/A | Duplicate with Point- 128
149 | GIS | User Experience | MOM | Critical | 2023-06-19 | BoQ feature to download passive/active devices separately | Completed | L&T Kaushal & T-FIBER | N/A
150 | GIS | User Experience | MOM | Critical | 2023-06-19 | Bulk Feasibility closure case reports from GIS | Pending | L&T Management & TFIBER | _ | To fulfill this requirement, an external feasibility application or tool is needed, as it cannot be achieved within the GIS application, 11 July 2025:- TFIBER is not agreed, asked to take with L&T upper management
151 | GIS | User Experience | MOM | Critical | 2023-06-19 | Route path identification through Google | Completed | L&T Kaushal & T-FIBER | N/A
152 | GIS | User Experience | MOM | Critical | 2023-06-19 | Network portal search functionality for objects | Completed | L&T Kaushal & T-FIBER | N/A
153 | GIS | User Experience | MOM | Critical | 2023-06-19 | GIS function for bulk feasibility report | Pending | L&T Management & TFIBER | _ | To fulfill this requirement, an external feasibility application or tool is needed, as it cannot be achieved within the GIS application,11 July 2025:- TFIBER is not agreed, asked to take with L&T upper management
154 | GIS | User Experience | MOM | Critical | 2023-06-19 | building logic / intelligence to populate the relevant information in the BoQ, presently available as a dump. | Completed | L&T Kaushal & T-FIBER | N/A
155 | GIS | Integration | MOM | Critical | 2023-06-19 | GIS integration with WFM tool | Completed | L&T Kaushal & T-FIBER | N/A
156 | GIS | User Experience | MOM | Critical | 2023-06-19 | Automation of active connectivity | Duplicate Points | No One | N/A | Duplicate with Point- 145
157 | GIS | Integration | MOM | Critical | 2023-06-19 | Sync issue error alerts in OSS and GIS | WIP | OEM (Hexagon) Alignment Required | 2025-10-20
158 | GIS | Design Features | MOM | Critical | 2024-01-24 | Discuss internally and provide a feasible response about leading the GIS data update process | Completed | L&T Kaushal & T-FIBER | N/A
159 | GIS | GIS Completion | MOM | Critical | 2023-07-04 | GIS OEM - Hexagon: L&T to ensure GIS readiness within 2 to 4 weeks for service provisioning automation. | Completed | L&T Kaushal & T-FIBER | N/A
160 | GIS | GIS Completion | MOM | Critical | 2023-07-05 | Evaluate the current readiness status of the GIS tool and address the pending issues. | Completed | L&T Kaushal & T-FIBER | N/A
161 | GIS | GIS Completion | MOM | Critical | 2023-07-05 | Submit revise plan for Complete GIS Tool (Basic) Readiness by 30th April’23, GIS Tool (Advanced) Readiness by 31st May’23, and GIS Tool (Integration) Readiness by 30th June’23. | Completed | L&T Kaushal & T-FIBER | N/A
162 | GIS | GIS Completion | MOM | Critical | 2023-07-05 | Submit responses on concerns of the number of GIS licences for data upload and readiness of current helpdesk to start taking calls for GI. | Completed | L&T Management & TFIBER | N/A | TFIBER is a critical dependency for closing the GIS licenses
163 | GIS | GIS Completion | MOM | Critical | 2023-07-05 | Integrate the processes recommended by the external auditor into the process flow of GIS readiness. | Completed | L&T Kaushal & T-FIBER | N/A | GIS SOP
164 | GIS | GIS Completion | MOM | Critical | 2023-07-05 | Improve coordination with GIS, OEMs, and explore the possibility of developing a new GIS OEM to deliver the requirements of T-Fiber. | Completed | L&T Kaushal & T-FIBER | N/A
165 | GIS | Launch Readiness | MOM | Critical | 2023-08-01 | Each MSI needs to commit to the target for Mandal upload in the GIS tool for business readiness. | Completed | L&T Kaushal & T-FIBER | N/A
166 | GIS | Launch Readiness | MOM | Critical | 2023-08-01 | Commit target dates for GIS Data Upload for each package. | Completed | L&T Kaushal & T-FIBER | N/A
167 | GIS | Launch Readiness | MOM | Critical | 2023-08-01 | Package A needs to provide a day by day Mandal upload action plan to meet the committed target dates. | Completed | L&T Kaushal & T-FIBER | N/A
168 | GIS | Launch Readiness | MOM | Critical | 2023-08-01 | Packages B and C are expected to submit a proposal to hasten data upload in consultation with GIS-SME, Pkg-A. | Completed | L&T Kaushal & T-FIBER | N/A
169 | GIS | Launch Readiness | MOM | Critical | 2023-08-01 | The current committed dates for GIS Data Upload are not meeting the expectations of T-Fiber. | Completed | L&T Kaushal & T-FIBER | N/A
170 | WFM | GIS Related | MOM | Critical | 2023-12-15 | Geo-fencing: L&T to explain how geo-fencing shall work for a fiber route and how it will be assigned for Mandal and GP locations. | Completed | L&T Kaushal & T-FIBER | N/A
171 | WFM | GIS Completion | MOM | Critical | 2023-12-19 | BSS-SME, L&T to ensure Dark Fiber with BSS and WFM flows can be shown by 30th December '23. | Pending | BSS Team | _ | Dark fiber integration has been completed with the OLD BSS-WFM system, and a demonstration has been provided. The new BSS system now needs to be prepared to support this integration, Dependency On New BSS
172 | GIS | Feasibility Logic | MOM | Critical | 2023-12-19 | Feasibility Logic: SVP, T-Fiber asked for the feasibility logic to include S1, S2 splitters and to be demonstrated in the next demo. | Completed | L&T Kaushal & T-FIBER | N/A | Dependency On OSS Splitter View has been given to OSS team
173 | GIS | Feasibility Logic | MOM | Critical | 2023-12-19 | Bandwidth Feasibility Logic: Director-P&E, T-Fiber requested the logic for Bandwidth feasibility in the backhaul to be provisioned and operationalised immediately. | Shifted to OSS | OSS Team | N/A | This point not related to GIS,11th July 2025:- As discussed with Sanjay Sir, this points need to be move to the OSS team.
174 | GIS | Integration | MOM | Critical | 2024-01-18 | Integrate live data for location feasibility | Shifted to OSS | OSS Team | N/A | This point not related to GIS,External Feasibility Tool is required ,11th July 2025:- As discussed with Sanjay Sir, this points need to be move to the OSS team.
175 | GIS | Integration | MOM | Critical | 2024-01-18 | Review and align ‘Ready for Service’ nomenclature | Shifted to OSS | OSS Team | N/A | This point not related to GIS, 11th July 2025:-this point needs to be discussed with Siva Sir to explore the possibility of accommodating the feature in the respective application, as it is not related to GIS
176 | GIS | User Experience | MOM | Critical | 2025-04-03 | GIS: Make a PPT for operationalisation of GIS Ops & updation. This will be shared to PKG-B & C | Completed | L&T Kaushal & T-FIBER | N/A
177 | WFM | User Experience | MOM | Critical | 2023-07-26 | Support for translation to Telugu | Not Feasible | No One | N/A | As per OEM this point is not feasible 11 July 2025:- A follow-up discussion with the OEM is required to assess feasibility. If it is found to be unfeasible, a call should be arranged with Sanjay Sir along with the OEM team & artefacts needs to submit
178 | WFM | Handbook & SOPs | MOM | Critical | 2023-07-26 | Scope of Order Processing and Service Ticket Management | Completed | L&T Kaushal & T-FIBER | N/A
179 | WFM | Handbook & SOPs | MOM | Critical | 2023-07-26 | Document references in SOW to be shared | Completed | L&T Kaushal & T-FIBER | N/A
180 | WFM | User Experience | MOM | Critical | 2023-07-26 | WFM tool's own Google Map | Completed | L&T Kaushal & T-FIBER | N/A
181 | WFM | Improvement | MOM | Critical | 2023-07-26 | Support for Re-assignment of workflow in case of leave | Completed | L&T Kaushal & T-FIBER | N/A
182 | WFM | Improvement | MOM | Critical | 2023-07-26 | Support for pre-defined routes | Completed | L&T Kaushal & T-FIBER | N/A
183 | WFM | User Experience | MOM | Critical | 2023-07-26 | Support for recording timeclocks of patrol routes | Completed | L&T Kaushal & T-FIBER | N/A
184 | WFM | User Experience | MOM | Critical | 2023-07-26 | Support for Barcode and QR code scanning | Completed | L&T Kaushal & T-FIBER | N/A
185 | WFM | Handbook & SOPs | MOM | Critical | 2023-07-26 | Confirmation of SOW addressing Packages B and C | Completed | L&T Kaushal & T-FIBER | N/A
186 | WFM | User Experience | MOM | Critical | 2023-07-26 | Clear definition and availability of existing filters in WFM dashboards | Completed | L&T Kaushal & T-FIBER | N/A | 11-7-2025:- The dashboard and report filter options should be showcased during the WFM application demonstration.
187 | WFM | User Experience | MOM | Critical | 2023-07-26 | Upload of video | Not Feasible | No One | N/A | As per OEM this point is not feasible 11 July 2025:- A follow-up discussion with the OEM is required to assess feasibility. If it is found to be unfeasible, a call should be arranged with Sanjay Sir along with the OEM team & artefacts needs to submit
188 | WFM | Dashboards | MOM | Critical | 2023-07-26 | Support for Workforce Management productivity statistics | Completed | L&T Kaushal & T-FIBER | N/A | 11-7-2025:- Various reports should be demonstrated during the WFM application demo to showcase its capabilities.
189 | WFM | Improvement | MOM | Critical | 2023-07-26 | Check if NOC Workforce Management is handled by the proposed WFM tool | Pending | L&T:- Kaushal | 2025-09-30 | The WFM application is designed to manage field force operations, task assignments, and service delivery. Separate licenses & functionally & user role will be required for managing NOC resources. 11 July 2025:- A note needs to be sent to Sanjay Sir outlining the benefits, potential duplication of work, and any associated drawbacks.
190 | WFM | Improvement | MOM | Critical | 2023-07-26 | Coverage of Planned Event Manpower assignment by WFM solution | Pending | OEM Aliment Required (Lepton & OT) / Field Team | 2025-10-30 | OT System Dependency
191 | WFM | Handbook & SOPs | MOM | Critical | 2023-07-26 | Overall fitment of WFM in E2E applications architecture with integration touchpoints highlighted, along with the WFM flows | Completed | L&T Kaushal & T-FIBER | N/A
192 | WFM | Handbook & SOPs | MOM | Critical | 2023-07-26 | Clarity required on the scope of WFM under Phase-2 and sharing of Phase-1 & 2 scope with T-Fiber | Completed | L&T Kaushal & T-FIBER | N/A | BSS Integration was on phase-II however it has integrated in phase-I
193 | WFM | Integration | MOM | Critical | 2023-07-26 | Integration with Material Management systems, ERP systems, and On-Demand dashboards to be covered in Phase-2 | Completed | L&T Kaushal & T-FIBER | N/A | For GI service delivery, the ONT inventory management feature has been given into the WFM application & integration completed between web & mobile also with BSS . application supports ONT authentication and inventory tracking. Additionally, various dashboards have been provided within the WFM application to enhance monitoring and management capabilities
194 | WFM | Improvement | MOM | Critical | 2023-07-26 | Proposed WFM solution support field personnel to schedule appointments with end customers | Completed | L&T Kaushal & T-FIBER | N/A | Customer appointment is being handled by BSS and FE appointment by WFM
195 | WFM | Handbook & SOPs | MOM | Critical | 2023-07-26 | Finalization of Operational Processes linked to WFM workflows | Completed | L&T Kaushal & T-FIBER | N/A
196 | WFM | Resource Related | MOM | Critical | 2023-07-26 | Perpetual licenses for WFM | Pending | L&T Management & TFIBER | _ | TFIBER is a critical dependency for closing the WFM license
197 | WFM | Handbook & SOPs | MOM | Critical | 2023-07-26 | To check for potential overlapping functions between proposed WFM app and GIS O&M app, and accordingly streamline the Operational process | Completed | L&T Kaushal & T-FIBER | N/A
198 | WFM | Improvement | MOM | Critical | 2023-07-26 | Manual overwrite of data | Completed | L&T Kaushal & T-FIBER | N/A | 11-7-2025:-WFM does not allow any manual data overwrite scenarios
199 | WFM | User Experience | MOM | Critical | 2023-07-26 | Verification process for checking whether the field technician has gone to the required location or not. | Completed | L&T Kaushal & T-FIBER | N/A
200 | WFM | WFM Application | MOM | Critical | 2023-09-26 | Clarify the distinction between smart app and WFM. | Completed | L&T Kaushal & T-FIBER | N/A
201 | WFM | WFM Application | MOM | Critical | 2024-01-25 | Complete the WFM-OSS integration | WIP | OEM (Lepton) Alignment Required | 2025-12-10
202 | WFM | WFM Application | MOM | Critical | 2024-01-25 | Understand use cases of WFM integration with BSS | Completed | L&T Kaushal & T-FIBER | N/A
203 | WFM | WFM Application | MOM | Critical | 2024-01-25 | Define authorization of PoP RFS criteria for approval | Shifted to OSS | OSS Team | N/A | Not a WFM Point 11th July 2025:-this point needs to be discussed with Siva Sir to explore the possibility of accommodating the feature in the respective application, as it is not related to WFM
204 | WFM | WFM Application | MOM | Critical | 2024-01-25 | Complete Fault Management and Trouble Ticketing assignment (OSS to WFM) | WIP | OEM (Lepton) Alignment Required | 2025-12-10 | DWDM Completed
205 | WFM | WFM Application | MOM | Critical | 2024-01-25 | Distinguish between the use of GIS mobile app and WFM mobile app | Completed | L&T Kaushal & T-FIBER | N/A
206 | WFM | WFM Application | MOM | Critical | 2024-01-25 | Submit the NDA signed between L&T and M/S Lepton | Completed | L&T Kaushal & T-FIBER | N/A
207 | WFM | WFM Application | MOM | Critical | 2024-01-25 | Submit sample reports and dashboards of WFM package | Completed | L&T Kaushal & T-FIBER | N/A
208 | WFM | WFM Application | MOM | Critical | 2024-01-25 | Verify proposed solution for WFM | Completed | L&T Kaushal & T-FIBER | N/A
209 | WFM | WFM Application | MOM | Critical | 2024-01-25 | Dry run and operationalize three routes for testing WFM with actual data | Completed | L&T Kaushal & T-FIBER | N/A
210 | WFM | WFM Application | MOM | Critical | 2024-01-25 | Conduct weekly training sessions for patrollers on WFM app | Completed | L&T Kaushal & T-FIBER | N/A | Completed on 100 Licenced Users, three months weekly training provide to PKG-A, Training given to PKG-B & C also
211 | WFM | WFM Application | MOM | Critical | 2024-01-25 | Check and confirm the watermarking feature on photos taken by field users | Completed | L&T Kaushal & T-FIBER | N/A
212 | WFM | Mobile Applications | MOM | Critical | 2023-07-04 | Develop and present mobile applications that are functional and meet the needs and preferences of users by 15th August '23. | Completed | L&T Kaushal & T-FIBER | N/A
213 | WFM | WFM Related | MOM | Critical | 2023-07-21 | WFM Integration: L&T commenced WFM integration and will arrange a demonstration for field operations . | Completed | L&T Kaushal & T-FIBER | N/A
214 | WFM | WFM Related | MOM | Critical | 2023-07-21 | Mobile App & WFM: SVP, T-Fiber requested clarity on the number of mobile apps and urged L&T to freeze the scope in consultation with MSI B and C. Demo with M/S Lepton scheduled for 21st June '23 . | Completed | L&T Kaushal & T-FIBER | N/A
215 | WFM | WFM Related | MOM | Critical | 2023-07-26 | Finalise and share the scope of work (SOW) for Work Force Management solution implementation with M/S Lepton. | Completed | L&T Kaushal & T-FIBER | N/A
216 | WFM | WFM Related | MOM | Critical | 2023-07-26 | Support for translation to Telugu to be checked with M/S Lepton. | Duplicate Points | No One | N/A | Duplicate with Point- 177
217 | WFM | WFM Related | MOM | Critical | 2023-07-26 | Clarity on the term “As-is solution to be deployed” under Order Management is to be provided. | Completed | L&T Kaushal & T-FIBER | N/A
218 | WFM | WFM Related | MOM | Critical | 2023-07-26 | Support for Barcode scanning as well as QR code scanning to be checked with M/S Lepton. | Completed | L&T Kaushal & T-FIBER | N/A
219 | WFM | WFM Related | MOM | Critical | 2023-07-26 | Receive clarification on the support for re-assignment of workflow in case a Field Technician is on leave. | Completed | L&T Kaushal & T-FIBER | N/A | Manager has to reassign TT to different FE
220 | WFM | WFM Related | MOM | Critical | 2023-07-26 | Verify processes for recording of timelocks of patrol routes. | Completed | L&T Kaushal & T-FIBER | N/A
221 | WFM | WFM Related | MOM | Critical | 2023-07-26 | Improve the clarity, definition, and availability of existing filters in WFM dashboards. | Duplicate Points | No One | N/A | Duplicate with Point- 186
222 | WFM | WFM Related | MOM | Critical | 2023-07-26 | Video upload support. | Duplicate Points | No One | N/A | Duplicate with Point- 187
223 | WFM | WFM Related | MOM | Critical | 2023-07-26 | Support for Workforce Management productivity statistics mentioned that this shall fall under the customisation scope. | Duplicate Points | No One | N/A | Duplicate with Point- 188
224 | WFM | WFM Related | MOM | Critical | 2023-07-26 | Coordination required with NOC, Operations, and Projects team of 3 MSIs for the WFM Demo of 3 Packages including BSS-SME- L&T. | Completed | L&T Kaushal & T-FIBER | N/A
225 | WFM | WFM Related | MOM | Critical | 2023-07-26 | Asses if NOC Work Force Management is handled by the proposed WFM tool | Duplicate Points | No One | N/A | Duplicate with Point- 189
226 | WFM | WFM Related | MOM | Critical | 2023-07-26 | Samples or actual reports and dashboards based on operational processes to be presented by 28th July’23. | Duplicate Points | No One | N/A | Duplicate with Point- 207
227 | WFM | WFM Related | MOM | Critical | 2023-07-26 | Assessment to ensure that planned Event Manpower assignment is covered by the WFM solution. | Duplicate Points | No One | N/A | Duplicate with Point- 190
228 | WFM | WFM Related | MOM | Critical | 2023-07-26 | Assessment about whether the proposed WFM solution supports field personnel to schedule appointments with end customers. | Duplicate Points | No One | N/A | Duplicate with Point- 194
229 | WFM | WFM Related | MOM | Critical | 2023-07-26 | Ensure the licenses for WFM are perpetual. | Duplicate Points | No One | N/A | Duplicate with Point- 196
230 | WFM | WFM Application | MOM | Critical | 2023-08-18 | WFM Tool Usage Demonstration: L&T to arrange a demonstration of WFM tool usage for field operations soon. | Duplicate Points | No One | N/A | Duplicate with Point- 235
231 | WFM | WFM Related | MOM | Critical | 2023-08-23 | Respond to the query of WFM integration. | Completed | L&T Kaushal & T-FIBER | N/A
232 | WFM | WFM Related | MOM | Critical | 2023-08-31 | Schedule WFM integration with BSS demo for 15th September '23. | Completed | L&T Kaushal & T-FIBER | N/A
233 | WFM | WFM Related | MOM | Critical | 2023-09-12 | L&T is to submit a proposal to T-Fiber on the scope to be showcased in the proposed WFM-BSS demonstration. | Completed | L&T Kaushal & T-FIBER | N/A
234 | WFM | WFM Related | MOM | Critical | 2023-09-12 | L&T is to identify a product owner for WFM. | Completed | L&T Kaushal & T-FIBER | N/A
235 | WFM | WFM Related | MOM | Critical | 2023-12-15 | WFM Tool Demonstration: L&T to arrange a demonstration of the WFM tool usage for field operations soon. | Completed | L&T Kaushal & T-FIBER | N/A
236 | WFM | WFM Related | MOM | Critical | 2023-12-15 | WFM Mobile App Features: L&T to provide clarity on GPS tracking availability, polling frequency, photo upload feature, file size limitations, and supported Android and iOS versions. | Completed | L&T Kaushal & T-FIBER | N/A
237 | WFM | WFM Related | MOM | Critical | 2023-12-15 | Offline Data Storage: L&T to address the lack of offline data storage feature in the mobile application. | Completed | L&T Kaushal & T-FIBER | N/A | 11-7-2025:- Offline data, such as images and documents, can be uploaded either from the mobile gallery or directly using the camera. To support the storage of LIDAR survey data and GIS images, an 80 TB NAS storage system has already been deployed at the NOC Data Center
238 | GIS | GIS Related | MOM | Critical | 2023-12-15 | Workflow Simulation: L&T to simulate a fiber cut and explain the workflow for clearing the fault and updating GIS. | Completed | L&T Kaushal & T-FIBER | N/A
239 | WFM | WFM Related | MOM | Critical | 2023-12-15 | Security Assurance: L&T to provide the NDA signed with M/S Lepton, assure API security, and share the contract copy. | Completed | L&T Kaushal & T-FIBER | N/A
240 | WFM | WFM Related | MOM | Critical | 2023-12-15 | Ticket Allocation: L&T to start manual ticket allocation and freeze the process for node and link ticket allocation. | Completed | L&T Kaushal & T-FIBER | N/A
241 | WFM | WFM Related | MOM | Critical | 2023-12-15 | Summary Dashboards/Management Reports: L&T to provide inputs based on Operations best practices for weekly/monthly management reports from the WFM package. | Completed | L&T Kaushal & T-FIBER | N/A
242 | WFM | WFM Related | MOM | Critical | 2023-12-15 | The urgency for L&T to demonstrate the WFM tool for field operations and to provide detailed information on its features and capabilities. | Completed | L&T Kaushal & T-FIBER | N/A
243 | WFM | WFM Related | MOM | Critical | 2023-12-15 | The necessity for L&T to address the absence of offline data storage in the mobile application and to simulate a fiber cut workflow. | Duplicate Points | No One | N/A | Duplicate with Point- 237
244 | WFM | WFM Related | MOM | Critical | 2023-12-15 | The requirement for L&T to assure security in the WFM package, including API security and geo-fencing capabilities. | Completed | L&T Kaushal & T-FIBER | N/A
245 | WFM | WFM Related | MOM | Critical | 2023-12-15 | The expectation for L&T to provide comprehensive management reports and dashboards to support process improvements and operational efficiency. | Completed | L&T Kaushal & T-FIBER | N/A
246 | WFM | WFM Related | MOM | Critical | 2023-12-19 | Mobile App & WFM: SVP, T-Fiber requested clarity on the number of mobile apps and urged L&T to freeze the scope in consultation with MSI B and C. Demo with M/S Lepton scheduled for 21st June '23. | Duplicate Points | No One | N/A | Duplicate with Point- 214
247 | WFM | WFM Related | MOM | Critical | 2024-01-25 | Adopt WFM by packages B & C and procure licenses | Pending | T-FIBER & PKG- B & C | _ | TFIBER is a critical dependency for closing the WFM license
248 | WFM | WFM Related | MOM | Critical | 2024-03-14 | Ensuring readiness of WFM integration, order fulfillment, service provisioning, and NOC critical points closure. | Completed | L&T Kaushal & T-FIBER | N/A
249 | WFM | WFM Related | MOM | Critical | 2024-03-14 | L&T to be prepared for the demonstration of WFM for order fulfillment/service provisioning. | Completed | L&T Kaushal & T-FIBER | N/A
250 | WFM | WFM | MOM | Critical | Date Not Available | Field Remarks like ETR, RFO updation pending against Open Task | Completed | OEM (Lepton) Alignment Required | N/A
251 | WFM | WFM | MOM | Critical | Date Not Available | Field team working without events and as a part of corrective actions at Passive | WIP | OEM (Lepton) Alignment Required | 2025-10-30 | 11-7-2025:- SM & WFM Intigration is WIP

## 65 Points of SOP and Handbook (hidden)
Slno | UniqueID | Category | Meeting Date | Priority | Ramana | Ramana-Domain | Domain | Sub-Domain | Action Point | Remarks | Owner(L&T) | Revised Status (L&T) As on 18-Sep-2025 | Derived Status (L&T) | Ramana Remarks as on 19-Sep-2025 | T Fiber Appoved Date | Artefacts
833 | M172 | MOM | 2023-09-12 | P3 |  |  | NOC Operationalization | Handbook & SOPs | SOPs Submission | Agreed SOPs are submitted and agreed with TFiber | Ahmad | Open | OPEN | Documentation |  | #N/A
863 | M2 | MOM | 2023-02-06 | P3 |  |  | NOC Operationalization | Handbook & SOPs | T-Fiber requested the inclusion of Protocol Manager and Regulatory roles in the TNOC organization chart. Also, emphasized clear demarcation and mapping of resources with names, roles, and responsibilities | NOC resources details is shared on weekly basis. Roles of NOC is as per RFP. | Ahmad | Closed | CLOSED | Not related to delivery |  | #N/A
1321 | M611 | MOM | 2023-07-04 | P3 |  |  | NOC Operationalization | Operational Handbook | Incorporate changes into the proposed operational framework as per T-Fiber's review, including adding a Vision and Mission statement, identifying additional relevant processes, updating the organisation structure, and correcting inconsistencies in the documentation of processes. | SOPs approved, have flow diagrams | Ahmad | Open | OPEN | Documentation |  | #VALUE!
1322 | M612 | MOM | 2023-07-04 |  |  |  | NOC Operationalization | Operational Handbook | Detail flow charts of the processes into SOPs. | 22-Sep-25: 44 agreed SOP doc submitted and signed off. Artefacts will be uploaded today in NAS | Siva Kumar | CLOSURE REVIEW PENDING | OPEN |  |  | #N/A
1330 | M62 | MOM | 2023-06-28 | P3 |  |  | NOC Operationalization | Handbook & SOPs | All KPIs details submission | NOC KPI report for submitted and signed for Oct24 to Dec24. Jan to March25 KPI submitted but sign-off pending with TFiber | Ahmad | Open | OPEN | Documentation |  | #N/A
1396 | M68 | MOM | 2023-07-04 | P3 |  |  | NOC Operationalization | Handbook & SOPs | RASCI & Escalation Matrix in NOC Operational Framework | OEM, vendor , Field/NOC escalation matrix available. This is a point in 472 tracker as well and this point is approved by TFiber | Ahmad | Closed | CLOSED | Not related to delivery |  | #N/A
1407 | M69 | MOM | 2023-07-04 | P3 |  |  | NOC Operationalization | Handbook & SOPs | clear definition of roles and responsibilities related to L1, L2 & L3 with number of resources which should be according to the fault rates. | NOC manpower report is shared on weekly basis. Manpower is as per RFP count. KRA is also submitted for L1/L2/L3 roles | Ahmad | Closed | CLOSED | Not related to delivery |  | #N/A
941 | M27 | MOM | 2023-06-07 |  |  |  | GIS | Handbook & SOPs | Approval mechanism for object changes/deletion |  | Kaushalendra Kumar | COMPLETED | CLOSED |  |  | #N/A
952 | M28 | MOM | 2023-06-07 |  |  |  | GIS | Handbook & SOPs | Change Management Log/User Log history |  | Kaushalendra Kumar | COMPLETED | CLOSED |  |  | #N/A
963 | M29 | MOM | 2023-06-07 |  |  |  | GIS | Handbook & SOPs | Data Validation Rules document |  | Kaushalendra Kumar | COMPLETED | CLOSED |  |  | #N/A
997 | M32 | MOM | 2023-06-07 |  |  |  | GIS | Handbook & SOPs | Detailed validation document |  | Kaushalendra Kumar | COMPLETED | CLOSED |  |  | #N/A
1463 | M74 | MOM | 2023-07-26 |  |  |  | WFM | Handbook & SOPs | Scope of Order Processing and Service Ticket Management |  | Kaushalendra Kumar | COMPLETED | CLOSED |  |  | #N/A
1474 | M75 | MOM | 2023-07-26 |  |  |  | WFM | Handbook & SOPs | Document references in SOW to be shared |  | Kaushalendra Kumar | COMPLETED | CLOSED |  |  | #N/A
1541 | M81 | MOM | 2023-07-26 |  |  |  | WFM | Handbook & SOPs | Confirmation of SOW addressing Packages B and C |  | Kaushalendra Kumar | COMPLETED | CLOSED |  |  | #N/A
1607 | M87 | MOM | 2023-07-26 |  |  |  | WFM | Handbook & SOPs | Overall fitment of WFM in E2E applications architecture with integration touchpoints highlighted, along with the WFM flows |  | Kaushalendra Kumar | COMPLETED | CLOSED |  |  | #N/A
1618 | M88 | MOM | 2023-07-26 |  |  |  | WFM | Handbook & SOPs | Clarity required on the scope of WFM under Phase-2 and sharing of Phase-1 & 2 scope with T-Fiber |  | Kaushalendra Kumar | COMPLETED | CLOSED |  |  | #N/A
1652 | M91 | MOM | 2023-07-26 |  |  |  | WFM | Handbook & SOPs | Finalization of Operational Processes linked to WFM workflows |  | Kaushalendra Kumar | COMPLETED | CLOSED |  |  | #N/A
1674 | M93 | MOM | 2023-07-26 |  |  |  | WFM | Handbook & SOPs | To check for potential overlapping functions between proposed WFM app and GIS O&M app, and accordingly streamline the Operational process |  | Kaushalendra Kumar | COMPLETED | CLOSED |  |  | #N/A
475 | M100 | MOM | 2023-08-01 |  |  |  | Helpdesk | Handbook & SOPs | Call Escalation Recording Process | Artefacts will be submitted. | Siva Kumar | CLOSURE REVIEW PENDING | OPEN |  |  | #N/A
519 | M104 | MOM | 2023-08-01 |  |  |  | Helpdesk | Handbook & SOPs | Incident categorization to be exhaustive, response timelines to be defined and attached based on incident categorization. | 11-Sep-25: Updated Document Shared 23-Aug-23 | Siva Kumar | CLOSURE REVIEW PENDING | OPEN |  |  | #N/A
552 | M107 | MOM | 2023-08-01 |  |  |  | Helpdesk | Handbook & SOPs | Clarification needed on whether general enquiries are treated as incidents. | 11-Sep-25 Ans: No | Siva Kumar | CLOSURE REVIEW PENDING | OPEN |  |  | #N/A
563 | M108 | MOM | 2023-08-01 |  |  |  | Helpdesk | Handbook & SOPs | Clarification needed on whether general enquiries are treated as incidents. | 11-Sep-25 Ans: No | Siva Kumar | CLOSURE REVIEW PENDING | OPEN |  |  | #N/A
574 | M109 | MOM | 2023-08-01 |  |  |  | Helpdesk | Handbook & SOPs | Detailed documentation needed on critical, major, minor escalations, and their related thresholds. | 11-Sep-25: Updated Document Shared 23-Aug-23 | Siva Kumar | CLOSURE REVIEW PENDING | OPEN |  |  | #N/A
597 | M111 | MOM | 2023-08-01 |  |  |  | Helpdesk | Handbook & SOPs | Documentation required stating that L2 agents shall make outbound calls to customers. | 11-Sep-25: Updated Document Shared 23-Aug-23 | Siva Kumar | CLOSURE REVIEW PENDING | OPEN |  |  | #N/A
619 | M113 | MOM | 2023-08-01 |  |  |  | Helpdesk | Handbook & SOPs | Clarification needed on the sphere of activity between NOC Technical administrators and Helpdesk agents. | 11-Sep-25: Updated Document Shared 23-Aug-23 | Siva Kumar | CLOSURE REVIEW PENDING | OPEN |  |  | #N/A
641 | M115 | MOM | 2023-08-01 |  |  |  | Helpdesk | Handbook & SOPs | Detailed Helpdesk Process Steps | 11-Sep-25: Updated Document Shared | Siva Kumar | CLOSURE REVIEW PENDING | OPEN |  |  | #N/A
652 | M116 | MOM | 2023-08-01 |  |  |  | Helpdesk | Handbook & SOPs | Clarification needed on addressing the subjective nature of "Non-Technical" calls. | 11-Sep-25: It will be Handled by Proposed T fiber Business Helpdesk | Siva Kumar | CLOSURE REVIEW PENDING | OPEN |  |  | #N/A
663 | M117 | MOM | 2023-08-01 |  |  |  | Helpdesk | Handbook & SOPs | Assumptions for Estimated Calls per Day | 11-Sep-25: Data Shared | Siva Kumar | CLOSURE REVIEW PENDING | OPEN |  |  | #N/A
674 | M118 | MOM | 2023-08-01 |  |  |  | Helpdesk | Handbook & SOPs | Readiness of Helpdesk to report on compliances and responsiveness and calculate penalties. |  | Siva Kumar | CLOSURE REVIEW PENDING | OPEN |  |  | #N/A
685 | M119 | MOM | 2023-08-01 |  |  |  | Helpdesk | Handbook & SOPs | Live Intrusion of Calls | 11-Sep-25: Feature Available, Shall be demonstrated | Siva Kumar | CLOSURE REVIEW PENDING | OPEN |  |  | #N/A
697 | M120 | MOM | 2023-08-01 |  |  |  | Helpdesk | Handbook & SOPs | Duration of Call Measurement | 11-Sep-25: Feature Available, Shall be demonstrated | Siva Kumar | CLOSURE REVIEW PENDING | OPEN |  |  | #N/A
708 | M121 | MOM | 2023-08-01 |  |  |  | Helpdesk | Handbook & SOPs | Exceptions in IVR User Response |  | Siva Kumar | CLOSURE REVIEW PENDING | OPEN |  |  | #N/A
719 | M122 | MOM | 2023-08-01 |  |  |  | Helpdesk | Handbook & SOPs | The unit of measurement is required for all Key Performance Indicator (KPI) parameters. | 11-Sep-25: Updated Document Shared 23-Aug-23 | Siva Kumar | CLOSURE REVIEW PENDING | OPEN |  |  | #N/A
730 | M123 | MOM | 2023-08-01 |  |  |  | Helpdesk | Handbook & SOPs | Sample Methods for KPI Calculations | 11-Sep-25: Updated Document Shared 23-Aug-23 | Siva Kumar | CLOSURE REVIEW PENDING | OPEN |  |  | #N/A
763 | M126 | MOM | 2023-08-01 |  |  |  | Helpdesk | Handbook & SOPs | Review of Agent Utilization Formula |  | Siva Kumar | CLOSURE REVIEW PENDING | OPEN |  |  | #N/A
774 | M127 | MOM | 2023-08-01 |  |  |  | Helpdesk | Handbook & SOPs | Customer-Specific SLA Flows | 11-Sep-25: Updated Document Shared 23-Aug-23 | Siva Kumar | CLOSURE REVIEW PENDING | OPEN |  |  | #N/A
775 | M1270 | MOM | 2025-02-14 |  |  |  | Helpdesk | Handbook & SOPs | Helpdesk IVR: after selecting any number (apart from configured 1/2/3), call is getting disconnected. This need to be corrected |  | Siva Kumar | CLOSURE REVIEW PENDING | OPEN |  |  | #N/A
784 | M128 | MOM | 2023-08-01 |  |  |  | Helpdesk | Handbook & SOPs | Exhaustive List of General Enquiries | 11--Sep-25: FAQ made available | Siva Kumar | CLOSURE REVIEW PENDING | OPEN |  |  | #N/A
785 | M129 | MOM | 2023-08-01 |  |  |  | Helpdesk | Handbook & SOPs | DoT KPIs Coverage in KPI Section | 11-Sep-25: Updated Document Shared 23-Aug-23 | Siva Kumar | CLOSURE REVIEW PENDING | OPEN |  |  | #N/A
787 | M130 | MOM | 2023-08-01 |  |  |  | Helpdesk | Handbook & SOPs | FAQs Based on Case Studies | 11-Sep-25: Updated Document Shared 23-Aug-23 | Siva Kumar | CLOSURE REVIEW PENDING | OPEN |  |  | #N/A
789 | M132 | MOM | 2023-08-01 |  |  |  | Helpdesk | Handbook & SOPs | the roles and responsibilities of NOC and Field Personnel be separate according to the RASCI matrix | 11-Sep-25: Updated Document Shared 23-Aug-23 | Siva Kumar | CLOSURE REVIEW PENDING | OPEN |  |  | #N/A
530 | M105 | MOM | 2023-08-01 |  |  |  | Helpdesk | Handbook & SOPs | Clarity required in the definition of roles and responsibilities of L1 and L2 agents, incident categorization to be handled at L1 level, type of queries, resolution time, escalation matrix to be better defined. |  | Siva Kumar | CLOSURE REVIEW PENDING | OPEN |  |  | #N/A
802 | M144 | MOM | 2023-08-23 |  |  |  | BSS | Handbook & SOPs | Process for Data Integrity of Bulk upload |  | Manoj Nibrad | OPEN | OPEN |  |  | #N/A
826 | M166 | MOM | 2023-09-08 |  |  |  | BSS | Handbook & SOPs | Order Fulfilment Process |  | Manoj Nibrad | OPEN | OPEN |  |  | #N/A
827 | M167 | MOM | 2023-09-08 |  |  |  | BSS | Handbook & SOPs | Service Delivery Process |  | Manoj Nibrad | OPEN | OPEN |  |  | #N/A
828 | M168 | MOM | 2023-09-08 |  |  |  | BSS | Handbook & SOPs | Service Delivery Team Resource and responsibilities & relationship with other packages |  | Manoj Nibrad | OPEN | OPEN |  |  | #N/A
829 | M169 | MOM | 2023-09-08 |  |  |  | BSS | Handbook & SOPs | Clearly define user system mapping with specific process steps with documentation for clarity |  | Manoj Nibrad | OPEN | OPEN |  |  | #N/A
909 | M240 | MOM | 2023-09-26 |  |  |  | NOC Operationalization | Handbook & SOPs | Provide clarification on the status of HOTO (Handover to Operations) and Knowledge Transfer. |  | Sivaprasad | OPEN | OPEN |  |  | #N/A
1074 | M39 | MOM | 2023-06-15 |  |  |  | BSS | Handbook & SOPs | State of maturity of all Business process flows mentioned in the HLD |  | Manoj Nibrad | OPEN | OPEN |  |  | #N/A
1363 | M65 | MOM | 2023-06-28 | P3 |  |  | NOC Operationalization | Handbook & SOPs | Create an archival policy for documentation storage, including retrieval systems, access matrix, and policies |  | Ahmad | Open | OPEN | Documentation |  | #N/A
1374 | M66 | MOM | 2023-06-28 | P3 |  |  | NOC Operationalization | Handbook & SOPs | Define categories of problems along with a resolution approach plan |  | Ahmad | Open | OPEN | Documentation |  | #N/A
1441 | M72 | MOM | 2023-07-04 | P3 |  |  | NOC Operationalization | Handbook & SOPs | service management of configuration |  | Ahmad | Open | OPEN | Documentation |  | #N/A
1627 | M888 | MOM | 2023-12-15 | P3 |  |  | NOC Operationalization | Operational Handbook | Operations Handbook: L&T to share document forms from the Operations Handbook to be used by the WFM app. |  | Ahmad | Open | OPEN | Documentation |  | #N/A
586 | M110 | MOM | 2023-08-01 |  |  |  | Helpdesk | Handbook & SOPs | Feedback Collection Review Mechanism |  | Siva Kumar | WIP | OPEN |  |  | #N/A
608 | M112 | MOM | 2023-08-01 |  |  |  | Helpdesk | Handbook & SOPs | Inquiry about how the Helpdesk addresses cases where the number of the person calling differs from the number registered in the BSS database. | 11-Sep-25: BSS Integration | Siva Kumar | WIP | OPEN |  |  | #N/A
741 | M124 | MOM | 2023-08-01 |  |  |  | Helpdesk | Handbook & SOPs | Inquiry into how Customer Satisfaction (CSAT) is measured and whether there is a mechanism for transactional feedback. |  | Siva Kumar | WIP | OPEN |  |  | #N/A
752 | M125 | MOM | 2023-08-01 |  |  |  | Helpdesk | Handbook & SOPs | Expression of First Call Resolution (FCR) as a percentage |  | Siva Kumar | WIP | OPEN |  |  | #N/A
788 | M131 | MOM | 2023-08-01 |  |  |  | Helpdesk | Handbook & SOPs | Request to differentiate between registered users and registered numbers using examples. | 11-Sep-25: BSS Integration to be completed | Siva Kumar | WIP | OPEN |  |  | #N/A
790 | M133 | MOM | 2023-08-01 |  |  |  | Helpdesk | Handbook & SOPs | Inclusion of Master and Child Service Level Agreement (SLA) monitoring; if any SLA is breached, a proper escalation matrix should be available for speedy escalation and resolution of the issue. |  | Siva Kumar | WIP | OPEN |  |  | #N/A
849 | M187 | MOM | 2023-09-22 |  |  |  | NSO | Handbook & SOPs | Train in-house L&T resources in NSO and NEDs for reduced dependency on Cisco. |  | Jayant Madavi | OPEN | OPEN |  |  | #N/A
1307 | M6 | MOM | 2023-03-27 |  |  |  | NOC Operationalization | Handbook & SOPs | Clear accountability and responsibility of SMEs, along with an presented RASCI matrix | Domain wise NOC L3 role exists at NOC | Sivaprasad | CLOSED | CLOSED |  |  | #N/A
1308 | M60 | MOM | 2023-06-28 |  |  |  | NOC Operationalization | Handbook & SOPs | Classification of Procedures and processes from ITIL and eTOM |  | Sivaprasad | WIP | OPEN |  |  | #N/A
1341 | M63 | MOM | 2023-06-28 |  |  |  | NOC Operationalization | Handbook & SOPs | The difference between problem and issue management. |  | Sivaprasad | CLOSED | CLOSED |  |  | #N/A
1352 | M64 | MOM | 2023-06-28 |  |  |  | NOC Operationalization | Handbook & SOPs | Establish a configuration management system to monitor all changes in NOC operations |  | Sivaprasad | CLOSED | CLOSED |  |  | #N/A
1385 | M67 | MOM | 2023-06-28 |  |  |  | NOC Operationalization | Handbook & SOPs | Adopt a continuous improvement framework such as DMAIC and Kaizen for process improvement |  | Sivaprasad | WIP | OPEN |  |  | #N/A

## MOM-Points (hidden)
Slno | UniqueID | Meeting Date | Domain | Sub-Domain | Action Point | Priority | Baseline Status | Application | Remarks | Owner(L&T) | Revised Status (L&T) | Approved BY (TF) | Approval Date(TF) | Link of evidences
817 | M817 | 2024-09-26 | AT Process | T&D Environment | Defining and aligning with the acceptance criteria for each system in the NOC. | NON-Critical | Open
1198 | M1198 | 2024-12-09 | BBNL | OSS | CDOT integration with NMS is highest priority. The team should be actively engaged with teams and visit sites. | Critical | Closed
1229 | M1229 | 2024-12-10 | BBNL | OSS | BBNL - API : is top priority. Each day update to be sent to Principal Consultant | Critical | Closed
1230 | M1230 | 2024-12-10 | BBNL | OSS | Tomorrow 3 PM. will call Rupa Maan and Akhilesh Gupta Sir for BBNL API | Critical | Closed
1236 | M1236 | 2024-12-10 | BBNL | OSS | Manoj: Complete BBNL ask tasks will be completed by 12 Dec24 (only GP and Block Node status API pending). Sanjay: Uptime gap ~7% to be addressed. For this, HPE support needed. Then only we can go to BBNL for closure. Alarm re-synchronization issue - need HPE support. Interim solution implemented (1 Hr). Same for Inventory. | Critical | Open
1253 | M1253 | 2024-12-11 | BBNL | OSS | Make a Focused WhatsApp group for BBNL | Critical | Closed
4 | M4 | 2023-03-27 | BSS | Service provisioning | BSS-based provisioning for regularizing 3000 GI through NOC BSS, with scalability to 30,000 GIs. | Critical | Open | OSS Dashboards
19 | M19 | 2023-05-18 | BSS | Resource Related | Inter-Dependence Matrix and Resource Identification | Critical | Open | OSS Dashboards
20 | M20 | 2023-05-18 | BSS | Full NOC Readiness | Roadmap for Network Service Order Fulfilment and Service Assurance | Critical | Open | OSS Dashboards
38 | M38 | 2023-06-15 | BSS | Resource Related | Billing Expert onboarding | Critical | Open | Billing
39 | M39 | 2023-06-15 | BSS | Handbook & SOPs | State of maturity of all Business process flows mentioned in the HLD | Critical | Open
136 | M136 | 2023-08-23 | BSS | Notification Template | comprehensive list of event notification scenarios and implementation plan. | Critical | Open
137 | M137 | 2023-08-23 | BSS | Improvement | Complete User Group creation | Critical | Closed
138 | M138 | 2023-08-23 | BSS | Improvement | customizable columns | Critical | Closed
139 | M139 | 2023-08-23 | BSS | Dashboards | Summary of Leads | NON-Critical | Closed
140 | M140 | 2023-08-23 | BSS | Improvement | Advance Search options | NON-Critical | Open
141 | M141 | 2023-08-23 | BSS | Resource Related | Structure & Composition of Service Delivery group | NON-Critical | Open
142 | M142 | 2023-08-23 | BSS | Resource Related | Roles & Responsibility of Service Delivery group | NON-Critical | Open
143 | M143 | 2023-08-23 | BSS | User Experience | Notification with status changes from Opportunity - RFO - RFS – Order | Critical | Open
144 | M144 | 2023-08-23 | BSS | Handbook & SOPs | Process for Data Integrity of Bulk upload | NON-Critical | Open
146 | M146 | 2023-08-23 | BSS | Dashboards | Summary before Feasibility Result | NON-Critical | Open
147 | M147 | 2023-08-23 | BSS | Manual Feasibility Plan | Order Fulfilment - Exception Scenarios | NON-Critical | Open
148 | M148 | 2023-08-23 | BSS | Action points | Ensure that site editing is restricted | Critical | Open
149 | M149 | 2023-08-23 | BSS | Data Upload | Entire network POI/ PoP status, including 12751 GPs, 1 NOC, all zones, districts & Mandal nodes, is available in the CRM database | Critical | Open
150 | M150 | 2023-08-23 | BSS | CSP User Experience | Telugu Subtitles in CSP | Critical | Open
151 | M151 | 2023-08-23 | BSS | CSP User Experience | Google Location Pickup | Critical | Open
152 | M152 | 2023-08-23 | BSS | CSP User Experience | Lat/Long coordinates and LGD codes should be removed from the search bar. | Critical | Closed
153 | M153 | 2023-08-23 | BSS | CSP User Experience | Check Residential" should be changed with a more appropriate term. | NON-Critical | Open
154 | M154 | 2023-08-23 | BSS | CSP User Experience | Introduce a "Thank You" page after a lead is submitted, displaying the lead number. This lead number could be useful for Helpdesk also. | NON-Critical | Open
155 | M155 | 2023-08-23 | BSS | CSP User Experience | The term "External" should be replaced with "Internal." | NON-Critical | Open
156 | M156 | 2023-08-23 | BSS | CSP User Experience | "Value-Add Partners" Tab | NON-Critical | Open
157 | M157 | 2023-08-23 | BSS | CSP User Experience | Landing Page Content | Critical | Open
158 | M158 | 2023-08-23 | BSS | CSP User Experience | The term "Last Miles" should be changed to "Partners. | Critical | Open
159 | M159 | 2023-08-23 | BSS | CSP User Experience | The "Government/Cell Tower/Enterprise" tab should have a dropdown for various services & information. | Critical | Open
160 | M160 | 2023-08-23 | BSS | CSP User Experience | Chatbot Feature | NON-Critical | Open
161 | M161 | 2023-08-23 | BSS | CSP User Experience | Leads Summary for B2B Partner | Critical | Open
162 | M162 | 2023-08-31 | BSS | User Experience | CRM should be in IST Times | Critical | Open
163 | M163 | 2023-08-31 | BSS | User Experience | User Group training for administrator to Add/Modify the user access in CSP and CRM | Critical | Open
164 | M164 | 2023-08-31 | BSS | Billing Related | SSL Certificate implementation | Critical | Open
165 | M165 | 2023-08-31 | BSS | User Experience | Corporate Number for WhatsApp | Critical | Open
166 | M166 | 2023-09-08 | BSS | Handbook & SOPs | Order Fulfilment Process | Critical | Open
167 | M167 | 2023-09-08 | BSS | Handbook & SOPs | Service Delivery Process | Critical | Open
168 | M168 | 2023-09-08 | BSS | Handbook & SOPs | Service Delivery Team Resource and responsibilities & relationship with other packages | Critical | Open
169 | M169 | 2023-09-08 | BSS | Handbook & SOPs | Clearly define user system mapping with specific process steps with documentation for clarity | Critical | Open
181 | M181 | 2023-09-12 | BSS | Dynamic Feature | Overall capability to support the creation of innovative new products and seamless customer experience | NON-Critical | Open
186 | M186 | 2023-09-22 | BSS | Dynamic Feature | Enhance BSS to allow flexibility in creating, modifying, adding, and deleting product categories | NON-Critical | Open
188 | M188 | 2023-09-22 | BSS | Notification Template | Notification Template Flexibility | NON-Critical | Open
189 | M189 | 2023-09-22 | BSS | Notification Template | CP to be changed to CP-TFGCLT | NON-Critical | Open
190 | M190 | 2023-09-22 | BSS | CSP User Experience | Ensure that only the logos of the Government of Telangana and T-Fiber are used in the CSP. | Critical | Open
191 | M191 | 2023-09-22 | BSS | Billing Related | CAF detailed analysis related to TRAI | Critical | Open
192 | M192 | 2023-09-22 | BSS | CSP User Experience | Clearly mention on the Landing Page that services are currently extended only for Rural Telangana; Capture and store leads for requests from Urban Telangana. | Critical | Open
193 | M193 | 2023-09-22 | BSS | CSP User Experience | User guides such as "May I help you", Chatbots, Videos | NON-Critical | Open
194 | M194 | 2023-09-22 | BSS | CSP User Experience | Definitions of terminologies to be available on mouseover | NON-Critical | Open
197 | M197 | 2023-09-22 | BSS | Integration | WFM-SMS Gateway integration | Critical | Open
198 | M198 | 2023-09-22 | BSS | CSP User Experience | L&T, to update the Landing Page to cater to all specified segments such as Pin code, Address, Lat-Long, or address pulling from Google API is required | Critical | Open
199 | M199 | 2023-09-22 | BSS | Notification Template | Replace "Re-confirm" with "View" in the notification template. | Critical | Open
200 | M200 | 2023-09-22 | BSS | Notification Template | Ensure that SMS includes a link to the CSP. | Critical | Open
201 | M201 | 2023-09-22 | BSS | Functional AT Plan | Perform testing of negative scenarios to identify and address any issues or vulnerabilities | Critical | Open
202 | M202 | 2023-09-22 | BSS | CSP User Experience | Validate all mandatory fields and associated asterisks to ensure completeness and accuracy of data entry | Critical | Open
203 | M203 | 2023-09-22 | BSS | Billing Related | Establish a mechanism to confirm the synchronization between the current account and the payment portal. | Critical | Open
204 | M204 | 2023-09-22 | BSS | CSP User Experience | Display Progress in CSP Post-Order | NON-Critical | Open
205 | M205 | 2023-09-22 | BSS | CSP User Experience | User-Friendly Product Naming | NON-Critical | Open
206 | M206 | 2023-09-22 | BSS | Action points | Address and resolve issues related to using the backspace key on the webpage, ensuring smooth navigation to the previous page. | NON-Critical | Open
207 | M207 | 2023-09-22 | BSS | Billing Related | Payments and policies : BSS billing module should have various frameworks of full payment, part payment, advance payment, based on customer credit worthiness , based on discount policy etc. | Critical | Open
208 | M208 | 2023-09-22 | BSS | CSP User Experience | Time Duration of OTP need to be fixed with timer | Critical | Open
209 | M209 | 2023-09-22 | BSS | CSP User Experience | Implement 'Request to Re-send OTP' | Critical | Open
210 | M210 | 2023-09-22 | BSS | Billing Related | Implement a system to generate a revised Proforma Invoice with the latest date if the ordering process is stopped and resumed. | Critical | Open
211 | M211 | 2023-09-22 | BSS | CSP User Experience | Configure the CSP portal to display only orders relevant to the specific customer, enhancing user experience and clarity. | Critical | Open
212 | M212 | 2023-09-22 | BSS | Service provisioning | Reservation of Bandwidth at Provisioning | Critical | Open
213 | M213 | 2023-09-22 | BSS | CSP User Experience | Customer Care should in bold | NON-Critical | Open
214 | M214 | 2023-09-22 | BSS | Billing Related | Align Order Confirmation with Payment Receipt | Critical | Open
215 | M215 | 2023-09-22 | BSS | Improvement | Improve 'Pick Order' Button and Placeholder | Critical | Open
216 | M216 | 2023-09-22 | BSS | Billing Related | Implement Alerts for CAF Approval and Payment | Critical | Open
217 | M217 | 2023-09-22 | BSS | Improvement | Customer Dashboards with visible website name for branding | Critical | Open
218 | M218 | 2023-09-22 | BSS | User Experience | Make Site ID More Relevant for Order Selection | Critical | Open
219 | M219 | 2023-09-22 | BSS | Improvement | Display Opportunity ID and Order ID Differently columns | Critical | Open
220 | M220 | 2023-09-22 | BSS | Action points | Address Missing Scroll Bar in Some Pages | Critical | Open
221 | M221 | 2023-09-22 | BSS | Billing Related | Incorporate a partial payment option for larger or priority accounts, allowing T-Fiber to decide on a case-by-case basis, along with an approval matrix. | Critical | Open
222 | M222 | 2023-09-22 | BSS | Action points | Rectify the issue with the 'Show Password' option to ensure its proper functionality | Critical | Open
223 | M223 | 2023-09-22 | BSS | Billing Related | Mandate the selection of the payment window (half-yearly or annually) during the ordering process, making it clear to the customer, rather than defaulting to monthly. | Critical | Open
224 | M224 | 2023-09-22 | BSS | Improvement | Modify the order submission process to collect secondary phone numbers and email IDs, as required. | Critical | Open
225 | M225 | 2023-09-22 | BSS | Billing Related | Implement a restriction to prevent order placement without the completion of payment, ensuring a secure and controlled ordering process. | Critical | Open
226 | M226 | 2023-09-22 | BSS | Improvement | Standardize colour coding across all UX/UI elements for consistency and a unified visual experience. | Critical | Open
227 | M227 | 2023-09-22 | BSS | Improvement | Allow users to refresh and continue after prolonged inactivity, enhancing the user experience and preventing disruptions | Critical | Open
228 | M228 | 2023-09-22 | BSS | Improvement | Welcome Message Placement | Critical | Open
229 | M229 | 2023-09-22 | BSS | Improvement | Introduce a flashing indicator for orders to attract attention and improve visibility. | Critical | Open
230 | M230 | 2023-09-22 | BSS | User Experience | Add a visual indication for users to select the service under the Create Order page. | Critical | Open
231 | M231 | 2023-09-22 | BSS | Action points | Investigate and address the issue where no details are displayed upon clicking on "Customer Premises Equipment." | Critical | Open
232 | M232 | 2023-09-22 | BSS | Improvement | Rephrase the error message that appears when clicking on the Remove button under Create Order Step 3 for better clarity. | Critical | Open
233 | M233 | 2023-09-22 | BSS | Improvement | Display Recurring Charge Frequency in Order Summary | Critical | Open
234 | M234 | 2023-09-22 | BSS | User Experience | Display Instructions for CAF Download | Critical | Open
235 | M235 | 2023-09-22 | BSS | User Experience | Indicate File Type and Size at Confirmation Stage | Critical | Open
236 | M236 | 2023-09-22 | BSS | User Experience | Implement Preview Option for Uploaded Documents | Critical | Open
237 | M237 | 2023-09-22 | BSS | Improvement | Emphasize the purpose of the "Edit Proceed" button for user understanding and clarity. | Critical | Open
238 | M238 | 2023-09-22 | BSS | Action points | Resolve Issues with "Edit Proceed" Button | Critical | Open
239 | M239 | 2023-09-22 | BSS | Improvement | Digitally Sign Proforma Invoice | Critical | Open
251 | M251 | 2023-10-11 | BSS | Resource Related | BSS Expert onboarding | Critical | Open
255 | M255 | 2023-10-18 | BSS | CSP User Experience | Back Button to be available in the Payment Screen. | Critical | Open
256 | M256 | 2023-10-18 | BSS | CSP User Experience | Guidelines to be available to the user in the CAF upload stage, what to upload in CAF upload stage is not clear. | Critical | Open
257 | M257 | 2023-10-18 | BSS | CSP User Experience | Add a disclaimer for “Subject to Verification of CAF”, with notification trigger | Critical | Open
258 | M258 | 2023-10-18 | BSS | CSP User Experience | Unable to view offline payment transactions uploaded | Critical | Open
259 | M259 | 2023-10-18 | BSS | CSP User Experience | Mandatory sections of the CAF to be highlighted. | Critical | Open
260 | M260 | 2023-10-18 | BSS | CSP User Experience | Notifications for ticket via SMS and Email not received. | Critical | Open
261 | M261 | 2023-10-18 | BSS | CSP User Experience | Received a Pop-up for incorrect entry of OTP despite entering the correct OTP | Critical | Open
262 | M262 | 2023-10-18 | BSS | CSP User Experience | Raised single ticket in CSP, however 3 distinct tickets are visible in CSP with same narration of issue, notification or alerts not received for any of these tickets. | Critical | Open
263 | M263 | 2023-10-18 | BSS | CSP User Experience | tickets raised are visible at the department level only, is this possible to be made available Departmental user wise? | Critical | Open
264 | M264 | 2023-10-18 | BSS | CSP User Experience | Searching by Order ID is case sensitive. | Critical | Open
265 | M265 | 2023-10-18 | BSS | CSP User Experience | Receiving the “Pending Feasibility” confirmation message, then receiving result as “Feasible” | Critical | Open
266 | M266 | 2023-10-18 | BSS | CSP User Experience | How does BSS handle dismantled GPs if there is no real-time sync between GIS-OSS | Critical | Open
267 | M267 | 2023-10-18 | BSS | CSP User Experience | Cygnet product name showing in the top of the tab, to be removed. | NON-Critical | Open
268 | M268 | 2023-10-18 | BSS | CSP User Experience | GP names are not aligned to government list | Critical | Open
269 | M269 | 2023-10-18 | BSS | CSP User Experience | Plot number to be renamed as Plot / House no | Critical | Open
270 | M270 | 2023-10-18 | BSS | CSP User Experience | In case of Manual Provisioning, is there a stage for Validation? | Critical | Open
271 | M271 | 2023-10-18 | BSS | CSP User Experience | Unable to enter the OTP, Unable to close the Pop-up window for OTP, require either a “Close” button OR closing the Pop-up should be allowed by clicking outside the Pop-up. | Critical | Open
272 | M272 | 2023-10-18 | BSS | CSP User Experience | Unable to go back to Home Screen | Critical | Open
273 | M273 | 2023-10-18 | BSS | CSP User Experience | In Landing Page, number of GPs is mentioned as 12,751, this number to be validated. | Critical | Open
274 | M274 | 2023-10-18 | BSS | CSP User Experience | Back Button required in Create Order and Order Summary screens | Critical | Open
275 | M275 | 2023-10-18 | BSS | CSP User Experience | What is the purpose of displaying segment as G2G in CAF ? | Critical | Open
276 | M276 | 2023-10-18 | BSS | CSP User Experience | How does a GI customer know the Site ID to be entered. | Critical | Open
277 | M277 | 2023-10-18 | BSS | CSP User Experience | Payment is showing as Net banking for all transactions, including offline transactions. | Critical | Open
278 | M278 | 2023-10-18 | BSS | CSP User Experience | Unable to see Order Summary just before Payment. | Critical | Open
279 | M279 | 2023-10-18 | BSS | CSP User Experience | Notification of Success / Failure to be available on Order Submission. | NON-Critical | Open
280 | M280 | 2023-10-18 | BSS | CSP User Experience | In Payment Screen, add a disclaimer that “Payment details are subject to verification for offline payments” to cover for the scenario of wrong / incorrect Payment ID provided by the user. | Critical | Open
281 | M281 | 2023-10-18 | BSS | CSP User Experience | Is a location added in CSP visible in the CRM as a lead? | Critical | Open
282 | M282 | 2023-10-18 | BSS | CSP User Experience | While adding a new location using the map, searching by name is working (example- Jagtial), however searching by Lat-Long is not working. | Critical | Open
283 | M283 | 2023-10-18 | BSS | CSP User Experience | Added a location, but GP name is not getting populated, how is this address added in the CRM, received a pop-up alert for location confirmation, but this location is not added to the list. | Critical | Open
284 | M284 | 2023-10-18 | BSS | CSP User Experience | Product Selection screen did not display “Last Mile Connectivity” with no view to scroll right, either restrict the size of the location name or display all columns in a single page. | Critical | Open
285 | M285 | 2023-10-18 | BSS | CSP User Experience | Email notifications not being triggered for a few actions where events are not configured | Critical | Open
286 | M286 | 2023-10-18 | BSS | CSP User Experience | Received order confirmation, but no notifications received for payment, no notification on save order. | Critical | Open
287 | M287 | 2023-10-18 | BSS | CSP User Experience | What is the Transaction number? | NON-Critical | Open
288 | M288 | 2023-10-18 | BSS | CSP User Experience | While adding a new address, selected a gram panchayat, changed Lat-Long, provided address details, successfully added these details, but the address for GP name is not seen, to be shown. | NON-Critical | Open
293 | M293 | 2023-10-19 | BSS | GeM Integration | GeM integration with BSS: the point may be deferred for 6 months, with timeline to be added by L&T for next review, L&T to issue a Note (Note 1) recording this statement. | NON-Critical | Open
321 | M321 | 2023-10-19 | BSS | Development & Unit Testing | Point No. 16: Development and Unit Testing - Service Assurance and trouble tickets To be linked with the points in follow-up with HP for completion by March ’24, with clarity on next steps by 1st week of November. | Critical | Open
333 | M333 | 2023-11-03 | BSS | Service provisioning | UD,SD Peramaters to be captured. | Critical | Open
335 | M335 | 2023-11-03 | BSS | Service provisioning | UD perameters for product based to be prepared. | Critical | Open
336 | M336 | 2023-11-03 | BSS | Service provisioning | Ashish to comeback with Design plan for Inventory Manager at NSO | Critical | Open
337 | M337 | 2023-11-03 | BSS | Service provisioning | Arvindam to comeback with product wise UD perameters | Critical | Open
338 | M338 | 2023-11-03 | BSS | Service provisioning | Additional information for VRF, VLAN , Inner vlan etc to capture in Master DB | Critical | Open
339 | M339 | 2023-11-03 | BSS | Service provisioning | As per Cisco LLD All 28 types of L2, L3 models to be mapped aginest products | Critical | Open
340 | M340 | 2023-11-03 | BSS | Service Codes | GL code to be mapped based on subtype GI under sub type Central & State | Critical | Open
341 | M341 | 2023-11-03 | BSS | Service Codes | Define the Code for Circuit type , Customer type , customer service type etc in single format | Critical | Open
342 | M342 | 2023-11-03 | BSS | Service Codes | Define design plan for House hold services in GPON Level | Critical | Open
343 | M343 | 2023-11-03 | BSS | Service Codes | Define Household plan for provisioning as per the GPON plan design | Critical | Open
344 | M344 | 2023-11-03 | BSS | Service Codes | OSS Method of distance from GIS need to comeback with plan | Critical | Open
345 | M345 | 2023-11-03 | BSS | Service Codes | Aravindam to update on previous meetings updates to be updated in next in continuous meetings | Critical | Open
351 | M351 | 2023-11-17 | BSS | Demo | Second Dry Run (details to be shared later) : week starting | Critical | Open
359 | M359 | 2023-11-17 | BSS | Resource Related | BSS-SME visit & extended stay for backlog clearance and sharing agenda prior to visit | Critical | Open
366 | M366 | 2023-11-17 | BSS | Dry Run | BSS product system readiness for usage | Critical | Open
414 | M414 | 2023-12-19 | BSS | Improvement | Investigate and expedite the issue on slowness of BSS Test Environment | Critical | Open
415 | M415 | 2023-12-19 | BSS | Dashboards | Explore web-based Analytic tools for performance benchmarking | Critical | Open
416 | M416 | 2023-12-19 | BSS | Compliance | Review the status of points with "No Change" status and obtain T-Fiber's consensus before rendering items as "Closed". | Critical | Open
417 | M417 | 2023-12-19 | BSS | Improvement | Verify the feature allowing multiple locations per customer | Critical | Open
418 | M418 | 2023-12-19 | BSS | Improvement | Cross-reference user experience feedback with related points | Critical | Open
419 | M419 | 2023-12-19 | BSS | SMS Integration | Implement notification of SMS dispatch in the CSP and provision of a link in SMS to the CSP page allowing T-Fiber user to Approve or Reject | Critical | Open
420 | M420 | 2023-12-19 | BSS | Product Demo | Provide a demo to showcase product catalogue configurability | Critical | Open
421 | M421 | 2023-12-19 | BSS | Product Demo | Provide a demo of Backend Validation and share a document with the steps for validation | Critical | Open
422 | M422 | 2023-12-19 | BSS | Product Demo | Address the delay in data load due to system limitation in the production instance | Critical | Open
423 | M423 | 2023-12-19 | BSS | Product Demo | Define a benchmark for page loading, login, browsing, and payment scenarios | Critical | Open
424 | M424 | 2023-12-19 | BSS | Product Demo | Review the status of Point no. 52 from Dry Run 1 with a demo | Critical | Open
425 | M425 | 2023-12-19 | BSS | Product Demo | Ensure uniform colour coding across the website | Critical | Open
426 | M426 | 2023-12-19 | BSS | Product Demo | Address the change of website heading for customer dashboards prior to moving into production | Critical | Open
427 | M427 | 2023-12-19 | BSS | Product Demo | Arrange for a demo of current products since significant time has passed since the Dry Run | Critical | Open
428 | M428 | 2023-12-19 | BSS | Product Demo | Show the flows of Dark Fiber with BSS and WFM | Critical | Open
429 | M429 | 2023-12-19 | BSS | Product Demo | Hold discussions for T-Cell product integration with respective OEMs | Critical | Open
430 | M430 | 2023-12-19 | BSS | Product Demo | Complete T-Cell, T-VPN, and GI-ILL | Critical | Open
431 | M431 | 2023-12-19 | BSS | Product Demo | Address delay in support for enabling newer products | Critical | Open
432 | M432 | 2023-12-19 | BSS | Product Demo | Complete T-Cell, T-VPN and GI-ILL on priority before impending visit to NOC by Hon’ Minister | Critical | Open
433 | M433 | 2023-12-19 | BSS | Product Demo | Include headers and check across pages in the CSP | Critical | Open
434 | M434 | 2023-12-19 | BSS | Product Demo | Start working on the CSP for listed schools | Critical | Open
435 | M435 | 2023-12-19 | BSS | Product Demo | Clarify scenario where GP location is feasible, whereas the feasibility of end customer location is yet to be ascertained | Critical | Open
436 | M436 | 2023-12-19 | BSS | Product Demo | Include feasibility logic for S1, and S2 splitters | Critical | Open
437 | M437 | 2023-12-19 | BSS | Product Demo | Present the logic for Bandwidth feasibility in the backhaul, network capacity planning to be progressively provisioned, and operationalised | Critical | Open
438 | M438 | 2023-12-19 | BSS | Improvement | Address immediate need for NSO inventory to be part of the final solution for feasibility | Critical | Open
439 | M439 | 2023-12-19 | BSS | Resource Related | Ask Segment Head, L&T to discuss with EVP, T-Fiber on the adequacy of NMS works resources | Critical | Open
440 | M440 | 2023-12-19 | BSS | Improvement | Clarify that Repository Module for Uploading of MSA, CAF form and other documents of a particular customer is in CRM, not in CSP | NON-Critical | Open
441 | M441 | 2023-12-19 | BSS | Integration | Incorporate advanced features in the CSP's WhatsApp Integration | NON-Critical | Open
442 | M442 | 2023-12-19 | BSS | User Experience | On-board an internal UI/UX resource and engage them with T-Fiber | Critical | Open
443 | M443 | 2023-12-28 | BSS | Product Demo | Complete T-VPN and T-DILL | Critical | Open
444 | M444 | 2023-12-28 | BSS | Product Demo | Complete basic products by | Critical | Open
445 | M445 | 2023-12-28 | BSS | Product Demo | Complete GI-BB, T-Cell, Dark Fiber | Critical | Open
458 | M458 | 2024-01-04 | BSS | Product category | Complete T-DILL & T-VPN | Critical | Open
459 | M459 | 2024-01-04 | BSS | Product category | Discuss network design for T-DILL with AD-P&E, T-Fiber & IPMPLS-SME | Critical | Open
461 | M461 | 2024-01-04 | BSS | Product category | Conduct a product discussion audit | Critical | Open
462 | M462 | 2024-01-04 | BSS | Product category | Submit evidence on commitment from OEMs for integration of various systems with BSS | Critical | Open
465 | M465 | 2024-01-04 | BSS | Product category | Finalize network design and initiate the implementation of Mandal-to-Mandal and Mandal-to-GP dark fiber process | Critical | Open
466 | M466 | 2024-01-04 | BSS | Product category | Prepare for mock audit regarding bill desk integration and prepare a road map for the dry run of T-DILL & T-VPN | Critical | Open
467 | M467 | 2024-01-04 | BSS | Product category | Finalize details of services of T3 & T4 | Critical | Open
472 | M472 | 2024-01-04 | BSS | Product category | Ensure all 29 BSNL locations are loaded for lead to order presentation | Critical | Open
473 | M473 | 2024-01-04 | BSS | Product category | Submit confirmation responses along with product notes on all raised points | Critical | Open
474 | M474 | 2024-01-05 | BSS | Product category | Review and finalize the Unique ID code convention for various attributes | Critical | Open
475 | M475 | 2024-01-05 | BSS | Product category | Provide demo on Circuit ID generation process and integrate it in BSS | Critical | Open
481 | M481 | 2024-01-05 | BSS | Product category | Provide option to add new Customer ID during onboarding a new customer | Critical | Open
482 | M482 | 2024-01-05 | BSS | Product category | Proceed with Payment approach Option 3 including one-time and recurring invoice generation | Critical | Open
483 | M483 | 2024-01-05 | BSS | Product category | If purchase order and CAF are already loaded in the CRM and mapped with customer account, the CAF generation and approval process should be skipped | Critical | Open
484 | M484 | 2024-01-05 | BSS | Billing Related | L&T and NMSworks to conduct a detailed training session on operational activities of the Billing module post invoice generation | Critical | Open
485 | M485 | 2024-01-05 | BSS | Integration | Offer option to perform manual assignment and auto-assignment of Task Tickets | Critical | Open
486 | M486 | 2024-01-05 | BSS | Dry Run | Demonstrate the complete Buyer and Seller journey | Critical | Open
487 | M487 | 2024-01-05 | BSS | Design & Documentation | Ensure workflows/activities carried outside the BSS system are captured and mapped in BSS process flows | Critical | Open
488 | M488 | 2024-01-05 | BSS | Billing Related | Introduce new column in the invoice template to distinguish billing items as ONE TIME or RECURRING | Critical | Open
489 | M489 | 2024-01-05 | BSS | Billing Related | Review the solution of automatic QR code generation integration with Clear Tax or any other third party portal | Critical | Open
490 | M490 | 2024-01-05 | BSS | Billing Related | Pending changes suggested by the Finance Director should be incorporated into the invoice template | Critical | Open
491 | M491 | 2024-01-05 | BSS | Billing Related | Onboard Pioneer and start generating bills | Critical | Open
492 | M492 | 2024-01-05 | BSS | Billing Related | Provide a detailed approach on how BSS is integrated with Bill Desk | Critical | Open
493 | M493 | 2024-01-05 | BSS | Billing Related | Finalize bill desk integration-related final solution documents covering aspects suggested by Assistant Director-P&E, T-Fiber | Critical | Open
494 | M494 | 2024-01-05 | BSS | Billing Related | Pending discussions from October’23 regarding bill desk integration should be completed | Critical | Open
495 | M495 | 2024-01-05 | BSS | Design Features | Schedule a separate session with OEMs regarding Ticketing process through OSS/BSS referring to the current design template | Critical | Open
496 | M496 | 2024-01-18 | BSS | Design Features | Finalize the Unique ID code convention for various attributes | Critical | Open
497 | M497 | 2024-01-18 | BSS | Design Features | Integrate Circuit ID generation process in BSS | Critical | Open
498 | M498 | 2024-01-18 | BSS | Design Features | Discuss and define a new naming convention for Circuit ID | Critical | Open
499 | M499 | 2024-01-18 | BSS | Design Features | Review direct order through GUI interface | Critical | Open
500 | M500 | 2024-01-18 | BSS | Design Features | Make dependency of A&O for generating Circuit ID independent of BSS | Critical | Open
501 | M501 | 2024-01-18 | BSS | Design Features | Circuit ID should distinguish the origin if a new front-end system is introduced | Critical | Open
502 | M502 | 2024-01-18 | BSS | Design Features | Include option to introduce new Customer ID when onboarding a new customer | Critical | Open
503 | M503 | 2024-01-18 | BSS | Design Features | Transition from Excel-based format to live data for Lit-up and other relevant data | Critical | Open
504 | M504 | 2024-01-18 | BSS | Design Features | Capture whether the network is linear or ring based | Critical | Open
505 | M505 | 2024-01-18 | BSS | Design Features | Review and finalize the definition of 'Ready for Service' | Critical | Open
506 | M506 | 2024-01-18 | BSS | Design Features | Implement user access control for converting from RFO to RFS in BSS | Critical | Open
507 | M507 | 2024-01-18 | BSS | Design Features | Use terms from the industry library for representing 'Ready for Service', etc. | Critical | Open
508 | M508 | 2024-01-18 | BSS | Design Features | Retry the implementation of the Mandal-to-Mandal and Mandal-to-GP dark fiber process | Critical | Open
509 | M509 | 2024-01-18 | BSS | Design Features | Integrate with GIS for live data capturing for feasibility check | Critical | Open
510 | M510 | 2024-01-18 | BSS | Design Features | Correct and finalize the changes suggested in the Lead page | Critical | Open
511 | M511 | 2024-01-18 | BSS | Design Features | Enable communication to customers via Quote Tab in system | Critical | Open
512 | M512 | 2024-01-18 | BSS | Design Features | Review Service order Form and related attributes | Critical | Open
513 | M513 | 2024-01-18 | BSS | Design Features | Implement immediate Dark Fiber service for Mandal to GP and Mandal to Mandal | Critical | Open
514 | M514 | 2024-01-18 | BSS | Design Features | Bring the approach for Bulk Feasibility into use | Critical | Open
515 | M515 | 2024-01-18 | BSS | Design Features | Confirm the list of personnel who will be part of BSS operations | Critical | Open
516 | M516 | 2024-01-18 | BSS | Design Features | Solve the issue of Document repository not being tagged with the order number | Critical | Open
517 | M517 | 2024-01-18 | BSS | Design Features | Present a lead to order and GIS integration way forward for BSNL locations | Critical | Open
518 | M518 | 2024-01-18 | BSS | Design Features | Confirm the timeline for GI-BB | Critical | Open
519 | M519 | 2024-01-18 | BSS | Design Features | Confirm the timeline for T-Cell | Critical | Open
520 | M520 | 2024-01-18 | BSS | Design Features | Discuss with T-Fiber regarding Route Mode and Bridge Mode for Internet Leased Line product | Critical | Open
522 | M522 | 2024-01-24 | BSS | Design & Documentation | Complete delivery of 24 variant products | Critical | Open
523 | M523 | 2024-01-24 | BSS | Design & Documentation | Submit documentation for each of 6 products with respect to flow, regulatory, connectivity to other elements signed off with T-Fiber | Critical | Open
531 | M531 | 2024-01-24 | BSS | Design Features | Finalize the readiness of all modules, including ticketing, Helpdesk, full automation, and WFM | Critical | Open
573 | M573 | 2024-02-14 | BSS | Dry Run | Finish all Dry runs | Critical | Open
581 | M581 | 2024-02-16 | BSS | O&M Strategy | Implement ticket tracking with OSS Service Manager | Critical | Open
582 | M582 | 2024-02-16 | BSS | GIS | Address challenge in BSS-GIS integration | Critical | Open
583 | M583 | 2024-02-16 | BSS | GIS | Ensure collection of required / optional parameters at each step | Critical | Open
584 | M584 | 2024-02-16 | BSS | CRM | Reconsider requirement for document collection in CAF approval stage | Critical | Open
585 | M585 | 2024-02-16 | BSS | CRM | Introduce 'Manual reference ID' attribute in service order form | Critical | Open
586 | M586 | 2024-02-16 | BSS | CRM | Enable option to close or update work order status manually | Critical | Open
587 | M587 | 2024-02-16 | BSS | CRM | Alter selections or drop-down options in Lead, Opportunity, and Service Order page | Critical | Open
588 | M588 | 2024-02-16 | BSS | CRM | Renaming certain attributes in the Opportunity Screen | Critical | Open
589 | M589 | 2024-02-16 | BSS | CRM | Rename 'Normal Loss' attribute to 'Optical Loss' in service order form | Critical | Open
590 | M590 | 2024-02-16 | BSS | CRM | Add multiple reference documents received from customer in service order | Critical | Open
591 | M591 | 2024-02-16 | BSS | BSS | Display order count bar chart in the Dashboard | Critical | Open
592 | M592 | 2024-02-16 | BSS | BSS | Issues observed in the generated CAF to be resolved | Critical | Open
593 | M593 | 2024-02-16 | BSS | GIS | Automatically populate Site FDMS name post-GIS integration | Critical | Open
594 | M594 | 2024-02-16 | BSS | BSS | Limit 'retry' options in BSS until process failure | Critical | Open
595 | M595 | 2024-02-16 | BSS | WFM Application | Ensure multiple tasks tied to single work order are visible in WFM | Critical | Open
596 | M596 | 2024-02-16 | BSS | WFM Application | Make manual acceptance function available in BSS for WFM | Critical | Open
597 | M597 | 2024-02-16 | BSS | NSO | Resolve configuration issues to operationalize Product Catalogue module | Critical | Open
598 | M598 | 2024-02-16 | BSS | BSS | Physical survey and customer signoff to be included in the next step | NON-Critical | Open
599 | M599 | 2024-02-16 | BSS | WFM Application | Feedback on WFM stages to be given in the next meeting | NON-Critical | Open
600 | M600 | 2024-02-16 | BSS | WFM Application | Generate customer signoff through WFM and create separate tabs for storing OTDR traces and customer signoff | NON-Critical | Open
631 | M631 | 2023-07-04 | BSS | T-Cell Launch | Cell Tower Launch: CRM-based demo by L&T with manual NSO loop and GIS by 27th March '23. | Critical | Open
632 | M632 | 2023-07-04 | BSS | T-Cell Launch | Dependencies for Cell Tower Launch: L&T to address payment gateway integration, product catalog sign-off, and E2E flows with T-Fiber approval. | Critical | Open
633 | M633 | 2023-07-04 | BSS | T-Cell Launch | GIS Feasibility for Cell Tower: L&T to present an alternative solution within 2 to 3 days and document risks and mitigation for seamless migration. | Critical | Open
637 | M637 | 2023-07-04 | BSS | BSS | BSS Cadence Calls: L&T to initiate and lead the required Cadence calls to meet project timelines. | Critical | Open
644 | M644 | 2023-07-05 | BSS | BSS | Ensure that the product being developed meets all the discussed and agreed-upon requirements and features. | Critical | Open
645 | M645 | 2023-07-05 | BSS | Dry Run | Complete the BSS Demo according to the feedback points received and demonstrate progress on the same by the first week of May. | Critical | Open
650 | M650 | 2023-07-05 | BSS | Dry Run | Provide BSS Demo with actual auto-feasibility check by 6th April. | Critical | Open
651 | M651 | 2023-07-05 | BSS | Dry Run | Present a clear day-wise plan for BSS readiness by 30th September 2023 for full-fledged production with automated GIS. | Critical | Open
655 | M655 | 2023-07-05 | BSS | WFM Application | Submit internal E2E Project Plan on 31st March’23 as committed for review. | Critical | Open
656 | M656 | 2023-07-05 | BSS | Dry Run | BSS Demo on 6th April’23 must provide order feasibility. | Critical | Open
660 | M660 | 2023-07-05 | BSS | GIS | Perform manual feasibility checking until the GIS tool is ready and data is uploaded into the tool. | Critical | Open
661 | M661 | 2023-07-05 | BSS | GI Demo | Showcase the GI demo by the end of May. | Critical | Open
664 | M664 | 2023-07-05 | BSS | CRM | Handle more professionally the field activity portion of the CRM flow. | Critical | Open
667 | M667 | 2023-07-05 | BSS | Dry Run | BSS Demo on 6th April ’23 to provide order feasibility. | Critical | Open
669 | M669 | 2023-07-05 | BSS | T-Cell Launch | Showcase the demo for T-Cell on 6th April ’23. | Critical | Open
670 | M670 | 2023-07-05 | BSS | Billing Related | Auto-approval of the Invoice by Finance users. | NON-Critical | Open
672 | M672 | 2023-07-21 | BSS | BSS | BSS Readiness Confirmation: L&T to review and update overall readiness for E2E NOC by EOD 8th September '23, including confirmation on launch deliverables and interim launch processes . | Critical | Open
673 | M673 | 2023-07-21 | BSS | Dry Run | BSS Demo Observations: L&T to address observations from the BSS Demo on 24th July '23 and action items from the meeting with Director-Finance, T-Fiber . | Critical | Open
675 | M675 | 2023-07-21 | BSS | NSO | Static IP and UI/UX Changes: Ready for demonstration by L&T . | NON-Critical | Open
677 | M677 | 2023-07-21 | BSS | Billing Related | Payment Gateway Completion: If SSL Certificate is provided by 11th September '23, L&T to complete the payment gateway by 30th September '23 . | Critical | Open
678 | M678 | 2023-07-21 | BSS | Dry Run | BSS E2E Demo: Chief Delivery Officer, L&T proposed to have the E2E BSS Demo on 4th July '23, with features to be confirmed by 1st July '23 . | Critical | Open
682 | M682 | 2023-07-21 | BSS | Testing Environment | Onboarding of Billing Specialist: L&T to update on the onboarding process for a long-term Billing Specialist . | Critical | Open
683 | M683 | 2023-07-21 | BSS | Billing Related | Closure of CRM Billing Process and Invoice Format: L&T to close action items regarding CRM Billing Process and Invoice format . | Critical | Open
684 | M684 | 2023-07-21 | BSS | Action Points | BSS Roadmap Progress: L&T to demonstrate completed points for closure and include related test cases . | Critical | Open
685 | M685 | 2023-07-21 | BSS | Dry Run | Next BSS Demo for Cell Tower: L&T to confirm the date of the next BSS Demo for Cell Tower by 21st August '23 . | Critical | Open
686 | M686 | 2023-07-21 | BSS | Action Points | User Groups Demonstration: L&T to showcase the demonstration on user groups along with the demo for Cell Tower . | Critical | Open
687 | M687 | 2023-07-21 | BSS | Action Points | Next BSS Demo Schedule: Scheduled for 23rd August '23, to include RFS/RFO status, notification templates, UI/UX validation, and exception scenarios . | Critical | Open
693 | M693 | 2023-07-26 | BSS | Dry Run | Preparation for a dry run of BSS to include WFM. | Critical | Open
714 | M714 | 2023-08-01 | BSS | Launch Readiness | Set up SMS based alerting. | Critical | Open
719 | M719 | 2023-08-01 | BSS | Launch Readiness | Create and finalize multiple channels of communication to the Helpdesk such as SMS, WhatsApp, and email. | Critical | Open
737 | M737 | 2023-08-18 | BSS | NSO | BSS Readiness and Demo: L&T to demonstrate Static IP and UI/UX changes, with WFM integration not part of the demonstration. | Critical | Open
739 | M739 | 2023-08-18 | BSS | Billing Related | Payment Gateway Completion: L&T to complete the payment gateway by 30th September '23 if SSL Certificate is provided by 11th September '23. | Critical | Open
741 | M741 | 2023-08-18 | BSS | BSS | BSS Integration with Lepton WFM: L&T to complete the demo of BSS Integration with Lepton WFM by 25th August '23. | Critical | Open
742 | M742 | 2023-08-18 | BSS | NSO | NSO Competency Plan: L&T to put in place an NSO competency plan. | Critical | Open
743 | M743 | 2023-08-18 | BSS | T&D Environment | Separation of T&D and Production Environments: L&T to provide a plan addressing the requirement for separate environments. | Critical | Open
744 | M744 | 2023-08-18 | BSS | Resource Augmentation | Onboarding of Billing Specialist: L&T to update on the onboarding process for a long-term Billing Specialist. | Critical | Open
745 | M745 | 2023-08-18 | BSS | Billing Related | Closure of CRM Billing Process and Invoice Format: L&T to close action items regarding CRM Billing Process and Invoice format. | Critical | Open
746 | M746 | 2023-08-18 | BSS | T&D Environment | BSS Roadmap Progress: L&T to demonstrate completed points for closure and include related test cases. | Critical | Open
747 | M747 | 2023-08-18 | BSS | Dry Run | Next BSS Demo for Cell Tower: L&T to confirm the date of the next BSS Demo for Cell Tower by 21st August '23. | Critical | Open
748 | M748 | 2023-08-18 | BSS | Dry Run | User Groups Demonstration: L&T to showcase the demonstration on user groups along with the demo for Cell Tower. | Critical | Open
749 | M749 | 2023-08-18 | BSS | Dry Run | Next BSS Demo Schedule: Scheduled for 23rd August '23, to include RFS/RFO status, notification templates, UI/UX validation, and exception scenarios. | Critical | Open
751 | M751 | 2023-08-18 | BSS |  | Dedication of Time to T-Fiber Project: Chief Delivery Officer, L&T to confirm dedicating 2 days a week to the T-Fiber Project in Hyderabad leading up to the Network Launch. | Critical | Open
752 | M752 | 2023-08-23 | BSS |  | Review of alert and notification templates and implementation. | Critical | Open
753 | M753 | 2023-08-23 | BSS |  | Lead data presentation for Airtel and GI_BB customers. | Critical | Open
754 | M754 | 2023-08-23 | BSS |  | Walkthrough of Ready for Service (RFS) Process. | Critical | Open
755 | M755 | 2023-08-23 | BSS |  | Identifying and addressing challenges for user experience in CRM. | Critical | Open
756 | M756 | 2023-08-23 | BSS |  | Development of BSS demo of CSP. | Critical | Open
757 | M757 | 2023-08-23 | BSS |  | Analysis of the issue impacting BSS demo. | Critical | Open
759 | M759 | 2023-08-23 | BSS |  | Establish a comprehensive list of event notification scenarios and implementation plan. | Critical | Open
760 | M760 | 2023-08-23 | BSS |  | Identify and create more user groups according to the business and workflow requirements. | Critical | Open
761 | M761 | 2023-08-23 | BSS |  | Resolve discrepancies with manual updates for RFO and RFS status. | Critical | Open
763 | M763 | 2023-08-23 | BSS |  | Improve user experience for better data accuracy. | Critical | Open
764 | M764 | 2023-08-23 | BSS |  | Ensure the BSS-Lead, L&T and Head Telecom Practice, L&T to discuss and create more user groups according to the business and workflow requirements. | Critical | Open
765 | M765 | 2023-08-23 | BSS |  | Introduce a status/bucket "Renewal" for orders that need further work / rectification. | Critical | Open
766 | M766 | 2023-08-23 | BSS |  | Ensure that the entire network POI/ PoP status including 12751 GPs, 1 NOC, all zones, districts & Mandal nodes should be available in CRM database. | Critical | Open
767 | M767 | 2023-08-23 | BSS |  | Address observations made in the CSP by L&T and implement changes. | Critical | Open
768 | M768 | 2023-08-23 | BSS | T-Cell Launch | Propose the next date for T-Cell Demo. | Critical | Open
773 | M773 | 2023-08-31 | BSS |  | Share status updates on BSS action items by 1st September '23. | Critical | Open
792 | M792 | 2023-09-08 | BSS |  | Payment Gateway Completion: L&T to complete the payment gateway by 30th September '23 if SSL Certificate is provided by 11th September '23. | Critical | Open
804 | M804 | 2023-09-22 | BSS |  | Overcoming technical issues observed in CSP and CRM. | Critical | Open
805 | M805 | 2023-09-22 | BSS |  | Reviewing processes of order booking to be communicated more simply and effectively to the end users. | Critical | Open
821 | M821 | 2023-10-18 | BSS | CSP Testing | Adding a back button on the payment screen. | Critical | Open
822 | M822 | 2023-10-18 | BSS | CSP Testing | Providing guidelines for the CAF upload stage and adding a disclaimer for "Subject to Verification of CAF." | Critical | Open
823 | M823 | 2023-10-18 | BSS | CSP Testing | Ensuring offline payment transactions are viewable and mandatory sections of the CAF are highlighted. | Critical | Open
824 | M824 | 2023-10-18 | BSS | CSP Testing | Addressing issues with ticket creation, notification, and enquiry handling in the CSP. | Critical | Open
825 | M825 | 2023-10-18 | BSS | CSP Testing | Clarifying the bulk upload of leads and the feasibility of integrating such a feature in the CSP. | Critical | Open
826 | M826 | 2023-10-18 | BSS | CSP Testing | Resolving user interface issues such as incorrect OTP entry pop-ups, case sensitivity in order ID searches, and real-time synchronization between GIS-OSS for feasibility checks. | Critical | Open
827 | M827 | 2023-10-18 | BSS | CSP Testing | Removing unnecessary elements from the UI, aligning GP names with government lists, and modifying the sequence of address fields. | Critical | Open
828 | M828 | 2023-10-18 | BSS | CSP Testing | Integrating Google API for auto-populating details based on service location selection. | Critical | Open
829 | M829 | 2023-10-18 | BSS | CSP Testing | Ensuring proper display and functionality of various screens within the CSP, including payment and order summary screens. | Critical | Open
830 | M830 | 2023-10-18 | BSS | CSP Testing | Configuring event-based email notifications for actions within the CSP. | NON-Critical | Open
894 | M894 | 2023-12-19 | BSS |  | BSS Test Environment: VP-Program, T-Fiber requested BSS-SME, L&T to investigate and expedite the resolution of the slowness in the BSS Test Environment. | NON-Critical | Open
895 | M895 | 2023-12-19 | BSS |  | Performance Benchmarking Tools: BSS-SME, L&T to explore web-based analytic tools for performance benchmarking. | NON-Critical | Open
896 | M896 | 2023-12-19 | BSS |  | Status of Action Items: VP-Program, T-Fiber emphasized that action items marked as "Completed" should only be rendered "Closed" upon concurrence from T-Fiber. | NON-Critical | Open
897 | M897 | 2023-12-19 | BSS |  | SMS and CSP Integration: BSS-SME, L&T to implement SMS dispatch notification in CSP and include a link to the CSP page for T-Fiber USER to Approve or Reject. | Critical | Open
898 | M898 | 2023-12-19 | BSS |  | Product Catalogue Demo: SVP, T-Fiber requested a demo to showcase the configurable product catalogue feature. | Critical | Open
899 | M899 | 2023-12-19 | BSS |  | Backend Validation Demo: Director-P&E, T-Fiber asked for a demo of Backend Validation and a document with validation steps. | Critical | Open
900 | M900 | 2023-12-19 | BSS |  | Page Load Benchmark: Director-P&E, T-Fiber requested a benchmark for page loading to be defined. | Critical | Open
901 | M901 | 2023-12-19 | BSS |  | Payment Gateway Integration: BSS-SME, L&T confirmed integration is completed with a test account. | Critical | Open
902 | M902 | 2023-12-19 | BSS |  | BSS E2E Demo: Chief Delivery Officer, L&T proposed to have the E2E BSS Demo on 4th July '23, with features to be confirmed by 1st July '23. | Critical | Open
908 | M908 | 2023-12-19 | BSS | Resource Augmentation | NMS Works Resources: SVP, T-Fiber requested a discussion with EVP, T-Fiber on the adequacy of NMS works resources. | Critical | Open
911 | M911 | 2023-12-19 | BSS |  | UI/UX Resource: BSS-SME, L&T updated that an internal UI/UX resource has been onboarded. | Critical | Open
912 | M912 | 2023-12-19 | BSS |  | Discussions on the BSS roadmap, including the status of action items from the dry run and CSP testing exercise. | Critical | Open
933 | M933 | 2024-01-05 | BSS | BSS | BSS readiness | Critical | Open
934 | M934 | 2024-01-05 | BSS | Product category | Unique ID – Naming Convention | Critical | Open
936 | M936 | 2024-01-05 | BSS | Billing Related | Payment Approach & Integration | Critical | Open
937 | M937 | 2024-01-05 | BSS | Billing Related | Invoice Template | Critical | Open
938 | M938 | 2024-01-05 | BSS | Billing Related | Integration of Bill Desk & Other Points | Critical | Open
939 | M939 | 2024-01-18 | BSS | Product category | BSS progress session for Dark Fiber | Critical | Open
942 | M942 | 2024-01-18 | BSS | CRM | Implement auto-population of fields in CRM | Critical | Open
943 | M943 | 2024-01-18 | BSS |  | Implement user access control for RFO to RFS conversion | Critical | Open
944 | M944 | 2024-01-18 | BSS | GIS | Integrate BSS with GIS for distance calculation | Critical | Open
945 | M945 | 2024-01-18 | BSS |  | Provide updates and roadmap for Lead/Opportunity/Order conversion process | Critical | Open
946 | M946 | 2024-01-18 | BSS |  | Implement Mandal to GP and Mandal to Mandal Dark fiber service | Critical | Open
947 | M947 | 2024-01-18 | BSS |  | Clarify the list of individuals involved in BSS operations | Critical | Open
948 | M948 | 2024-01-18 | BSS |  | Resolve document upload feature with order tagging | Critical | Open
949 | M949 | 2024-01-18 | BSS |  | Prepare for soft launch in accordance with management's direction | Critical | Open
950 | M950 | 2024-01-18 | BSS |  | Upload BSNL locations for demonstration and discuss GIS integration and document repository issues | Critical | Open
951 | M951 | 2024-01-18 | BSS |  | Confirm timeline for GI-BB and T-Cell | Critical | Open
952 | M952 | 2024-01-18 | BSS |  | Discuss Route and Bridge Mode for Internet Leased Line product | Critical | Open
995 | M995 | 2024-01-25 | BSS |  | Continue defining logic for Dark Fiber and GI-BB products | Critical | Open
1024 | M1024 | 2024-02-16 | BSS |  | Ticketing process and tracking | Critical | Open
1025 | M1025 | 2024-02-16 | BSS |  | Task creation in billing module | Critical | Open
1027 | M1027 | 2024-02-16 | BSS |  | Contact synchronization in Lead creation and conversion | Critical | Open
1035 | M1035 | 2024-03-14 | BSS |  | Addressing the delays in the End-to-End demonstration of products due to billing/invoice module issues. | Critical | Open
1046 | M1046 | 2024-03-14 | BSS |  | L&T to be prepared for the next dry run demo and update the order management and quote management statuses. | Critical | Open
1194 | M1194 | 2024-12-09 | BSS |  | Aravindham have personal challenges, can come on MS Team. Request him to come for 2 day for physical meeting | Critical | Closed
1207 | M1207 | 2024-12-10 | BSS |  | One call with BSS and NSO SME to be done tomorrow morning | Critical | Closed
1227 | M1227 | 2024-12-10 | BSS |  | Is our network integrated with Aadhar servers, GST? LTTS confirmed it is not integrated | Critical | Open
1258 | M1258 | 2024-12-11 | BSS |  | Capture Aadhar integration need in our requirement doc / soln/SOW for BSS/NSO. | Critical | Open
1261 | M1261 | 2024-12-11 | BSS |  | Business flow discussed like existing telecom operator customer mgmt. case study . BSS Workout sheet made by Principal Consultant will be sent to you, and will discuss in detailed along with KNOT, TFIBER, TFIBER business/finance team when Aravindhan comes over to HYD at TFIBER office | Critical | Open
195 | M195 | 2023-09-22 | DR | O&M Strategy | a brief note on what is required to be delivered by CtrlS for DR | NON-Critical | Open
196 | M196 | 2023-09-22 | DR | Functional AT Plan | Share the test results of DR systems with T-Fiber. | NON-Critical | Open
322 | M322 | 2023-10-19 | DR | DNS Switchover | Point No. 79: to confirm that DNS switchover between DC and DR locations should be automatic • Chief Delivery Officer, LTTS updated that this in follow-up with Cisco and CtrlS, next update by 26th October ’23. | NON-Critical | Closed | [6 empty] | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\DR\Artifact for - T79
323 | M323 | 2023-10-19 | DWDM | Integration | Point No. 103: DWDM-OSS integration - Service Inventory Data Availability in HPE OSS & Point No. 237: DWDM-OSS integration - Service inventory data availability in HPE OSS • Technical Head, L&T updated that this is targeted for closure by 15th November ’23. | Critical | Open |  |  |  | Dependancy on NSO, part of 472-points, Point No. 103 & 237
324 | M324 | 2023-10-19 | DWDM | Integration | Point No. 104 – DWDM-OSS integration: Planned Event Service Impact analysis report & Point No. 238: DWDM-OSS integration: For planned event service impact analysis data / report SVP, T-Fiber asked for the SOP that shall be put in place by L&T until the Service Inventory solution from HP is in place | Critical | Open |  |  |  | Dependancy on NSO, part of 472-points, Point No. 104 & 238
642 | M642 | 2023-07-04 | Field Related | Zonal Path connectivity | Zonal Path Completion: L&T to complete Medak to Mahbubnagar Zonal path by 31st March and AT by 15th April '23; AT of other completed zonal paths by 31st March '23. | Critical | Open
652 | M652 | 2023-07-05 | Field Related | Full NOC Readiness | Complete the connection of 589 Mandals by 1st week of June, with an expectation of minimum 3 hours and maximum of 5 hours for each Mandal. | Critical | Open
710 | M710 | 2023-08-01 | Field Related | Launch Readiness | MSIs to prioritise a district-wise approach over a scattered approach. | Critical | Open
711 | M711 | 2023-08-01 | Field Related | Mandal Rings | The status of Mandal Rings completion i.e. GIS uploading done, splicing pending, attribute updating is pending. | NON-Critical | Open
775 | M775 | 2023-09-08 | Field Related | GI Connectivity | Rectification and progress of GI Connectivity. | NON-Critical | Open
913 | M913 | 2023-12-19 | Field Related | District Completion Target | The urgency for STL to complete E2E for additional districts by 07th April '23 and the need to resolve issues impacting project progress. | NON-Critical | Open
915 | M915 | 2023-12-19 | Field Related | Resource Augmentation | The requirement for STL to address resource productivity issues and ensure sufficient resources for project completion. | NON-Critical | Open
916 | M916 | 2023-12-19 | Field Related | Payment Related | The need for T-Fiber to expedite payment processes and for STL to provide a senior resource to orchestrate project completion efforts. | NON-Critical | Open
918 | M918 | 2023-12-19 | Field Related | Zonal Path connectivity | The completion of zonal paths and the delivery of districts within the committed timelines. | NON-Critical | Open
997 | M997 | 2024-01-25 | Field Related |  | Improve resource mobilization & achieve 65% network availability | NON-Critical | Open
998 | M998 | 2024-01-25 | Field Related |  | Engage partners for O&M resources augmentation and ensure active spares availability | NON-Critical | Open
999 | M999 | 2024-01-25 | Field Related |  | Deploy committed resources and achieve network availability | NON-Critical | Open
1001 | M1001 | 2024-01-25 | Field Related |  | Complete implementation of Mandal rings for NoFN PH-1 to declare District Go-Live | Critical | Open
1002 | M1002 | 2024-01-25 | Field Related |  | Restore all social welfare and tribal welfare schools to serviceable condition | Critical | Open
1003 | M1003 | 2024-01-25 | Field Related |  | Complete all GI connectivity by March '24 and secure GI payments | Critical | Open
1004 | M1004 | 2024-01-25 | Field Related |  | Focus on top 4 priorities for network readiness | Critical | Open
1005 | M1005 | 2024-01-25 | Field Related |  | Make the network ready for service review by State IT&EC Minister | Critical | Open
1006 | M1006 | 2024-02-13 | Field Related |  | Issue with status of Sangareddy district E2E completion | Critical | Open
1007 | M1007 | 2024-02-13 | Field Related |  | Status of GP migrations and POP completion | Critical | Open
1008 | M1008 | 2024-02-13 | Field Related |  | Pending mandals for End-End AT | Critical | Open
1040 | M1040 | 2024-03-14 | Field Related | Network Availibilty | Achieving network availability reports compliance and readiness. | Critical | Open
1052 | M1052 | 2024-03-14 | Field Related | District Completion Target | Complete E2E AT Certificate of Rangareddy, Mahbubnagar, Vikarabad & Narayanpet districts by 7th April 2024. | NON-Critical | Open
1056 | M1056 | 2024-03-14 | Field Related | Network Availibilty | Achieve 97% Network availability in Gadwal & Wanaparthy from 1st April 2024. | NON-Critical | Open
1057 | M1057 | 2024-03-14 | Field Related | Network Availibilty | Achieve 90% Network availability in Mahbubnagar and Rangareddy for April 2024. | NON-Critical | Open
10 | M10 | 2023-04-03 | GIS | Resource Related | Evaluation of License Sufficiency and Ramp-Up Plan | Critical | Open | OSS Dashboards
16 | M16 | 2023-04-19 | GIS | Functional AT Plan | Loading Sample Data and Internal Quality Test Report Submission | NON-Critical | Open | OSS Dashboards
17 | M17 | 2023-05-18 | GIS | Functional AT Plan | Basic GIS Tool UAT for TPA | Critical | Open | OSS Dashboards
21 | M21 | 2023-06-01 | GIS | User Experience | Google Map availability in Geo Media Tool with real time navigation | Critical | Open | OSS Dashboards
22 | M22 | 2023-06-01 | GIS | User Experience | Fixed Topology Nomenclature | Critical | Open | OSS Dashboards
23 | M23 | 2023-06-01 | GIS | User Experience | Character size in G-Tech | Critical | Open | OSS Dashboards
24 | M24 | 2023-06-01 | GIS | User Experience | Searching for location accuracy in G-Tech with pinpoint accuracy | Critical | Open | OSS Dashboards
25 | M25 | 2023-06-01 | GIS | User Experience | Self-address auto-population in G-Tech | Critical | Open | OSS Dashboards
26 | M26 | 2023-06-01 | GIS | User Experience | GPON Fiber Termination plan adherence | Critical | Open | Gtech
27 | M27 | 2023-06-07 | GIS | Handbook & SOPs | Approval mechanism for object changes/deletion | Critical | Open | Gtech
28 | M28 | 2023-06-07 | GIS | Handbook & SOPs | Change Management Log/User Log history | Critical | Open | Gtech
29 | M29 | 2023-06-07 | GIS | Handbook & SOPs | Data Validation Rules document | Critical | Open | Gtech
30 | M30 | 2023-06-07 | GIS | User Experience | Show duct length, Cable length, chambers, and joint closures in a Mandal | NON-Critical | Open | Gtech
31 | M31 | 2023-06-07 | GIS | User Experience | Correct Actual Measure Length and Loop length in BOQ | NON-Critical | Open | Gtech
32 | M32 | 2023-06-07 | GIS | Handbook & SOPs | Detailed validation document | NON-Critical | Open | Gtech
33 | M33 | 2023-06-07 | GIS | User Experience | Hyperlink real images to GPs and Mandals | Critical | Open | Gtech
34 | M34 | 2023-06-07 | GIS | Installation | 100TB storage for LIDAR survey data | Critical | Closed | Gtech | 75 TB Storage is allotted, 25 TB is Provisioned for each PKG.
35 | M35 | 2023-06-07 | GIS | Training | Hands-on Training on GIS tool | NON-Critical | Open | Gtech
36 | M36 | 2023-06-07 | GIS | Dashboards | Discuss and Develop Dashboard for GIS tool | NON-Critical | Open | Gtech
37 | M37 | 2023-06-07 | GIS | User Experience | New validation Logic to be incorporated in DI tool - if Depth is zero and construction method is HDD/OT, Protection is required | NON-Critical | Open | Gtech
40 | M40 | 2023-06-19 | GIS | User Experience | Download active port connectivity details | Critical | Closed | Gtech
41 | M41 | 2023-06-19 | GIS | User Experience | Real-time sync of topology details from OSS | Critical | Open | Gtech
42 | M42 | 2023-06-19 | GIS | User Experience | automate active connectivity within site with logical link name populated from OSS | Critical | Open | Gtech
43 | M43 | 2023-06-19 | GIS | Functional AT Plan | TPA to validate active-active connectivity | Critical | Closed | Gtech
44 | M44 | 2023-06-19 | GIS | User Experience | Add card/module/slot level details | Critical | Open | Gtech
45 | M45 | 2023-06-19 | GIS | User Experience | Ensure Topology name uniqueness | Critical | Closed | Gtech
46 | M46 | 2023-06-19 | GIS | User Experience | BoQ feature to download passive/active devices separately | Critical | Closed | Gtech
47 | M47 | 2023-06-19 | GIS | User Experience | Feasibility closure case reports from GIS | Critical | Open | Gtech
48 | M48 | 2023-06-19 | GIS | User Experience | Route path identification through Google | Critical | Closed | Gtech
49 | M49 | 2023-06-19 | GIS | User Experience | Network portal search functionality for objects | Critical | Open | Gtech
50 | M50 | 2023-06-19 | GIS | User Experience | GIS function for bulk feasibility report | Critical | Open | Gtech
51 | M51 | 2023-06-19 | GIS | User Experience | building logic / intelligence to populate the relevant information in the BoQ, presently available as a dump. | Critical | Closed | Gtech
52 | M52 | 2023-06-19 | GIS | Integration | GIS integration with WFM tool | Critical | Open | Gtech
53 | M53 | 2023-06-19 | GIS | User Experience | Automation of active connectivity | Critical | Open | Gtech
54 | M54 | 2023-06-19 | GIS | Integration | Sync issue error alerts in OSS and GIS | Critical | Open | Gtech
532 | M532 | 2024-01-24 | GIS | Design Features | Discuss internally and provide a feasible response about leading the GIS data update process | Critical | Open
634 | M634 | 2023-07-04 | GIS | GIS Completion | GIS OEM - Hexagon: L&T to ensure GIS readiness within 2 to 4 weeks for service provisioning automation. | Critical | Open
643 | M643 | 2023-07-05 | GIS | GIS Completion | Evaluate the current readiness status of the GIS tool and address the pending issues. | Critical | Open
647 | M647 | 2023-07-05 | GIS | GIS Completion | Submit revise plan for Complete GIS Tool (Basic) Readiness by 30th April’23, GIS Tool (Advanced) Readiness by 31st May’23, and GIS Tool (Integration) Readiness by 30th June’23. | Critical | Open
648 | M648 | 2023-07-05 | GIS | GIS Completion | Submit responses on concerns of the number of GIS licences for data upload and readiness of current helpdesk to start taking calls for GI. | Critical | Open
659 | M659 | 2023-07-05 | GIS | GIS Completion | Integrate the processes recommended by the external auditor into the process flow of GIS readiness. | Critical | Open
662 | M662 | 2023-07-05 | GIS | GIS Completion | Improve coordination with GIS, OEMs, and explore the possibility of developing a new GIS OEM to deliver the requirements of T-Fiber. | Critical | Open
706 | M706 | 2023-08-01 | GIS | Launch Readiness | Each MSI needs to commit to the target for Mandal upload in the GIS tool for business readiness. | Critical | Open
707 | M707 | 2023-08-01 | GIS | Launch Readiness | Commit target dates for GIS Data Upload for each package. | Critical | Open
708 | M708 | 2023-08-01 | GIS | Launch Readiness | Package A needs to provide a day by day Mandal upload action plan to meet the committed target dates. | Critical | Open
709 | M709 | 2023-08-01 | GIS | Launch Readiness | Packages B and C are expected to submit a proposal to hasten data upload in consultation with GIS-SME, Pkg-A. | Critical | Open
712 | M712 | 2023-08-01 | GIS | Launch Readiness | The current committed dates for GIS Data Upload are not meeting the expectations of T-Fiber. | Critical | Open
886 | M886 | 2023-12-15 | GIS | GIS Related | Geo-fencing: L&T to explain how geo-fencing shall work for a fiber route and how it will be assigned for Mandal and GP locations. | Critical | Open
904 | M904 | 2023-12-19 | GIS | GIS Completion | GIS Integration: BSS-SME, L&T to ensure Dark Fiber with BSS and WFM flows can be shown by 30th December '23. | Critical | Open
906 | M906 | 2023-12-19 | GIS | Feasibility Logic | Feasibility Logic: SVP, T-Fiber asked for the feasibility logic to include S1, S2 splitters and to be demonstrated in the next demo. | Critical | Open
907 | M907 | 2023-12-19 | GIS | Feasibility Logic | Bandwidth Feasibility Logic: Director-P&E, T-Fiber requested the logic for Bandwidth feasibility in the backhaul to be provisioned and operationalised immediately. | Critical | Open
940 | M940 | 2024-01-18 | GIS | Integration | Integrate live data for location feasibility | Critical | Open | Gtech
941 | M941 | 2024-01-18 | GIS | Integration | Review and align ‘Ready for Service’ nomenclature | Critical | Open | Gtech
1274 | M1274 | 2025-04-03 | GIS | User Experience | GIS: Make a PPT for operationalisation of GIS Ops & updation. This will be shared to PKG-B & C | Critical | Closed | Gtech
294 | M294 | 2023-10-19 | GPON | Interim NOC | Request a Note (Note 2) from L&T addressing the impact of the unavailability of NBI API availability for BW query Dependent on new OLT build for GI deployment and how NOC operations will be managed in the interim period until the required features are developed and integrated with seamless transition. | Critical | Open |  | Updated in 472 Tracker point-T175 | Sayyad Pasha
295 | M295 | 2023-10-19 | GPON | Integration | Point No. 175: CR for Nokia API integration to resolve BW query and PMS-related issues. 1. Note 2 should also cover Point No. 175. 2. Set a target completion date of November 20th '23 for this activity. | Critical | Open |  | Updated in 472 Tracker point-T175 | Sayyad Pasha
296 | M296 | 2023-10-19 | GPON | Upgradation | Point No. 179: Troubleshooting required with Tejas and Nokia for Tejas ONT firmware upgrade issue. 1. Technical Head from L&T to seek support from L&T-Contracts team and aim for implementation within 15-20 days from the resolution of the issue. 2. L&T to submit the agreed Scope between L&T and NOC OEMs (primarily OSS, BSS, NSO) by October 24th '23. 3.Request a Note (Note 3) outlining the interim/final solution and an undertaking co-signed by Package Owners to be submitted by October 26th '23. 4.Target completion of Point No. 179 by November 20th '23. | Critical | Open |  | Updated in 472 Tracker point-T179 | Sayyad Pasha
297 | M297 | 2023-10-19 | GPON | Upgradation | Point No. 180: Nokia ONT to support NAT, DHCP in both Router and Bridge modes. 1. Instruct L&T to identify the number of ONTs in the warehouse and send them to the Nokia Warehouse immediately for upgrade. 2. Coordinate with Package B&C for similar actions. 3.Note 4 on the mitigation and deployment plan for remediation, along with the timelines, testing to be part of the method of deployment. | Critical | Open |  | Updated in 472 Tracker point-T180 | Sayyad Pasha
318 | M318 | 2023-10-19 | Security | Design features | Point No. 333: Alepo AAA to be integrated with AD SVP, T-Fiber asked for an SOP to be defined for this. • SVP, T-Fiber asked for a note (Note 8) recording this statement. | Critical | Open |  | This is Security point
96 | M96 | 2023-08-01 | Helpdesk | User Experience | Toll Free-Number | NON-Critical | Open |  | 11-09-2025: Same as T366(472) Closed |  | COMPLETED & APPROVED | Yes | 2025-07-19 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\T366
97 | M97 | 2023-08-01 | Helpdesk | User Experience | Different communication channels such as SMS, WhatsApp, Email | Critical | open |  | 11- Sep-25: SMS and E-mail Integrated and Whatsapp existing Product will not support |  | CLOSURE REVIEW PENDING
98 | M98 | 2023-08-01 | Helpdesk | Dashboards | Categorization of Incoming Queries | Critical | open |  | 11- Sep-25: Available in Neox Application |  | CLOSURE REVIEW PENDING
99 | M99 | 2023-08-01 | Helpdesk | User Experience | Bilingual IVR | Critical | open |  |  |  | CLOSURE REVIEW PENDING
100 | M100 | 2023-08-01 | Helpdesk | Handbook & SOPs | Call Escalation Recording Process | Critical | open |  |  |  | CLOSURE REVIEW PENDING
101 | M101 | 2023-08-01 | Helpdesk | User Experience | Missed Call Feature on WhatsApp | Critical | open |  | 11-Sep-25: Existing product will not Support |  | CLOSURE REVIEW PENDING
102 | M102 | 2023-08-01 | Helpdesk | User Experience | Automated Response for Email Complaints | Critical | Open |  |  |  | WIP
103 | M103 | 2023-08-01 | Helpdesk | Resource Related | Helpdesk Manager Availability for 24 Hrs | Critical | open |  | 11-Sep-25: Existing Lead available during Business Hours, Remaining duration Shift Lead will Manage |  | CLOSURE REVIEW PENDING
104 | M104 | 2023-08-01 | Helpdesk | Handbook & SOPs | Incident categorization to be exhaustive, response timelines to be defined and attached based on incident categorization. | Critical | open |  |  |  | CLOSURE REVIEW PENDING
105 | M105 | 2023-08-01 | Helpdesk | Handbook & SOPs | Clarity required in the definition of roles and responsibilities of L1 and L2 agents, incident categorization to be handled at L1 level, type of queries, resolution time, escalation matrix to be better defined. | Critical | open |  |  |  | CLOSURE REVIEW PENDING
106 | M106 | 2023-08-01 | Helpdesk | Mini Helpdesk | Mechanism needed between T-NOC Helpdesk and District Collector offices for complaints that may be made directly to the District Collector office. Provision for a mini-Helpdesk node at each district, with a facility/hotline for an authorized person to log a call/complaint on behalf of the District Collector Office, similar to the direct walk-in channel for customer complaints at T-NOC. | NON-Critical | open |  | 11-Sep-25: Duplicate as Above |  | CLOSURE REVIEW PENDING
107 | M107 | 2023-08-01 | Helpdesk | Handbook & SOPs | Clarification needed on whether general enquiries are treated as incidents. | NON-Critical | open |  | 11-Sep-25 Ans: No |  | CLOSURE REVIEW PENDING
108 | M108 | 2023-08-01 | Helpdesk | Handbook & SOPs | Clarification needed on whether general enquiries are treated as incidents. | NON-Critical | open |  | 11-Sep-25 Ans: No |  | CLOSURE REVIEW PENDING
109 | M109 | 2023-08-01 | Helpdesk | Handbook & SOPs | Detailed documentation needed on critical, major, minor escalations, and their related thresholds. | NON-Critical | open |  | 11-Sep-25: Updated Document Shared 23-Aug-23 |  | CLOSURE REVIEW PENDING
110 | M110 | 2023-08-01 | Helpdesk | Handbook & SOPs | Feedback Collection Review Mechanism | NON-Critical | Open |  |  |  | WIP
111 | M111 | 2023-08-01 | Helpdesk | Handbook & SOPs | Documentation required stating that L2 agents shall make outbound calls to customers. | NON-Critical | open |  | 11-Sep-25: Updated Document Shared 23-Aug-23 |  | CLOSURE REVIEW PENDING
112 | M112 | 2023-08-01 | Helpdesk | Handbook & SOPs | Inquiry about how the Helpdesk addresses cases where the number of the person calling differs from the number registered in the BSS database. | NON-Critical | open |  | 11-Sep-25: BSS Integration |  | CLOSURE REVIEW PENDING
113 | M113 | 2023-08-01 | Helpdesk | Handbook & SOPs | Clarification needed on the sphere of activity between NOC Technical administrators and Helpdesk agents. | NON-Critical | open |  | 11-Sep-25: Updated Document Shared 23-Aug-23 |  | CLOSURE REVIEW PENDING
114 | M114 | 2023-08-01 | Helpdesk | Training | Training for Helpdesk Users and Managers | Critical | open |  |  |  | CLOSURE REVIEW PENDING
115 | M115 | 2023-08-01 | Helpdesk | Handbook & SOPs | Detailed Helpdesk Process Steps | Critical | open |  | 11-Sep-25: Updated Document Shared |  | CLOSURE REVIEW PENDING
116 | M116 | 2023-08-01 | Helpdesk | Handbook & SOPs | Clarification needed on addressing the subjective nature of "Non-Technical" calls. | Critical | open |  | 11-Sep-25: It will be Handled by Proposed T fiber Business Helpdesk |  | CLOSURE REVIEW PENDING
117 | M117 | 2023-08-01 | Helpdesk | Handbook & SOPs | Assumptions for Estimated Calls per Day | Critical | open |  | 11-Sep-25: Data Shared |  | CLOSURE REVIEW PENDING
118 | M118 | 2023-08-01 | Helpdesk | Handbook & SOPs | Readiness of Helpdesk to report on compliances and responsiveness and calculate penalties. | Critical | open |  |  |  | CLOSURE REVIEW PENDING
119 | M119 | 2023-08-01 | Helpdesk | Handbook & SOPs | Live Intrusion of Calls | Critical | open |  | 11-Sep-25: Feature Available, Shall be demonstrated |  | CLOSURE REVIEW PENDING
120 | M120 | 2023-08-01 | Helpdesk | Handbook & SOPs | Duration of Call Measurement | Critical | open |  | 11-Sep-25: Feature Available, Shall be demonstrated |  | CLOSURE REVIEW PENDING
121 | M121 | 2023-08-01 | Helpdesk | Handbook & SOPs | Exceptions in IVR User Response | Critical | open |  |  |  | CLOSURE REVIEW PENDING
122 | M122 | 2023-08-01 | Helpdesk | Handbook & SOPs | The unit of measurement is required for all Key Performance Indicator (KPI) parameters. | Critical | open |  | 11-Sep-25: Updated Document Shared 23-Aug-23 |  | CLOSURE REVIEW PENDING
123 | M123 | 2023-08-01 | Helpdesk | Handbook & SOPs | Sample Methods for KPI Calculations | Critical | open |  | 11-Sep-25: Updated Document Shared 23-Aug-23 |  | CLOSURE REVIEW PENDING
124 | M124 | 2023-08-01 | Helpdesk | Handbook & SOPs | Inquiry into how Customer Satisfaction (CSAT) is measured and whether there is a mechanism for transactional feedback. | Critical | Open |  |  |  | WIP
125 | M125 | 2023-08-01 | Helpdesk | Handbook & SOPs | Expression of First Call Resolution (FCR) as a percentage | Critical | Open |  |  |  | WIP
126 | M126 | 2023-08-01 | Helpdesk | Handbook & SOPs | Review of Agent Utilization Formula | Critical | open |  |  |  | CLOSURE REVIEW PENDING
127 | M127 | 2023-08-01 | Helpdesk | Handbook & SOPs | Customer-Specific SLA Flows | Critical | open |  | 11-Sep-25: Updated Document Shared 23-Aug-23 |  | CLOSURE REVIEW PENDING
128 | M128 | 2023-08-01 | Helpdesk | Handbook & SOPs | Exhaustive List of General Enquiries | Critical | open |  | 11--Sep-25: FAQ made available |  | CLOSURE REVIEW PENDING
129 | M129 | 2023-08-01 | Helpdesk | Handbook & SOPs | DoT KPIs Coverage in KPI Section | Critical | open |  | 11-Sep-25: Updated Document Shared 23-Aug-23 |  | CLOSURE REVIEW PENDING
130 | M130 | 2023-08-01 | Helpdesk | Handbook & SOPs | FAQs Based on Case Studies | Critical | open |  | 11-Sep-25: Updated Document Shared 23-Aug-23 |  | CLOSURE REVIEW PENDING
131 | M131 | 2023-08-01 | Helpdesk | Handbook & SOPs | Request to differentiate between registered users and registered numbers using examples. | Critical | Open |  | 11-Sep-25: BSS Integration to be completed |  | WIP
132 | M132 | 2023-08-01 | Helpdesk | Handbook & SOPs | the roles and responsibilities of NOC and Field Personnel be separate according to the RASCI matrix | Critical | open |  | 11-Sep-25: Updated Document Shared 23-Aug-23 |  | CLOSURE REVIEW PENDING
133 | M133 | 2023-08-01 | Helpdesk | Handbook & SOPs | Inclusion of Master and Child Service Level Agreement (SLA) monitoring; if any SLA is breached, a proper escalation matrix should be available for speedy escalation and resolution of the issue. | Critical | open |  | 11-Sep-25: Trianing completed |  | CLOSURE REVIEW PENDING
134 | M134 | 2023-08-01 | Helpdesk | Training | Training for Call Transferring | Critical | open |  | 11-Sep-25: Trianing completed |  | CLOSURE REVIEW PENDING
135 | M135 | 2023-08-01 | Helpdesk | User Experience | Proactive Intimation of Planned Downtime | Critical | open |  |  |  | CLOSURE REVIEW PENDING
170 | M170 | 2023-09-08 | Helpdesk | User Experience | Change in IVRS Welcome Message | Critical | open |  | 11-Sep-25: Changed and operational Now |  | CLOSURE REVIEW PENDING
171 | M171 | 2023-09-08 | Helpdesk | Resource Related | Other package involvement | Critical | open |  | 11-Sep-25: Clarified as its only L&T Manpower |  | CLOSURE REVIEW PENDING
174 | M174 | 2023-09-12 | Helpdesk | Improvement | Streamlining of Helpdesk and Ticketing system | Critical | open |  | 11-Sep-25: Same has been Submitted |  | CLOSURE REVIEW PENDING
320 | M320 | 2023-10-19 | Helpdesk | Demo | Assistant Director-P&E, T-Fiber asked L&T to submit the Helpdesk Compliance report along with a summary with respect to RFP by 23rd October’23 and the Demonstration on Helpdesk NEOX to be scheduled after the compliance report submission. | Critical | open |  | 11-Sep-25: Same has been Submitted |  | CLOSURE REVIEW PENDING
346 | M346 | 2023-11-17 | Helpdesk | Demo | Neox helpdesk Demo : | Critical | Open |  |  |  | WIP
347 | M347 | 2023-11-17 | Helpdesk | Compliance | Neox Compliance confirmation : | Critical | open |  | 11-Sep-25: Same has been Submitted |  | CLOSURE REVIEW PENDING
361 | M361 | 2023-11-17 | Helpdesk | Resource Related | Dimensioning of Helpdesk calls | Critical | open |  |  |  | CLOSURE REVIEW PENDING
449 | M449 | 2023-12-28 | Helpdesk | Training | Improve maturity of Helpdesk to handle incoming calls | Critical | Open |  |  |  | WIP
527 | M527 | 2024-01-24 | Helpdesk | Helpdesk | Obtain T-Fiber's review in the next two days and submit revised Helpdesk SOPs | Critical | open |  | 11-Sep-25: Same has been Submitted |  | CLOSURE REVIEW PENDING
533 | M533 | 2024-01-24 | Helpdesk | Design Features | Arrange Helpdesk toll-free (1800-XXX-XX) number | Critical | Open |  | 11-09-2025: Same as T366(472) Closed |  | COMPLETED & APPROVED | Yes | 2025-07-19 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\T366
534 | M534 | 2024-01-24 | Helpdesk | Design Features | Share finalized notification readiness of SMS, WhatsApp & Email formats for T-Fiber customers | Critical | Open |  |  |  | WIP
535 | M535 | 2024-01-24 | Helpdesk | Helpdesk | Arrange a demonstration of Helpdesk and IVR functions flow | Critical | open |  | 11-Sep-25: Complied, Part of Interim NOC KPI |  | CLOSURE REVIEW PENDING
576 | M576 | 2024-02-14 | Helpdesk | Helpdesk | Ensure helpdesk is ready by | Critical | Open |  |  |  | WIP
621 | M621 | 2023-07-04 | Helpdesk | Helpdesk | Evaluate the readiness of the current Helpdesk to start taking calls for GI and validate the sufficiency of the Helpdesk based on the fault rate, waiting time for each agent etc. by 15th July'23 | Critical | open |  |  |  | CLOSURE REVIEW PENDING
663 | M663 | 2023-07-05 | Helpdesk | Helpdesk | Take the performance measurement processes into consideration for measuring the performance of the identified Helpdesk resources. | Critical | Open |  |  |  | WIP
671 | M671 | 2023-07-05 | Helpdesk | Helpdesk | Make Helpdesk operational by 15th July ’23. | Critical | Open |  |  |  | WIP
713 | M713 | 2023-08-01 | Helpdesk | Launch Readiness | Complete Helpdesk integration with OSS and BSS. | Critical | Open |  |  |  | WIP
715 | M715 | 2023-08-01 | Helpdesk | Launch Readiness | Handle 150-160 calls per day in Helpdesk. | Critical | open |  |  |  | CLOSURE REVIEW PENDING
716 | M716 | 2023-08-01 | Helpdesk | Launch Readiness | Ensure that Helpdesk SLAs from the RFP are met. | Critical | open |  |  |  | CLOSURE REVIEW PENDING
718 | M718 | 2023-08-01 | Helpdesk | Launch Readiness | Make the number for reaching Helpdesk toll-free. | Critical | Open |  | 11-09-2025: Same as T366(472) Closed |  | COMPLETED & APPROVED | Yes | 2025-07-19 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\T366
721 | M721 | 2023-08-01 | Helpdesk | Launch Readiness | Specify features of Helpdesk not presently available for future deployment. | Critical | Open |  |  |  | WIP
722 | M722 | 2023-08-01 | Helpdesk | Launch Readiness | Training for Helpdesk users and managers for call center response and management. | Critical | open |  |  |  | CLOSURE REVIEW PENDING
723 | M723 | 2023-08-01 | Helpdesk | Launch Readiness | Set up a mechanism for non-technical call handling improvement. | Critical | open |  | 11-Sep-25: Established Business Helpdesk Setup at T Fiber office |  | CLOSURE REVIEW PENDING
724 | M724 | 2023-08-01 | Helpdesk | Launch Readiness | Get readiness of Helpdesk and Business to accept issues with order login. | Critical | open |  | 11-Sep-25: Established Business Helpdesk Setup at T Fiber office |  | CLOSURE REVIEW PENDING
725 | M725 | 2023-08-01 | Helpdesk | Launch Readiness | Determine how to handle calls originating from different packages given the shared Helpdesk agents. | Critical | open |  | 11-Sep-25: IVR Flows made ready Accordingly |  | CLOSURE REVIEW PENDING
726 | M726 | 2023-08-01 | Helpdesk | Launch Readiness | Problems with not supporting Telugu language in IVR and Helpdesk. | Critical | open |  | 11-Se-25: Now its in 3 Languages |  | CLOSURE REVIEW PENDING
727 | M727 | 2023-08-01 | Helpdesk | Launch Readiness | Unclear about support for integration with WhatsApp. | Critical | open |  | 11-Se-25:This Prouct Not Support |  | CLOSURE REVIEW PENDING
728 | M728 | 2023-08-01 | Helpdesk | Resource Augmentation | Confirm if the current load handled by Helpdesk is sufficient. | Critical | open |  | 11-Sep-25: Data Shared |  | CLOSURE REVIEW PENDING
729 | M729 | 2023-08-01 | Helpdesk | Launch Readiness | Concern over non-availability of Helpdesk Manager between 10 PM – 6 AM and how emergencies are handled during this time. | Critical | open |  |  |  | CLOSURE REVIEW PENDING
731 | M731 | 2023-08-01 | Helpdesk | Launch Readiness | Differentiate between registered users and registered numbers. | Critical | Open |  | 11-Sep-25: BSS Integration to be completed |  | WIP
732 | M732 | 2023-08-01 | Helpdesk | Launch Readiness | Resolve confusion over the categorisation of incoming queries. | Critical | open |  |  |  | CLOSURE REVIEW PENDING
733 | M733 | 2023-08-01 | Helpdesk |  | Check how the Call management system can support live intrusion of calls for instant feedback. | Critical | open |  | 11-Sep-25: Feature is available, Shall be demonstrated |  | CLOSURE REVIEW PENDING
734 | M734 | 2023-08-01 | Helpdesk |  | Define how readiness of Helpdesk to report on compliances and responsiveness and penalties calculation. | Critical | open |  |  |  | CLOSURE REVIEW PENDING
735 | M735 | 2023-08-04 | Helpdesk |  | Determine how the Helpdesk to NOC and Field is going to be integrated with the operational framework when they currently lack synergy. | Critical | open |  | 11-Sep-25: IVR Flows are aligned accordingly, Post Approval and Implementation we can meet expectations |  | CLOSURE REVIEW PENDING
736 | M736 | 2023-08-04 | Helpdesk |  | Concern over Toll-free levels availability for the Helpdesk. | Critical | Open |  |  |  | WIP
818 | M818 | 2023-09-26 | Helpdesk |  | Inclusion of Helpdesk and other missing items as per the RFP and solution in the Build. | Critical | Open |  |  |  | WIP
845 | M845 | 2023-11-17 | Helpdesk |  | Neox Helpdesk Demo: Scheduled for either 23rd or 24th November. | Critical | Open |  |  |  | WIP
846 | M846 | 2023-11-17 | Helpdesk |  | Neox Compliance Confirmation: Closed on 17th November. | Critical | open |  | 11-Sep-25 Same has been Submitted |  | CLOSURE REVIEW PENDING
847 | M847 | 2023-11-17 | Helpdesk |  | Reference for 24 Points: Praveen to share the reference of 24 points by 20th November. | Critical | open |  |  |  | CLOSURE REVIEW PENDING
929 | M929 | 2023-12-28 | Helpdesk |  | Address maturity of the Helpdesk; clarify integration aspects and ensure Helpdesk is ready to handle calls. | Critical | Open |  |  |  | WIP
1026 | M1026 | 2024-02-16 | Helpdesk | Training Module | Recruitment and training of billing officers | Critical | open |  | 11-Sep-25: its part of Business Helpdesk(T FIber) |  | CLOSURE REVIEW PENDING
1188 | M1188 | 2024-12-09 | Helpdesk |  | Helpdesk LLD/HLD to be discussed in detailed | Critical | Open |  |  |  | WIP
1270 | M1270 | 2025-02-14 | Helpdesk |  | Helpdesk IVR: after selecting any number (apart from configured 1/2/3), call is getting disconnected. This need to be corrected | Critical | open |  |  |  | CLOSURE REVIEW PENDING
298 | M298 | 2023-10-19 | IPMPLS | Service Solution | Point No. 186: IPTV to Household ,Point No. 190: CCTV Multicast ,Point No. 193: SDC content to Household and GI ,Point No. 194: Incremental Product/ Services finalization in T-Fiber network,Point No. 197: Service Provisioning PoC for SCCM/NSO - MVPN (all scenarios) ,Point No. 198: Simulation and testing network for parameters like network convergence etc & Point No. 344: CCTV Solution - solution to start PoC with DC connectivity at Cyberabad location as receiver and Sircilla NVR as source. To respond with relevant evidence on how the scope is contracted between L&T and its NOC OEMs, how L&T will implement the Network AT given the Launch date of 30th November ’23. | Critical | Open |  | All updated in 472 tracker 186, 190 - Closed 344 - CCTV PoC completed. 193 - Plan re-submitted on 12-Sep-25 198 - Pending, OEM dependancy 197 - NSO point | RS Rao Jayant M |  | 186, 190 - AD-UT(TFiber) | 2025-05-05 | T186 - \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\House Hold VoIP Services Design LLD V1.2 - t187.pdf T190 - \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\CCTV Multicast Solution LLD V1.2 - T190.pdf T344 -
59 | M59 | 2023-06-22 | Mobile Application | User Experience | Mobile App supported in Android & IOS | Critical | Open
399 | M399 | 2023-12-15 | Mobile Application | WFM Application | Arrange a demonstration of WFM Tool for field operations | Critical | Open
400 | M400 | 2023-12-15 | Mobile Application | WFM Application | Clarity on GPS tracking availability and battery consumption | Critical | Open
401 | M401 | 2023-12-15 | Mobile Application | WFM Application | Clarify on the frequency of field location polling | Critical | Open
402 | M402 | 2023-12-15 | Mobile Application | WFM Application | Clarify on photo upload feature and impact on mobile phone memory | NON-Critical | Open
403 | M403 | 2023-12-15 | Mobile Application | WFM Application | Clarity on offline data storage feature availability | NON-Critical | Open
404 | M404 | 2023-12-15 | Mobile Application | WFM Application | Clarity on file size limitations during upload | NON-Critical | Open
405 | M405 | 2023-12-15 | Mobile Application | WFM Application | . | NON-Critical | Open
406 | M406 | 2023-12-15 | Mobile Application | WFM Application | Clarify the usage differences between GIS and WFM mobile apps | NON-Critical | Open
407 | M407 | 2023-12-15 | Mobile Application | WFM Application | Request for NDA between L&T and M/S Lepton and details on API security | NON-Critical | Open
408 | M408 | 2023-12-15 | Mobile Application | WFM Application | Explain how Geo-fencing will work for fiber route allocations | Critical | Open
409 | M409 | 2023-12-15 | Mobile Application | WFM Application | Request to start manual ticket allocation process | Critical | Open
410 | M410 | 2023-12-15 | Mobile Application | WFM Application | Request to freeze the process for node and link ticket allocation | NON-Critical | Open
411 | M411 | 2023-12-15 | Mobile Application | WFM Application | Use of document forms from the Operations Handbook by the WFM app | Critical | Open
412 | M412 | 2023-12-15 | Mobile Application | WFM Application | Request for Summary Dashboards/Management Reports for task management and progress tracking | Critical | Open
413 | M413 | 2023-12-19 | Mobile Application | WFM Application | Arrange a demonstration of WFM Tool for field operations | Critical | Open
1 | M1 | 2023-02-06 | NOC Operationalization | Dashboards | Submit a fortnightly report (Kanban chart) for monitoring all activities in TNOC, including OSS, BSS, NSO, etc. | Critical | Open | OSS Dashboards
2 | M2 | 2023-02-06 | NOC Operationalization | Handbook & SOPs | T-Fiber requested the inclusion of Protocol Manager and Regulatory roles in the TNOC organization chart. Also, emphasized clear demarcation and mapping of resources with names, roles, and responsibilities | Critical | Completed | OSS Dashboards | NOC resources details is shared on weekly basis. Roles of NOC is as per RFP.
3 | M3 | 2023-03-27 | NOC Operationalization | Full NOC Readiness | Present a plan on how digital processes and tools will be used for GI connectivity provisioning, customer acceptance, and O&M functions | Critical | Open | OSS Dashboards
6 | M6 | 2023-03-27 | NOC Operationalization | Handbook & SOPs | Clear accountability and responsibility of SMEs, along with an presented RASCI matrix | Critical | Completed | NSO | Domain wise NOC L3 role exists at NOC
7 | M7 | 2023-04-03 | NOC Operationalization | Full NOC Readiness | Request for submission of Test Reports, outcomes, and documentation on a common server for continuous testing and monitoring. (Shared Folder) | Critical | Completed | OSS Dashboards | NOC KPIs, reports, forms are available in shared folder
8 | M8 | 2023-04-03 | NOC Operationalization | Full NOC Readiness | All Test Plans to be submitted to TPA in coordination with Package B&C; reviewed by Assistant Director Technical, T-Fiber. | Critical | Open | OSS Dashboards
9 | M9 | 2023-04-03 | NOC Operationalization | Full NOC Readiness | Demonstration of Depository Module | Critical | Open | Helpdesk
13 | M13 | 2023-04-03 | NOC Operationalization | Functional AT Plan | Quality test report submission for DWDM & IPMPLS each zonal path. | Critical | Open | OSS Dashboards
15 | M15 | 2023-04-16 | NOC Operationalization | Full NOC Readiness | Secretary, DoT advised to show more KPIs, Video wall extension is required | Critical | Open | OSS Dashboards
60 | M60 | 2023-06-28 | NOC Operationalization | Handbook & SOPs | Classification of Procedures and processes from ITIL and eTOM | Critical | Open
61 | M61 | 2023-06-28 | NOC Operationalization | Resource Related | L&T with ITIL or eTOM certifications | Critical | Open
62 | M62 | 2023-06-28 | NOC Operationalization | Handbook & SOPs | All KPIs details submission | Critical | Completed |  | NOC KPI report for submitted and signed for Oct24 to Dec24. Jan to March25 KPI submitted but sign oending with TFiber
63 | M63 | 2023-06-28 | NOC Operationalization | Handbook & SOPs | The difference between problem and issue management. | Critical | Open
64 | M64 | 2023-06-28 | NOC Operationalization | Handbook & SOPs | Establish a configuration management system to monitor all changes in NOC operations | Critical | Completed |  | Planned event process in place. Planned changes discussed with Tfiber NOC team, post approval CR is raised for approval
65 | M65 | 2023-06-28 | NOC Operationalization | Handbook & SOPs | Create an archival policy for documentation storage, including retrieval systems, access matrix, and policies | Critical | Open
66 | M66 | 2023-06-28 | NOC Operationalization | Handbook & SOPs | Define categories of problems along with a resolution approach plan | Critical | Open
67 | M67 | 2023-06-28 | NOC Operationalization | Handbook & SOPs | Adopt a continuous improvement framework such as DMAIC and Kaizen for process improvement | Critical | Open
68 | M68 | 2023-07-04 | NOC Operationalization | Handbook & SOPs | RASCI & Escalation Matrix in NOC Operational Framework | Critical | Closed |  | OEM, vendor , Field/NOC escalation matrix available. This is a point in 472 tracker as well and this point is approved by TFiber
69 | M69 | 2023-07-04 | NOC Operationalization | Handbook & SOPs | clear definition of roles and responsibilities related to L1, L2 & L3 with number of resources which should be according to the fault rates. | Critical | Completed |  | NOC manpower report is shared on weekly basis. Manpower is as per RFP count. KRA is also submitted for L1/L2/L3 roles
70 | M70 | 2023-07-04 | NOC Operationalization | Audit | Checklist for issue handling and first level troubleshooting | Critical | Completed |  | Checklist available with Helpdesk
71 | M71 | 2023-07-04 | NOC Operationalization | Audit | Latency/Jitter & Backbone packet loss SLAs | Critical | Completed |  | Report & SLA compliance is shared on monhtly basis
72 | M72 | 2023-07-04 | NOC Operationalization | Handbook & SOPs | service management of configuration | Critical | Open
172 | M172 | 2023-09-12 | NOC Operationalization | Handbook & SOPs | SOPs Submission | Critical | Closed |  | Agreed SOPs are submitted and agreed with TFiber
175 | M175 | 2023-09-12 | NOC Operationalization | Dashboards | Dashboards for each element of the Video Wall, specifying manual or automatic clarity | Critical | Completed |  | Curently Video wall is displaying dashboards as per agreement with TFiber
176 | M176 | 2023-09-12 | NOC Operationalization | Resource Related | T-NOC Resource details and deployment with Roles and Responsibilities | Critical | Completed |  | TNOC resource is deployed as per RFP. Manpower report is shared on weekly basis.
178 | M178 | 2023-09-12 | NOC Operationalization | Dashboards | SLA Monitoring and Network Performance Statistics | Critical | Open
179 | M179 | 2023-09-12 | NOC Operationalization | O&M Strategy | Spares Management | Critical | Open
180 | M180 | 2023-09-12 | NOC Operationalization | O&M Strategy | Repair and Replacement process | Critical | Completed |  | Have agreement with OEMs for R&R and SLA defined
184 | M184 | 2023-09-22 | NOC Operationalization | O&M Strategy | Redundancy Plan for NSO and OSS | Critical | Open
185 | M185 | 2023-09-22 | NOC Operationalization | O&M Strategy | Limitations in OSS and NSO Scalability for post go live | Critical | Open
240 | M240 | 2023-09-26 | NOC Operationalization | Handbook & SOPs | Provide clarification on the status of HOTO (Handover to Operations) and Knowledge Transfer. | Critical | Open
241 | M241 | 2023-09-26 | NOC Operationalization | Functional AT Plan | Systems functional Acceptance Tests Plan yet | Critical | Completed |  | FAT documents shared, Tracker & updates are sent on periodic basis
242 | M242 | 2023-09-26 | NOC Operationalization | Full NOC Readiness | Launch Road Map | Critical | Completed |  | 12 NOC points, 472 Tracker is being tracked with timelines and updates / reiew happening on regular basis
244 | M244 | 2023-09-26 | NOC Operationalization | Full NOC Readiness | Provide assurance that comprehensive solutions and designs will be within the specified list, considering anything beyond as a change request. | Critical | Open
248 | M248 | 2023-09-26 | NOC Operationalization | Full NOC Readiness | Consider RFP, technical bid, and solutions for understanding the requirements of a staging system after go-live. | Critical | Open
249 | M249 | 2023-09-26 | NOC Operationalization | OEM's Details | Provide all OEMs' test cases & certificates for T-Fiber network testing | Critical | Open
250 | M250 | 2023-10-11 | NOC Operationalization | Full NOC Readiness | Full NOC to be ready by 10th Nov'23 | Critical | Open |  | NOC Go-Live plan is shared
289 | M289 | 2023-10-19 | NOC Operationalization | Interim NOC | Provide a list of points that need to be available for the Network Launch targeted for November 30th, 2023. Identify the points that will be included in the roadmap and specify the timelines for their implementation | Critical | Completed |  | 12 NOC points, 472 Tracker is being tracked with timelines and updates / reiew happening on regular basis
290 | M290 | 2023-10-19 | NOC Operationalization | Interim NOC | explain their approach for handling Operations and Maintenance (O&M) to meet the SLAs (Service Level Agreements) and provide process documents for features that are currently unavailable. | Critical | Open |  | SOPs are agreed with TFiber. Interim NOC KPIs were met for Oct24 to Dec24 which is signed by TFiber also
291 | M291 | 2023-10-19 | NOC Operationalization | Interim NOC | To clarify how they plan to transition the O&M responsibilities and data once the currently unavailable features are made available. | Critical | Open
292 | M292 | 2023-10-19 | NOC Operationalization | Interim NOC | Evidence from L&T on the timelines for fulfilling the feature gaps | Critical | Open
348 | M348 | 2023-11-17 | NOC Operationalization | Action Points | 370 points out of which 24 points which are already covered in 370 : Praveen to share indicating the reference of 24 points by | Critical | Closed |  | 472 point tracker is being tracked, approvals is being taken for done cases, and updates are sent/discussed with TFiber
349 | M349 | 2023-11-17 | NOC Operationalization | Action Points | 196 points closure along with artefacts : | Critical | Closed |  | Mail approvals recieved for approved cases from TFiber
350 | M350 | 2023-11-17 | NOC Operationalization | Documentation | Revised Organization structure : | Critical | Completed |  | NOC structure and manpower details shared
352 | M352 | 2023-11-17 | NOC Operationalization | Documentation | Artefacts storage link : | Critical | Completed |  | 472 points arte-facts links are being shared while taking approvals
354 | M354 | 2023-11-17 | NOC Operationalization | Resource Related | HP & Cisco OEM teams onboarding from 20th November'23. | Critical | Closed |  | OEM are onboarded
355 | M355 | 2023-11-17 | NOC Operationalization | Documentation | Letter from all OEMs apart from Cisco & HP to be submitted by 22nd November'23 | Critical | Open
356 | M356 | 2023-11-17 | NOC Operationalization | Documentation | Letter from from Cisco & HP to be submitted by 24th November'23 | Critical | Open
357 | M357 | 2023-11-17 | NOC Operationalization | Documentation | Letter of confirmation for closure of issues with Tejas & Nokia on or before 30th November’23 | Critical | Open
358 | M358 | 2023-11-17 | NOC Operationalization | Meeting | Date for All OEMs Meeting | Critical | Open
360 | M360 | 2023-11-17 | NOC Operationalization | Documentation | Revert pending on 8 Notes(Undertaking) | Critical | Open
362 | M362 | 2023-11-17 | NOC Operationalization | Documentation | Revert on 26 SOPS & O&M Handbook | Critical | Open
363 | M363 | 2023-11-17 | NOC Operationalization | Documentation | Measurable KPI for individual TNOC team | Critical | Completed |  | NOC role KRA and KPI submitted to TFiber
364 | M364 | 2023-11-17 | NOC Operationalization | Resource Related | Service delivery & Service assurance Manager | Critical | Completed |  | Not part of RFP. Service Provisioning is being done by NOC team
365 | M365 | 2023-11-17 | NOC Operationalization | Resource Related | Plan for Manpower augmentation to handle Infra Alarm in TNOC & field to finalize O&M | Critical | Completed |  | NOC manpower is deputed as per RFP and manpower report is shared with TFiber on weekly basis
367 | M367 | 2023-11-17 | NOC Operationalization | Resource Related | Additional resources for fast tracking of project | Critical | Open
368 | M368 | 2023-11-28 | NOC Operationalization | Meeting | L&T to communicate with OEMs and arrange a meeting on behalf of T-Fiber. 1. To seek evidence from L&T on the commitment from respective OEMs of BSS, OSS, NSO, GIS, GPON on closure of gaps identified so far, related to the operationalization of various systems along with firm dates for delivery from respective OEMs for the same. 2. L&T to provide a plan on how the NOC O&M will be handled with SOPs where relevant in the interim period. 3. How L&T transitions the systems from the interim to the final state without any business impact while ensuring data integrity. | Critical | Open
370 | M370 | 2023-11-28 | NOC Operationalization | Demo | L&T to prepare and execute the next DRY run effectively. | Critical | Open
371 | M371 | 2023-11-28 | NOC Operationalization | Documentation | L&T to develop a comprehensive presentation on product readiness and NOC operationalization schedule. | Critical | Completed |  | 12 NOC point covers timelines for NOC readiness
451 | M451 | 2023-12-28 | NOC Operationalization | Action Points | Cover all requirements from workshops, RFP, and discussions in the roadmap | Critical | Open
452 | M452 | 2023-12-28 | NOC Operationalization | Action Points | Generate SLA reports automatically from NOC | Critical | Open
453 | M453 | 2023-12-28 | NOC Operationalization | Action Points | Submit a Roadmap covering all requirements raised in all Workshops, the RFP requirements, the 396-point Worksheet maintained by L&T, and all the discussions | Critical | Open |  | Points are covered in 472 points tracker, 12 NOC points, and in HLD/LLD/FAT documents
454 | M454 | 2023-12-28 | NOC Operationalization | Action Points | Explore templates from BBNL NOC for invoice settlement | Critical | Open
456 | M456 | 2023-12-28 | NOC Operationalization | Action Points | Deliver NOC before the end of T3 | Critical | Open
469 | M469 | 2024-01-04 | NOC Operationalization | O&M Strategy | Achieve readiness of all 'T0' NOC functions | Critical | Open
470 | M470 | 2024-01-04 | NOC Operationalization | O&M Strategy | Submit details of remaining services of T3 & T4 | Critical | Open
471 | M471 | 2024-01-04 | NOC Operationalization | O&M Strategy | Start daily meetings and share progress updates | Critical | Open
524 | M524 | 2024-01-24 | NOC Operationalization | Design & Documentation | Provide final timeline for all conditional approvals & workshop tracker and detailed scope document | Critical | Open
526 | M526 | 2024-01-24 | NOC Operationalization | Design & Documentation | Share detailed scope document and conditional approvals & workshops tracker | Critical | Open
528 | M528 | 2024-01-24 | NOC Operationalization | O&M Strategy | Discuss and revert all pending points with MD(I/C), T-Fiber, and T-Fiber Operations Team | Critical | Open
577 | M577 | 2024-02-14 | NOC Operationalization | O&M Strategy | Provide daily updates on the progress made in NOC by | Critical | Open
578 | M578 | 2024-02-14 | NOC Operationalization | O&M Strategy | Resolve all issues | Critical | Open
579 | M579 | 2024-02-14 | NOC Operationalization | O&M Strategy | Establish two distinct setup—one for live operations, another for pre-production | Critical | Completed |  | In place
580 | M580 | 2024-02-14 | NOC Operationalization | O&M Strategy | Share all related details for pre-production setup to Director-NOC, T-Fiber | Critical | Completed |  | Pre production setup is in place at NOC
611 | M611 | 2023-07-04 | NOC Operationalization | Operational Handbook | Incorporate changes into the proposed operational framework as per T-Fiber's review, including adding a Vision and Mission statement, identifying additional relevant processes, updating the organisation structure, and correcting inconsistencies in the documentation of processes. | Critical | Open
612 | M612 | 2023-07-04 | NOC Operationalization | Operational Handbook | Detail flow charts of the processes into SOPs. | Critical | Open
614 | M614 | 2023-07-04 | NOC Operationalization | O&M Strategy | Revert on the segregation of current, interim, and final organisation structure along with the timelines in which these should be applicable. | Critical | Open
615 | M615 | 2023-07-04 | NOC Operationalization | Hiddencove suggestions | Include the processes recommended by the external auditor (Hiddencove) such as Handover deployment to Operation process, Service Request Process, Configuration Management, Asset Management, Critical Event Management, Site Access Management, Handover Deployment to Operations Process (Transition Process). | Critical | Open
616 | M616 | 2023-07-04 | NOC Operationalization | O&M Strategy | Include a Continuous Improvement framework covering the process of identification/initiation of the areas for continuous improvement on a regular basis. Standard frameworks like KAIZEN Or PDCA are suggested. | Critical | Open
617 | M617 | 2023-07-04 | NOC Operationalization | Escalation Matrix | Include aspects like document processes, RASCI & Escalation Matrix in NOC Operational Framework. | Critical | Open
618 | M618 | 2023-07-04 | NOC Operationalization | O&M Strategy | Highlight the processes that will be implemented and ready by 15th August ’23 and provide a roadmap of which module will be ready by when. | Critical | Open
619 | M619 | 2023-07-04 | NOC Operationalization | Escalation Matrix | Define clear roles and responsibilities related to L1, L2 & L3 with an appropriate number of resources which should be according to the fault rates. | Critical | Open
620 | M620 | 2023-07-04 | NOC Operationalization | GIS | Ensure the coverage of GIS operations as part of a single integrated picture of NOC, Field including handovers to/from Field and NOC. | Critical | Open
622 | M622 | 2023-07-04 | NOC Operationalization | O&M Strategy | Submission of the proposed TNOC Operational Framework document on 9th July ’23 for review. | Critical | Open
623 | M623 | 2023-07-04 | NOC Operationalization | O&M Strategy | Next review on Operational Framework by 11th July ’23. | Critical | Open
624 | M624 | 2023-07-04 | NOC Operationalization | O&M Strategy | Develop a process and framework for order fulfillment, ensuring that all applications and tools are ready for production. | Critical | Open
625 | M625 | 2023-07-04 | NOC Operationalization | O&M Strategy | Prepare a more comprehensive plan for product catalog and infrastructure management and maintenance. | Critical | Open
626 | M626 | 2023-07-04 | NOC Operationalization | O&M Strategy | Develop a comprehensive plan for improving network service management and address any issues related to MPLS-related resources. | Critical | Open
627 | M627 | 2023-07-04 | NOC Operationalization | Dry Run | Schedule the first dry run for the NOC Operationalization for 24th July '23. | Critical | Open
629 | M629 | 2023-07-04 | NOC Operationalization |  | The Tools Assigned the Operation to be ready and deployed by 9th July '23. | Critical | Open
630 | M630 | 2023-07-04 | NOC Operationalization |  | HLD & LLD Approval: L&T to expedite closure of pending points with daily discussions, aiming for 6th April '23. | NON-Critical | Open
638 | M638 | 2023-07-04 | NOC Operationalization | Resource Augmentation | IPMPLS SME Resignation: L&T to address the resignation and retention of the IPMPLS SME. | Critical | Open
639 | M639 | 2023-07-04 | NOC Operationalization | Communication Matrix | Project SPOC: Mr. Anthony from L&T to coordinate across all domains to deliver the project. | Critical | Open
640 | M640 | 2023-07-04 | NOC Operationalization | Service Solution | T-NOC Operationalisation Plan: L&T to present a phased plan on 27th March '23 for minimal readiness by 5th April, stage 2 by 20th April, and stage 3 by 30th April, with the entire T-NOC operational by 30th April and launch by 15th May '23. | Critical | Open
641 | M641 | 2023-07-04 | NOC Operationalization | Resource Augmentation | Resource Deployment for District Delivery: L&T to ramp up resources to meet the delivery target of five and a half districts by 7th April '23. | Critical | Open
646 | M646 | 2023-07-05 | NOC Operationalization |  | Develop and present a comprehensive proposal for improving the appearance of T-NOC. | Critical | Open
649 | M649 | 2023-07-05 | NOC Operationalization | Operational Framework | Identify and rectify inconsistencies in the document processes presented in the NOC's Operational Framework. | Critical | Open
653 | M653 | 2023-07-05 | NOC Operationalization | Full NOC Readiness | Highlight the processes that will be implemented and ready by 15th August ’23 and provide a roadmap of which module will be ready by when during the meeting on 4th July'23. | Critical | Open
657 | M657 | 2023-07-05 | NOC Operationalization | Operational Framework | Ensure that all references to processes from ITIL and eTOM are clearly explained and utilized in the operational framework. | Critical | Open
658 | M658 | 2023-07-05 | NOC Operationalization | Escalation Matrix | Implement a robust RASCI & Escalation Matrix in the NOC Operational Framework. | Critical | Open
666 | M666 | 2023-07-05 | NOC Operationalization | Daily Meetings | Officially commence up the daily stand-up call on 16th June ’23, with the call to be held routinely from this date. | Critical | Open
668 | M668 | 2023-07-05 | NOC Operationalization | Operational Framework | Review of the Operational Framework by 11th July ’23. | Critical | Open
705 | M705 | 2023-07-26 | NOC Operationalization | Launch Readiness | Assessment and redistribution of support because of the launch date approaching on 15th August. | Critical | Open
730 | M730 | 2023-08-01 | NOC Operationalization | Launch Readiness | The relationship between people and functions as realised by RASCI matrix needs improvement. | Critical | Open
758 | M758 | 2023-08-23 | NOC Operationalization |  | Fixing issues with OSS - BSS integration. | Critical | Open
769 | M769 | 2023-08-31 | NOC Operationalization |  | L&T to review NOC readiness and demonstrate service excellence for launch; separate meeting for 360 View presentation on 31st August '23. | Critical | Open
770 | M770 | 2023-08-31 | NOC Operationalization | Launch Readiness | Implement IST in SCCM and confirm BSS readiness for live customers like Airtel by 31st August '23. | Critical | Open
771 | M771 | 2023-08-31 | NOC Operationalization | NOC Operationalization | Data cleanup before Airtel onboarding and present GI migration approach from trial to production. | Critical | Open
776 | M776 | 2023-09-08 | NOC Operationalization | Launch Readiness | Completion of Pause-Mechanism and QOS Visibility part of the committed deliverables. | Critical | Open
777 | M777 | 2023-09-08 | NOC Operationalization | Launch Readiness | Reviewing readiness for launch, readiness of O&M Approach, and readiness of NOC from a multiple perspectives. | Critical | Open
778 | M778 | 2023-09-08 | NOC Operationalization |  | Submissio of module wise Functional Acceptance Test Plan. | Critical | Open
779 | M779 | 2023-09-08 | NOC Operationalization | Launch Readiness | Implementation and readiness in order for Interim Launch from NOC to field level. | Critical | Open
780 | M780 | 2023-09-08 | NOC Operationalization |  | Establishing a security system including hardware, IT Infra, and Applications security certifications. | Critical | Open
781 | M781 | 2023-09-08 | NOC Operationalization |  | Submit report capturing the number of test cases and their status. | Critical | Open
782 | M782 | 2023-09-08 | NOC Operationalization | Launch Readiness | Include more sample sites in the 2nd Dry Run by the end of September' 23. | Critical | Open
783 | M783 | 2023-09-08 | NOC Operationalization | Launch Readiness | Review and finalize the process design related to Service Delivery linked to manpower. | Critical | Open
784 | M784 | 2023-09-08 | NOC Operationalization |  | Revise LLD for DWDM. | NON-Critical | Open
786 | M786 | 2023-09-08 | NOC Operationalization | Launch Readiness | The readiness of E2E NOC will be reviewed and updated by 8th Sep ‘23. | Critical | Open
787 | M787 | 2023-09-08 | NOC Operationalization | Launch Readiness | The status of pending deliverables that were committed for delivery by 15th August ’23 has not been mentioned to have been met by specific dates. | Critical | Open
788 | M788 | 2023-09-08 | NOC Operationalization | Launch Readiness | T-NOC Readiness Confirmation: EVP, T-Fiber requested confirmation on launch deliverables and interim launch processes by EOD 8th September '23. | Critical | Open
789 | M789 | 2023-09-08 | NOC Operationalization |  | Review of Pending Activities: Director-P&E, T-Fiber to review and update the status of 92 pending activities related to the 15th August '23 deliverables. | Critical | Open
790 | M790 | 2023-09-08 | NOC Operationalization |  | Revised LLD for DWDM: Technical Head, L&T submitted the revised LLD for approval. | NON-Critical | Open
801 | M801 | 2023-09-22 | NOC Operationalization | Launch Readiness | Overcoming technical issues hampering the setup for the 1st Dry Run. | Critical | Open
802 | M802 | 2023-09-22 | NOC Operationalization | Launch Readiness | Reviewing the setup for 1st Dry Run observed by the EVP, T-Fiber. | Critical | Open
803 | M803 | 2023-09-22 | NOC Operationalization | Launch Readiness | Gaining clarity on roles and functionalities of NSO and OSS. | Critical | Open
806 | M806 | 2023-09-22 | NOC Operationalization |  | L&T to identify provisioning/monitoring features limited because of interoperability issues in a multi-vendor eco-system. | Critical | Open
807 | M807 | 2023-09-22 | NOC Operationalization |  | L&T to articulate how NSO and OSS are complementing each other and their roles in service provisioning. | Critical | Open
808 | M808 | 2023-09-22 | NOC Operationalization |  | L&T to provide the redundancy plan if entire DC were to go down and the backup measures if NSO were to fail. | Critical | Open
809 | M809 | 2023-09-22 | NOC Operationalization |  | L&T to work towards a system that is foolproof, automated, futuristic, and provides seamless service experience for end users. | Critical | Open
810 | M810 | 2023-09-22 | NOC Operationalization | Dry Run | L&T to propose the date for the 2nd Dry Run inclusive of Internet Leased Line, P2P, and P2MP flavors of service. | Critical | Open
811 | M811 | 2023-09-22 | NOC Operationalization | Dry Run | L&T to confirm target date for E2E BSS Demo. | Critical | Open
812 | M812 | 2023-09-22 | NOC Operationalization | Dry Run | L&T to consider the creation of a template for tracking observations. | Critical | Open
813 | M813 | 2023-09-22 | NOC Operationalization | NSO | Provision of training for L&T pool of resources in NSO and development of NEDs. | Critical | Open
814 | M814 | 2023-09-22 | NOC Operationalization |  | L&T to create a timetable displaying the percentage of progress on activities week-wise and fortnight-wise. | Critical | Open
815 | M815 | 2023-09-22 | NOC Operationalization |  | L&T to confirm the features ready for showcase in the E2E Demo by 25th September’23. | Critical | Open
816 | M816 | 2023-09-22 | NOC Operationalization |  | Target the 2nd Dry Run on 30th September ’23 with more ONTs, covering GI BB, Point to point, dedicated ILL & Dark fiber by end of L&T. | Critical | Open
852 | M852 | 2023-12-12 | NOC Operationalization |  | Submit updated Acceptable Usage Policy | Critical | Open
888 | M888 | 2023-12-15 | NOC Operationalization | Operational Handbook | Operations Handbook: L&T to share document forms from the Operations Handbook to be used by the WFM app. | Critical | Open
905 | M905 | 2023-12-19 | NOC Operationalization | Launch Readiness | T-Cell, T-VPN, and GI-ILL Completion: SVP, T-Fiber called for these to be completed on priority before the visit by Hon’ Minister. | Critical | Open
914 | M914 | 2023-12-19 | NOC Operationalization |  | The necessity for STL to complete T-NOC Operationalization by 6th April 2023 to begin commercialization. | Critical | Open
917 | M917 | 2023-12-19 | NOC Operationalization |  | The presentation of a comprehensive T-NOC operationalisation plan by STL, with clear phases and readiness stages. | Critical | Open
919 | M919 | 2023-12-28 | NOC Operationalization | Launch Readiness | Achieve T-VPN and T-DILL completion by 31st Jan '24; confirm Dark Fiber P2P link target date later. | Critical | Open
920 | M920 | 2023-12-28 | NOC Operationalization | Launch Readiness | Ensure basic products are available by end of April '24; complete all 28 products within 2 months beyond April '24. | Critical | Open
925 | M925 | 2023-12-28 | NOC Operationalization | Launch Readiness | Conduct Dry Run for 3 Products (GI-BB, T-CELL, Dark Fiber) on 5th January '24 with BSS & WFM; share date soon. | Critical | Open
926 | M926 | 2023-12-28 | NOC Operationalization | Communication Matrix | Initiate daily meetings with T-Fiber; share progress updates daily. | Critical | Open
927 | M927 | 2023-12-28 | NOC Operationalization | O&M Related | Start daily uptime report immediately; resolve duplicate TroubleTicket issue within the week. | Critical | Open
930 | M930 | 2023-12-28 | NOC Operationalization | Launch Readiness | Cover all requirements in the roadmap with completion dates; explore standard templates for SLA reports to settle invoices with BBNL. | Critical | Open
931 | M931 | 2023-12-28 | NOC Operationalization | O&M Related | Provide clarity on Alarm Correlation, cross-domain RCA, SIA, Helpdesk design, Network and Service Topology. | Critical | Open
932 | M932 | 2023-12-28 | NOC Operationalization | Launch Readiness | Deliver NOC before the end of T3 as mandated by EVP, T-Fiber. | Critical | Open
953 | M953 | 2024-01-24 | NOC Operationalization |  | NOC Readiness Review | Critical | Open
954 | M954 | 2024-01-24 | NOC Operationalization |  | Ensure full delivery of NOC including field O&M and basic six products | Critical | Open
955 | M955 | 2024-01-24 | NOC Operationalization |  | Confirm readiness of all NOC modules including ticketing, Helpdesk and WFM | Critical | Open
956 | M956 | 2024-01-24 | NOC Operationalization |  | Deliver service inventory module | Critical | Open
957 | M957 | 2024-01-24 | NOC Operationalization |  | Create a tracker sheet for conditional approvals and workshop points | Critical | Open
958 | M958 | 2024-01-24 | NOC Operationalization |  | Submit detailed plan for module-wise readiness | Critical | Open
959 | M959 | 2024-01-24 | NOC Operationalization |  | Present documentation for automation of 6 products | Critical | Open
960 | M960 | 2024-01-24 | NOC Operationalization |  | Submit package for NOC readiness, roadmaps, and sheets | Critical | Open
961 | M961 | 2024-01-24 | NOC Operationalization |  | Engage OEMs till end-to-end stabilization of services | Critical | Open
962 | M962 | 2024-01-24 | NOC Operationalization |  | Discuss pending points and close the final scope with T-Fiber | Critical | Open
963 | M963 | 2024-01-24 | NOC Operationalization |  | Share a business continuity plan for 6 manual to automated product transitions | Critical | Open
964 | M964 | 2024-01-24 | NOC Operationalization |  | Present NOC pre-production testing and environment plan | Critical | Open
965 | M965 | 2024-01-24 | NOC Operationalization |  | Confirm list of BSS operation team members | Critical | Open
966 | M966 | 2024-01-24 | NOC Operationalization |  | Update the GIS data and confirm its operation SOP | Critical | Open
967 | M967 | 2024-01-24 | NOC Operationalization |  | Deploy senior resource for managing T-Fiber helpdesk | Critical | Open
968 | M968 | 2024-01-24 | NOC Operationalization |  | Separate helpdesk and call center desk with transition plan | Critical | Open
969 | M969 | 2024-01-24 | NOC Operationalization |  | Arrange toll-free number and update on notification formats readiness | Critical | Open
970 | M970 | 2024-01-24 | NOC Operationalization |  | Integrate WhatsApp for customer communication through calls with IVR | Critical | Open
971 | M971 | 2024-01-24 | NOC Operationalization |  | Provide updates on NOC progress and ensure commitment dates are met | Critical | Open
972 | M972 | 2024-01-24 | NOC Operationalization |  | Deploy stable standard product for IPDR | Critical | Open
973 | M973 | 2024-01-24 | NOC Operationalization |  | Ensure pre-scheduled meetings occur without SMEs absence | Critical | Open
974 | M974 | 2024-01-24 | NOC Operationalization |  | Prepare NOC for review by the State IT&EC Minister and PS-ITE&C | Critical | Open
975 | M975 | 2024-01-24 | NOC Operationalization |  | Project Review with 3 MSIs | Critical | Open
976 | M976 | 2024-01-24 | NOC Operationalization |  | Resource mobilization and network availability | Critical | Open
977 | M977 | 2024-01-24 | NOC Operationalization |  | Adoption of WFM by packages B & C | Critical | Open
978 | M978 | 2024-01-24 | NOC Operationalization |  | Implementation of Mandal rings of NoFN PH-1 | NON-Critical | Open
979 | M979 | 2024-01-24 | NOC Operationalization |  | Restoration of social welfare and tribal welfare schools to service | Critical | Open
980 | M980 | 2024-01-24 | NOC Operationalization |  | Complete all GI connectivity before March '24 | Critical | Open
981 | M981 | 2024-01-24 | NOC Operationalization |  | Focus on top 4 network readiness priorities | Critical | Open
982 | M982 | 2024-01-25 | NOC Operationalization |  | WFM Patrolling App Demo | Critical | Open
983 | M983 | 2024-01-25 | NOC Operationalization |  | Complete WFM-OSS integration | Critical | Open
984 | M984 | 2024-01-25 | NOC Operationalization |  | Submit solution document for PoP RFS | Critical | Open
985 | M985 | 2024-01-25 | NOC Operationalization |  | Explore WFM integration with BSS | Critical | Open
986 | M986 | 2024-01-25 | NOC Operationalization |  | Complete Fault Management and Trouble Ticketing | Critical | Open
987 | M987 | 2024-01-25 | NOC Operationalization |  | Clarify GIS vs WFM mobile app usage | Critical | Open
988 | M988 | 2024-01-25 | NOC Operationalization |  | Provide NDA with M/S Lepton | Critical | Open
989 | M989 | 2024-01-25 | NOC Operationalization |  | Ensure API security measures | Critical | Open
990 | M990 | 2024-01-25 | NOC Operationalization |  | Submit sample dashboards/reports | Critical | Open
991 | M991 | 2024-01-25 | NOC Operationalization |  | Provide Operations Handbook document forms | Critical | Open
992 | M992 | 2024-01-25 | NOC Operationalization |  | Clarify attendance watermarking feature | Critical | Open
993 | M993 | 2024-01-25 | NOC Operationalization |  | Schedule weekly training for patrollers | Critical | Open
994 | M994 | 2024-01-25 | NOC Operationalization |  | Update on previous MoM action items | Critical | Open
996 | M996 | 2024-01-25 | NOC Operationalization |  | Operationalize ready features of WFM tool | Critical | Open
1012 | M1012 | 2024-02-13 | NOC Operationalization |  | Status of asset management automation | Critical | Open
1034 | M1034 | 2024-03-14 | NOC Operationalization | Launch Readiness | Assessing the progress achieved after the Governance meeting held on March 5, 2024. | Critical | Open
1036 | M1036 | 2024-03-14 | NOC Operationalization | Launch Readiness | Achieving operationalization and readiness of T-NOC. | Critical | Open
1037 | M1037 | 2024-03-14 | NOC Operationalization | Launch Readiness | Addressing product gaps and OEM execution delays for the readiness of 5 products. | Critical | Open
1043 | M1043 | 2024-03-14 | NOC Operationalization | Launch Readiness | L&T to address the delays in demonstrating the End-to-End of the Dark Fiber product. | Critical | Open
1044 | M1044 | 2024-03-14 | NOC Operationalization | NOC Readiness | L&T to complete 423 critical points and provide a summary of the status along with action required for balance points. | Critical | Open
1045 | M1045 | 2024-03-14 | NOC Operationalization | NOC Readiness | L&T to ensure understanding of the interim T-NOC operationalization plan and work towards readiness. | Critical | Open
1047 | M1047 | 2024-03-14 | NOC Operationalization | NOC Readiness | L&T to provide updates and clarifications on the payment gateway, ticket functionalities, and NSO readiness. | Critical | Open
1050 | M1050 | 2024-03-14 | NOC Operationalization | Launch Readiness | The demonstration of the End-to-End of one product by 18th March 2024. | Critical | Open
1051 | M1051 | 2024-03-14 | NOC Operationalization | Launch Readiness | T0 phase points to be completed by March 2024. | Critical | Open
1055 | M1055 | 2024-03-14 | NOC Operationalization | Launch Readiness | Ensure all 5 products are ready by April 2024. | Critical | Open
1058 | M1058 | 2024-03-14 | NOC Operationalization | Network Availibilty | All critical points for T-NOC operationalization to be completed by 30th March 2024. | Critical | Open
1059 | M1059 | 2024-06-11 | NOC Operationalization |  | Interim NOC O&M: L&T to complete pending tasks and seek T-Fiber approval for the start of Interim NOC O&M. | Critical | Open
1060 | M1060 | 2024-06-11 | NOC Operationalization |  | NOC Go-Live: L&T requested recognition of NOC Go-Live status despite manual provisioning; T-Fiber requires full automation for transition from interim to Full NOC. | Critical | Open
1061 | M1061 | 2024-06-11 | NOC Operationalization |  | Functional Gaps in NOC Elements: L&T to meet with OEMs to identify scope gaps and evaluate alternate BSS solutions, presenting recommendations within a week. | Critical | Open
1062 | M1062 | 2024-06-11 | NOC Operationalization |  | Time Delays: L&T to comply with RFP and submit timelines for Full NOC readiness. | Critical | Open
1063 | M1063 | 2024-06-11 | NOC Operationalization |  | WFM Tool Implementation: L&T to operationalize the WFM tool for Package A within one week. | Critical | Open
1064 | M1064 | 2024-06-11 | NOC Operationalization |  | MB and LOA Amendment: L&T to complete MB duct reconciliation; T-Fiber to review data submitted by L&T. | Critical | Open
1065 | M1065 | 2024-06-11 | NOC Operationalization |  | Chemical Storage in GP PoPs: L&T to create guidelines for panchayat chemical storage handling. | Critical | Open
1066 | M1066 | 2024-06-11 | NOC Operationalization |  | PoP Relocation: L&T to re-offer rates for PoP relocation. | Critical | Open
1067 | M1067 | 2024-06-11 | NOC Operationalization |  | Centralized Billing for EB: L&T to submit a proposal for centralized billing. | Critical | Open
1068 | M1068 | 2024-06-11 | NOC Operationalization |  | L&T Cash Flow Pressures: L&T to submit invoices as per RFP compliance for payment release. | Critical | Open
1069 | M1069 | 2024-06-11 | NOC Operationalization |  | GST Payments: T-Fiber to explore options within regulatory norms to resolve GST payment issues. | Critical | Open
1070 | M1070 | 2024-06-11 | NOC Operationalization |  | Interim O&M Payment: L&T to submit supporting documents for payment against Interim O&M. | Critical | Open
1071 | M1071 | 2024-06-11 | NOC Operationalization |  | Full NOC Readiness Plan: L&T to submit a comprehensive plan for Full NOC readiness. | Critical | Open
1072 | M1072 | 2024-06-11 | NOC Operationalization |  | GI Connectivity: L&T to address slow progress and start NoFN connectivity. | Critical | Open
1073 | M1073 | 2024-06-11 | NOC Operationalization |  | AT Completion: L&T to complete AT of 10 districts by July 2024, accounting for monsoon season. | Critical | Open
1074 | M1074 | 2024-06-11 | NOC Operationalization |  | RV – GIs: L&T to identify new partners to connect Rhythu Vedikas. | Critical | Open
1075 | M1075 | 2024-06-11 | NOC Operationalization |  | SLA Achievement: L&T to improve O&M availability to meet the target of 97%. | Critical | Open
1076 | M1076 | 2024-06-11 | NOC Operationalization |  | The urgency for L&T to demonstrate agreed SOPs are in place for Interim NOC O&M and to submit sample reports. | Critical | Open
1077 | M1077 | 2024-06-11 | NOC Operationalization |  | The need for L&T to address the slow progress in GI connectivity and to start NoFN connectivity. | Critical | Open
1078 | M1078 | 2024-06-11 | NOC Operationalization |  | The expectation for L&T to complete AT for multiple districts by July 2024 and to increase resources to meet targets. | Critical | Open
1079 | M1079 | 2024-06-11 | NOC Operationalization |  | The requirement for L&T to resolve issues with OEMs and to consider ready-made BSS solutions to mitigate risks. | Critical | Open
1080 | M1080 | 2024-06-11 | NOC Operationalization |  | Asset Management Policy to be drafted and submitted by L&T before 29th June 2024. | Critical | Open
1081 | M1081 | 2024-06-11 | NOC Operationalization |  | Security Audit of ILL (10G) commissioning to be completed urgently and communicated to DOT prior to service launch. | Critical | Open
1082 | M1082 | 2024-06-11 | NOC Operationalization |  | L&T to set up a dedicated security team for the project to resolve all pending security actions. | Critical | Open
1083 | M1083 | 2024-06-11 | NOC Operationalization |  | L&T to finalize the appointment of a Security SME, with Vikram Khatri being considered for the role. | Critical | Open
1084 | M1084 | 2024-06-11 | NOC Operationalization |  | L&T to send pre-read material at least one day before the next meeting. | Critical | Open
1085 | M1085 | 2024-06-11 | NOC Operationalization |  | Mr. Rajesh Thangavelu, Security in-charge, was absent from the meeting despite specific requests for his presence. | Critical | Open
1086 | M1086 | 2024-06-11 | NOC Operationalization |  | No action items from earlier Minutes of Meetings (MOMs) were presented in the RMC Meeting. | Critical | Open
1087 | M1087 | 2024-06-11 | NOC Operationalization |  | No formal intimation regarding the exit of the existing Security SME (Mr. Gandhi) by L&T. | Critical | Open
1088 | M1088 | 2024-06-11 | NOC Operationalization |  | Cisco firewall and ISE integration is still pending despite being from the same OEM. | Critical | Open
1089 | M1089 | 2024-06-11 | NOC Operationalization |  | Address the absence of the central Security resource in future meetings. | Critical | Open
1090 | M1090 | 2024-06-11 | NOC Operationalization |  | Provide closure status of all old action points in a single sheet before the next meeting. | Critical | Open
1091 | M1091 | 2024-06-11 | NOC Operationalization |  | Complete the scope for Vulnerability Assessment and Penetration Testing as defined and submit the results. | Critical | Open
1092 | M1092 | 2024-06-11 | NOC Operationalization |  | Address the issue of the Cisco firewall and ISE not being integrated. | Critical | Open
1186 | M1186 | 2024-12-09 | NOC Operationalization |  | Principal Consultant to be added in WA groups (only NOC , Service Delivery, Project Delivery , and Technology wise group along with OEMs) | Critical | Closed
1189 | M1189 | 2024-12-09 | NOC Operationalization |  | Only one Issue Tracker to be maintained to track whatever is discussed during current week review | Critical | Closed
1190 | M1190 | 2024-12-09 | NOC Operationalization |  | Share NOC Dec24 roaster | Critical | Closed
1191 | M1191 | 2024-12-09 | NOC Operationalization |  | OSS to be discussed on 10Dec24 or today | Critical | Closed
1192 | M1192 | 2024-12-09 | NOC Operationalization |  | Send all presentations to Principal Consultant | Critical | Closed
1193 | M1193 | 2024-12-09 | NOC Operationalization |  | Change Mgmt. system to be made up, currently its manual on mails/excel | Critical | Open
1196 | M1196 | 2024-12-09 | NOC Operationalization |  | Current PRIORITY discussion to be done for : NOC Review, OSS, DC-Infra, Call Centre HLD/LLD, IP MPLS. Balance to be communicated during the sessions | NON-Critical | Closed
1197 | M1197 | 2024-12-09 | NOC Operationalization |  | Different kinds of reports to be discussed : Daily reports/dashboards, Capacity reports for all nodes/links (like ISP Util, Capacities utilization, licenses , availability reports for PCK-A/B/C technology wise, etc.) | Critical | Closed
1199 | M1199 | 2024-12-09 | NOC Operationalization |  | Principal Consultant meeting with NOC L3s | Critical | Closed
1200 | M1200 | 2024-12-09 | NOC Operationalization |  | NOC 2.0 Mission : 30th April - All systems should be live. BSS KNOT(phase1) should be ready by 15th March OSS should be ready by Jan end NSO should be ready by mid-March | Critical | Open
1201 | M1201 | 2024-12-09 | NOC Operationalization |  | L&T should recommend systems that should be procured for better efficiencies. A tendering process may be taken up as suitable by TFIBER. | Critical | Closed
1202 | M1202 | 2024-12-09 | NOC Operationalization |  | Map of technology vis-à-vis OEM vis-à-vis issues | Critical | Closed
1203 | M1203 | 2024-12-09 | NOC Operationalization |  | Passive Infra-Additional capacity needed in the NOC | Critical | Closed
1204 | M1204 | 2024-12-09 | NOC Operationalization |  | CCTV to be configured on Principal Consultant office and laptop. L&T to come up with solution | Critical | Closed
1205 | M1205 | 2024-12-09 | NOC Operationalization |  | Test labs and staging environment, currently project equipment's (routers, GPON, etc.) are being used | Critical | Closed
1206 | M1206 | 2024-12-09 | NOC Operationalization |  | HLD and LLD documents to be revised for DC Infra | NON-Critical | Open
1210 | M1210 | 2024-12-10 | NOC Operationalization |  | Tejas: Pending API to be given on priority | Critical | Closed
1211 | M1211 | 2024-12-10 | NOC Operationalization |  | Make one WhatsApp group for Tejas only (LTTS, TFIBER, Tejas) | Critical | Closed
1212 | M1212 | 2024-12-10 | NOC Operationalization |  | Suggested one format for SME tasks tracking Each SME to update that tracker putting all critical/major/minor tasks/issues listed in this. To be updated on daily basis with dates | Critical | Closed
1217 | M1217 | 2024-12-10 | NOC Operationalization |  | One resource from Tejas to be placed at TNOC for sorting out Tejas related issues | Critical | Closed
1220 | M1220 | 2024-12-10 | NOC Operationalization |  | Make one WhatsApp group for NSO only (LTTS, TFIBER, OEM) | Critical | Closed
1224 | M1224 | 2024-12-10 | NOC Operationalization |  | Make other WhatsApp group for Cisco other domains (apart from NSO). Make Ravindar Admin to add other Cisco team members. (LTTS except NSO, TF, Cisco) | Critical | Closed
1228 | M1228 | 2024-12-10 | NOC Operationalization |  | Agreement status for all OEM to be shared | Critical | Closed
1232 | M1232 | 2024-12-10 | NOC Operationalization |  | All inhouse automation : LLD to be made by SME and handover to Ops & TFIBER team | NON-Critical | Open
1235 | M1235 | 2024-12-10 | NOC Operationalization |  | Make P1/P2/P3 list for all pending tasks for all domain P1: 25% P2 : 30% P3 : 45% And then list of some additional ask if needed like new HW or software required. | Critical | Closed
1239 | M1239 | 2024-12-10 | NOC Operationalization |  | Pending AT for all Application and DC systems to be shared by tomorrow | Critical | Open
1240 | M1240 | 2024-12-10 | NOC Operationalization |  | Major nodes/links utilization report to be shared (Deployed V/s Utilized) by tomorrow | Critical | Closed
1241 | M1241 | 2024-12-10 | NOC Operationalization |  | Did anyone visited DR Ctrl-S location at Mumbai? No, except of earlier L&T Delivery Head Principal Consultant: Will plan visit to this location in future | Critical | Open
1242 | M1242 | 2024-12-10 | NOC Operationalization |  | Send Cluster wise utilization report for DC infra | Critical | Closed
1243 | M1243 | 2024-12-10 | NOC Operationalization |  | Login in OSS, BSS, ticketing, NSO and to share all links with Principal Consultant | Critical | Closed
1245 | M1245 | 2024-12-10 | NOC Operationalization |  | Access to NAS server to be provided to Principal Consultant to get access to HLD / LLD / reports. | NON-Critical | Closed
1246 | M1246 | 2024-12-10 | NOC Operationalization |  | Dashboards samples were shared by the Principal Consultant, a brief discussions carried on how critical data to be presented | Critical | Closed
1247 | M1247 | 2024-12-11 | NOC Operationalization |  | Actual implemented IP MPLS ring details needed. | Critical | Closed
1248 | M1248 | 2024-12-11 | NOC Operationalization |  | Share Test Setup proposal which was sent to TFIBER by LTTS. | Critical | Open
1249 | M1249 | 2024-12-11 | NOC Operationalization |  | What is total scope of the project V/S implementation. And then total equipment procured Vs installed Vs Available in field and at DC | Critical | Closed
1251 | M1251 | 2024-12-11 | NOC Operationalization |  | Tomorrow Field Project team discussion is scheduled (Different Packages , Different Slots, Need OSS and NOC team) | Critical | Closed
1252 | M1252 | 2024-12-11 | NOC Operationalization |  | Inventory, down, nodes/links with aging, team deployed in field to be shown to them | Critical | Closed
1254 | M1254 | 2024-12-11 | NOC Operationalization |  | Holistic IP planning for all service type to be done based on discussion in near future | Critical | Closed
1255 | M1255 | 2024-12-11 | NOC Operationalization |  | Official mail to IPNIC from TFIBER MD office for additional IPs to be sent | Critical | Open
1256 | M1256 | 2024-12-11 | NOC Operationalization |  | For all equipment's, need confirmation mail/letter from all OEMs for IPv4 and IPv6 dual stack implementation compliance | Critical | Open
1257 | M1257 | 2024-12-11 | NOC Operationalization |  | A consistent process of design review to acceptance of artefact is missing. Requested Principal Consultant to agree process to set a design authority | Critical | Closed
1259 | M1259 | 2024-12-11 | NOC Operationalization |  | What BSS & NSO does? Can you make flow of processes/data/provisioning/delivery etc. across BSS, NSO, OSS, EMS, Billing, Helpdesk | Critical | Closed
1260 | M1260 | 2024-12-11 | NOC Operationalization |  | What all services are automated and what is not automated list to be provided | Critical | Closed
1262 | M1262 | 2024-12-13 | NOC Operationalization |  | Make Node Availability as per today's format as suggested by Principal Consultant | Critical | Closed
1263 | M1263 | 2024-12-13 | NOC Operationalization |  | All nodes/applications AMC details to be shared | Critical | Closed
1264 | M1264 | 2024-12-31 | NOC Operationalization |  | Network alarms to be reduced, currently 90K alarms | Critical | Closed
1265 | M1265 | 2025-02-14 | NOC Operationalization |  | Go-live plan discussion and action items to be tracked and closed | Critical | Closed
1266 | M1266 | 2025-02-14 | NOC Operationalization |  | One-to-one meeting with complete TNOC resources to be completed | Critical | Open
1268 | M1268 | 2025-02-14 | NOC Operationalization |  | Undertaking from L&T is needed for all In-House software | Critical | Open
1269 | M1269 | 2025-02-14 | NOC Operationalization |  | PKG-A WH inventory data to be uploaded in Asset Manager | Critical | Open
1271 | M1271 | 2025-04-03 | NOC Operationalization |  | One slide to be presented showing status of work capturing: a. Status (last week actions), b) Issues, c) Achievements d) Plan for Next week. Only major points to be mentioned | Critical | Closed
1272 | M1272 | 2025-04-03 | NOC Operationalization |  | Review slides to capture: 1. Tech/SME/OEM wise update 2. Domain Status - one slide for each domain 3. HLD/LLD/FAT update 4. Detailed HLD/LLD/FAT open points list: 20-30 points 5. Other important points (NOC also like DWDM losses, infra issues at ZOnal/mandal, etc.) 6. 742 Tracker, MoM update | NON-Critical | Closed
1273 | M1273 | 2025-04-03 | NOC Operationalization |  | Aggressive followups with TPA to be done by L&T SMEs. Post 2-3 followups, then come to Principal Consultant for support alongwith TPA | Critical | Open
1275 | M1275 | 2025-04-03 | NOC Operationalization |  | Incorporate MoM points in HLD/LLD documents | NON-Critical | Closed
1276 | M1276 | 2025-04-03 | NOC Operationalization |  | Make proper justification for A&O for Tfiber MD approval. Shpw project plan. Show previous delivered systems like IPDR, BBNL solution which his made solely by L&T inhouse team. Include Support system/mechanism to Tfiber during 7 years and post L&T exit project | Critical | Closed
1278 | M1278 | 2025-04-03 | NOC Operationalization |  | Every Thursday 11 AM review meeting to be planned with Principal Consultant on NOC project | Critical | Closed
5 | M5 | 2023-03-27 | NSO | Full NOC Readiness | variance in L2 & L3, requiring time to understand along with NSO & OSS SMEs | Critical | Open | OSS Dashboards
11 | M11 | 2023-04-03 | NSO | Functional AT Plan | Use-Cases Testing under NSO | Critical | Open | OSS Dashboards
182 | M182 | 2023-09-22 | NSO | Service provisioning | NSO provisioning is happening through EMS and asked for the list of provisioning/monitoring features being limited or constrained due to any interoperability issues in a multi-vendor eco-system. | Critical | Open
187 | M187 | 2023-09-22 | NSO | Handbook & SOPs | Train in-house L&T resources in NSO and NEDs for reduced dependency on Cisco. | Critical | Open
246 | M246 | 2023-09-26 | NSO | Service provisioning | IP Pool analysis with clearly define the ownership structure of IPs, specifying whether it's co-ownership or complete ownership by the OEM. | NON-Critical | Open
299 | M299 | 2023-10-19 | NSO | Design features | Point No. 221: MAG/GAC ports reservation feasibility for services booked in BSS with payments made. - BSS-SME, L&T to seek clarity on port reservation as a business requirement and the time period required for reservation. - Head Telecom Networks, L&T to record the statement that the port reservation is not a blocker for Network Launch. - Request a Note (Note 5) documenting the statement made by Head Telecom Networks. - L&T to make a decision on the period of port reservation considering the scope of NOC O&M for 7 years. | Critical | Open
300 | M300 | 2023-10-19 | NSO | Development & Unit Testing | Point No. 223: IPTV tested needs to be finalised for additional configuration for multicast and tested as per lab availability and final sign off Technical Head, L&T to get the solution sign-off from T-Fiber for additional IPTV configuration and testing. - Target implementation date set for November 15th '23. - Request a Note (Note 6) recording the statement that this point is not a blocker for Network Launch. | Critical | Open
319 | M319 | 2023-10-19 | NSO | Design & Documentation | Point No. 343: SDC content to GI – Design document required. Head Telecom Networks, L&T to update on the next steps by 26th October ’23. | NON-Critical | Open
334 | M334 | 2023-11-03 | NSO | Service provisioning | NSo inventory manager funtionality to check. | Critical | Open
460 | M460 | 2024-01-04 | NSO | Service Solution | Submit a plan for the completion of the 28 services, along with dependencies | Critical | Open
463 | M463 | 2024-01-04 | NSO | Service Solution | Submit a road map for the completion of the 28 services and all variants | Critical | Open
464 | M464 | 2024-01-04 | NSO | Service Solution | Initiate daily meetings and share progress updates | Critical | Open
476 | M476 | 2024-01-05 | NSO | Service provisioning | Revisit current Circuit ID logic in NSO and define new naming convention | Critical | Open
477 | M477 | 2024-01-05 | NSO | Service provisioning | Ensure GUI interface to initiate the order from NSO directly | Critical | Open
478 | M478 | 2024-01-05 | NSO | Service provisioning | Make A&O independent of BSS for generating Circuit ID | Critical | Open
479 | M479 | 2024-01-05 | NSO | Service provisioning | Circuit ID should distinguish origin system if a new front-end system is introduced | Critical | Open
480 | M480 | 2024-01-05 | NSO | Service provisioning | Ensure Circuit ID isn't limited to 6/8 digits; it should follow the industry-recommended approach | Critical | Open
521 | M521 | 2024-01-24 | NSO | O&M Strategy | Complete basic six products and field O&M | Critical | Open
529 | M529 | 2024-01-24 | NSO | Design Features | Provide road map detailing how the 6 products will move from manual process to automation | Critical | Open
530 | M530 | 2024-01-24 | NSO | Design Features | Share a plan about how 6 products Dark Fiber, GI-BB, T-Cell, T-VPN, T-Dill will move from manual process to automation | Critical | Open
568 | M568 | 2024-02-14 | NSO | Service provisioning | Resolve issues with the NSO features | Critical | Open
569 | M569 | 2024-02-14 | NSO | Service provisioning | Fast track the making of the pre-production environment | Critical | Open
570 | M570 | 2024-02-14 | NSO | Service provisioning | Upload government orders in the BSS | Critical | Open
571 | M571 | 2024-02-14 | NSO | Service provisioning | Re-initiate the daily cadence calls | Critical | Open
572 | M572 | 2024-02-14 | NSO | Service provisioning | Make all products for the government and cellular business segments ready by | Critical | Open
574 | M574 | 2024-02-14 | NSO | Service provisioning | Work parallelly on household business products | Critical | Open
575 | M575 | 2024-02-14 | NSO | Service provisioning | Onboard all L&T SMEs and involve OEMs for 15th March'24 target | Critical | Open
665 | M665 | 2023-07-05 | NSO | NSO | Arrive at feasible alternatives to handle situations such as NSO provisioning timeouts, submit alternative approaches in such scenarios and revert with exact steps taken to achieve this. | Critical | Open
680 | M680 | 2023-07-21 | NSO | NSO related | NSO Competency Plan: L&T to put in place an NSO competency plan . | Critical | Open
832 | M832 | 2023-11-03 | NSO | Service Delivery | UD,SD Peramaters to be captured. | Critical | Open
833 | M833 | 2023-11-03 | NSO | Service Delivery | NSo inventory manager funtionality to check. | Critical | Open
834 | M834 | 2023-11-03 | NSO | Service Delivery | UD perameters for product based to be prepared. | Critical | Open
835 | M835 | 2023-11-03 | NSO | Service Delivery | Ashish to comeback with Design plan for Inventory Manager at NSO | Critical | Open
836 | M836 | 2023-11-03 | NSO | Service Delivery | Arvindam to comeback with product wise UD perameters | Critical | Open
837 | M837 | 2023-11-03 | NSO | Service Delivery | Additional information for VRF, VLAN , Inner vlan etc to capture in Master DB | Critical | Open
838 | M838 | 2023-11-03 | NSO | Service Delivery | As per Cisco LLD All 28 types of L2, L3 models to be mapped aginest products | Critical | Open
839 | M839 | 2023-11-03 | NSO | Service Delivery | GL code to be mapped based on subtype GI under sub type Central & State | Critical | Open
840 | M840 | 2023-11-03 | NSO | Service Delivery | Definbe the Code for Circuit type , Customer type , customer service type etc in single format | Critical | Open
841 | M841 | 2023-11-03 | NSO | Service Delivery | Define design plan for House hold services in GPON Level | Critical | Open
842 | M842 | 2023-11-03 | NSO | Service Delivery | Define Household plan for provisioning as per the GPON plan design | Critical | Open
843 | M843 | 2023-11-03 | NSO | Service Delivery | OSS Method of distance from GIS need to comeback with plan | Critical | Open
844 | M844 | 2023-11-03 | NSO | Service Delivery | Aravindam to update on previous meetings updates to be updated in next in continuous meetings | Critical | Open
921 | M921 | 2023-12-28 | NSO | Service Delivery | Develop Service Delivery – Provisioning through OSS module; address potential failures and industry best practices. | Critical | Open
924 | M924 | 2023-12-28 | NSO | Resource Augmentation | NSO resource available from 3rd January '24; ensure readiness to operate remotely and train L&T resources. | Critical | Open
935 | M935 | 2024-01-05 | NSO | Service provisioning | GUI Interface for NSO | Critical | Open
1039 | M1039 | 2024-03-14 | NSO | Service Delivery | Ensuring the service delivery organization is structured for an interim period. | Critical | Open
1195 | M1195 | 2024-12-09 | NSO | Service provisioning | IP Schema to discussed | Critical | Closed
1213 | M1213 | 2024-12-10 | NSO | Service provisioning | 27 services NSO licenses details to be shared with Principal Consultant | Critical | Closed
1214 | M1214 | 2024-12-10 | NSO | Service provisioning | NSO VMs details for T&D to be shared with Principal Consultant along with issue details (what support needed from Cisco) | Critical | Closed
1215 | M1215 | 2024-12-10 | NSO | Service provisioning | Trial licenses will be given as stop gap arrangement for NSO T&D setup. VM details to be shared with Ravindra (MAC id , etc.) by LTTS | Critical | Closed
1218 | M1218 | 2024-12-10 | NSO | Service provisioning | Agreed SOW for NSO to be shared | Critical | Closed
1219 | M1219 | 2024-12-10 | NSO | Service provisioning | SOW for Cisco NSO - by when quotation will be closed by Cisco? Cisco to revert back with quotation timelines, probably tomorrow, also with TAT for implementation | Critical | Open
1221 | M1221 | 2024-12-10 | NSO | Service provisioning | Dark Fiber as a service | Critical | Closed
1222 | M1222 | 2024-12-10 | NSO | Service provisioning | List down all services which are needed for launch (As per LTTS understanding). During 2PM workshop tomorrow KNOT, Aravindham, Ashish, Ravindra Cisco, TFIBER will be there on call | Critical | Closed
1277 | M1277 | 2025-04-03 | NSO | Service provisioning | GI-BB Demo to be shown to Principal Consultant on 15th April2025 | Critical | Closed
635 | M635 | 2023-07-04 | OEM Related | Security | Cisco Firewall Limitation: L&T to demonstrate GI Internet workflow by 5th April '23 and confirm support for full capacity of 30 thousand institutions. | Critical | Open
848 | M848 | 2023-11-17 | OEM Related | GPON | Closure of Issues with Tejas & Nokia: Letter of confirmation for closure to be submitted on or before 30th November ’23. | Critical | Open
849 | M849 | 2023-11-17 | OEM Related | GPON | OEM Teams Onboarding: HP & Cisco OEM teams to be onboarded from 20th November '23. | Critical | Open
850 | M850 | 2023-11-17 | OEM Related |  | Letters from OEMs: Letters from all OEMs, excluding Cisco & HP, to be submitted by 22nd November '23. Letters from Cisco & HP to be submitted by 24th November '23. | Critical | Open
866 | M866 | 2023-12-12 | OEM Related | Tejas Related | Submit updated undertakings for Tejas - Alepo and Nokia | Critical | Open
922 | M922 | 2023-12-28 | OEM Related | Service Delivery | Manual KPI for service assurance due to lack of OEM confirmation; address concerns about NSO and OSS use. | Critical | Open
923 | M923 | 2023-12-28 | OEM Related |  | Align L&T and OEM with product vision and delivery cadence; consider product development strategy. | Critical | Open
1010 | M1010 | 2024-02-13 | OEM Related |  | Issues with application integration | Critical | Open
1041 | M1041 | 2024-03-14 | OEM Related | Network Availibilty | Resolving OEM-related gaps and achieving automation roadmap targets. | Critical | Open
1054 | M1054 | 2024-03-14 | OEM Related |  | Provide updates on the pre-production environment, OEM gaps, and integration of systems and applications by 16th March 2024. | Critical | Open
1093 | M1093 | 2024-06-14 | OEM Related |  | All API Documents by HP to be submitted by L&T as soon as possible. | Critical | Open
1094 | M1094 | 2024-06-14 | OEM Related |  | BBNL integration solution to be provided by the end of June 2024, with testing beginning from 24th June 2024. | Critical | Open
1095 | M1095 | 2024-06-14 | OEM Related |  | Alarm enrichment with custom attributes and other new SOW items are in progress, with some attributes completed and others recently given. | Critical | Open
1096 | M1096 | 2024-06-14 | OEM Related |  | L&T to map documents as per RFP requirements and identify gaps for new SOW internally to their OEMs. | Critical | Open
1097 | M1097 | 2024-06-14 | OEM Related |  | HPE to provide Admin user privilege to L&T for filtering after a professional agreement is signed. | Critical | Open
1098 | M1098 | 2024-06-14 | OEM Related |  | OpenText to share all required documents by 24th June 2024. | Critical | Open
1099 | M1099 | 2024-06-14 | OEM Related |  | L&T to demonstrate the correlation engine and event alarm management for all domains. | Critical | Open
1100 | M1100 | 2024-06-14 | OEM Related |  | External API details provided by L&T are currently not functioning. | Critical | Open
1101 | M1101 | 2024-06-14 | OEM Related |  | API extension for Alarm Enrichment is not functioning, and inventory API is operational. | Critical | Open
1102 | M1102 | 2024-06-14 | OEM Related |  | Service impact analysis is not available, and cross-domain RCA is not provided. | Critical | Open
1103 | M1103 | 2024-06-14 | OEM Related |  | Alarm forwarding API is not working, and there is a need for service impact and network impact information. | Critical | Open
1104 | M1104 | 2024-06-14 | OEM Related |  | There is no topology and zonal view of IPMPLS, and some performance management points are pending validation. | Critical | Open
1105 | M1105 | 2024-06-14 | OEM Related |  | L&T to submit all API documents, not just BBNL, and involve T-Fiber for review. | Critical | Open
1106 | M1106 | 2024-06-14 | OEM Related |  | L&T to demonstrate functionality and ensure alarm management is in place with the necessary enrichments. | Critical | Open
1107 | M1107 | 2024-06-14 | OEM Related |  | OpenText to demonstrate the NNMi KPI dashboard and complete the end-to-end demo for threshold values. | Critical | Open
1108 | M1108 | 2024-06-14 | OEM Related |  | L&T to define the scope with NSO for the Service Inventory module and ensure it is part of the deliverables. | Critical | Open
1109 | M1109 | 2024-06-14 | OEM Related |  | HPE to revisit all alarm scenarios, involve T-Fiber for review, and bring in industry best practices. | Critical | Open
1110 | M1110 | 2024-06-14 | OEM Related |  | HPE to review the RFP, compliance documents, solution documents, and HLD document, and offer the system for AT if everything is in compliance. | Critical | Open
1111 | M1111 | 2024-06-14 | OEM Related |  | L&T to provide API library access and complete API documents of OpenText to T-Fiber as soon as possible, with follow-up by Director-NOC, T-Fiber. | Critical | Open
1112 | M1112 | 2024-06-14 | OEM Related |  | BBNL integration task completion by 30th June 2024, with day-to-day progress monitoring by Director-NOC, T-Fiber. | Critical | Open
1113 | M1113 | 2024-06-14 | OEM Related |  | OpenText to provide a SMAX proposal with a detailed presentation for potential replacement analysis. | Critical | Open
1114 | M1114 | 2024-06-14 | OEM Related |  | L&T to arrange a demo for Server Performance Monitoring and submit all KPI details. | Critical | Open
1115 | M1115 | 2024-06-14 | OEM Related |  | OpenText to define custom reports for centralized and customizable service level reporting. | Critical | Open
1116 | M1116 | 2024-06-14 | OEM Related |  | OpenText to provide a 7-year direct support commitment and an approval system via email & mobile app. | Critical | Open
1117 | M1117 | 2024-06-14 | OEM Related |  | OpenText to provide a list of device models supported for SNMP polling. | Critical | Open
1118 | M1118 | 2024-06-14 | OEM Related |  | Full API library of vTemIP is unavailable, affecting self-testing of modules. | Critical | Open
1119 | M1119 | 2024-06-14 | OEM Related |  | Product support status from OpenText and incident management issues, including ticket grouping and content filtering. | Critical | Open
1120 | M1120 | 2024-06-14 | OEM Related |  | Unavailability of a consolidated dashboard and cross-domain topology visibility. | Critical | Open
1121 | M1121 | 2024-06-14 | OEM Related |  | Instability of OBR and NNMi causing issues in IT event management. | Critical | Open
1122 | M1122 | 2024-06-14 | OEM Related |  | Concerns about the pending Network Automation and the process for implementing upgrades. | Critical | Open
1123 | M1123 | 2024-06-14 | OEM Related |  | OpenText to check and revert with timelines for API library access. | Critical | Open
1124 | M1124 | 2024-06-14 | OEM Related |  | OpenText to revisit the issue of limited ticket visibility in the UI and accommodate more data. | Critical | Open
1125 | M1125 | 2024-06-14 | OEM Related |  | L&T to establish a product service contract and ensure the operational team is fully engaged. | Critical | Open
1126 | M1126 | 2024-06-14 | OEM Related |  | OpenText to provide a solution for Service Level Reporting & availability and to demonstrate WAN-LAN connectivity mapping. | Critical | Open
1127 | M1127 | 2024-06-14 | OEM Related |  | L&T to discuss with OpenText about Network Automation for Deployment and configuration check module License. | Critical | Open
1128 | M1128 | 2024-06-14 | OEM Related |  | OpenText to deploy a dedicated resource in Hyderabad to close all open points and establish a standard test bed environment. | Critical | Open
1129 | M1129 | 2024-06-14 | OEM Related |  | All demonstrations should be conducted in the presence of T-Fiber representatives, and product compliance with ITIL Gold level certification needs to be rechecked. | Critical | Open
1147 | M1147 | 2024-07-12 | OEM Related |  | Cisco confirmed that Airtel uses NSO for IP/MPLS with around 70,000 devices, and Jio uses it for transport management and service provisioning. | Critical | Open
1148 | M1148 | 2024-07-12 | OEM Related |  | In T-Fiber, NSO interfaces with EMS for GPON (Nokia & Tejas) and directly with network elements for Cisco IP/MPLS. | Critical | Open
1149 | M1149 | 2024-07-12 | OEM Related |  | SVP, T-Fiber requested a comprehensive update on the project's progress, including accomplishments, pending tasks, and future plans. | Critical | Open
1150 | M1150 | 2024-07-12 | OEM Related |  | Cisco confirmed that lab licenses are provided free with production licenses and that it is standard practice to set up a pre-production environment. | Critical | Open
1151 | M1151 | 2024-07-12 | OEM Related |  | Cisco assured to provide access to the Smartlicenses portal for T-Fiber and to share the full library of APIs for all A&O modules. | Critical | Open
1152 | M1152 | 2024-07-12 | OEM Related |  | Technical Support and Operations: | Critical | Open
1153 | M1153 | 2024-07-12 | OEM Related |  | Discussions were held about the method of operation for NED and product lifecycle management. | Critical | Open
1154 | M1154 | 2024-07-12 | OEM Related |  | Cisco suggested a gradual handover process with a joint account of L&T and Cisco for a smooth transition. | Critical | Open
1155 | M1155 | 2024-07-12 | OEM Related | NSO | Director-P&E, T-Fiber inquired about the system responsible for maintaining the complete inventory within NSO. | Critical | Open
1156 | M1156 | 2024-07-12 | OEM Related |  | Cisco mentioned that full orchestration currently requires human intervention, and a service discovery and reconciliation module is needed for full automation. | Critical | Open
1157 | M1157 | 2024-07-12 | OEM Related |  | Concerns were raised about customization in the pre-production phase and the need to complete customizations before going live. | Critical | Open
1158 | M1158 | 2024-07-12 | OEM Related |  | Cisco emphasized the importance of a change management system for configuration changes and the need for a service audit feature. | Critical | Open
1159 | M1159 | 2024-07-12 | OEM Related |  | Cisco to provide all API libraries and hand over NED with knowledge transfers. | Critical | Open
1160 | M1160 | 2024-07-12 | OEM Related |  | Inventory module and bandwidth manager are still open issues. | Critical | Open
1161 | M1161 | 2024-07-12 | OEM Related |  | L&T to provide lifecycle processes and how change management and customization are done post-production. | Critical | Open
1162 | M1162 | 2024-07-12 | OEM Related | NSO | Cisco to provide E2E topology feasibility, including bandwidth management using NSO. | Critical | Open
1163 | M1163 | 2024-07-12 | OEM Related |  | Director-P&E, T-Fiber asked for the deployment of the system in a pre-production environment for thorough testing. | Critical | Open
1164 | M1164 | 2024-07-12 | OEM Related |  | SVP, T-Fiber requested access to all modules within the pre-production environment, along with necessary licenses. | Critical | Open
1165 | M1165 | 2024-07-12 | OEM Related |  | Director-P&E, T-Fiber emphasized the importance of the system being modular and raised concerns about functionality without BSS. | Critical | Open
1166 | M1166 | 2024-07-15 | OEM Related |  | L&T to inform T-Fiber and provide details once solution support is fully deployed. | Critical | Open
1167 | M1167 | 2024-07-15 | OEM Related |  | L&T to focus on solution reports and resolve operational issues related to UTM. | Critical | Open
1168 | M1168 | 2024-07-15 | OEM Related |  | HPE to consider features not possible for alternative solutions. | Critical | Open
1169 | M1169 | 2024-07-15 | OEM Related |  | L&T to provide automation in the purge-auto termination process without manual intervention. | Critical | Open
1170 | M1170 | 2024-07-15 | OEM Related |  | L&T to ensure GIS is the master source for passive infra and it should be a permanent solution. | Critical | Open
1171 | M1171 | 2024-07-15 | OEM Related |  | L&T to provide all relevant data to facilitate customization requirements for business. | Critical | Open
1172 | M1172 | 2024-07-15 | OEM Related |  | L&T assured that technical support would be available for the long term and operational training would continue until the complete delivery of the contract. | Critical | Open
1173 | M1173 | 2024-07-15 | OEM Related |  | L&T to demonstrate all points, including completed points, to ensure transparency on solutions implemented. | Critical | Open
1174 | M1174 | 2024-07-15 | OEM Related |  | L&T to prioritize tasks to support business along with T-Fiber to maintain efficient and effective operational workflows. | Critical | Open
1175 | M1175 | 2024-07-15 | OEM Related |  | L&T and HPE to provide timelines for operational, delivery, and technical support, as well as a plan for out-of-the-box features. | Critical | Open
1176 | M1176 | 2024-07-15 | OEM Related |  | L&T to provide updated LLD document and ensure that all Licenses are provided to T-Fiber as they are an asset of T-Fiber. | Critical | Open
1177 | M1177 | 2024-07-15 | OEM Related |  | L&T to submit customize reports and ensure that all open HP APIs should be made available to L&T and T-Fiber. | Critical | Open
1178 | M1178 | 2024-07-15 | OEM Related |  | L&T to ensure that the pre-production environment is set up and additional infrastructure needs are met. | Critical | Open
1179 | M1179 | 2024-07-15 | OEM Related |  | Director-P&E, T-Fiber emphasized the importance of delivering services and suggested scheduling calls to ensure delivery is on track. | Critical | Open
1180 | M1180 | 2024-07-15 | OEM Related |  | Director-P&E, T-Fiber requested an out-of-box demo as per the pre-bid agreement. | Critical | Open
1181 | M1181 | 2024-07-15 | OEM Related |  | A detailed discussion is required for DR with all stakeholders, including HPE, OT, and CTRL S, for a comprehensive approach. | Critical | Open
1183 | M1183 | 2024-07-22 | OEM Related |  | MD, T-Fiber asked L&T to work with the OEM for a higher license count for the Work Force Management Tool (WFM) and to explore features of government tools for comparison. | Critical | Open
1184 | M1184 | 2024-07-22 | OEM Related |  | Concerns were raised about the delay in onboarding OEMs like OpenText, HP, and Cisco. | Critical | Open
1185 | M1185 | 2024-07-22 | OEM Related |  | Concerns were raised about the lack of response from Nokia on Hybrid mode solutioning. | Critical | Open
1187 | M1187 | 2024-12-09 | OEM Related |  | OEM wise physical meeting to be called | Critical | Closed
1208 | M1208 | 2024-12-10 | OEM Related |  | Tejas : TR069 feature to be enabled for TFIBER network | NON-Critical | Open
1209 | M1209 | 2024-12-10 | OEM Related |  | One resource from Tejas to be placed at TNOC for sorting out Tejas related issues | Critical | Closed
1216 | M1216 | 2024-12-10 | OEM Related | Cisco EPNM | License issue for EPNM and ISE to be resolved | Critical | Open
1223 | M1223 | 2024-12-10 | OEM Related |  | SG350 switch EOS/EOL: GP all OK. Mandal/Zonal level have some discrepancy like less ports compared to current version or at least match to RFP | NON-Critical | Open
1225 | M1225 | 2024-12-10 | OEM Related |  | SG350 switch: EOSale/EOL/LDOHWS (Last date of HW support which is Oct2026. Till LDOHWS that RMA will be given with new CBS model. Post that support will stop. Mail request to be send to Cisco to extend support. | NON-Critical | Open
1226 | M1226 | 2024-12-10 | OEM Related |  | EPNM license upgraded, in smart account licenses are not working. Its issue with PKG-A only (PKG-B/C had procured separately 5.x so they don’t have this issue, while LTTS procured 2.x as per Ravindra) | Critical | Open
1231 | M1231 | 2024-12-10 | OEM Related |  | Principal Consultant Room Dashboard - Excel sheet sent, to discuss and finetune. Discussed. Need this report through OSS, to be added in HPE/OT scope once they are onboarded - discuss jointly with TFIBER along with OEM | Critical | Open
1233 | M1233 | 2024-12-10 | OEM Related |  | OSS out of Scope: 1. Service Topology 2. Retail Services (5Mn), 3. Services & Service KPI Monitoring. As per SOR this is not there. This is for Principal Consultant information | Critical | Closed
1234 | M1234 | 2024-12-10 | OEM Related |  | Share all OSS documents (RFP points, LLD, FRS, etc.) | Critical | Closed
1237 | M1237 | 2024-12-10 | OEM Related |  | Bottomline for OSS: Engagement with HPE and OT to start to get all OSS open/pending tasks done | Critical | Open
1238 | M1238 | 2024-12-10 | OEM Related | All OEM's | Priority engagement with HPE/OT/Cisco/Aleppo needed to meet Apr25 target. Current payment/cash flow issues hindering this right now | Critical | Open
1244 | M1244 | 2024-12-10 | OEM Related | Neox | Neox team to be called for meeting | Critical | Open
1250 | M1250 | 2024-12-11 | OEM Related | HPSM | In Asset Manager deployed inventory status is available. WH equipment data also available for PKG-B & C. | Critical | Closed
1267 | M1267 | 2025-02-14 | OEM Related | Nokia | All APIs to be taken from Nokia | Critical | Open
14 | M14 | 2023-04-16 | OSS | Full NOC Readiness | Secretary, DoT enquired to show the MTTR through against individual TT in the OSS | Critical | Open | OSS Dashboards
18 | M18 | 2023-05-18 | OSS | Integration | IP MPLS auto trouble tickets | Critical | Open | OSS Dashboards
145 | M145 | 2023-08-23 | OSS | Manual Feasibility Plan | Plan for manual feasibility in the OSS | NON-Critical | Open
183 | M183 | 2023-09-22 | OSS | Service provisioning | Role of OSS in Service Provisioning | Critical | Open
301 | M301 | 2023-10-19 | OSS | Integration | Point No. 251: Fetch SLA violation by BSS billing & Point No. 252 Circuit performance data to BSS CRM L&T to provide an outline of the interim solution before the Service Inventory solution from HP is in place. - Ensure no impact on operations during the interim period. - L&T proposes interim measures such as manual computation of downtime, manual SLA performance management, etc. - Request an Undertaking (Note 7) confirming that the interim solution will have no cost impact to T-Fiber. - Timelines for interim milestones and emphasize the need to plan for the final deliverables and a seamless transition. - Segment Head, L&T to provide clear confirmation by the 1st week of November '23. | Critical | Open
302 | M302 | 2023-10-19 | OSS | Integration | Point No. 264: Network Downtime, fault reported to be mapped with BSS to consider during billing process & Point No. 265: Feasibility Engine & Point No. 266: Commercial engine to be designed along with rules to Budgetary calculation for network and customer feasibilities L&T to submit the SOW agreed between L&T and HP by EoD 19th October ’23. | Critical | Open
303 | M303 | 2023-10-19 | OSS | Development & Unit Testing | Point No. 267: Port Block against Service ID ( Note 5) | Critical | Open
304 | M304 | 2023-10-19 | OSS | Design & Documentation | Point No. 272: Infra team to maintain the SSH connectivity • Security-SME, L&T to submit the design document for SSH. | Critical | Open
305 | M305 | 2023-10-19 | OSS | Dashboards | Point No. 280: Cross domain Corelation and exact reason for any outage in Network till ONT Port with E2E topology is targeted for closure by November 15th '23. | Critical | Open
306 | M306 | 2023-10-19 | OSS | Dashboards | Point No. 282: For ONT Down cases, Some of the Alarms and cause code given by OEM is not matching with RFO provided by field engineer with target date as 25th October ’23. | Critical | Open
307 | M307 | 2023-10-19 | OSS | Dashboards | Point No. 283: Alert Mechanism (event rule) when power supply is through UPS which is running on Battery backup mode then there should be alert in the form of SMS sent to field team so outages can be avoided or minimized proactively. target date is 15th November ’23. | Critical | Open
308 | M308 | 2023-10-19 | OSS | Dashboards | Point No. 290: IP MPLS node status report to be automated (Zonal / Mandal/GP) along with Alias Name (Like Actual Mandal /GP names) -Feasibility check required if Alias can be updated & fetched by OSS tool will be informed | Critical | Open
309 | M309 | 2023-10-19 | OSS | Dashboards | Point No. 292: Customised dashboard template with available set of fields for different set of user views by 20th Oct'23 | Critical | Open
310 | M310 | 2023-10-19 | OSS | Dashboards | Point No. 294: OSS MTTR report to include additional columns like RFO, Sub RFO, Resolution etc. By 20th Oct'23 | Critical | Open
311 | M311 | 2023-10-19 | OSS | Dashboards | Point No. 296: Service Management dashboard should list planned outages and corelate TT if that is on same device or NW component by 20th Oct'23 | Critical | Open
314 | M314 | 2023-10-19 | OSS | Resource Related | SVP, T-Fiber emphasized the importance of L&T establishing its own resources for the HPE related tasks and they should not rely solely on one individual. | Critical | Open
325 | M325 | 2023-10-19 | OSS | Integration | Point No. 231: Ciena DWDM Network Topology has been created in HPE OSS topology MAP along with neighbour NE details. SVP, T-Fiber suggested that this requirement may be revisited later. | Critical | Open
326 | M326 | 2023-10-19 | OSS | Design Features | Point No. 259: OSS E2E Topology it will be completed by 30th December’23 | Critical | Open
327 | M327 | 2023-10-19 | OSS | Dashboards | Point No. 275: In OSS management dashboard, Block count should count only Mandal OLTs and not GP OLTs target date as 30th December ’23. | Critical | Open
328 | M328 | 2023-10-19 | OSS | Design Features | Point No. 281: Problem Management report for various recurring outages for the given period target date as 30th December ’23 | Critical | Open
329 | M329 | 2023-10-19 | OSS | Design Features | Point No. 287: Exact SPAN/Link details must be taken from GIS (Including Lat, Long) for Fiber cut/outage scenario to understand fix is permanent or temporary in nature and impact on Multiple Nodes/GP’s. | Critical | Open
330 | M330 | 2023-10-19 | OSS | Dashboards | Point No. 288: Report for Backup Status (success/failure) of all VM (source it from Vcenter Report) L&T to conclude discussions with HP to obtain the target date. | Critical | Open
331 | M331 | 2023-10-19 | OSS | Dashboards | Point No. 289: DC Active infra-Health check-up /Utilization and Resource Availability report L&T to conclude discussions with HP to obtain the target date. | Critical | Open
332 | M332 | 2023-10-19 | OSS | Dashboards | Point No. 293: Service VLAN status report from EMS (Nokia and Tejas) Technical Head, L&T to conclude discussions to obtain the target date. | Critical | Open
446 | M446 | 2023-12-28 | OSS | HPSM | Remove duplicate TroubleTicket issue | Critical | Open
450 | M450 | 2023-12-28 | OSS | HPSM | Freeze the process for node ticket allocation | Critical | Open
455 | M455 | 2023-12-28 | OSS | HPSM | Ensure cross-domain RCA, SIA, Helpdesk and Network Service Topology are in place | Critical | Open
457 | M457 | 2024-01-04 | OSS | HPSM | Implement ticket tracking with OSS Service Manager | Critical | Open
468 | M468 | 2024-01-04 | OSS | Service Solution | Resolve discrepancies in readiness status of Fault Management, Network Performance Management Security Management, Regulatory Compliances, Service Delivery- Feasibility, DR readiness, and Technical Helpdesk | Critical | Open
525 | M525 | 2024-01-24 | OSS | Design Features | Present the readiness of service inventory module | Critical | Open
613 | M613 | 2023-07-04 | OSS | O&M Strategy | Justify the use of the implemented HPSM tool as best suited to ITIL compliant processes. | Critical | Open
717 | M717 | 2023-08-01 | OSS | Launch Readiness | Deploy the Knowledge Management module in HPSM. | Critical | Open
720 | M720 | 2023-08-01 | OSS | Launch Readiness | Define incident categorisation. | Critical | Open
636 | M636 | 2023-07-04 | PM Tool Issue | PM Tool Issue | Digital Process for GI Connectivity: L&T to present a plan for digital process and tools usage by 5th April '23, with the possibility of presenting earlier in Cadence calls. | NON-Critical | Open
909 | M909 | 2023-12-19 | PM Tool Issue |  | Repository Module for Document Upload: BSS-SME, L&T to ensure the module is available in CRM and discussed with OEM. | NON-Critical | Open
1042 | M1042 | 2024-03-14 | Pre-Production | Network Availibilty | Establishing a pre-production environment for testing applications before moving to production. | NON-Critical | Open
1049 | M1049 | 2024-03-14 | Pre-Production |  | L&T to provide details on modules working in pre-production and production environments and seek approvals for transitions. | NON-Critical | Open
1053 | M1053 | 2024-03-14 | Pre-Production |  | Provide a summary of applications in pre-production & production environments by 16th March 2024. | NON-Critical | Open
1182 | M1182 | 2024-07-22 | Pre-Production |  | MD, T-Fiber emphasized the necessity of a pre-production setup and directed L&T to submit an infrastructure proposal. | NON-Critical | Open
312 | M312 | 2023-10-19 | Regulatory Compliance | Compliance | Point No. 308: IPDR - Developing in-house solution, also exploring with external vendors. to obtain clarity from the Regulator on the requirements, along with the industry best practices. • VP-Program, T-Fiber asked L&T to revert on the next steps by 26th October ’23. | Critical | Open
313 | M313 | 2023-10-19 | Regulatory Compliance | Compliance | Point No. 312: SLA Reporting for Cell Tower and GIs • Head Telecom Networks, L&T mentioned that two approaches are under consideration, solution approach to be finalised, target for completion is 30th November ’23. | Critical | Open
353 | M353 | 2023-11-17 | Regulatory Compliance | Compliance | Security Assessment Review Meeting : week starting | Critical | Open
369 | M369 | 2023-11-28 | Regulatory Compliance | Compliance | Fast-track track closure of Regulatory and security requirements along with SLA monitoring for the immediate start of Business related to Cell Tower, GI BB, GI ILL & VPN service delivery. | Critical | Open
372 | M372 | 2023-12-12 | Regulatory Compliance | RMC meeting | Submit Acceptable Usage Policy document with suggested changes | Critical | Open
373 | M373 | 2023-12-12 | Regulatory Compliance | RMC meeting | Complete the configuration of CA signed SSL certificate | Critical | Open
374 | M374 | 2023-12-12 | Regulatory Compliance | RMC meeting | Concur with T-Fiber for annual external VAPT testing | Critical | Open
375 | M375 | 2023-12-12 | Regulatory Compliance | RMC meeting | Submit Vulnerability Management Policy | Critical | Open
376 | M376 | 2023-12-12 | Regulatory Compliance | RMC meeting | List and share the Security Policy documents and SOPS | Critical | Open
377 | M377 | 2023-12-12 | Regulatory Compliance | RMC meeting | Upload all RMC MoMs to the shared folder and share access | Critical | Open
378 | M378 | 2023-12-12 | Regulatory Compliance | RMC meeting | Submit Asset Management policy | Critical | Open
379 | M379 | 2023-12-12 | Regulatory Compliance | RMC meeting | Submit onboarding/offboarding policy | Critical | Open
380 | M380 | 2023-12-12 | Regulatory Compliance | RMC meeting | Submit scope of work for External VAPT | Critical | Open
381 | M381 | 2023-12-12 | Regulatory Compliance | RMC meeting | Collect Cryptography encryption model document from all OEMs | Critical | Open
384 | M384 | 2023-12-12 | Regulatory Compliance | RMC meeting | Submit document on Privilege management | Critical | Open
385 | M385 | 2023-12-12 | Regulatory Compliance | RMC meeting | Submit password management policy | Critical | Open
386 | M386 | 2023-12-12 | Regulatory Compliance | RMC meeting | Submit artefacts for all banners | Critical | Open
387 | M387 | 2023-12-12 | Regulatory Compliance | RMC meeting | Submit internal/external, Trusted, untrusted zone checklist | Critical | Open
388 | M388 | 2023-12-12 | Regulatory Compliance | RMC meeting | Submit internal network policies details | Critical | Open
389 | M389 | 2023-12-12 | Regulatory Compliance | RMC meeting | Submit SSL implementation report for all APIs | Critical | Open
390 | M390 | 2023-12-12 | Regulatory Compliance | RMC meeting | Submit Acceptable Usage Policy | Critical | Open
536 | M536 | 2024-01-24 | Regulatory Compliance | Regulatory Compliance | Ensure L&T meets all regulatory compliance for poducts and provide NOC operationalisation | Critical | Open
601 | M601 | 2023-07-03 | Regulatory Compliance | Internal Audit | Security Audit | Critical | Open
602 | M602 | 2023-07-03 | Regulatory Compliance | Internal Security | Acceptable Usage of information | Critical | Open
605 | M605 | 2023-07-03 | Regulatory Compliance | Internal Security | VAPT | Critical | Open
606 | M606 | 2023-07-03 | Regulatory Compliance | Internal Security | Security Incident management | Critical | Open
688 | M688 | 2023-07-21 | Regulatory Compliance |  | Regulatory Reports Review: L&T to identify available reports in BSS as Ready/WIP by 21st August '23 and review with T-Fiber for approval . | Critical | Open
750 | M750 | 2023-08-18 | Regulatory Compliance | BSS | Regulatory Reports Review: L&T to identify available reports in BSS as Ready/WIP by 21st August '23 and review with T-Fiber for approval. | Critical | Open
831 | M831 | 2023-10-19 | Regulatory Compliance | IPDR | Clarity from the Regulator on IPDR requirements to be obtained by L&T: Discussion on industry best practices and regulatory aspects to be concluded by 26th October '23. | Critical | Open
877 | M877 | 2023-12-12 | Regulatory Compliance |  | Provide a list of applications generating Syslog, not generating syslog | Critical | Open
880 | M880 | 2023-12-12 | Regulatory Compliance |  | Finalise the duration and frequency of backup, provide storage utilisation report weekly, provide config backup details of all routers/switches/devices, submit weekly report capturing online & offline storage status | Critical | Open
928 | M928 | 2023-12-28 | Regulatory Compliance | Compliance | Clarify NOC resource roles and seating; discuss and fix scope for external audit by 3rd Jan '24; conduct External Audit by 31st January '24. | Critical | Open
1009 | M1009 | 2024-02-13 | Regulatory Compliance |  | Non-compliance with IP-MAC binding | Critical | Open
1011 | M1011 | 2024-02-13 | Regulatory Compliance |  | Review of submitted policy documents | Critical | Open
1015 | M1015 | 2024-02-13 | Regulatory Compliance |  | Review of SSL for applications | Critical | Open
1016 | M1016 | 2024-02-13 | Regulatory Compliance |  | Access control policy | Critical | Open
1017 | M1017 | 2024-02-13 | Regulatory Compliance |  | Concern about remote access management | Critical | Open
1021 | M1021 | 2024-02-13 | Regulatory Compliance |  | Requirements for RMC's reporting | Critical | Open
1022 | M1022 | 2024-02-13 | Regulatory Compliance |  | Proposal for security updates bulletin | Critical | Open
1023 | M1023 | 2024-02-13 | Regulatory Compliance |  | Implementation of SOC's best practices | Critical | Open
1028 | M1028 | 2024-02-16 | Regulatory Compliance |  | Review of submitted security policy documents | Critical | Open
1030 | M1030 | 2024-02-16 | Regulatory Compliance |  | Control of user and visitor access | Critical | Open
1031 | M1031 | 2024-02-16 | Regulatory Compliance |  | Concerns about security reporting and compliance | Critical | Open
1032 | M1032 | 2024-02-16 | Regulatory Compliance |  | VPAT implementation and firmware patching | Critical | Open
1033 | M1033 | 2024-02-16 | Regulatory Compliance |  | Compliance to access management policy | Critical | Open
55 | M55 | 2023-06-22 | Security | Audit | Scope submission for external audit | Critical | Open
56 | M56 | 2023-06-22 | Security | Audit | External agency Audit with certification | Critical | Open
57 | M57 | 2023-06-22 | Security | Audit | external auditor to be government empanelled (MeitY / STQC). | Critical | Open
58 | M58 | 2023-06-22 | Security | Audit | simulation of attacks on the network and hardening of applications in the NOC | Critical | Open
173 | M173 | 2023-09-12 | Security | OEM's Details | Submit details on OEM alignment, warranty, AMC, and engagement status for go-live and post-go-live phases, location-wise & application-wise, to Director-Contracts, T-Fiber | Critical | Open
177 | M177 | 2023-09-12 | Security | Patch update | Engagements with vendors for Patch Delivery and Testing | Critical | Open
252 | M252 | 2023-10-11 | Security | Functional AT Plan | Share scope and test plans of the External Audit. | Critical | Open
253 | M253 | 2023-10-11 | Security | Physical Execution | Physical User access : Button is used for exit and still L&T have to finalise vendor | Critical | Open
254 | M254 | 2023-10-11 | Security | Dashboards | QoS reporting- Breakdown between automated and manual aspects | Critical | Open
315 | M315 | 2023-10-19 | Security | User Traceability | Point No. 316: User Traceability,targeted for closure by 15th November ’23. this point to be included in the SOPs for NOC. | Critical | Open
316 | M316 | 2023-10-19 | Security | Policy Implementation | Point No. 318: Policy Implementation – Network Forensics the process for tracing all incidents including security incidents is yet to be put in place, targeted for 15th November ’23. | Critical | Open
317 | M317 | 2023-10-19 | Security | Report | Point no. 326: IPDR static IP report SVP, T-Fiber asked for the Regulatory aspects to be discovered by 26th October ’23. | Critical | Open
382 | M382 | 2023-12-12 | Security | RMC meeting | Submit the revised undertaking for Tejas - Alepo and Nokia | Critical | Open
383 | M383 | 2023-12-12 | Security | RMC meeting | Provide compliance documents for all applications and devices | Critical | Open
391 | M391 | 2023-12-12 | Security | RMC meeting | Submit Security endpoints list of Infra, workstations | Critical | Open
392 | M392 | 2023-12-12 | Security | RMC meeting | Submit SOP for security policies | Critical | Open
393 | M393 | 2023-12-12 | Security | RMC meeting | Submit DR reports for all Applications | Critical | Open
394 | M394 | 2023-12-12 | Security | RMC meeting | Submit attendance list for security awareness trainings | Critical | Open
395 | M395 | 2023-12-12 | Security | RMC meeting | Finalize backup duration and frequency, and provide utilization report | Critical | Open
396 | M396 | 2023-12-12 | Security | RMC meeting | Submit a report capturing online and offline storage status | Critical | Open
397 | M397 | 2023-12-12 | Security | RMC meeting | Finalize Technology Risk Management checklist | Critical | Open
398 | M398 | 2023-12-12 | Security | RMC meeting | Further audit and VAPT by Allied Boston | Critical | Open
447 | M447 | 2023-12-28 | Security | Regulatory Compliance | Finalize scope of external audit in consultation with T-Fiber | Critical | Open
448 | M448 | 2023-12-28 | Security | Regulatory Compliance | Conduct external audit | Critical | Open
548 | M548 | 2024-02-13 | Security | RMC meeting | Implement IP-MAC binding to prevent IP spoofing | Critical | Open
549 | M549 | 2024-02-13 | Security | RMC meeting | Ensure the standardization of usernames across applications | Critical | Open
550 | M550 | 2024-02-13 | Security | RMC meeting | Obtain T-Fiber's review and approval for policy documents | Critical | Open
551 | M551 | 2024-02-13 | Security | RMC meeting | Work on implementing the guidelines for Dark Fiber from T-Fiber and GIS team | Critical | Open
552 | M552 | 2024-02-13 | Security | RMC meeting | Get clarity on integration rules and timeline for activating 'Ready for Order' and 'Ready for Service' statuses | Critical | Open
553 | M553 | 2024-02-13 | Security | RMC meeting | Implement user access control for converting from RFO to RFS | Critical | Open
554 | M554 | 2024-02-13 | Security | RMC meeting | Populate data fields automatically while feeding site information | Critical | Open
555 | M555 | 2024-02-13 | Security | RMC meeting | Submit a document explaining reformatted guidelines for service | Critical | Open
556 | M556 | 2024-02-13 | Security | RMC meeting | Initiate the implementation of Mandal-to-Mandal and Mandal-to-GP dark fiber process | Critical | Open
557 | M557 | 2024-02-13 | Security | RMC meeting | Introduce the approach for Bulk Feasibility | Critical | Open
558 | M558 | 2024-02-13 | Security | RMC meeting | Capture and demonstrate BSS integration with Bill Desk | Critical | Open
559 | M559 | 2024-02-13 | Security | RMC meeting | Ensure all 29 BSNL locations are loaded for lead to order presentation | Critical | Open
560 | M560 | 2024-02-13 | Security | RMC meeting | Finalize GI-BB timeline | Critical | Open
561 | M561 | 2024-02-13 | Security | RMC meeting | Finalize T-Cell timeline | Critical | Open
562 | M562 | 2024-02-13 | Security | RMC meeting | Make user access control to convert from RFO to RFS | Critical | Open
563 | M563 | 2024-02-13 | Security | RMC meeting | Revisit the actual requirements of SSL certifications and implementation policies | Critical | Open
564 | M564 | 2024-02-13 | Security | RMC meeting | Submit a document with details on implementing the suggested process changes | Critical | Open
565 | M565 | 2024-02-13 | Security | RMC meeting | Develop a standard training program followed by quizzes for improving security | Critical | Open
566 | M566 | 2024-02-13 | Security | RMC meeting | Start a weekly security bulletin | Critical | Open
567 | M567 | 2024-02-13 | Security | RMC meeting | Study the best practices of the State Security Operations Center and implement them | Critical | Open
603 | M603 | 2023-07-03 | Security | Safety | ERT and mock drills | Critical | Open
604 | M604 | 2023-07-03 | Security | Internal Security | Gate pass for materials | Critical | Open
607 | M607 | 2023-07-03 | Security | Safety | Training | Critical | Open
608 | M608 | 2023-07-03 | Security | Internal Security | Assest Management | Critical | Open
609 | M609 | 2023-07-03 | Security | Internal Security | Crytography | Critical | Open
610 | M610 | 2023-07-03 | Security | Internal Security | Access control | Critical | Open
654 | M654 | 2023-07-05 | Security | Full NOC Readiness | Still update on the perceived firewall limitation issue is pending , asked on 3rd April'24 | Critical | Open
676 | M676 | 2023-07-21 | Security | Compliance | Security and Compliance: L&T to address critical security-related activities for launch and regulatory compliances with specific target dates . | Critical | Open
740 | M740 | 2023-08-18 | Security | Compliance | Security Related Activities: L&T to address various security and compliance sub-activities with specific target dates. | Critical | Open
791 | M791 | 2023-09-08 | Security | Compliance | Risk Assessment: VP-Program emphasized the need for a Risk register with a responsible SPOC and response plan. | Critical | Open
793 | M793 | 2023-09-08 | Security | Compliance | Security Related Activities: Director-P&E, T-Fiber stressed the importance of security activities for launch and regulatory compliances. | Critical | Open
794 | M794 | 2023-09-08 | Security | Compliance | Security and Compliance Sub-Activities: L&T to address various security and compliance sub-activities with specific target dates ranging from 31st August to 15th September '23. | Critical | Open
795 | M795 | 2023-09-08 | Security | Compliance | Alepo AAA and TACACS Integration: Alepo to test integration with Nokia and Ciena nodes on TACACS with supporting artefacts of testing. | Critical | Open
796 | M796 | 2023-09-08 | Security | Compliance | OSS Firewall Ports: L&T to address OSS firewall ports required for security compliance. | Critical | Open
797 | M797 | 2023-09-08 | Security | Compliance | Security LLD: Customer requested a complete Security LLD that outlines the security architecture and interactions between security products. | Critical | Open
798 | M798 | 2023-09-08 | Security | Compliance | External Audit and VAPT: L&T to conduct external audits and vulnerability assessments for applications and network elements. | Critical | Open
851 | M851 | 2023-11-28 | Security | Compliance | Regulatory and Security Requirements: L&T to fast-track the closure of regulatory and security requirements, along with SLA monitoring for the immediate start of business services. | Critical | Open
853 | M853 | 2023-12-12 | Security | Compliance | Complete configuration of CA signed SSL certificate for all web-based applications | Critical | Open
854 | M854 | 2023-12-12 | Security | Compliance | Obtain T-Fiber’s approval for annual external VAPT testing | Critical | Open
855 | M855 | 2023-12-12 | Security | Compliance | Submit Vulnerability Management Policy as part of Patch Management Policy | Critical | Open
856 | M856 | 2023-12-12 | Security | Compliance | Submit a list of Security Policy documents and all SOPs, Checklist | Critical | Open
857 | M857 | 2023-12-12 | Security | Compliance | Deliver security policy documents and SOPs for launch | Critical | Open
858 | M858 | 2023-12-12 | Security | Compliance | Upload RMC MoMs to shared folder and grant access to T-Fiber | Critical | Open
859 | M859 | 2023-12-12 | Security | Compliance | Provide comments against each sub-point in Internal Audit Report | Critical | Open
860 | M860 | 2023-12-12 | Security | Compliance | Submit Asset Management policy | Critical | Open
861 | M861 | 2023-12-12 | Security | Compliance | Submit onboarding/offboarding policy | Critical | Open
862 | M862 | 2023-12-12 | Security | Compliance | Report on the management of physical and environmental security | Critical | Open
863 | M863 | 2023-12-12 | Security | Compliance | Provide review of work scope for External VAPT prior | Critical | Open
864 | M864 | 2023-12-12 | Security | Compliance | Close Vulnerability & patch management after audit document is finalized | Critical | Open
865 | M865 | 2023-12-12 | Security | Compliance | Submit Cryptography encryption model document | Critical | Open
867 | M867 | 2023-12-12 | Security | Compliance | Provide compliance with supporting documents for all applications & devices | Critical | Open
868 | M868 | 2023-12-12 | Security | Compliance | Submit document on Privilege management | Critical | Open
869 | M869 | 2023-12-12 | Security | Compliance | Submit a password management policy for the entire Network | Critical | Open
870 | M870 | 2023-12-12 | Security | Compliance | Disable all Remote access | Critical | Open
871 | M871 | 2023-12-12 | Security | Compliance | Submit artefacts for all banners | Critical | Open
872 | M872 | 2023-12-12 | Security | Compliance | Submit checklist of internal/external, Trusted, untrusted zones | Critical | Open
873 | M873 | 2023-12-12 | Security | Compliance | Submit details of the policies for DMZ and internet-facing interfaces | Critical | Open
874 | M874 | 2023-12-12 | Security | Compliance | Re-audit of Section 4.8 with the response captured in 4 sub-points | Critical | Open
875 | M875 | 2023-12-12 | Security | Compliance | Submit list of APIs for all applications with risk information & conduct detailed audit on API security | Critical | Open
876 | M876 | 2023-12-12 | Security | Compliance | Submit Security Endpoints List of Infrastructure, Workstations, etc. | Critical | Open
878 | M878 | 2023-12-12 | Security | Compliance | Submit DR reports for all Applications that have been tested for DC-DR switchover | Critical | Open
879 | M879 | 2023-12-12 | Security | Compliance | Submit attendance list for security awareness trainings, ensure all NOC resources attend | Critical | Open
1013 | M1013 | 2024-02-13 | Security | Compliance | Matter of security for personnel access | Critical | Open
1014 | M1014 | 2024-02-13 | Security | Compliance | Incomplete detailing in security report | Critical | Open
1018 | M1018 | 2024-02-13 | Security | Compliance | Inquiry on DMZ details | Critical | Open
1019 | M1019 | 2024-02-13 | Security | Compliance | Status of leave and potential impacts | Critical | Open
1020 | M1020 | 2024-02-13 | Security | Compliance | Directive for approval and proper usage of tool services and resources | Critical | Open
1029 | M1029 | 2024-02-16 | Security | Compliance | Asset management and data classification | Critical | Open
1130 | M1130 | 2024-06-28 | Security | Compliance | L&T Security Teams & Technical Head to resolve login issues for Pkg B & C teams by the end of the next week. | Critical | Open
1131 | M1131 | 2024-06-28 | Security | Compliance | L&T OSS SME to provide updates on the PMS issue with the secondary database after consultation with the OEM. | Critical | Open
1132 | M1132 | 2024-06-28 | Security | Compliance | L&T to work with the vendor to define a solution for integrating AD with Alepo AAA. | Critical | Open
1133 | M1133 | 2024-06-28 | Security | Compliance | GPON SME to discuss with OEM and understand the reporting for categorizing users in EMS & AMS systems. | Critical | Open
1134 | M1134 | 2024-06-28 | Security | Compliance | L&T Security team & DC infra team to complete the RBAC list updates with domain-wise user information. | Critical | Closed
1135 | M1135 | 2024-06-28 | Security | Compliance | AD not integrating with Alepo AAA. | Critical | Open
1136 | M1136 | 2024-06-28 | Security | Compliance | Local users not removed in EMS, AMS, etc., and not verified through AD/Alepo AAA. | Critical | Open
1137 | M1137 | 2024-06-28 | Security | Compliance | Cisco EPNM has two separate profiles for a single user after login through TACACS, which needs resolution. | Critical | Open
1138 | M1138 | 2024-06-28 | Security | Compliance | L&T does not have HPE Admin access and is missing some OT systems in OSS. | Critical | Open
1139 | M1139 | 2024-06-28 | Security | Compliance | ISE HA DC to DR not working due to pending ISE software upgrade. | Critical | Open
1140 | M1140 | 2024-06-28 | Security | Compliance | L&T to share user details with Ravi for reconciliation in RBAC worksheets. | Critical | Open
1141 | M1141 | 2024-06-28 | Security | Compliance | L&T to ensure all users are domain verified through AD/Alepo AAA and remove local users. | Critical | Open
1142 | M1142 | 2024-06-28 | Security | Compliance | L&T to follow a consistent format for user IDs across all domains. | Critical | Open
1143 | M1143 | 2024-06-28 | Security | Compliance | L&T OSS SME to initiate communication with OEMs for admin user control access. | Critical | Open
1144 | M1144 | 2024-06-28 | Security | Compliance | L&T to prepare a checklist, test user access domain-wise, and create users based on necessary approvals. | Critical | Open
1145 | M1145 | 2024-06-28 | Security | Compliance | L&T to rebuild CSM with necessary resources (storage) as a long-term solution. | Critical | Open
1146 | M1146 | 2024-06-28 | Security | Compliance | Mark Mr. Sandeep in any escalation emails for pending issues with L&T. | Critical | Open
12 | M12 | 2023-04-03 | Test Lab | T&D Environment | Test Lab Setup Equipments and Plan | NON-Critical | Open
243 | M243 | 2023-09-26 | Test Lab | T&D Environment | Provide details on the completion status of test and development of systems. | NON-Critical | Open
247 | M247 | 2023-09-26 | Test Lab | T&D Environment | Clarify constraints related to infra upgradation for testing & development. | NON-Critical | Open
681 | M681 | 2023-07-21 | Test Lab | Testing Environment | Separation of T&D and Production Environments: L&T to provide a plan addressing the requirement for separate environments . | NON-Critical | Open
785 | M785 | 2023-09-08 | Test Lab | Testing Environment | BSS T&D license to be accessible by 30/6/23. It will be moved to a production environment afterward. | NON-Critical | Open
819 | M819 | 2023-09-26 | Test Lab | T&D Environment | Implementation of Test and Development environment. | NON-Critical | Open
820 | M820 | 2023-09-26 | Test Lab | T&D Environment | Discussion on the requirements for Test Lab/Staging environment. | NON-Critical | Open
73 | M73 | 2023-07-26 | WFM | User Experience | Support for translation to Telugu | Critical | Open
74 | M74 | 2023-07-26 | WFM | Handbook & SOPs | Scope of Order Processing and Service Ticket Management | Critical | Open
75 | M75 | 2023-07-26 | WFM | Handbook & SOPs | Document references in SOW to be shared | Critical | Open
76 | M76 | 2023-07-26 | WFM | User Experience | WFM tool's own Google Map | Critical | Open
77 | M77 | 2023-07-26 | WFM | Improvement | Support for Re-assignment of workflow in case of leave | Critical | Open
78 | M78 | 2023-07-26 | WFM | Improvement | Support for pre-defined routes | Critical | Open
79 | M79 | 2023-07-26 | WFM | User Experience | Support for recording timeclocks of patrol routes | Critical | Open
80 | M80 | 2023-07-26 | WFM | User Experience | Support for Barcode and QR code scanning | Critical | Open
81 | M81 | 2023-07-26 | WFM | Handbook & SOPs | Confirmation of SOW addressing Packages B and C | Critical | Open
82 | M82 | 2023-07-26 | WFM | User Experience | Clear definition and availability of existing filters in WFM dashboards | Critical | Open
83 | M83 | 2023-07-26 | WFM | User Experience | Upload of video | Critical | Open
84 | M84 | 2023-07-26 | WFM | Dashboards | Support for Workforce Management productivity statistics | Critical | Open
85 | M85 | 2023-07-26 | WFM | Improvement | Check if NOC Workforce Management is handled by the proposed WFM tool | Critical | Open
86 | M86 | 2023-07-26 | WFM | Improvement | Coverage of Planned Event Manpower assignment by WFM solution | Critical | Open
87 | M87 | 2023-07-26 | WFM | Handbook & SOPs | Overall fitment of WFM in E2E applications architecture with integration touchpoints highlighted, along with the WFM flows | Critical | Open
88 | M88 | 2023-07-26 | WFM | Handbook & SOPs | Clarity required on the scope of WFM under Phase-2 and sharing of Phase-1 & 2 scope with T-Fiber | Critical | Open
89 | M89 | 2023-07-26 | WFM | Integration | Integration with Material Management systems, ERP systems, and On-Demand dashboards to be covered in Phase-2 | Critical | Open
90 | M90 | 2023-07-26 | WFM | Improvement | Proposed WFM solution support field personnel to schedule appointments with end customers | Critical | Open
91 | M91 | 2023-07-26 | WFM | Handbook & SOPs | Finalization of Operational Processes linked to WFM workflows | Critical | Open
92 | M92 | 2023-07-26 | WFM | Resource Related | Perpetual licenses for WFM | Critical | Open
93 | M93 | 2023-07-26 | WFM | Handbook & SOPs | To check for potential overlapping functions between proposed WFM app and GIS O&M app, and accordingly streamline the Operational process | Critical | Open
94 | M94 | 2023-07-26 | WFM | Improvement | Manual overwrite of data | Critical | Open
95 | M95 | 2023-07-26 | WFM | User Experience | Verification process for checking whether the field technician has gone to the required location or not. | Critical | Open
245 | M245 | 2023-09-26 | WFM | WFM Application | Clarify the distinction between smart app and WFM. | Critical | Open
537 | M537 | 2024-01-25 | WFM | WFM Application | Complete the WFM-OSS integration | Critical | Open
538 | M538 | 2024-01-25 | WFM | WFM Application | Understand use cases of WFM integration with BSS | Critical | Open
539 | M539 | 2024-01-25 | WFM | WFM Application | Define authorization of PoP RFS criteria for approval | Critical | Open
540 | M540 | 2024-01-25 | WFM | WFM Application | Complete Fault Management and Trouble Ticketing assignment (OSS to WFM) | Critical | Open
541 | M541 | 2024-01-25 | WFM | WFM Application | Distinguish between the use of GIS mobile app and WFM mobile app | Critical | Open
542 | M542 | 2024-01-25 | WFM | WFM Application | Submit the NDA signed between L&T and M/S Lepton | Critical | Open
543 | M543 | 2024-01-25 | WFM | WFM Application | Submit sample reports and dashboards of WFM package | Critical | Open
544 | M544 | 2024-01-25 | WFM | WFM Application | Verify proposed solution for WFM | Critical | Open
545 | M545 | 2024-01-25 | WFM | WFM Application | Dry run and operationalize three routes for testing WFM with actual data | Critical | Open
546 | M546 | 2024-01-25 | WFM | WFM Application | Conduct weekly training sessions for patrollers on WFM app | Critical | Open
547 | M547 | 2024-01-25 | WFM | WFM Application | Check and confirm the watermarking feature on photos taken by field users | Critical | Open
628 | M628 | 2023-07-04 | WFM | Mobile Applications | Develop and present mobile applications that are functional and meet the needs and preferences of users by 15th August '23. | Critical | Open
674 | M674 | 2023-07-21 | WFM |  | WFM Integration: L&T commenced WFM integration and will arrange a demonstration for field operations . | Critical | Open
679 | M679 | 2023-07-21 | WFM |  | Mobile App & WFM: SVP, T-Fiber requested clarity on the number of mobile apps and urged L&T to freeze the scope in consultation with MSI B and C. Demo with M/S Lepton scheduled for 21st June '23 . | Critical | Open
689 | M689 | 2023-07-26 | WFM |  | Finalise and share the scope of work (SOW) for Work Force Management solution implementation with M/S Lepton. | Critical | Open
690 | M690 | 2023-07-26 | WFM |  | Support for translation to Telugu to be checked with M/S Lepton. | Critical | Open
691 | M691 | 2023-07-26 | WFM |  | Clarity on the term “As-is solution to be deployed” under Order Management is to be provided. | Critical | Open
692 | M692 | 2023-07-26 | WFM |  | Support for Barcode scanning as well as QR code scanning to be checked with M/S Lepton. | Critical | Open
694 | M694 | 2023-07-26 | WFM |  | Receive clarification on the support for re-assignment of workflow in case a Field Technician is on leave. | Critical | Open
695 | M695 | 2023-07-26 | WFM |  | Verify processes for recording of timelocks of patrol routes. | Critical | Open
696 | M696 | 2023-07-26 | WFM |  | Improve the clarity, definition, and availability of existing filters in WFM dashboards. | Critical | Open
697 | M697 | 2023-07-26 | WFM |  | Video upload support. | Critical | Open
698 | M698 | 2023-07-26 | WFM |  | Support for Workforce Management productivity statistics mentioned that this shall fall under the customisation scope. | Critical | Open
699 | M699 | 2023-07-26 | WFM |  | Coordination required with NOC, Operations, and Projects team of 3 MSIs for the WFM Demo of 3 Packages including BSS-SME- L&T. | Critical | Open
700 | M700 | 2023-07-26 | WFM |  | Asses if NOC Work Force Management is handled by the proposed WFM tool | Critical | Open
701 | M701 | 2023-07-26 | WFM |  | Samples or actual reports and dashboards based on operational processes to be presented by 28th July’23. | Critical | Open
702 | M702 | 2023-07-26 | WFM |  | Assessment to ensure that planned Event Manpower assignment is covered by the WFM solution. | Critical | Open
703 | M703 | 2023-07-26 | WFM |  | Assessment about whether the proposed WFM solution supports field personnel to schedule appointments with end customers. | Critical | Open
704 | M704 | 2023-07-26 | WFM |  | Ensure the licenses for WFM are perpetual. | Critical | Open
738 | M738 | 2023-08-18 | WFM | WFM Application | WFM Tool Usage Demonstration: L&T to arrange a demonstration of WFM tool usage for field operations soon. | Critical | Open
762 | M762 | 2023-08-23 | WFM |  | Respond to the query of WFM integration. | Critical | Open
774 | M774 | 2023-08-31 | WFM |  | Schedule WFM integration with BSS demo for 15th September '23. | Critical | Open
799 | M799 | 2023-09-12 | WFM |  | L&T is to submit a proposal to T-Fiber on the scope to be showcased in the proposed WFM-BSS demonstration. | Critical | Open
800 | M800 | 2023-09-12 | WFM |  | L&T is to identify a product owner for WFM. | Critical | Open
881 | M881 | 2023-12-15 | WFM |  | WFM Tool Demonstration: L&T to arrange a demonstration of the WFM tool usage for field operations soon. | Critical | Open
882 | M882 | 2023-12-15 | WFM |  | WFM Mobile App Features: L&T to provide clarity on GPS tracking availability, polling frequency, photo upload feature, file size limitations, and supported Android and iOS versions. | Critical | Open
883 | M883 | 2023-12-15 | WFM |  | Offline Data Storage: L&T to address the lack of offline data storage feature in the mobile application. | Critical | Open
884 | M884 | 2023-12-15 | WFM |  | Workflow Simulation: L&T to simulate a fiber cut and explain the workflow for clearing the fault and updating GIS. | Critical | Open
885 | M885 | 2023-12-15 | WFM |  | Security Assurance: L&T to provide the NDA signed with M/S Lepton, assure API security, and share the contract copy. | Critical | Open
887 | M887 | 2023-12-15 | WFM | GIS Completion | Ticket Allocation: L&T to start manual ticket allocation and freeze the process for node and link ticket allocation. | Critical | Open
889 | M889 | 2023-12-15 | WFM |  | Summary Dashboards/Management Reports: L&T to provide inputs based on Operations best practices for weekly/monthly management reports from the WFM package. | Critical | Open
890 | M890 | 2023-12-15 | WFM |  | The urgency for L&T to demonstrate the WFM tool for field operations and to provide detailed information on its features and capabilities. | Critical | Open
891 | M891 | 2023-12-15 | WFM |  | The necessity for L&T to address the absence of offline data storage in the mobile application and to simulate a fiber cut workflow. | Critical | Open
892 | M892 | 2023-12-15 | WFM |  | The requirement for L&T to assure security in the WFM package, including API security and geo-fencing capabilities. | Critical | Open
893 | M893 | 2023-12-15 | WFM |  | The expectation for L&T to provide comprehensive management reports and dashboards to support process improvements and operational efficiency. | Critical | Open
903 | M903 | 2023-12-19 | WFM |  | Mobile App & WFM: SVP, T-Fiber requested clarity on the number of mobile apps and urged L&T to freeze the scope in consultation with MSI B and C. Demo with M/S Lepton scheduled for 21st June '23. | Critical | Open
1000 | M1000 | 2024-01-25 | WFM |  | Adopt WFM by packages B & C and procure licenses | Critical | Open
1038 | M1038 | 2024-03-14 | WFM |  | Ensuring readiness of WFM integration, order fulfillment, service provisioning, and NOC critical points closure. | Critical | Open
1048 | M1048 | 2024-03-14 | WFM |  | L&T to be prepared for the demonstration of WFM for order fulfillment/service provisioning. | Critical | Open
772 | M772 | 2023-08-31 | WhatsApp |  | List pending action items from T-Fiber; SSL certificate and WhatsApp Integration expected closure in 2-3 days. | NON-Critical | Open
910 | M910 | 2023-12-19 | WhatsApp |  | WhatsApp Integration: BSS-SME, L&T to incorporate advanced features into WhatsApp Integration with CSP. | NON-Critical | Open

## Sheet2 (hidden)
Row Labels | Count of Unique ID
CLOSURE REVIEW PENDING | 18
COMPLETED & APPROVED | 252
DEPENDENCY(Client/Ext.) | 87
REOPENED | 10
WIP | 105
Grand Total | 472

## 472-Points (hidden)
S.No | Unique ID | Domain | Sub Domain | Type | Description of the Activity | SME | Owner of the Task | Dependency ON | Management Status | Remarks- (Progress /MoM RFP Ask/MoM not in RFP/MoM points with interpretation of RFP) | Target Date to close the task | Action Plan | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | TargetWeek | Artefacts against completion | pp | Approved By | Approved Date | Remarks
163 | T348 | TNOC-Ops | NOC Operation |  | Placement of T-Fiber logo and Telangana State emblem in TNOC reception area | Ahmad |  | TFIBER | DEPENDENCY(Client/Ext.) | 05May: Sanjay Ji asked for New Logo incorporation in submitted Options and resubmission to be done. Gaurav taking up with Sekhar for this. 12May: Sekhar trying to onboard Tfiber contract who did work at TFiber office, within 1 week Sekhar will try to onboard vender. And then another 3 week for deployment at TNOC 24May: Sekhar shared vendor details to Gaurav. Work in progress. 18Jun: Logo design submitted by Vendor/Gaurav. 25Jun: Revised Logo design recieved and submitted to TFiber for choosing design options. Post design selection by Tfiber, will process for PO/execution 28Jun: TFiber to confirm on way forward. Will check internally on this and confirm back. 10Aug25: Designed for reception wall finalised. Also quotation sought by customer for main gate, DC gate, reception table, Electric Room, DG Bay for taking it forward | 2025-07-23 | 1. Post design approval, vendor will be aligned for execution | [10 empty] | 1 | [7 empty] | #REF!
164 | T350 | TNOC-Ops | NOC Operation |  | Manpower Structure for TNOC Operationalization | Ahmad |  |  | COMPLETED & APPROVED |  |  |  | 1 | [18 empty] | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\T166 |  | AD-UT-Tfiber | 2025-05-13
165 | T354 | TNOC-Ops | NOC Operation |  | Resource deployment at TNOC | Ahmad |  |  | COMPLETED & APPROVED |  |  |  | 1 | [18 empty] | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\T166 |  | AD-UT-Tfiber | 2025-05-13
166 | T355 | TNOC-Ops | NOC Operation |  | Interlocking and Interdependencies with resources of package B & C operating at TNOC | Ahmad |  |  | COMPLETED & APPROVED | [5 empty] | 1 | [16 empty] | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\T166 |  | Mr Sanjay Kaligotla | 2025-05-26
168 | T357 | TNOC-Ops | NOC Operation |  | Spare for Business continuity - RS&R for NOC and DR elements and assets | Ahmad |  | Sekhar | WIP | 05May: Discussed with Sanjay & RK Ji. For DC nodes, minumum 2% spares to be placed at NOC irrespective of HA configs at DC nodes. Next Busines Day spare clauses not acceptable. Sekhar/Ravi to Order cards/SFPs and patch cords, tools, etc as per list shared 12May: Sekhar update: Sekhar have submitted LOI/contracts copies with TFiber Contract team. This arrangement is as per those contracts. 27May: TFiber asking for 2% spare availabiltiy at TNOC. Sekhar to revert on this.. repeated followups down 25Jun25: Consumables & Spare ordering WIP (list provided to Sekhar in May25) 03Jul25: Clarity shall come in next 2-3 days. 21Aug25: In progress | 2025-08-27 | [16 empty] | 1 |  |  | #REF!
83 | T205 | A&O Solution | Installation |  | Installation of NSO Applications | Jayant Madavi |  | Alternate OEM Solution | DEPENDENCY(Client/Ext.) | Post 24.06.25 review and direction, working for a alternate options for NSO. will come back as earliest with closure plan. | [20 empty] | #N/A
84 | T206 | A&O Solution | Integration |  | Integration with Third Party Applications/Nodes | Jayant Madavi |  | Alternate OEM Solution | DEPENDENCY(Client/Ext.) | Post 24.06.25 review and direction, working for a alternate options for NSO. will come back as earliest with closure plan. | [20 empty] | #N/A
85 | T207 | A&O Solution | Integration |  | OSS | Jayant Madavi |  | Alternate OEM Solution | DEPENDENCY(Client/Ext.) | Post 24.06.25 review and direction, working for a alternate options for NSO. will come back as earliest with closure plan. | [20 empty] | #N/A
86 | T208 | A&O Solution | Integration |  | BSS | Jayant Madavi |  | Alternate OEM Solution | DEPENDENCY(Client/Ext.) | Post 24.06.25 review and direction, working for a alternate options for NSO. will come back as earliest with closure plan. | [20 empty] | #N/A
87 | T209 | A&O Solution | Integration |  | Nodes | Jayant Madavi |  | Alternate OEM Solution | DEPENDENCY(Client/Ext.) | Post 24.06.25 review and direction, working for a alternate options for NSO. will come back as earliest with closure plan. | [20 empty] | #N/A
88 | T210 | A&O Solution | Integration |  | EMS-GPON | Jayant Madavi |  | Alternate OEM Solution | DEPENDENCY(Client/Ext.) | Post 24.06.25 review and direction, working for a alternate options for NSO. will come back as earliest with closure plan. | [20 empty] | #N/A
89 | T211 | A&O Solution | Integration |  | EMS-DWDM | Jayant Madavi |  | Alternate OEM Solution | DEPENDENCY(Client/Ext.) | Post 24.06.25 review and direction, working for a alternate options for NSO. will come back as earliest with closure plan. | [20 empty] | #N/A
141 | T217 | A&O Solution | MoM Action |  | Cisco NSO to test all the cisco elements including SG350 Horizontal switch to deliver service | Jayant Madavi |  | Alternate OEM Solution | DEPENDENCY(Client/Ext.) | Post 24.06.25 review and direction, working for a alternate options for NSO. will come back as earliest with closure plan. | [20 empty] | #N/A
142 | T220 | A&O Solution | MoM Action |  | T-Cell Service definition sign off | Jayant Madavi |  | Alternate OEM Solution | DEPENDENCY(Client/Ext.) | Post 24.06.25 review and direction, working for a alternate options for NSO. will come back as earliest with closure plan. | [20 empty] | #N/A
143 | T222 | A&O Solution | MoM Action |  | Tejas NED readiness | Jayant Madavi |  | Alternate OEM Solution | DEPENDENCY(Client/Ext.) | Post 24.06.25 review and direction, working for a alternate options for NSO. will come back as earliest with closure plan. | [20 empty] | #N/A
204 | T195 | IPMPLS | Service Provisioning |  | Service Provisioning PoC for SCCM/NSO - L2, L3 VPN | Jayant Madavi |  | Alternate OEM Solution | DEPENDENCY(Client/Ext.) | Post 24.06.25 review and direction, working for a alternate options for NSO. will come back as earliest with closure plan. | [20 empty] | #N/A
205 | T196 | IPMPLS | Service Provisioning |  | Service Provisioning PoC for SCCM/NSO - QoS (all scenarios) | Jayant Madavi |  | Alternate OEM Solution | DEPENDENCY(Client/Ext.) | Post 24.06.25 review and direction, working for a alternate options for NSO. will come back as earliest with closure plan. | [20 empty] | #N/A
206 | T197 | IPMPLS | Service Provisioning |  | Service Provisioning PoC for SCCM/NSO - MVPN (all scenarios) | Jayant Madavi |  | Alternate OEM Solution | DEPENDENCY(Client/Ext.) | Post 24.06.25 review and direction, working for a alternate options for NSO. will come back as earliest with closure plan. | [20 empty] | #N/A
271 | T212 | A&O Solution | Development and unit testing |  | Service verification and provisioning - IP MPLS | Jayant Madavi |  | Alternate OEM Solution | DEPENDENCY(Client/Ext.) | Post 24.06.25 review and direction, working for a alternate options for NSO. will come back as earliest with closure plan. | [20 empty] | #N/A
272 | T213 | A&O Solution | Development and unit testing |  | Service verification and activation - GPON Nokia and Tejas | Jayant Madavi |  | Alternate OEM Solution | DEPENDENCY(Client/Ext.) | Post 24.06.25 review and direction, working for a alternate options for NSO. will come back as earliest with closure plan. | [20 empty] | #N/A
273 | T214 | A&O Solution | Development and unit testing |  | SCCM provisioning request for HSI, IPTV, T-Wire,T-VPN,VoIP,CCTV SDD | Jayant Madavi |  | Alternate OEM Solution | DEPENDENCY(Client/Ext.) | Post 24.06.25 review and direction, working for a alternate options for NSO. will come back as earliest with closure plan. | [20 empty] | #N/A
274 | T215 | A&O Solution | Development and unit testing |  | NSO module final implementation | Jayant Madavi |  | Alternate OEM Solution | DEPENDENCY(Client/Ext.) | Post 24.06.25 review and direction, working for a alternate options for NSO. will come back as earliest with closure plan. | [20 empty] | #N/A
275 | T216 | A&O Solution | Integration |  | NSO integration with SCCM | Jayant Madavi |  | Alternate OEM Solution | DEPENDENCY(Client/Ext.) | Post 24.06.25 review and direction, working for a alternate options for NSO. will come back as earliest with closure plan. | [20 empty] | #N/A
294 | T308 | Security | IPDR |  | Developing in-house solution, also exploring with external vendors. 3 vendors declined. | Jayant Madavi |  |  | WIP | 27.06.25 , IPDR solution operational , pending document will be submitted by 1st week of Jul'25 | [10 empty] | 1 | [9 empty] | #REF!
305 | T373 | A&O Solution | Deployment and Installations |  | HSI (High Speed Internet to Household) implementation | Jayant Madavi |  | Alternate OEM Solution | DEPENDENCY(Client/Ext.) | Post 24.06.25 review and direction, working for a alternate options for NSO. will come back as earliest with closure plan. | [20 empty] | #N/A
306 | T374 | A&O Solution | Deployment and Installations |  | IPTV to Household implementation | Jayant Madavi |  | Alternate OEM Solution | DEPENDENCY(Client/Ext.) | Post 24.06.25 review and direction, working for a alternate options for NSO. will come back as earliest with closure plan. | [20 empty] | #N/A
307 | T375 | A&O Solution | Deployment and Installations |  | VOIP to Household implementation | Jayant Madavi |  | Alternate OEM Solution | DEPENDENCY(Client/Ext.) | Post 24.06.25 review and direction, working for a alternate options for NSO. will come back as earliest with closure plan. | [20 empty] | #N/A
309 | T377 | A&O Solution | Deployment and Installations |  | CCTV Unicast implementation | Jayant Madavi |  | Alternate OEM Solution | DEPENDENCY(Client/Ext.) | Post 24.06.25 review and direction, working for a alternate options for NSO. will come back as earliest with closure plan. | [20 empty] | #N/A
310 | T378 | A&O Solution | Deployment and Installations |  | CCTV Multicast implementation | Jayant Madavi |  | Alternate OEM Solution | DEPENDENCY(Client/Ext.) | Post 24.06.25 review and direction, working for a alternate options for NSO. will come back as earliest with closure plan. | [20 empty] | #N/A
312 | T380 | A&O Solution | Deployment and Installations |  | Dhanush Telemedicine Application implementation | Jayant Madavi |  | TFIBER | DEPENDENCY(Client/Ext.) | Post 24.06.25 review and direction, working for a alternate options for NSO. will come back as earliest with closure plan. | [20 empty] | #N/A
313 | T381 | A&O Solution | Deployment and Installations |  | SDC content to Household and GI implementation | Jayant Madavi |  | TFIBER | DEPENDENCY(Client/Ext.) | Post 24.06.25 review and direction, working for a alternate options for NSO. will come back as earliest with closure plan. | [20 empty] | #N/A
325 | T218 | A&O Solution | MoM Action |  | NSO LLD | Jayant Madavi |  | Alternate OEM Solution | DEPENDENCY(Client/Ext.) | Post 24.06.25 review and direction, working for a alternate options for NSO. will come back as earliest with closure plan. | [20 empty] | #N/A
326 | T219 | A&O Solution | MoM Action |  | Service catalog with product concept note for all services with target requirement date. | Jayant Madavi |  | TFIBER | DEPENDENCY(Client/Ext.) | Post 24.06.25 review and direction, working for a alternate options for NSO. will come back as earliest with closure plan. | [20 empty] | #N/A
327 | T223 | A&O Solution | MoM Action |  | IPTV tested needs to be finalised for additional configuration for multicast and tested as per lab availability and final sign off | Jayant Madavi |  | Alternate OEM Solution | DEPENDENCY(Client/Ext.) | Post 24.06.25 review and direction, working for a alternate options for NSO. will come back as earliest with closure plan. | [20 empty] | #N/A
328 | T224 | A&O Solution | MoM Action |  | BSS to provide actual feasibility parameters e.g PE port number(s) from OSS . Right now values are hard-coded . In turn OSS to get these details from GIS. We havent seen an e2e workign scenario on this yet. | Jayant Madavi |  | Alternate OEM Solution | DEPENDENCY(Client/Ext.) | Post 24.06.25 review and direction, working for a alternate options for NSO. will come back as earliest with closure plan. | [20 empty] | #N/A
384 | T221 | A&O Solution | MoM Action |  | MAG/GAC ports reservation feasibility for services booked in BSS with payments made | Jayant Madavi |  | Alternate OEM Solution | DEPENDENCY(Client/Ext.) | Post 24.06.25 review and direction, working for a alternate options for NSO. will come back as earliest with closure plan. | [20 empty] | #N/A
144 | T225 | A&O Solution | MoM Action |  | VLAN logic : Vlan logic for HSI-SVLAN has beed provided per zone information. But most of deployments are coming with vlan 256 of PIONEER for any service . This needs to be looked at. VLAN ID should be changed to as per plan shared by Aravindhan. | Jayant Madavi |  | Alternate OEM Solution | DEPENDENCY(Client/Ext.) | Post 24.06.25 review and direction, working for a alternate options for NSO. will come back as earliest with closure plan. | [20 empty] | #N/A
31 | T108 | GIS | Data gathering |  | Data Gathering for RFS Mandals | Kaushal |  | PKG A, B & C | COMPLETED & APPROVED | 21May: 255 mandals data uplaoded as per fiel AT progress. Balance to be done as per field AT status , no visibility for completion date from field | [12 empty] | 1 | [8 empty] | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T108 |  | Approval Email received from NOC Director & TPA | 2025-06-02
32 | T109 | GIS | Data gathering |  | Data Upload of RFS Mandals | Kaushal |  | PKG A, B & C | COMPLETED & APPROVED | 21May: 255 mandals data uplaoded as per fiel AT progress. Balance to be done as per field AT status , no visibility for completion date from field | [12 empty] | 1 | [8 empty] | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T109 |  | Approval Email received from NOC Director & TPA | 2025-06-02
33 | T110 | GIS | Basic Readiness |  | Each Package 5 Mandal (Total-15 Mandal) Upload | Kaushal |  |  | COMPLETED & APPROVED | [22 empty] | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T110 |  | Approval Email received from NOC Director & TPA | 2025-06-02
34 | T111 | GIS | Deployment |  | GIS Hardware & Software deployment at DC | Kaushal |  |  | COMPLETED & APPROVED | [22 empty] | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T111 |  | Approval Email received from NOC Director & TPA | 2025-06-02
35 | T112 | GIS | Deployment |  | High Availability & Load Balancer Testing | Kaushal |  |  | COMPLETED & APPROVED | Approved By TFIBER NOC AD |  | Approved By TFIBER NOC AD | [8 empty] | 1 | [9 empty] | #REF! | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T112 |  | Approved By TFIBER NOC AD | 2025-07-07 | Approved By TFIBER NOC AD
36 | T113 | GIS | Deployment |  | PCs & Licences (G-tech, DI, Geo Media) | Kaushal |  | TFIBER | CLOSURE REVIEW PENDING | Tool & PCs has been installed in NOC GIS room. for Licesnes dependecy on T FIber. During the meeting, the Managing Director of T-Fiber directed that only the minimum number of additional licenses will be procured, and T-Fiber will handle the procurement (Kaushal): Held discussions with Sanjay Sir and TPA at the NOC on 27 June 2025. A formal email requesting approval was also sent on same day waiting for approval ,I followed up four times, but have not received any update yet |  | T FIber to support for closure. | [14 empty] | 1 |  |  |  | 2025-09-30 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T113
37 | T114 | GIS | Deployment |  | G-Tech | Kaushal |  |  | COMPLETED & APPROVED | [21 empty] | 45882 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T114 |  | Approval Email received from NOC Director & TPA | 2025-06-02
38 | T115 | GIS | Deployment |  | Network Portal | Kaushal |  |  | COMPLETED & APPROVED | [21 empty] | 45882 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T115 |  | Approval Email received from NOC Director & TPA | 2025-06-02
39 | T116 | GIS | Deployment |  | Mobile App | Kaushal |  |  | COMPLETED & APPROVED | [21 empty] | 45882 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T116 |  | Approval Email received from NOC Director & TPA | 2025-06-02
40 | T117 | GIS | DC-DR |  | Requirement Vs Solution | Kaushal |  |  | COMPLETED & APPROVED | Completed & Approved by TNOC-AD |  | Completed & Approved by TNOC-AD | [11 empty] | 1 | [6 empty] | 2025-08-13 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T117 |  | Completed & Approved by TNOC-AD | 2025-07-09 | Completed & Approved by TNOC-AD
41 | T118 | GIS | DC-DR |  | DC-DR Testing | Kaushal |  |  | COMPLETED & APPROVED | Completed & Approved by TNOC-AD |  | Completed & Approved by TNOC-AD | [11 empty] | 1 | [6 empty] | 2025-08-13 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T118 |  | Completed & Approved by TNOC-AD | 2025-07-09 | Completed & Approved by TNOC-AD
42 | T119 | GIS | Basic Readiness |  | Google Map API configuration | Kaushal |  |  | COMPLETED & APPROVED | [22 empty] | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T119 |  | Approval Email received from NOC Director & TPA | 2025-06-02
43 | T120 | GIS | Basic Readiness |  | Fixing of telco Boundaries in GIS | Kaushal |  |  | COMPLETED & APPROVED | [22 empty] | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T120 |  | Approval Email received from NOC Director & TPA | 2025-06-02
44 | T121 | GIS | Basic Readiness |  | Data Model Optimization | Kaushal |  |  | COMPLETED & APPROVED | [22 empty] | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\ |  | Approval Email received from NOC Director & TPA | 2025-06-02
45 | T122 | GIS | Basic Readiness |  | ISP/OSP object modelling in tool as per T-Fibre | Kaushal |  |  | COMPLETED & APPROVED | [22 empty] | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T122 |  | Approval Email received from NOC Director & TPA | 2025-06-02
46 | T123 | GIS | Basic Readiness |  | Make & Model deployment against all object as per T-Fibre Project | Kaushal |  |  | COMPLETED & APPROVED | [22 empty] | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T123 |  | Approval Email received from NOC Director & TPA | 2025-06-02
47 | T124 | GIS | Basic Readiness |  | Device (Active/Passive) ( All Type as per T-Fibre Project) & Port Modelling In Tool | Kaushal |  |  | COMPLETED & APPROVED | [22 empty] | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\ |  | Approval Email received from NOC Director & TPA | 2025-06-02
48 | T125 | GIS | Basic Readiness |  | Correction In Fttx Network placement rules (GP To GI) | Kaushal |  |  | COMPLETED & APPROVED | [22 empty] | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\ |  | Approval Email received from NOC Director & TPA | 2025-06-02
49 | T126 | GIS | Basic Readiness |  | Fine tuning or Enable of Cart feature. ( Pan, Zoom, Vertex, Selection method, ruler Etc.) | Kaushal |  |  | COMPLETED & APPROVED | [22 empty] | D:\T-Fiber Project\Hexagon GIS\Artefacts Of T-NOC Tracker\T126 |  | Approval Email received from NOC Director & TPA | 2025-06-02
50 | T127 | GIS | Basic Readiness |  | Trace Feature ( Link/Spare/Topology) | Kaushal |  |  | COMPLETED & APPROVED | [22 empty] | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T127 |  | Approval Email received from NOC Director & TPA | 2025-06-02
51 | T128 | GIS | Basic Readiness |  | Reports (Fibre Utilisation, BOQ, Area selection, ISP/OSP Quantify) | Kaushal |  |  | COMPLETED & APPROVED | [22 empty] | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T128 |  | Approval Email received from NOC Director & TPA | 2025-06-02
52 | T129 | GIS | Basic Readiness |  | Document/Image Upload feature | Kaushal |  |  | COMPLETED & APPROVED | [22 empty] | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\ |  | Approval Email received from NOC Director & TPA | 2025-06-02
53 | T130 | GIS | Basic Readiness |  | Port level & Fibre stand lever attribute | Kaushal |  |  | COMPLETED & APPROVED | [22 empty] | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T130 |  | Approval Email received from NOC Director & TPA | 2025-06-02
54 | T131 | GIS | Basic Readiness |  | Topology Highlight feature | Kaushal |  |  | COMPLETED & APPROVED | [22 empty] | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T131 |  | Approval Email received from NOC Director & TPA | 2025-06-02
55 | T132 | GIS | Basic Readiness |  | Data Model G-TECH Alignment | Kaushal |  |  | COMPLETED & APPROVED | [22 empty] | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T132 |  | Approval Email received from NOC Director & TPA | 2025-06-02
56 | T133 | GIS | Basic Readiness |  | DI alignment as per new 35 Layer data model | Kaushal |  |  | COMPLETED & APPROVED | [22 empty] | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\ |  | Approval Email received from NOC Director & TPA | 2025-06-02
57 | T134 | GIS | Basic Readiness |  | Active to Passive, Active to active connectivity correction | Kaushal |  |  | COMPLETED & APPROVED | [22 empty] | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T134 |  | Approval Email received from NOC Director & TPA | 2025-06-02
58 | T135 | GIS | Basic Readiness |  | DI processing timing optimisation | Kaushal |  |  | COMPLETED & APPROVED | [22 empty] | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\ |  | Approval Email received from NOC Director & TPA | 2025-06-02
59 | T136 | GIS | Basic Readiness |  | Rack to Rack Connectivity | Kaushal |  |  | COMPLETED & APPROVED | [22 empty] | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T136 |  | Approval Email received from NOC Director & TPA | 2025-06-02
60 | T137 | GIS | Advance Readiness |  | Graphical Symbology deployment against all object | Kaushal |  |  | COMPLETED & APPROVED | [22 empty] | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T137 |  | Approval Email received from NOC Director & TPA | 2025-06-02
61 | T138 | GIS | Advance Readiness |  | Fixing Of Labelling (Sequencing & Attributes) | Kaushal |  |  | COMPLETED & APPROVED | [22 empty] | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T138 |  | Approval Email received from NOC Director & TPA | 2025-06-02
62 | T139 | GIS | Advance Readiness |  | Object search options to user | Kaushal |  |  | COMPLETED & APPROVED | [22 empty] | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T139 |  | Approval Email received from NOC Director & TPA | 2025-06-02
63 | T140 | GIS | Advance Readiness |  | G-tech to .shp & Kml conversion | Kaushal |  |  | COMPLETED & APPROVED | [22 empty] | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T140 |  | Approval Email received from NOC Director & TPA | 2025-06-02
64 | T141 | GIS | Advance Readiness |  | Plotting & Print Feature | Kaushal |  |  | COMPLETED & APPROVED | [22 empty] | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T141 |  | Approval Email received from NOC Director & TPA | 2025-06-02
65 | T142 | GIS | Advance Readiness |  | 4 More API from Google Map | Kaushal |  |  | COMPLETED & APPROVED | [22 empty] | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T142 |  | Approval Email received from NOC Director & TPA | 2025-06-02
66 | T143 | GIS | Advance Readiness |  | Fibre Utilisation Reports | Kaushal |  |  | COMPLETED & APPROVED | [22 empty] | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T143 |  | Approval Email received from NOC Director & TPA | 2025-06-02
67 | T144 | GIS | Advance Readiness |  | Consolidated reports from GIS | Kaushal |  |  | COMPLETED & APPROVED | [22 empty] | D:\T-Fiber Project\Hexagon GIS\Artefacts Of T-NOC Tracker\T144 |  | Approval Email received from NOC Director & TPA | 2025-06-02
68 | T145 | GIS | Advance Readiness |  | Link trace Reports | Kaushal |  |  | COMPLETED & APPROVED | [22 empty] | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T145 |  | Approval Email received from NOC Director & TPA | 2025-06-02
69 | T146 | GIS | Advance Readiness |  | Consolidation/Customization of Dashboard feature in G-tech, Network Portal | Kaushal |  |  | COMPLETED & APPROVED | [22 empty] | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T146 |  | Approval Email received from NOC Director & TPA | 2025-06-02
70 | T147 | GIS | Advance Readiness |  | Network data availability in G-Tech & Network portal & Geo media | Kaushal |  |  | COMPLETED & APPROVED | [22 empty] | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T147 |  | Approval Email received from NOC Director & TPA | 2025-06-02
71 | T148 | GIS | Advance Readiness |  | Final Demo to customer | Kaushal |  |  | COMPLETED & APPROVED | [22 empty] | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T148 |  | Approval Email received from NOC Director & TPA | 2025-06-02
72 | T149 | GIS | Mobile Applications |  | Network availability in Mobile application with G-MAP | Kaushal |  |  | COMPLETED & APPROVED | [22 empty] | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T149 |  | Approval Email received from NOC Director & TPA | 2025-06-02
73 | T150 | GIS | Mobile Applications |  | Red line, Red Point Feature deployment in Mobile application | Kaushal |  |  | COMPLETED & APPROVED | [22 empty] | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T150 |  | Approval Email received from NOC Director & TPA | 2025-06-02
74 | T151 | GIS | Mobile Applications |  | JOB creation testing in GIS tool from GIS Mobile app | Kaushal |  |  | COMPLETED & APPROVED | [22 empty] | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T151 |  | Approval Email received from NOC Director & TPA | 2025-06-02
75 | T152 | GIS | Design & Documentation |  | Feasible Points closure of workshop | Kaushal |  |  | COMPLETED & APPROVED | [22 empty] | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T152 |  | Approval Email received from NOC Director & TPA | 2025-06-02
76 | T154 | GIS | Data gathering |  | T-NOC Creation in GIS Tool with connectivity | Kaushal |  |  | COMPLETED & APPROVED | [22 empty] | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T154 |  | Approval Email received from NOC Director & TPA | 2025-06-02
77 | T155 | GIS | Design & Documentation |  | SOP Creation | Kaushal |  |  | COMPLETED & APPROVED | [22 empty] | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T155 |  | Approval Email received from NOC Director & TPA | 2025-06-02
78 | T161 | GIS | Integration |  | Auto feasibility | Kaushal |  | OSS+BSS | CLOSURE REVIEW PENDING | BSS(knot) has demonstrated the Auto Feasibility feature for single location business cases. If, Customer is expecting Bulk feasibility capabilities, which is not a feature of GIS, required external tool., 11 Aug. 25:- Need To Provide Demo To Customer (Dhanjay Sir & Sanjay Sir), Required to align BSS & OSS team. |  | T FIber to procure tool for bulk feasibility, if needed. |  |  |  |  | 0.2 | [10 empty] | 1 |  |  | 2025-09-30 | Multiple demonstrations were provided to showcase auto-feasibility during the GIBB demo
138 | T156 | GIS | MoM Action |  | MB kilometers vs UG and arial to path and over all route length to be added in webapplication | Kaushal |  |  | COMPLETED & APPROVED | [22 empty] | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T156 |  | Approval Email received from NOC Director & TPA | 2025-06-02
139 | T157 | GIS | MoM Action |  | 3 Formats of Lat long (DMS, DMM & Mtr) required in Hexagon tool | Kaushal |  |  | COMPLETED & APPROVED | [22 empty] | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T157 |  | Approval Email received from NOC Director & TPA | 2025-06-02
187 | T153 | GIS | Resources |  | Resources onboarding, Licences arrangement, Workstation plan | Kaushal |  | TFIBER | DEPENDENCY(Client/Ext.) | Resource & PCs has been deployed in NOC GIS room. for Licesnes dependecy on T FIber. 11 Aug 2025 :- TFIBER (Sanjay Sir) has asked for GIS O&M head for handling the Daily application & Data Management of GIS on(26 June 2025) , Shiva Prasad Sir (L&T) Commented that Kaushalendra Will be the Head of GIS for operations also. |  | T FIber to support fpr closure. | [15 empty] | 1 |  |  | 2025-09-30 | Resources and workstations have already been deployed in the NOC GIS Room. Decisions regarding additional licenses need to be made by L&T and TFIBER
268 | T159 | GIS | Integration |  | Physical Device sync-up with OSS System | Kaushal |  | OSS | WIP | DB view has been created by the GIS.Valdiation is pending in OSS. OSS to provide port and device view. |  | DIsucssion with OSS-OEM/SME. |  |  | 0.2 | 0.1 | 0.1 | 0.1 | [10 empty] | 1 |  | 2025-10-20 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T159
269 | T160 | GIS | Integration |  | Common Span Path | Kaushal |  | oss | WIP | This point is dependent on the synchronization of the physical device |  | After physical device sync up. | [5 empty] | 0.2 | [11 empty] | 1 | 2025-11-05 | Dependency On Physical Device Syn-up (Integration) & alarm corelation
140 | T158 | GIS | MoM Action |  | GIS LLD submitted to T-Fiber on 02.03.2025, to be discussed with T-Fiber | Kaushal |  |  | CLOSURE REVIEW PENDING | Resubmission done after discussion. Date-19.03.25. queries on LLD with mail dated 25.03.25 (Kaushal): Held discussions with Sanjay Sir and TPA at the NOC on 27 June 2025. A formal email requesting approval was also sent on same day waiting for approval , I followed up four times, but have not received any update yet, 11 Aug 2025:- Pending With Dhanjay Sir |  | T FIBER to approve. | [16 empty] | 1 |  | 2025-09-30 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T158
2 | T11 | BSS | Development and unit testing |  | Import Sub-Departments, Import Leads, Campaign Management, Opportunity/Quote/order Management, order booking and Service Order workflow for tested services | Manoj Nibrad |  | TFIBER | WIP | 29-08-2025: All points are completed Import Sub-Departments, Import Leads, Opportunity/Quote/order Management, order booking and Service Order workflow for tested services Demo to be conducted to TFIBER. "Campaign Management" is Pending where inputs are required from TFIBER Business team 26-06-2025: Awaiting few inputs from TFIBER |  |  | 0.1 | 0.1 | 0.2 | 0.2 | 0.1 | 0.1 | 0.2 | 0.5 |  |  |  | 1 | [6 empty] | #REF!
3 | T19 | BSS | MoM Action |  | T-Cell service definition for workflow implementation in BSS for creating Spoke primary and secondary | Manoj Nibrad |  | TFIBER | WIP | 29-08-2025:Update product concept note similar to GIBB and share with TFIBER for review 26-06-2025: We can deliver this post getting product concept note from TFIBER | [13 empty] | 1 | [6 empty] | #REF!
128 | T25 | BSS | MoM Action |  | Product concept note configuration in BSS queries to be shared | Manoj Nibrad |  | TFIBER | WIP | 29-08-2025: Queries to be prepared and share with TFIBER for discussion. 17-07-2025: Business Team of TFIBER needs to finalize and confirm all product. 26-06-2025: Need Product concept note from TFIBER | [12 empty] | 1 | [7 empty] | #REF!
129 | T26 | BSS | MoM Action |  | Location id logic for NSO provisioning | Manoj Nibrad |  | NSO | WIP | 29-08-2025: Ciruit ID logic PPT shared by Sivakumar, needs to use and implement in BSS. 26-06-2025: Timeline 30th July is considering NSO support is available in 2-3 days | [13 empty] | 1 | [6 empty] | #REF!
156 | T346 | TNOC-Ops | MoM Action |  | all EMS Devices for provisioning through BSS | Manoj Nibrad |  | NSO | WIP | 26-06-2025: Deuplicate of S.No#246_Unique ID#T9 |  |  | 0.25 | [11 empty] | 0.5 |  |  |  | 1 |  | #REF!
243 | T6 | BSS | Installation |  | Installation of BSS Application | Manoj Nibrad |  |  | CLOSURE REVIEW PENDING | 29-08-2025: Design and Solution document to be shared with GM NOC and Physical instllation of BSS need to validate according to solution from L&T Side before submitting for for review with T Fiber 26-06-2025: We have offered Installation AT. TFIBER has asked DC architecture review including license validity |  | Cordinating with TFIBER for acceptance. | 1 | [7 empty] | 1 | [9 empty] | #REF!
244 | T7 | BSS | Integration |  | Initial Integration with Third Party Applications (OSS & NSO) | Manoj Nibrad |  | NSO | WIP | 26-06-2025: OSS Integration is done. NSO integration is pending. Awaiting NSO Team. |  |  | 0.5 |  |  |  | 0.1 | 0.1 | 0.1 | 0.5 |  |  |  |  | 1 | [5 empty] | #REF!
245 | T8 | BSS | Integration |  | OSS interfaces | Manoj Nibrad |  |  | WIP | 26-06-2025: Feasibility API & Ticket API integration is completed. |  |  | 1 | [7 empty] | 1 | [9 empty] | #REF!
246 | T9 | BSS | Integration |  | NSO interfaces | Manoj Nibrad |  | NSO | WIP | 26-06-2025: Awaiting NSO Team | [6 empty] | 0.2 | 0.2 | 0.2 | [5 empty] | 0.5 |  |  |  | 1 |  | #REF!
247 | T12 | BSS | Development and unit testing |  | Product/Service Catalogue integration | Manoj Nibrad |  | TFIBER | CLOSURE REVIEW PENDING | 29-08-2025: Feature is available to admin User(Product Team) to configure new product based on requirement. BSS Team will provide Demo to the TFIBER (business team([Uday]/Solution Team[Sanjay]) for their acceptance. 26-06-2025: Artifacts submitted. Closure review is pending with TFIBER | [10 empty] | 1 | [9 empty] | #REF!
248 | T13 | BSS | Development and unit testing |  | Billing, Discounts & Adjustments, Invoice generation, Bill Formatting | Manoj Nibrad |  | TFIBER | CLOSURE REVIEW PENDING | 29-08-2025: Feature is made available in the BSS application, BSS Team will provide demo to TFIBER Team (Business [Uday] & Finance[Bhaskar]) 26-06-2025: Artifacts submitted. Closure review is pending with TFIBER | [10 empty] | 1 | [9 empty] | #REF!
249 | T14 | BSS | Development and unit testing |  | Feasibility API response from OSS for service provisioning request | Manoj Nibrad |  |  | CLOSURE REVIEW PENDING | 29-08-2025: Feaibility API is already integrated with BSS and demonstrated in GIBB demo and it is applicable for all products. 26-06-2025: Artifacts submitted. Closure review is pending with TFIBER | 2025-08-30 |  | 1 | [7 empty] | 1 | [9 empty] | #REF!
250 | T15 | BSS | Development and unit testing |  | SMS notification, email gateway, Field engineer mobile app readiness | Manoj Nibrad |  |  | CLOSURE REVIEW PENDING | 29-08-2025: Integration is already completed and applicable for all product same has demonstrated to TFIBER during GIBB demo session. 26-06-2025: Artifacts submitted. Closure review is pending with TFIBER | 2025-08-30 |  | 1 | [7 empty] | 1 | [9 empty] | #REF!
251 | T16 | BSS | Development and unit testing |  | Service Assurance and trouble tickets | Manoj Nibrad |  |  | CLOSURE REVIEW PENDING | 29-08-2025: Integration with Service Manager is done for technical ticket and BSS have functionality to handle the non-technical ticket in BSS itself. BSS team will demonstrate this functionality to TFIBER. Sanjay Sir needs to confirm demo date. 26-06-2025: Artifacts submitted. Closure review is pending with TFIBER | [6 empty] | 0.2 | 0.2 | 0.2 |  | 1 | [9 empty] | #REF!
252 | T17 | BSS | Development and unit testing |  | Customer Self care portal development for T-CELL, T-NET, L0 | Manoj Nibrad |  |  | CLOSURE REVIEW PENDING | 29-08-2025: Webportal is available. BSS team needs to demonstrate to TFIBER team. Sanjay Sir needs to confirm demo date. 26-06-2025: Artifacts submitted. Closure review is pending with TFIBER | [10 empty] | 1 | [9 empty] | #REF!
253 | T18 | BSS | Integration |  | Integration modules Like on board Un-Assist & dependent module to be completed for all products from system to be initiated a workshop and to be closed in next 2 Weeks | Manoj Nibrad |  | TFIBER | DEPENDENCY(Client/Ext.) | 29-08-2025: Seek input from Business team (Uday) and deploy post assisted completion. 26-06-2025: Input awaited from TFIBER | [20 empty] | #N/A
254 | T20 | BSS | Development and unit testing |  | Rules for primary and secondary spoke implementation in BSS- - GP with shortest distance will be primary - To display dropdown and concerned user group to select and confirm | Manoj Nibrad |  | KNOT | WIP | 17-05-2025: BSS should give option to upload excel and check feasibility from given API. | [13 empty] | 1 | [6 empty] | #REF!
255 | T24 | BSS | MoM Action |  | PoP location confirmation usergroup for connectivity to O&M | Manoj Nibrad |  | TFIBER | DEPENDENCY(Client/Ext.) | 29-08-2025: Seek input from O&M team (Umesh) 26-06-2025: Input awaited from TFIBER | [20 empty] | #N/A
256 | T27 | BSS | Integration |  | Tariff plan parameters viz. 5G, 4G finalisation. (BSS should capture QOS parameter & Requirements) | Manoj Nibrad |  | TFIBER | DEPENDENCY(Client/Ext.) | 29-08-2025: Product Can be configured in BSS product catalogue Demo to be given to TFIBER 26-06-2025: Input awaited from TFIBER | [20 empty] | #N/A
300 | T347 | BSS | Functional AT |  | Lead to Cash, Order to cash & Request to resolution to operate and demonestrate | Manoj Nibrad |  |  | WIP | [10 empty] | 0.5 | 0.5 | 1 | [8 empty] | #REF!
314 | T382 | BSS | Development and unit testing |  | EY need to present landing page for suggestion - Design features of web page | Manoj Nibrad |  | TFIBER | COMPLETED & APPROVED | 17-05-2025:Inhouse landing page already delivered and operation. TFIBER needs to give closure confirmation. 26-06-2025: Artifacts submitted. Closure review is pending with TFIBER | [10 empty] | 1 | [9 empty] | #REF! | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\BSS\Artifact_T382 |  | Approval Email received from NOC Director | 2025-07-16
365 | T33 | BSS | Security |  | Security policies to evolve related to DOT/CDOT etc | Manoj Nibrad |  | KNOT | DEPENDENCY(Client/Ext.) | 29-08-2025: Collect data from Sivakumar and read user to access the data by DOT. 26-06-2025: Waiting for inputs for multiple deliverables | [7 empty] | 0.25 | 0.25 | [9 empty] | 1 |  | #REF!
379 | T390 | OSS | OSS Dashboards |  | OSS Power BI Dashboard | Suresh Pawar |  |  | WIP | 26-06-2025 : Variaous dashboards are already given to TFIBER but due to instability in NNMi/OBM/UTM data acuracy is not achieved. |  |  | 0.2 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.5 | 0.7 | 1 | [8 empty] | #REF!
380 | T10 | BSS | Integration |  | GeM Portal | Manoj Nibrad |  | TFIBER | COMPLETED & APPROVED | 26-06-2025: As per discussion with TFIBER this point is not possible. Awaiting written confirmation from TFIBER 16-07-2025: It is on Hold | On Hold | On Hold | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | #N/A | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\BSS\Artifact_T10 |  | On-Hold confirmation mail received from NOC Director | 2025-07-16
5 | T45 | DC-IT | Commvault Backup | Tech | Application Installation | Ravi Kishore |  |  | COMPLETED & APPROVED | Commvault Backup Application is installed as per the Application Requirements. Application Installation completed and shown all the test cases in installation AT, ATP was approved. Artifacts are captured. | [21 empty] | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\DC IT-Infra\Artifact for - T45 |  | AD-UT-Tfiber | 2025-05-14
6 | T46 | DC-IT | Commvault Backup | Tech | Application Configuration | Ravi Kishore |  |  | COMPLETED & APPROVED | Application configuration is completed as per the design and shown all the test cases in Installation AT, ATP was approved. Artifacts are Captured. | [21 empty] | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\DC IT-Infra\Artifact for - T46 |  | AD-UT-Tfiber | 2025-05-14
7 | T47 | DC-IT | Commvault Backup | Doc | Application Installation AT | Ravi Kishore |  |  | COMPLETED & APPROVED | Application Installation completed and shown all the test cases in Installation AT, ATP was approved. | [21 empty] | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\DC IT-Infra\Artifact for - T47 |  | AD-UT-Tfiber | 2025-05-14
8 | T48 | DC-IT | Commvault Backup | Doc | Application Functional AT | Ravi Kishore |  |  | WIP | Working on the Extra Test cases which are received from the TPA & T-Fiber. |  | Need to Prepare Test cases along with Procedure and resubmit FAT documnet | [10 empty] | 1 | [7 empty] | 23/09/2025 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\DC IT-Infra\Artifact for - T48
9 | T51 | DC-IT | Commvault Backup | Tech | Backup retention and Backup activity (such as when incremental backup,full backup are scheduled and time duration required to complete such backup). Application Wise Backup Retention should be as per DOT Guidelines | Ravi Kishore |  |  | COMPLETED & APPROVED | All application servers (VM level) backups are configured as per the backup standards. VM's Incremental Backup's on Daily base. VM's Full Backup on Weekly base. At present retention period is maintained for one week. Restoration time will depend upon the Size of the Backup data, storage type and Network throughput. Artifacts are Captured. | [21 empty] | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\DC IT-Infra\Artifact for - T51 |  | AD-UT-Tfiber | 2025-05-14
10 | T52 | DC-IT | Commvault Backup | Tech | Backup solution should have hot , cold and archieve storage inorder to decrease the backup size/capacity in long run. | Ravi Kishore |  |  | COMPLETED & APPROVED | Primary storage is stored in the 3PAR and Backup Storage is stored in MSA. Online (3PAR-Hot) storage and Offline Storage (Backup-Cold)) details are captured. | [21 empty] | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\DC IT-Infra\Artifact for - T52 |  | AD-UT-Tfiber | 2025-05-14
11 | T66 | DR | DC (TNOC-DR) | Tech | Network Readiness | Ravi Kishore |  |  | COMPLETED & APPROVED | 1. All applications & DB installations are completed at DR. 2. Network communication is through for all the Applications & DB. 3. DR application servers to Field devices communication was established. | [21 empty] | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\DR\Artifact for - T66 |  | AD-UT-Tfiber | 2025-05-14
12 | T67 | DR | Mahbubnagar-DR | Tech | Network Readiness | Ravi Kishore |  |  | COMPLETED & APPROVED | 1. Network & link termination was completed. 2. DR application servers to Field devices communication was established through Mahbubnagar link. | [21 empty] | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\DR\Artifact for -T67 |  | AD-UT-Tfiber | 2025-05-14
13 | T70 | DR | Design & Documentation | Tech | DC-DR redunancy Test | Ravi Kishore |  |  | COMPLETED & APPROVED | DC-DR Link Redundancy Test Completed; Test report is captured. | [21 empty] | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\DR\Artifact for - T70 |  | AD-UT-Tfiber | 2025-05-14
131 | T55 | DC-IT | MoM Action | Tech | VM Placing should be verified & rectified, Same service VM needs to be placed in different Physical Server/host. | Ravi Kishore |  |  | COMPLETED & APPROVED | VM's placing verified, Same service (Application) VM's placed in different physical Hosts. | [21 empty] | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\DC IT-Infra\Artifact for - T55 |  | AD-UT-Tfiber | 2025-05-14
132 | T56 | DC-IT | MoM Action | Doc | SOP documents needs to be provided | Ravi Kishore |  |  | REOPENED | SOP documents submitted to Operations team. Remaining pending documents to be prepared periodically. |  | Operations related SOP documents is continuous process, will update on daly base. | [11 empty] | 1 | [6 empty] | 2025-09-17 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\DC IT-Infra\Artifact for - T56
133 | T75 | DR | MoM Action | Tech | To confirm on backups for DR Virtual machines | Ravi Kishore |  |  | COMPLETED & APPROVED | DR Servers VM Backup is getting through Commvault Backup system. | [21 empty] | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\DR\Artifact for - T75 |  | AD-UT-Tfiber | 2025-05-14
134 | T76 | DR | MoM Action | Tech | Backup storage to 25 TB | Ravi Kishore |  |  | COMPLETED & APPROVED | Total 25 TB provisioned for the Backup System, Artifacts captured. | [21 empty] | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\DR\Artifact for - T76 |  | AD-UT-Tfiber | 2025-05-14
135 | T78 | DR | MoM Action | Tech | to monitor the DR Servers | Ravi Kishore |  |  | WIP | DR servers monitoring through DR vCentre happening. DR is maintained by CtrlS team as per contract. Feasibility to be checked to integrated through OSS OBM. |  | DR VM's to be integrated with DC OSS OBM, OBM agent to be installed in all DR VM's. | [13 empty] | 1 |  |  |  |  | #REF! | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\DR\Artifact for - T78
137 | T82 | DR | MoM Action | Tech | To confirm the applications which support Veem Replication for Reconfiguration | Ravi Kishore |  |  | COMPLETED & APPROVED | All Applications Veeam Replication/Reconfiguration details are captured in DR LLD (As per OEM recommendations) Artifacts are Captured. | [21 empty] | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\DR\Artifact for - T82 |  | AD-UT-Tfiber | 2025-05-14
198 | T41 | DC-IT | Servers and Strorage (Deployment and Installations) | Tech | 1. Compute & Storage | Ravi Kishore |  |  | REOPENED | As per the OEM's/SME's request, storage is allocated as per requirements. Artifacts are Captured. OEM Confirmation Emails to be captured as a Reference. |  | Client is Expecting older emails which are recieved from the OEM for resource provisioning, not able to cllect the old email's. SO, will be collecting emails from the OEM/SME's freshly. | [11 empty] | 1 | [6 empty] | #REF! | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\DC IT-Infra\Artifact for - T41
199 | T42 | DC-IT | Servers and Strorage (Deployment and Installations) | Tech | 2. Virtulization | Ravi Kishore |  |  | COMPLETED & APPROVED | VM's are created and handed over to application teams for Application installations. DC Inventory master sheet. Artifacts are Captured. | [21 empty] | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\DC IT-Infra\Artifact for -T42 |  | AD-UT-Tfiber | 2025-05-14
200 | T43 | DC-IT | Servers and Strorage (Deployment and Installations) | Tech | 3. Anti-virus | Ravi Kishore |  |  | COMPLETED & APPROVED | Antivirus is installed in all the VM'S and workstations. Antivirus installation status captured in DC Inventory master sheet. | [21 empty] | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\DC IT-Infra\Artifact for -T43 |  | AD-UT-Tfiber | 2025-05-14
201 | T44 | DC-IT | Servers and Strorage (Deployment and Installations) | Tech | 4. VM's Deployment Application Installations | Ravi Kishore |  |  | COMPLETED & APPROVED | Applications installation completed in the given VM's. Storage/resource Allocation details captured in the TNOC IT Infra Server & Storage-LLD_v_1.5 & DC Inventory master sheet. Artifacts are captured. | [21 empty] | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\DC IT-Infra\Artifact for -T44 |  | AD-UT-Tfiber | 2025-05-14
202 | T65 | DR | Servers and Strorage (Deployment and Installations) | Tech | Virtulization | Ravi Kishore |  |  | COMPLETED & APPROVED | VM's are created and handed over to application teams for Application installations. Artifacts are captured. | [21 empty] | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\DR\Artifact for - T65 |  | AD-UT-Tfiber | 2025-05-14
203 | T297 | DC-IT | Servers and Strorage (Deployment and Installations) | Tech | VM's Deployment Application Installations | Ravi Kishore |  |  | REOPENED | As per the OEM's/SME's request, storage is allocated as per requirements. OEM Confirmation Emails to be captured as a Reference. Artifacts are Captured. |  | Client is Expecting older emails which are recieved from the OEM for resource provisioning, not able to cllect the old email's. SO, will be collecting emails from the OEM/SME's freshly. | [11 empty] | 1 | [6 empty] | #REF! | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\DC IT-Infra\Artifact for - T297
215 | T53 | DC-IT | SSD storage migration – EPNM/PI | Tech | EPNM/PI VMs migration to SSD Storage | Ravi Kishore |  |  | COMPLETED & APPROVED | EPNM/PI VMs are migrated from SAS to SSD storage and validated by SMEs and confirmed IOPS are as per recommendations. | [21 empty] | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\DC IT-Infra\Artifact for - T53 |  | AD-UT-Tfiber | 2025-05-14
216 | T54 | DC-IT | SSD storage migration – ISE/FMC | Tech | ISE & FMC VMs migration to SSD Storage | Ravi Kishore |  |  | COMPLETED & APPROVED | ISE & FMC VM's migrated to SSD storage. | [21 empty] | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\DC IT-Infra\Artifact for - T54 |  | AD-UT-Tfiber | 2025-05-14
260 | T49 | DC-IT | LLD | Doc | LLD Approved conditionally with few punch points. Updated LLD to be submitted | Ravi Kishore |  |  | WIP | Working on DC IT-Infra Server and storage-MoM Points received from the T-Fiber. |  | updated LLD to be submitted | [14 empty] | 1 |  |  |  | #REF! | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\DC IT-Infra\Artifact for - T49
261 | T57 | DC-IT | LLD | Doc | Approved conditionally with few punch points. Updated LLD to be submitted | RS Rao | TPA | TFIBER | CLOSURE REVIEW PENDING | 14-Aug-25 : Discussion was done with TPA and Tfiber and submitted updated LLD document. 18-Jun-25 : Updated DC Network LLD submitted on 18-Jun-25 for TFiber review |  | Review and Approval pending form TPA/T Fiber.
263 | T64 | DC-IT | Functional AT | Tech | DC Network Infra AT | RS Rao | Sandeep Deshmukh | TPA/Cisco | DEPENDENCY(Client/Ext.) | 08-Jul-2025 - Sandeep will come back by EoD today on extension of Cisco support renewal 01-Jul-25 : Revised FAT documents submission pending (TPA observations to be included) OEM(Cisco) suport is required to show the new test cases, Inputs provided to OEM on 14th May & 30th Jun. OEM onboarding is in progress & LnT Contracts team is coordinating |  | Working with Cisco onboarding. | [18 empty] | #N/A
264 | T68 | DR | Design & Documentation | Doc | LLD: Approved conditionally with few punch points. Updated LLD to be submitted | Ravi Kishore |  |  | WIP | Working on additional points shared by Tfiber. |  | updated LLD to be submitted | [12 empty] | 1 | [5 empty] | #REF! | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\DR\Artifact for -T68
265 | T69 | DR | Design & Documentation | Doc | HLD: Revised solution to submitted | Ravi Kishore |  |  | WIP | Working on additional points shared by Tfiber. |  | Revised HLD to be submitted | [10 empty] | 1 | [7 empty] | 19/09/2025 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\DR\Artifact for -T69
296 | T324 | Security | Deployment and Installations | Tech | Syslog to maintain for 2 years | Ravi Kishore |  |  | COMPLETED & APPROVED | Total 30 TB is allotted for Sys logs. It will be maintained for 02 yrs. 6 Months Online and 1.5 Years Offline. |  | currently only 18 month Syslog data shown to customer . However as data progressively reach for 02 years will be submitted to customer . ( In case customer agree with 18 month old data artefacts . Point will closed immediately) | [19 empty] | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\Security\T324 |  | AD-UT-Tfiber | 2025-05-14
323 | T77 | DR | MoM Action | Tech | To submit the SOPs for DC-DR switchover, DC-DR failover and failback | Ravi Kishore |  |  | REOPENED | Tejas, Nokia, GIS & Ciena MCP documnets are received. Remaining all Applications domains SOP's to be updated. |  | Sent email to all SME's to share the Failover and Failback documents. | [11 empty] | 1 | [6 empty] | 2025-10-31 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\DR\Artifact for - T77
324 | T79 | DR | MoM Action | Tech | To confirm that DNS switchover between DC and DR locations should be automatic | Ravi Kishore |  |  | COMPLETED & APPROVED | Having Primary Domain Controller and Additional Domain Controller at DC, another additional Domain Controller at DR location. Always, all three Domain Controllers are in Sync each other. | [21 empty] | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\DR\Artifact for - T79 |  | AD-UT-Tfiber | 2025-05-14
82 | T199 | IPMPLS | Design & Documentation |  | HLD | RS Rao |  |  | COMPLETED & APPROVED | [22 empty] | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\E2E_Network HLD_Part1_V2.0_ 29.10.2020(Approved) - T199.pdf |  | AD-UT-Tfiber | 2025-05-05
127 | T385 | A&O Solution | Design & Documentation |  | solution document - GI internet solution | RS Rao |  |  | COMPLETED & APPROVED | Post 24.06.25 review and direction, working for a alternate options for NSO. will come back as earliest with closure plan. | [21 empty] | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\T-FIBER T-Net for GI Broadband Service Design LLD V1.1 - T188.pdf |  | AD-UT-Tfiber | 2025-05-05 | Refer T188
136 | T80 | DR | MoM Action |  | Mahubnagar as NTP | RS Rao |  |  | COMPLETED & APPROVED | [22 empty] | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\Primary NTP - T60,T61,T62.pdf \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\Secondary NTP - T60,T61,T62.pdf |  | AD-UT-Tfiber | 2025-05-05
158 | T339 | IPMPLS | MPLS Core network QoS |  | Egress Policy structure and BW as per discussion | RS Rao |  |  | COMPLETED & APPROVED | [22 empty] | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\QOS for TFiber Network LLD V2.0 - T339, T340, T341, T342.pdf |  | AD-UT-Tfiber | 2025-05-05
159 | T340 | IPMPLS | MPLS Core network QoS |  | Egress QoS policy for ASR99xx | RS Rao |  |  | COMPLETED & APPROVED | [22 empty] | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\QOS for TFiber Network LLD V2.0 - T339, T340, T341, T342.pdf |  | AD-UT-Tfiber | 2025-05-05
160 | T341 | IPMPLS | MPLS Core network QoS |  | Egress QoS policy for ASR907 | RS Rao |  |  | COMPLETED & APPROVED | [22 empty] | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\QOS for TFiber Network LLD V2.0 - T339, T340, T341, T342.pdf |  | AD-UT-Tfiber | 2025-05-05
161 | T342 | IPMPLS | MPLS Core network QoS |  | Egress QoS policy for ASR920 | RS Rao |  |  | COMPLETED & APPROVED | [22 empty] | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\QOS for TFiber Network LLD V2.0 - T339, T340, T341, T342.pdf |  | AD-UT-Tfiber | 2025-05-05
176 | T60 | DC-IT | NTP |  | Installation | RS Rao |  |  | COMPLETED & APPROVED | [22 empty] | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\Primary NTP - T60,T61,T62.pdf \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\Secondary NTP - T60,T61,T62.pdf |  | AD-UT-Tfiber | 2025-05-05
177 | T61 | DC-IT | NTP |  | Configuration | RS Rao |  |  | COMPLETED & APPROVED | [22 empty] | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\Primary NTP - T60,T61,T62.pdf \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\Secondary NTP - T60,T61,T62.pdf |  | AD-UT-Tfiber | 2025-05-05
178 | T62 | DC-IT | NTP |  | NTP Installation AT | RS Rao |  |  | COMPLETED & APPROVED | [22 empty] | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\Primary NTP - T60,T61,T62.pdf \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\Secondary NTP - T60,T61,T62.pdf |  | AD-UT-Tfiber | 2025-05-05
179 | T63 | DC-IT | NTP |  | NTP Functional AT | RS Rao |  |  | COMPLETED & APPROVED | 01-Jul-25 : NTP demonstration and testing completed. Functional AT document submitted to TPA for approval.Target closure - 04/07 | 2025-07-04 | Submission of FAT observation for approval by 2nd July. | [7 empty] | 1 | [10 empty] | #REF! | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\NTP FAT & Acceptance - T63.pdf |  | AD-UT-Tfiber | 2025-07-03
188 | T343 | IPMPLS | Service Solution | Tech | Design Document require SDC content to GI | RS Rao | Sanjay | TFIBER | DEPENDENCY(Client/Ext.) | 12-Sep-25 : Peering plan submitted as per discussion on 11-Sep-25 01-Jul-25 : Design document submitted with suggested approaches. Require inputs from TFiber to conduct PoC and finalize service design. |  | Dependency on Tfiber for further steps | [18 empty] | #N/A
207 | T185 | IPMPLS | Service Solution |  | HSI (High Speed Internet to Household) | RS Rao |  |  | COMPLETED & APPROVED | [22 empty] | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\House Hold HSI Services Design LLD V1.2 - T185.pdf |  | AD-UT-Tfiber | 2025-05-05
208 | T186 | IPMPLS | Service Solution |  | IPTV to Household | RS Rao |  |  | COMPLETED & APPROVED | [22 empty] | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\House Hold IPTV Services Design LLD V1.2 - T186.pdf |  | AD-UT-Tfiber | 2025-05-05
209 | T187 | IPMPLS | Service Solution |  | VOIP to Household | RS Rao |  |  | COMPLETED & APPROVED | [22 empty] | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\House Hold VoIP Services Design LLD V1.2 - t187.pdf |  | AD-UT-Tfiber | 2025-05-05
210 | T188 | IPMPLS | Service Solution |  | Internet to GI (Govt. Institution) | RS Rao |  |  | COMPLETED & APPROVED | [22 empty] | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\T-FIBER T-Net for GI Broadband Service Design LLD V1.1 - T188.pdf |  | AD-UT-Tfiber | 2025-05-05
211 | T189 | IPMPLS | Service Solution |  | CCTV Unicast | RS Rao |  |  | COMPLETED & APPROVED | [22 empty] | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\Centrailzed CCTV Surveillance Monitoring over T-Fiber Network-Solution Doucment_Initial Draft V1.0 - T189.pdf |  | AD-UT-Tfiber | 2025-05-05
212 | T190 | IPMPLS | Service Solution |  | CCTV Multicast | RS Rao |  |  | COMPLETED & APPROVED | [22 empty] | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\CCTV Multicast Solution LLD V1.2 - T190.pdf |  | AD-UT-Tfiber | 2025-05-05
213 | T191 | IPMPLS | Service Solution |  | Cell Tower L2VPN | RS Rao |  |  | COMPLETED & APPROVED | [22 empty] | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\TFIBER T-CELL Service Design & Solution V4.3 T197, T336, T337, T338.pdf |  | AD-UT-Tfiber | 2025-05-05
214 | T192 | IPMPLS | Service Solution |  | Dhanush Telemedicine Application | RS Rao |  |  | COMPLETED & APPROVED | [22 empty] | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\T-FIBER DHANUSH TELEMEDICINE SOLUTION LLD V1.0 - T192.pdf |  | AD-UT-Tfiber | 2025-05-05
219 | T336 | IPMPLS | T-Cell Solution Design |  | Egress QoS policy for ASR907 | RS Rao |  |  | COMPLETED & APPROVED | [22 empty] | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\TFIBER T-CELL Service Design & Solution V4.3 T197, T336, T337, T338.pdf |  | AD-UT-Tfiber | 2025-05-05
220 | T337 | IPMPLS | T-Cell Solution Design |  | Egress QoS policy for ASR920 – QoS policy to be applied on Gigabit interfaces instead of on Port Channel (LAG) which is not suitable for CIR application | RS Rao |  |  | COMPLETED & APPROVED | [22 empty] | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\TFIBER T-CELL Service Design & Solution V4.3 T197, T336, T337, T338.pdf |  | AD-UT-Tfiber | 2025-05-05
221 | T338 | IPMPLS | T-Cell Solution Design |  | Additional scenarios for generic Cell tower Solution shared with Cisco, Cisco to check and provide the design | RS Rao |  |  | COMPLETED & APPROVED | [22 empty] | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\TFIBER T-CELL Service Design & Solution V4.3 T197, T336, T337, T338.pdf |  | AD-UT-Tfiber | 2025-05-05
262 | T59 | DC-IT | Cisco PI | Tech | Cisco prime infrastructure AT | RS Rao | Sandeep Deshmukh | TPA/Cisco | DEPENDENCY(Client/Ext.) | 08-Jul-2025 - Sandeep will come back by EoD today on extension of Cisco support renewal 01-Jul-25 : Revised FAT documents submission pending (TPA observations to be included) OEM(Cisco) suport is required to show the new test cases, Inputs provided to OEM on 14th May & 30th Jun. OEM onboarding is in progress & LnT Contracts team is coordinating |  | Working with Cisco onboarding. | [18 empty] | #N/A
270 | T200 | IPMPLS | Design & Documentation |  | Approved conditionally with few punch points. Updated LLD to be submitted | RS Rao |  | TFIBER | COMPLETED & APPROVED | 21-Aug-25 : Updated IPMPLS Network LLD submitted on 02-Jun-25 and approved on 21-Aug-25 after discussions | [21 empty] | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\IP MPLS Network LLD V1.7 14-Aug-2025.pdf |  | AD-UT, Tfiber (Sanjay ji) | 2025-08-21
315 | T383 | DC-IT | Functional AT | Tech | Cisco prime infrastructure AT | RS Rao | Sandeep Deshmukh | TPA/Cisco | DEPENDENCY(Client/Ext.) | 08-Jul-2025 - Sandeep will come back by EoD today on extension of Cisco support renewal 01-Jul-25 : Revised FAT documents submission pending (TPA observations to be included) OEM(Cisco) suport is required to show the new test cases, Inputs provided to OEM on 14th May & 30th Jun. OEM onboarding is in progress & LnT Contracts team coordinating |  | Working with Cisco onboarding. | [18 empty] | #N/A
318 | T58 | DC-IT | Cisco EPNM | Tech | Cisco EPNM infrastructure AT | RS Rao | Sandeep Deshmukh | TPA/Cisco | DEPENDENCY(Client/Ext.) | 08-Jul-2025 - Sandeep will come back by EoD today on extension of Cisco support renewal 01-Jul-25 : Revised FAT documents submission pending (TPA observations to be included) OEM(Cisco) suport is required to show the new test cases, Inputs provided to OEM on 14th May & 30th Jun. OEM onboarding is in progress & LnT Contracts team coordinating |  | Working with Cisco onboarding. | [18 empty] | #N/A
320 | T72 | DR | MoM Action | Tech | To configure LACP between L3 Switch and Core Router | RS Rao | Sandeep Deshmukh | CtrlS | DEPENDENCY(Client/Ext.) | 08-Jul-2025 Sandeep will ensure on CTRL-S support and update by EoD 01-Jul-25 : Ticket (SR01301726) raised with CtrlS on 27-Jun, Config & testing to be carried out. This is additional task as per CtrlS and commercials may be involved. LnT Contracts team also talking to CtrlS account team to complete the task. 24-Dec-25 : SR01036770 opened with CtrlS for LACP configuration and it is not O&M activity as per CtrlS ops. team. escalated to LnT Contracts team for supoort. |  | Ownership - Sandeep | [8 empty] | 1 | [9 empty] | #REF!
321 | T73 | DR | MoM Action | Tech | To configure LACP between Core Router and Firewall | RS Rao | Sandeep Deshmukh | CtrlS | DEPENDENCY(Client/Ext.) | 01-Jul-25 : Ticket (SR01301726) raised with CtrlS on 27-Jun, Config & testing to be carried out. This is additional task as per CtrlS and commercials may be involved. LnT Contracts team also talking to CtrlS account team to complete the task. 24-Dec-25 : SR01036770 opened with CtrlS for LACP configuration and it is not O&M activity as per CtrlS ops. team. escalated to LnT Contracts team for supoort. |  | Working with CtrlS | [8 empty] | 1 | [9 empty] | #REF!
322 | T74 | DR | MoM Action | Tech | To configure LACP between Firewall and L2 Switch | RS Rao | Sandeep Deshmukh | CtrlS | DEPENDENCY(Client/Ext.) | 01-Jul-25 : Ticket (SR01301726) raised with CtrlS on 27-Jun, Config & testing to be carried out. This is additional task as per CtrlS and commercials may be involved. LnT Contracts team also talking to CtrlS account team to complete the task. 24-Dec-25 : SR01036770 opened with CtrlS for LACP configuration and it is not O&M activity as per CtrlS ops. team. escalated to LnT Contracts team for supoort. |  | Working with CtrlS | [8 empty] | 1 | [9 empty] | #REF!
339 | T198 | IPMPLS | Network AT | Tech | Simulation and testing network for parameters like network convergence etc | RS Rao | Sandeep Deshmukh | Cisco | DEPENDENCY(Client/Ext.) | 08-Jul-2025 - Sandeep will come back by EoD today on extension of Cisco support renewal 01-Jul-25 : OEM(Cisco) suport is required to perform network AT, Inputs provided to OEM. OEM to provide Network AT procedure including all tests and test procedures. OEM onboarding is in progress & LnT Contracts team is coordinating |  | Working with Cisco onboarding. | [18 empty] | #N/A
348 | T201 | IPMPLS | OSS | Tech | FMS Fault Management System (Device, Link ticketing etc) | RS Rao | Manoj Nibrad | OSS | WIP | 08-Jul-25 : Requirement given to OSS for implementation. FMS parameters given 1. Node down (Router, Switch, DC Network Switches, DWDM, OTN, OADM, OLT, UPS) : Field alarm should be received in NNMi. NNMi has to forward the alarm to OBM, NPS and to TeMiP. UCA has to carryout correlation and accordingly pass the root cause to SM to generate TT. once TT is generated it is assigned to respective District Engineer along with mail. After Fault resolution, TT should be resolved in system with alarm clearance and NoC has to close the TT with RFO. Link down, Protocol down, RSP/Card/PSU down, High Temperature, Latency, Packet Loss, Jitter. End-to-end implementation and demonstration pending in OSS |  | Working with OSS SME/OEM. | [13 empty] | 1 |  |  |  |  | #REF!
349 | T202 | IPMPLS | OSS | Tech | PMS Performance Management System (Utilization, Errors etc) | RS Rao | Manoj Nibrad | OSS | WIP | 07-Jul-25 : Requirement given to OSS for implementation. PMS parameters given - CPU, Memory, Backplane and Link utilization, CRC errors, Optical power, QoS parameters . End-to-end implementation and demonstration pending in OSS |  | Working with OSS SME/OEM. | [13 empty] | 1 |  |  |  |  | #REF!
350 | T203 | IPMPLS | OSS | Tech | Dashboard (Network Parameter Dash Boards) | RS Rao | Manoj Nibrad | OSS | WIP | 07-Jul-25 : Requirement given to OSS for implementation. Dash Board required - Top CPU, Memory, Link utilization, Temperature, All Critical alarms . Demonstration pending in OSS |  | Working with OSS SME/OEM. | [13 empty] | 1 |  |  |  |  | #REF!
351 | T204 | IPMPLS | OSS | Tech | Reports (Invetory, Device avability, Link Availability) | RS Rao | Manoj Nibrad | OSS | WIP | 07-Jul-25 : Requirement given to OSS for implementation. Reports required - Node availability, Link availability, Link utilization, Inventory, CPU utilization, Memory Utilization, Latecy. Demonstration pending in OSS |  | Working with OSS SME/OEM. | [13 empty] | 1 |  |  |  |  | #REF!
370 | T194 | IPMPLS | Service Catalogue | Doc | Incremental Product/ Services finalization in T-Fiber network | RS Rao | Sanjay | TFIBER | DEPENDENCY(Client/Ext.) | 01-Jul-25 : Dependecy on Tfiber in PCN (Product Concept Note) finalisation. Tracked in BSS action item T12 (part of 472 tracker) |  | T Fiber to revert with all Product concept note required for the T Fiber network. | [18 empty] | #N/A
371 | T193 | IPMPLS | Service Solution | Tech | SDC content to Household and GI | RS Rao | Sanjay | TFIBER | DEPENDENCY(Client/Ext.) | 12-Sep-25 : Peering plan submitted as per discussion on 11-Sep-25 01-Jul-25 : Design document submitted with suggested approaches. Require inputs from TFiber to conduct PoC and finalize service design. |  | Dependency on Tfiber for further steps | [18 empty] | #N/A
372 | T344 | IPMPLS | Service Solution | Tech | Solution document for GI connectivity (intranet & internet) TVPN | RS Rao | Sanjay | TFIBER | DEPENDENCY(Client/Ext.) | 01-Jul-25 : Design document submitted with suggested approaches. Require inputs from TFiber to conduct PoC and finalize service design. |  | Dependency on Tfiber for further steps | [18 empty] | #N/A
1 | T3 | Security | Integration |  | Accouting data from Ciena MCP and field nodes to be captured in Alepo AAA | Sarmendra |  | Alepo | DEPENDENCY(Client/Ext.) | Aleppo TAC support Resumed and MCP upgradation awaited |  | Artefacts will be collected . | 0.1 | 0.2 | 0.5 | 0.7 | 0.8 | [13 empty] | #N/A
14 | T81 | DR | Configuration | Tech | All application to be migrated to implement DR LB configuration | Sarmendra and RaKishore |  |  | WIP | Artifacts created for LB configuration and only Nokia is installed All appilcation to be migrated at DR LB Action by Ravi |  | Dependent on readiness of all application. and eployed over LB DR. | [8 empty] | 1 | [9 empty] | #REF!
115 | T300 | OSS | Configuration and best practices |  | User IDs created. Need to work with users for testing for NOC desktops | Sarmendra |  |  | COMPLETED & APPROVED | Artifacts will be created and submitted on 03 Jul 25 | 2025-07-11 | Artifacts were submitted with Customer. Additonal point raised to group all user as per privilege. | [9 empty] | 1 | [8 empty] | #REF! | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\NW-Security\T300
116 | T303 | OSS | Configuration |  | OSS- Redware LB-There were configuration issues and have been sorted our by having multiple sessions over the past few weeks | Sarmendra |  |  | CLOSURE REVIEW PENDING | Artifact created and will be submitted to customer on 03 Jul 25. | Will be cordinated with OSS and artfact will be submitted to Customer. | Artifacts were submitted with Customer. Additonal point raised to test OSS with both Radware LB and prove the HA. | [8 empty] | 1 | [9 empty] | #REF!
117 | T305 | OSS | Configuration | Tech | We have identified memory needed. Need help with space allocation for VM and also need license for a syslog server. ( we can also use Default Linux daemon) Syslog | Ravi Kishore | Sanjay | TFIBER | COMPLETED & APPROVED | Syslog is activated for both Redhat and Windows servers, Artifacts are captured. | 2025-09-17 | Syslog integration with both Redhat and Windows servers Completed. | [9 empty] | 1 | [8 empty] | #REF! | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\OSS\T305 |  | AD-UT-Tfiber
118 | T315 | OSS | Fire and Safety Drill |  | Certificate and artefacts of last fire & safety drill submitted | Sarmendra |  |  | COMPLETED & APPROVED | Artifact created and will be submitted to customer on 03 Jul 25. Artfact submitted closure on 10 Jul 25 | its a recurring task. | [8 empty] | 1 | [10 empty] | #REF! | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\NW-Security\T315
119 | T317 | OSS | Certifications |  | ITIL Product certification | Manoj Nibrad |  |  | COMPLETED & APPROVED | Artifact created and submitted with TFIBER and Sanjay Sir has appoved on 12th Sept 2025. | [11 empty] | 1 | [8 empty] | #REF! | \\172.28.9.34\SHARE DRIVE\Artefacts_T-Fiber TNOC Tracker\OSS |  | AD-UT-Tfiber | 2025-09-12
120 | T349 | TNOC-Ops | Design & Documentation |  | TNOC operational framework with respect to processes (Incident, Problem, Major Event, Change, Version, Security, AAA, Planned Event, SLA Management etc) | Sarmendra | AUP submitted to customer, HLD submitted to customer | Security SOP is in progress. will be aligned only after policy is approved | WIP | Remarks on policy is being worked out as per inputs of Tfiber . | [11 empty] | 1 | [8 empty] | #REF!
130 | T50 | DC-IT | MoM Action |  | Radware , A10 Configuration file needed to be shared to RaviKishore | Sarmendra |  |  | COMPLETED & APPROVED | Artfacts submitted . point Closure on 10 Jul 25 | [20 empty] | #N/A | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\NW-Security\T50
151 | T321 | Security | MoM Action |  | Firewall policy compare from DC to DR validation check for redundancy | Sarmendra |  |  | REOPENED | all Policy will be compared with current configuration of firewall and be submitted . | Complete policy verification can be done when all application migrated to LB | Generation of artefacts and clsoure disucssion with T Fiber. | [9 empty] | 1 | [8 empty] | #REF!
152 | T322 | Security | MoM Action |  | Day 0 attacks for any government departments lifecycle (GIBB to be protected from the day of connection) | Sarmendra |  | Cisco | DEPENDENCY(Client/Ext.) | Manual Blocking of URL were not successful till date , CISCO is checking for the same . All session log shared. URL filterimg success is the key for Day O security extension to new GIBB connectiom |  | T Fiber to suggest for way forward. | [18 empty] | #N/A
153 | T329 | Security | MoM Action |  | Cisco ISE to be integrated with AD for Authentication | Sarmendra |  |  | COMPLETED & APPROVED | Point closed | [21 empty] | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\NW-Security\T153 |  | AD-UT-Tfiber | 2025-05-19
154 | T330 | Security | MoM Action |  | syslog storage requirement for respective OEM devices | Sarmendra |  |  | COMPLETED & APPROVED
155 | T331 | Security | MoM Action |  | Tejas OLT to integrate with Alepo AAA Tejas EMS to integrate with Alepo AAA | Sarmendra |  |  | CLOSURE REVIEW PENDING | Alepo AMC Support required for Evidence submission to customer |  | Generation of artefacts and clsoure disucssion with T Fiber. | [8 empty] | 1 | [9 empty] | #REF!
162 | T310 | Security | NAT |  | Developed in-house solution, also exploring with external vendors. 3 vendors declined. In-house solution is ready for demo, tested with the sample data. | Sarmendra |  |  | COMPLETED & APPROVED | artefacts need to be generated and submitted. |  | Generation of artefacts and clsoure disucssion with T Fiber. | [8 empty] | 1 | [9 empty] | #REF!
185 | T318 | Security | Policy Implementation |  | Network Forensic | Sarmendra |  | Dependency On License | COMPLETED & APPROVED | License need for Evidence submission to customer [26/05] Discussed with AD, approval awaited |  | Point Closed . However License needeto comply with it in future. | [19 empty] | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\NW-Security\T318 |  | AD-UT-Tfiber | 2025-05-19
186 | T327 | Security | Report |  | Syslog NAT report | Sarmendra |  |  | COMPLETED & APPROVED | [26/05] Discussed and awaited approval |  | Point Closed. | [19 empty] | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\NW-Security\T327 |  | AD-UT-Tfiber | 2025-05-19
189 | T2A | Security | Security |  | Ciena to comply the password policy for MCP and field nodes, though Alepo AAA. | Sarmendra |  | Dependency On License | WIP | Alepo AMC Support required for Evidence submission to customer |  | Alepo support to be activate for aretfactes and further clousre. | [9 empty] | 1 | [8 empty] | #REF!
190 | T4 | Security | Security |  | Alepo confirmed that Alepo AAA supports TACACS, Alepo to test Nokia and Ciena nodes integration on TACACS , with supporting artefacts of testing | Sarmendra |  | Dependency On License | CLOSURE REVIEW PENDING | Alepo AMC Support required for Evidence submission to customer |  | Alepo support to be activate for aretfactes and further clousre. | [9 empty] | 1 | [8 empty] | #REF!
191 | T22 | BSS | Security |  | Roadmap for password policy implementation in CSP | Sarmendra |  | BSS | WIP | Discussion with BSS team has completed . Rwquirement ofr password policy has been shared with Manoj and Vendor. | [11 empty] | 1 | [8 empty] | #REF!
192 | T31 | Security | Security |  | Internal Audit for all applications | Sarmendra |  |  | WIP | OEM Vendor certification awaited to submit |  | all application owner to get a bug free certificate from respective OEM for onward submission to customer. Burp suit is require to carry out Application audit. | [9 empty] | 1 | [8 empty] | #REF!
193 | T32 | Security | Security |  | Internal audit for network elements | Sarmendra |  |  | WIP | Internal audit in progress. Workstation , VMs, and server are already done. |  | 1.Other Network element will be subsequently audited. 2.Nmap and Nessus Scan tool needed to complete and submit Scan report to customer | [9 empty] | 1 | [8 empty] | #REF!
305 | T36 | Security | Security |  | Physical user access | Sarmendra |  |  | COMPLETED & APPROVED | Has completed , Artefacts will be resubmitted. | Artefact were submitted to Customer. Some new points added to close the same points | [9 empty] | 1 | [9 empty] | #REF! | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\NW-Security\T36
195 | T37 | Security | Security |  | Virtual user access-VPN | Sarmendra |  |  | REOPENED | Has completed , Artefacts will be resubmitted. | Artefact were discussed with customer, asked to further refine the artefacts | [9 empty] | 1 | [9 empty] | #REF!
196 | T38 | Security | Security |  | Role based severity access | Sarmendra |  |  | WIP | Evidences preparation completed, submission pending. After disucssion will be submitted by 16.07.25 |  | To disucss with T Fiber for closure. | [9 empty] | 1 | [8 empty] | #REF!
197 | T39 | Security | Security |  | ISE integration with Cisco elements | Sarmendra |  |  | CLOSURE REVIEW PENDING | Artefacts will be submitted. | [10 empty] | 1 | [9 empty] | #REF!
217 | T309 | Security | Storage |  | Storage requirement worked out and given to contract team. PO to be issued | Sarmendra |  |  | COMPLETED & APPROVED
218 | T323 | Security | Storage |  | User access logs& Commands to be maintained for 2 years | Sarmendra |  |  | COMPLETED & APPROVED | [26/05] Reviewed and approval awaited |  | Point Closed | [19 empty] | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\NW-Security\T323 |  | AD-UT-Tfiber | 2025-05-19
228 | T316 | Security | User Traceability |  | User access traceability | Sarmendra |  |  | COMPLETED & APPROVED | [26/05] Discussed and awaited approval |  | Point Closed | [9 empty] | T50 | [9 empty] | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\NW-Security\T316 |  | AD-UT-Tfiber | 2025-05-19
241 | T1 | Security | Configuration |  | Integration testing of All supported devices is complete and adding all the devices is underway. | Sarmendra |  | Packages B&C | DEPENDENCY(Client/Ext.) | Done for the data shared of element. As an when data will be given , integration will be done. |  | Working with all packages. | [18 empty] | #N/A
242 | T5 | Security | Functional AT |  | Had a meeting with Ashwani from Alepo and sent him updated test cases. He is working on data gathering and will send us back by Tuesday. | Sarmendra |  |  | WIP | FAT were submitted to customer, Customer observation in being work out. Target to resubmission.- 23.07.25 | [12 empty] | 1 | [7 empty] | #REF!
257 | T28 | IPMPLS | Functional AT |  | Internal AT 83% complete. Waiting Cisco to update data sent by Vikram and then we will submit to TPA ( for pending cases, we just need a maintanence window to test as it is impacting activity) This is for ISE | Sarmendra |  |  | WIP | FAT were submitted to customer, Customer observation in being work out. Target to resubmission.- 23.07.25 | [12 empty] | 1 | [7 empty] | #REF!
258 | T29 | IPMPLS | Functional AT |  | CSM is having memory issues. Need to sort it out before we do AT. Working on settling that with Cisco. Memory will be allocated and tested in the first week of July | Sarmendra |  |  | COMPLETED & APPROVED | CSM has reached EOS. It is currently non functional and no TAC support exist. | [12 empty] | 1 | [7 empty] | #REF!
259 | T30 | IPMPLS | Functional AT |  | Internal AT 72% complete. Waiting on Cisco to update data sent by Vikram and then we will submit to TPA. ( for pending cases, we just need a maintanence window to test as it is impacting activity) | Sarmendra |  |  | WIP | FAT were submitted to customer, Customer observation in being work out. Target to resubmission.- 23.07.25 | [12 empty] | 1 | [7 empty] | #REF!
290 | T301 | Security | Configuration |  | On A-10 -Configuration done on LB side. WAF will be configure with License | Sarmendra |  |  | WIP | Configuration Completed. WAF License needed and AMC . |  | Getting the AMC of A10 get activated for further action. | [10 empty] | 1 | [7 empty] | #REF!
291 | T302 | Security | Functional AT |  | Will start next week as KT happened this week for all the new resources | Sarmendra |  |  | CLOSURE REVIEW PENDING | [21 empty] | #N/A
292 | T304 | Security | Functional AT |  | Radware LB - Will start next week as KT happened this week for all the new resources | Sarmendra |  |  | WIP | Test case were submitted to customer. Asked to include more test case. | [20 empty] | #N/A
293 | T306 | Security | Documentation |  | Customer has requested a complete Security LLD that states how our security architechture is and how different security products talk to each other | Sarmendra |  |  | WIP | Submittted to TFIBER, T Fiber has some chnages and resubmission plan by 23th july'25 |  | Reworking on LLD. | [10 empty] | 1 | [7 empty] | #REF!
295 | T314 | Security | External Audit and VAPT |  | External Audit and VAPT (Tfiber will be arranging a partner for third party audit) | Sarmendra |  | TFIBER | DEPENDENCY(Client/Ext.) | T Fiber to conduct the Audit and VAPT |  | T Fiber to support for closure with timeline. | [18 empty] | #N/A
297 | T328 | Security | AAA |  | ISE-Completed, Alepo-Completed for Nokia GPON, Accounting feature demo to be done for Tejas GPON and Ciena DWDM | Sarmendra |  |  | WIP | Confirmation of purchase of ISE. License needed to upgrade for HA |  | ISE perpetual license to be uograded and converted from perpetual license to subscription based. | [11 empty] | 1 | [6 empty] | #REF!
298 | T334 | Security | Functional AT |  | Cisco Firewall, ISE, IPS/IDS Functional AT | Sarmendra |  |  | WIP | Licenses to be re activated to excecute the AT. |  | working with internal team and Cisco. | [13 empty] | 1 |  |  |  |  | #REF!
299 | T335 | Security | Design & Documentation |  | Security LLD to finalised and submitted to T-Fiber for approval. Customer has requested a complete Security LLD that states how our security architechture is and how different security products talk to each other | Sarmendra |  |  | WIP | Submittted to TFIBER, T Fiber has some chnages and resubmission plan by 23th july'25 |  | Reworking on LLD. | [10 empty] | 1 | [7 empty] | #REF!
319 | T71 | DR | MoM Action |  | UTM Features (DR FW) | Sarmendra |  |  | WIP | Artefacts will be submitted. | [11 empty] | 1 | [8 empty] | #REF!
338 | T332 | Security | MoM Action |  | Nokia AMS to integrate with Alepo AAA | Sarmendra |  |  | COMPLETED & APPROVED | artefacts need to be generated and submitted
355 | T319 | Security | Policy Implementation |  | Network Hardening | Sarmendra |  |  | WIP | Required IPS URL and anti malware. | [10 empty] | 1 | [9 empty] | #REF!
356 | T320 | Security | Policy Implementation |  | Network Penetration Test | Sarmendra |  | TFIBER | DEPENDENCY(Client/Ext.) | External Audit outcome based actions | [20 empty] | #N/A
357 | T325 | Security | Policy Implementation |  | Organizational Security Policy | Sarmendra |  | TFIBER | DEPENDENCY(Client/Ext.) | Security policy were submitted to customer . Howeever customer has specific requirement , which is other than International standard. Customer member need to be associated with security team to tailor as per customer requirements. |  | T Fiber support for closure timeline. | [18 empty] | #N/A
358 | T311 | Security | QoS Reporting |  | QoS Reporting related to all parameters | Sarmendra |  |  | WIP | Ongoing nature, submission pending |  | QoS is Maintained. Any specific observation if any will be corrected . | [9 empty] | 1 | [8 empty] | #REF!
361 | T313 | Security | Regulatory compliance |  | Communication made to T-Fiber. Procedure need to be finalized for remote access | Sarmendra |  | TFIBER | DEPENDENCY(Client/Ext.) | [21 empty] | #N/A
363 | T326 | Security | Report |  | IPDR static IP report | Sarmendra |  |  | COMPLETED & APPROVED | Points Closed | [21 empty] | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\NW-Security\T326 |  | AD-UT-Tfiber | 2025-05-19
364 | T23 | BSS | Security |  | DMZ requirements for CSP | Sarmendra |  | BSS | WIP | 26-06-2025: Call schedulled with KNOT, Security team and Infra Team to discuss and close. | [11 empty] | 1 | [8 empty] | #REF!
366 | T34 | IPMPLS | Security |  | external Audit for all applications (Tfiber will be arranging a partner for third party audit) | Sarmendra |  | TFIBER | DEPENDENCY(Client/Ext.) | Awaited TSTG Audit party to engage | [20 empty] | #N/A
367 | T35 | IPMPLS | Security |  | external audit for network elements(Tfiber will be arranging a partner for third party audit) | Sarmendra |  | TFIBER | DEPENDENCY(Client/Ext.) | Awaited TSTG Audit party to engage | [20 empty] | #N/A
369 | T384 | IPMPLS | Security |  | GCT implementation | Sarmendra |  |  | WIP | Internal discussions to plan completion 16 July 23 | [12 empty] | 1 | [7 empty] | #REF!
376 | T386 | Security | Testing |  | Network audit and certification by ISO certified agency(Tfiber will be arranging a partner for third party audit) | Sarmendra |  | TFIBER | DEPENDENCY(Client/Ext.) | Awaited TSTG Audit party to engage | [20 empty] | #N/A
390 | T333 | Security | MoM Action |  | Alepo AAA to be integrated with AD | Sarmendra |  | Alepo | DEPENDENCY(Client/Ext.) | SOW, CR and BOQ Shared for approval and consideration. | [20 empty] | #N/A
114 | T299 | OSS | Integrating AD so that there is single user ID for all apps and they can integrate better in future if there is a need |  | Integration testing done for all apps that are ready currently except Alepo. Apps like HP OSS, Cisco ISE and other such applications are already integrated. We can switch IDs to AD anytime | Sarmendra |  | OSS | WIP | Once AD integration happen for Aleppo this point also will be closed along with T333. | [13 empty] | 1 | [6 empty] | #REF!
359 | T40 | Security | Regulatory |  | Regulatory Compliance with respect DoT policies 1. Security Policy-Complied 2. Security Architecture of Telecom Network-Complied 3. Information Security Risk Assessment and Risk Treatment processes and their implementation plan-WIP, Target: Dec 2024 reviewed with customer. 4. Recruitment processes and employee's record-WIP, Target:12-10-2025 5. Controls for effectiveness of security management-WIP, Target: 28 -02-2025 6. Evidence of monitoring, measurement results and management reviews of security management-WIP, Target: 28-02-2025 7. Security Audit programs and audit results-Complied 8. Inventory management and classification of information assets and their handling Completed 9. Procedure for responding to information and network security incidents-WIP, Target: 28-02-2025 - SIRT reviewed 10. Main S/W updation and changes-WIP, Target: 28-02-2025 11. Supply chain of products (HW/SW). To be taken from manufacturer/supplier-Communicated to Sekhar. WIP, Target: 14-02-2025 12. SW details and documentation obtained from manufacturers/supplier-Communicated to Sekhar WIP, Target: 14-02-2025 13. O&M procedures in the form of manual-O&M manual and OEM wise manuals WIP, Target: 14-02-2025 14. Processes for internal and external communication relevant to the security management-WIP, Target: 07-3-2025 | Sarmendra |  | TFIBER | DEPENDENCY(Client/Ext.) | 1.Policy submitted awaiting Tfiber approval 2. HLD submitted awaiting Tfiber approval 3.Policy submitted awaiting Tfiber approval 4. BG and mobile devices management Policy submitted awaiting Tfiber approval 5. Ongoing, Policy submitted awaiting Tfiber approval. ( Customer remarks are being updated) 6. 02 Policy has been approved by TPA . 7.Back up policy work is in progress |  | Points Duplicated as the Policy Points cover all. | [18 empty] | #N/A
| T307 | Security | User Access Rights |  | Cisco: PKGA-testing in WIP, PKGB&C-will be replicated after PKGA completion GPON: Segregation is done, implementation is WIP DWDM: Segregation is done, implementation is WIP HPE OSS: User to access mapping is done, implementation WIP by hp team Other Apps: Will have meetings this week and sort it out. | Sarmendra |  |  | WIP | Evidences preparation is in progress |  | Artefacts will be submitted to customer | [8 empty] | 1 | [9 empty] | #REF!
4 | T21 | BSS | MoM Action |  | BSS firewall ports required for Security compliance | Sarmendra/Manoj Nibrad |  | BSS | WIP | BSSport has been enabled as required by BSS. Rest all port has been hardened. Howver BSS work is still going on . Same will be completed post completion of BSS. |  | Cordinating with BSS and Security teamOne app | [8 empty] | 1 | [9 empty] | #REF!
79 | T162 | GPON-Tejas | Design & Documentation |  | Customer Requirement Document | Sayyad |  |  | COMPLETED & APPROVED | [22 empty] | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T162 |  | AD-UT-Tfiber | 2025-04-30
80 | T163 | GPON-Tejas | Design & Documentation |  | HLD | Sayyad |  |  | COMPLETED & APPROVED | [22 empty] | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T163 Please refer Section-3 in E2E Network HLD |  | AD-UT-Tfiber | 2025-04-30
81 | T164 | GPON-Nokia | Design & Documentation |  | LLD for 152 Mandals | Sayyad |  |  | COMPLETED & APPROVED | [22 empty] | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T164 |  | AD-UT-Tfiber | 2025-04-30
169 | T170 | GPON-Nokia | Nokia |  | Accounting Feature with New build & Logs filteration | Sayyad |  |  | COMPLETED & APPROVED | [22 empty] | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T170 |  | AD-UT-Tfiber | 2025-04-30
170 | T177 | GPON-Nokia | Nokia |  | ONT devices have been recovered and validated as per AMS count. | Sayyad |  |  | COMPLETED & APPROVED | [22 empty] | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T177 |  | AD-UT-Tfiber | 2025-04-30
171 | T178 | GPON-Nokia | Nokia |  | Authentication and authorization have been tested with Nokia devices except CB OLT. | Sayyad |  |  | COMPLETED & APPROVED | [22 empty] | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T178 |  | AD-UT-Tfiber | 2025-04-30
172 | T181 | GPON-Nokia | Nokia |  | Accounting logs are forwarded to Alepo server, same was reflecting in Alepo server but it was forwarding towards syslog server. | Sayyad |  |  | COMPLETED & APPROVED | [22 empty] | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T181 |  | AD-UT-Tfiber | 2025-04-30
173 | T183 | GPON-Nokia | Nokia |  | DC-DR Switchover activity need to plan. | Sayyad |  |  | COMPLETED & APPROVED | [22 empty] | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T183 |  | AD-UT-Tfiber | 2025-04-30
174 | T184 | GPON-Nokia | Nokia |  | Nokia OLTs reachability is pending for DR Servers. | Sayyad |  |  | COMPLETED & APPROVED | [22 empty] | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T184 |  | AD-UT-Tfiber | 2025-04-30
175 | T372 | GPON-Nokia | Nokia |  | TACACS Feature | Sayyad |  |  | COMPLETED & APPROVED | [22 empty] | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T372 |  | AD-UT-Tfiber | 2025-04-30
222 | T165 | GPON-Tejas | Tejas |  | Latest EMS Integration with OSS (Hold due to CR) | Sayyad |  |  | COMPLETED & APPROVED | [22 empty] | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T165 |  | AD-UT-Tfiber | 2025-04-30
223 | T168 | GPON-Tejas | Tejas |  | Authentication & Authorization with RAIDUS | Sayyad |  |  | COMPLETED & APPROVED | [22 empty] | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T168 |  | AD-UT-Tfiber | 2025-04-30
224 | T169 | GPON-Tejas | Tejas |  | EMS authentication & Authorization with Alepo | Sayyad |  |  | COMPLETED & APPROVED | [22 empty] | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T169 |  | AD-UT-Tfiber | 2025-04-30
225 | T172 | GPON-Tejas | Tejas |  | Tejas EMS ATP | Sayyad |  |  | COMPLETED & APPROVED | [22 empty] | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T172 |  | AD-UT-Tfiber | 2025-04-30
226 | T173 | GPON-Tejas | Tejas |  | DC-DR Switchover Activity | Sayyad |  |  | COMPLETED & APPROVED | [22 empty] | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T173 |  | AD-UT-Tfiber | 2025-04-30
227 | T174 | GPON-Tejas | Tejas |  | NBI API availability for BW query Dependent on new OLT build, which supposed to released on 31- March23. | Sayyad |  |  | COMPLETED & APPROVED | [22 empty] | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T174 |  | AD-UT-Tfiber | 2025-04-30
233 | T175 | GPON-Nokia | Nokia |  | CR for Nokia API integration to close BW query and PMS related issues | Sayyad |  | Service Inventory and NSO | DEPENDENCY(Client/Ext.) | 13-Sep-2025: Having dependency on A&O/NSO and service inventory deployment. 29-Aug-2025: Having dependency on A&O/NSO and service inventory deployment. 07-July-2025: L&T Remarks: As per the Tfiber suggestion, this is feasible and will be considered during A&O OEM solution deployemenet. 05-July-2025 : TFiber Comments: Available bandwidth has to be calculated before provisioning service to a customer. Available bandwidth can be achieved either from OSS or from Service Inventory systems- which already have the services provisioned data Internal discussion planned on 07-July-2025 30-June-2025 : To arrange a call with Tfiber for the discussion and conclusion Nokia provided the available upload bandwidth on PON Port but Nokia claiming that devices/AMS does not support to provide the available download bandwidth of a PON Port. This feature is not available with Nokia | [20 empty] | #N/A
343 | T176 | GPON-Nokia | Nokia |  | OLT devices status in OSS is not as per AMS. | Sayyad |  |  | COMPLETED & APPROVED | [22 empty] | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T176 |  | AD-UT-Tfiber | 2025-04-30
344 | T179 | GPON-Nokia | Nokia |  | Tejas ONT firmware upgradation not happing through Nokia OLT. Joint troubleshooting is required with Tejas and Nokia. | Sayyad |  |  | COMPLETED & APPROVED | Tejas ONT under Nokia OLT are able to upgrade | [21 empty] | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T179 |  | AD-UT-Tfiber | 2025-04-30
345 | T180 | GPON-Nokia | Nokia |  | Nokia ONT to support NAT, DHCP, both Router and Bridge mode | Sayyad |  |  | WIP | 13-09-2025 : Nokia has provided the SOP, which has been tested and is working as expected. However, Nokia ONTs connected to Tejas OLTs cannot be enabled directly through the Tejas OLT. As discussed with TFiber, we have prepared an SOP for the field team and are currently working on mapping the Nokia ONTs under Tejas OLTs to nearby Nokia OLTs 30-Aug-2025: To prepare the mapping for the list of Nokia ONTs under Tejas OLT to nearby OLT. Also to prepare the SOP for the field team on what are the actions to be performed 08-Aug-2025 : Services have been successfully delivered at two locations using Hybrid Mode along with port forwarding 02-Aug-2025 : Discussed with TFiber as below 1. Nokia ONTs which are under Nokia OLT will be upgraded 2. ONTs which are under Tejas OLT, will be upgraded upon request and to inform the field teams to connect the Nokia ONTs which are under Tejas OLT to nearby Nokia OLT and inform to NOC for the upgrade. Post upgrad ONT will be connected back to as it is. 22-July-2025 : Discussed with Nokia to provide the solution for the ONTs which are connected under Tejas OLT. They are checking for the solution of carrying a Nokia OLT to the cluster location and connect the Nokia ONTs from Tejas to Nokia OLT and complete the upgrade of the ONT 18-July-2025 : A call scheduled with Nokia on 21-July-2025 to discuss on this issue for the resolution 13-July-2025 : Nokia working internally to check and confirm the below 2 possibilities 1. As per shared MOP, there are 2 files which need to be pushed to ONT. Instead of 2 files provide a single file to enable the Hybrid mode 2. To upgrade the ONTs directly by logging into ONT 04-July-2025 : Nokia confirmed that they will check internally and confirm 02-July-2025 : Tejas confirmed Hybrid mode conversion is not possible from Tejas OLT as Nokia provided 2 files and both has to be download to ONT at same time, which is not possible from Tejas OLT Checking with Nokia to provide alternate solution 25-June-2025 : Nokia shared the SOP and same has been successfully tested in Lab. Working with Tejas on upgrating the Nokia ONTs under Tejas OLT | [20 empty] | #N/A
374 | T167 | GPON-Tejas | Tejas |  | TACACS Feature | Sayyad |  |  | COMPLETED & APPROVED | [22 empty] | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T167 |  | AD-UT-Tfiber | 2025-04-30
375 | T171 | GPON-Tejas | Tejas |  | Accounting Feature with New build & Logs filteration | Sayyad |  |  | COMPLETED & APPROVED | [22 empty] | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T171 |  | AD-UT-Tfiber | 2025-04-30
398 | 398 | GPON-Tejas | Tejas |  | L&T is asked to submit response against untdertakings for the GPON Tejas issues | Sayyad |  |  | COMPLETED & APPROVED | [22 empty] | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\Tejas Undertaking |  | AD-UT-Tfiber | 2025-04-30
399 | 399 | GPON-Tejas | Tejas |  | Requested Tejas to enable the TR-069 for T-Fiber deployed elements | Sayyad |  | Tejas | DEPENDENCY(Client/Ext.) | 13-Sep-2025: Tejas shared the branch tree supported by Tejas ONTs. However confirmation on support of shared list is not provided 28-Aug-2025 : Having Dependency on Tejas Tejas checking internally, update awaited from the Tejas 02-Aug-2025 : Tejas yet to share the confirmation on the support of the parameters which was shared by TFiber 25-July-2025 : Tejas yet to share the confirmation on the support of the parameters which was shared by TFiber 19-July-2025 : Tejas working internally on the shared parameters, after that Tejas will confirm upon the support of those parameters 14-July-2025 : TFiber shared a list of parameters which will be available in ACS. Shared with Tejas, to provide the confirmation of support availability in the ONTs 05-July-2025 : As discussed with TFiber, asked the Tejas to confirm on the list of parameters which fall under TR098 data model. Update awaited from Tejas 02-July-2025 : Tejas confirmed that ONTs are compatible with TR098 data model 30-June-2025 : To escalate OEM by looping Tfiber in mail MoM point Not in RFP and L&T confirmed this is not in scope In the TNOC meeting, Tejas agree to provide the support and post checking Tejas confirmed TR069 feature is compatible in TFiber delpoyed ONTs. However, TFiber asked to provide the more details like what are the parameters can be monitored, configurable parameters etc. Update is awaited from Tejas | [20 empty] | #N/A
400 | 400 | GPON-Tejas | Tejas |  | Accounting for Tejas OLT and EMS | Sayyad |  |  | COMPLETED & APPROVED | [22 empty] | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T167 |  | AD-UT-Tfiber | 2025-04-30
401 | 401 | GPON-Tejas | Tejas |  | Accounting: All the parameters are not available in service created and Activated log(Including creation/activation of UNI) | Sayyad |  |  | COMPLETED & APPROVED | [22 empty] | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T167 |  | AD-UT-Tfiber | 2025-04-30
402 | 402 | GPON-Tejas | Tejas |  | Accounting: All the parameters are not available in service deactivated and deleted log(Including deactivation/deletion of UNI) | Sayyad |  |  | COMPLETED & APPROVED | [22 empty] | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T167 |  | AD-UT-Tfiber | 2025-04-30
403 | 403 | GPON-Tejas | Tejas |  | Accounting: Log is not available for OLT reboot | Sayyad |  |  | COMPLETED & APPROVED | [22 empty] | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T167 |  | AD-UT-Tfiber | 2025-04-30
404 | 404 | GPON-Tejas | Tejas |  | Accounting: Log is not available for ONT reboot | Sayyad |  |  | COMPLETED & APPROVED | [22 empty] | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T167 |  | AD-UT-Tfiber | 2025-04-30
405 | 405 | GPON-Tejas | Tejas |  | Accounting: Log is not available for the change of OLT location parameter from EMS | Sayyad |  |  | COMPLETED & APPROVED | [22 empty] | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T167 |  | AD-UT-Tfiber | 2025-04-30
406 | 406 | GPON-Tejas | Tejas |  | Enabling TACACS in Tejas OLT | Sayyad |  |  | COMPLETED & APPROVED | [22 empty] | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T167 |  | AD-UT-Tfiber | 2025-04-30
407 | 407 | GPON-Tejas | Tejas |  | CIR/PIR in OLT/EMS | Sayyad |  | Tejas | DEPENDENCY(Client/Ext.) | 13-Sep-2025: Update awaited from the Tejas 25-Aug-2025 : Having dependency on Tejas Tejas is working internally with their team for the solution 08-Aug-2025: In the call Tejas confirmed that they will test for a solution and confirm 02-Aug-2025 : Call is scheduled with TFiber on 04-Aug-2025 @4PM 25-July-2025 : Discussed with the TFiber on the prepared policy document and made changes in the document as suggested. However, call to be scheduled with Tejas 11-July-2025 : Call with Tejas scheduled for 11th July 2025 was cancelled due to a conflict with BSS GI-BB demo call. A new call will be scheduled by the availability of both the parties 07-July-2025: L&T Comments: Call will be scheduled with Tejas, L&T and TFiber. Parallelly will prepare the policy document as suggested by TFiber and submit for the review 05-July-2025 : TFiber Comments: 1. To arrange a joint call between TFiber, L&T and Tejas 2. To prepare a policy document which defines the below a) For ILL , only CIR will be configured on Bridge Mode b) For broadband services, bandwidth is not assigned to individual users; instead, it will be on shared basis Internal discussion planned on 07-July-2025 30-June-2025 : To arrange a call with Tfiber for the discussion and conclusion Issue raised with Tejas. OLT TT: 555768, EMS TT: 555700 Tejas confirmed in download profile, CIR and PIR is made available for Bridge Mode but for Route mode, only CIR is available, and PIR is not feasible. However Rate limiting(PIR in Bridge Mode) is not working for Nokia ONT when connected under Tejas OLT | [20 empty] | #N/A
408 | 408 | GPON-Tejas | Tejas |  | Port Description is not available for ONT Eth Ports | Sayyad |  |  | COMPLETED & APPROVED | [22 empty] | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\ONT Ports description |  | AD-UT-Tfiber | 2025-04-30
409 | 409 | GPON-Tejas | Tejas |  | Unable to modify the Service Name | Sayyad |  |  | COMPLETED & APPROVED | Tejas confirmed modifying the service name is available in EMS however service name should be unique 02-July-2025 : Deferred due to not essential | [21 empty] | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\409 |  | AD-UT-Tfiber | 2025-07-03 | Deferred
410 | 410 | GPON-Tejas | Tejas |  | Special Characters not allowing in User Creation in EMS | Sayyad |  |  | COMPLETED & APPROVED | [22 empty] | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\Special Characters |  | AD-UT-Tfiber | 2025-04-30
411 | 411 | GPON-Tejas | Tejas |  | Unable to add 4th UNI in a service with 1Gb bandwidth | Sayyad |  |  | COMPLETED & APPROVED | [22 empty] | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\Report of ONT UNI in a Service |  | AD-UT-Tfiber | 2025-04-30
412 | 412 | GPON-Tejas | Tejas |  | End Customer MAC Address report from EMS | Sayyad |  |  | COMPLETED & APPROVED | [22 empty] | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\Ens users MAC address report |  | AD-UT-Tfiber | 2025-04-30
414 | 414 | GPON-Tejas | Tejas |  | Live PM monitoring per UNI in EMS service Window | Sayyad |  |  | COMPLETED & APPROVED | Issue raised with Tejas. TT: 520074 Tejas stating that it is not recommended to enable PM in all the ONTs in the Network. Recommended to enable the PM on a specific ONT only for specific time 30-June-2025 : To arrange a call with Tfiber for the discussion and conclusion 05-July-2025 : TFiber Comments: PM will be enabled only on GI connected locations Optional : PM can be enabled on HH ONTs for a specific time on a specific ONT. This will be applied for both Tejas and Nokia, recommended by OEM that not to enable the PM on all the ONTs Internal discussion planned on 07-July-2025 07-July-2025: L&T Remarks: As suggested by TFiber, PM will be enabled only on GIs and other ONTs will be in disable mode 10-July-2025: Artifact showcased and submitted | [21 empty] | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\416 |  | AD-UT-Tfiber | 2025-07-10
415 | 415 | GPON-Tejas | Tejas |  | Required Consolidated Service invenotry report with ONT UNI details from EMS | Sayyad |  |  | COMPLETED & APPROVED | [22 empty] | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\Serivce Report |  | AD-UT-Tfiber | 2025-04-30
416 | 416 | GPON-Tejas | Tejas |  | Unable to Enable PM from EMS | Sayyad |  |  | COMPLETED & APPROVED | Issue raised with Tejas. TT: 639643 Tejas stating that it is not recommended to enable PM in all the ONTs in the Network. Recommended to enable the PM on a specific ONT only for specific time 30-June-2025 : To arrange a call with Tfiber for the discussion and conclusion 05-July-2025 : TFiber Comments: PM will be enabled only on GI connected locations Optional : PM can be enabled on HH ONTs for a specific time on a specific ONT. This will be applied for both Tejas and Nokia, recommended by OEM that not to enable the PM on all the ONTs Internal discussion planned on 07-July-2025 07-July-2025: L&T Remarks: As suggested by TFiber, PM will be enabled only on GIs and other ONTs will be in disable mode 10-July-2025: Artifact showcased and submitted | [21 empty] | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\414 |  | AD-UT-Tfiber | 2025-07-07
417 | 417 | GPON-Tejas | Tejas |  | While creating service profile, maximum bandwidth is not taking 1024000 only considering 1000000 | Sayyad |  |  | COMPLETED & APPROVED | Issue raised with Tejas. TT: 648868 Timelines awaited from Tejas 30-June-2025 : Tejas yet to respond with target date 06-July-2025 : Tejas has to respond 25-July-2025 : Able to create and map the download profile with more than 1024000 value, however in upload profile only 1000000 is only allowed due to GPON upload maximum profile is only 1.24 Gbps | [20 empty] | #N/A | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\417 |  | AD-UT-TFiber | 2025-07-31
418 | 418 | GPON-Tejas | Tejas |  | Report of Syslog enabled in OLT | Sayyad |  |  | COMPLETED & APPROVED | [22 empty] | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\Report of Syslog enabled in Tejas OLTs |  | AD-UT-Tfiber | 2025-04-30
419 | 419 | GPON-Tejas | Tejas |  | Report of Radius enable in OLT | Sayyad |  |  | COMPLETED & APPROVED | [22 empty] | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\Report of Radius enabled in Tejas OLTs |  | AD-UT-Tfiber | 2025-04-30
420 | 420 | GPON-Tejas | Tejas |  | OLT (SNMP-V3) status is not updating in EMS | Sayyad |  |  | COMPLETED & APPROVED | [22 empty] | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T167 |  | AD-UT-Tfiber | 2025-04-30
421 | 421 | GPON-Tejas | Tejas |  | ONT status showing as Unexpected | Sayyad |  |  | COMPLETED & APPROVED | [22 empty] | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\ONT Unexpected State |  | AD-UT-Tfiber | 2025-04-30
422 | 422 | GPON-Tejas | Tejas |  | Unable to add multiple unis while creating mixed service | Sayyad |  |  | COMPLETED & APPROVED | [22 empty] | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\Create Service with Mulitple UNIs |  | AD-UT-Tfiber | 2025-04-30
423 | 423 | GPON-Tejas | Tejas |  | ONT ETH Port status monitoring from OSS | Sayyad |  |  | COMPLETED & APPROVED | [22 empty] | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\Tejas LAN LOS |  | AD-UT-Tfiber | 2025-04-30
424 | 424 | GPON-Tejas | Tejas |  | Unable to create service with same vlans on 2 diferent UNI ports | Sayyad |  |  | COMPLETED & APPROVED | [22 empty] | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\Service Report |  | AD-UT-Tfiber | 2025-04-30
425 | 425 | GPON-Tejas | Tejas |  | OLT Node not reachable alarm clearance and regeneration | Sayyad |  | Tejas | COMPLETED & APPROVED | Tejas confirmed this feature is not available in their products. 30-June-2025 : To arrange a call with Tfiber for the discussion and conclusion 05-July-2025 : For the availability report submitted to BBNL, all tickets from 1 April 2024 onward have been considered. Devices that were down prior to this date were tracked separately in a CSV file. To eliminate the dependency on this CSV file, it was necessary to clear and regenerate the corresponding device alarms. However, the CSV file has been removed, and the relevant data has been updated in the OSS database. All logs have been collected and are already available in the OSS database. The availability report is now being generated directly from the OSS database, with no further dependency on the CSV file or the need to clear/regenerate device alarms in the system | [21 empty] | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\425 |  | AD-UT-Tfiber | 2025-07-05
426 | 426 | GPON-Tejas | Tejas |  | Port Description is not available for all ONT UNI Ports | Sayyad |  |  | COMPLETED & APPROVED | [22 empty] | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\ONT Ports description |  | AD-UT-Tfiber | 2025-04-30
427 | 427 | GPON-Tejas | Tejas |  | In the Manage ONT Page we need have'(District name Location Name) 'In the Location field | Sayyad |  |  | COMPLETED & APPROVED | [22 empty] | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\OLT Partition Label in ONT Page |  | AD-UT-Tfiber | 2025-04-30
428 | 428 | GPON-Tejas | Tejas |  | Automatically services converting from Active to Conflict - EMS | Sayyad |  |  | COMPLETED & APPROVED | [22 empty] | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T167 |  | AD-UT-Tfiber | 2025-04-30
429 | 429 | GPON-Tejas | Tejas |  | DIAGUSER credentials getting reset after OLT Reboot | Sayyad |  |  | COMPLETED & APPROVED | [22 empty] | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\DIAGUSER Credentials are Not Resetting |  | AD-UT-Tfiber | 2025-04-30
430 | 430 | GPON-Tejas | Tejas |  | while adding uni in EMS, list of downstream profiles are highlighting in the bottom | Sayyad |  | Tejas | COMPLETED & APPROVED | Timelines awaited from Tejas for the fix 30-06-2025 : Tejas yet to respond with target date 05-July-2025: This task has been deferred as it is not essential and does not involve any complications Communicated to OEM for the resolution in upcoming versions of EMS | [21 empty] | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\430 |  | AD-UT-Tfiber | 2025-07-05 | Defferred
431 | 431 | GPON-Tejas | Tejas |  | Unable to add uni without translation in a translation service | Sayyad |  |  | COMPLETED & APPROVED | [22 empty] | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\Add UNI in Translated Service |  | AD-UT-Tfiber | 2025-04-30
432 | 432 | GPON-Tejas | Tejas |  | Nokia ONT ethernet port status is not updating | Sayyad |  | Nokia & Tejas | DEPENDENCY(Client/Ext.) | 13-Sep-2025: Testing is in progress for the ONT ETH status for different 3rd party ONTs under Tejas OLT 30-Aug-2025: Having dependency on both Tejas and Nokia. Also to test and verify the behaviour of the ONT ETH status for different 3rd party ONTs under Tejas OLT 18-Aug-2025 : Tejas updated as below As per ITU-T 988 standard, Section 9.5.1 – Physical path termination point Ethernet UNI, the Operational State attribute indicated whether the ME is capable of performing its function. As this is function of ONU, the operational state of the ONU Ethernet UNI is updated to OLT via AVC indications from the ONU. As per debugging done, the AVC indications are not received from Nokia ONU because of which OLT is not able to update UI about the “Operational State” of the ONU Ethernet port. 08-Aug-2025 : This point has been discussed in the call and TFiber asked to provide the solution. Tejas confirmed that they will check and confirm 02-Aug-2025 : This issue has been discussed with TFiber. When a LAN cable is connected to or removed from the ONT Ethernet port, the operational status is not updating in the OLT. However, the corresponding alarm is being generated and cleared as expected. This matter will be raised during the Tejas call scheduled for 04-Aug-2025 at 4:00 PM. 22-July-2025 : As per Nokia they are having the status update by alarm notification but not with the seperate byte for the status update. Same has been checking with Tejas to get the solution 18-July-2025 : A call scheduled with Nokia on 21-July-2025 to discuss on this issue 11-July-2025 : Also observed that ONT ethernet status is not updating only when Eth port is bridge mode whereas in Route status is updating. Same has been highlighted to Tejas. Working with both Nokia and Tejas for the closure 04-July-2025 : Nokia checking internally on the shared logs 03-July-2025 : Tejas responded that whenever ONT eth status is updating Nokia ONT is not sending the expected OMCI message. In the OMCI message, 3rd byte represents the status of ONT Eth which is not updating. Same has been checking with Nokia 30-June-2025 : Tejas analysing the shared logs on 23-June-2025 and Tejas has to revert with update Nokia ONT ethernet port status is not updating when connected under Tejas OLT however alarms are receiveing on ont eth port. Workaround applied as alarms available for the ONT ETH port status. Nokia has provided the required logs and Tejas is working on the same | [20 empty] | #N/A
433 | 433 | GPON-Tejas | Tejas |  | Tejas ONT Software Upgrade which are connected under Nokia OLT | Sayyad |  | Tejas | DEPENDENCY(Client/Ext.) | 13-Sep-2025: Tejas confirmed that they don't have the 9logs to provide but shared the RCA by verifyting the ONTs at the time of repair 30-Aug2025: Having dependency on Tejas. Asked Tejas to provide the supporting logs. As per Tejas RCA ONT got faulty due to component faulty and memory corruption but these ONTs are working fine before the upgarde activity and only went faulty while performing the upgrade. Tejas have provide the clarity on this to proceed the upgrade for the remaining ONTs 08-Aug-2025 : Tejas provided the below RCA As per analysis, the ONT software upgrade from NOC is not the cause for ONT going down. On 3 ONTs a component was entering faulty state, this has been replaced. Remaining 8 ONTs had a file corruption in memory due to earlier multiple reboot events, this has been resolved by Re-Programming the ONT 02-Aug-2025 : Tejas yet to respond on this issue, same will be raised during the Tejas call scheduled for 04-Aug-2025 at 4:00 PM. 25-July-2025 : Tejas working on the delivered ONTs at their repair center. Tejas yet to share the update on this 14-July-2025 : ONTs delivered at Tejas repair center on 14-July-2025. Same has been communicated to Tejas team to expedite the process and share the RCA 14-July-2025 : ONT still not delivered at Tejas repai center, seems to be courier issue. Informed to concerned team to check and make it to delivier 07-July-2025 : ONTs are intransit to Tejas repair center To provide the contract of RMA on faulty devices replacement or repair 30-June-2025 : Successfully upgraded 600 ONTs in the production environment. All of them came up operational with no issue observed. However, 11 ONTs went unresponsive, and RMA raised for those. 23-June-2025 : RMA raised with Tejas for the ONTs ONTs which are running software version lower than 2.3.5.53 are upgrading locally | [18 empty] | 1 |  | #REF!
435 | 435 | GPON-Tejas | Tejas |  | Unable to configure downstream profiles to the ONT UNIs -- This option is available in production EMS but not available in latest released EMS | Sayyad |  |  | COMPLETED & APPROVED | [22 empty] | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T167 |  | AD-UT-Tfiber | 2025-04-30
436 | 436 | GPON-Tejas | Tejas |  | MAC address of end device is not reflecting in COLT FDB entries whereas MAC address is available in service level FDB entries | Sayyad |  |  | COMPLETED & APPROVED | [22 empty] | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T167 |  | AD-UT-Tfiber | 2025-04-30
437 | 437 | GPON-Tejas | Tejas |  | Whenever the ONT software is being downloaded to the OLT, the OLT management going down | Sayyad |  | Tejas | COMPLETED & APPROVED | Issue raised with Tejas. TT: 710520 This issue is observed only in Pizzabox OLT and also observed there is no impact on traffic. Update awaited from Tejas for fix OLT is coming reachable within a minute without any manual intervention 30-June-2025 : Tejas yet to respond with target date 03-July-2025 : Tejas is checking internally to provide the resolution 16-July-2025 : Tejas Comments: The s/w download to OLT from server is a one-time activity. Further upon, the ONTs upgrade can be done without disruption 25-July-2025 : The ONT software is downloaded to the OLT only once. During this process, OLT management is going down for about a minute, but there is no impact on traffic. The OLT becomes reachable automatically without any manual intervention. | [20 empty] | #N/A | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\437 |  | AD-UT-TFiber | 2025-07-31
438 | 438 | GPON-Tejas | Tejas |  | The download bandwidth is not controlled for Nokia ONTs connected to the Tejas OLT | Sayyad |  |  | COMPLETED & APPROVED | [22 empty] | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T167 |  | AD-UT-Tfiber | 2025-04-30
439 | 439 | GPON-Tejas | Tejas |  | Unable to add node in EMS with TACACS user | Sayyad |  |  | COMPLETED & APPROVED | [22 empty] | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T167 |  | AD-UT-Tfiber | 2025-04-30
440 | 440 | GPON-Tejas | Tejas |  | API for ONT creation (Bridge/Route), location name update | Sayyad |  |  | COMPLETED & APPROVED | [22 empty] | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API |  | AD-UT-Tfiber | 2025-04-30
441 | 441 | GPON-Tejas | Tejas |  | API for GI-BB Service, combo port, mixed service - Bridge Mode with/without translation, including uplink port configuration | Sayyad |  |  | COMPLETED & APPROVED | [22 empty] | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API |  | AD-UT-Tfiber | 2025-04-30
442 | 442 | GPON-Tejas | Tejas |  | API for GI-BB Service, combo port, mixed service - Route Mode with/without translation, including uplink port configuration | Sayyad |  | Tejas | COMPLETED & APPROVED | Tejas released the EMS software and testing is in progress 05-July-2025 : Testing of EMS version EMS_Release_8_1_0_a58_21_7 has been completed. However, Tejas has confirmed that the next version of EMS will be released by 14 July 2025 and has recommended upgrading to the upcoming release 19-July-2025 : This is resolved in latest release of Tejas EMS version EMS_Release_8_1_0_a58_21_8. Same will review with TFiber for the closure 25-July-2025 : This is resolved in EMS version EMS_Release_8_1_0_a58_21_8. But there is a change in the ONT PM report attributes, same has been communicated to OSS along with the sample. OSS will make the necessary changes and test in T&D. 28-July-2025 : OSS confirmed there is no impact in OSS PM report due to file attribute change 02-Aug-2025 : DC production PKG-A Tejas EMS upgraded successfully and observed there is no impact on OSS with respect to alarms, inventory, bandwidth utilisation of OLT/ONT. This point has been discussed with TFiber, Tfiber suggested the changes in the artifact to add the screenshots of services working through DHCP 05-Aug-2025 : Added the required screenshots as suggested by T-Fiber in the artifacts | [12 empty] | 1 | [7 empty] | #REF! | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\442 |  | AD-UT-TFiber | 2025-08-06
443 | 443 | GPON-Tejas | Tejas |  | API for TDIA Service, combo port, mixed service - Bridge Mode(Tag, Untag) including uplink port configuration | Sayyad |  |  | COMPLETED & APPROVED | [22 empty] | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API |  | AD-UT-Tfiber | 2025-04-30
444 | 444 | GPON-Tejas | Tejas |  | API for TDIA Service, combo port, mixed service - Route Mode, including uplink port configuration | Sayyad |  |  | COMPLETED & APPROVED | [22 empty] | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API |  | AD-UT-Tfiber | 2025-04-30
445 | 445 | GPON-Tejas | Tejas |  | API for Household Services, including uplink port configuration | Sayyad |  |  | COMPLETED & APPROVED | [22 empty] | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API |  | AD-UT-Tfiber | 2025-04-30
446 | 446 | GPON-Tejas | Tejas |  | AP for IPTV services, including uplink port configuration | Sayyad |  |  | COMPLETED & APPROVED | [22 empty] | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API |  | AD-UT-Tfiber | 2025-04-30
447 | 447 | GPON-Tejas | Tejas |  | API for VOIP services, including uplink port configuration | Sayyad |  |  | COMPLETED & APPROVED | [22 empty] | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API |  | AD-UT-Tfiber | 2025-04-30
448 | 448 | GPON-Tejas | Tejas |  | API required to provision ONT along with selecting specific UNI port in ONT | Sayyad |  |  | COMPLETED & APPROVED | [22 empty] | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API |  | AD-UT-Tfiber | 2025-04-30
449 | 449 | GPON-Tejas | Tejas |  | API required to provision ONT with multiple services along with selecting specific UNI port in ONT | Sayyad |  |  | COMPLETED & APPROVED | [22 empty] | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API |  | AD-UT-Tfiber | 2025-04-30
450 | 450 | GPON-Tejas | Tejas |  | API required to provision ONT with same service on all ports | Sayyad |  |  | COMPLETED & APPROVED | [22 empty] | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API |  | AD-UT-Tfiber | 2025-04-30
451 | 451 | GPON-Tejas | Tejas |  | API to configure multiple vlans on single ONT UNI Port | Sayyad |  |  | COMPLETED & APPROVED | [22 empty] | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API |  | AD-UT-Tfiber | 2025-04-30
452 | 452 | GPON-Tejas | Tejas |  | API for the Q&Q services | Sayyad |  |  | COMPLETED & APPROVED | [22 empty] | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API |  | AD-UT-Tfiber | 2025-04-30
453 | 453 | GPON-Tejas | Tejas |  | Configuration, API for extedning services to enterprise customers for cell towers | Sayyad |  |  | COMPLETED & APPROVED | [22 empty] | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API |  | AD-UT-Tfiber | 2025-04-30
454 | 454 | GPON-Tejas | Tejas |  | API to configure Rythuvedika, MRO, School Services, CCTV | Sayyad |  |  | COMPLETED & APPROVED | [22 empty] | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API |  | AD-UT-Tfiber | 2025-04-30
455 | 455 | GPON-Tejas | Tejas |  | API to verify and enable the PM | Sayyad |  |  | COMPLETED & APPROVED | [22 empty] | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API |  | AD-UT-Tfiber | 2025-04-30
456 | 456 | GPON-Tejas | Tejas |  | API to configure Vlan and Profiles in OLT | Sayyad |  |  | COMPLETED & APPROVED | [22 empty] | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API |  | AD-UT-Tfiber | 2025-04-30
457 | 457 | GPON-Tejas | Tejas |  | Verification of the services configured by NSO through Playbook(Cisco Tool) | Sayyad |  |  | COMPLETED & APPROVED | [22 empty] | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API to validate the configured Services |  | AD-UT-Tfiber | 2025-04-30
458 | 458 | GPON-Tejas | Tejas |  | API to configure ONT UNI Port as tagged vlan | Sayyad |  |  | COMPLETED & APPROVED | [22 empty] | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API |  | AD-UT-Tfiber | 2025-04-30
459 | 459 | GPON-Tejas | Tejas |  | API to validate the profiles, vlans available in OLT,ONT | Sayyad |  |  | COMPLETED & APPROVED | [22 empty] | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API to validate the configured Services |  | AD-UT-Tfiber | 2025-04-30
460 | 460 | GPON-Tejas | Tejas |  | API to change the ONT ETH Port to Bridge to Route and Vice versa | Sayyad |  |  | COMPLETED & APPROVED | [22 empty] | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API |  | AD-UT-Tfiber | 2025-04-30
461 | 461 | GPON-Tejas | Tejas |  | API to suspend/delete the service from a ONT UNI Port | Sayyad |  |  | COMPLETED & APPROVED | [22 empty] | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API |  | AD-UT-Tfiber | 2025-04-30
462 | 462 | GPON-Tejas | Tejas |  | API to suspend/delete the complete service | Sayyad |  |  | COMPLETED & APPROVED | [22 empty] | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API |  | AD-UT-Tfiber | 2025-04-30
463 | 463 | GPON-Tejas | Tejas |  | API to modify the service- ONT, UNI Port, bandwidth, vlan, description, unatgged to tag or vice versa., | Sayyad |  | KNOT | DEPENDENCY(Client/Ext.) | 13-Sep-2025: Having dependency on BSS and NSO 29-Aug-2025: Having dependency on BSS and NSO 01-Aug-2025 : Having dependency on BSS and NSO 22-July-2025 : Having dependency on BSS and NSO 07-July-2025: L&T Remarks: As every operation of the services are intiated from BSS, modified logs will be available in BSS system 05-July-2025: TFiber Comments: Whenever a service modification request arises, the corresponding log should be maintained in the BSS, Provisioning System, or Service Inventory. However, at the network layer, the change may be implemented by deleting and recreating the service. Discussion will be held internally on 07-July-2025 Internal discussion planned on 07-July-2025 30-June-2025 : To arrange a call with Tfiber for the discussion and conclusion Tejas confirmed ONT location/description can be modified but there are no modify APIs available for others Recommended is delete and recreate the service | [20 empty] | #N/A
464 | 464 | GPON-Tejas | Tejas |  | API to configure and delete the WAN profiles in WiFi ONT | Sayyad |  |  | COMPLETED & APPROVED | [22 empty] | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API |  | AD-UT-Tfiber | 2025-04-30
465 | 465 | GPON-Tejas | Tejas |  | API to make PON Port admin up / down | Sayyad |  |  | COMPLETED & APPROVED | [22 empty] | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API |  | AD-UT-Tfiber | 2025-04-30
466 | 466 | GPON-Tejas | Tejas |  | API to create/delete service Profile | Sayyad |  |  | COMPLETED & APPROVED | [22 empty] | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API |  | AD-UT-Tfiber | 2025-04-30
467 | 467 | GPON-Tejas | Tejas |  | Required complete API and Template developer document | Sayyad |  |  | COMPLETED & APPROVED | [22 empty] | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API Document |  | AD-UT-Tfiber | 2025-04-30
468 | 468 | GPON-Nokia | Nokia |  | ONT Ethernet Port PM Report | Sayyad |  |  | COMPLETED & APPROVED | [22 empty] | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\ONT ETH PM Report |  | AD-UT-Tfiber | 2025-04-30
469 | 469 | GPON-Nokia | Nokia |  | ONT Wifi/Route Mode PM Report | Sayyad |  |  | COMPLETED & APPROVED | [22 empty] | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\ONT WiFi PM Report |  | AD-UT-Tfiber | 2025-04-30
470 | 470 | GPON-Nokia | Nokia |  | PM Report for 24hrs of OLT,ONT,ONT Eth Port(Bridge/Route), Wifi | Sayyad |  | Nokia | COMPLETED & APPROVED | Nokia support required to enable the PM report for 24hrs Better solution available in OSS using 15mins PM files 30-06-2025 : Nokia yet to respond with target date 04-July-2025 : As per Nokia, this has to implement and test on non-production setup, follow up call with Nokia planned on 07-July-2025 13-July-2025 : Planning to implement this first in DR and post testing it will be implemented in DC. Nokia asked for the logs which were shared to them 18-July-2025 : A call scheduled with Nokia on 21-July-2025 to discuss on this issue 25-July-2025 : Since it is already capturing in OSS from EMS 15mins files so OSS will provide the 24hrs data by consolidating. This action item is deferred | [20 empty] | #N/A | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\470 |  | AD-UT-TFiber | 2025-07-31
471 | 471 | GPON-Nokia | Nokia |  | ONT ETH Port status monitoring from OSS | Sayyad |  |  | COMPLETED & APPROVED | [22 empty] | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\Nokia LAN LOS |  | AD-UT-Tfiber | 2025-04-30
472 | 472 | GPON-Nokia | Nokia |  | Unable to browse Internet when IPV6 configured in wifi ONT | Sayyad |  | Nokia | COMPLETED & APPROVED | Nokia support required to troubleshoot this issue 17-05-2025 : Nokia TAC commenting this is not not tested earlier and asking to check with Nokia solution team. 26-06-2025: Nokia team took the access of the setup, captured the required logs and they will provide update after checking with internal team Nokia will respond by 30-06-2025 04-July-2025 : Nokia collected the relevent logs. They are checking internally and will confirm by 09-July-2025 11-July-2025 : The Nokia product team joined the call to troubleshoot the issue, but it remains unresolved. They mentioned that they will investigate internally and get back to us by 14th July 2025. 14-July-2025 : Call scheduled with R&D team today at 2pm 18-July-2025 : R&D team joined the call and worked on this issue. They will revert by 21-July-2025 25 -July-2025 : Tested successfully IPV6 service through Nokia Wi-Fi ONT and working fine |  | Working with Nokia team for the solution | [10 empty] | 1 | [7 empty] | #REF! | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\472 |  | AD-UT-TFiber | 2025-07-31
150 | T298 | GPON-Tejas | MoM Action |  | Deployment process - Process of building network & passive device connectivity to T-NOC through SG350, ONT (One port Voice, 2nd - Data, 3rd - Video & 4 th port to T-NOC for SNMP traps) . Along with , and also all other Services to be test and provision in SG350 | Sayyad |  |  | COMPLETED & APPROVED | [22 empty] | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T298 |  | AD-UT-Tfiber | 2025-04-30
413 | 413 | GPON-Tejas | Tejas |  | If Mixed service deleted from EMS and discovered then service type is changing to HIS | Sayyad |  |  | COMPLETED & APPROVED | [22 empty] | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\Discovery of Mixed Service |  | AD-UT-Tfiber | 2025-04-30
434 | 434 | GPON-Tejas | Tejas |  | Script to change the pasword of DIAGUSER and tejas users | Sayyad |  |  | COMPLETED & APPROVED | [22 empty] | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\434 |  | AD-UT-Tfiber | 2025-04-30
121 | T353 | TNOC-Ops | Helpdesk |  | Regulatory Compliance_PMR on QoS | Siva Kumar |  |  | COMPLETED & APPROVED | [22 empty] | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\T353 |  | AD-UT-Tfiber | 2025-05-13
122 | T361 | TNOC-Ops | Helpdesk |  | Updated Process document Submission after last Meeting with T Fiber Management | Siva Kumar |  |  | COMPLETED & APPROVED | [22 empty] | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\T361 |  | AD-UT-Tfiber | 2025-05-13
124 | T363 | TNOC-Ops | Helpdesk |  | IVR Recording file required for call landing and Hold time | Siva Kumar |  |  | COMPLETED & APPROVED | [22 empty] | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\T363 |  | AD-UT-Tfiber | 2025-05-13
125 | T367 | TNOC-Ops | Helpdesk |  | Training for Agents and Helpdesk Manager | Siva Kumar |  |  | COMPLETED & APPROVED | [22 empty] | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\T367 |  | AD-UT-Tfiber | 2025-05-13
126 | T370 | TNOC-Ops | Helpdesk |  | If all 10 lines are engaged for a longer time. Can the Helpdesk system call back to that missed call? | Siva Kumar |  | WIP | WIP | 11-Sep-25: OEM confirmed this feature is not available/feasible Based on CDR record with Agent and Manager Login, Call back can be done manually with CDR or Agent Call report. It will be displayed in queue to agent. But Missed call to be handled by outbound team. Which required complete Set of call Center. If required Helpdesk Manager will review missed call to take action accordingly. | 2025-07-18 | OEM Working with R&D Team | [9 empty] | 1 | [8 empty] | #REF! |  |  |  |  | OEM confirmed this feature is not available/feasible Based on CDR record with Agent and Manager Login, Call back can be done manually with CDR or Agent Call report. It will be displayed in queue to agent. But Missed call to be handled by outbound team. Which required complete Set of call Center. If required Helpdesk Manager will review missed call to take action accordingly.
157 | T352 | TNOC-Ops | MoM Action |  | Induction Training program – To be developed and feedback mechanism to be considered, for newly on-boarded resources | Siva Kumar |  |  | COMPLETED & APPROVED | [22 empty] | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\T166 |  | AD-UT-Tfiber | 2025-05-13
167 | T356 | TNOC-Ops | NOC Operation |  | OEM Escalation processes for NOC Applications, DBs, IT Infra and Network along with TATs aligned to SLA | Siva Kumar |  |  | COMPLETED & APPROVED | 28Jun25: Discussed with TFiber with details available in Escalation Matrix excel sheet. Asked to share Dates for support validity from system screenshots. 02Jul25: Screenshots taken for HPE servers, Cisco. Rest WIP. For many Support Date not available on system. List is being made. Will discuss on 05Jul with TFiber for further approvals. 08Jul25: Screenshots from support portal, system, mail and LOI collated in a PDF file and uploaded in NAS server. Mail sent to TFiber for approval | 2025-07-09 | [9 empty] | 1 | [9 empty] | #REF! | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\TNOC |  | ad-ut-tfiber | 2025-07-08
231 | T369 | TNOC-Ops | Helpdesk |  | If T-NOC is totally down for some reason like fire, earthquake, lockdown etc….then how Helpdesk will work from DR? | Siva Kumar |  | WIP | WIP | [13 empty] | 1 | [7 empty] | #REF! |  |  | Not part of RFP
232 | T365 | TNOC-Ops | Helpdesk |  | Integration of Whatsapp, Chatbot | Siva Kumar |  | TFIBER | DEPENDENCY(Client/Ext.) | 11-Sep-25: Not Part of RFP and Existing product didn’t support, need to upgrade to Omni based Solution. | [20 empty] | #N/A
301 | T351 | TNOC-Ops | Design & Documentation |  | Helpdesk Readiness Plan | Siva Kumar |  | WIP | WIP | 1. Soft training completed on 06&07 Sep 2. All Resources will be from L&T only- Resource available to handle current calls 3. updated process document shared, Pending for discussion 4. SOP Submitted for inbound and outbound calls- Discussion Pending 5. Regulatory reports were available(DOT) 6. Integration with OSS and BSS is Pending 7. Based on trainer suggestion, implemented day to day and weekly assestments 8. Neox call Manager functioanlity validated as standlone 9. All Features required for Call Manager completed including Business Helpdesk 10. LLD and RFP Compliance also ready for review | [6 empty] | 0.2 | 0.2 | 0.2 |  |  | 1 | [8 empty] | #REF! |  |  |  |  | 1. Soft training completed on 06&07 Sep 2. All Resources will be from L&T only- Resource available to handle current calls 3. updated process document shared, Pending for discussion 4. SOP Submitted for inbound and outbound calls- Discussion Pending 5. Regulatory reports were available(DOT) 6. Integration with OSS and BSS is Pending 7. Based on trainer suggestion, implemented day to day and weekly assestments 8. Neox call Manager functioanlity validated as standlone 9. All Features required for Call Manager completed including Business Helpdesk 10. LLD and RFP Compliance also ready for review
302 | T358 | TNOC-Ops | Functional AT |  | Network HOTO and KT from Respective Domain and Packages | Siva Kumar |  |  | WIP | 1. Basis monthly O&M scope coming from TFiber for mandals/GP, NOC is doing monitoring and measuring KPIs 2. Network: NOC SME and L2 managing DWDM, IP MPLS, GPON, DC Active Infra, DC Security, DC WAN/L&S, DC Passive elements 3. DC Applications: On the job trainings for OSS, BSS, Automation happening. GIS NOC team working full fledged. Cisco NSO deplopyment pending which is delaying closure of this point. | 2025-08-20 | [15 empty] | 1 |  |  |  | #REF!
303 | T364 | TNOC-Ops | Helpdesk |  | Integration with BSS and OSS | Siva Kumar |  |  | WIP | 11-Sep-25: Basic integration completed with BSS and HPSM(Ticketing). IVR has to be freezed to implement same. As per Neox is one time configuration but Since its ongoing changes will happen in IVR, So it would be configurble as per L&T/T Fiber- Which to be discussed. 360 View also Pending from BSS |  | Dependent on IVR Flow Approval from T Fiber | [18 empty] | #N/A |  |  |  |  | Basic integration completed with BSS and HPSM(Ticketing). IVR has to be freezed to implement same. As per Neox is one time configuration but Since its ongoing changes will happen in IVR, So it would be configurble as per L&T/T Fiber- Which to be discussed. 360 View also Pending from BSS
304 | T366 | TNOC-Ops | Helpdesk |  | Fancy 4 digit number for Helpdesk or Tollfree number Availability | Siva Kumar |  |  | COMPLETED & APPROVED | Differed due to action to be taken from T fiber Management.. communication letter already submitted to T fiber that a official letter from T fiber to be given to DOT for same | [20 empty] | #N/A | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\T366 |  | AD-UT-Tfiber | 2025-07-19
317 | T365 | TNOC-Ops | Helpdesk |  | Integration of SMS, E-Mail | Siva Kumar |  | TFIBER | DEPENDENCY(Client/Ext.) | E-mail & SMS Integration completed. SMS testing pending due to no balance in SMS striker portal. 28 Apri-2025: TFIBER to share SMS GW details to integrate with OSS/BSS. Integration must be configurable without any cost impact to TFIBER. | [20 empty] | #N/A |  |  |  |  | E-mail & SMS Integration completed. SMS testing pending due to no balance in SMS striker portal. 28 Apri-2025: TFIBER to share SMS GW details to integrate with OSS/BSS. Integration must be configurable without any cost impact to TFIBER.
360 | T312 | Security | Regulatory compliance |  | SLA Reporting for Cell Tower and GIs | Siva Kumar |  |  | COMPLETED & APPROVED | [22 empty] | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\T312 |  | AD-UT-Tfiber | 2025-05-13
362 | T387 | Security | Regulatory compliance |  | SLA Reporting for products other than Cell Tower and GIs | Siva Kumar |  |  | COMPLETED & APPROVED | Points closed | [21 empty] | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\T387 |  | AD-UT-Tfiber | 2025-05-13
123 | T362 | TNOC-Ops | Helpdesk |  | Categorisation of incoming calls to be detailed and IVR to bilingual(Incoming IVR call flow) | Siva Kumar |  |  | COMPLETED & APPROVED | [22 empty] | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\T362 |  | AD-UT-Tfiber | 2025-05-13
230 | T368 | TNOC-Ops | Helpdesk |  | Interface mechanism between T-NOC Helpdesk and District Collector offices for complaints that may be made directly(Walk-in) to District Collector office, provision for a mini-Helpdesk node at each district, provide a facility/ hotline using which an authorised person can log a call / complaint on behalf of the District Collector Office, such mechanism to be similar to the Direct walk-in channel for customer complaints at T-NOC | Siva Kumar |  |  | COMPLETED & APPROVED | Test completed in Baddenpally GP(Sircilla Dist) and as well call forwarding to T Fiber office, Same solution shall be extended to District Collectarate office | [20 empty] | #N/A | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\T368 |  | AD-UT-Tfiber | 2025-07-19
342 | T360 | TNOC-Ops | NOC Operation |  | Domain wise training | SMEs / Ahmad |  |  | WIP | 1. GPON :Inhouse and OEM completed 2. Skilled Resources available for DWDM, IP-MPLS, DC Infra, DC Passive & OSS. 3. On the job training for OSS, BSS happening (Jakky, Bindu Madhav, etc working with Engineering team) 4. In house trainings being conducted by SME/L3 to NOC team members 5. NSO & Security Policy/SOP training to be done post NSO deloyment and approvals of security SOPs/HLD/LLD . Till that time, this point will remain open | 2025-08-20 | 1. Security Policy approval 2. NSO - decision | [14 empty] | 1 |  |  |  | #REF!
308 | T376 | A&O Solution | Deployment and Installations |  | Internet to GI (Govt. Institution) implementation | Jayant Madavi |  | Alternate OEM Solution | DEPENDENCY(Client/Ext.) | Post 24.06.25 review and direction, working for a alternate options for NSO. will come back as earliest with closure plan. |  | Interim inhouse solution made available | [18 empty] | #N/A
311 | T379 | A&O Solution | Deployment and Installations |  | Cell Tower L2VPN implementation | Jayant Madavi |  | Alternate OEM Solution | DEPENDENCY(Client/Ext.) | Post 24.06.25 review and direction, working for a alternate options for NSO. will come back as earliest with closure plan. |  | Interim inhouse solution made available | [18 empty] | #N/A
15 | T89 | DWDM | Design & Documentation |  | HLD (Revised) with OADM Solution | Suresh Kumar |  |  | COMPLETED & APPROVED | [22 empty] | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\DWDM\Artefact - T89 |  | AD-UT-Tfiber | 2025-05-06 |  | 25-08-25: HPE Replied that Working on it 23-08-25:Ticketing is not created properly for all incidnets related to DWDM and informed to HPE
16 | T90 | DWDM | Design & Documentation |  | LLD (Revised) with OADM Solution (Ciena) | Suresh Kumar |  |  | COMPLETED & APPROVED | [22 empty] | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\DWDM\Artefact - T90 |  | AD-UT-Tfiber | 2025-05-06
17 | T91 | DWDM | Design & Documentation |  | Nodal ATP | Suresh Kumar |  |  | COMPLETED & APPROVED | [22 empty] | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\DWDM\Artefact - T91 & T92 |  | AD-UT-Tfiber | 2025-05-06
18 | T92 | DWDM | Design & Documentation |  | Link ATP | Suresh Kumar |  |  | COMPLETED & APPROVED | [22 empty] | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\DWDM\Artefact - T91 & T92 |  | AD-UT-Tfiber | 2025-05-06
19 | T93 | DWDM | Design & Documentation |  | Ring ATP | Suresh Kumar |  |  | COMPLETED & APPROVED | [22 empty] | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\DWDM\Artefact - T93 |  | AD-UT-Tfiber | 2025-05-06
20 | T94 | DWDM | Design & Documentation |  | DWDM EMS (MCP) Functional ATP | Suresh Kumar |  |  | WIP | 13-Sep-25: Response awaited from TPA team 29-August-2025: Spoken with Mr. Bijju, response awaited 26-July-25: FAT document approval pending 08-July-2025: 1. MCP FAT document prepared as per RFP requirements and TPA remarks 2. 100G traffic throughput will be shown during Ring ATP 07-July-2025: 1. SME not aware of MCP FAT Check list, but prepared FAT document and sent to TPA for validation 05-July-2025: Submitted AT document to T Fiber TPA 30-June-2025: target to submit by 2nd July'25, based on OEM reply Revised version to be submitted as per T Fiber remarks on 29th Apr'25 | [9 empty] | 1 | [10 empty] | #REF!
21 | T95 | DWDM | Integration with OSS |  | DWDM Network Alarms Integration | Suresh Kumar |  |  | COMPLETED & APPROVED | [22 empty] | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\DWDM\Artefact - T95 |  | AD-UT-Tfiber | 2025-05-06
22 | T96 | DWDM | Integration with OSS |  | Hardware Inventory Integration in HPE OSS | Suresh Kumar |  |  | COMPLETED & APPROVED | [22 empty] | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\DWDM\Artefact - T96 |  | AD-UT-Tfiber | 2025-05-06
23 | T97 | DWDM | Integration with OSS |  | DWDM Network Topology | Suresh Kumar |  | HPE | DEPENDENCY(Client/Ext.) | 26-July-2025: Superimposing border map on existing map denied by HP as their R&D team confirmed it is not possible. Further POA awaited from OSS team 12-July-2025: Update awaited from HPE 07-July-2025: Topology is visible but border is not highlighted. HP checking for the possibility to impose of border map on topology. Required 02 weeks post confirmation 05-July-2025: In discussion with HPE, required 02 weeks post confirmation, 21st July 30-June-2025: As discussed with Suresh P checking with HPE. Tentative date: 16th July. As discussed in the meeting, call to be arranged along with OSS SME and HP team |  | working with OSS OEM /SME. | [18 empty] | #N/A
24 | T98 | DWDM | Integration with OSS |  | Auto Ticket & RCA for Fiber Cuts | Suresh Kumar |  |  | COMPLETED & APPROVED | [22 empty] | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\DWDM\Artefact - T98 |  | AD-UT-Tfiber | 2025-05-06
25 | T99 | DWDM | Integration with OSS |  | Auto Ticket & RCA for Hardware Failures | Suresh Kumar |  | OSS | COMPLETED & APPROVED | Hardware failure Auto TT history not available/not generating in OSS Console 21-05-2025: WIP with HPE, 10th June 2025 15-06-2025: WIP with HPE, target date 21-06-25 30-June-2025: WIP with HPE, target date 09-07-25 As discussed in the meeting, call to be arranged along with OSS SME and HP team 05-July-25: In progress with HPE, revised target date would be 14th July 12-July-25: RCA TT's raising for all type of hardware now, observed details are missing in SM. Same raised to HP. Target date - 18-07-25 19_July-25: Issue resolved and RCA TT's are raised with the required details for all hardware type 26-July-25: Got confirmation from client for the point closure | [10 empty] | 1 | [9 empty] | #REF!
26 | T100 | DWDM | Integration with OSS |  | Auto Ticket & RCA for Infra Failures | Suresh Kumar |  | OSS | WIP | 13-09-25: Few issues observed, corrected by HP. Validation is in progress 10-08-2025: HP team confirmed cause of failure updated, validation is in progress 26-July-2025: Raised the concerns to HP team, cause of failure yet to update by them, Target date awaited9 12-July-2025: Configuration updated in production and RCA TT's for node down are generating. But having issue in cause of failure, same informed to HP team. Target date - 18-07-25 05-July-2025: Cofiguration in production planned on 8th July'25 30-June-25: WIP with HPE, target date 09-07-25 As discussed in the meeting, call to be arranged along with OSS SME and HP team 15-06-2025: WIP with HPE, target date 30-06-2025 21-05-2025: RCA Yet to be started by HPE, date: 30th June 2025 30APR'25: Node down Auto TT is ok but RCA pending |  | working with OSS OEM /SME. | [8 empty] | 1 | [9 empty] | #REF!
27 | T102 | DWDM | Integration with OSS |  | Bandwidth Utilization Data in HPE OSS | Suresh Kumar |  |  | COMPLETED & APPROVED | [22 empty] | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\DWDM\Artefact - T102 |  | AD-UT-Tfiber | 2025-05-06
28 | T105 | DWDM | Integration with NSO |  | 1+1 , 1+0 and 1+R service provisioning testing through NSO | Suresh Kumar |  | NSO/Alternate OEM Solution | DEPENDENCY(Client/Ext.) | Post 24.06.25 review and direction, working for a alternate options for NSO. will come back as earliest with closure plan. | [20 empty] | #N/A
29 | T2 | DWDM | Integration with Alepo |  | RADIUS Configuration Testing on Ciena Node & EMS (MCP) | Suresh Kumar |  |  | COMPLETED & APPROVED | [22 empty] | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\DWDM\Artefact - T106 |  | AD-UT-Tfiber | 2025-05-06
30 | T3 | DWDM | Integration with Alepo |  | TACACS+/Radius testing for AAA on ciena node | Suresh Kumar |  |  | WIP | 13-09-25:MCP upgradation is in progress, will be able to check the logs by next week 28-08-2025: Activity is in progress, target to complete by 25th Sep'25 Authentication and Authorization tested and found OK for Node and MCP. 19-08-2025: Due to issue in disk partition and file type of storage, activity is not started 10-08-2025: OEM confirmation recieved and activity is planned from 18th August'25. 05-July-2025: DC OSS to DR MCP communication is through now, need to integrate and test before activity 12-July-2025: DC OSS to DR MCP integration testing done. Alarms and Autoticketing functioning as expected. Upgradation activity will be scheduled as per OEM confirmation, Target date - 30-07-25 26-July-2025: Schedule awaited from OEM 30-June-2025: DC OSS to DR MCP connectivity to be extended for PE approval, WIP. Target date - 30-07-25 15-06-25: Targeting to close the upgradation by month end, 30-06-25 30-05-2025: Accounting issue resolved in latest MCP version, verified in 8.2 Ver (Node logs are now capturing in MCP). Upgradation schedule awaited from Teleindia for our MCP from 7.1-P02 5/21/2025: Correlation to identified to find the user logged in at the specific time 28APR'25: As discussed with Sanjay sir, if user id not avaialble pls. try for correlation with IP. Some how Correlation to be done. In Accounting, Node and MCP logs are successfully reporting in Alepo with below limitation. Node Logs - Active profile name (ADMIN/RADIUS) is displayed against User ID (Ciena confirmed it is as per design no changes are possible) |  | MCP upgradation activity in progress | [11 empty] | 1 | [6 empty] | #REF!
234 | T101 | DWDM | Integration with OSS |  | Network and service performance monitoring KPIs report in HPE OSS | Suresh Kumar |  |  | COMPLETED & APPROVED | [22 empty] | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\DWDM\Artefact - T101 |  | AD-UT-Tfiber | 2025-05-06
235 | T86 | DWDM | Network Deployment & AT Status |  | Nodal AT (67/71) | Suresh Kumar |  | Field - Pkg C | DEPENDENCY(Client/Ext.) | 31-July-2025:As per discussion with Ramanaiah sir, need to discuss these points with T Fiber Project team for further action, till that time this point kept on hold Nirmal, Jainoor, Gudihatnoor & Bhimni RFE pending due to forest permission 28th-Apr'25: As per Sandeep Sanmani - Forest permission still pending 15-06-25: No progress on the permission, target - D+15 05-July-25: No progress on the forest permission | [20 empty] | #N/A
236 | T88 | DWDM | Network Deployment & AT Status |  | Zonal Link AT (7/15) | Suresh Kumar |  | Field - Pkg A,B | DEPENDENCY(Client/Ext.) | 31-July-2025:As per discussion with Ramanaiah sir, need to discuss these points with T Fiber Project team for further action, till that time this point kept on hold 04 Link AT's approved by T Fiber and 03 Link AT's pending due to letter from Ciena awaited (No impact due to ILA to OADM upgradation) 05 Link AT pending due to high losses in the spans, depend on all packages 02 Links integrated as per interim plan, so not considered for Link AT 20May'25: Declaration letter submitted to T Fiber for 03 links AT approval 25-06-2025: Dependancy on field, no progress. 30-June-2025: As discussed in the meeting, need to arrange meeting with all stakeholders | [20 empty] | #N/A
237 | T83 | DWDM | Network Deployment & integration |  | Zonal Links Integration (12/15) | Suresh Kumar |  | Field - Pkg C | DEPENDENCY(Client/Ext.) | 31-July-2025:As per discussion with Ramanaiah sir, need to discuss these points with T Fiber Project team for further action, till that time this point kept on hold Depend on 04 Facilities RFE in Pkg-C Asifabad - Warangal & Karimnagar - Asifabad - Links integrated as per interim plan, actual integration pending Nizamabad - Asifabad - E2E link integration pending 28th-Apr'25: As per Sandeep Sanmani - Forest permission still pending 6/25/2025: Status is same no visibility on forest permission, Target date would be D+21 05-July-25: No progress on the forest permission | [20 empty] | #N/A
238 | T84 | DWDM | Network Deployment & integration |  | Nodes Live & Operational (67/71) | Suresh Kumar |  | Field - Pkg C | DEPENDENCY(Client/Ext.) | 31-July-2025:As per discussion with Ramanaiah sir, need to discuss these points with T Fiber Project team for further action, till that time this point kept on hold Nirmal, Jainoor, Gudihatnoor & Bhimni RFE pending due to forest permission 28th-Apr'25: As per Sandeep Sanmani - Forest permission still pending 15-06-25: No progress on the permission, target - D+15 05-July-25: No progress on the forest permission | [20 empty] | #N/A
239 | T85 | DWDM | Network Deployment & integration |  | Zonal Rings readiness with 1+R protection (5/7) | Suresh Kumar |  | Field - Pkg C | DEPENDENCY(Client/Ext.) | 31-July-2025:As per discussion with Ramanaiah sir, need to discuss these points with T Fiber Project team for further action, till that time this point kept on hold 02 rings depend on 04 Facilities RFE readiness in Pkg-C, which is pending due to forest permission 28th-Apr'25: As per Sandeep Sanmani - Forest permission still pending 6/25/2025: No visibility on forest permission, target date would be D+30 05-July-25: No progress on the forest permission | [20 empty] | #N/A
240 | T87 | DWDM | Network Deployment & integration |  | Mandal Ring Integration through OADM | Suresh Kumar |  | Field - Pkg A, B, C | DEPENDENCY(Client/Ext.) | 31-July-2025:As per discussion with Ramanaiah sir, need to discuss these points with T Fiber Project team for further action, till that time this point kept on hold Mandal services are provisioned (10G) as per integration plan by all packages 6/25/2025: 203 services provisioned out of 270 planned. Remaining can be provisioned as per the requirement | [20 empty] | #N/A
266 | T103 | DWDM | Integration with OSS |  | Service Inventory Data Availibilty in HPE OSS | Suresh Kumar |  | NSO/Alternate OEM Solution | DEPENDENCY(Client/Ext.) | Post 24.06.25 review and direction, working for a alternate options for NSO. will come back as earliest with closure plan. | [20 empty] | #N/A
267 | T104 | DWDM | Integration with OSS |  | Planned Event Service Impact analysis report | Suresh Kumar |  | NSO/Alternate OEM Solution | DEPENDENCY(Client/Ext.) | Post 24.06.25 review and direction, working for a alternate options for NSO. will come back as earliest with closure plan. | [20 empty] | #N/A
90 | T229 | OSS | DWDM Integration with OSS |  | DWDM Network Alarms integration has been completed in HPE OSS. However, all alarm counts are not in sync with Ciena MCP to HPE vTeMIP. | Suresh Pawar |  |  | COMPLETED & APPROVED |  |  |  |  | 1 | [17 empty] | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\OSS\T229 |  | AD-UT-Tfiber | 2025-05-29
91 | T230 | OSS | DWDM Integration with OSS |  | Hardware inventory integration has been completed in HPE OSS. | Suresh Pawar |  |  | COMPLETED & APPROVED |  |  |  |  | 1 | [17 empty] | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\OSS\T230 |  | AD-UT-Tfiber | 2025-05-26
92 | T232 | OSS | DWDM Integration with OSS |  | Auto Ticket Generation- Fiber Cut | Suresh Pawar |  |  | COMPLETED & APPROVED |  |  |  |  | 1 | [17 empty] | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\OSS\T232 |  | AD-UT-Tfiber | 2025-05-26
93 | T233 | OSS | DWDM Integration with OSS |  | Auto Ticket Generation- Hardwares Failures | Suresh Pawar |  | HPE & Ciena | COMPLETED & APPROVED | 12-06-2025: HPE required some inputs from Ciena and also exploring workaround for inventory missmatch 24-06-2025: HPE said its unhandlled scenario and need a CR; Pursuing to do without CR if not agreed the commercial team help required 18-07-2025: HPE Deployed and under observation from NOC |  |  |  | 1 | [7 empty] | 1 | [8 empty] | #REF! | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\OSS\T233
94 | T234 | OSS | DWDM Integration with OSS |  | Auto Ticket Generation- Infra Failure | Suresh Pawar |  |  | COMPLETED & APPROVED |  |  |  |  | 1 | [17 empty] | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\OSS\T234 |  | AD-UT-Tfiber | 2025-05-26
95 | T235 | OSS | DWDM Integration with OSS |  | Network and service performance monitoring KPIs report in HPE OSS | Suresh Pawar |  |  | COMPLETED & APPROVED |  |  |  |  | 1 | [17 empty] | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\OSS\T235 |  | AD-UT-Tfiber | 2025-05-26
96 | T236 | OSS | DWDM Integration with OSS |  | Bandwidth utilization data in HPE OSS is available and under validation. | Suresh Pawar |  |  | COMPLETED & APPROVED |  |  |  |  | 1 | [17 empty] | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\OSS\T236 |  | AD-UT-Tfiber | 2025-05-26
97 | T240 | OSS | IPMPLS Integration with OSS |  | PMS reports for IPMPLS domain network elements | Suresh Pawar |  |  | WIP | 17-05-2025: Data collection rom internal (SME & NOC team) and then OT support is required for NPS to enable all permormance parameters. 24-06-2025: NPS reports available and NOC came back with some observation of wrong data, for which OT has asked evidences which are awaited from NOC |  | Discussion palnned with NOC/IPMPLS team. |  |  | 1 | [6 empty] | 1 | [8 empty] | #REF!
98 | T241 | OSS | IPMPLS Integration with OSS |  | Dashboards for IPMPLS Domain | Suresh Pawar |  | L&T NOC | WIP | 17-05-2025: OOB dashboards are already available in NNMi, L&T NOC team needs to review and confirm if any descripancy observed. |  | Discussion palnned with NOC/IPMPLS team. |  |  | 1 | [6 empty] | 1 | [8 empty] | #REF!
99 | T243 | OSS | GPON-NOKIA Integration with OSS |  | CR for Nokia API integration to close BW query and PMS related issues | Suresh Pawar |  |  | WIP | On track with HPE , will be delivered as per the plan. |  | In discussion with HPE. |  |  |  | 0.5 | 0.5 | 1 |  |  | 1 | [9 empty] | #REF!
100 | T248 | OSS | GPON |  | Nokia API integration - . PMS ( Chassi OLT ), Inventory, Device Status (ONT ) | Suresh Pawar |  |  | WIP | 17-05-2025: HPE team will deliver post application upgradation 23-06-2025: for Device status, HPE said the the Nokia alarm format is wrong; post having calls with Nokia HPE reviewing the NBI documentation. 17-07-2025: Solution deplyed for one package, for other 2 package need to raise PE on 22nd July |  | In Discussion with HPE & Nokia | [8 empty] | 1 | [9 empty] | #REF!
101 | T249 | OSS | GPON-NOKIA Integration with OSS |  | OLT & ONT devices status in OSS is not as per AMS | Suresh Pawar |  | HPE | REOPENED | 06-06-2025: HPE requested a call with Nokia 11-06-2025: Nokia call happened and inputs were shared with HPE 23-06-2025: Post having calls with Nokia one more time last week they have share NBI documents with HPE today which they are reviewing. 22-07-2025: count matching, confirmation awaited from NOC |  | In Discussion with HPE & Nokia |  | 1 | [7 empty] | 1 | [8 empty] | #REF!
102 | T250 | OSS | GPON-NOKIA Integration with OSS |  | ONT devices have been recovered and validated as per AMS count | Suresh Pawar |  |  | REOPENED | 15-06-2025: validation pending from NOC |  | Followup with NOC Team |  | 1 | [5 empty] | 1 | [10 empty] | #REF!
103 | T253 | OSS | DWDM |  | Alarm Sync issue with MCP | Suresh Pawar |  |  | COMPLETED & APPROVED |  |  |  |  | 1 | [17 empty] | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\OSS\T253 |  | AD-UT-Tfiber | 2025-05-29
104 | T256 | OSS | IPMPLS |  | EPNM & PI Inventory | Suresh Pawar |  |  | WIP | 20-06-2025: Inventory available, few parameter highlighted by NOC which are wrong. 24-06-2025: All EPNM and Pi inventory available as per API response, however some data is coming wrong on console(EMS IP) which HPE is working to fix. 26-06-2025: HPE highlighted issue in source data, Rajnish/IPMPLS team has to fix it. 22-07-2025: Inventory issues corrected, verification pending from NOC |  | Followup with NOC Team |  | 1 | [6 empty] | 1 | [9 empty] | #REF!
105 | T261 | OSS | Infra |  | Data enrichment - Location information PKG A B C, etc | Suresh Pawar |  |  | WIP | 17-05-2025: GIS Integration with UTM is WIP(OT dependancy) 24-06-2025: OT has shared the API for attributes required by HPE |  | Weekly call on going with GIS & HPE to complete the GIS integration | [10 empty] | 1 | [7 empty] | #REF!
106 | T271 | OSS | GPON |  | ONT & OLT vendor name should be mapped to OSS Inventory & PMS Inventory. | Suresh Pawar |  |  | COMPLETED & APPROVED | 12-06-2025: confirmation pending from NOC 20-06-2025: Some vendors are wrong, for which sayyad provided new logic to calculate the vendor name 24-06-2025: HPE required CR to implement it. 25-06-2025: Vendor name mapping for Pioneer, Dasan, Altice, etc should be mapped as per. |  | Sayyad kept it in observation for a few days |  | 1 | [5 empty] | 1 | [10 empty] | #REF! | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\OSS\T271
109 | T278 | OSS | Firewall |  | OSS firewall ports required for Security compliance | Suresh Pawar |  | Security | REOPENED | 09-09-2025: Security team is already taking care with help of MTR sharma 26-06-2025: Samrendra to provide inputs forOSS Firewall compliance |  | security team to raise in flags with firewall ports of OSS |  | 1 | [7 empty] | 1 | [8 empty] | #REF!
111 | T284 | OSS | Dashboards |  | Weekly, Monthly E2E Network Availability Trend for each Packages and over all per District, Zone level. | Suresh Pawar |  |  | WIP | 26-06-2025: HPE bulding the availabilility in UOC based on the data provided from SM. |  | In Track with HPE along with regular call |  |  |  | 1 | [5 empty] | 1 | [8 empty] | #REF!
112 | T285 | OSS | Dashboards |  | District wise Performance report for period of infra, fiber, ISP, config issues etc. | Suresh Pawar |  |  | WIP | 17-06-2025: OOB Dashboards are already available in UOC Console, NOC team needs to start utilizing and confirm if any descripency found. |  | NOC team to use it and provide the confirmation | [9 empty] | 1 | [8 empty] | #REF!
113 | T291 | OSS | Dashboards |  | IP MPLS Node/Link/Port availability & Utilization | Suresh Pawar |  | OT | WIP | 17-05-2025: Utilization is already available. Node and Link availability is WIP. OT Support not available to check port availability, it needs to resume. 26-06-2025: all data available now except Link availability, need confirmation from NOC |  | Followup with NOC Team & get confirmation |  |  |  | 1 | [5 empty] | 1 | [8 empty] | #REF!
145 | T270 | OSS | MoM Action |  | Device status in OSS ciena inventory, details received from Ciena | Suresh Pawar |  |  | COMPLETED & APPROVED |  |  |  |  | 1 | [17 empty] | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\OSS\T270 |  | AD-UT-Tfiber | 2025-05-26
146 | T275 | OSS | MoM Action |  | In OSS management dashboard, Block count should count only Mandal OLTs and not GP OLTs. | Suresh Pawar |  |  | COMPLETED & APPROVED |  |  |  |  | 1 | [5 empty] | 1 | [10 empty] | #REF! | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\OSS\T275
147 | T276 | OSS | MoM Action |  | DG Set integration with OSS is in progress for Package A, details for DG set integration with OSS awaited from Package B and C. | Suresh Pawar |  |  | WIP | 26-06-2025: Functionality is delivered, but system is not stable; same issue is escalated to HPE and OT. 22-07-2025: genset alarms are working now, confirmation required from NOC |  | Stabilization work is going on with OT and HPE vendors |  |  | 1 | [5 empty] | 1 | [9 empty] | #REF!
148 | T277 | OSS | MoM Action |  | UPS and DG Device status, GP Name and LGD code & Block Name and LGD code are not available in the Passive Infra (Non-IT) inventory | Suresh Pawar |  |  | WIP | 17-05-2025: Possible in UOC, which will be available post GIS integration. |  | Verification to be done post GIS integration | [11 empty] | 1 | [6 empty] | #REF!
149 | T295 | OSS | MoM Action |  | Service Management tool has having duplicate tickets for same node which is impacting availability, outage reports. Issue needs to be fixed. | Suresh Pawar |  | HPE | REOPENED | 12-06-2025: duplicate ticket booking needs to be handle by HPE, HPE working on a script to handle it. 26-06-2025: Script deplyed by HPE, need confirmation from NOC |  | To be completed the verification by 9th July |  | 1 | [6 empty] | 1 | [9 empty] | #REF!
180 | T227 | OSS | Other Applications Integrations with OSS |  | Create trouble ticket by BSS CRM | Suresh Pawar |  |  | COMPLETED & APPROVED |  |  |  |  | 1 | [17 empty] | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\OSS\T227 |  | AD-UT-Tfiber | 2025-05-26
181 | T244 | OSS | Other Applications Integrations with OSS |  | Fetch trouble ticket status for ticket(s) by BSS CRM | Suresh Pawar |  |  | COMPLETED & APPROVED | [5 empty] | 1 | [16 empty] | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\OSS\T244 |  | AD-UT-Tfiber | 2025-05-26
182 | T255 | OSS | Other Applications Integrations with OSS |  | Send SMS communication to SMS gateway | Suresh Pawar |  |  | COMPLETED & APPROVED | 12-06-2025:Screenshot from SMS GW as well required |  |  |  | 1 | [5 empty] | 1 | [10 empty] | #REF! | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\OSS\T255
183 | T245 | OSS | Passive Infra Integration with OSS |  | Integration with DG - HPE | Suresh Pawar |  |  | COMPLETED & APPROVED |  |  |  |  | 1 | [17 empty] | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\OSS\T245 |  | AD-UT-Tfiber | 2025-05-26
184 | T246 | OSS | Passive Infra Integration with OSS |  | Integration with UPS - HPE | Suresh Pawar |  |  | COMPLETED & APPROVED |  |  |  |  | 1 | [17 empty] | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\OSS\T246 |  | AD-UT-Tfiber | 2025-05-26
229 | T392 | OSS | OSS |  | BBNL Status and Availability API integration | Suresh Pawar |  |  | COMPLETED & APPROVED | [5 empty] | 1 |  |  |  |  | 1 | [10 empty] | #REF! | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\OSS\T392
276 | T226 | OSS | IPMPLS |  | Alarm & Auto TT | Suresh Pawar |  | NOC | WIP | 17-05-2025: NOC team needs to start utilizing auto ticketing 26-06-2025: Functionality is delivered, but system is not stable; same issue is escalated to HPE and OT. |  | Stabilization work is going on with OT and HPE vendors |  |  | 1 | [7 empty] | 1 | [7 empty] | #REF! |  |  |  |  | 10-June-2025: This point will be closed when IPMPLS ticketing work as expected.
278 | T237 | OSS | DWDM Integration with OSS |  | Service inventory data availability in HPE OSS | Suresh Pawar |  | NSO | WIP | 17-05-2025: Dependancy on NSO 26-06-2025: Cisco to be onboarded then it will take ~30 days to complete(timeline is given concidering NSO support available on 1st July) |  | 26-06-2025: Cisco to be onboarded then it will take ~30 days to complete(timeline is given concidering NSO support available on 1st July) | [12 empty] | 1 | [5 empty] | #REF!
279 | T239 | OSS | IPMPLS Integration with OSS |  | FMS (Inventory, Alarm, Auto TT) Ref 226 | Suresh Pawar |  | OT | WIP | 24-05-2025:Working with some operational challenges like frequent NNMi and OBM hung issue, queue increase. |  | Discussion to be done with IPMPLS/RS Rao | [5 empty] | 1 |  |  |  | 1 | [8 empty] | #REF!
280 | T242 | OSS | IPMPLS Integration with OSS |  | Reports | Suresh Pawar |  | OT | WIP | 24-05-2025: Operational Challenges 26-06-2025: Multiple reports are already available, need clarity if anything is missing from IPMPLS |  | Discussion to be done with IPMPLS/RS Rao |  |  | 1 | [5 empty] | 1 | [9 empty] | #REF!
281 | T254 | OSS | GPON |  | Co-located OLT topology view | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | 17-05-2025: As per previous joint discussion with TFIBER and HPE team, this is not required.(to be discuss and remove/close) 26-06-2025: Completed, need confirmation from NOC |  | Followup with NOC and get confirmation | [7 empty] | 1 | [10 empty] | #REF!
282 | T258 | OSS | GIS |  | GIS integration | Suresh Pawar |  |  | WIP | 17-05-2025: WIP with HPE team | [11 empty] | 1 | [8 empty] | #REF!
283 | T259 | OSS | E2E |  | TOPOLOGY | Suresh Pawar |  |  | WIP | 17-05-2025: WIP with HPE team | [11 empty] | 1 | [8 empty] | #REF!
284 | T260 | OSS | E2E |  | Cross domain RCA corelation | Suresh Pawar |  |  | WIP | 17-05-2025: WIP with HPE team | [11 empty] | 0.2 | 0.5 | 0.7 | 0.9 | 1 |  |  |  |  | #REF!
285 | T262 | OSS | DC - Active infra Alarm and Auto TT |  | DC-Active infra Alarm, RCA and Auto TT | Suresh Pawar |  | OT | WIP | 17-05-2025: URL unreachable alarms are there but tickets are not getting generated. OT support required. 26-06-2025: Functionality is delivered,under stabilization. |  | Call schedulled with OT and HPE for troubleshooting issue on 27th June |  |  | 1 | [6 empty] | 1 | [8 empty] | #REF!
286 | T263 | OSS | Documentation - LLD, FAT, HA Testing |  | OSS Documentation - LLD, FAT, HA Testing | Suresh Pawar |  | OT | WIP | 17-05-2025: OT support is required. 26-06-2025: OT & HPE working on preparing the document concidering the BSOW |  | To be completed post BSOW, Aug 2025 | [15 empty] | 1 |  |  | #REF!
287 | T268 | OSS | Design & Documentation |  | LLD | Suresh Pawar |  | OT | WIP | 17-05-2025:Combined LLD for old scope and Balance scope to be prepare. HPE Support is available, OT should be resumed. 26-06-2025: OT & HPE working on preparing the document concidering the BSOW |  | To be completed post BSOW, Aug 2025 |  |  | 1 | [12 empty] | 1 |  |  | #REF!
288 | T272 | OSS | Design & Documentation |  | Infra team to maintain the SSL connectivity | Suresh Pawar |  |  | WIP | 17-05-2025: Dependancy on HPE upgrade and OT PS Team support 23-06-2025: New VM was requested by OT and same is provided. OT will to the testing in TND and confirm for production by 27th June 2025 | [11 empty] | 1 | [8 empty] | #REF!
289 | T280 | OSS | Correlations |  | Cross domain Corelation and exact reason for any outage in Network till ONT Port with E2E topology | Suresh Pawar |  | HPE & L&T | WIP | 17-05-2025: WIP with HPE team |  | to be verified post cross domain functionality delivered | [10 empty] | 0.7 | 1 | [6 empty] | #REF!
316 | T388 | OSS | Helpdesk |  | OSS Integration with Helpdesk | Suresh Pawar |  | WIP | WIP | 17-05-2025: Artefacts needs to be collected from Sivakumar and seek approval. 26-06-2025: completed from OSS end |  | Confirmation required from Sivakumar |  |  | 1 |  |  |  |  | 1 | [10 empty] | #REF!
329 | T265 | OSS | MoM Action |  | Feasibility Engine | Suresh Pawar |  | OT | WIP | 24-05-2025: WIP with HPE, OT dendancy for data. 26-06-2025: OT has provided necessary data to HPE, HPE to complete remaining development |  | On track with HPE and will be completed by Mid July | [9 empty] | 1 | [8 empty] | #REF!
330 | T269 | OSS | MoM Action |  | Change management process (eg. planned /Unplanned ) activities to be demonstrated | Suresh Pawar |  | OT | WIP | 17-05-2025: OT Team has to work and deliver 26-06-2025: change managemnt is delivered, NOC team has to confirm | [10 empty] | 1 | [9 empty] | #REF!
331 | T281 | OSS | MoM Action |  | Problem Management report for various recurring outages for the given period like i) one Unique LGD code >5 times in a Month ii) Fiber cut SPAN/Link >2 times in a month iii) Unique LGD code Down for >2 times with Same RFO iv) etc. | Suresh Pawar |  | OT | WIP | 17-05-2025: OT Team has to work and deliver 26-06-2025: Problem management, relation data required from Sivakumar |  | Sivakumar to share the relationship data | [6 empty] | 1 |  | 1 | [9 empty] | #REF!
333 | T287 | OSS | MoM Action |  | Exact SPAN/Link details must be taken from GIS(Including Lat,Long) for Fiber cut/outage scenario to undserstand fix is permanent or temporarary in nature and impact on Multiple Nodes/GP’s . | Suresh Pawar |  | HPE & L&T | WIP | 17-05-2025: Common span scenarios solution needs to be finalization pending with L&T and will be finalized based on data coming from GIS integration. 26-06-2025: Dependancy on GIS integration. Expected to be completed by 16th July and then ~30 days needed for Common span |  | to be started post GIS integration | [14 empty] | 1 |  |  |  | #REF!
334 | T288 | OSS | MoM Action | Tech | Report for Backup Status (success/failure) of all VM (source it from Vcenter Report) | Ravi Kishore |  | DCITACTIVEINFRA | COMPLETED & APPROVED | Backups are happening for all OSS Application VM's and Database. Artifacts are captured. | 2025-07-05 | [20 empty] | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\OSS\Artifact-T288 |  | AD-UT-Tfiber | 2025-07-05
335 | T289 | OSS | MoM Action |  | DC Active infra-Health check-up /Utilization and Resource Availability report.—Hardware and Servers. (Source it from Vcenter to OSS tool) | Suresh Pawar |  |  | WIP | 26-06-2025: data available in OBM, need confirmation from DC team |  | Need to take confirmation from DC-IT | [9 empty] | 1 | [8 empty] | #REF!
336 | T290 | OSS | MoM Action |  | IP MPLS node status report to be automated(Zonal / Mandal/GP) along with Alias Name(Like Actual Mandal /GP names) -Feasibility check required if Alias can be updated & fetched by OSS tool | Suresh Pawar |  |  | WIP | 26-06-2025: IPMPLS node status available in NNMi, need confirmation from NOC | [8 empty] | 1 |  | 1 | [9 empty] | #REF!
337 | T294 | OSS | MoM Action |  | OSS MTTR report to include additional columns like RFO, Sub RFO, Resolution etc. | Suresh Pawar |  |  | COMPLETED & APPROVED | 17-05-2025: Under observation. Seek approval from Sivakumar | [8 empty] | 1 | 1 | [10 empty] | #REF! | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\OSS\T294
341 | T359 | TNOC-Ops | NOC Operation |  | OSS - stability and Operational issues with respect to inventory, ticketing and utilization modules | Suresh Pawar |  |  | WIP | 26-06-2025: Frequent stability issues are because of NNMi, OBM instability and Vendor asking for upgrade | [16 empty] | 1 |  |  |  | #REF!
352 | T228 | OSS | Other Applications Integrations with OSS |  | Creation of technical incident by Helpdesk | Suresh Pawar |  | Helpdesk | WIP | 17-05-2025: Under observation. Seek approval from Sivakumar 26-06-2025: closed from OSS end, help desk to start using |  | Confirmation required from Sivakumar |  |  | 1 | [5 empty] | 1 | [9 empty] | #REF!
353 | T247 | OSS | Other Applications Integrations with OSS |  | Inventory Synch - Physical devices with GIS | Suresh Pawar |  |  | WIP | 24-05-2025:WIP with HPE 26-06-2025: To be tested post GIS integration |  | To be tested post GIS Integration | [10 empty] | 1 | [7 empty] | #REF!
354 | T257 | OSS | Other Applications Integrations with OSS |  | Syslog Sync to Syslog Server | Suresh Pawar |  |  | WIP | 17-06-2025: Support required from Sys-log team/Sarmendra & Ravikishore |  | Will be discussed and closed post discussion with Samrendra & Ravi | [10 empty] | 1 | [7 empty] | #REF!
368 | T279 | OSS | Security |  | Security policies to evolve related to DOT/CDOT etc.. from internal and intigration | Suresh Pawar |  |  | WIP | 26-06-2025: Dependacy on Cross domain delivery |  | to be done post cross domain delivery is completed. | [15 empty] | 1 |  |  | #REF!
378 | T389 | OSS | OSS |  | BBNL Report stabilization | Suresh Pawar |  |  | COMPLETED & APPROVED |  |  |  |  | 1 | [5 empty] | 1 | [10 empty] | #REF! | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\OSS\T389
381 | T238 | OSS | DWDM Integration with OSS |  | For planned event service impact analysis data / report | Suresh Pawar |  |  | WIP | 17-05-2025: Dependancy on NSO 26-06-2025: Cisco to be onboarded then it will take ~30 days to complete(timeline is given concidering NSO support available on 1st July) |  | 26-06-2025: Cisco to be onboarded then it will take ~30 days to complete(timeline is given concidering NSO support available on 1st July) | [12 empty] | 1 | [5 empty] | #REF!
382 | T286 | OSS | Dashboards |  | Individual NOC Engineer and shift Lead Performance Measurement for handling the TT's | Suresh Pawar |  |  | WIP | 17-05-2025: Artefacts needs to be collected from Sivakumar and seek approval. 26-06-2025: Waiting for Sivakumar's approval |  |  |  |  | 1 | [6 empty] | 1 | [8 empty] | #REF!
383 | T293 | OSS | Dashboards |  | Service VLAN status report from EMS (Nokia and Tejas) | Suresh Pawar |  |  | WIP | 24-05-2025: Inhouse solution being built by rishik | [5 empty] | 1 | [5 empty] | 1 | [8 empty] | #REF!
385 | T264 | OSS | MoM Action |  | Network Downtime, fault reported to be mapped with BSS to consider during billing process | Suresh Pawar |  | NSO | WIP | 26-06-2025: Post NSO integration |  | 26-06-2025: Cisco to be onboarded then it will take ~30 days to complete(timeline is given concidering NSO support available on 1st July) | [13 empty] | 1 |  |  |  |  | #REF!
386 | T266 | OSS | MoM Action |  | Commercial engine to be designed along with rules to Budgetory calculation for network and customer feasibilies | Suresh Pawar |  | KNOT | DEPENDENCY(Client/Ext.) | 26-06-2025: this needs to be taken care by BSS side | [20 empty] | #N/A
387 | T267 | OSS | MoM Action |  | Port Block (reservation) against Service ID | Suresh Pawar |  | TFIBER | DEPENDENCY(Client/Ext.) | 17-05-2025: Not feasible, Take mail confirmation from HPE team. | [20 empty] | #N/A
388 | T292 | OSS | MoM Action |  | Customised dashboard template with available set of fields for different set of users views | Suresh Pawar |  |  | WIP | 17-05-2025: OOB is available, to be reviewed with NOC |  | confirmation will be taken from NOC | [8 empty] | 1 | [9 empty] | #REF!
389 | T296 | OSS | MoM Action |  | Service Management dashboard should list planned outages and corelate TT if that is on same device or NW component. | Suresh Pawar |  | OT & NSO | WIP | 17-05-2025: OT & NSO support required |  | 26-06-2025: Cisco to be onboarded then it will take ~30 days to complete(timeline is given concidering NSO support available on 1st July) |  |  |  | 1 | [8 empty] | 1 | [5 empty] | #REF!
391 | T251 | OSS | Other Applications Integrations with OSS |  | Fetch SLA violation by BSS billing | Suresh Pawar |  | L&T | WIP | 26-06-2025: table to exposed with BSS, awating sevice ID from BSS and same needs to implemented in Network |  | To provide details to KNOT | [18 empty] | #N/A
392 | T252 | OSS | Other Applications Integrations with OSS |  | Circuit performance data to BSS CRM | Suresh Pawar |  |  | WIP | 26-06-2025: table to exposed with BSS, awating sevice ID from BSS and same needs to implemented in Network | [15 empty] | 1 |  |  |  |  | #REF!
393 | T391 | OSS | OSS |  | Auto TT for Genset | Suresh Pawar |  |  | WIP | 26-06-2025: Confirmation awaited from NOC |  |  |  |  | 1 | [5 empty] | 1 | [9 empty] | #REF!
107 | T273 | OSS | Deployment and Installations |  | Deployment process - Process of building network & passive device connectivity to T-NOC through SG350, ONT (One port Voice, 2nd - Data, 3rd - Video & 4th port to T-NOC for SNMP traps) . Along with , and also all other Services to be test and provision in SG350 | Suresh Pawar |  |  | CLOSURE REVIEW PENDING | 26-06-2025: duplicate and aready completed, need confirmation from customer |  |  |  | 1 | [6 empty] | 1 | [9 empty] | #REF!
108 | T274 | OSS | Development and unit testing |  | In OSS Script File, both Nokia Primary and Secondary IPs are mentioned, however OSS is considering only the first mentioned IP even if Secondary IP is master. Due to this alarms are not reflecting in OSS. Infra team has to setup Virtual IP. | Suresh Pawar |  |  | COMPLETED & APPROVED | [5 empty] | 1 | [16 empty] | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\OSS\T274 |  | AD-UT-Tfiber | 2025-05-26
110 | T283 | OSS | Dashboards |  | Alert Mechanism (event rule) when power supply is through UPS which is running on Battery backup mode then there should be alert in the form of SMS sent to field team so outages can be avoided or minimized proactively. threshold can be configured (TBD) )for given range for Battery backup status i) <50%- - Minor ii) <40%-Major iii) <30% -Critical) | Suresh Pawar |  |  | WIP | 26-06-2025: need to finalize with OT |  | Will be discussed with OT for changes based on Threshold | [10 empty] | 1 | [7 empty] | #REF!
277 | T231 | OSS | DWDM Integration with OSS |  | Ciena DWDM Network Topology has been created in HPE OSS topology MAP along with neighbour NE details. Adding the geographical map in the background of HPE OSS is possible with openstreet map.. Not posisble to integarted with GIS map | Suresh Pawar |  | HPE & L&T | WIP | 17-05-2025: Suresh will discuss with GIS & DWDM SME and then with HPE to fullfil the ask. 26-06-2025: The HPE says its not in scope to change the background so need to discuss it with management |  | Management discussion is needed | [8 empty] | 1 | [9 empty] | #REF!
332 | T282 | OSS | MoM Action |  | For ONT Down cases, Some of the Alarms and cause code given by OEM is not matching with RFO provided by field engg., for example incase of Particular ONT goes down at GP level then exact RFO should be available for NOC to correlate with outages due to UPS power or other issue? | Suresh Pawar |  |  | WIP | 17-05-2025: HPE Team is working on the issue 26-06-2025: Cause code are correct now on tickets, to be confirmed by NOC |  | Confirmation to be taken from NOC for this |  |  | 1 | [5 empty] | 1 | [9 empty] | #REF!
340 | T345 | TNOC-Ops | NOC Operation |  | OEM Professional services for all products post NOC operationalization | T Chinnaiah Sekhar |  | TFIBER | DEPENDENCY(Client/Ext.) | AMC and TAC support exists. Expired AMC is being renewed f0r support, regular AMC status is being shared with stakeholders. | NA | [17 empty] | 1 |  | #REF!
394 | 394 | TNOC-Ops | License | Tech | Once excel license for VM | Ravi Kishore |  |  | COMPLETED & APPROVED | 27Jun: Alternate solution working on Desktop, no need for VM. Discussed with TFiber, agreed for closure. 08Jul: Mail approval came from TFiber | 2025-07-08 | [20 empty] | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\TNOC\Artifact for - 394 |  | ad-ut-tfiber | 2025-07-08 | Mail approval received
395 | 395 | TNOC-Ops | Payments |  | SMS Gateway recharge | T Chinnaiah Sekhar |  |  | COMPLETED & APPROVED | On TFiber for SMS reimbursements | 2025-07-07 | [9 empty] | 1 | [9 empty] | #REF! | Not applicable |  | ad-ut-tfiber | 2025-07-08
396 | 396 | TNOC-Ops | AMC |  | AMC status including HPE/OT | T Chinnaiah Sekhar |  |  | COMPLETED & APPROVED | 05May: AMC tracker is being shared on weekly basis. Expired AMCs to be renewed. 28Jun25: Discussed with TFiber with details available in AMC tracker. Was asked to share Dates for support validity from system screenshots. 02Jul25: Screenshots taken for HPE servers, Cisco. Rest WIP. For many Support Date not available on system. List is being made. Will discuss on 05Jul with TFiber for further approvals. 08Jul25: Screenshots from support portal, system, mail and LOI collated in a PDF file and uploaded in NAS server. Mail sent to TFiber for approval | 2025-07-07 | [9 empty] | 1 | [9 empty] | #REF! | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\TNOC |  | ad-ut-tfiber | 2025-07-08
397 | 397 | TNOC-Ops | Security |  | Access cards - 38 QTY | T Chinnaiah Sekhar |  |  | COMPLETED & APPROVED | 05May: Sekhar to confirm date for delivery 12May: Sekhar gave 17May date for access cards delivery 25Jun: Card delivered were of different model. One sample card tested and confirmed OK. Expected to recieve cards by 01Jul25. 03Jul: OEM couriered cards today, expected delivery by 05Jul25. Activation of cards either on 05 Jul or 07 Jul25 depending on card delivery time. 08Jul25: Card recieved today. Activation of cards done. Mail sent to Tfiber for approval. | 2025-07-07 | [9 empty] | 1 | [9 empty] | #REF! | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\TNOC |  | ad-ut-tfiber | 2025-07-08
347 | T371 | GPON-Nokia | Nokia |  | * Testing done for new build in T-Fiber test lab . * Plan event for OLTs new SW upgradation in production environment. | Sayyad |  | Field team(PKG_A) and PKG-B&C | DEPENDENCY(Client/Ext.) | 13-Sep-2025: Below is the status of the OLT upgrade PKG-A : 872/881 PKG-B : 641/675 PKG-C : 419/420 29-Aug-2025: Having dependency on PKG-B&C(Mr.Mahesh) and PKG-A field team (Mr. Srinivas Kodali) Below is the status of the OLT upgrade PKG-A : 872/881 PKG-B : 634/675 PKG-C : 419/420 02-Aug-2025 : Received reasons for OLT not reachable cases pertaining to PKG-A. Out of 9 pending, 3 Gps are dismantled, 5 GPs having fiber issues and in 1 GP OLT is shifted to other district. 22-July-2025 : For the pending cases escalated to project team to make OLTs reachable for the completion of upgrade 18-July-2025 : PKG-B&C team provided the plan of action on the pending OLT however there are OLT which are down >30days, for those they are working on. 14-July-2025 : Escalated to respective teams to vmake OLTs reachable for the completion of upgrade. Also looped the T-Fiber team in the mail 04-July-2025 : To escalate the respective teams where having the dependecy. All the reacahble OLTs are upgraded. Below are the count PKG-A : 878/886 PKG-B : 639/678 PKG-C : 417/420 Having dependency on field team and PKG-B&C |  | Following up with field Team and PKG-B&C | [16 empty] | 1 |  | #REF!
373 | T166 | GPON-Tejas | Tejas |  | * Testing done for new build in T-Fiber test lab . * Plan event for OLTs new SW upgradation in production environment. | Sayyad |  | Field team and PKG-B&C | DEPENDENCY(Client/Ext.) | 13-Sep-2025: Below are the OLT upgrade status PKG-A : 430/464 PKG-B : 192/300 PKG-C : 93/165 29-Aug-2025: Having dependency on PKG-B&C(Mr.Mahesh) and PKG-A field team (Mr. Srinivas Kodali) Below are the OLT upgrade status PKG-A : 425/461 PKG-B : 198/300 PKG-C : 94/165 02-Aug-2025 : All reachable OLTs are upgraded except POC OLTs 22-July-2025 : For the pending cases escalated to project team but they are claiming that OLTs are faulty at the site and few sites are replaced with Nokia OLT but due to fiber cut OLTs are not reachable to NOC to make the necessary changes in EMS 18-July-2025 : PKG-B&C team provided the plan of action on the pending OLT however there are OLT which are down >30days, for those they are working on. 14-July-2025 : Escalated to respective teams to vmake OLTs reachable for the completion of upgrade. Also looped the T-Fiber team in the mail 04-July-2025 : To escalate the respective teams where having the dependecy. Below are the count of upgraded OLT version as Chassis OLT : REL_10_0_13_a56_66_1_22 Pizzabox OLT : REL_10_0_13_a56_66_1_11 PKG-A : 453/458 PKG-B : 273/297 PKG-C : 164/166 Having dependency on field team and PKG-B&C Below are the count of upgraded OLT version (AAA enabled) Chassis OLT : REL_10_0_13_a56_187 Pizzabox OLT : REL_10_0_13_a56_96_19_1_68 PKG-A : 415/458 PKG-B : 192/297 PKG-C : 93/166 |  | Following up with field Team and PKG-B&C | [16 empty] | 1 |  | #REF!
346 | T182 | GPON-Nokia | Nokia |  | Nokia EMS functional ATP to be closed with customer | Sayyad |  | Nokia | DEPENDENCY(Client/Ext.) | 13-Sep-2025: Working with OEM for the support on ATP 29-Aug-2025 : Working with OEM 02-Aug-2025 : Having dependency on OEM 25-July-2025 : Working with OEM for the support on ATP 11-July-2025 : Following up with the OEM to extend the support for the Test cases 05-July-2025 : Working with OEM Revised version to be submitted as per T Fiber remarks. |  | Working with OEM | [18 empty] | #N/A

## Sec Doc (hidden)
S.No | Unique ID | Domain | Sub domain | Description of the Activity | SME | Remarks- @07.05.25(Progress /MoM RFP Ask/MoM not in RFP/MoM points with interpertation of RFP) | Artefacts against completion | Management Status | Approved By | Approved Date | Remark
185 | T318 | Security | Policy Implementation | Network Forensic | Sarmendra | [26/05] Discussed with AD, approval awaited | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\NW-Security\T318 | CLOSURE REVIEW PENDING
186 | T327 | Security | Report | Syslog NAT report | Sarmendra | [26/05] Discussed and awaited approval | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\NW-Security\T327 | CLOSURE REVIEW PENDING
218 | T323 | Security | Storage | User access logs& Commands to be maintained for 2 years | Sarmendra | [26/05] Reviewed and approval awaited | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\NW-Security\T323 | CLOSURE REVIEW PENDING
228 | T316 | Security | User Traceability | User access traceability | Sarmendra | [26/05] Discussed and awaited approval | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\NW-Security\T316 | CLOSURE REVIEW PENDING
363 | T326 | Security | Report | IPDR static IP report | Sarmendra | [25/05] Reviewed with AD and awaiting approval over email | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\NW-Security\T326 | CLOSURE REVIEW PENDING
153 | T329 | Security | MoM Action | Cisco ISE to be integrated with AD for Authentication | Sarmendra | [25/05] Reviewed and email awaited | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\NW-Security\T329 | CLOSURE REVIEW PENDING

## NOC-Points (hidden)
Sl.No | UniqueID | Domain | Domain-1 | TNOC Dashboards | Priority | Application | Module | Owner(L&T) | Remarks(L&T) | Status(L&T)
1 | NOC1 | DC | OSS | DC Active Infra uptime & SLA Daily | Critical | HPSM | Incident Management | Manoj Nibrad
2 | NOC2 | DC | OSS | DC Active Infra uptime & SLA Weekly | Critical | HPSM | Incident Management | Manoj Nibrad
3 | NOC3 | DC | OSS | DC Active Infra uptime & SLA Monthly | Critical | HPSM | Incident Management | Manoj Nibrad
4 | NOC4 | DC | OSS | DC Active Infra uptime & SLA Custom(Selective from and to dates) | Critical | HPSM | Incident Management | Manoj Nibrad
5 | NOC5 | DC | OSS | DC Applications uptime & SLA Daily | Critical | HPSM | Incident Management | Manoj Nibrad
6 | NOC6 | DC | OSS | DC Applications uptime & SLA Weekly | Critical | HPSM | Incident Management | Manoj Nibrad
7 | NOC7 | DC | OSS | DC Applications uptime & SLA Monthly | Critical | HPSM | Incident Management | Manoj Nibrad
8 | NOC8 | DC | OSS | DC Applications uptime & SLA (Selective from and to dates) | Critical | HPSM | Incident Management | Manoj Nibrad
9 | NOC9 | DC | OSS | DC Passive infra uptime & SLA Daily | Critical | HPSM | Incident Management | Manoj Nibrad
10 | NOC10 | DC | OSS | DC Passive infra uptime & SLA Weekly | Critical | HPSM | Incident Management | Manoj Nibrad
11 | NOC11 | DC | OSS | DC Passive infra uptime & SLA Monthly | Critical | HPSM | Incident Management | Manoj Nibrad
12 | NOC12 | DC | OSS | DC Passive infra uptime & SLA (Selective from and to dates) | Critical | HPSM | Incident Management | Manoj Nibrad
13 | NOC13 | DC | OSS | DC Network link uptime & SLA Daily | Critical | HPSM | Incident Management | Manoj Nibrad
14 | NOC14 | DC | OSS | DC Network link uptime & SLA Weekly | Critical | HPSM | Incident Management | Manoj Nibrad
15 | NOC15 | DC | OSS | DC Network link uptime & SLA Monthly | Critical | HPSM | Incident Management | Manoj Nibrad
16 | NOC16 | DC | OSS | DC Network link uptime & SLA (Selective from and to dates) | Critical | HPSM | Incident Management | Manoj Nibrad
17 | NOC17 | Service Provisioning | BSS | configure of GI services and tracking and publishing data Daily | Critical | BSS | CRM | Manoj Nibrad
18 | NOC18 | Service Provisioning | BSS | configure of GI services and tracking and publishing data Weekly | Critical | BSS | CRM | Manoj Nibrad
19 | NOC19 | Service Provisioning | BSS | configure of GI services and tracking and publishing data Monthly | Critical | BSS | CRM | Manoj Nibrad
20 | NOC20 | Service Provisioning | BSS | configure of GI services and tracking and publishing data (Selective from and to dates) | Critical | BSS | CRM | Manoj Nibrad
21 | NOC21 | Service Assurance | OSS | Monitoring,tracking of field details, Tracking of GI services form and prepare Service assurance dashboard Hourly | NON-Critical | HPSM | Incident Management | Manoj Nibrad
22 | NOC22 | Service Assurance | OSS | Monitoring,tracking of field details, Tracking of GI services form and prepare Service assurance dashboard Daily | NON-Critical | HPSM | Incident Management | Manoj Nibrad
23 | NOC23 | Service Assurance | OSS | Monitoring,tracking of field details, Tracking of GI services form and prepare Service assurance dashboard Weekly | NON-Critical | HPSM | Incident Management | Manoj Nibrad
24 | NOC24 | Service Assurance | OSS | Monitoring,tracking of field details, Tracking of GI services form and prepare Service assurance dashboard Monthly | NON-Critical | HPSM | Incident Management | Manoj Nibrad
25 | NOC25 | Service Assurance | OSS | Monitoring,tracking of field details, Tracking of GI services form and prepare Service assurance dashboard(Selective from and to dates) | NON-Critical | HPSM | Incident Management | Manoj Nibrad
26 | NOC26 | Service Monitoring | OSS | Monitoring,tracking service details, Tracking of GI services uptime Service assurance dashboard Daily | Critical | HPSM | Incident Management | Manoj Nibrad
27 | NOC27 | Service Monitoring | OSS | Monitoring,tracking service details, Tracking of GI services uptime Service assurance dashboard Weekly | Critical | HPSM | Incident Management | Manoj Nibrad
28 | NOC28 | Service Monitoring | OSS | Monitoring,tracking service details, Tracking of GI services uptime Service assurance dashboard Monthly | Critical | HPSM | Incident Management | Manoj Nibrad
29 | NOC29 | Service Monitoring | OSS | Monitoring,tracking service details, Tracking of GI services uptime Service assurance dashboard (Selective from and to dates) | Critical | HPSM | Incident Management | Manoj Nibrad
30 | NOC30 | Help Desk | OSS | Service Delivery & Service Assurance Dash Board Daily | Critical | HPSM | Incident Management | Manoj Nibrad |  | WIP
31 | NOC31 | Help Desk | OSS | Service Delivery & Service Assurance Dash Board Weekly | Critical | HPSM | Incident Management | Manoj Nibrad |  | WIP
32 | NOC32 | Help Desk | OSS | Service Delivery & Service Assurance Dash Board Monthly | Critical | HPSM | Incident Management | Manoj Nibrad |  | WIP
33 | NOC33 | Help Desk | OSS | Service Delivery & Service Assurance Dash Board (Selective from and to dates) | Critical | HPSM | Incident Management | Manoj Nibrad |  | WIP
34 | NOC34 | Help Desk | OSS | Incident Reporting and Field Assignment(Any failure/incident on any part of the network infrastructure or its facilities shall be communicated immediately to Helpdesk by Network Monitoring team/ field representative / end user giving details of the incident/fault/problem.) Daily | Critical | HPSM | Incident Management | Manoj Nibrad |  | WIP
35 | NOC35 | Help Desk | OSS | Incident Reporting and Field Assignment(Any failure/incident on any part of the network infrastructure or its facilities shall be communicated immediately to Helpdesk by Network Monitoring team/ field representative / end user giving details of the incident/fault/problem.) Weekly | Critical | HPSM | Incident Management | Manoj Nibrad |  | WIP
36 | NOC36 | Help Desk | OSS | Incident Reporting and Field Assignment(Any failure/incident on any part of the network infrastructure or its facilities shall be communicated immediately to Helpdesk by Network Monitoring team/ field representative / end user giving details of the incident/fault/problem.) Monthly | Critical | HPSM | Incident Management | Manoj Nibrad |  | WIP
37 | NOC37 | Help Desk | OSS | Incident Reporting and Field Assignment(Any failure/incident on any part of the network infrastructure or its facilities shall be communicated immediately to Helpdesk by Network Monitoring team/ field representative / end user giving details of the incident/fault/problem.) (Selective from and to dates) | Critical | HPSM | Incident Management | Manoj Nibrad |  | WIP
38 | NOC38 | Help Desk | Help Desk | Help Desk managing and publishing KPI like Total I/O call, answereed call withing time frame etc. Hourly | NON-Critical | Helpdesk | Dial center | Sivakumar S | 11-Sep-25: Option available to Choose Dates, daily, Weekly and Monthly But not Direct as Daily, Weekly, Monthly | Completed
39 | NOC39 | Help Desk | Help Desk | Help Desk managing and publishing KPI like Total I/O call, answereed call withing time frame etc. Daily | NON-Critical | Helpdesk | Dial center | Sivakumar S | 11-Sep-25: Option available to Choose Dates, daily, Weekly and Monthly But not Direct as Daily, Weekly, Monthly | Completed
40 | NOC40 | Help Desk | Help Desk | Help Desk managing and publishing KPI like Total I/O call, answereed call withing time frame etc. Weekly | NON-Critical | Helpdesk | Dial center | Sivakumar S | 11-Sep-25: Option available to Choose Dates, daily, Weekly and Monthly But not Direct as Daily, Weekly, Monthly | Completed
41 | NOC41 | Help Desk | Help Desk | Help Desk managing and publishing KPI like Total I/O call, answereed call withing time frame etc. Monthly | NON-Critical | Helpdesk | Dial center | Sivakumar S | 11-Sep-25: Option available to Choose Dates, daily, Weekly and Monthly But not Direct as Daily, Weekly, Monthly | Completed
42 | NOC42 | Help Desk | Help Desk | Help Desk managing and publishing KPI like Total I/O call, answereed call withing time frame etc. (Selective from and to dates) | NON-Critical | Helpdesk | Dial center | Sivakumar S |  | Completed
43 | NOC43 | Service Assurance | OSS | Raised Proactive and reactive TT for all service deliverable sites and troubleshoot, escalation to field, follow up with field and resolve the issue Hourly | Critical | HPSM | Incident Management | Manoj Nibrad
44 | NOC44 | Service Assurance | OSS | Raised Proactive and reactive TT for all service deliverable sites and troubleshoot, escalation to field, follow up with field and resolve the issue Daily | Critical | HPSM | Incident Management | Manoj Nibrad
45 | NOC45 | Service Assurance | OSS | Raised Proactive and reactive TT for all service deliverable sites and troubleshoot, escalation to field, follow up with field and resolve the issue Weekly | Critical | HPSM | Incident Management | Manoj Nibrad
46 | NOC46 | Service Assurance | OSS | Raised Proactive and reactive TT for all service deliverable sites and troubleshoot, escalation to field, follow up with field and resolve the issue Monthly | Critical | HPSM | Incident Management | Manoj Nibrad
47 | NOC47 | Service Assurance | OSS | Raised Proactive and reactive TT for all service deliverable sites and troubleshoot, escalation to field, follow up with field and resolve the issue (Selective from and to dates) | Critical | HPSM | Incident Management | Manoj Nibrad
48 | NOC48 | GPON | OSS | Summary Status of complete 424 Mandal OLTs ( Blocks ) of PKG-ABC Daily | Critical | HPSM | Incident Management | Manoj Nibrad
49 | NOC49 | GPON | OSS | Summary Status of complete 424 Mandal OLTs ( Blocks ) of PKG-ABC Weekly | Critical | HPSM | Incident Management | Manoj Nibrad
50 | NOC50 | GPON | OSS | Summary Status of complete 424 Mandal OLTs ( Blocks ) of PKG-ABC Monthly | Critical | HPSM | Incident Management | Manoj Nibrad
51 | NOC51 | GPON | OSS | Summary Status of complete 424 Mandal OLTs ( Blocks ) of PKG-ABC (Selective from and to dates) | Critical | HPSM | Incident Management | Manoj Nibrad
52 | NOC52 | GPON | OSS | Summary of Lit-up GPs Status_8894 as on 14-05-2025_4PM(Revised) Daily | Critical | HPSM | Incident Management | Manoj Nibrad
53 | NOC53 | GPON | OSS | Summary of Lit-up GPs Status_8894 as on 14-05-2025_4PM(Revised) Weekly | Critical | HPSM | Incident Management | Manoj Nibrad
54 | NOC54 | GPON | OSS | Summary of Lit-up GPs Status_8894 as on 14-05-2025_4PM(Revised) Monthly | Critical | HPSM | Incident Management | Manoj Nibrad
55 | NOC55 | GPON | OSS | Summary of Lit-up GPs Status_8894 as on 14-05-2025_4PM(Revised) (Selective from and to dates) | Critical | HPSM | Incident Management | Manoj Nibrad
56 | NOC56 | GPON | OSS | T-NOC Report :: Summary of O&M Cluster OLTs status Daily | Critical | HPSM | Incident Management | Manoj Nibrad
57 | NOC57 | GPON | OSS | T-NOC Report :: Summary of O&M Cluster OLTs status Weekly | Critical | HPSM | Incident Management | Manoj Nibrad
58 | NOC58 | GPON | OSS | T-NOC Report :: Summary of O&M Cluster OLTs status Monthly | Critical | HPSM | Incident Management | Manoj Nibrad
59 | NOC59 | GPON | OSS | T-NOC Report :: Summary of O&M Cluster OLTs status (Selective from and to dates) | Critical | HPSM | Incident Management | Manoj Nibrad
60 | NOC60 | GPON | OSS | Router UP - OLT Down cases Daily | Critical | NNMI | NNMI | Manoj Nibrad
61 | NOC61 | GPON | OSS | Router UP - OLT Down cases Weekly | Critical | NNMI | NNMI | Manoj Nibrad
62 | NOC62 | GPON | OSS | Router UP - OLT Down cases Monthly | Critical | NNMI | NNMI | Manoj Nibrad
63 | NOC63 | GPON | OSS | Router UP - OLT Down cases (Selective from and to dates) | Critical | NNMI | NNMI | Manoj Nibrad
64 | NOC64 | GPON | OSS | ONTs down more than 8 hrs. list Daily | Critical | OSS Dashboards | UOC | Manoj Nibrad
65 | NOC65 | GPON | OSS | ONTs down more than 8 hrs. list Weekly | Critical | OSS Dashboards | UOC | Manoj Nibrad
66 | NOC66 | GPON | OSS | ONTs down more than 8 hrs. list Monthly | Critical | OSS Dashboards | UOC | Manoj Nibrad
67 | NOC67 | GPON | OSS | ONTs down more than 8 hrs. list (Selective from and to dates) | Critical | OSS Dashboards | UOC | Manoj Nibrad
68 | NOC68 | GPON | OSS | Mandal OLT down more than 6 hrs. list Daily | Critical | OSS Dashboards | UOC | Manoj Nibrad
69 | NOC69 | GPON | OSS | Mandal OLT down more than 6 hrs. list Weekly | Critical | OSS Dashboards | UOC | Manoj Nibrad
70 | NOC70 | GPON | OSS | Mandal OLT down more than 6 hrs. list Monthly | Critical | OSS Dashboards | UOC | Manoj Nibrad
71 | NOC71 | GPON | OSS | Mandal OLT down more than 6 hrs. list (Selective from and to dates) | Critical | OSS Dashboards | UOC | Manoj Nibrad
72 | NOC72 | GPON | OSS | HH_PM Utilization Dump _PKGA_PKGC Daily | NON-Critical | NNMI | NPS | Manoj Nibrad
73 | NOC73 | GPON | OSS | HH_PM Utilization Dump _PKGA_PKGC Weekly | NON-Critical | NNMI | NPS | Manoj Nibrad
74 | NOC74 | GPON | OSS | HH_PM Utilization Dump _PKGA_PKGC Monthly | NON-Critical | NNMI | NPS | Manoj Nibrad
75 | NOC75 | GPON | OSS | HH_PM Utilization Dump _PKGA_PKGC (Selective from and to dates) | NON-Critical | NNMI | NPS | Manoj Nibrad
76 | NOC76 | GPON | OSS | Summary of Lit-up GPs Status_8895 Daily | NON-Critical | HPSM | Incident Management | Manoj Nibrad
77 | NOC77 | GPON | OSS | Summary of Lit-up GPs Status_8895 Weekly | NON-Critical | HPSM | Incident Management | Manoj Nibrad
78 | NOC78 | GPON | OSS | Summary of Lit-up GPs Status_8895 Monthly | NON-Critical | HPSM | Incident Management | Manoj Nibrad
79 | NOC79 | GPON | OSS | Summary of Lit-up GPs Status_8895 (Selective from and to dates) | Critical | HPSM | Incident Management | Manoj Nibrad
80 | NOC80 | GPON | OSS | GPON OLT TT trend dashboard Daily | Critical | HPSM | Incident Management | Manoj Nibrad
81 | NOC81 | GPON | OSS | GPON OLT TT trend dashboard Weekly | Critical | HPSM | Incident Management | Manoj Nibrad
82 | NOC82 | GPON | OSS | GPON OLT TT trend dashboard Monthly | Critical | HPSM | Incident Management | Manoj Nibrad
83 | NOC83 | GPON | OSS | GPON OLT TT trend dashboard (Selective from and to dates) | Critical | HPSM | Incident Management | Manoj Nibrad
84 | NOC84 | GPON | OSS | GPON ONT TT trend dashboard Daily | Critical | HPSM | Incident Management | Manoj Nibrad
85 | NOC85 | GPON | OSS | GPON ONT TT trend dashboard Weekly | Critical | HPSM | Incident Management | Manoj Nibrad
86 | NOC86 | GPON | OSS | GPON ONT TT trend dashboard Monthly | Critical | HPSM | Incident Management | Manoj Nibrad
87 | NOC87 | GPON | OSS | GPON ONT TT trend dashboard (Selective from and to dates) | Critical | HPSM | Incident Management | Manoj Nibrad
88 | NOC88 | GPON | OSS | POP uptime_ GP Mandal and Zonal Daily | Critical | HPSM | Incident Management | Manoj Nibrad
89 | NOC89 | GPON | OSS | POP uptime_ GP Mandal and Zonal Weekly | Critical | HPSM | Incident Management | Manoj Nibrad
90 | NOC90 | GPON | OSS | POP uptime_ GP Mandal and Zonal Monthly | Critical | HPSM | Incident Management | Manoj Nibrad
91 | NOC91 | GPON | OSS | POP uptime_ GP Mandal and Zonal (Selective from and to dates) | Critical | HPSM | Incident Management | Manoj Nibrad
92 | NOC92 | GPON | OSS | Weekly BW utilization Supporting data Daily | NON-Critical | OSS Dashboards | PMS(UOC) | Manoj Nibrad
93 | NOC93 | GPON | OSS | Weekly BW utilization Supporting data Weekly | NON-Critical | OSS Dashboards | PMS(UOC) | Manoj Nibrad
94 | NOC94 | GPON | OSS | Weekly BW utilization Supporting data Monthly | NON-Critical | OSS Dashboards | PMS(UOC) | Manoj Nibrad
95 | NOC95 | GPON | OSS | Weekly BW utilization Supporting data (Selective from and to dates) | NON-Critical | OSS Dashboards | PMS(UOC) | Manoj Nibrad
96 | NOC96 | GPON | OSS | T-NOC Report :: Migrated & Duplicated GPs still available both Tejas EMS & Nokia AMS Daily | NON-Critical | HPSM | Incident Management | Manoj Nibrad
97 | NOC97 | GPON | OSS | T-NOC Report :: Migrated & Duplicated GPs still available both Tejas EMS & Nokia AMS Weekly | NON-Critical | HPSM | Incident Management | Manoj Nibrad
98 | NOC98 | GPON | OSS | T-NOC Report :: Migrated & Duplicated GPs still available both Tejas EMS & Nokia AMS Monthly | NON-Critical | HPSM | Incident Management | Manoj Nibrad
99 | NOC99 | GPON | OSS | T-NOC Report :: Migrated & Duplicated GPs still available both Tejas EMS & Nokia AMS (Selective from and to dates) | NON-Critical | HPSM | Incident Management | Manoj Nibrad
100 | NOC100 | GPON | OSS | Governenmnet Institutions ( GI ) links delivery. Preparation and publishing of KPI Daily | Critical | NNMI | NPS | Manoj Nibrad
101 | NOC101 | GPON | OSS | Governenmnet Institutions ( GI ) links delivery. Preparation and publishing of KPI Weekly | Critical | NNMI | NPS | Manoj Nibrad
102 | NOC102 | GPON | OSS | Governenmnet Institutions ( GI ) links delivery. Preparation and publishing of KPI Monthly | Critical | NNMI | NPS | Manoj Nibrad
103 | NOC103 | GPON | OSS | Governenmnet Institutions ( GI ) links delivery. Preparation and publishing of KPI (Selective from and to dates) | Critical | NNMI | NPS | Manoj Nibrad
104 | NOC104 | GPON | OSS | Published GP Network uptime (like, total scope, litup count and availability according to the category) Daily | Critical | HPSM | Incident Management | Manoj Nibrad
105 | NOC105 | GPON | OSS | Published GP Network uptime (like, total scope, litup count and availability according to the category) Weekly | Critical | HPSM | Incident Management | Manoj Nibrad
106 | NOC106 | GPON | OSS | Published GP Network uptime (like, total scope, litup count and availability according to the category) Monthly | Critical | HPSM | Incident Management | Manoj Nibrad
107 | NOC107 | GPON | OSS | Published GP Network uptime (like, total scope, litup count and availability according to the category) (Selective from and to dates) | Critical | HPSM | Incident Management | Manoj Nibrad
108 | NOC108 | GPON | OSS | Publishing Package wise and District wise GP Network uptime and GP TT resolution MTTR dashboard Daily | Critical | HPSM | Incident Management | Manoj Nibrad
109 | NOC109 | GPON | OSS | Publishing Package wise and District wise GP Network uptime and GP TT resolution MTTR dashboard Weekly | Critical | HPSM | Incident Management | Manoj Nibrad
110 | NOC110 | GPON | OSS | Publishing Package wise and District wise GP Network uptime and GP TT resolution MTTR dashboard Monthly | Critical | HPSM | Incident Management | Manoj Nibrad
111 | NOC111 | GPON | OSS | Publishing Package wise and District wise GP Network uptime and GP TT resolution MTTR dashboard (Selective from and to dates) | Critical | HPSM | Incident Management | Manoj Nibrad
112 | NOC112 | GPON | OSS | Published Mandal Network uptime (like, total scope, litup count and availability according to the category) Hourly | Critical | HPSM | Incident Management | Manoj Nibrad
113 | NOC113 | GPON | OSS | Published Mandal Network uptime (like, total scope, litup count and availability according to the category) Daily | Critical | HPSM | Incident Management | Manoj Nibrad
114 | NOC114 | GPON | OSS | Published Mandal Network uptime (like, total scope, litup count and availability according to the category) Weekly | Critical | HPSM | Incident Management | Manoj Nibrad
115 | NOC115 | GPON | OSS | Published Mandal Network uptime (like, total scope, litup count and availability according to the category) Monthly | Critical | HPSM | Incident Management | Manoj Nibrad
116 | NOC116 | GPON | OSS | Published Mandal Network uptime (like, total scope, litup count and availability according to the category) (Selective from and to dates) | Critical | HPSM | Incident Management | Manoj Nibrad
117 | NOC117 | GPON | OSS | Publishing Package wise and district wise Mandal Network uptime and Mandal TT resolution MTTR dashboard Daily | Critical | HPSM | Incident Management | Manoj Nibrad
118 | NOC118 | GPON | OSS | Publishing Package wise and district wise Mandal Network uptime and Mandal TT resolution MTTR dashboard Weekly | Critical | HPSM | Incident Management | Manoj Nibrad
119 | NOC119 | GPON | OSS | Publishing Package wise and district wise Mandal Network uptime and Mandal TT resolution MTTR dashboard Monthly | Critical | HPSM | Incident Management | Manoj Nibrad
120 | NOC120 | GPON | OSS | Publishing Package wise and district wise Mandal Network uptime and Mandal TT resolution MTTR dashboard (Selective from and to dates) | Critical | HPSM | Incident Management | Manoj Nibrad
121 | NOC121 | All Domain | OSS | Based on DFR, prepare and publishing domain wise Ticketing dashboard Hourly | Critical | HPSM | Incident Management | Manoj Nibrad
122 | NOC122 | All Domain | OSS | Based on DFR, prepare and publishing domain wise Ticketing dashboard Daily | Critical | HPSM | Incident Management | Manoj Nibrad
123 | NOC123 | All Domain | OSS | Based on DFR, prepare and publishing domain wise Ticketing dashboard Weekly | Critical | HPSM | Incident Management | Manoj Nibrad
124 | NOC124 | All Domain | OSS | Based on DFR, prepare and publishing domain wise Ticketing dashboard Monthly | Critical | HPSM | Incident Management | Manoj Nibrad
125 | NOC125 | All Domain | OSS | Based on DFR, prepare and publishing domain wise Ticketing dashboard (Selective from and to dates) | Critical | HPSM | Incident Management | Manoj Nibrad
126 | NOC126 | All Domain | OSS | Publishing of total field network devices dashboard Daily | Critical | OSS Dashboards | UTM | Manoj Nibrad
127 | NOC127 | All Domain | OSS | Publishing of total field network devices dashboard Weekly | Critical | OSS Dashboards | UTM | Manoj Nibrad
128 | NOC128 | All Domain | OSS | Publishing of total field network devices dashboard Monthly | Critical | OSS Dashboards | UTM | Manoj Nibrad
129 | NOC129 | All Domain | OSS | Publishing of total field network devices dashboard (Selective from and to dates) | Critical | OSS Dashboards | UTM | Manoj Nibrad
130 | NOC130 | Field Passive Infra | OSS | Preparion and publishing Field Passive Infra Devices Uptime dashboard (Zone,Mandal,GP wise) Daily | Critical | HPSM | Incident Management | Manoj Nibrad
131 | NOC131 | Field Passive Infra | OSS | Preparion and publishing Field Passive Infra Devices Uptime dashboard (Zone,Mandal,GP wise) Weekly | Critical | HPSM | Incident Management | Manoj Nibrad
132 | NOC132 | Field Passive Infra | OSS | Preparion and publishing Field Passive Infra Devices Uptime dashboard (Zone,Mandal,GP wise) Monthly | Critical | HPSM | Incident Management | Manoj Nibrad
133 | NOC133 | Field Passive Infra | OSS | Preparion and publishing Field Passive Infra Devices Uptime dashboard (Zone,Mandal,GP wise) (Selective from and to dates) | Critical | NNMI | NPS | Manoj Nibrad
134 | NOC134 | Planned Events | OSS | Publishing Planned Events dashboard of all the packages(like , PE applied,Success,cancelation etc) Daily | Critical | NNMI | NPS | Manoj Nibrad
135 | NOC135 | Planned Events | OSS | Publishing Planned Events dashboard of all the packages(like , PE applied,Success,cancelation etc) Weekly | Critical | NNMI | NPS | Manoj Nibrad
136 | NOC136 | Planned Events | OSS | Publishing Planned Events dashboard of all the packages(like , PE applied,Success,cancelation etc) Monthly | Critical | NNMI | NPS | Manoj Nibrad
137 | NOC137 | Planned Events | OSS | Publishing Planned Events dashboard of all the packages(like , PE applied,Success,cancelation etc) (Selective from and to dates) | Critical | NNMI | NPS | Manoj Nibrad
138 | NOC138 | DC IT Active Infra | OSS | Preparation and publishing of all DC IT devices availability dashboard Daily | NON-Critical | HPSM | Incident Management | Manoj Nibrad
139 | NOC139 | DC IT Active Infra | OSS | Preparation and publishing of all DC IT devices availability dashboard Weekly | NON-Critical | HPSM | Incident Management | Manoj Nibrad
140 | NOC140 | DC IT Active Infra | OSS | Preparation and publishing of all DC IT devices availability dashboard Monthly | NON-Critical | HPSM | Incident Management | Manoj Nibrad
141 | NOC141 | DC IT Active Infra | OSS | Preparation and publishing of all DC IT devices availability dashboard (Selective from and to dates) | NON-Critical | HPSM | Incident Management | Manoj Nibrad
142 | NOC142 | DC Passive Infra | OSS | Preparation and publishing of all DC Non IT devices availability dashboard Daily | NON-Critical | HPSM | Incident Management | Manoj Nibrad
143 | NOC143 | DC Passive Infra | OSS | Preparation and publishing of all DC Non IT devices availability dashboard Weekly | NON-Critical | HPSM | Incident Management | Manoj Nibrad
144 | NOC144 | DC Passive Infra | OSS | Preparation and publishing of all DC Non IT devices availability dashboard Monthly | NON-Critical | HPSM | Incident Management | Manoj Nibrad
145 | NOC145 | DC Passive Infra | OSS | Preparation and publishing of all DC Non IT devices availability dashboard (Selective from and to dates) | NON-Critical | HPSM | Incident Management | Manoj Nibrad
146 | NOC146 | OSS | OSS | Preparation and publishing of all application availability dashboard Daily | Critical | OSS Dashboards | UOC | Manoj Nibrad
147 | NOC147 | OSS | OSS | Preparation and publishing of all application availability dashboard Weekly | Critical | OSS Dashboards | UOC | Manoj Nibrad
148 | NOC148 | OSS | OSS | Preparation and publishing of all application availability dashboard Monthly | Critical | OSS Dashboards | UOC | Manoj Nibrad
149 | NOC149 | OSS | OSS | Preparation and publishing of all application availability dashboard (Selective from and to dates) | Critical | OSS Dashboards | UOC | Manoj Nibrad
150 | NOC150 | OSS | OSS | Service assurance & Dashboards | Critical | OSS Dashboards | HPE Telco Unified OSS Console | Manoj Nibrad
151 | NOC151 | OSS | OSS | Network Service Assurance Dashboards | Critical | OSS Dashboards | HPE Telco Unified OSS Console | Manoj Nibrad
152 | NOC152 | OSS | OSS | Business Service Assurance Dashboards | Critical | OSS Dashboards | HPE Telco Unified OSS Console | Manoj Nibrad
153 | NOC153 | OSS | OSS | Customer Service Dashboards | Critical | OSS Dashboards | HPE Telco Unified OSS Console | Manoj Nibrad
154 | NOC154 | OSS | OSS | Security Assurance Dashboard | Critical | OSS Dashboards | HPE Telco Unified OSS Console | Manoj Nibrad
155 | NOC155 | OSS | OSS | Service Inventory | Critical | OSS Dashboards | HPE Telco Unified OSS Console | Manoj Nibrad
156 | NOC156 | OSS | OSS | Service Monitoring | Critical | OSS Dashboards | HPE Telco Unified OSS Console | Manoj Nibrad
157 | NOC157 | OSS | OSS | OSS Intigration for POC Locations LCO,RMSO & MSO | Critical | HPSM | Incident Management | Manoj Nibrad
158 | NOC158 | OSS | OSS | OSS Intigration for Live LCO , RMSO & MSO | Critical | HPSM | Incident Management | Manoj Nibrad
159 | NOC159 | OSS | OSS | Video customer inventory , Internet customer inventory , Bandwidth allocation inventory count etc., | Critical | HPSM | Incident Management | Manoj Nibrad
160 | NOC160 | DC Passive Infra | OSS | Preparation and publishing of all DC passive infra(Internal, OEM) PM dashboard Daily | NON-Critical | OSS Dashboards | UOC | Manoj Nibrad
161 | NOC161 | DC Passive Infra | OSS | Preparation and publishing of all DC passive infra(Internal, OEM) PM dashboard Weekly | NON-Critical | OSS Dashboards | UOC | Manoj Nibrad
162 | NOC162 | DC Passive Infra | OSS | Preparation and publishing of all DC passive infra(Internal, OEM) PM dashboard Monthly | NON-Critical | OSS Dashboards | UOC | Manoj Nibrad
163 | NOC163 | DC Passive Infra | OSS | Preparation and publishing of all DC passive infra(Internal, OEM) PM dashboard (Selective from and to dates) | NON-Critical | OSS Dashboards | UOC | Manoj Nibrad
164 | NOC164 | NOC | OSS | Preparation and publishing of all devices, application, software AMC dashboard Daily | Critical | OSS Dashboards | Asset Manager | Manoj Nibrad
165 | NOC165 | NOC | OSS | Preparation and publishing of all devices, application, software AMC dashboard Weekly | Critical | OSS Dashboards | Asset Manager | Manoj Nibrad
166 | NOC166 | NOC | OSS | Preparation and publishing of all devices, application, software AMC dashboard Monthly | Critical | OSS Dashboards | Asset Manager | Manoj Nibrad
167 | NOC167 | NOC | OSS | Preparation and publishing of all devices, application, software AMC dashboard (Selective from and to dates) | Critical | OSS Dashboards | Asset Manager | Manoj Nibrad
168 | NOC168 | NOC | OSS | Publishing of all major events in Tnoc dashboard Daily | Critical | HPSM | Incident Management | Manoj Nibrad
169 | NOC169 | NOC | OSS | Publishing of all major events in Tnoc dashboard Weekly | Critical | HPSM | Incident Management | Manoj Nibrad
170 | NOC170 | NOC | OSS | Publishing of all major events in Tnoc dashboard Monthly | Critical | HPSM | Incident Management | Manoj Nibrad
171 | NOC171 | NOC | OSS | Publishing of all major events in Tnoc dashboard (Selective from and to dates) | Critical | HPSM | Incident Management | Manoj Nibrad
172 | NOC172 | BBNL Reports | OSS | Publishing of BBNL dashboard Daily | Critical | HPSM | Incident Management | Manoj Nibrad
173 | NOC173 | BBNL Reports | OSS | Publishing of BBNL dashboard Weekly | Critical | HPSM | Incident Management | Manoj Nibrad
174 | NOC174 | BBNL Reports | OSS | Publishing of BBNL dashboard Monthly | Critical | HPSM | Incident Management | Manoj Nibrad
175 | NOC175 | BBNL Reports | OSS | Publishing of BBNL dashboard (Selective from and to dates) | Critical | HPSM | Incident Management | Manoj Nibrad
176 | NOC176 | Field Passive Infra | OSS | Publishing of Field Passive infra total devices dashboard Daily | Critical | NNMI | NNMI | Manoj Nibrad
177 | NOC177 | Field Passive Infra | OSS | Publishing of Field Passive infra total devices dashboard Weekly | Critical | NNMI | NNMI | Manoj Nibrad
178 | NOC178 | Field Passive Infra | OSS | Publishing of Field Passive infra total devices dashboard Monthly | Critical | NNMI | NNMI | Manoj Nibrad
179 | NOC179 | Field Passive Infra | OSS | Publishing of Field Passive infra total devices dashboard (Selective from and to dates) | Critical | NNMI | NNMI | Manoj Nibrad
180 | NOC180 | DWDM | OSS | Published Zonal Network uptime (like, total scope, litup count and availability according to the category) Daily | Critical | HPSM | Incident Management | Manoj Nibrad
181 | NOC181 | DWDM | OSS | Published Zonal Network uptime (like, total scope, litup count and availability according to the category) Weekly | Critical | HPSM | Incident Management | Manoj Nibrad
182 | NOC182 | DWDM | OSS | Published Zonal Network uptime (like, total scope, litup count and availability according to the category) Monthly | Critical | HPSM | Incident Management | Manoj Nibrad
183 | NOC183 | DWDM | OSS | Published Zonal Network uptime (like, total scope, litup count and availability according to the category) (Selective from and to dates) | Critical | HPSM | Incident Management | Manoj Nibrad
184 | NOC184 | DWDM | OSS | Publishing Package wise , district wise and node wise (like DWDM,OADM) Zonal Network uptime and Mandal TT resolution MTTR dashboard Daily | Critical | HPSM | Incident Management | Manoj Nibrad
185 | NOC185 | DWDM | OSS | Publishing Package wise , district wise and node wise (like DWDM,OADM) Zonal Network uptime and Mandal TT resolution MTTR dashboard Weekly | Critical | HPSM | Incident Management | Manoj Nibrad
186 | NOC186 | DWDM | OSS | Publishing Package wise , district wise and node wise (like DWDM,OADM) Zonal Network uptime and Mandal TT resolution MTTR dashboard Monthly | Critical | HPSM | Incident Management | Manoj Nibrad
187 | NOC187 | DWDM | OSS | Publishing Package wise , district wise and node wise (like DWDM,OADM) Zonal Network uptime and Mandal TT resolution MTTR dashboard (Selective from and to dates) | Critical | HPSM | Incident Management | Manoj Nibrad
188 | NOC188 | DWDM | OSS | Preparation and publishing of Zonal link summary , uptime and MTTR dashboard Daily | Critical | HPSM | Incident Management | Manoj Nibrad
189 | NOC189 | DWDM | OSS | Preparation and publishing of Zonal link summary , uptime and MTTR dashboard Weekly | Critical | HPSM | Incident Management | Manoj Nibrad
190 | NOC190 | DWDM | OSS | Preparation and publishing of Zonal link summary , uptime and MTTR dashboard Monthly | Critical | HPSM | Incident Management | Manoj Nibrad
191 | NOC191 | DWDM | OSS | Preparation and publishing of Zonal link summary , uptime and MTTR dashboard (Selective from and to dates) | Critical | HPSM | Incident Management | Manoj Nibrad
192 | NOC192 | DWDM | OSS | Preparing and publishing Zonal Link Fiber MTTR dashboard Daily | Critical | HPSM | Incident Management | Manoj Nibrad
193 | NOC193 | DWDM | OSS | Preparing and publishing Zonal Link Fiber MTTR dashboard Weekly | Critical | HPSM | Incident Management | Manoj Nibrad
194 | NOC194 | DWDM | OSS | Preparing and publishing Zonal Link Fiber MTTR dashboard Monthly | Critical | HPSM | Incident Management | Manoj Nibrad
195 | NOC195 | DWDM | OSS | Preparing and publishing Zonal Link Fiber MTTR dashboard (Selective from and to dates) | Critical | HPSM | Incident Management | Manoj Nibrad
196 | NOC196 | DWDM | OSS | Preparation and publishing dashboard for major events happened in network Hourly | Critical | HPSM | Incident Management | Manoj Nibrad
197 | NOC197 | DWDM | OSS | Preparation and publishing dashboard for major events happened in network Daily | Critical | HPSM | Incident Management | Manoj Nibrad
198 | NOC198 | DWDM | OSS | Preparation and publishing dashboard for major events happened in network Weekly | Critical | HPSM | Incident Management | Manoj Nibrad
199 | NOC199 | DWDM | OSS | Preparation and publishing dashboard for major events happened in network Monthly | Critical | HPSM | Incident Management | Manoj Nibrad
200 | NOC200 | DWDM | OSS | Preparation and publishing dashboard for major events happened in network (Selective from and to dates) | Critical | HPSM | Incident Management | Manoj Nibrad
201 | NOC201 | DWDM | OSS | Preparation and publishing of all DC DWDM devices availability dashboard Daily | Critical | OSS Dashboards | UOC | Manoj Nibrad
202 | NOC202 | DWDM | OSS | Preparation and publishing of all DC DWDM devices availability dashboard Weekly | Critical | OSS Dashboards | UOC | Manoj Nibrad
203 | NOC203 | DWDM | OSS | Preparation and publishing of all DC DWDM devices availability dashboard Monthly | Critical | OSS Dashboards | UOC | Manoj Nibrad
204 | NOC204 | DWDM | OSS | Preparation and publishing of all DC DWDM devices availability dashboard (Selective from and to dates) | Critical | OSS Dashboards | UOC | Manoj Nibrad
205 | NOC205 | DWDM | OSS | T-NOC Report : Zonal Links DWDM DFR Status as on 15-May-2025 Action to be taken on Top Most Priority Daily | Critical | HPSM | Incident Management | Manoj Nibrad
206 | NOC206 | DWDM | OSS | T-NOC Report : Zonal Links DWDM DFR Status as on 15-May-2025 Action to be taken on Top Most Priority Weekly | Critical | HPSM | Incident Management | Manoj Nibrad
207 | NOC207 | DWDM | OSS | T-NOC Report : Zonal Links DWDM DFR Status as on 15-May-2025 Action to be taken on Top Most Priority Monthly | Critical | HPSM | Incident Management | Manoj Nibrad
208 | NOC208 | DWDM | OSS | T-NOC Report : Zonal Links DWDM DFR Status as on 15-May-2025 Action to be taken on Top Most Priority (Selective from and to dates) | Critical | HPSM | Incident Management | Manoj Nibrad
209 | NOC209 | DWDM | OSS | Zonal High Received Span Losses with TT for PKG_A Daily | Critical | OSS Dashboards | UOC | Manoj Nibrad
210 | NOC210 | DWDM | OSS | Zonal High Received Span Losses with TT for PKG_A Weekly | Critical | OSS Dashboards | UOC | Manoj Nibrad
211 | NOC211 | DWDM | OSS | Zonal High Received Span Losses with TT for PKG_A Monthly | Critical | OSS Dashboards | UOC | Manoj Nibrad
212 | NOC212 | DWDM | OSS | Zonal High Received Span Losses with TT for PKG_A (Selective from and to dates) | Critical | OSS Dashboards | UOC | Manoj Nibrad
213 | NOC213 | DWDM | OSS | Zonal High Received Span Losses with TT for PKG_B Daily | Critical | OSS Dashboards | UOC | Manoj Nibrad
214 | NOC214 | DWDM | OSS | Zonal High Received Span Losses with TT for PKG_B Weekly | Critical | OSS Dashboards | UOC | Manoj Nibrad
215 | NOC215 | DWDM | OSS | Zonal High Received Span Losses with TT for PKG_B Monthly | Critical | OSS Dashboards | UOC | Manoj Nibrad
216 | NOC216 | DWDM | OSS | Zonal High Received Span Losses with TT for PKG_B (Selective from and to dates) | Critical | OSS Dashboards | UOC | Manoj Nibrad
217 | NOC217 | DWDM | OSS | Zonal High Received Span Losses with TT for PKG_C Daily | Critical | OSS Dashboards | UOC | Manoj Nibrad
218 | NOC218 | DWDM | OSS | Zonal High Received Span Losses with TT for PKG_C Weekly | Critical | OSS Dashboards | UOC | Manoj Nibrad
219 | NOC219 | DWDM | OSS | Zonal High Received Span Losses with TT for PKG_C Monthly | Critical | OSS Dashboards | UOC | Manoj Nibrad
220 | NOC220 | DWDM | OSS | Zonal High Received Span Losses with TT for PKG_C (Selective from and to dates) | Critical | OSS Dashboards | UOC | Manoj Nibrad
221 | NOC221 | GPON/IPMPLS | OSS | Monitoring and published of Dark Fiber and TSWAN KPI Daily | Critical | HPSM | Incident Management | Manoj Nibrad
222 | NOC222 | GPON/IPMPLS | OSS | Monitoring and published of Dark Fiber and TSWAN KPI Weekly | Critical | HPSM | Incident Management | Manoj Nibrad
223 | NOC223 | GPON/IPMPLS | OSS | Monitoring and published of Dark Fiber and TSWAN KPI Monthly | Critical | HPSM | Incident Management | Manoj Nibrad
224 | NOC224 | GPON/IPMPLS | OSS | Monitoring and published of Dark Fiber and TSWAN KPI (Selective from and to dates) | Critical | HPSM | Incident Management | Manoj Nibrad
225 | NOC225 | IP/MPLS | OSS | Preparation and publishing of GP to GP and GP to Mandal link summary , uptime and MTTR dashboard Hourly | Critical | HPSM | Incident Management | Manoj Nibrad
226 | NOC226 | IP/MPLS | OSS | Preparation and publishing of GP to GP and GP to Mandal link summary , uptime and MTTR dashboard Daily | Critical | HPSM | Incident Management | Manoj Nibrad
227 | NOC227 | IP/MPLS | OSS | Preparation and publishing of GP to GP and GP to Mandal link summary , uptime and MTTR dashboard Weekly | Critical | HPSM | Incident Management | Manoj Nibrad
228 | NOC228 | IP/MPLS | OSS | Preparation and publishing of GP to GP and GP to Mandal link summary , uptime and MTTR dashboard Monthly | Critical | HPSM | Incident Management | Manoj Nibrad
229 | NOC229 | IP/MPLS | OSS | Preparation and publishing of GP to GP and GP to Mandal link summary , uptime and MTTR dashboard (Selective from and to dates) | Critical | HPSM | Incident Management | Manoj Nibrad
230 | NOC230 | IP/MPLS | OSS | Preparation and publishing of Mandal to Mandal and Mandal to Zonal link summary , uptime and MTTR dashboard Daily | Critical | HPSM | Incident Management | Manoj Nibrad
231 | NOC231 | IP/MPLS | OSS | Preparation and publishing of Mandal to Mandal and Mandal to Zonal link summary , uptime and MTTR dashboard Weekly | Critical | HPSM | Incident Management | Manoj Nibrad
232 | NOC232 | IP/MPLS | OSS | Preparation and publishing of Mandal to Mandal and Mandal to Zonal link summary , uptime and MTTR dashboard Monthly | Critical | HPSM | Incident Management | Manoj Nibrad
233 | NOC233 | IP/MPLS | OSS | Preparation and publishing of Mandal to Mandal and Mandal to Zonal link summary , uptime and MTTR dashboard (Selective from and to dates) | Critical | HPSM | Incident Management | Manoj Nibrad
234 | NOC234 | IP/MPLS | OSS | High priority link like Tfiber ring monitoring and publishing KPI Hourly | Critical | HPSM | Incident Management | Manoj Nibrad
235 | NOC235 | IP/MPLS | OSS | High priority link like Tfiber ring monitoring and publishing KPI Daily | Critical | HPSM | Incident Management | Manoj Nibrad
236 | NOC236 | IP/MPLS | OSS | High priority link like Tfiber ring monitoring and publishing KPI Weekly | Critical | HPSM | Incident Management | Manoj Nibrad
237 | NOC237 | IP/MPLS | OSS | High priority link like Tfiber ring monitoring and publishing KPI Monthly | Critical | HPSM | Incident Management | Manoj Nibrad
238 | NOC238 | IP/MPLS | OSS | High priority link like Tfiber ring monitoring and publishing KPI (Selective from and to dates) | Critical | HPSM | Incident Management | Manoj Nibrad
239 | NOC239 | IP/MPLS | OSS | Enteprise Services Delivery ( Aitel Towers, Airtel LWEsite, pioneer etc ) Monitoring, preparation KPI like Service Up reports Hourly | Critical | HPSM | Incident Management | Manoj Nibrad
240 | NOC240 | IP/MPLS | OSS | Enteprise Services Delivery ( Aitel Towers, Airtel LWEsite, pioneer etc ) Monitoring, preparation KPI like Service Up reports Daily | Critical | HPSM | Incident Management | Manoj Nibrad
241 | NOC241 | IP/MPLS | OSS | Enteprise Services Delivery ( Aitel Towers, Airtel LWEsite, pioneer etc ) Monitoring, preparation KPI like Service Up reports Weekly | Critical | HPSM | Incident Management | Manoj Nibrad
242 | NOC242 | IP/MPLS | OSS | Enteprise Services Delivery ( Aitel Towers, Airtel LWEsite, pioneer etc ) Monitoring, preparation KPI like Service Up reports Monthly | Critical | HPSM | Incident Management | Manoj Nibrad
243 | NOC243 | IP/MPLS | OSS | Enteprise Services Delivery ( Aitel Towers, Airtel LWEsite, pioneer etc ) Monitoring, preparation KPI like Service Up reports (Selective from and to dates) | Critical | HPSM | Incident Management | Manoj Nibrad
244 | NOC244 | IP/MPLS | OSS | Preparation and publishing of Enterprise Customer Service KPIs like availability, packet drops, latency, jitter & bandwidth utilization Daily | Critical | HPSM | Incident Management | Manoj Nibrad
245 | NOC245 | IP/MPLS | OSS | Preparation and publishing of Enterprise Customer Service KPIs like availability, packet drops, latency, jitter & bandwidth utilization Weekly | Critical | HPSM | Incident Management | Manoj Nibrad
246 | NOC246 | IP/MPLS | OSS | Preparation and publishing of Enterprise Customer Service KPIs like availability, packet drops, latency, jitter & bandwidth utilization Monthly | Critical | HPSM | Incident Management | Manoj Nibrad
247 | NOC247 | IP/MPLS | OSS | Preparation and publishing of Enterprise Customer Service KPIs like availability, packet drops, latency, jitter & bandwidth utilization (Selective from and to dates) | Critical | HPSM | Incident Management | Manoj Nibrad
248 | NOC248 | IP/MPLS | OSS | Preparation and publishing of all DC MPLS Network devices availability dashboard Daily | Critical | NNMI | NPS | Manoj Nibrad
249 | NOC249 | IP/MPLS | OSS | Preparation and publishing of all DC MPLS Network devices availability dashboard Weekly | Critical | NNMI | NPS | Manoj Nibrad
250 | NOC250 | IP/MPLS | OSS | Preparation and publishing of all DC MPLS Network devices availability dashboard Monthly | Critical | NNMI | NPS | Manoj Nibrad
251 | NOC251 | IP/MPLS | OSS | Preparation and publishing of all DC MPLS Network devices availability dashboard (Selective from and to dates) | Critical | NNMI | NPS | Manoj Nibrad
252 | NOC252 | IP/MPLS | OSS | Prepartion and publishing of Core link availability and utilization dashboard Hourly | Critical | HPSM | Incident Management | Manoj Nibrad
253 | NOC253 | IP/MPLS | OSS | Prepartion and publishing of Core link availability and utilization dashboard Daily | Critical | NNMI | NPS | Manoj Nibrad
254 | NOC254 | IP/MPLS | OSS | Prepartion and publishing of Core link availability and utilization dashboard Weekly | Critical | NNMI | NPS | Manoj Nibrad
255 | NOC255 | IP/MPLS | OSS | Prepartion and publishing of Core link availability and utilization dashboard Monthly | Critical | NNMI | NPS | Manoj Nibrad
256 | NOC256 | IP/MPLS | OSS | Prepartion and publishing of Core link availability and utilization dashboard (Selective from and to dates) | Critical | NNMI | NPS | Manoj Nibrad
257 | NOC257 | IP/MPLS | OSS | Package A Low RX Optical Power Levels in IPMPLS Network Daily | Critical | NNMI | NNMI | Manoj Nibrad
258 | NOC258 | IP/MPLS | OSS | Package A Low RX Optical Power Levels in IPMPLS Network Weekly | Critical | NNMI | NNMI | Manoj Nibrad
259 | NOC259 | IP/MPLS | OSS | Package A Low RX Optical Power Levels in IPMPLS Network Monthly | Critical | NNMI | NNMI | Manoj Nibrad
260 | NOC260 | IP/MPLS | OSS | Package A Low RX Optical Power Levels in IPMPLS Network (Selective from and to dates) | Critical | NNMI | NNMI | Manoj Nibrad
261 | NOC261 | IP/MPLS | OSS | Package B Low RX Optical Power Levels in IPMPLS Network Daily | Critical | NNMI | NNMI | Manoj Nibrad
262 | NOC262 | IP/MPLS | OSS | Package B Low RX Optical Power Levels in IPMPLS Network Weekly | Critical | NNMI | NNMI | Manoj Nibrad
263 | NOC263 | IP/MPLS | OSS | Package B Low RX Optical Power Levels in IPMPLS Network Monthly | Critical | NNMI | NNMI | Manoj Nibrad
264 | NOC264 | IP/MPLS | OSS | Package B Low RX Optical Power Levels in IPMPLS Network (Selective from and to dates) | Critical | NNMI | NNMI | Manoj Nibrad
265 | NOC265 | IP/MPLS | OSS | Package C Low RX Optical Power Levels in IPMPLS Network Daily | Critical | NNMI | NNMI | Manoj Nibrad
266 | NOC266 | IP/MPLS | OSS | Package C Low RX Optical Power Levels in IPMPLS Network Weekly | Critical | NNMI | NNMI | Manoj Nibrad
267 | NOC267 | IP/MPLS | OSS | Package C Low RX Optical Power Levels in IPMPLS Network Monthly | Critical | NNMI | NNMI | Manoj Nibrad
268 | NOC268 | IP/MPLS | OSS | Package C Low RX Optical Power Levels in IPMPLS Network (Selective from and to dates) | Critical | NNMI | NNMI | Manoj Nibrad
269 | NOC269 | IP/MPLS | OSS | Mandal Link Down + GP Link Down DFR Daily | Critical | HPSM | Incident Management | Manoj Nibrad
270 | NOC270 | IP/MPLS | OSS | Mandal Link Down + GP Link Down DFR Weekly | Critical | HPSM | Incident Management | Manoj Nibrad
271 | NOC271 | IP/MPLS | OSS | Mandal Link Down + GP Link Down DFR Monthly | Critical | HPSM | Incident Management | Manoj Nibrad
272 | NOC272 | IP/MPLS | OSS | Mandal Link Down + GP Link Down DFR (Selective from and to dates) | Critical | HPSM | Incident Management | Manoj Nibrad
273 | NOC273 | All Domain | OSS | All Domain RMA Tracker //Daily Daily//Domain And package wise Filtering | Critical | HPSM | Incident Management | Manoj Nibrad
274 | NOC274 | All Domain | OSS | All Domain RMA Tracker //Daily Weekly Domain and package Wise Filtering | Critical | HPSM | Incident Management | Manoj Nibrad
275 | NOC275 | All Domain | OSS | All Domain RMA Tracker //Daily Monthly Domain and package Wise Filtering | Critical | HPSM | Incident Management | Manoj Nibrad
276 | NOC276 | All Domain | OSS | All OEM_TAC Cases Tracker Daily Domain and package Wise Filtering | Critical | HPSM | Incident Management | Manoj Nibrad
277 | NOC277 | All Domain | OSS | All OEM_TAC Cases Tracker Weekly Domain and package Wise Filtering | Critical | HPSM | Incident Management | Manoj Nibrad
278 | NOC278 | All Domain | OSS | All OEM_TAC Cases Tracker Monthly Domain and package Wise Filtering | Critical | HPSM | Incident Management | Manoj Nibrad
279 | NOC279 | All Domain | OSS | All OEM_TAC Cases Tracker (Selective from and to dates) Domain and package Wise Filtering | Critical | HPSM | Incident Management | Manoj Nibrad
280 | NOC280 | All Domain | OSS | All Sites Infra OPEN TTs details for HRT(High Temparature) Alarm Daily | Critical | HPSM | Incident Management | Manoj Nibrad
281 | NOC281 | All Domain | OSS | All Sites Infra OPEN TTs details for HRT(High Temparature) Alarm Weekly | Critical | HPSM | Incident Management | Manoj Nibrad
282 | NOC282 | All Domain | OSS | All Sites Infra OPEN TTs details for HRT(High Temparature) Alarm Monthly | Critical | HPSM | Incident Management | Manoj Nibrad
283 | NOC283 | All Domain | OSS | All Sites Infra OPEN TTs details for HRT(High Tempararure) Alarm (Selective from and to dates) | Critical | HPSM | Incident Management | Manoj Nibrad
284 | NOC284 | Field Passive Infra | OSS | Field Passive Infra :: Package Wise District Level Visibility Status Daily | Critical | NNMI | NNMI | Manoj Nibrad
285 | NOC285 | Field Passive Infra | OSS | Field Passive Infra :: Package Wise District Level Visibility Status Weekly | Critical | NNMI | NNMI | Manoj Nibrad
286 | NOC286 | Field Passive Infra | OSS | Field Passive Infra :: Package Wise District Level Visibility Status Monthly | Critical | NNMI | NNMI | Manoj Nibrad
287 | NOC287 | Field Passive Infra | OSS | Field Passive Infra :: Package Wise District Level Visibility Status (Selective from and to dates) | Critical | NNMI | NNMI | Manoj Nibrad
288 | NOC288 | Field Passive Infra | OSS | NNMI :: Integration Status with Reachability Daily | Critical | NNMI | NNMI | Manoj Nibrad
289 | NOC289 | Field Passive Infra | OSS | NNMI :: Integration Status with Reachability Weekly | Critical | NNMI | NNMI | Manoj Nibrad
290 | NOC290 | Field Passive Infra | OSS | NNMI :: Integration Status with Reachability Monthly | Critical | NNMI | NNMI | Manoj Nibrad
291 | NOC291 | Field Passive Infra | OSS | NNMI :: Integration Status with Reachability (Selective from and to dates) | Critical | NNMI | NNMI | Manoj Nibrad
292 | NOC292 | Field Passive Infra | OSS | PKG -A :: Open TTs for O&M GP for UPS Daily | Critical | HPSM | Incident Management | Manoj Nibrad
293 | NOC293 | Field Passive Infra | OSS | PKG -A :: Open TTs for O&M GP for UPS Weekly | Critical | HPSM | Incident Management | Manoj Nibrad
294 | NOC294 | Field Passive Infra | OSS | PKG -A :: Open TTs for O&M GP for UPS Monthly | Critical | HPSM | Incident Management | Manoj Nibrad
295 | NOC295 | Field Passive Infra | OSS | PKG -A :: Open TTs for O&M GP for UPS (Selective from and to dates) | Critical | HPSM | Incident Management | Manoj Nibrad
296 | NOC296 | Field Passive Infra | OSS | PKG -B :: Open TTs for O&M GP for UPS Daily | Critical | HPSM | Incident Management | Manoj Nibrad
297 | NOC297 | Field Passive Infra | OSS | PKG -B :: Open TTs for O&M GP for UPS Weekly | Critical | HPSM | Incident Management | Manoj Nibrad
298 | NOC298 | Field Passive Infra | OSS | PKG -B :: Open TTs for O&M GP for UPS Monthly | Critical | HPSM | Incident Management | Manoj Nibrad
299 | NOC299 | Field Passive Infra | OSS | PKG -B :: Open TTs for O&M GP for UPS (Selective from and to dates) | Critical | HPSM | Incident Management | Manoj Nibrad
300 | NOC300 | Field Passive Infra | OSS | PKG -C :: Open TTs for O&M GP for UPS Daily | Critical | HPSM | Incident Management | Manoj Nibrad
301 | NOC301 | Field Passive Infra | OSS | PKG -C :: Open TTs for O&M GP for UPS Weekly | Critical | HPSM | Incident Management | Manoj Nibrad
302 | NOC302 | Field Passive Infra | OSS | PKG -C :: Open TTs for O&M GP for UPS Monthly | Critical | HPSM | Incident Management | Manoj Nibrad
303 | NOC303 | Field Passive Infra | OSS | PKG -C :: Open TTs for O&M GP for UPS (Selective from and to dates) | Critical | HPSM | Incident Management | Manoj Nibrad
304 | NOC304 | Field Passive Infra | OSS | SNMP issues _ Report Daily | Critical | NNMI | NNMI | Manoj Nibrad
305 | NOC305 | Field Passive Infra | OSS | SNMP issues _ Report Weekly | Critical | NNMI | NNMI | Manoj Nibrad
306 | NOC306 | Field Passive Infra | OSS | SNMP issues _ Report Monthly | Critical | NNMI | NNMI | Manoj Nibrad
307 | NOC307 | Field Passive Infra | OSS | SNMP issues _ Report (Selective from and to dates) | Critical | NNMI | NNMI | Manoj Nibrad
308 | NOC308 | Field Passive Infra | OSS | Mandal EB & Zonal DG Running report Daily | Critical | HPSM | Incident Management | Manoj Nibrad
309 | NOC309 | Field Passive Infra | OSS | Mandal EB & Zonal DG Running report Weekly | Critical | HPSM | Incident Management | Manoj Nibrad
310 | NOC310 | Field Passive Infra | OSS | Mandal EB & Zonal DG Running report Monthly | Critical | HPSM | Incident Management | Manoj Nibrad
311 | NOC311 | Field Passive Infra | OSS | Mandal EB & Zonal DG Running report (Selective from and to dates) | Critical | HPSM | Incident Management | Manoj Nibrad
312 | NOC312 | Field Passive Infra | OSS | DG Running status NNMi Logs Daily | Critical | NNMI | NNMI | Manoj Nibrad
313 | NOC313 | Field Passive Infra | OSS | DG Running status NNMi Logs Weekly | Critical | NNMI | NNMI | Manoj Nibrad
314 | NOC314 | Field Passive Infra | OSS | DG Running status NNMi Logs Monthly | Critical | NNMI | NNMI | Manoj Nibrad
315 | NOC315 | Field Passive Infra | OSS | DG Running status NNMi Logs (Selective from and to dates) | Critical | NNMI | NNMI | Manoj Nibrad
316 | NOC316 | Service Monitoring | OSS | Customised Dashboard as per Department/Service/Locations, etc.. Daily | Critical | HPSM | Incident Management | Manoj Nibrad
317 | NOC317 | Service Monitoring | OSS | Customised Dashboard as per Department/Service/Locations, etc..Weekly | Critical | HPSM | Incident Management | Manoj Nibrad
318 | NOC318 | Service Monitoring | OSS | Customised Dashboard as per Department/Service/Locations, etc..Monthly | Critical | HPSM | Incident Management | Manoj Nibrad
319 | NOC319 | Service Monitoring | OSS | Customised Dashboard as per Department/Service/Locations, etc..Selective Dates | Critical | HPSM | Incident Management | Manoj Nibrad
320 | NOC320 | Service Monitoring | OSS | T-NOC Report :: GI Sites SD SA Report Daily | Critical | HPSM | Incident Management | Manoj Nibrad
321 | NOC321 | Service Monitoring | OSS | T-NOC Report :: GI Sites SD SA Report Weekly | Critical | HPSM | Incident Management | Manoj Nibrad
322 | NOC322 | Service Monitoring | OSS | T-NOC Report :: GI Sites SD SA Report Monthly | Critical | HPSM | Incident Management | Manoj Nibrad
323 | NOC323 | Service Monitoring | OSS | T-NOC Report :: GI Sites SD SA Report (Selective from and to dates) | Critical | HPSM | Incident Management | Manoj Nibrad
324 | NOC324 | Service Monitoring | OSS | List of GI with bandwidth Utilization Details Daily | Critical | OSS Dashboards | PMS(UOC) | Manoj Nibrad
325 | NOC325 | Service Monitoring | OSS | List of GI with bandwidth Utilization Details Weekly | Critical | OSS Dashboards | PMS(UOC) | Manoj Nibrad
326 | NOC326 | Service Monitoring | OSS | List of GI with bandwidth Utilization Details Monthly | Critical | OSS Dashboards | PMS(UOC) | Manoj Nibrad
327 | NOC327 | Service Monitoring | OSS | List of GI with bandwidth Utilization Details (Selective from and to dates) | Critical | OSS Dashboards | PMS(UOC) | Manoj Nibrad
328 | NOC328 | Service Monitoring | OSS | T-NOC :: Status Summary of Bandwidth Utilization & Non Utilization of WIFI Routers in GB & ONTs Status Daily | Critical | OSS Dashboards | PMS(UOC) | Manoj Nibrad
329 | NOC329 | Service Monitoring | OSS | T-NOC :: Status Summary of Bandwidth Utilization & Non Utilization of WIFI Routers in GB & ONTs Status Weekly | Critical | OSS Dashboards | PMS(UOC) | Manoj Nibrad
330 | NOC330 | Service Monitoring | OSS | T-NOC :: Status Summary of Bandwidth Utilization & Non Utilization of WIFI Routers in GB & ONTs Status Monthly | Critical | OSS Dashboards | PMS(UOC) | Manoj Nibrad
331 | NOC331 | Service Monitoring | OSS | T-NOC :: Status Summary of Bandwidth Utilization & Non Utilization of WIFI Routers in GB & ONTs Status (Selective from and to dates) | Critical | OSS Dashboards | PMS(UOC) | Manoj Nibrad
332 | NOC332 | Service Monitoring | OSS | Request for FTTH Connection Details Sheet for T-Fiber Daily | Critical | OSS Dashboards | PMS(UOC) | Manoj Nibrad
333 | NOC333 | Service Monitoring | OSS | Request for FTTH Connection Details Sheet for T-Fiber Weekly | Critical | OSS Dashboards | PMS(UOC) | Manoj Nibrad
334 | NOC334 | Service Monitoring | OSS | Request for FTTH Connection Details Sheet for T-Fiber Monthly | Critical | OSS Dashboards | PMS(UOC) | Manoj Nibrad
335 | NOC335 | Service Monitoring | OSS | Request for FTTH Connection Details Sheet for T-Fiber (Selective from and to dates) | Critical | OSS Dashboards | PMS(UOC) | Manoj Nibrad
336 | NOC336 | Service Monitoring | OSS | Service Delivery & Service Assurance Dash Board (Signed Forms) Daily | Critical | HPSM | Incident Management | Manoj Nibrad
337 | NOC337 | Service Monitoring | OSS | Service Delivery & Service Assurance Dash Board (Signed Forms) Weekly | Critical | HPSM | Incident Management | Manoj Nibrad
338 | NOC338 | Service Monitoring | OSS | Service Delivery & Service Assurance Dash Board (Signed Forms) Monthly | Critical | HPSM | Incident Management | Manoj Nibrad
339 | NOC339 | Service Monitoring | OSS | Service Delivery & Service Assurance Dash Board (Signed Forms) (Selective from and to dates) | Critical | HPSM | Incident Management | Manoj Nibrad
340 | NOC340 | All Domain | OSS | PE Mapping with MTTR report Daily | Critical | HPSM | Incident Management | Manoj Nibrad
341 | NOC341 | All Domain | OSS | PE Mapping with MTTR report Weekly | Critical | HPSM | Incident Management | Manoj Nibrad
342 | NOC342 | All Domain | OSS | PE Mapping with MTTR report Monthly | Critical | HPSM | Incident Management | Manoj Nibrad
343 | NOC343 | All Domain | OSS | PE Mapping with MTTR report (Selective from and to dates) | Critical | HPSM | Incident Management | Manoj Nibrad
344 | NOC344 | Service Delivery | BSS | GI GP Wifi HH Delivery Status Daily | Critical | BSS | CRM | Manoj Nibrad
345 | NOC345 | Service Delivery | BSS | GI GP Wifi HH Delivery Status Weekly | Critical | BSS | CRM | Manoj Nibrad
346 | NOC346 | Service Delivery | BSS | GI GP Wifi HH Delivery Status Monthly | Critical | BSS | CRM | Manoj Nibrad
347 | NOC347 | Service Delivery | BSS | GI GP Wifi HH Delivery Status (Selective from and to dates) | Critical | BSS | CRM | Manoj Nibrad
348 | NOC348 | Service Delivery | BSS | Service IDs for all GI Locatinos Daily | Critical | BSS | CRM | Manoj Nibrad
349 | NOC349 | Service Delivery | BSS | Service IDs for all GI Locatinos Weekly | Critical | BSS | CRM | Manoj Nibrad
350 | NOC350 | Service Delivery | BSS | Service IDs for all GI Locatinos Monthly | Critical | BSS | CRM | Manoj Nibrad
351 | NOC351 | Service Delivery | BSS | Service IDs for all GI Locatinos (Selective from and to dates) | Critical | BSS | CRM | Manoj Nibrad
352 | NOC352 | Service Delivery | BSS | Household Delivery Status Report Daily | Critical | BSS | CRM | Manoj Nibrad
353 | NOC353 | Service Delivery | BSS | Household Delivery Status Report Weekly | Critical | BSS | CRM | Manoj Nibrad
354 | NOC354 | Service Delivery | BSS | Household Delivery Status Report Monthly | Critical | BSS | CRM | Manoj Nibrad
355 | NOC355 | Service Delivery | BSS | Household Delivery Status Report (Selective from and to dates) | Critical | BSS | CRM | Manoj Nibrad
356 | NOC356 | All Domain | OSS | Alarm seviority(Critical/major/Minor)(Domain wise Filter) Daily | Critical | OSS Dashboards | VTemip | Manoj Nibrad
357 | NOC357 | All Domain | OSS | Alarm seviority(Critical/major/Minor)(Domain wise Filter) Weekly | Critical | OSS Dashboards | VTemip | Manoj Nibrad
358 | NOC358 | All Domain | OSS | Alarm seviority(Critical/major/Minor)(Domain wise Filter) Monthly | Critical | OSS Dashboards | VTemip | Manoj Nibrad
359 | NOC359 | All Domain | OSS | Alarm seviority(Critical/major/Minor)(Domain wise Filter) (Selective from and to dates) | Critical | OSS Dashboards | VTemip | Manoj Nibrad
360 | NOC360 | All Domain | OSS | Inventory Dashboard and Report(Domain wise Filter) Daily | Critical | OSS Dashboards | UTM | Manoj Nibrad
361 | NOC361 | All Domain | OSS | Inventory Dashboard and Report(Domain wise Filter) Weekly | Critical | OSS Dashboards | UTM | Manoj Nibrad
362 | NOC362 | All Domain | OSS | Inventory Dashboard and Report(Domain wise Filter) Monthly | Critical | OSS Dashboards | UTM | Manoj Nibrad
363 | NOC363 | All Domain | OSS | Inventory Dashboard and Report(Domain wise Filter) (Selective from and to dates) | Critical | OSS Dashboards | UTM | Manoj Nibrad
364 | NOC364 | All Domain | OSS | Correlation within Domain and cross domain Daily | Critical | OSS Dashboards | UCA | Manoj Nibrad
365 | NOC365 | All Domain | OSS | Correlation within Domain and cross domain Weekly | Critical | OSS Dashboards | UCA | Manoj Nibrad
366 | NOC366 | All Domain | OSS | Correlation within Domain and cross domain Monthly | Critical | OSS Dashboards | UCA | Manoj Nibrad
367 | NOC367 | All Domain | OSS | Correlation within Domain and cross domain (Selective from and to dates) | Critical | OSS Dashboards | UCA | Manoj Nibrad
368 | NOC368 | DC IT Active Infra | OSS | Service Monitoring of All DC Elements(DC WAN, Leaf, Spine and Service riding on these Network and Servers) Daily | Critical | HPSM | Incident Management | Manoj Nibrad
369 | NOC369 | DC IT Active Infra | OSS | Service Monitoring of All DC Elements(DC WAN, Leaf, Spine and Service riding on these Network and Servers) Weekly | Critical | HPSM | Incident Management | Manoj Nibrad
370 | NOC370 | DC IT Active Infra | OSS | Service Monitoring of All DC Elements(DC WAN, Leaf, Spine and Service riding on these Network and Servers) Monthly | Critical | HPSM | Incident Management | Manoj Nibrad
371 | NOC371 | DC IT Active Infra | OSS | Service Monitoring of All DC Elements(DC WAN, Leaf, Spine and Service riding on these Network and Servers) (Selective from and to dates) | Critical | HPSM | Incident Management | Manoj Nibrad
372 | NOC372 | All Domain | OSS | Interface Utilisation(>80%) Hourly | Critical | NNMI | NPS | Manoj Nibrad
373 | NOC373 | All Domain | OSS | Interface Utilisation(>80%) Daily | Critical | NNMI | NPS | Manoj Nibrad
374 | NOC374 | All Domain | OSS | Interface Utilisation(>80%) Weekly | Critical | NNMI | NPS | Manoj Nibrad
375 | NOC375 | All Domain | OSS | Interface Utilisation(>80%) Monthly | Critical | NNMI | NPS | Manoj Nibrad
376 | NOC376 | All Domain | OSS | Interface Utilisation(% of Utilisation configurable) | Critical | NNMI | NPS | Manoj Nibrad
377 | NOC377 | All Domain | OSS | Interface Utilisation(Polling Duration configurable) | Critical | NNMI | NPS | Manoj Nibrad
378 | NOC378 | All Domain | OSS | Interface Utilisation(>80%) (Selective from and to dates) | Critical | NNMI | NPS | Manoj Nibrad
379 | NOC379 | All Domain | OSS | CPU/RAM(>80%) Daily | Critical | NNMI | NPS | Manoj Nibrad
380 | NOC380 | All Domain | OSS | CPU/RAM(>80%) Weekly | Critical | NNMI | NPS | Manoj Nibrad
381 | NOC381 | All Domain | OSS | CPU/RAM(>80%) Monthly | Critical | NNMI | NPS | Manoj Nibrad
382 | NOC382 | All Domain | OSS | CPU/RAM(% of Utilisation configurable) | Critical | NNMI | NPS | Manoj Nibrad
383 | NOC383 | All Domain | OSS | CPU/RAM(Polling Duration configurable) | Critical | NNMI | NPS | Manoj Nibrad
384 | NOC384 | All Domain | OSS | CPU/RAM(>80%) (Selective from and to dates) | Critical | NNMI | NPS | Manoj Nibrad
385 | NOC385 | All Domain | OSS | Incident/Alarm Notifciation via SMS, E-mail and Call, Whatsapp as per escalation Matrix (Selective from and to dates) | Critical | HPSM | Incident Management | Manoj Nibrad
386 | NOC386 | All Domain | OSS | Node(POP) wise Availability Daily | Critical | HPSM | Incident Management | Manoj Nibrad
387 | NOC387 | All Domain | OSS | Node(POP) wise Availability Weekly | Critical | HPSM | Incident Management | Manoj Nibrad
388 | NOC388 | All Domain | OSS | Node(POP) wise Availability Monthly | Critical | HPSM | Incident Management | Manoj Nibrad
389 | NOC389 | All Domain | OSS | Node(POP) wise Availability (Selective from and to dates) | Critical | HPSM | Incident Management | Manoj Nibrad
390 | NOC390 | All Domain | OSS | Equipment wise Availability Daily | Critical | HPSM | Incident Management | Manoj Nibrad
391 | NOC391 | All Domain | OSS | Equipment wise Availability Weekly | Critical | HPSM | Incident Management | Manoj Nibrad
392 | NOC392 | All Domain | OSS | Equipment wise Availability Monthly | Critical | HPSM | Incident Management | Manoj Nibrad
393 | NOC393 | All Domain | OSS | Equipment wise Availability (Selective from and to dates) | Critical | HPSM | Incident Management | Manoj Nibrad
394 | NOC394 | All Domain | OSS | Link wise Uptime Daily | Critical | HPSM | Incident Management | Manoj Nibrad
395 | NOC395 | All Domain | OSS | Link wise Uptime Weekly | Critical | HPSM | Incident Management | Manoj Nibrad
396 | NOC396 | All Domain | OSS | Link wise Uptime Monthly | Critical | HPSM | Incident Management | Manoj Nibrad
397 | NOC397 | All Domain | OSS | Link wise Uptime (Selective from and to dates) | Critical | HPSM | Incident Management | Manoj Nibrad
398 | NOC398 | All Domain | OSS | Link wise MTTR Daily | Critical | HPSM | Incident Management | Manoj Nibrad
399 | NOC399 | All Domain | OSS | Link wise MTTR Weekly | Critical | HPSM | Incident Management | Manoj Nibrad
400 | NOC400 | All Domain | OSS | Link wise MTTR Monthly | Critical | HPSM | Incident Management | Manoj Nibrad
401 | NOC401 | All Domain | OSS | Link wise MTTR (Selective from and to dates) | Critical | HPSM | Incident Management | Manoj Nibrad
402 | NOC402 | DC and Field IPMPLS | OSS | IPSLA Daily(Packet Drops, Latency, Jitter, ect..) | Critical | NNMI | NPS | Manoj Nibrad
403 | NOC403 | DC and Field IPMPLS | OSS | IPSLA Weekly(Packet drops, latency, jitter, etc..) | Critical | NNMI | NPS | Manoj Nibrad
404 | NOC404 | DC and Field IPMPLS | OSS | IPSLA Monthly (Packet drops, latency, jitter, etc..) | Critical | NNMI | NPS | Manoj Nibrad
405 | NOC405 | DC and Field IPMPLS | OSS | IPSLA (Selective from and to dates)(Packet drops, latency, jitter, etc..) | Critical | NNMI | NPS | Manoj Nibrad
406 | NOC406 | DC and Field IPMPLS | OSS | IPSLA (Packet drops to be configurable and existing >1% to be reported in Dashboard | Critical | NNMI | NPS | Manoj Nibrad
407 | NOC407 | DC and Field IPMPLS | OSS | IPSLA (Latency to be configurable and existing >10ms to be reported in Dashboard | Critical | NNMI | NPS | Manoj Nibrad
408 | NOC408 | DC and Field IPMPLS | OSS | IPSLA (Jitter to be configurable and existing >30ms to be reported in Dashboard | Critical | NNMI | NPS | Manoj Nibrad
409 | NOC409 | DC and Field IPMPLS | OSS | Traffic Utilisation covering All QoS Partameters Daily | Critical | NNMI | NPS | Manoj Nibrad
410 | NOC410 | DC and Field IPMPLS | OSS | Traffic Utilisation covering All QoS Partameters Weekly | Critical | NNMI | NPS | Manoj Nibrad
411 | NOC411 | DC and Field IPMPLS | OSS | Traffic Utilisation covering All QoS Partameters Monthly | Critical | NNMI | NPS | Manoj Nibrad
412 | NOC412 | DC and Field IPMPLS | OSS | Traffic Utilisation covering All QoS Partameters (Selective from and to dates) | Critical | NNMI | NPS | Manoj Nibrad
413 | NOC413 | BBNL Reports | OSS | Block and GP Status Daily | Critical | HPSM | Incident Management | Manoj Nibrad
414 | NOC414 | BBNL Reports | OSS | Block and GP Status Weekly | Critical | HPSM | Incident Management | Manoj Nibrad
415 | NOC415 | BBNL Reports | OSS | Block and GP Status Monthly | Critical | HPSM | Incident Management | Manoj Nibrad
416 | NOC416 | BBNL Reports | OSS | Block and GP Status (Selective from and to dates) | Critical | HPSM | Incident Management | Manoj Nibrad
417 | NOC417 | BBNL Reports | OSS | Block and GP Availability Daily | Critical | HPSM | Incident Management | Manoj Nibrad
418 | NOC418 | BBNL Reports | OSS | Block and GP Availability Weekly | Critical | HPSM | Incident Management | Manoj Nibrad
419 | NOC419 | BBNL Reports | OSS | Block and GP Availability Monthly | Critical | HPSM | Incident Management | Manoj Nibrad
420 | NOC420 | BBNL Reports | OSS | Block and GP Availability (Selective from and to dates) | Critical | HPSM | Incident Management | Manoj Nibrad
421 | NOC421 | BBNL Reports | BSS | FTTH Connections and their utilisation(Including Household) Daily | Critical | BSS | CRM | Manoj Nibrad
422 | NOC422 | BBNL Reports | BSS | FTTH Connections and their utilisation(Including Household) Weekly | Critical | BSS | CRM | Manoj Nibrad
423 | NOC423 | BBNL Reports | BSS | FTTH Connections and their utilisation(Including Household) Monthly | Critical | BSS | CRM | Manoj Nibrad
424 | NOC424 | BBNL Reports | BSS | FTTH Connections and their utilisation(Including Household) (Selective from and to dates) | Critical | BSS | CRM | Manoj Nibrad
425 | NOC425 | Regulatory | BSS | Customer connections Daily | Critical | BSS | CRM | Manoj Nibrad
426 | NOC426 | Regulatory | BSS | Customer connections Weekly | Critical | BSS | CRM | Manoj Nibrad
427 | NOC427 | Regulatory | BSS | Customer connections Monthly | Critical | BSS | CRM | Manoj Nibrad
428 | NOC428 | Regulatory | BSS | Customer connections (Selective from and to dates) | Critical | BSS | CRM | Manoj Nibrad
429 | NOC429 | Regulatory | BSS | Billing Daily | Critical | BSS | Billing | Manoj Nibrad
430 | NOC430 | Regulatory | BSS | Billing Weekly | Critical | BSS | Billing | Manoj Nibrad
431 | NOC431 | Regulatory | BSS | Billing Monthly | Critical | BSS | Billing | Manoj Nibrad
432 | NOC432 | Regulatory | BSS | Billing (Selective from and to dates) | Critical | BSS | Billing | Manoj Nibrad
433 | NOC433 | Regulatory | BSS | Waiver Daily | Critical | BSS | Billing | Manoj Nibrad
434 | NOC434 | Regulatory | BSS | Waiver Weekly | Critical | BSS | Billing | Manoj Nibrad
435 | NOC435 | Regulatory | BSS | Waiver Monthly | Critical | BSS | Billing | Manoj Nibrad
436 | NOC436 | Regulatory | BSS | Waiver (Selective from and to dates) | Critical | BSS | Billing | Manoj Nibrad
437 | NOC437 | Regulatory | IPDR | Customer data logs(Session with MAC) Daily | Critical | IPDR | IPDR | Manoj Nibrad
438 | NOC438 | Regulatory | IPDR | Customer data logs(Session with MAC) Weekly | Critical | IPDR | IPDR | Manoj Nibrad
439 | NOC439 | Regulatory | IPDR | Customer data logs(Session with MAC) Monthly | Critical | IPDR | IPDR | Manoj Nibrad
440 | NOC440 | Regulatory | IPDR | Customer data logs(Session with MAC) (Selective from and to dates) | Critical | IPDR | IPDR | Manoj Nibrad
441 | NOC441 | Regulatory | BSS | Service Delivery TAT Dashboard and Reporting Daily | Critical | BSS | CRM | Manoj Nibrad
442 | NOC442 | Regulatory | BSS | Service Delivery TAT Dashboard and Reporting Weekly | Critical | BSS | CRM | Manoj Nibrad
443 | NOC443 | Regulatory | BSS | Service Delivery TAT Dashboard and Reporting Monthly | Critical | BSS | CRM | Manoj Nibrad
444 | NOC444 | Regulatory | BSS | Service Delivery TAT Dashboard and Reporting (Selective from and to dates) | Critical | BSS | CRM | Manoj Nibrad
445 | NOC445 | Service Monitoring | OSS | VLAN | Critical | HPSM | Service Inventory | Manoj Nibrad
446 | NOC446 | Service Monitoring | OSS | ONT Downlink Port(Service segregation 4- UPS, 1-4 for Services) | Critical | HPSM | Service Inventory | Manoj Nibrad
447 | NOC447 | Service Monitoring | OSS | Service ID Mapping for UPS and Customer services | Critical | HPSM | Service Inventory | Manoj Nibrad
448 | NOC448 | Service Provisioning | NSO | Service Provision using NSO Daily | Critical | NSO | SCCM | Jayant Madavi
449 | NOC449 | Service Provisioning | NSO | Service template configuration | Critical | NSO | SCCM | Jayant Madavi
450 | NOC450 | Service Provisioning | BSS | ILL(G2G) Daily | Critical | BSS | CRM | Manoj Nibrad
451 | NOC451 | Service Provisioning | BSS | ILL(G2G) with QoS Daily | Critical | BSS | CRM | Manoj Nibrad
452 | NOC452 | Service Provisioning | BSS | ILL(G2G) with QoS Weekly | Critical | BSS | CRM | Manoj Nibrad
453 | NOC453 | Service Provisioning | BSS | ILL(G2G) with QoS Monthly | Critical | BSS | CRM | Manoj Nibrad
454 | NOC454 | Service Provisioning | BSS | ILL(G2G) with QoS (Selective from and to dates) | Critical | BSS | CRM | Manoj Nibrad
455 | NOC455 | Service Provisioning | BSS | GI BB(G2G) Direct Bandwidth Daily | Critical | BSS | CRM | Manoj Nibrad
456 | NOC456 | Service Provisioning | BSS | GI BB(G2G) Direct Bandwidth Weekly | Critical | BSS | CRM | Manoj Nibrad
457 | NOC457 | Service Provisioning | BSS | GI BB(G2G) Direct Bandwidth Monthly | Critical | BSS | CRM | Manoj Nibrad
458 | NOC458 | Service Provisioning | BSS | GI BB(G2G) Direct Bandwidth (Selective from and to dates) | Critical | BSS | CRM | Manoj Nibrad
459 | NOC459 | Service Provisioning | BSS | GI BB(G2G) Bandidth with QoS filtered Daily | Critical | BSS | CRM | Manoj Nibrad
460 | NOC460 | Service Provisioning | BSS | GI BB(G2G) Bandidth with QoS filtered Weekly | Critical | BSS | CRM | Manoj Nibrad
461 | NOC461 | Service Provisioning | BSS | GI BB(G2G) Bandidth with QoS filtered Monthly | Critical | BSS | CRM | Manoj Nibrad
462 | NOC462 | Service Provisioning | BSS | GI BB(G2G) Bandidth with QoS filtered (Selective from and to dates) | Critical | BSS | CRM | Manoj Nibrad
463 | NOC463 | Service Provisioning | BSS | Dark Fiber Daily | Critical | BSS | CRM | Manoj Nibrad
464 | NOC464 | Service Provisioning | BSS | Dark Fiber Weekly | Critical | BSS | CRM | Manoj Nibrad
465 | NOC465 | Service Provisioning | BSS | Dark Fiber Monthly | Critical | BSS | CRM | Manoj Nibrad
466 | NOC466 | Service Provisioning | BSS | Dark Fiber (Selective from and to dates) | Critical | BSS | CRM | Manoj Nibrad
467 | NOC467 | Service Provisioning | BSS | Household(G2C) Daily | Critical | BSS | CRM | Manoj Nibrad
468 | NOC468 | Service Provisioning | BSS | Household(G2C) Weekly | Critical | BSS | CRM | Manoj Nibrad
469 | NOC469 | Service Provisioning | BSS | Household(G2C) Monthly | Critical | BSS | CRM | Manoj Nibrad
470 | NOC470 | Service Provisioning | BSS | Household(G2C) (Selective from and to dates) | Critical | BSS | CRM | Manoj Nibrad
471 | NOC471 | Service Provisioning | BSS | VPN(B2B) Daily | Critical | BSS | CRM | Manoj Nibrad
472 | NOC472 | Service Provisioning | BSS | VPN(B2B) Weekly | Critical | BSS | CRM | Manoj Nibrad
473 | NOC473 | Service Provisioning | BSS | VPN(B2B) Monthly | Critical | BSS | CRM | Manoj Nibrad
474 | NOC474 | Service Provisioning | BSS | VPN(B2B) (Selective from and to dates) | Critical | BSS | CRM | Manoj Nibrad
475 | NOC475 | Service Provisioning | BSS | VPN(B2B)with filtered QoS Daily | Critical | BSS | CRM | Manoj Nibrad
476 | NOC476 | Service Provisioning | BSS | VPN(B2B)with filtered QoS Weekly | Critical | BSS | CRM | Manoj Nibrad
477 | NOC477 | Service Provisioning | BSS | VPN(B2B)with filtered QoS Monthly | Critical | BSS | CRM | Manoj Nibrad
478 | NOC478 | Service Provisioning | BSS | VPN(B2B)with filtered QoS (Selective from and to dates) | Critical | BSS | CRM | Manoj Nibrad
479 | NOC479 | Service Provisioning | BSS | Enterprise(B2B) Daily | Critical | BSS | CRM | Manoj Nibrad
480 | NOC480 | Service Provisioning | BSS | Enterprise(B2B) Weekly | Critical | BSS | CRM | Manoj Nibrad
481 | NOC481 | Service Provisioning | BSS | Enterprise(B2B) Monthly | Critical | BSS | CRM | Manoj Nibrad
482 | NOC482 | Service Provisioning | BSS | Enterprise(B2B) (Selective from and to dates) | Critical | BSS | CRM | Manoj Nibrad
483 | NOC483 | Service Provisioning | BSS | Enterprise(B2B) with filtered QoS Daily | Critical | BSS | CRM | Manoj Nibrad
484 | NOC484 | Service Provisioning | BSS | Enterprise(B2B) with filtered QoS Weekly | Critical | BSS | CRM | Manoj Nibrad
485 | NOC485 | Service Provisioning | BSS | Enterprise(B2B) with filtered QoS Monthly | Critical | BSS | CRM | Manoj Nibrad
486 | NOC486 | Service Provisioning | BSS | Enterprise(B2B) with filtered QoS (Selective from and to dates) | Critical | BSS | CRM | Manoj Nibrad
487 | NOC487 | Service Provisioning | BSS | Partner(B2B2C) Daily | Critical | BSS | CRM | Manoj Nibrad
488 | NOC488 | Service Provisioning | BSS | Partner(B2B2C) Weekly | Critical | BSS | CRM | Manoj Nibrad
489 | NOC489 | Service Provisioning | BSS | Partner(B2B2C) Monthly | Critical | BSS | CRM | Manoj Nibrad
490 | NOC490 | Service Provisioning | BSS | Partner(B2B2C) (Selective from and to dates) | Critical | BSS | CRM | Manoj Nibrad
491 | NOC491 | Service Provisioning | BSS | Partner(B2B2C) with Filtered QoS Daily | Critical | BSS | CRM | Manoj Nibrad
492 | NOC492 | Service Provisioning | BSS | Partner(B2B2C) with Filtered QoS Weekly | Critical | BSS | CRM | Manoj Nibrad
493 | NOC493 | Service Provisioning | BSS | Partner(B2B2C) with Filtered QoS Monthly | Critical | BSS | CRM | Manoj Nibrad
494 | NOC494 | Service Provisioning | BSS | Partner(B2B2C) with Filtered QoS (Selective from and to dates) | Critical | BSS | CRM | Manoj Nibrad
495 | NOC495 | Service Provisioning | BSS | T-cell (P2MP) Daily | Critical | BSS | CRM | Manoj Nibrad
496 | NOC496 | Service Provisioning | BSS | T-cell (P2MP) Weekly | Critical | BSS | CRM | Manoj Nibrad
497 | NOC497 | Service Provisioning | BSS | T-cell (P2MP) Monthly | Critical | BSS | CRM | Manoj Nibrad
498 | NOC498 | Service Provisioning | BSS | T-cell (P2MP) (Selective from and to dates) | Critical | BSS | CRM | Manoj Nibrad
499 | NOC499 | Service Provisioning | BSS | T-cell P2MP with Filtered QoS Daily | Critical | BSS | CRM | Manoj Nibrad
500 | NOC500 | Service Provisioning | BSS | T-cell P2MP with Filtered QoS Weekly | Critical | BSS | CRM | Manoj Nibrad
501 | NOC501 | Service Provisioning | BSS | T-cell P2MP with Filtered QoS Monthly | Critical | BSS | CRM | Manoj Nibrad
502 | NOC502 | Service Provisioning | BSS | T-cell P2MP with Filtered QoS (Selective from and to dates) | Critical | BSS | CRM | Manoj Nibrad
503 | NOC503 | Service Provisioning | BSS | T-cell (P2P) Daily | Critical | BSS | CRM | Manoj Nibrad
504 | NOC504 | Service Provisioning | BSS | T-cell (P2P) Weekly | Critical | BSS | CRM | Manoj Nibrad
505 | NOC505 | Service Provisioning | BSS | T-cell (P2P) Monthly | Critical | BSS | CRM | Manoj Nibrad
506 | NOC506 | Service Provisioning | BSS | T-cell (P2P) (Selective from and to dates) | Critical | BSS | CRM | Manoj Nibrad
507 | NOC507 | Service Provisioning | BSS | T-cell P2P with Filtered QoS Daily | Critical | BSS | CRM | Manoj Nibrad
508 | NOC508 | Service Provisioning | BSS | T-cell P2P with Filtered QoS Weekly | Critical | BSS | CRM | Manoj Nibrad
509 | NOC509 | Service Provisioning | BSS | T-cell P2P with Filtered QoS Monthly | Critical | BSS | CRM | Manoj Nibrad
510 | NOC510 | Service Provisioning | BSS | T-cell P2P with Filtered QoS (Selective from and to dates) | Critical | BSS | CRM | Manoj Nibrad
511 | NOC511 | Service Provisioning | OSS and NSO | Bandwidth Feasibility for New Provisioning, Exising configured bandwidth to be made available at OSS Daily | Critical | OSS and NSO | Service Inventory, SCCM | Manoj Nibrad
512 | NOC512 | Service Provisioning | OSS and NSO | Bandwidth Feasibility for New Provisioning, Exising configured bandwidth to be made available at OSS Weekly | Critical | OSS and NSO | Service Inventory, SCCM | Manoj Nibrad
513 | NOC513 | Service Provisioning | OSS and NSO | Bandwidth Feasibility for New Provisioning, Exising configured bandwidth to be made available at OSS Monthly | Critical | OSS and NSO | Service Inventory, SCCM | Manoj Nibrad
514 | NOC514 | Service Provisioning | OSS and NSO | Bandwidth Feasibility for New Provisioning, Exising configured bandwidth to be made available at OSS (Selective from and to dates) | Critical | OSS and NSO | Service Inventory, SCCM | Manoj Nibrad
515 | NOC515 | Service Provisioning | OSS | Capacity augmentationn based on Feasible/NON- Feasible status count and required bandwidth Daily | Critical | OSS | Service Inventory, UTM | Manoj Nibrad
516 | NOC516 | Service Provisioning | OSS | Capacity augmentationn based on Feasible/NON- Feasible status count and required bandwidth Weekly | Critical | OSS | Service Inventory, UTM | Manoj Nibrad
517 | NOC517 | Service Provisioning | OSS | Capacity augmentationn based on Feasible/NON- Feasible status count and required bandwidth Monthly | Critical | OSS | Service Inventory, UTM | Manoj Nibrad
518 | NOC518 | Service Provisioning | OSS | Capacity augmentationn based on Feasible/NON- Feasible status count and required bandwidth (Selective from and to dates) | Critical | OSS | Service Inventory, UTM | Manoj Nibrad
519 | NOC519 | WFM | WFM | User level view for Number of tasks assigned/resolved/closed Daily | Critical | WFM | Corrective | Kaushal
520 | NOC520 | WFM | WFM | User level view for Number of tasks assigned/resolved/closed Weekly | Critical | WFM | Incident Management | Kaushal
521 | NOC521 | WFM | WFM | User level view for Number of tasks assigned/resolved/closed Monthly | Critical | WFM | Incident Management | Kaushal
522 | NOC522 | WFM | WFM | User level view for Number of tasks assigned/resolved/closed (Selective from and to dates) | Critical | WFM | Smart track | Kaushal
523 | NOC523 | WFM | WFM | Management Dashboard Patroller Daily | Critical | WFM | Smart track | Kaushal
524 | NOC524 | WFM | WFM | Management Dashboard Patroller Weekly | Critical | WFM | Smart track | Kaushal
525 | NOC525 | WFM | WFM | Management Dashboard Patroller Monthly | Critical | WFM | Smart track | Kaushal
526 | NOC526 | WFM | WFM | Management Dashboard Patroller (Selective from and to dates) | Critical | WFM | Smart track | Kaushal
527 | NOC527 | WFM | WFM | Management Dashboard FRT Daily | Critical | WFM | Smart track | Kaushal
528 | NOC528 | WFM | WFM | Management Dashboard FRT Weekly | Critical | WFM | Smart track | Kaushal
529 | NOC529 | WFM | WFM | Management Dashboard FRT Monthly | Critical | WFM | Smart track | Kaushal
530 | NOC530 | WFM | WFM | Management Dashboard FRT (Selective from and to dates) | Critical | WFM | Smart track | Kaushal
531 | NOC531 | WFM | WFM | Management Dashboard Engineers Daily | Critical | WFM | Smart track | Kaushal
532 | NOC532 | WFM | WFM | Management Dashboard Engineers Weekly | Critical | WFM | Smart track | Kaushal
533 | NOC533 | WFM | WFM | Management Dashboard Engineers Monthly | Critical | WFM | Smart track | Kaushal
534 | NOC534 | WFM | WFM | Management Dashboard Engineers (Selective from and to dates) | Critical | WFM | Smart track | Kaushal
535 | NOC535 | Help Desk | BSS | Integration to be Aligned with Approved IVR flow(All Customers) Daily | NON-Critical | BSS | CRM | Sivakumar S | IVR Flows Submitted for Approval | Completed
536 | NOC536 | Help Desk | BSS | Integration to be Aligned with Approved IVR flow(All Customers) Weekly | NON-Critical | BSS | CRM | Sivakumar S | IVR Flows Submitted for Approval | Completed
537 | NOC537 | Help Desk | BSS | Integration to be Aligned with Approved IVR flow(All Customers) Monthly | NON-Critical | BSS | CRM | Sivakumar S | IVR Flows Submitted for Approval | Completed
538 | NOC538 | Help Desk | BSS | Integration to be Aligned with Approved IVR flow(All Customers) (Selective from and to dates) | NON-Critical | BSS | CRM | Sivakumar S | IVR Flows Submitted for Approval | Completed
539 | NOC539 | Help Desk | BSS | Integration to be Aligned with Approved IVR flow(All Enterprise) Daily | NON-Critical | BSS | CRM | Sivakumar S | IVR Flows Submitted for Approval | Completed
540 | NOC540 | Help Desk | BSS | Integration to be Aligned with Approved IVR flow(All Enterprise) Weekly | NON-Critical | BSS | CRM | Sivakumar S | IVR Flows Submitted for Approval | Completed
541 | NOC541 | Help Desk | BSS | Integration to be Aligned with Approved IVR flow(All Enterprise) Monthly | NON-Critical | BSS | CRM | Sivakumar S | IVR Flows Submitted for Approval | Completed
542 | NOC542 | Help Desk | BSS | Integration to be Aligned with Approved IVR flow(All Enterprise) (Selective from and to dates) | NON-Critical | BSS | CRM | Sivakumar S | IVR Flows Submitted for Approval | Completed
543 | NOC543 | Help Desk | BSS | Integration to be Aligned with Approved IVR flow(All Partners) Daily | NON-Critical | BSS | CRM | Sivakumar S | IVR Flows Submitted for Approval | Completed
544 | NOC544 | Help Desk | BSS | Integration to be Aligned with Approved IVR flow(All Partners) Weekly | NON-Critical | BSS | CRM | Sivakumar S | IVR Flows Submitted for Approval | Completed
545 | NOC545 | Help Desk | BSS | Integration to be Aligned with Approved IVR flow(All Partners) Monthly | NON-Critical | BSS | CRM | Sivakumar S | IVR Flows Submitted for Approval | Completed
546 | NOC546 | Help Desk | BSS | Integration to be Aligned with Approved IVR flow(All Partners) (Selective from and to dates) | NON-Critical | BSS | CRM | Sivakumar S | IVR Flows Submitted for Approval | Completed
547 | NOC547 | Help Desk | OSS | Integration to be Aligned with Approved IVR flow(MSI) Daily | NON-Critical | HPSM | Incident Management | Sivakumar S | IVR Flows Submitted for Approval | Completed
548 | NOC548 | Help Desk | OSS | Integration to be Aligned with Approved IVR flow(MSI) Weekly | NON-Critical | HPSM | Incident Management | Sivakumar S | IVR Flows Submitted for Approval | Completed
549 | NOC549 | Help Desk | OSS | Integration to be Aligned with Approved IVR flow(MSI) Monthly | NON-Critical | HPSM | Incident Management | Sivakumar S | IVR Flows Submitted for Approval | Completed
550 | NOC550 | Help Desk | OSS | Integration to be Aligned with Approved IVR flow(MSI) (Selective from and to dates) | NON-Critical | HPSM | Incident Management | Sivakumar S | IVR Flows Submitted for Approval | Completed
551 | NOC551 | Help Desk | OSS | Integration to be Aligned with Approved IVR flow(NOC) Daily | NON-Critical | HPSM | Incident Management | Sivakumar S | IVR Flows Submitted for Approval | Completed
552 | NOC552 | Help Desk | OSS | Integration to be Aligned with Approved IVR flow(NOC) Weekly | NON-Critical | HPSM | Incident Management | Sivakumar S | IVR Flows Submitted for Approval | Completed
553 | NOC553 | Help Desk | OSS | Integration to be Aligned with Approved IVR flow(NOC) Monthly | NON-Critical | HPSM | Incident Management | Sivakumar S | IVR Flows Submitted for Approval | Completed
554 | NOC554 | Help Desk | OSS | Integration to be Aligned with Approved IVR flow(NOC) (Selective from and to dates) | NON-Critical | HPSM | Incident Management | Sivakumar S | IVR Flows Submitted for Approval | Completed
555 | NOC555 | Service Provisioning | NSO | VLAN Planning | Critical | NSO | SCCM/Playbook | Jayant Madavi
556 | NOC556 | Service Provisioning | NSO | IPV4 and IPV6 Planning | Critical | NSO | SCCM/Playbook | Jayant Madavi
557 | NOC557 | Service Provisioning | BSS, NSO | Migration of Existing customers provision via BSS-NSO | Critical | BSS, NSO | CRM, SCCM | Manoj Nibrad
558 | NOC558 | All Domain | OSS | TT should not be generated for planned event window and Affected CI | Critical | HPSM | Change Management | Manoj Nibrad
559 | NOC559 | All Domain | OSS | Planned event to be rejected/Postponed incase another side Ring is open | Critical | HPSM | Change Management | Manoj Nibrad
560 | NOC560 | WFM | WFM | Field Remarks like ETR, RFO updation pending against Open Task | Critical | WFM | Smart track | Kaushal
561 | NOC561 | WFM | WFM | Field team working without events and as a part of corrective actions at Passive | Critical | WFM | Smart track | Kaushal
562 | NOC562 | WFM | OSS | Auto Escalation Matrix | Critical | HPSM | Incident Management | Kaushal
563 | NOC563 | All Domain | OSS | Configutable paramters for SLA | Critical | NNMI | NPS | Manoj Nibrad
564 | NOC564 | GPON | GPON | Requested Tejas to enable the TR-069 for T-Fiber deployed elements | Critical | Tejas OEM | EMS | Sayyad Pasha | MoM point Not in RFP and L&T confirmed this is not in scope Update awaited from Tejas on confirmation of the shared parameters | Dependency on OEM
565 | NOC565 | GPON | GPON | CIR/PIR in OLT/EMS | Critical | Tejas OEM | EMS | Sayyad Pasha | As per the joint discussion with TFIber and Tejas, Tejas confirmed that they will provide a solution post testing internally. Update awaited from OEM | Dependency on OEM
566 | NOC566 | GPON | GPON | Unable to modify the Service Name | Critical | Tejas OEM | EMS | Sayyad Pasha |  | Closed
567 | NOC567 | GPON | GPON | Live PM monitoring per UNI in EMS service Window | Critical | Tejas OEM | EMS | Sayyad Pasha |  | Closed
568 | NOC568 | GPON | GPON | Unable to Enable PM from EMS | Critical | Tejas OEM | EMS | Sayyad Pasha |  | Closed
569 | NOC569 | GPON | GPON | While creating service profile, maximum bandwidth is not taking 1024000 only considering 1000000 | Critical | Tejas OEM | EMS | Sayyad Pasha |  | Closed
570 | NOC570 | GPON | GPON | OLT Node not reachable alarm clearance and regeneration | Critical | Tejas OEM | EMS | Sayyad Pasha |  | Closed
571 | NOC571 | GPON | GPON | while adding uni in EMS, list of downstream profiles are highlighting in the bottom | Critical | Tejas OEM | EMS | Sayyad Pasha |  | Closed
572 | NOC572 | GPON | GPON | Nokia ONT ethernet port status is not updating | Critical | Tejas OEM | EMS | Sayyad Pasha |  | Dependency on OEM
573 | NOC573 | GPON | GPON | Tejas ONT Software Upgrade which are connected under Nokia OLT | Critical | Tejas OEM | EMS | Sayyad Pasha |  | Closed
574 | NOC574 | GPON | GPON | API for GI-BB Service, combo port, mixed service - Route Mode with/without translation, including uplink port configuration | Critical | Tejas OEM | EMS | Sayyad Pasha |  | Closed
575 | NOC575 | GPON | GPON | API for TDIA Service, combo port, mixed service - Route Mode with/without translation, including uplink port configuration | Critical | Tejas OEM | EMS | Sayyad Pasha |  | Closed
576 | NOC576 | GPON | GPON | API to restirct/block the PON port to a specific customer | Critical | Tejas OEM | EMS | Sayyad Pasha |  | Closed
577 | NOC577 | GPON | GPON | API to modify the service- ONT, UNI Port, bandwidth, vlan, description, unatgged to tag or vice versa., | Critical | Tejas OEM | EMS | Sayyad Pasha |  | Open
578 | NOC578 | GPON | GPON | PIR not working in route mode | Critical | Tejas OEM | EMS | Sayyad Pasha | Duplicate of point-565 | Dependency on OEM
579 | NOC579 | GPON | GPON | Nokia ONT/3rd party ONT under Tejas OLT Remote access for WAN port | Critical | Tejas OEM | EMS | Sayyad Pasha | OEM confirmed this feature is not available | Dependency on OEM
580 | NOC580 | GPON | GPON | Unable to browse Internet when IPV6 configured in wifi ONT | Critical | Nokia OEM | AMS | Sayyad Pasha |  | Closed
581 | NOC581 | GPON | GPON | Hybrid Mode of the G-240G-E ONT | Critical | Nokia OEM | AMS | Sayyad Pasha | Nokia has provided the SOP, which has been tested and is working as expected. However, Nokia ONTs connected to Tejas OLTs cannot be enabled directly through the Tejas OLT. As discussed with TFiber, we have prepared an SOP for the field team and are currently working on mapping the Nokia ONTs under Tejas OLTs to nearby Nokia OLTs | Open
582 | NOC582 | GPON | GPON | Nokia ONT under Nokia OLT Remote access for WAN port | Critical | Nokia OEM | AMS | Sayyad Pasha | OEM confirmed this feature is not available | Dependency on OEM
583 | NOC583 | GPON | GPON | Tejas ONT/3rd party ONT under Nokia OLT Remote access for WAN port | Critical | Nokia OEM | AMS | Sayyad Pasha | OEM confirmed this feature is not available | Dependency on OEM
584 | NOC584 | GPON | GPON | Nokia ONT under Tejas OLT Remote access for WAN port | Critical | Nokia OEM | AMS | Sayyad Pasha | OEM confirmed this feature is not available | Dependency on OEM
585 | NOC585 | GPON | GPON | ONT cosumed count is showing wrong in license page | Critical | Nokia OEM | AMS | Sayyad Pasha | For the resolution of this issue, required AMS upgrade. Nokia team will share the plan of action, post that will take necessary approvals from TFiber | Dependency on OEM
586 | NOC586 | GPON | GPON | API and Template for ILL Service - Bridge Mode, including uplink port configuration | Critical | Nokia OEM | AMS | Sayyad Pasha | OEM confirmed API is not availble for uplink configuration | Dependency on OEM
587 | NOC587 | GPON | GPON | API and Template for ILL Service - Route Mode, including uplink port configuration | Critical | Nokia OEM | AMS | Sayyad Pasha | OEM confirmed API is not availble for uplink configuration | Dependency on OEM
588 | NOC588 | GPON | GPON | API and Template for Household Services, including uplink port configuration | Critical | Nokia OEM | AMS | Sayyad Pasha | OEM confirmed API is not availble for uplink configuration | Dependency on OEM
589 | NOC589 | GPON | GPON | API and Template for IPTV services, including uplink port configuration | Critical | Nokia OEM | AMS | Sayyad Pasha | OEM confirmed API is not availble for uplink configuration | Dependency on OEM
590 | NOC590 | GPON | GPON | API, Template and configuration for VOIP services, including uplink port configuration | Critical | Nokia OEM | AMS | Sayyad Pasha | OEM confirmed API is not availble for uplink configuration | Dependency on OEM
591 | NOC591 | GPON | GPON | API and Template for GI-BB Service - Bridge Mode, including uplink port configuration | Critical | Nokia OEM | AMS | Sayyad Pasha | OEM confirmed API is not availble for uplink configuration | Dependency on OEM
592 | NOC592 | GPON | GPON | API and Template for GI-BB Service - Route Mode, including uplink port configuration | Critical | Nokia OEM | AMS | Sayyad Pasha | OEM confirmed API is not availble for uplink configuration | Dependency on OEM
593 | NOC593 | GPON | GPON | API to fetch the configured services in AMS, including uplink port configuration | Critical | Nokia OEM | AMS | Sayyad Pasha | OEM confirmed API is not availble for uplink configuration | Dependency on OEM
594 | NOC594 | GPON | GPON | Configuration, API and Template for applying QOS for the different types of services | Critical | Nokia OEM | AMS | Sayyad Pasha | OEM confirmed API is not availble for uplink configuration | Dependency on OEM
595 | NOC595 | GPON | GPON | API and Template required to provision ONT along with selecting specific UNI port in ONT | Critical | Nokia OEM | AMS | Sayyad Pasha | OEM confirmed API is not availble for uplink configuration | Dependency on OEM
596 | NOC596 | GPON | GPON | API and Template required to provision ONT with multiple services along with selecting specific UNI port in ONT | Critical | Nokia OEM | AMS | Sayyad Pasha | OEM confirmed API is not availble for uplink configuration | Dependency on OEM
597 | NOC597 | GPON | GPON | API and Template required to provision ONT with same service on all ports | Critical | Nokia OEM | AMS | Sayyad Pasha | OEM confirmed API is not availble for uplink configuration | Dependency on OEM
598 | NOC598 | GPON | GPON | API and Template to configure multiple vlans on single ONT UNI Port | Critical | Nokia OEM | AMS | Sayyad Pasha | OEM confirmed API is not availble for uplink configuration | Dependency on OEM
599 | NOC599 | GPON | GPON | Configuration, API and Template for extedning services to enterprise customers | Critical | Nokia OEM | AMS | Sayyad Pasha | OEM confirmed API is not availble for uplink configuration | Dependency on OEM
600 | NOC600 | GPON | GPON | API and Template to verify and enable the PM | Critical | Nokia OEM | AMS | Sayyad Pasha | OEM confirmed API is not availble for uplink configuration | Dependency on OEM
601 | NOC601 | GPON | GPON | API and Template to configure Vlan and Profiles in OLT | Critical | Nokia OEM | AMS | Sayyad Pasha | OEM confirmed API is not availble for uplink configuration | Dependency on OEM
602 | NOC602 | GPON | GPON | Required complete API and Template developer document | Critical | Nokia OEM | AMS | Sayyad Pasha | OEM shared the document for the deployed API and templates | Dependency on OEM
603 | NOC603 | GPON | GPON | API and Template to validate the profiles, vlans available in OLT,ONT | Critical | Nokia OEM | AMS | Sayyad Pasha | API has to share by OEM | Dependency on OEM
604 | NOC604 | GPON | GPON | API and Template to restirct/block the PON port to a specific customer | Critical | Nokia OEM | AMS | Sayyad Pasha | OEM confirmed API is not availble | Dependency on OEM
605 | NOC605 | GPON | GPON | API and Template to modify the service- ONT, UNI Port, bandwidth, vlan, description, unatgged to tag or vice versa., | Critical | Nokia OEM | AMS | Sayyad Pasha | API is available for the modification of bandwidth | Dependency on OEM
606 | NOC606 | GPON | GPON | API and Template to configure,modify,suspend,delete the WAN profiles in WiFi ONT | Critical | Nokia OEM | AMS | Sayyad Pasha | OEM confirmed API is not availble | Dependency on OEM
607 | NOC607 | GPON | GPON | Verification of the service provisioning templates which are prepared for the different types of services | Critical | Nokia OEM | AMS | Sayyad Pasha |  | Dependency on OEM
608 | NOC608 | GPON | GPON | Verification of the services configured by NSO through Playbook(Cisco Tool) | Critical | Nokia OEM | AMS | Sayyad Pasha | API has to share by OEM | Dependency on OEM
609 | NOC609 | GPON | GPON | Mapping bandiwdth profiles per vlan in a ONT UNI | Critical | Nokia OEM | AMS | Sayyad Pasha | Update awaited from the OEM | Dependency on OEM
610 | NOC610 | GPON | GPON | NOKIA ONT is not supporting Rate Limit On Ethernet UNI when connected under Tejas OLT | Critical | Nokia OEM | AMS | Sayyad Pasha | Nokia confirmed that Rate Limiting is not supported in Nokia ONTs | Dependency on OEM
611 | NOC611 | GPON | GPON | PM Report for 24hrs of OLT,ONT,ONT Eth Port(Bridge/Route), Wifi | Critical | Nokia OEM | AMS | Sayyad Pasha |  | Closed
612 | NOC612 | GPON | GPON | Nokia ONT ethernet port status is not updating | Critical | Nokia OEM | AMS | Sayyad Pasha | Duplicate of point-572 | Dependency on OEM
613 | NOC613 | GPON | GPON | Unable to provide available download bandwidth of PON Port for Nokia devices (Nokia BW Query) | Critical | Nokia OEM | AMS | Sayyad Pasha | Having dependency on Service Inventory and NSO | Dependency on OEM
614 | NOC614 | All Domain | OSS | EOL and EOS Through inventory Dashboard-Weekly | Critical | HPSM | Asset Manager | Manoj Nibrad
615 | NOC615 | All Domain | OSS | EOL and EOS Through inventory Dashboard-Monthly | Critical | HPSM | Asset Manager | Manoj Nibrad
616 | NOC616 | All Domain | OSS | Infra Server Url Services Intigration | Critical | HPSM | Site scope | Manoj Nibrad
617 | NOC617 | All Domain | OSS | Infra Server Url Services Monitoring | Critical | HPSM | Site scope | Manoj Nibrad
618 | NOC618 | All Domain | OSS | Infra Server Url Services Reporting | Critical | HPSM | Site scope | Manoj Nibrad
619 | NOC619 | All Domain | OSS | real-time information | Critical | HPSM | Site scope | Manoj Nibrad
620 | NOC620 | All Domain | OSS | Health of the Performance for Traffic | Critical | HPSM | NNM iSPI | Manoj Nibrad
621 | NOC621 | All Domain | OSS | Analyze Flow Packets | Critical | HPSM | NNM iSPI | Manoj Nibrad
622 | NOC622 | All Domain | OSS | Performance for Traffic Maps | Critical | HPSM | NNM iSPI | Manoj Nibrad
623 | NOC623 | NSO | NSO | NSO Intigration for POC Locations LCO,RMSO & MSO | Critical | NSO | SCCM/Playbook | Jayant Madavi
624 | NOC624 | NSO | NSO | Video customer inventory , Internet customer inventory , Bandwidth allocation inventory count etc., | Critical | NSO | SCCM/Playbook | Jayant Madavi
625 | NOC625 | NSO | NSO | NSO Intigration for Live Locations LCO,RMSO & MSO | Critical | NSO | SCCM/Playbook | Jayant Madavi
626 | NOC626 | NSO | NSO | Video customer inventory , Internet customer inventory , Bandwidth allocation inventory count etc., | Critical | NSO | SCCM/Playbook | Jayant Madavi
627 | NOC627 | BSS | BSS | TFiber BSS to be integrated with Partners SMS & BSS (LCO, RMSO & MSO etc..) for POC Locations | Critical | KNOT | CRM | Manoj Nibrad
628 | NOC628 | BSS | BSS | After completion of POC Same solution shall be implemented for All Household of Telangana (TFiber BSS to be integrated with all other Partners SMS & BSS for Live (LCO , RMSO & MSO etc..)) | Critical | KNOT | CRM | Manoj Nibrad
629 | NOC629 | BSS | BSS | New Customer order HouseHolds | Critical | KNOT | CRM | Manoj Nibrad
630 | NOC630 | BSS | BSS | Existing customer alignment for order | Critical | KNOT | CRM | Manoj Nibrad
631 | NOC631 | BSS | BSS | Customer service ID allocation | Critical | KNOT | CRM | Manoj Nibrad
632 | NOC632 | BSS | BSS | Activation & Deactivation update to BSS | Critical | KNOT | CRM | Manoj Nibrad
633 | NOC633 | BSS | BSS | New customer package & billing | Critical | KNOT | Billing | Manoj Nibrad
634 | NOC634 | BSS | BSS | Existing customer renewal & package modification update | Critical | KNOT | Billing | Manoj Nibrad
635 | NOC635 | BSS | BSS | Customer address change intigration | Critical | KNOT | Billing | Manoj Nibrad
636 | NOC636 | BSS | BSS | Customer Discount update to BSS | Critical | KNOT | Billing | Manoj Nibrad
637 | NOC637 | BSS | BSS | Partner Dashboard Number of customers through TFiber | Critical | BSS | CRM | Manoj Nibrad
638 | NOC638 | BSS | BSS | Partner Dashboard Uptime SLA customers through TFiber | Critical | HPSM | Incident Management | Manoj Nibrad
639 | NOC639 | BSS | BSS | Partner Dashboard Access | Critical | BSS | CRM | Manoj Nibrad
640 | NOC640 | BSS | BSS | TFiber BSS to be Implemented for all GI of Telangana | Critical | KNOT | CRM | Manoj Nibrad
641 | NOC641 | BSS | BSS | After completion of POC Same solution shall be implemented for All Government Institutions of Telangana (TFiber BSS to be Utilized for go Live ) | Critical | KNOT | CRM | Manoj Nibrad
642 | NOC642 | BSS | BSS | New Customer order GI | Critical | KNOT | CRM | Manoj Nibrad
643 | NOC643 | BSS | BSS | Existing customer alignment for order | Critical | KNOT | CRM | Manoj Nibrad
644 | NOC644 | BSS | BSS | Customer service ID allocation | Critical | KNOT | CRM | Manoj Nibrad
645 | NOC645 | BSS | BSS | Activation & Deactivation update to BSS | Critical | KNOT | CRM | Manoj Nibrad
646 | NOC646 | BSS | BSS | New customer package & billing | Critical | KNOT | Billing | Manoj Nibrad
647 | NOC647 | BSS | BSS | Existing customer renewal & package modification update | Critical | KNOT | Billing | Manoj Nibrad
648 | NOC648 | BSS | BSS | Customer address change intigration | Critical | KNOT | Billing | Manoj Nibrad
649 | NOC649 | BSS | BSS | Customer Discount update to BSS | Critical | KNOT | Billing | Manoj Nibrad
650 | NOC650 | BSS | BSS | Customer Dashboard Number of customers through TFiber | Critical | BSS | CRM | Manoj Nibrad
651 | NOC651 | BSS | BSS | Customer Dashboard Uptime SLA customers through TFiber | Critical | HPSM | Incident Management | Manoj Nibrad
652 | NOC652 | BSS | BSS | Customer Dashboard Access | Critical | BSS | CRM | Manoj Nibrad
653 | NOC653 | BSS | BSS | TFiber BSS to be Implemented for all Enterprice P2p & P2MP services in Telangana | Critical | KNOT | CRM | Manoj Nibrad
654 | NOC654 | BSS | BSS | After completion of POC Same solution shall be implemented for All Enterprice P2p & P2MP services in Telangana (TFiber BSS to be Utilized for go Live ) | Critical | KNOT | CRM | Manoj Nibrad
655 | NOC655 | BSS | BSS | New Customer order Enterprice | Critical | KNOT | CRM | Manoj Nibrad
656 | NOC656 | BSS | BSS | Existing customer alignment for order | Critical | KNOT | CRM | Manoj Nibrad
657 | NOC657 | BSS | BSS | Customer service ID allocation | Critical | KNOT | CRM | Manoj Nibrad
658 | NOC658 | BSS | BSS | Activation & Deactivation update to BSS | Critical | KNOT | CRM | Manoj Nibrad
659 | NOC659 | BSS | BSS | New customer package & billing | Critical | KNOT | Billing | Manoj Nibrad
660 | NOC660 | BSS | BSS | Existing customer renewal & package modification update | Critical | KNOT | Billing | Manoj Nibrad
661 | NOC661 | BSS | BSS | Customer address change intigration | Critical | KNOT | Billing | Manoj Nibrad
662 | NOC662 | BSS | BSS | Customer Discount update to BSS | Critical | KNOT | Billing | Manoj Nibrad
663 | NOC663 | BSS | BSS | Customer Dashboard Number of customers through TFiber | NON-Critical | BSS | CRM | Manoj Nibrad
664 | NOC664 | BSS | BSS | Customer Dashboard Uptime SLA customers through TFiber | NON-Critical | HPSM | Incident Management | Manoj Nibrad
665 | NOC665 | BSS | BSS | Customer Dashboard Access | NON-Critical | BSS | CRM | Manoj Nibrad
666 | NOC666 | Service Solutions | NSO | GI-BB | Critical | NSO | SCCM/Playbook | Jayant Madavi
667 | NOC667 | Service Solutions | NSO | T-CELL | Critical | NSO | SCCM/Playbook | Jayant Madavi
668 | NOC668 | Service Solutions | NSO | HH Triple Play (Internet, IPTV, VoIP) | Critical | NSO | SCCM/Playbook | Jayant Madavi
669 | NOC669 | Service Solutions | NSO | CCTV Unicast | Critical | NSO | SCCM/Playbook | Jayant Madavi
670 | NOC670 | Service Solutions | NSO | CCTV Multicast | Critical | NSO | SCCM/Playbook | Jayant Madavi
671 | NOC671 | Service Solutions | NSO | T-DIA (ILL) | Critical | NSO | SCCM/Playbook | Jayant Madavi
672 | NOC672 | Service Solutions | NSO | L2VPN | Critical | NSO | SCCM/Playbook | Jayant Madavi
673 | NOC673 | Service Solutions | NSO | L3VPN | Critical | NSO | SCCM/Playbook | Jayant Madavi
674 | NOC674 | Service Solutions | NSO | TVPN - Rythu Vedika | Critical | NSO | SCCM/Playbook | Jayant Madavi
675 | NOC675 | Service Solutions | NSO | TVPN - DHQ to SHQ Connectivity | Critical | NSO | SCCM/Playbook | Jayant Madavi
676 | NOC676 | Service Solutions | NSO | TVPN - MRO Office Connectivity | Critical | NSO | SCCM/Playbook | Jayant Madavi
677 | NOC677 | Service Solutions | NSO | SDC/TSWAN integration | Critical | NSO | SCCM/Playbook | Jayant Madavi
678 | NOC678 | Service Solutions | NSO | TSP NNI | Critical | NSO | SCCM/Playbook | Jayant Madavi

## Key deliverables (hidden)
B 1. Key Deliverables
S.No. | Domain | Key Deliverables | Completion Timeline | Remarks
1 | Engineering Solutions | Requirement, Solution and LLD for OSS, GIS, A&O Solution, BSS etc | 2025-07-31 | OSS, GIS,A&O Solution balance work design is WIP for the balance scope SOWs. A new BSS systems is being setup, the solution, requirements and integration points are getting redefined(dates will be revisited upon workshops)
2 | Engineering Solutions | NOC disaster management and bcp plan | 2025-09-30 | Original DR/BCP plan's review points incorporated, a followed-on review to be setup by LTTS
3 | Engineering Solutions | OSS - Service Assurance Module (SLA, SIA etc) performance modules along with specific metrices, NMS functionality, Topologies, cross domain SIAs | 2025-07-31 | Incorporated into OSS - Balance Scope of Work
4 | Engineering Solutions | Basic operational BSS – CRM, CSP, Billing and PCM not ready, integration with ERP system and WFM | 2025-05-31 | The functional scope is being worked upon for the chosen vendor OEM. The acceptance of scope by Tfiber will be used to determine roadmap
5 | Engineering Solutions | Fully operational BSS | 2025-07-31 | The functional scope is being worked upon for the chosen vendor OEM. The acceptance of scope by Tfiber will be used to determine roadmap
6 | Engineering Solutions | A&O Solution Resource/Asset module, Service Inventory module for all the domains - DWDM GPON and MPLS architecture to be discussed | 2025-07-31 | Workshop conducted for compliances and architecture points between Tfiber, OEM(Cisco) and LTTS. The open points to be discussed in subsequent tripartite meetings
7 | Engineering Solutions | GIS SOP and dashboards, mobile application | 2025-02-28 | GIS SOP is submitted. Mobile application will be rolledout per the Interim-NOC roadmap submitted
8 | Engineering Solutions | Adherence to completion of all pending workshops, conditional approval points | 2024-11-30 | OT, HP, A&O Solution workshops completed. New SOWs are being worked upon based on balance scope for Tfiber program
9 | Engineering Solutions | Critical resources - A&O Solution BSS OSS Help desk etc for maintenance and new feature additions after NOC readiness | 2025-03-31 | For identified features, the BSS roadmap will be worked out and would be submitted with Helpdesk and other integrations.
10 | Engineering Solutions | Helpdesk – Integrated with OSS and BSS and other related systems | 2025-05-31 | Standalone Helpdesk system is rolled out. A new BSS systems is getting evaluated, the integration with technical helpdesk will be carried out. Standard BSS API will be exposed for LCO systems to integrate
11 | Engineering Solutions | Service Delivery Modules, Teams and their Roles | 2025-05-31 | Ongoing support continues for Service Provisioning
12 | Engineering Solutions | DR Solution and Mock Drills | 2025-10-31 | Timelines captured in sheet Roadmap-Interim NOC | DR Solution will be submitted on 19-09-2025
13 | Engineering Solutions | WFM-Demo, Delivery and Assurance module | 2025-05-31 | Timelines captured in sheet TNOC and Interim NOC Applications Readiness. Needs exec decision on WFM modules and services compensated to align with roadmap presented
14 | Engineering Solutions | GI Plan in GIS | 2024-12-30
15 | Engineering Solutions | Dashboard Finalization – standard and specific / customized requirements | 2025-05-31
16 | Engineering Solutions | Automation module, Roadmap, Teams and Deliverables | 2025-05-31 | Timelines captured in sheet TNOC Application Readiness and in sheet Interim NOC O&M.
17 | Engineering Solutions | Pre-production environment for all the applications and IT infrastructure, resources, process-approach | Completed | 1. The newly build cluster is carved out of existing infra envisaged for full rollout 2. OEMs has provided required pre-prod licenses 3.Remaining application deployment will be carried out in phased manner.WFM is deployed on pre-prod
18 | Resources & Contracts | OEM and L&T for NOC unavailability and regular basis, SME unavailability | 2024-11-15 | SMEs are available, OEM resources not available on-site. L&T will front end all discussions.
19 | Resources & Contracts | Issues between HPE and Microfocus | 2024-10-30 | Multiple tripartite meetings carried out between OEMS, Tfiber and L&T. L&T Will submit the balance scope and agreements of OEMs with T-Fiber.
20 | Resources & Contracts | All OEM meeting |  | Adhoc and need based meetings are arranged
21 | ATPs | AT Plans | 2025-06-30 | Captured application wise in an internal worksheet
22 | ATPs | Dry Runs and Roadmap | 2025-06-30 | Dry runs will be aligned with new BSS onboarding and rollout plans
23 | ATPs | Handover approach after 7 years | 2025-06-30 | LTTS is working upon an approach for KT, shadow and handover into identified Tfiber vendor/teams
24 | Security & Regulatory | Security design and Regulatory compliance and systems along with design documents (AAA, VAPT etc) | 2025-03-15 | Revised security documents to be submitted as per TNOC Design and Documentation for Secuirity
25 | Security & Regulatory | Integration with NKN, SOC, GeM, and SDC applications | 2025-06-30 | Discussion to be done with T-Fiber for mentioned integrations and to be aligned with new BSS onboarding and roadmap
26 | Undertakings | Submission of back to back agreement with their OEM for NOC readiness and Gap with respect to RFP | 2025-06-30 | All OEM agreements have been submitted, HPE and Microfocus (Opentext) agreement has to be submitted.
27 | Undertakings | Tejas and Nokia compliance / undertaking | 2025-07-30 | 13-09-2025 : Nokia has provided the SOP, which has been tested and is working as expected. However, Nokia ONTs connected to Tejas OLTs cannot be enabled directly through the Tejas OLT. As discussed with TFiber, we have prepared an SOP for the field team and are currently working on mapping the Nokia ONTs under Tejas OLTs to nearby Nokia OLTs 06-03-2025 : Tejas Undertaking Completed on 28-02-2025 and letter submitted to TFiber on 06-03-2025
28 | Undertakings | Undertaking mentioning Interim Plan, Roadmap, and Transition plan including letter from OEMs | 2025-06-30 | Undertaking mentioning Interim Plan, Roadmap, and Transition plan including letter from OEMs In Progress-emails are submitted, however OEMs are reluctant for sharing on a letter
29 | Undertakings | Tejas undertaking (AAA) | 2025-02-28 | 28-02-2025 : Tejas Undertaking Completed on 28-02-2025
30 | Undertakings | Nokia undertaking (DHCP) | 2025-07-30 | 13-09-2025 : Nokia has provided the SOP, which has been tested and is working as expected. However, Nokia ONTs connected to Tejas OLTs cannot be enabled directly through the Tejas OLT. As discussed with TFiber, we have prepared an SOP for the field team and are currently working on mapping the Nokia ONTs under Tejas OLTs to nearby Nokia OLTs
31 | NDA | NDAs from OEMs | 2025-06-30 | NDA submitted, any new OEMs onboarded will be shared on the top

## LOV (hidden)
LIST
OPEN
COMPLETED & APPROVED
WIP
REOPENED
CLOSURE REVIEW PENDING
DEPENDENCY(Client/Ext)
LIST 2
YES
NO
Owner(L&T) List
Suresh Kumar
Manoj Nibrad
Ravi Kishore
RS Rao
Kaushalendra Kumar
Sayyad Pasha
Suresh Pawar
Sarmendra
Siva Kumar
Ahmad
T Chinnaiah Sekhar
Jayant Madavi
Sandeep Deshmukh
Siva Prasad
LOV
Security & Regulatory Compliance
DWDM
BSS
IP/MPLS
DC-IT
DR
GIS
GPON
NSO
OSS
TNOC-Ops
BSS

## Design_Doc (hidden)
B 2. TNOC Design & Documentation
S.No. | Topic | Domain | Deliverable/Activity Description | Completion Timeline | Remarks
1 | Design and Documentation | BSS | Requirement Document | 2025-05-01
2 | Design and Documentation | BSS | Solution Document | 2025-05-31
3 | Design and Documentation | BSS | LLD | 2025-08-14
4 | Design and Documentation | BSS | Functional ATPs | 2025-08-14
5 | Design and Documentation | OSS | Requirement Document | 2025-05-01
6 | Design and Documentation | OSS | Solution Document | 2025-05-31
7 | Design and Documentation | OSS | LLD | 2025-08-14
8 | Design and Documentation | OSS | Functional ATPs | 2025-08-14 | OT Support required
9 | Design and Documentation | A&O Solution | Requirement Document | 2025-05-01
10 | Design and Documentation | A&O Solution | Solution Document | 2025-05-31
11 | Design and Documentation | A&O Solution | LLD | 2025-08-14
12 | Design and Documentation | A&O Solution | Functional ATPs | 2025-08-14
13 | Design and Documentation | GIS | Requirement Document | Completed (part of LLD) | Submission & Resubmission also done with feedback incorporation
14 | Design and Documentation | GIS | Solution Document | Completed (part of LLD) | Submission & Resubmission also done with feedback incorporation
15 | Design and Documentation | GIS | LLD | Completed (3.3.2025) | Submission & Resubmission also done with feedback incorporation
16 | Design and Documentation | GIS | Functional ATPs | Completed(25.02.2025) | Submission & Resubmission also done with feedback incorporation
17 | Design and Documentation | WFM | Requirement Document | Completed | Submission & Resubmission also done with feedback incorporation
18 | Design and Documentation | WFM | Solution Document-(HLD) | Completed (part of LLD)18.02.2025 | Submission & Resubmission also done with feedback incorporation
19 | Design and Documentation | WFM | LLD | Completed.20.02.25 | Submission & Resubmission also done with feedback incorporation
20 | Design and Documentation | WFM | Functional ATPs | 2025-06-30
21 | Design and Documentation | DC IT Infra | Requirement Document | 2025-05-31
22 | Design and Documentation | DC IT Infra | Solution Document | 2025-09-15
23 | Design and Documentation | DC IT Infra | LLD | 2025-09-29
24 | Design and Documentation | DC IT Infra | Functional ATPs | 2025-09-30
25 | Design and Documentation | DC Network | Requirement Document
27 | Design and Documentation | DC Network | Solution+LLD | 2025-06-18 | Updated document submitted for approval
28 | Design and Documentation | DC Network | Functional ATPs | WIP | Need OEM support for FAT procedures asked by TPA & Customer
29 | Design and Documentation | Security | Requirement Document | 2025-06-30
30 | Design and Documentation | Security | Solution Document | 2025-06-30
31 | Design and Documentation | Security | LLD | 2025-06-30
32 | Design and Documentation | DWDM | Requirement Document | Completed
33 | Design and Documentation | DWDM | Solution Document | Completed
34 | Design and Documentation | DWDM | LLD | Completed
35 | Design and Documentation | DWDM | Functional ATPs | Completed | MCP FAT document approval pending from T Fiber
36 | Design and Documentation | GPON | Requirement Document | Completed
37 | Design and Documentation | GPON | Solution Document | Completed
38 | Design and Documentation | GPON | Functional ATPs | WIP | 13-09-2025 : EMS/AMS Functional ATP document to be submitted
39 | Design and Documentation | IPMPLS | Requirement Document
40 | Design and Documentation | IPMPLS | Solution Document
41 | Design and Documentation | IPMPLS | Solution+LLD | Completed | LLD appoved on 21st Aug'25
42 | Design and Documentation | IPMPLS | Functional ATPs | WIP | Field AT process for IPMPLS lead by implementation team
43 | Design and Documentation | DR | Requirement Document | 2025-06-30
44 | Design and Documentation | DR | Solution Document | 2025-09-17
45 | Design and Documentation | DR | LLD | 2025-06-30
46 | Design and Documentation | DR | Functional ATPs | 2025-06-30
47 | Design and Documentation | NOC | Disaster Management & BCP | 2025-07-30
48 | Design and Documentation | GIS | SOP Document | Completed (17.1.2024) | Reviewed by TFIBER and currently being utilized by the team
49 | Resources & Contracts | Resources | OEM & L&T SMEs are available, OEM resources not available on-site. L&T will front end all discussions. OEMs are reengaged based on Tfiber guidance on making the dedicated members available at onsite in TFiber. | 2024-12-30
50 | Resources & Contracts | HPE/OT | L&T will submit the balance scope and agreements of OEMs with T-Fiber. OT engaged wef 1st Sep 2024, HPE and Csco A&O Solution are reengaged, target 2nd week Nov 2024 | 2024-11-15
51 | Resources & Contracts | Meeting | All OEMs -As and when required, can be planned with relevant OEMs | Need Basis
| ATPs | N/W & Applications | Captured application wise in an internal worksheet for 2 batches | 2025-03-30
53 | ATPs | N/W & Applications | Separate dry run roadmap will be shared with T-Fiber along with BSS revised roadmap | 2025-06-30
54 | ATPs | N/W & Applications | LTTS is working upon an approach for KT, shadow and handover into identified Tfiber vendor/teams | 2025-06-30
55 | Security & Regulatory | Compliance & Systems | Security design and regulatory compliance and systems along with design documents (AAA, VAPT etc) | 2025-06-30
56 | Security & Regulatory | Integrations | Integration with NKN, SOC, GeM and SDC applications. Will be covered in the BSS delivery roadmap | 2025-06-30
57 | Undertakings | All OEMs | All OEM agreements have been submitted, HPE and Microfocus (Opentext) agreement has to be submitted. | 2025-06-30
58 | Undertakings | Tejas/Nokia | Tejas Undertaking Completed on 28-02-2025 and letter submitted to TFiber on 06-03-2025 Nokia provided the SOP to enable the Hybrid Mode in the Nokia ONT(G-240G-E) and same has been tested successfully. However, working with Nokia for the SOP of Nokia ONTs connected under Tejas OLT | WIP | 13-09-2025 : Nokia has provided the SOP, which has been tested and is working as expected. However, Nokia ONTs connected to Tejas OLTs cannot be enabled directly through the Tejas OLT. As discussed with TFiber, we have prepared an SOP for the field team and are currently working on mapping the Nokia ONTs under Tejas OLTs to nearby Nokia OLTs 28-02-2025 : Tejas Undertaking Completed on 28-02-2025
59 | Undertakings | All OEMs | Undertaking mentioning Interim Plan, Roadmap, and Transition plan including letter from OEMs In Progress-emails are submitted, however OEMs are reluctant for sharing on a letter | 2025-06-30
60 | Undertakings | Tejas | Tejas Undertaking Completed on 28-02-2025 and letter submitted to TFiber on 06-03-2025 | 2025-02-28 | 28-02-2025 : Tejas Undertaking Completed on 28-02-2025
61 | Undertakings | Nokia | Nokia provided the SOP to enable the Hybrid Mode in the Nokia ONT(G-240G-E) and same has been tested successfully. However, working with Nokia for the SOP of Nokia ONTs connected under Tejas OLT | WIP | 13-09-2025 : Nokia has provided the SOP, which has been tested and is working as expected. However, Nokia ONTs connected to Tejas OLTs cannot be enabled directly through the Tejas OLT. As discussed with TFiber, we have prepared an SOP for the field team and are currently working on mapping the Nokia ONTs under Tejas OLTs to nearby Nokia OLTs

## T0-T6 (hidden)
B 3. TNOC Applications Readiness Roadmap
S.No. | NOC Applications | Sub-modules | Functionality | Completed | 1-Apr-25 To 30-Apr-25 | 1-May-25 To 31-May-25 | 1-Jun-24 To 30-Jun-24 | 1-Jul-25 To 31-Jul-25 | 1-Aug-25 To 31-Aug-25 | 1-Sep-25 To 30-Sep-25 |  | Remarks
1 | BSS | Multiple Modules | G2G, GI Order Handling | WIP | Planned |  |  |  |  | Optimisation and Stabilisation. AT Completion
| BSS | Multiple Modules | Migration all existing | WIP | Planned |  |  |  |  | Optimisation and Stabilisation. AT Completion
| BSS | Multiple Modules | Billing | WIP | Planned |  |  |  |  | Optimisation and Stabilisation. AT Completion
| BSS | Multiple Modules | Reports & Dashboards | Completed | Planned |  |  |  |  | Optimisation and Stabilisation. AT Completion
| BSS | Multiple Modules | LMO Partner Onboarding* | Completed | Planned |  |  |  |  | Optimisation and Stabilisation. AT Completion
| BSS | Multiple Modules | B2B2C Implementation* (with technical Helpdesk) | WIP |  | Planned |  |  |  | Optimisation and Stabilisation. AT Completion
| BSS | Multiple Modules | Revenue Sharing & Reports* | WIP |  |  | Planned |  |  | Optimisation and Stabilisation. AT Completion
| BSS | Multiple Modules | Regulatory Report | WIP |  |  |  | Planned |  | Optimisation and Stabilisation. AT Completion
1 | BSS | Multiple Modules | Other Services (SME/Corporate/Trans) | WIP |  |  | Planned 1 | Planned 2 | Planned 3 | Optimisation and Stabilisation. AT Completion
2 | OSS | UOC | User CoA&O Solutionle | Completed | System stabilization, # Bug Fixing if any |  |  | GPON Availability Report | Fault Segregation Report | Management dashboard
3 | OSS | UOC | Web GUI | Completed | System stabilization, # Bug Fixing if any |  |  |  | Fault Ageing report | PMS Reports
4 | OSS | UOC | Alarms reporting for GPON (Tejas, Nokia) | Completed | System stabilization, # Bug Fixing if any |  |  |  |  | User Profile and Roles
5 | OSS | UOC | Alarms reporting for DWDM | Completed | System stabilization, # Bug Fixing if any
6 | OSS | UOC | Alarms reporting for IPMLS | Completed | System stabilization, # Bug Fixing if any
7 | OSS | UOC | Alarms reporting for Passive Infra | Completed | System stabilization, # Bug Fixing if any
8 | OSS | UOC | Alarms reporting for Active IT Infra | Completed | Report delivery
9 | OSS | UOC | Alarm corelation within Domain | WIP | Cross domain logic deployment & Delivery and testing |  |  |  |  | Optimisation and Stabilisation. AT Completion
10 | OSS | UOC | Cross Domain Alarm Corelation | WIP | Cross domain logic planning and deployment (part1) | Cross domain logic deployment (part2) | Testing & fixing issue if any | delivery of Cross Domain Alarm Corelation |  | Optimisation and Stabilisation. AT Completion
11 | OSS | UCA | RCA GPON | WIP |  |  |  | Alarms Co-relation & Cross domain to be deploy | System stabilization, # Bug Fixing if any | System stabilization, # Bug Fixing if any
12 | OSS | UCA | RCA DWDM | WIP |  |  |  | Alarms Co-relation & Cross domain to be deploy | System stabilization, # Bug Fixing if any | System stabilization, # Bug Fixing if any
13 | OSS | UCA | RCA IPMPLS | WIP |  |  |  | Alarms Co-relation & Cross domain to be deploy | System stabilization, # Bug Fixing if any | System stabilization, # Bug Fixing if any
14 | OSS | UCA | Network Impact Analysis | WIP | Finalize the work flow and deployement (part1) | deployement (part2) | Testing | Delivery & Fixing issue if any
15 | OSS | UCA | Service Impact Analysis | WIP |  |  | Service Inventory available in HPSM/SM |  | Ticket enablement for services, and impact analysis | System stabilization, # Bug Fixing if any
16 | OSS | UTM | Network Data Load from EMS | WIP | System stabilization, # Bug Fixing if any | physical device syn-up Implementation |  | E2E Cross domain Topology | Optimisation and Stabilisation. AT Completion | Optimisation and Stabilisation. AT Completion
17 | OSS | UTM | Network Data Load from GIS into TeMIP | WIP |  | Additional Few parameter to be pass in Existing API | Final testing and issue fixing if any |  | Optimisation and Stabilisation. AT Completion | Optimisation and Stabilisation. AT Completion
18 | OSS | UTM | UCA & uCMDB | WIP | System stabilization, # Bug Fixing if any | System stabilization, # Bug Fixing if any | System stabilization, # Bug Fixing if any |  | Optimisation and Stabilisation. AT Completion | Optimisation and Stabilisation. AT Completion
19 | OSS | TeMIP | Fault Management for GPON | WIP | System stabilization | Testing and issue fixing if any |  | event corelation and enrichment | Testing and issue fixing if any | Optimisation and Stabilisation. AT Completion
20 | OSS | TeMIP | Fault Management for DWDM | WIP | System stabilization | Testing and issue fixing if any |  | event corelation and enrichment | Testing and issue fixing if any | Optimisation and Stabilisation. AT Completion
21 | OSS | TeMIP | Fault Management for IPMPLS | WIP | System stabilization | Testing and issue fixing if any |  | event corelation and enrichment | Testing and issue fixing if any | Optimisation and Stabilisation. AT Completion
22 | OSS | TeMIP | Performance management for GPON | WIP | System stabilization | PMS Reports | Testing and issue fixing if any
23 | OSS | TeMIP | Performance management for DWDM | WIP | System stabilization | PMS Reports | Testing and issue fixing if any
24 | OSS | NPS | Performance management for IPMPLS: Latency, Jitter, Packet Loss | WIP |  | NetFlow enabling and testing | Testing and issue fixing if any | # Bug Fixing and Additional customization if required | Optimisation and Stabilisation. AT Completion | Optimisation and Stabilisation. AT Completion
25 | OSS | Asset Manager | Asset Management | WIP | System stabilization, # Bug Fixing if any | issue fixing if any |  | Optimisation and Stabilisation. AT Completion | Optimisation and Stabilisation. AT Completion | Optimisation and Stabilisation. AT Completion
26 | OSS | UCMDB/UD | Discovery/Inventory | WIP | System stabilization, # Bug Fixing if any
27 | OSS | OMi | Server Availability and performance management-Active IT Infra | WIP | DC Fault/ Performance Monitoring. Monitoring Parameters / KPIs Details Event Management | Dashboard | Monitoring Dashboard & Performance Graphs | Final testing and issue fixing if any
28 | OSS | OBR | Server Availability and performance management-Active IT Infra | WIP | OBR Report - Service and Operations Bridge (OMI) & System Management (DC Components) | Executive Summary Reports Performance Reports Operational Reports | Final testing and issue fixing if any
29 | OSS | Network Automation | Automation | WIP | NA Deployment Diagram, Onboarding Process & Policy Deployment.Alert’s on NNMi | issue fixing if any |  | Reports -Compliance Audit Report - Non-Compliance report | Final testing and issue fixing if any
30 | OSS | Sitescope | Application Alarm collection | WIP | issue fixing if any | issue fixing if any | issue fixing if any | Optimisation and Stabilisation. AT Completion | Optimisation and Stabilisation. AT Completion | Optimisation and Stabilisation. AT Completion
31 | OSS | NNMi | Fault Management for IPMPLS | WIP | # Bug Fixing and Additional customization if required |  |  |  | Optimisation and Stabilisation. AT Completion | Optimisation and Stabilisation. AT Completion
32 | OSS | NNMi | Performance management for IPMPLS | WIP | NetFlow enabling and testing. Montoring all reports | Final testing and issue fixing if any |  |  | Optimisation and Stabilisation. AT Completion | Optimisation and Stabilisation. AT Completion
33 | OSS | NNMi | Fault Management for Passive Infra | WIP | # Bug Fixing and Additional customization if required |  |  |  | Optimisation and Stabilisation. AT Completion | Optimisation and Stabilisation. AT Completion
34 | OSS | HPSM | Auto TT DWDM | Completed | System stabilization, # Bug Fixing | issue fixing if any | issue fixing if any | issue fixing if any | Optimisation and Stabilisation. AT Completion | Optimisation and Stabilisation. AT Completion
35 | OSS | HPSM | Auto TT GPON | Completed | System stabilization, # Bug Fixing | issue fixing if any | issue fixing if any | issue fixing if any | Optimisation and Stabilisation. AT Completion | Optimisation and Stabilisation. AT Completion
36 | OSS | HPSM | Auto TT Infra Passive | Completed | System stabilization, # Bug Fixing | issue fixing if any | issue fixing if any | issue fixing if any | Optimisation and Stabilisation. AT Completion | Optimisation and Stabilisation. AT Completion
37 | OSS | HPSM | Auto TT DC-Active | Completed | System stabilization, # Bug Fixing | issue fixing if any | issue fixing if any | issue fixing if any | Optimisation and Stabilisation. AT Completion | Optimisation and Stabilisation. AT Completion
38 | OSS | HPSM | Auto TT MPLS | Completed | System stabilization, # Bug Fixing | issue fixing if any | issue fixing if any | issue fixing if any | Optimisation and Stabilisation. AT Completion | Optimisation and Stabilisation. AT Completion
39 | OSS | HPSM | Service Management | Completed | System stabilization, # Bug Fixing | issue fixing if any | issue fixing if any | Service SLA to be made available | Final testing and issue fixing if any | Optimisation and Stabilisation. AT Completion
40 | OSS | HPSM | Manual TT Assignment in WFM | WIP | WFM Integration | WFM Integration Completion & Testing | Final testing and issue fixing if any | Final testing and issue fixing if any |  | Optimisation and Stabilisation. AT Completion
41 | OSS | HPSM | Auto TT Assignment in WFM | WIP | WFM Integration | WFM Integration Completion & Testing | Final testing and issue fixing if any | Final testing and issue fixing if any |  | Optimisation and Stabilisation. AT Completion
42 | A&O Solution | Integration | Integration framework completion with OSS/BSS | WIP | Completed for OSS | Stabilisation for the OSS Integration | Align for BSS ( pending Interlock with BSS roadmap) | Align for BSS ( with Interlock with BSS roadmap TBA ) | Align for BSS ( with Interlock with BSS roadmap TBA ) | Align for BSS ( with Interlock with BSS roadmap TBA )
43 | A&O Solution | Integration | Integration framework completion with DWDM EMS | Completed | Completed for implemented services
44 | A&O Solution | Integration | Integration framework completion with GPON EMS | Completed | Completed for implemented services |  | Align for BSS ( pending Interlock with BSS roadmap) | Align for BSS ( with Interlock with BSS roadmap TBA ) | Align for BSS ( with Interlock with BSS roadmap TBA ) | Align for BSS ( with Interlock with BSS roadmap TBA )
45 | A&O Solution | Integration | Integration framework completion with IPMPLS | Completed | Completed for implemented services |  | Align for BSS ( pending Interlock with BSS roadmap) | Align for BSS ( with Interlock with BSS roadmap TBA ) | Align for BSS ( with Interlock with BSS roadmap TBA ) | Align for BSS ( with Interlock with BSS roadmap TBA )
46 | A&O Solution | Playbook | Verification-GPON (Tejas, Nokia), DWDM, IPMPLS | Completed |  |  | Align for BSS ( pending Interlock with BSS roadmap) | Align for BSS ( with Interlock with BSS roadmap TBA ) | Align for BSS ( with Interlock with BSS roadmap TBA ) | Align for BSS ( with Interlock with BSS roadmap TBA )
47 | A&O Solution | Playbook | Verification-DWDM | Completed |  |  | Align for BSS ( pending Interlock with BSS roadmap) | Align for BSS ( with Interlock with BSS roadmap TBA ) | Align for BSS ( with Interlock with BSS roadmap TBA ) | Align for BSS ( with Interlock with BSS roadmap TBA )
48 | A&O Solution | Playbook | Verification-IPMPLS | Completed |  |  | Align for BSS ( pending Interlock with BSS roadmap) | Align for BSS ( with Interlock with BSS roadmap TBA ) | Align for BSS ( with Interlock with BSS roadmap TBA ) | Align for BSS ( with Interlock with BSS roadmap TBA )
49 | A&O Solution | A&O Solution-NED | Provisioning & Activation-GPON (Tejas, Nokia) | WIP | Framework Completed |  | NEDs to be configured for new Service Types | NEDs to be configured for new Service Types | NEDs to be configured for new Service Types | NEDs to be configured for new Service Types
50 | A&O Solution | A&O Solution-NED | Provisioning & Activation-DWDM | WIP | Framework Completed
51 | A&O Solution | A&O Solution-NED | Provisioning & Activation-IPMPLS | WIP | Framework Completed |  | NEDs to be configured for new Service Types | NEDs to be configured for new Service Types | NEDs to be configured for new Service Types | NEDs to be configured for new Service Types
52 | A&O Solution | SCCM | API-OSS/BSS | WIP | Completed for GIBB, T-Cell SPOKE |  | Align for BSS ( pending Interlock with BSS roadmap) | Align for BSS ( with Interlock with BSS roadmap TBA ) | Align for BSS ( with Interlock with BSS roadmap TBA ) | Align for BSS ( with Interlock with BSS roadmap TBA )
53 | A&O Solution | SCCM UI | Per service UI | WIP | Order tracking completed |  | Semi-Auto (For 2 using SCCM UI) in absence of BSS(GI-BB, T-Cell, Dark Fiber, T VPN, T-Dia) | BSS-A&O Solution Integration, SCCM-UI additional 2 Services | New BSS-A&O Solution integration for a service + SCCM UI for remaining services | New BSS-A&O Solution integration for additional services | New BSS-A&O Solution integration for additional 1 service
54 | A&O Solution | Feasibility-Services | Service Feasibility using A&O Solution (TBA per new architectural guidance) | WIP | TBA - To be aligned with BSS delivery plans | TBA - To be aligned with BSS delivery plans | TBA - To be aligned with BSS delivery plans | TBA - To be aligned with BSS delivery plans | TBA - To be aligned with BSS delivery plans | TBA - To be aligned with BSS delivery plans
55 | GIS | Gtech | Gtech readiness with data model, ISP/OSP object modelling | Completed | G-tech (GIS System) is ready & Operational, along with Data model finalisation & ISP,OSP object modelling and deployment.
56 | GIS | Gtech | Reports-Fiber Utilization | Completed | Fiber Utilisation Report is deployed & Operational .
57 | GIS | Gtech | Overall NW summary | Completed | Overall NW summary Report is deployed & Operational.
58 | GIS | Gtech | Active BOQ | Completed | Active BOQ Report is deployed & Operational
59 | GIS | Gtech | Passive BOQ | Completed | Passive BOQ Report is deployed & Operational
60 | GIS | Gtech | User Log History | Completed | User Log History Report is deployed & Operational.
61 | GIS | Gtech | Link trace, spare fiber | Completed | Link trace, spare fiber Report is deployed & Operational.
62 | GIS | Gtech | Data conversion-.kml & .shp file from Gtech | Completed | Data conversion-.kml & .shp file from Gtech is deployed & Operational.
63 | GIS | Gtech | Completion of Data uploading into GIS System | Completed | Targeted to reach 70% | Targeted to reach 80% | Targeted to reach 85% | Targeted to reach 90% | Targeted to reach 95% | Targeted to reach 100%
64 | GIS | DI | Data Integrator | Completed | Data Integrator tool is ready & Operational.
65 | GIS | Network Portal | Dashboards, replication of network from Gtech | Completed | Dashboard Function Completed & Deployed - Completed "It is Operational by NOC users ". Targeted To make operational for all Concerns
66 | GIS | Network Portal | Manual Feasibility tools & feature | Completed | Tools For Manual feasibility has been deployed in Network portal System is operational
67 | GIS | Mobile Application | Network availability with G-MAP | Completed | Function Is ready & Deployed and operational
68 | GIS | Mobile Application | Red line, Red Point Feature deployment | Completed | Function Is ready & Deployed and operational
69 | GIS | Mobile Application | JOB creation testing in GIS tool from GIS Mobile app | Completed | Function Is ready & Deployed and operational | Targeted To make operational for all Concerns
70 | GIS | Integration | Complete integration with OSS (active device sync up) | WIP | DB-DB Integrations completed & Device level attributes are available in view of OSS to GIS, Only Mac & IPV6 is missing for Switch & Router. | Target to make available missing level information view for Devices level Attribute. | Port Level Attribute syncing GIS-OSS,OSS-GIS Sync Report, Testing of function & data mismatch Error Fixing | Optimisation and Stabilisation. AT Completion | Optimisation and Stabilisation. AT Completion | Optimisation and Stabilisation. AT Completion
71 | GIS | Integration | Complete integration with OSS (Common Span) | WIP | Approach Finalisation done, Alaram scenario finalised, corelation rule discussed with OSS. | Input (OSS) & Output (GIS) event/Data finalisation,API creation for OSS System. | API Integration between both the system | Ticket/RCA testing & Bug fixing Completion | Optimisation and Stabilisation. AT Completion | Optimisation and Stabilisation. AT Completion
72 | GIS | Integration | Complete integration with OSS (Auto Feasibility) | Completed | Integration completed between OSS & GIS, Auto feasibility feature to be tested by New BSS system. | Optimisation and Stabilisation. | Optimisation and Stabilisation. | Optimisation and Stabilisation. | AT Completion | AT Completion
73 | GIS | Integration | Complete integration with WFM | Completed | GIS & WFM integration GIS CM TT process also implemented with Redline & Redpoint Features. | Optimisation and Stabilisation. | Optimisation and Stabilisation. | Optimisation and Stabilisation. | AT Completion | AT Completion
74 | WFM | Order Management | GPON Service Fulfilment/Activation | Completed | WFM all the functions are working, closure API integration pending from BSS ( Dependency On BSS)
75 | WFM | Order Management | Dark Fiber delivery | Completed | Dark fibre order management solution deployed in WFM.
76 | WFM | Fault Management | Route Patrolling | Completed | Function/Aplication is ready & Deployed, access and training provided to some of person from TFIBER & PKG Owners and operational
77 | WFM | Fault Management | Auto assignment of TT from HPSM (Corrective & Preventive) | WIP | TT Format finalisation done for WFM Completed. Detailed discussions with stakeholders to agree requirements Documenting use cases, integration points, and data flows,Data mapping, API specifications, and security measures. Establishing milestones and timelines | Developing interfaces/APIs for HPSM and WFM integration cases Implementing the request/response format Developing scripts for data transfer and processingUnit testing of individual components. Integration testing to ensure data flows correctly between HPSM and WFM. User acceptance testing (UAT) with the operation team to validate the solution (Dependency On OT Onboarding )
78 | WFM | Work Force Management | Roster Management | Completed | This feature is available needs to align with TFIBER project and operational
79 | WFM | Work Force Management | Attendance & Leave Management | Completed | All the required correction completion in smart inventory for order fulfilment, User level Hierarchy deployment as per TFIBER project is operational
80 | WFM | Reports & Dashboards | Operational requirement customised dashboards & reports | Completed | 11 types, Out of the box reports are available, discussion completed on proposed reports. 5 additional Reports has been deployed . All Report of Patrolling module will be completed | Service delivery related Report development & customisation of existing reports | Service delivery related Report development & customisation of existing reports (Completion) | Service assurance report development will start after integration completion | Completion of all the reports & dashboards
81 | IPMPLS | EPNM | FCAPS | Completed | Operational | [6 empty] | SmartLicenses issues and wider Cisco Support
82 | IPMPLS | PI | FCAPS | Completed | Operational
83 | IPMPLS | NTP | Network Timing Servers | Completed | Operational
84 | DWDM | MCP | FCAPS | Completed | Operational
85 | GPON-Tejas | EMS | FCAPS | Completed | Operational
86 | GPON-Nokia | AMS | FCAPS | Completed | Operational
87 | Security | FMC | Fire wall manager | Completed | Operational
88 | Security | ISE | AAA | Completed | Operational
89 | Security | Alepo | AAA | Completed | Operational | Integration with AD
90 | DC-IT | Commvault | Backup | Completed | Operational
91 | DC-IT | Syslog | Systems syslog | Completed | Operational
92 | DC-IT | Active Directory | Active Directory | Completed | Operational
93 | DR | Applications | All applications readiness | Completed
94 | DR | Network | Design, Installation | Completed | Operational
95 | DR | Failover Tests | Each Application wise | WIP | [5 empty] | Tejas, Nokia, GIS, DWDM, IPDR Applictions Testing Completed. Testing is pending for EPNM, PI, AAA, ISE, OSS, BSS, NSO. | Cisco EPNM
96 | DR | DR Drill |  | Pending |  |  |  | Planned Part1 | Planned Part2 | To be planned |  | SME's to be initiated
[5 empty] | 199 | 15 | 18 | 25 | 125 | 16

## Data Val (hidden)
BSS | T0-T6 |  | Alepo/AAA
OSS |  |  | BSS
A&O Solution | Completed | Completed | DC IT- Infra
GIS | WIP | Completed but approval awaited | DR
WFM |  | WIP | DWDM
IPMPLS |  | Dependency | GIS
DWDM |  |  | GPON
GPON-Tejas |  |  | IPMPLS
GPON-Nokia |  |  | NSO
Security |  |  | OSS
DC-IT |  |  | OSS Dashboards
DR |  |  | Security
TNOC-Ops |  |  | TNOC
Service Design
DC-Network Infra
Cisco

## SUM (hidden)
Weekly Progress tracker
[7 empty] | W1-Plan | W1-Achived | W2 | W2-Achived | W3 | W3-Achived | W4 | W4-Achived | W5 | W5-Achived
SME-Ownership | [5 empty] | WIP Points | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Jayant Madhavi | [5 empty] | #REF! | 0 |  | 0 |  | 0 |  | 0 |  | 0
Manoj | [5 empty] | #REF! | 0 |  | 0 |  | 0 |  | 0 |  | 0
Ravikishor | [5 empty] | #REF! | 0 |  | 0 |  | 0 |  | 0 |  | 0
Ravikishor | [5 empty] | #REF! | 0 |  | 0 |  | 0 |  | 0 |  | 0
Suresh T | [5 empty] | #REF! | 0 |  | 0 |  | 0 |  | 0 |  | 0
Kaushal | [5 empty] | #REF! | 0 |  | 0 |  | 0 |  | 0 |  | 0
Sayed | [5 empty] | #REF! | 0 |  | 0 |  | 0 |  | 0 |  | 0
Sayed | [5 empty] | #REF! | 0 |  | 0 |  | 0 |  | 0 |  | 0
RS rao | [5 empty] | #REF! | 0 |  | 0 |  | 0 |  | 0 |  | 0
Suresh K | [5 empty] | #REF! | 0 |  | 0 |  | 0 |  | 0 |  | 0
Samrendra | [5 empty] | #REF! | 0 |  | 0 |  | 0 |  | 0 |  | 0
Ahmad | [5 empty] | #REF! | 0 |  | 0 |  | 0 |  | 0 |  | 0
[6 empty] | #REF! | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Row Labels | Count of Functionality |  | CRD |  | HLD/SD |  | LLD |  | FAT |  | Testing & Commisioning
SME-Ownership | A&O Solution | 13 |  | Submission status | Approval Status | Submission status | Approval Status | Submission status | Approval Status | Submission status | Approval Status | Submission status | Approval Status
Jayant Madhavi | BSS | 9
Manoj | DC-IT | 3
Ravikishor | DR | 3
Ravikishor | DWDM | 1
Suresh T | GIS | 19
Kaushal | GPON-Nokia | 1 | Go Live
Sayed | GPON-Tejas | 1
Sayed | IPMPLS | 3
RS rao | OSS | 40
Suresh K | Security | 3
Samrendra | WFM | 7
Kaushal | Grand Total | 103
Support required.
1
2
3
4

## 472
Slno | UniqueID | Category | Domain | Sub-Domain | Action Point | Remarks | 2025-12-11 | Owner(L&T) | Target Date | Revised Status (L&T) As on 18-Sep-2025 | T Fiber Appoved Date | Artefacts | Ramana-Remarks | Updated on 01-Dec-2025 | 2025-10-13 | Remarks(1399) | Final Remarks(27-Dec-25)
1 | T1 | 472 | Security & Regulatory Compliance | Configuration | Integration testing of All supported devices is complete and adding all the devices is underway. | what ever request has come all are integrated with ISE , any new device request comes same will be added . Also Aleppo PO get relaesed for ADintegration , it will also get integrated with AD. |  | Bajiba Shaik |  | COMPLETED & APPROVED | 2025-11-12 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\NW-Security\T1_01-Nov-25.pdf | Completed & Approved | Closed after 07-Nov-25 | Open |  | Completed & Approved
2 | T2 | 472 | DWDM | Integration with Alepo | RADIUS Configuration Testing on Ciena Node & EMS (MCP) |  |  | Suresh Kumar |  | COMPLETED & APPROVED | 2025-05-06 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\DWDM\Artefact - T106 | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
3 | T3 | 472 | Security & Regulatory Compliance | Integration | Accouting data from Ciena MCP and field nodes to be captured in Alepo AAA | 28-Nov-25: The Alepo team is integrating AD Once done these points will be closed. MCP upgradation is in pipeline . same will be completed by 25 Sep 2025 |  | Bajiba Shaik |  | WIP |  |  | Open | Open | Open |  | Open
4 | T3 | 472 | DWDM | Integration with Alepo | TACACS+/Radius testing for AAA on ciena node | 28-Nov-25: The Alepo team is integrating AD Once done these points will be closed. 20-09-2025: 8.1 MCP software Patch upgradation will be completed by 27-Sep-25, After completetion of upgrdation AAA functionalities will be tested for ciena devices by using radius 13-09-25:MCP upgradation is in progress, will be able to check the logs by next week 28-08-2025: Activity is in progress, target to complete by 25th Sep'25 Authentication and Authorization tested and found OK for Node and MCP. 19-08-2025: Due to issue in disk partition and file type of storage, activity is not started 10-08-2025: OEM confirmation recieved and activity is planned from 18th August'25. 05-July-2025: DC OSS to DR MCP communication is through now, need to integrate and test before activity 12-July-2025: DC OSS to DR MCP integration testing done. Alarms and Autoticketing functioning as expected. Upgradation activity will be scheduled as per OEM confirmation, Target date - 30-07-25 26-July-2025: Schedule awaited from OEM 30-June-2025: DC OSS to DR MCP connectivity to be extended for PE approval, WIP. Target date - 30-07-25 15-06-25: Targeting to close the upgradation by month end, 30-06-25 30-05-2025: Accounting issue resolved in latest MCP version, verified in 8.2 Ver (Node logs are now capturing in MCP). Upgradation schedule awaited from Teleindia for our MCP from 7.1-P02 5/21/2025: Correlation to identified to find the user logged in at the specific time 28APR'25: As discussed with Sanjay sir, if user id not avaialble pls. try for correlation with IP. Some how Correlation to be done. In Accounting, Node and MCP logs are successfully reporting in Alepo with below limitation. Node Logs - Active profile name (ADMIN/RADIUS) is displayed against User ID (Ciena confirmed it is as per design no changes are possible) |  | Suresh Kumar |  | WIP |  |  | Open | Open | Open |  | Open
5 | T4 | 472 | Security & Regulatory Compliance | Security | Alepo confirmed that Alepo AAA supports TACACS, Alepo to test Nokia and Ciena nodes integration on TACACS , with supporting artefacts of testing. 1.TACACS Testing with Tejas, Nokia, Ciena 2. Alepo Testing with Tejas, Nokia and Ciena | 28-Nov-25: The Alepo team is integrating AD Once done these points will be closed. 1.TACACS Testing with Tejas, Nokia, Ciena completed 2. Alepo Testing with Tejas, Nokia and Ciena |  | Bajiba Shaik |  | CLOSURE REVIEW PENDING |  | Artefacts to be Submitted | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process |  | Closure Review Pending
6 | T5 | 472 | Security & Regulatory Compliance | Functional AT | Had a meeting with Ashwani from Alepo and sent him updated test cases. He is working on data gathering and will send us back by Tuesday. | FAT were submitted to customer, Customer observation in being work out. Target to resubmission.- 23.07.25 |  | Bajiba Shaik |  | COMPLETED & APPROVED | 2025-10-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\NW-Security\T5_29-Oct-25.pdf | Closed | Closed After 14-Oct | Completed but Verification undrer Process |  | Completed & Approved
7 | T6 | 472 | BSS | Installation | Installation of BSS Application | 29-08-2025: Design and Solution document to be shared with GM NOC and Physical instllation of BSS need to validate according to solution from L&T Side before submitting for for review with T Fiber 26-06-2025: We have offered Installation AT. TFIBER has asked DC architecture review including license validity |  | Sandeep Deshmukh |  | CLOSURE REVIEW PENDING |  |  | Open | Open | Open |  | Closure Review Pending
8 | T7 | 472 | BSS | Integration | Initial Integration with Third Party Applications (OSS & NSO) | 26-06-2025: OSS Integration is done. NSO integration is pending. Awaiting NSO Team. |  | Sandeep Deshmukh |  | Open |  |  | Open | Open | Open |  | Open
9 | T8 | 472 | BSS | Integration | OSS interfaces | 26-06-2025: Feasibility API & Ticket API integration is completed. |  | Sandeep Deshmukh |  | Open |  |  | Open | Open | Open |  | Open
10 | T9 | 472 | BSS | Integration | NSO interfaces | 26-06-2025: Awaiting NSO Team |  | Sandeep Deshmukh |  | Open |  |  | Open | Open | Open |  | Open
11 | T10 | 472 | BSS | Integration | GeM Portal |  |  | Sandeep Deshmukh |  | Open | 2025-07-16 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\BSS\Artifact_T10 | Open | Open | Open |  | Open
12 | T11 | 472 | BSS | Development and unit testing | Import Sub-Departments, Import Leads, Campaign Management, Opportunity/Quote/order Management, order booking and Service Order workflow for tested services | 29-08-2025: All points are completed Import Sub-Departments, Import Leads, Opportunity/Quote/order Management, order booking and Service Order workflow for tested services Demo to be conducted to TFIBER. "Campaign Management" is Pending where inputs are required from TFIBER Business team 26-06-2025: Awaiting few inputs from TFIBER |  | Sandeep Deshmukh |  | Open |  |  | Open | Open | Open |  | Open
13 | T12 | 472 | BSS | Development and unit testing | Product/Service Catalogue integration | 29-08-2025: Feature is available to admin User(Product Team) to configure new product based on requirement. BSS Team will provide Demo to the TFIBER (business team([Uday]/Solution Team[Sanjay]) for their acceptance. 26-06-2025: Artifacts submitted. Closure review is pending with TFIBER |  | Sandeep Deshmukh |  | CLOSURE REVIEW PENDING |  |  | Open | Open | Open |  | Closure Review Pending
14 | T13 | 472 | BSS | Development and unit testing | Billing, Discounts & Adjustments, Invoice generation, Bill Formatting | 29-08-2025: Feature is made available in the BSS application, BSS Team will provide demo to TFIBER Team (Business [Uday] & Finance[Bhaskar]) 26-06-2025: Artifacts submitted. Closure review is pending with TFIBER |  | Sandeep Deshmukh |  | CLOSURE REVIEW PENDING |  |  | Open | Open | Open |  | Closure Review Pending
15 | T14 | 472 | BSS | Development and unit testing | Feasibility API response from OSS for service provisioning request | 29-08-2025: Feaibility API is already integrated with BSS and demonstrated in GIBB demo and it is applicable for all products. 26-06-2025: Artifacts submitted. Closure review is pending with TFIBER |  | Sandeep Deshmukh |  | CLOSURE REVIEW PENDING |  |  | Open | Open | Open |  | Closure Review Pending
16 | T15 | 472 | BSS | Development and unit testing | SMS notification, email gateway, Field engineer mobile app readiness | 29-08-2025: Integration is already completed and applicable for all product same has demonstrated to TFIBER during GIBB demo session. 26-06-2025: Artifacts submitted. Closure review is pending with TFIBER |  | Sandeep Deshmukh |  | Open |  |  | Open | Open | Open |  | Open
17 | T16 | 472 | BSS | Development and unit testing | Service Assurance and trouble tickets | 29-08-2025: Integration with Service Manager is done for technical ticket and BSS have functionality to handle the non-technical ticket in BSS itself. BSS team will demonstrate this functionality to TFIBER. Sanjay Sir needs to confirm demo date. 26-06-2025: Artifacts submitted. Closure review is pending with TFIBER |  | Sandeep Deshmukh |  | CLOSURE REVIEW PENDING |  |  | Open | Open | Open |  | Closure Review Pending
18 | T17 | 472 | BSS | Development and unit testing | Customer Self care portal development for T-CELL, T-NET, L0 | 29-08-2025: Webportal is available. BSS team needs to demonstrate to TFIBER team. Sanjay Sir needs to confirm demo date. 26-06-2025: Artifacts submitted. Closure review is pending with TFIBER |  | Sandeep Deshmukh |  | Open |  |  | Open | Open | Open |  | Open
19 | T18 | 472 | BSS | Integration | Integration modules Like on board Un-Assist & dependent module to be completed for all products from system to be initiated a workshop and to be closed in next 2 Weeks | 29-08-2025: Seek input from Business team (Uday) and deploy post assisted completion. 26-06-2025: Input awaited from TFIBER |  | Sandeep Deshmukh |  | Open |  |  | Open | Open | Open |  | Open
20 | T19 | 472 | BSS | MoM Action | T-Cell service definition for workflow implementation in BSS for creating Spoke primary and secondary | 29-08-2025:Update product concept note similar to GIBB and share with TFIBER for review 26-06-2025: We can deliver this post getting product concept note from TFIBER |  | Sandeep Deshmukh |  | Open |  |  | Open | Open | Open |  | Open
21 | T20 | 472 | BSS | Development and unit testing | Rules for primary and secondary spoke implementation in BSS- - GP with shortest distance will be primary - To display dropdown and concerned user group to select and confirm | #N/A |  | Sandeep Deshmukh |  | Open |  |  | Open | Open | Open |  | Open
22 | T21 | 472 | BSS | MoM Action | BSS firewall ports required for Security compliance | BSS has to forward list of Port as per deiffrent modules of application |  | Bajiba Shaik |  | COMPLETED & APPROVED | 2025-11-01 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\NW-Security\T21_31-Oct-25.pdf | Closed | Closed After 14-Oct | Open |  | Completed & Approved
23 | T22 | 472 | BSS | Security | Roadmap for password policy implementation in CSP | Ciriteria for Paswword policy hase been Shared wioth BSS team . BSS team has to implement and submit report for verifications. 30-Oct-25: Ciriteria for Paswword policy hase been Shared wioth BSS team . BSS team has to implement and submit report for verifications. Point to be moved to BSS |  | Bajiba Shaik |  | WIP |  |  | Open | Open | Open |  | Open
24 | T23 | 472 | BSS | Security | DMZ requirements for CSP | IP amd URL required by BSS foir NAT through DMZ has been Completed |  | Bajiba Shaik |  | COMPLETED & APPROVED | 2025-11-01 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\NW-Security\T23_31-Oct-25.pdf | Closed | Closed After 14-Oct | Open |  | Completed & Approved
25 | T24 | 472 | BSS | MoM Action | PoP location confirmation usergroup for connectivity to O&M | 29-08-2025: Seek input from O&M team (Umesh) 26-06-2025: Input awaited from TFIBER |  | Sandeep Deshmukh |  | Open |  |  | Open | Open | Open |  | Open
26 | T25 | 472 | BSS | MoM Action | Product concept note configuration in BSS queries to be shared | 29-08-2025: Queries to be prepared and share with TFIBER for discussion. 17-07-2025: Business Team of TFIBER needs to finalize and confirm all product. 26-06-2025: Need Product concept note from TFIBER |  | Sandeep Deshmukh |  | Open |  |  | Open | Open | Open |  | Open
27 | T26 | 472 | BSS | MoM Action | Location id logic for NSO provisioning | 29-08-2025: Ciruit ID logic PPT shared by Sivakumar, needs to use and implement in BSS. 26-06-2025: Timeline 30th July is considering NSO support is available in 2-3 days |  | Sandeep Deshmukh |  | Open |  |  | Open | Open | Open |  | Open
28 | T27 | 472 | BSS | Integration | Tariff plan parameters viz. 5G, 4G finalisation. (BSS should capture QOS parameter & Requirements) | 29-08-2025: Product Can be configured in BSS product catalogue Demo to be given to TFIBER 26-06-2025: Input awaited from TFIBER |  | Sandeep Deshmukh |  | Open |  |  | Open | Open | Open |  | Open
29 | T28 | 472 | IP/MPLS | Functional AT | Internal AT 83% complete. Waiting Cisco to update data sent by Vikram and then we will submit to TPA ( for pending cases, we just need a maintanence window to test as it is impacting activity) This is for ISE | 28-Nov-25: Document preparation in progress once done points will be closed. FAT documents were submitted to TPA , However it has some common observation which will be discussed with TPA team by Mr Sharma. Subsequently , correction will be made in FAT doc |  | Bajiba Shaik |  | WIP |  |  | Open | Open | Open |  | Open
30 | T29 | 472 | IP/MPLS | Functional AT | CSM is having memory issues. Need to sort it out before we do AT. Working on settling that with Cisco. Memory will be allocated and tested in the first week of July | CSM has been replaced by ASDM |  | Bajiba Shaik |  | COMPLETED & APPROVED | 2025-10-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\NW-Security\M1145_29-Oct-25.pdf | Closed | Closed After 14-Oct | Open |  | Completed & Approved
31 | T30 | 472 | IP/MPLS | Functional AT | Internal AT 72% complete. Waiting on Cisco to update data sent by Vikram and then we will submit to TPA. ( for pending cases, we just need a maintanence window to test as it is impacting activity) | 28-Nov-25: Document preparation in progress once done points will be closed. FAT documents were submitted to TPA , However it has some common observation which will be discussed with TPA team by Mr Sharma. Subsequently , correction will be made in FAT doc |  | Bajiba Shaik |  | WIP |  |  | Open | Open | Open |  | Open
32 | T31 | 472 | Security & Regulatory Compliance | Security | Internal Audit for all applications | 28-Nov-25: VAPT is going on, once VAPT is done points will be closed. Application audited partally , howver PT audit couldnot be done due to lack of necessary tools. Same has been requested with LTTS team , but it could not be materialised. |  | Bajiba Shaik |  | WIP |  |  | Open | Open | Open |  | Open
33 | T32 | 472 | Security & Regulatory Compliance | Security | Internal audit for network elements | 28-Nov-25: VAPT is going on, once VAPT is done points will be closed. Network elemants auditted including NOC end points , However PT for same is pending. |  | Bajiba Shaik |  | WIP |  |  | Open | Open | Open |  | Open
34 | T33 | 472 | BSS | Security | Security policies to evolve related to DOT/CDOT etc | 29-08-2025: Collect data from Sivakumar and read user to access the data by DOT. 26-06-2025: Waiting for inputs for multiple deliverables |  | Sandeep Deshmukh |  | Open |  |  | Open | Open | Open |  | Open
35 | T34 | 472 | IP/MPLS | Security | external Audit for all applications (Tfiber will be arranging a partner for third party audit) | 28-Nov-25: VAPT is going on, once VAPT is done points will be closed. Awaited TSTG Audit party to engage. |  | Bajiba Shaik |  | DEPENDENCY(Client/Ext.) | 2025-12-19 |  | Open | Open | Open |  | Completed & Approved
36 | T35 | 472 | IP/MPLS | Security | external audit for network elements(Tfiber will be arranging a partner for third party audit) | 28-Nov-25: VAPT is going on, once VAPT is done points will be closed. Awaited TSTG Audit party to engage |  | Bajiba Shaik |  | DEPENDENCY(Client/Ext.) | 2025-12-19 |  | Open | Open | Open |  | Completed & Approved
37 | T36 | 472 | Security & Regulatory Compliance | Security | Physical user access | Has completed , Artefacts will be resubmitted. |  | Bajiba Shaik |  | COMPLETED & APPROVED | 2025-10-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\NW-Security\T36_28-Oct-25.pdf | Closed | Closed After 14-Oct | Open |  | Completed & Approved
38 | T37 | 472 | Security & Regulatory Compliance | Security | Virtual user access-VPN | Has completed , Artefacts will be resubmitted. |  | Bajiba Shaik |  | COMPLETED & APPROVED | 2025-10-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\NW-Security\T37_28-Oct-25.pdf | Closed | Closed After 14-Oct | Open |  | Completed & Approved
39 | T38 | 472 | Security & Regulatory Compliance | Security | Role based severity access | 28-Nov-25: Work in Progress. Completed and Review pending. Artfacts submitted |  | Bajiba Shaik |  | WIP |  |  | Open | Open | Open |  | Open
40 | T39 | 472 | Security & Regulatory Compliance | Security | ISE integration with Cisco elements | 28-Nov-25: Work in Progress. Artefacts will be submitted. |  | Bajiba Shaik |  | CLOSURE REVIEW PENDING |  | Artefacts to be Submitted | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process |  | Closure Review Pending
41 | T40 | 472 | Security & Regulatory Compliance | Regulatory | Regulatory Compliance with respect DoT policies 1. Security Policy-Complied 2. Security Architecture of Telecom Network-Complied 3. Information Security Risk Assessment and Risk Treatment processes and their implementation plan-WIP, Target: Dec 2024 reviewed with customer. 4. Recruitment processes and employee's record-WIP, Target:12-10-2025 5. Controls for effectiveness of security management-WIP, Target: 28 -02-2025 6. Evidence of monitoring, measurement results and management reviews of security management-WIP, Target: 28-02-2025 7. Security Audit programs and audit results-Complied 8. Inventory management and classification of information assets and their handling Completed 9. Procedure for responding to information and network security incidents-WIP, Target: 28-02-2025 - SIRT reviewed 10. Main S/W updation and changes-WIP, Target: 28-02-2025 11. Supply chain of products (HW/SW). To be taken from manufacturer/supplier-Communicated to Sekhar. WIP, Target: 14-02-2025 12. SW details and documentation obtained from manufacturers/supplier-Communicated to Sekhar WIP, Target: 14-02-2025 13. O&M procedures in the form of manual-O&M manual and OEM wise manuals WIP, Target: 14-02-2025 14. Processes for internal and external communication relevant to the security management-WIP, Target: 07-3-2025 | 28-Nov-25: Document preparation in progress once done points will be closed. Confirmation of purchase of ISE. License needed to upgrade for HA |  | Bajiba Shaik |  | DEPENDENCY(Client/Ext.) |  |  | Open | Open | Open |  | Open
42 | T41 | 472 | DC-IT | Servers and Strorage (Deployment and Installations) | 1. Compute & Storage | 11-Oct-25: As per the OEM's/SME's request, storage is allocated as per requirements. Artifacts are Captured. OEM Confirmation Emails to be captured as a Reference. |  | Ravi Kishore |  | REOPENED |  |  | Open | Open | Open |  | Open
43 | T42 | 472 | DC-IT | Servers and Strorage (Deployment and Installations) | 2. Virtulization |  |  | Ravi Kishore |  | COMPLETED & APPROVED | 2025-05-14 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\DC IT-Infra\Artifact for -T42 | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
44 | T43 | 472 | DC-IT | Servers and Strorage (Deployment and Installations) | 3. Anti-virus |  |  | Ravi Kishore |  | COMPLETED & APPROVED | 2025-05-14 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\DC IT-Infra\Artifact for -T43 | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
45 | T44 | 472 | DC-IT | Servers and Strorage (Deployment and Installations) | 4. VM's Deployment Application Installations |  |  | Ravi Kishore |  | COMPLETED & APPROVED | 2025-05-14 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\DC IT-Infra\Artifact for -T44 | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
46 | T45 | 472 | DC-IT | Commvault Backup | Application Installation |  |  | Ravi Kishore |  | COMPLETED & APPROVED | 2025-05-14 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\DC IT-Infra\Artifact for - T45 | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
47 | T46 | 472 | DC-IT | Commvault Backup | Application Configuration |  |  | Ravi Kishore |  | COMPLETED & APPROVED | 2025-05-14 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\DC IT-Infra\Artifact for - T46 | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
48 | T47 | 472 | DC-IT | Commvault Backup | Application Installation AT |  |  | Ravi Kishore |  | COMPLETED & APPROVED | 2025-05-14 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\DC IT-Infra\Artifact for - T47 | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
49 | T48 | 472 | DC-IT | Commvault Backup | Application Functional AT | Working on the Extra Test cases which are received from the TPA & T-Fiber. |  | Ravi Kishore |  | WIP |  |  | Open | Open | Open |  | Open
50 | T49 | 472 | DC-IT | LLD | LLD Approved conditionally with few punch points. Updated LLD to be submitted | Working on DC IT-Infra Server and storage-MoM Points received from the T-Fiber. |  | Ravi Kishore |  | WIP |  |  | Open | Open | Open |  | Closure Review Pending
51 | T50 | 472 | DC-IT | MoM Action | Radware , A10 Configuration file needed to be shared to RaviKishore | Artfacts submitted . point Closure on 10 Jul 25 |  | Bajiba Shaik |  | COMPLETED & APPROVED |  | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\NW-Security\T50 | Completed & Approved | Closed before june-2025 | Closed after June |  | Completed & Approved
52 | T51 | 472 | DC-IT | Commvault Backup | Backup retention and Backup activity (such as when incremental backup,full backup are scheduled and time duration required to complete such backup). Application Wise Backup Retention should be as per DOT Guidelines |  |  | Ravi Kishore |  | COMPLETED & APPROVED | 2025-05-14 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\DC IT-Infra\Artifact for - T51 | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
53 | T52 | 472 | DC-IT | Commvault Backup | Backup solution should have hot , cold and archieve storage inorder to decrease the backup size/capacity in long run. |  |  | Ravi Kishore |  | COMPLETED & APPROVED | 2025-05-14 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\DC IT-Infra\Artifact for - T52 | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
54 | T53 | 472 | DC-IT | SSD storage migration – EPNM/PI | EPNM/PI VMs migration to SSD Storage |  |  | Ravi Kishore |  | COMPLETED & APPROVED | 2025-05-14 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\DC IT-Infra\Artifact for - T53 | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
55 | T54 | 472 | DC-IT | SSD storage migration – ISE/FMC | ISE & FMC VMs migration to SSD Storage |  |  | Ravi Kishore |  | COMPLETED & APPROVED | 2025-05-14 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\DC IT-Infra\Artifact for - T54 | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
56 | T55 | 472 | DC-IT | MoM Action | VM Placing should be verified & rectified, Same service VM needs to be placed in different Physical Server/host. |  |  | Ravi Kishore |  | COMPLETED & APPROVED | 2025-05-14 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\DC IT-Infra\Artifact for - T55 | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
57 | T56 | 472 | DC-IT | MoM Action | SOP documents needs to be provided | SOP documents submitted to Operations team. Remaining pending documents to be prepared periodically. |  | Ravi Kishore |  | REOPENED |  |  | Open | Open | Open |  | Open
58 | T57 | 472 | DC-IT | LLD | Approved conditionally with few punch points. Updated LLD to be submitted | 14-Aug-25 : Discussion was done with TPA and Tfiber and submitted updated LLD document. 18-Jun-25 : Updated DC Network LLD submitted on 18-Jun-25 for TFiber review |  | RS Rao |  | COMPLETED & APPROVED | 2025-08-14 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\DC Network LLD V1.7 14-Aug-2025.pdf | Completed & Approved | Closed before june-2025 | Closed after June |  | Completed & Approved
59 | T58 | 472 | DC-IT | Cisco EPNM | Cisco EPNM infrastructure AT | 22-Sep-25: IPMPLS Domain team to submit detailed remarks on raised queries. 08-Jul-2025 - Sandeep will come back by EoD today on extension of Cisco support renewal 01-Jul-25 : Revised FAT documents submission pending (TPA observations to be included) OEM(Cisco) suport is required to show the new test cases, Inputs provided to OEM on 14th May & 30th Jun. OEM onboarding is in progress & LnT Contracts team coordinating |  | RS Rao |  | Open |  |  | Open | Open | Open |  | Closure Review Pending
60 | T59 | 472 | DC-IT | Cisco PI | Cisco prime infrastructure AT | 22-Sep-25: IPMPLS Domain team to submit detailed remarks on raised queries. 08-Jul-2025 - Sandeep will come back by EoD today on extension of Cisco support renewal 01-Jul-25 : Revised FAT documents submission pending (TPA observations to be included) OEM(Cisco) suport is required to show the new test cases, Inputs provided to OEM on 14th May & 30th Jun. OEM onboarding is in progress & LnT Contracts team is coordinating |  | RS Rao |  | Open |  |  | Open | Open | Open |  | Closure Review Pending
61 | T60 | 472 | DC-IT | NTP | Installation |  |  | RS Rao |  | COMPLETED & APPROVED | 2025-05-05 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\Primary NTP - T60,T61,T62.pdf \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\Secondary NTP - T60,T61,T62.pdf | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
62 | T61 | 472 | DC-IT | NTP | Configuration |  |  | RS Rao |  | COMPLETED & APPROVED | 2025-05-05 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\Primary NTP - T60,T61,T62.pdf \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\Secondary NTP - T60,T61,T62.pdf | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
63 | T62 | 472 | DC-IT | NTP | NTP Installation AT |  |  | RS Rao |  | COMPLETED & APPROVED | 2025-05-05 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\Primary NTP - T60,T61,T62.pdf \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\Secondary NTP - T60,T61,T62.pdf | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
64 | T63 | 472 | DC-IT | NTP | NTP Functional AT |  |  | RS Rao |  | COMPLETED & APPROVED | 2025-07-03 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\NTP FAT & Acceptance - T63.pdf | Completed & Approved | Closed before june-2025 | Closed after June |  | Completed & Approved
65 | T64 | 472 | DC-IT | Functional AT | DC Network Infra AT | 22-Sep-25: IPMPLS Domain team to submit detailed remarks on raised queries. 08-Jul-2025 - Sandeep will come back by EoD today on extension of Cisco support renewal 01-Jul-25 : Revised FAT documents submission pending (TPA observations to be included) OEM(Cisco) suport is required to show the new test cases, Inputs provided to OEM on 14th May & 30th Jun. OEM onboarding is in progress & LnT Contracts team is coordinating |  | RS Rao |  | Open |  |  | Open | Open | Open |  | Closure Review Pending
66 | T65 | 472 | DR | Servers and Strorage (Deployment and Installations) | Virtulization |  |  | Ravi Kishore |  | COMPLETED & APPROVED | 2025-05-14 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\DR\Artifact for - T65 | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
67 | T66 | 472 | DR | DC (TNOC-DR) | Network Readiness |  |  | Ravi Kishore |  | COMPLETED & APPROVED | 2025-05-14 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\DR\Artifact for - T66 | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
68 | T67 | 472 | DR | Mahbubnagar-DR | Network Readiness |  |  | Ravi Kishore |  | COMPLETED & APPROVED | 2025-05-14 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\DR\Artifact for - T66 | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
69 | T68 | 472 | DR | Design & Documentation | LLD: Approved conditionally with few punch points. Updated LLD to be submitted | Working on additional points shared by Tfiber. |  | Ravi Kishore |  | WIP |  |  | Open | Open | Open |  | Open
70 | T69 | 472 | DR | Design & Documentation | HLD: Revised solution to submitted | Working on additional points shared by Tfiber. |  | Ravi Kishore |  | WIP |  |  | Open | Open | Open |  | Open
71 | T70 | 472 | DR | Design & Documentation | DC-DR redunancy Test |  |  | Ravi Kishore |  | COMPLETED & APPROVED | 2025-05-14 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\DR\Artifact for - T70 | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
72 | T71 | 472 | DR | MoM Action | UTM Features (DR FW) | Meeting scheduled with CTRL S to verify the UTM features 30-Oct-25: Duplicate to Point T71. DR does not have a public-facing application, and DR and DC firewalls are different |  | Bajiba Shaik |  | COMPLETED & APPROVED | 2025-11-01 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\NW-Security\T71_31-Oct-25.pdf | Completed & Approved | Closed After 14-Oct | Open |  | Completed & Approved
73 | T72 | 472 | DR | MoM Action | To configure LACP between L3 Switch and Core Router | 11-Oct-25: CtrlS has to give proposal for procurement for addtional BoQ. IT infra SME need to Re-intiate a mail to get BoQ 22-Sep-25: The existing switch which was placed at DR by CtrlS doesnt have feature on LACP Bundling. CtrlS is planning to relplace the exising switch with LACP supported switch. DC Infra admin need to provide tentative timelines for replacement. 08-Jul-2025 Sandeep will ensure on CTRL-S support and update by EoD 01-Jul-25 : Ticket (SR01301726) raised with CtrlS on 27-Jun, Config & testing to be carried out. This is additional task as per CtrlS and commercials may be involved. LnT Contracts team also talking to CtrlS account team to complete the task. 24-Dec-25 : SR01036770 opened with CtrlS for LACP configuration and it is not O&M activity as per CtrlS ops. team. escalated to LnT Contracts team for supoort. |  | Ravi Kishore |  | WIP |  |  | Open | Open | Open |  | Open
74 | T73 | 472 | DR | MoM Action | To configure LACP between Core Router and Firewall | 11-Oct-25: CtrlS has to give proposal for procurement for addtional BoQ. IT infra SME need to Re-intiate a mail to get BoQ 22-Sep-25: The existing switch which was placed at DR by CtrlS doesnt have feature on LACP Bundling. CtrlS is planning to relplace the exising switch with LACP supported switch. DC Infra admin need to provide tentative timelines for replacement. 01-Jul-25 : Ticket (SR01301726) raised with CtrlS on 27-Jun, Config & testing to be carried out. This is additional task as per CtrlS and commercials may be involved. LnT Contracts team also talking to CtrlS account team to complete the task. 24-Dec-25 : SR01036770 opened with CtrlS for LACP configuration and it is not O&M activity as per CtrlS ops. team. escalated to LnT Contracts team for supoort. |  | Ravi Kishore |  | WIP |  |  | Open | Open | Open |  | Open
75 | T74 | 472 | DR | MoM Action | To configure LACP between Firewall and L2 Switch | 11-Oct-25: CtrlS has to give proposal for procurement for addtional BoQ. IT infra SME need to Re-intiate a mail to get BoQ 22-Sep-25: The existing switch which was placed at DR by CtrlS doesnt have feature on LACP Bundling. CtrlS is planning to relplace the exising switch with LACP supported switch. DC Infra admin need to provide tentative timelines for replacement. 01-Jul-25 : Ticket (SR01301726) raised with CtrlS on 27-Jun, Config & testing to be carried out. This is additional task as per CtrlS and commercials may be involved. LnT Contracts team also talking to CtrlS account team to complete the task. 24-Dec-25 : SR01036770 opened with CtrlS for LACP configuration and it is not O&M activity as per CtrlS ops. team. escalated to LnT Contracts team for supoort. |  | Ravi Kishore |  | WIP |  |  | Open | Open | Open |  | Open
76 | T75 | 472 | DR | MoM Action | To confirm on backups for DR Virtual machines |  |  | Ravi Kishore |  | COMPLETED & APPROVED | 2025-05-14 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\DR\Artifact for - T75 | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
77 | T76 | 472 | DR | MoM Action | Backup storage to 25 TB |  |  | Ravi Kishore |  | COMPLETED & APPROVED | 2025-05-14 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\DR\Artifact for - T76 | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
78 | T77 | 472 | DR | MoM Action | To submit the SOPs for DC-DR switchover, DC-DR failover and failback | Tejas, Nokia, GIS & Ciena MCP documnets are received. Remaining all Applications domains SOP's to be updated. |  | Ravi Kishore |  | REOPENED |  |  | Open | Open | Open |  | Open
79 | T78 | 472 | DR | MoM Action | to monitor the DR Servers | DR servers monitoring through DR vCentre happening. DR is maintained by CtrlS team as per contract. Feasibility to be checked to integrated through OSS OBM. |  | Ravi Kishore |  | WIP |  |  | Open | Open | Open |  | Open
80 | T79 | 472 | DR | MoM Action | To confirm that DNS switchover between DC and DR locations should be automatic |  |  | Ravi Kishore |  | COMPLETED & APPROVED | 2025-05-14 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\DR\Artifact for - T79 | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
81 | T80 | 472 | DR | MoM Action | Mahubnagar as NTP |  |  | RS Rao |  | COMPLETED & APPROVED | 2025-05-05 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\Primary NTP - T60,T61,T62.pdf \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\Secondary NTP - T60,T61,T62.pdf | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
82 | T81 | 472 | DR | Configuration | All application to be migrated to implement DR LB configuration | 11-Oct-25: Approved DR HLD document to be shared with T Fiber for further discussion. Noikia app is integrated with DR LB . Balance application migration on DR LB is in Pipeline |  | Ravi Kishore |  | WIP |  |  | Open | Open | Open |  | Open
83 | T82 | 472 | DR | MoM Action | To confirm the applications which support Veem Replication for Reconfiguration |  |  | Ravi Kishore |  | COMPLETED & APPROVED | 2025-05-14 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\DR\Artifact for - T82 | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
84 | T83 | 472 | DWDM | Network Deployment & integration | Zonal Links Integration (12/15) | 20-Sep-25: Nirmal, Jainoor, Gudihatnoor & Bhimni RFE pending due to forest permission 31-July-2025:As per discussion with Ramanaiah sir, need to discuss these points with T Fiber Project team for further action, till that time this point kept on hold Depend on 04 Facilities RFE in Pkg-C Asifabad - Warangal & Karimnagar - Asifabad - Links integrated as per interim plan, actual integration pending Nizamabad - Asifabad - E2E link integration pending 28th-Apr'25: As per Sandeep Sanmani - Forest permission still pending 6/25/2025: Status is same no visibility on forest permission, Target date would be D+21 05-July-25: No progress on the forest permission |  | Suresh Kumar |  | CLOSURE REVIEW PENDING |  |  | Open | Open | Open |  | Closure Review Pending
85 | T84 | 472 | DWDM | Network Deployment & integration | Nodes Live & Operational (67/71) | 31-July-2025:As per discussion with Ramanaiah sir, need to discuss these points with T Fiber Project team for further action, till that time this point kept on hold Nirmal, Jainoor, Gudihatnoor & Bhimni RFE pending due to forest permission 28th-Apr'25: As per Sandeep Sanmani - Forest permission still pending 15-06-25: No progress on the permission, target - D+15 05-July-25: No progress on the forest permission |  | Suresh Kumar |  | CLOSURE REVIEW PENDING |  |  | Open | Open | Open |  | Closure Review Pending
86 | T85 | 472 | DWDM | Network Deployment & integration | Zonal Rings readiness with 1+R protection (5/7) | 31-July-2025:As per discussion with Ramanaiah sir, need to discuss these points with T Fiber Project team for further action, till that time this point kept on hold 02 rings depend on 04 Facilities RFE readiness in Pkg-C, which is pending due to forest permission 28th-Apr'25: As per Sandeep Sanmani - Forest permission still pending 6/25/2025: No visibility on forest permission, target date would be D+30 05-July-25: No progress on the forest permission |  | Suresh Kumar |  | CLOSURE REVIEW PENDING |  |  | Open | Open | Open |  | Closure Review Pending
87 | T86 | 472 | DWDM | Network Deployment & AT Status | Nodal AT (67/71) | 31-July-2025:As per discussion with Ramanaiah sir, need to discuss these points with T Fiber Project team for further action, till that time this point kept on hold Nirmal, Jainoor, Gudihatnoor & Bhimni RFE pending due to forest permission 28th-Apr'25: As per Sandeep Sanmani - Forest permission still pending 15-06-25: No progress on the permission, target - D+15 05-July-25: No progress on the forest permission |  | Suresh Kumar |  | CLOSURE REVIEW PENDING |  |  | Open | Open | Open |  | Closure Review Pending
88 | T87 | 472 | DWDM | Network Deployment & integration | Mandal Ring Integration through OADM | 31-July-2025:As per discussion with Ramanaiah sir, need to discuss these points with T Fiber Project team for further action, till that time this point kept on hold Mandal services are provisioned (10G) as per integration plan by all packages 6/25/2025: 203 services provisioned out of 270 planned. Remaining can be provisioned as per the requirement |  | Suresh Kumar |  | CLOSURE REVIEW PENDING |  |  | Open | Open | Open |  | Closure Review Pending
89 | T88 | 472 | DWDM | Network Deployment & AT Status | Zonal Link AT (7/15) | 31-July-2025:As per discussion with Ramanaiah sir, need to discuss these points with T Fiber Project team for further action, till that time this point kept on hold 04 Link AT's approved by T Fiber and 03 Link AT's pending due to letter from Ciena awaited (No impact due to ILA to OADM upgradation) 05 Link AT pending due to high losses in the spans, depend on all packages 02 Links integrated as per interim plan, so not considered for Link AT 20May'25: Declaration letter submitted to T Fiber for 03 links AT approval 25-06-2025: Dependancy on field, no progress. 30-June-2025: As discussed in the meeting, need to arrange meeting with all stakeholders |  | Suresh Kumar |  | CLOSURE REVIEW PENDING |  |  | Open | Open | Open |  | Closure Review Pending
90 | T89 | 472 | DWDM | Design & Documentation | HLD (Revised) with OADM Solution |  |  | Suresh Kumar |  | COMPLETED & APPROVED | 2025-05-06 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\DWDM\Artefact - T89 | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
91 | T90 | 472 | DWDM | Design & Documentation | LLD (Revised) with OADM Solution (Ciena) |  |  | Suresh Kumar |  | COMPLETED & APPROVED | 2025-05-06 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\DWDM\Artefact - T90 | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
92 | T91 | 472 | DWDM | Design & Documentation | Nodal ATP |  |  | Suresh Kumar |  | COMPLETED & APPROVED | 2025-05-06 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\DWDM\Artefact - T91 & T92 | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
93 | T92 | 472 | DWDM | Design & Documentation | Link ATP |  |  | Suresh Kumar |  | COMPLETED & APPROVED | 2025-05-06 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\DWDM\Artefact - T91 & T92 | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
94 | T93 | 472 | DWDM | Design & Documentation | Ring ATP |  |  | Suresh Kumar |  | COMPLETED & APPROVED | 2025-05-06 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\DWDM\Artefact - T93 | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
95 | T94 | 472 | DWDM | Design & Documentation | DWDM EMS (MCP) Functional ATP | 20-Sep-25: MCP FAT document submitted to TPA on XX-XX-XXXX. Meeting need to be scheduled on 22-Sep-25 with TPA to get the clarifications on delay. 13-Sep-25: Response awaited from TPA team 29-August-2025: Spoken with Mr. Bijju, response awaited 26-July-25: FAT document approval pending 08-July-2025: 1. MCP FAT document prepared as per RFP requirements and TPA remarks 2. 100G traffic throughput will be shown during Ring ATP 07-July-2025: 1. SME not aware of MCP FAT Check list, but prepared FAT document and sent to TPA for validation 05-July-2025: Submitted AT document to T Fiber TPA 30-June-2025: target to submit by 2nd July'25, based on OEM reply Revised version to be submitted as per T Fiber remarks on 29th Apr'25 |  | Suresh Kumar |  | CLOSURE REVIEW PENDING |  |  | Open | Open | Open |  | Closure Review Pending
96 | T95 | 472 | DWDM | Integration with OSS | DWDM Network Alarms Integration |  |  | Suresh Kumar |  | COMPLETED & APPROVED | 2025-05-06 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\DWDM\Artefact - T95 | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
97 | T96 | 472 | DWDM | Integration with OSS | Hardware Inventory Integration in HPE OSS |  |  | Suresh Kumar |  | COMPLETED & APPROVED | 2025-05-06 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\DWDM\Artefact - T96 | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
98 | T97 | 472 | DWDM | Integration with OSS | DWDM Network Topology | 11-Nov-25: 26-July-2025: HPE conveyed that Topology border unable to make bold or hilight 12-July-2025: Update awaited from HPE 07-July-2025: Topology is visible but border is not highlighted. HP checking for the possibility to impose of border map on topology. Required 02 weeks post confirmation 05-July-2025: In discussion with HPE, required 02 weeks post confirmation, 21st July 30-June-2025: As discussed with Suresh P checking with HPE. Tentative date: 16th July. As discussed in the meeting, call to be arranged along with OSS SME and HP team |  | Venkatesh |  | CLOSURE REVIEW PENDING |  |  | Open | Open | Open |  | Closure Review Pending
99 | T98 | 472 | DWDM | Integration with OSS | Auto Ticket & RCA for Fiber Cuts |  |  | Suresh Kumar |  | COMPLETED & APPROVED | 2025-05-06 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\DWDM\Artefact - T98 | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
100 | T99 | 472 | DWDM | Integration with OSS | Auto Ticket & RCA for Hardware Failures |  |  | Suresh Kumar |  | COMPLETED & APPROVED |  | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\DWDM\Artefact - T99 | Completed & Approved | Closed before june-2025 | Closed after June |  | Completed & Approved
101 | T100 | 472 | DWDM | Integration with OSS | Auto Ticket & RCA for Infra Failures | 20-Sep-25: Required configuration changes was done by HPE team. DWDM team will validate and confirm by 23-Sep-25 13-09-25: Few issues observed, corrected by HP. Validation is in progress 10-08-2025: HP team confirmed cause of failure updated, validation is in progress 26-July-2025: Raised the concerns to HP team, cause of failure yet to update by them, Target date awaited9 12-July-2025: Configuration updated in production and RCA TT's for node down are generating. But having issue in cause of failure, same informed to HP team. Target date - 18-07-25 05-July-2025: Cofiguration in production planned on 8th July'25 30-June-25: WIP with HPE, target date 09-07-25 As discussed in the meeting, call to be arranged along with OSS SME and HP team 15-06-2025: WIP with HPE, target date 30-06-2025 21-05-2025: RCA Yet to be started by HPE, date: 30th June 2025 30APR'25: Node down Auto TT is ok but RCA pending |  | Suresh Kumar |  | COMPLETED & APPROVED | 2025-09-23 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\DWDM\Artefact 100 | Completed & Approved | Closed before june-2025 | Closed after June |  | Completed & Approved
102 | T101 | 472 | DWDM | Integration with OSS | Network and service performance monitoring KPIs report in HPE OSS |  |  | Suresh Kumar |  | COMPLETED & APPROVED | 2025-05-06 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\DWDM\Artefact - T101 | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
103 | T102 | 472 | DWDM | Integration with OSS | Bandwidth Utilization Data in HPE OSS |  |  | Suresh Kumar |  | COMPLETED & APPROVED | 2025-05-06 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\DWDM\Artefact - T102 | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
104 | T103 | 472 | DWDM | Integration with OSS | Service Inventory Data Availibilty in HPE OSS | 11-Nov-25: As per OSS SME Mr. manoj this task would be completed by 13-Nov-25 in TND based on test result shall move to production. Post 24.06.25 review and direction, working for a alternate options for NSO. will come back as earliest with closure plan. |  | Venkatesh | 2025-11-13 | DEPENDENCY(Client/Ext.) |  |  | Open | Open | Open |  | Open
105 | T104 | 472 | DWDM | Integration with OSS | Planned Event Service Impact analysis report | 11-Nov-25: Once Service inventory(Unique ID: T103) is ready, same can be used for impact Analysis Post 24.06.25 review and direction, working for a alternate options for NSO. will come back as earliest with closure plan. |  | Venkatesh | 2025-11-13 | DEPENDENCY(Client/Ext.) |  |  | Open | Open | Open |  | Open
106 | T105 | 472 | DWDM | Integration with NSO | 1+1 , 1+0 and 1+R service provisioning testing through NSO | Post 24.06.25 review and direction, working for a alternate options for NSO. will come back as earliest with closure plan. |  | Jayant Madavi |  | DEPENDENCY(Client/Ext.) |  |  | Open | Open | Open |  | Open
107 | T108 | 472 | GIS | Data gathering | Data Gathering for RFS Mandals | 15-Nov-25: 256 Mandal uploaded and AT Completed for 250 Mandals,Ongoing & Approved |  | Kaushalendra Kumar | Ongoing Activity | COMPLETED & APPROVED | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T108 | Closed | Closed After 14-Oct | Open |  | Completed & Approved
108 | T109 | 472 | GIS | Data gathering | Data Upload of RFS Mandals | 15-Nov-25: 256 Mandal uploaded and AT Completed for 250 Mandals,Ongoing & Approved |  | Kaushalendra Kumar | Ongoing Activity | COMPLETED & APPROVED | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T109 | Closed | Closed After 14-Oct | Open |  | Completed & Approved
109 | T110 | 472 | GIS | Basic Readiness | Each Package 5 Mandal (Total-15 Mandal) Upload | As a PoC, 15 Mandals data uploaded for testing purpose |  | Kaushalendra Kumar |  | COMPLETED & APPROVED | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T110 | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
110 | T111 | 472 | GIS | Deployment | GIS Hardware & Software deployment at DC | HA Re-Testing Planned with TPA & TFIBER on 2nd June 2025 |  | Kaushalendra Kumar |  | COMPLETED & APPROVED | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T111 | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
111 | T112 | 472 | GIS | Deployment | High Availability & Load Balancer Testing | Awaiting for approval from TFIBER & TPA |  | Kaushalendra Kumar |  | COMPLETED & APPROVED | 2025-07-07 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T112 | Completed & Approved | Closed before june-2025 | Closed after June |  | Completed & Approved
112 | T113 | 472 | GIS | Deployment | PCs & Licences (G-tech, DI, Geo Media) | Tool & PCs has been installed in NOC GIS room. for Licesnes dependecy on T FIber. During the meeting, the Managing Director of T-Fiber directed that only the minimum number of additional licenses will be procured, and T-Fiber will handle the procurement |  | Kaushalendra Kumar |  | COMPLETED & APPROVED | After Jun-25 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T113 | Completed & Approved | Closed before june-2025 | Closed after June |  | Completed & Approved
113 | T114 | 472 | GIS | Deployment | G-Tech |  |  | Kaushalendra Kumar |  | COMPLETED & APPROVED | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T114 | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
114 | T115 | 472 | GIS | Deployment | Network Portal | Network Portal in Production and provided by the approval NoC team but need to demonstarte for Core team |  | Kaushalendra Kumar |  | COMPLETED & APPROVED | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T115 | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
115 | T116 | 472 | GIS | Deployment | Mobile App | Mobile App in Production and provided by the approval NoC team but need to demonstarte for Core team |  | Kaushalendra Kumar |  | COMPLETED & APPROVED | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T116 | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
116 | T117 | 472 | GIS | DC-DR | Requirement Vs Solution | #N/A |  | Kaushalendra Kumar |  | COMPLETED & APPROVED | 2025-07-09 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T117 | Completed & Approved | Closed before june-2025 | Closed after June |  | Completed & Approved
117 | T118 | 472 | GIS | DC-DR | DC-DR Testing | DC-DR Testing completed & Document has been kept on share drive,Awaiting TFIBER Approval |  | Kaushalendra Kumar |  | COMPLETED & APPROVED | 2025-07-09 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T118 | Completed & Approved | Closed before june-2025 | Closed after June |  | Completed & Approved
118 | T119 | 472 | GIS | Basic Readiness | Google Map API configuration |  |  | Kaushalendra Kumar |  | COMPLETED & APPROVED | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T119 | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
119 | T120 | 472 | GIS | Basic Readiness | Fixing of telco Boundaries in GIS |  |  | Kaushalendra Kumar |  | COMPLETED & APPROVED | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T120 | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
120 | T121 | 472 | GIS | Basic Readiness | Data Model Optimization |  |  | Kaushalendra Kumar |  | COMPLETED & APPROVED | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\ | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
121 | T122 | 472 | GIS | Basic Readiness | ISP/OSP object modelling in tool as per T-Fibre |  |  | Kaushalendra Kumar |  | COMPLETED & APPROVED | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T122 | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
122 | T123 | 472 | GIS | Basic Readiness | Make & Model deployment against all object as per T-Fibre Project |  |  | Kaushalendra Kumar |  | COMPLETED & APPROVED | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T123 | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
123 | T124 | 472 | GIS | Basic Readiness | Device (Active/Passive) ( All Type as per T-Fibre Project) & Port Modelling In Tool |  |  | Kaushalendra Kumar |  | COMPLETED & APPROVED | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\ | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
124 | T125 | 472 | GIS | Basic Readiness | Correction In Fttx Network placement rules (GP To GI) |  |  | Kaushalendra Kumar |  | COMPLETED & APPROVED | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\ | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
125 | T126 | 472 | GIS | Basic Readiness | Fine tuning or Enable of Cart feature. ( Pan, Zoom, Vertex, Selection method, ruler Etc.) |  |  | Kaushalendra Kumar |  | COMPLETED & APPROVED | 2025-06-02 | D:\T-Fiber Project\Hexagon GIS\Artefacts Of T-NOC Tracker\T126 | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
126 | T127 | 472 | GIS | Basic Readiness | Trace Feature ( Link/Spare/Topology) |  |  | Kaushalendra Kumar |  | COMPLETED & APPROVED | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T127 | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
127 | T128 | 472 | GIS | Basic Readiness | Reports (Fibre Utilisation, BOQ, Area selection, ISP/OSP Quantify) |  |  | Kaushalendra Kumar |  | COMPLETED & APPROVED | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T128 | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
128 | T129 | 472 | GIS | Basic Readiness | Document/Image Upload feature |  |  | Kaushalendra Kumar |  | COMPLETED & APPROVED | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\ | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
129 | T130 | 472 | GIS | Basic Readiness | Port level & Fibre stand lever attribute |  |  | Kaushalendra Kumar |  | COMPLETED & APPROVED | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T130 | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
130 | T131 | 472 | GIS | Basic Readiness | Topology Highlight feature |  |  | Kaushalendra Kumar |  | COMPLETED & APPROVED | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T131 | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
131 | T132 | 472 | GIS | Basic Readiness | Data Model G-TECH Alignment |  |  | Kaushalendra Kumar |  | COMPLETED & APPROVED | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T132 | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
132 | T133 | 472 | GIS | Basic Readiness | DI alignment as per new 35 Layer data model |  |  | Kaushalendra Kumar |  | COMPLETED & APPROVED | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\ | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
133 | T134 | 472 | GIS | Basic Readiness | Active to Passive, Active to active connectivity correction |  |  | Kaushalendra Kumar |  | COMPLETED & APPROVED | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T134 | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
134 | T135 | 472 | GIS | Basic Readiness | DI processing timing optimisation |  |  | Kaushalendra Kumar |  | COMPLETED & APPROVED | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\ | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
135 | T136 | 472 | GIS | Basic Readiness | Rack to Rack Connectivity |  |  | Kaushalendra Kumar |  | COMPLETED & APPROVED | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T136 | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
136 | T137 | 472 | GIS | Advance Readiness | Graphical Symbology deployment against all object |  |  | Kaushalendra Kumar |  | COMPLETED & APPROVED | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T137 | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
137 | T138 | 472 | GIS | Advance Readiness | Fixing Of Labelling (Sequencing & Attributes) |  |  | Kaushalendra Kumar |  | COMPLETED & APPROVED | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T138 | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
138 | T139 | 472 | GIS | Advance Readiness | Object search options to user |  |  | Kaushalendra Kumar |  | COMPLETED & APPROVED | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T139 | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
139 | T140 | 472 | GIS | Advance Readiness | G-tech to .shp & Kml conversion |  |  | Kaushalendra Kumar |  | COMPLETED & APPROVED | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T140 | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
140 | T141 | 472 | GIS | Advance Readiness | Plotting & Print Feature |  |  | Kaushalendra Kumar |  | COMPLETED & APPROVED | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T141 | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
141 | T142 | 472 | GIS | Advance Readiness | 4 More API from Google Map |  |  | Kaushalendra Kumar |  | COMPLETED & APPROVED | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T142 | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
142 | T143 | 472 | GIS | Advance Readiness | Fibre Utilisation Reports |  |  | Kaushalendra Kumar |  | COMPLETED & APPROVED | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T143 | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
143 | T144 | 472 | GIS | Advance Readiness | Consolidated reports from GIS |  |  | Kaushalendra Kumar |  | COMPLETED & APPROVED | 2025-06-02 | D:\T-Fiber Project\Hexagon GIS\Artefacts Of T-NOC Tracker\T144 | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
144 | T145 | 472 | GIS | Advance Readiness | Link trace Reports |  |  | Kaushalendra Kumar |  | COMPLETED & APPROVED | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T145 | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
145 | T146 | 472 | GIS | Advance Readiness | Consolidation/Customization of Dashboard feature in G-tech, Network Portal |  |  | Kaushalendra Kumar |  | COMPLETED & APPROVED | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T146 | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
146 | T147 | 472 | GIS | Advance Readiness | Network data availability in G-Tech & Network portal & Geo media |  |  | Kaushalendra Kumar |  | COMPLETED & APPROVED | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T147 | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
147 | T148 | 472 | GIS | Advance Readiness | Final Demo to customer |  |  | Kaushalendra Kumar |  | COMPLETED & APPROVED | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T148 | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
148 | T149 | 472 | GIS | Mobile Applications | Network availability in Mobile application with G-MAP |  |  | Kaushalendra Kumar |  | COMPLETED & APPROVED | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T149 | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
149 | T150 | 472 | GIS | Mobile Applications | Red line, Red Point Feature deployment in Mobile application |  |  | Kaushalendra Kumar |  | COMPLETED & APPROVED | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T150 | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
150 | T151 | 472 | GIS | Mobile Applications | JOB creation testing in GIS tool from GIS Mobile app |  |  | Kaushalendra Kumar |  | COMPLETED & APPROVED | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T151 | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
151 | T152 | 472 | GIS | Design & Documentation | Feasible Points closure of workshop |  |  | Kaushalendra Kumar |  | COMPLETED & APPROVED | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T152 | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
152 | T153 | 472 | GIS | Resources | Resources onboarding, Licences arrangement, Workstation plan | Resource & PCs has been deployed in NOC GIS room. for Licesnes dependecy on T FIber. |  | Kaushalendra Kumar |  | COMPLETED & APPROVED | After Jun-25 | Artefacts not Required | Completed & Approved | Closed before june-2025 | Closed after June |  | Completed & Approved
153 | T154 | 472 | GIS | Data gathering | T-NOC Creation in GIS Tool with connectivity |  |  | Kaushalendra Kumar |  | COMPLETED & APPROVED | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T154 | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
154 | T155 | 472 | GIS | Design & Documentation | SOP Creation |  |  | Kaushalendra Kumar |  | COMPLETED & APPROVED | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T155 | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
155 | T156 | 472 | GIS | MoM Action | MB kilometers vs UG and arial to path and over all route length to be added in webapplication |  |  | Kaushalendra Kumar |  | COMPLETED & APPROVED | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T156 | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
156 | T157 | 472 | GIS | MoM Action | 3 Formats of Lat long (DMS, DMM & Mtr) required in Hexagon tool |  |  | Kaushalendra Kumar |  | COMPLETED & APPROVED | 2025-06-02 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T157 | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
157 | T158 | 472 | GIS | MoM Action | GIS LLD submitted to T-Fiber on 02.03.2025, to be discussed with T-Fiber | 15-Nov-25: Resubmission done after discussion. Date-19.03.25. queries on LLD with mail dated 25.03.25 |  | Kaushalendra Kumar |  | COMPLETED & APPROVED | After Jun-25 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T158 | Completed & Approved | Closed before june-2025 | Closed after June |  | Completed & Approved
158 | T159 | 472 | GIS | Integration | Physical Device sync-up with OSS System | 15-Nov-25:Integration with OSS Is WIP |  | Kaushalendra Kumar | 2025-10-20 | WIP |  | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\GIS\T159 | Open | Open | Open |  | Open
159 | T160 | 472 | GIS | Integration | Common Span Path | 15-Nov-25: Integration with OSS Is WIP |  | Kaushalendra Kumar | 2025-11-05 | WIP |  | Dependency On Physical Device Syn-up (Integration) & alarm corelation | Open | Open | Open |  | Open
160 | T161 | 472 | GIS | Integration | Auto feasibility | 15-Nov-25: BSS(knot) has demonstrated the Auto Feasibility feature for single location business cases. If, Customer is expecting Bulk feasibility capabilities, which is not a feature of GIS, required external tool. |  | Kaushalendra Kumar |  | CLOSURE REVIEW PENDING |  | Multiple demonstrations were provided to showcase auto-feasibility during the GIBB demo | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process |  | Closure Review Pending
161 | T162 | 472 | GPON | Tejas-Design & Documentation | Customer Requirement Document |  |  | Sayyad Pasha |  | COMPLETED & APPROVED | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T162 | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
162 | T163 | 472 | GPON | Tejas-Design & Documentation | HLD |  |  | Sayyad Pasha |  | COMPLETED & APPROVED | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T163 Please refer Section-3 in E2E Network HLD | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
163 | T164 | 472 | GPON | Nokkia-Design & Documentation | LLD for 152 Mandals |  |  | Sayyad Pasha |  | COMPLETED & APPROVED | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T164 | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
164 | T165 | 472 | GPON | Tejas | Latest EMS Integration with OSS (Hold due to CR) |  |  | Sayyad Pasha |  | COMPLETED & APPROVED | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T165 | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
165 | T166 | 472 | GPON | Tejas | * Testing done for new build in T-Fiber test lab . * Plan event for OLTs new SW upgradation in production environment. | 15-Nov-25: Below is the breakup of pending OLT status PKG-A : 430/462 PKG-B : 228/322 PKG-C : 94/165 13-Oct-25: GPON SME has to provide the breakup for all Pending OLT upgradation activities, need to send a mail to concern packages with respective pending OLT upgradation. 20-Sep-25: All the reachable OLT to EMS are upgraded successfully. And Not reachbale OLTs need to be upgraded, There is a dependecny on All 3 Packages field teams to make reachability to EMS. GPON SME need to submit detailed report on Scope vs upgraded and Pending devices breakup(Package wise). |  | Sayyad Pasha |  | DEPENDENCY(Client/Ext.) |  |  | Open | Open | Open |  | Open
166 | T167 | 472 | GPON | Tejas | TACACS Feature |  |  | Sayyad Pasha |  | COMPLETED & APPROVED | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T372 | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
167 | T168 | 472 | GPON | Tejas | Authentication & Authorization with RAIDUS |  |  | Sayyad Pasha |  | COMPLETED & APPROVED | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T168 | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
168 | T169 | 472 | GPON | Tejas | EMS authentication & Authorization with Alepo |  |  | Sayyad Pasha |  | COMPLETED & APPROVED | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T169 | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
169 | T170 | 472 | GPON | Nokia | Accounting Feature with New build & Logs filteration |  |  | Sayyad Pasha |  | COMPLETED & APPROVED | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T170 | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
170 | T171 | 472 | GPON | Tejas | Accounting Feature with New build & Logs filteration |  |  | Sayyad Pasha |  | COMPLETED & APPROVED | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T170 | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
171 | T172 | 472 | GPON | Tejas | Tejas EMS ATP |  |  | Sayyad Pasha |  | COMPLETED & APPROVED | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T172 | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
172 | T173 | 472 | GPON | Tejas | DC-DR Switchover Activity |  |  | Sayyad Pasha |  | COMPLETED & APPROVED | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T173 | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
173 | T174 | 472 | GPON | Tejas | NBI API availability for BW query Dependent on new OLT build, which supposed to released on 31- March23. |  |  | Sayyad Pasha |  | COMPLETED & APPROVED | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T174 | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
174 | T175 | 472 | GPON | Nokia | CR for Nokia API integration to close BW query and PMS related issues | 15-Nov-25: Having dependency on Service Inventory and NSO |  | Sayyad Pasha |  | DEPENDENCY(Client/Ext.) |  |  | Open | Open | Open |  | Open
175 | T176 | 472 | GPON | Nokia | OLT devices status in OSS is not as per AMS. |  |  | Sayyad Pasha |  | COMPLETED & APPROVED | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T176 | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
176 | T177 | 472 | GPON | Nokia | ONT devices have been recovered and validated as per AMS count. |  |  | Sayyad Pasha |  | COMPLETED & APPROVED | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T177 | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
177 | T178 | 472 | GPON | Nokia | Authentication and authorization have been tested with Nokia devices except CB OLT. |  |  | Sayyad Pasha |  | COMPLETED & APPROVED | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T178 | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
178 | T179 | 472 | GPON | Nokia | Tejas ONT firmware upgradation not happing through Nokia OLT. Joint troubleshooting is required with Tejas and Nokia. |  |  | Sayyad Pasha |  | COMPLETED & APPROVED | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T179 | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
179 | T180 | 472 | GPON | Nokia | Nokia ONT to support NAT, DHCP, both Router and Bridge mode | Nokia has provided the SOP, which has been tested and is working as expected. However, Nokia ONTs connected to Tejas OLTs cannot be enabled directly through the Tejas OLT. As discussed with TFiber, we have prepared an SOP for the field team and are currently working on mapping the Nokia ONTs under Tejas OLTs to nearby Nokia OLTs |  | Sayyad Pasha |  | COMPLETED & APPROVED | 2025-09-20 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T180 | Completed & Approved | Closed before june-2025 | Closed after June |  | Completed & Approved
180 | T181 | 472 | GPON | Nokia | Accounting logs are forwarded to Alepo server, same was reflecting in Alepo server but it was forwarding towards syslog server. |  |  | Sayyad Pasha |  | COMPLETED & APPROVED | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T181 | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
181 | T182 | 472 | GPON | Nokia | Nokia EMS functional ATP to be closed with customer | 15-Nov-25: Working with OEM 20-Sep-25: ATP document submitted to TPA, And TPA Shared 12 observations related to RFP compliance.Same has been given to OEM for closure. Nokia team provided clarifications for 10 points and 2 points are WIP. GPON team has to share clarifications of 10 points to TPA and need to confirm timelines for remaining 2 points on 23-Sep-25. |  | Sayyad Pasha |  | DEPENDENCY(Client/Ext.) |  |  | Open | Open | Open |  | Open
182 | T183 | 472 | GPON | Nokia | DC-DR Switchover activity need to plan. |  |  | Sayyad Pasha |  | COMPLETED & APPROVED | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T183 | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
183 | T184 | 472 | GPON | Nokia | Nokia OLTs reachability is pending for DR Servers. |  |  | Sayyad Pasha |  | COMPLETED & APPROVED | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T184 | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
184 | T185 | 472 | IP/MPLS | Service Solution | HSI (High Speed Internet to Household) |  |  | RS Rao |  | COMPLETED & APPROVED | 2025-05-05 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\House Hold HSI Services Design LLD V1.2 - T185.pdf | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
185 | T186 | 472 | IP/MPLS | Service Solution | IPTV to Household |  |  | RS Rao |  | COMPLETED & APPROVED | 2025-05-05 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\House Hold IPTV Services Design LLD V1.2 - T186.pdf | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
186 | T187 | 472 | IP/MPLS | Service Solution | VOIP to Household |  |  | RS Rao |  | COMPLETED & APPROVED | 2025-05-05 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\House Hold VoIP Services Design LLD V1.2 - t187.pdf | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
187 | T188 | 472 | IP/MPLS | Service Solution | Internet to GI (Govt. Institution) |  |  | RS Rao |  | COMPLETED & APPROVED | 2025-05-05 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\T-FIBER T-Net for GI Broadband Service Design LLD V1.1 - T188.pdf | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
188 | T189 | 472 | IP/MPLS | Service Solution | CCTV Unicast |  |  | RS Rao |  | COMPLETED & APPROVED | 2025-05-05 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\Centrailzed CCTV Surveillance Monitoring over T-Fiber Network-Solution Doucment_Initial Draft V1.0 - T189.pdf | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
189 | T190 | 472 | IP/MPLS | Service Solution | CCTV Multicast |  |  | RS Rao |  | COMPLETED & APPROVED | 2025-05-05 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\CCTV Multicast Solution LLD V1.2 - T190.pdf | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
190 | T191 | 472 | IP/MPLS | Service Solution | Cell Tower L2VPN |  |  | RS Rao |  | COMPLETED & APPROVED | 2025-05-05 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\TFIBER T-CELL Service Design & Solution V4.3 T197, T336, T337, T338.pdf | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
191 | T192 | 472 | IP/MPLS | Service Solution | Dhanush Telemedicine Application |  |  | RS Rao |  | COMPLETED & APPROVED | 2025-05-05 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\T-FIBER DHANUSH TELEMEDICINE SOLUTION LLD V1.0 - T192.pdf | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
192 | T193 | 472 | IP/MPLS | Service Solution | SDC content to Household and GI | 22-Sep-25: Need to review plan and approve 12-Sep-25 : Peering plan submitted as per discussion on 11-Sep-25 01-Jul-25 : Design document submitted with suggested approaches. Require inputs from TFiber to conduct PoC and finalize service design. |  | RS Rao |  | Completed & Approved | 2025-10-31 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\T-Fiber & SDC Peering Plan V1.1 - T193 T343.pdf | Closed | Closed After 14-Oct | Open |  | Completed & Approved
193 | T194 | 472 | BSS | Service Catalogue | Incremental Product/ Services finalization in T-Fiber network | 01-Jul-25 : Dependecy on Tfiber in PCN (Product Concept Note) finalisation. Tracked in BSS action item T12 (part of 472 tracker) |  | Sandeep Deshmukh |  | Open |  |  | Open | Open | Open |  | Open
194 | T195 | 472 | IP/MPLS | Service Provisioning | Service Provisioning PoC for SCCM/NSO - L2, L3 VPN | Post 24.06.25 review and direction, working for a alternate options for NSO. will come back as earliest with closure plan. |  | Jayant Madavi |  | DEPENDENCY(Client/Ext.) |  |  | Open | Open | Open |  | Open
195 | T196 | 472 | IP/MPLS | Service Provisioning | Service Provisioning PoC for SCCM/NSO - QoS (all scenarios) | Post 24.06.25 review and direction, working for a alternate options for NSO. will come back as earliest with closure plan. |  | Jayant Madavi |  | DEPENDENCY(Client/Ext.) |  |  | Open | Open | Open |  | Open
196 | T197 | 472 | IP/MPLS | Service Provisioning | Service Provisioning PoC for SCCM/NSO - MVPN (all scenarios) | Post 24.06.25 review and direction, working for a alternate options for NSO. will come back as earliest with closure plan. |  | Jayant Madavi |  | DEPENDENCY(Client/Ext.) |  |  | Open | Open | Open |  | Open
197 | T198 | 472 | IP/MPLS | Network AT | Simulation and testing network for parameters like network convergence etc | 22-Sep-2025: Need to have discussion on Network AT parameters 8-Jul-2025 - Sandeep will come back by EoD today on extension of Cisco support renewal 01-Jul-25 : OEM(Cisco) suport is required to perform network AT, Inputs provided to OEM. OEM to provide Network AT procedure including all tests and test procedures. OEM onboarding is in progress & LnT Contracts team is coordinating |  | RS Rao |  | DEPENDENCY(Client/Ext.) |  |  | Open | Open | Open |  | Open
198 | T199 | 472 | IP/MPLS | Design & Documentation | HLD |  |  | RS Rao |  | COMPLETED & APPROVED | 2025-05-05 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\E2E_Network HLD_Part1_V2.0_ 29.10.2020(Approved) - T199.pdf | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
199 | T200 | 472 | IP/MPLS | Design & Documentation | Approved conditionally with few punch points. Updated LLD to be submitted |  |  | RS Rao |  | COMPLETED & APPROVED | 2025-08-21 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\IP MPLS Network LLD V1.7 14-Aug-2025.pdf | Completed & Approved | Closed before june-2025 | Closed after June |  | Completed & Approved
200 | T201 | 472 | IP/MPLS | OSS | FMS Fault Management System (Device, Link ticketing etc) | 22-Sep-25: Auto ticketing verification is depending on OSS, reqiured configguration or changes done in OSS. Now auto ticket is working atrefatcs to be submitted for Node and Link. 08-Jul-25 : Requirement given to OSS for implementation. FMS parameters given 1. Node down (Router, Switch, DC Network Switches, DWDM, OTN, OADM, OLT, UPS) : Field alarm should be received in NNMi. NNMi has to forward the alarm to OBM, NPS and to TeMiP. UCA has to carryout correlation and accordingly pass the root cause to SM to generate TT. once TT is generated it is assigned to respective District Engineer along with mail. After Fault resolution, TT should be resolved in system with alarm clearance and NoC has to close the TT with RFO. Link down, Protocol down, RSP/Card/PSU down, High Temperature, Latency, Packet Loss, Jitter. End-to-end implementation and demonstration pending in OSS |  | Venkatesh |  | CLOSURE REVIEW PENDING |  |  | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process |  | Closure Review Pending
201 | T202 | 472 | IP/MPLS | OSS | PMS Performance Management System (Utilization, Errors etc) | 25-Sep-25: Implementation completed, Need to validate and cofirm 07-Jul-25 : Requirement given to OSS for implementation. PMS parameters given - CPU, Memory, Backplane and Link utilization, CRC errors, Optical power, QoS parameters . End-to-end implementation and demonstration pending in OSS |  | Venkatesh |  | CLOSURE REVIEW PENDING |  |  | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process |  | Closure Review Pending
202 | T203 | 472 | IP/MPLS | OSS | Dashboard (Network Parameter Dash Boards) | 25-Sep-25: Implementation completed, Need to validate and cofirm 07-Jul-25 : Requirement given to OSS for implementation. Dash Board required - Top CPU, Memory, Link utilization, Temperature, All Critical alarms . Demonstration pending in OSS |  | Venkatesh |  | Open |  |  | Open | Open | Open |  | Open
203 | T204 | 472 | IP/MPLS | OSS | Reports (Invetory, Device avability, Link Availability) | 25-Sep-25: Reports are available in UOC, Artefacts to be submitted for clsore 07-Jul-25 : Requirement given to OSS for implementation. Reports required - Node availability, Link availability, Link utilization, Inventory, CPU utilization, Memory Utilization, Latecy. Demonstration pending in OSS |  | Venkatesh |  | COMPLETED & APPROVED | 2025-11-18 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\OSS\52 Artefcats_18112025 | Closed after 14-Nov-25 | Closed after 14-Nov-25 | Completed but Verification undrer Process |  | Completed & Approved
204 | T205 | 472 | NSO | Installation | Installation of NSO Applications | Post 24.06.25 review and direction, working for a alternate options for NSO. will come back as earliest with closure plan. |  | Jayant Madavi |  | DEPENDENCY(Client/Ext.) |  |  | Open | Open | Open |  | Open
205 | T206 | 472 | NSO | Integration | Integration with Third Party Applications/Nodes | Post 24.06.25 review and direction, working for a alternate options for NSO. will come back as earliest with closure plan. |  | Jayant Madavi |  | DEPENDENCY(Client/Ext.) |  |  | Open | Open | Open |  | Open
206 | T207 | 472 | NSO | Integration | OSS | Post 24.06.25 review and direction, working for a alternate options for NSO. will come back as earliest with closure plan. |  | Jayant Madavi |  | DEPENDENCY(Client/Ext.) |  |  | Open | Open | Open |  | Open
207 | T208 | 472 | NSO | Integration | BSS | Post 24.06.25 review and direction, working for a alternate options for NSO. will come back as earliest with closure plan. |  | Jayant Madavi |  | DEPENDENCY(Client/Ext.) |  |  | Open | Open | Open |  | Open
208 | T209 | 472 | NSO | Integration | Nodes | Post 24.06.25 review and direction, working for a alternate options for NSO. will come back as earliest with closure plan. |  | Jayant Madavi |  | DEPENDENCY(Client/Ext.) |  |  | Open | Open | Open |  | Open
209 | T210 | 472 | NSO | Integration | EMS-GPON | Post 24.06.25 review and direction, working for a alternate options for NSO. will come back as earliest with closure plan. |  | Jayant Madavi |  | DEPENDENCY(Client/Ext.) |  |  | Open | Open | Open |  | Open
210 | T211 | 472 | NSO | Integration | EMS-DWDM | Post 24.06.25 review and direction, working for a alternate options for NSO. will come back as earliest with closure plan. |  | Jayant Madavi |  | DEPENDENCY(Client/Ext.) |  |  | Open | Open | Open |  | Open
211 | T212 | 472 | NSO | Development and unit testing | Service verification and provisioning - IP MPLS | Post 24.06.25 review and direction, working for a alternate options for NSO. will come back as earliest with closure plan. |  | Jayant Madavi |  | DEPENDENCY(Client/Ext.) |  |  | Open | Open | Open |  | Open
212 | T213 | 472 | NSO | Development and unit testing | Service verification and activation - GPON Nokia and Tejas | Post 24.06.25 review and direction, working for a alternate options for NSO. will come back as earliest with closure plan. |  | Jayant Madavi |  | DEPENDENCY(Client/Ext.) |  |  | Open | Open | Open |  | Open
213 | T214 | 472 | NSO | Development and unit testing | SCCM provisioning request for HSI, IPTV, T-Wire,T-VPN,VoIP,CCTV SDD | Post 24.06.25 review and direction, working for a alternate options for NSO. will come back as earliest with closure plan. |  | Jayant Madavi |  | DEPENDENCY(Client/Ext.) |  |  | Open | Open | Open |  | Open
214 | T215 | 472 | NSO | Development and unit testing | NSO module final implementation | Post 24.06.25 review and direction, working for a alternate options for NSO. will come back as earliest with closure plan. |  | Jayant Madavi |  | DEPENDENCY(Client/Ext.) |  |  | Open | Open | Open |  | Open
215 | T216 | 472 | NSO | Integration | NSO integration with SCCM | Post 24.06.25 review and direction, working for a alternate options for NSO. will come back as earliest with closure plan. |  | Jayant Madavi |  | DEPENDENCY(Client/Ext.) |  |  | Open | Open | Open |  | Open
216 | T217 | 472 | NSO | MoM Action | Cisco NSO to test all the cisco elements including SG350 Horizontal switch to deliver service | Post 24.06.25 review and direction, working for a alternate options for NSO. will come back as earliest with closure plan. |  | Jayant Madavi |  | DEPENDENCY(Client/Ext.) |  |  | Open | Open | Open |  | Open
217 | T218 | 472 | NSO | MoM Action | NSO LLD | Post 24.06.25 review and direction, working for a alternate options for NSO. will come back as earliest with closure plan. |  | Jayant Madavi |  | DEPENDENCY(Client/Ext.) |  |  | Open | Open | Open |  | Open
218 | T219 | 472 | NSO | MoM Action | Service catalog with product concept note for all services with target requirement date. | Post 24.06.25 review and direction, working for a alternate options for NSO. will come back as earliest with closure plan. |  | Jayant Madavi |  | DEPENDENCY(Client/Ext.) |  |  | Open | Open | Open |  | Open
219 | T220 | 472 | NSO | MoM Action | T-Cell Service definition sign off | Post 24.06.25 review and direction, working for a alternate options for NSO. will come back as earliest with closure plan. |  | Jayant Madavi |  | DEPENDENCY(Client/Ext.) |  |  | Open | Open | Open |  | Open
220 | T221 | 472 | NSO | MoM Action | MAG/GAC ports reservation feasibility for services booked in BSS with payments made | Post 24.06.25 review and direction, working for a alternate options for NSO. will come back as earliest with closure plan. |  | Jayant Madavi |  | DEPENDENCY(Client/Ext.) |  |  | Open | Open | Open |  | Open
221 | T222 | 472 | NSO | MoM Action | Tejas NED readiness | Post 24.06.25 review and direction, working for a alternate options for NSO. will come back as earliest with closure plan. |  | Jayant Madavi |  | DEPENDENCY(Client/Ext.) |  |  | Open | Open | Open |  | Open
222 | T223 | 472 | NSO | MoM Action | IPTV tested needs to be finalised for additional configuration for multicast and tested as per lab availability and final sign off | Post 24.06.25 review and direction, working for a alternate options for NSO. will come back as earliest with closure plan. |  | Jayant Madavi |  | DEPENDENCY(Client/Ext.) |  |  | Open | Open | Open |  | Open
223 | T224 | 472 | NSO | MoM Action | BSS to provide actual feasibility parameters e.g PE port number(s) from OSS . Right now values are hard-coded . In turn OSS to get these details from GIS. We havent seen an e2e workign scenario on this yet. | Post 24.06.25 review and direction, working for a alternate options for NSO. will come back as earliest with closure plan. |  | Jayant Madavi |  | DEPENDENCY(Client/Ext.) |  |  | Open | Open | Open |  | Open
224 | T225 | 472 | NSO | MoM Action | VLAN logic : Vlan logic for HSI-SVLAN has beed provided per zone information. But most of deployments are coming with vlan 256 of PIONEER for any service . This needs to be looked at. VLAN ID should be changed to as per plan shared by Aravindhan. | Post 24.06.25 review and direction, working for a alternate options for NSO. will come back as earliest with closure plan. |  | Jayant Madavi |  | DEPENDENCY(Client/Ext.) |  |  | Open | Open | Open |  | Open
225 | T226 | 472 | OSS | IPMPLS | Alarm & Auto TT | 1. OT Stack upgrade is under discussion 2. Resync stabilization is WIP : Action Plan to submitted by 9th Sept 2025 |  | Venkatesh |  | CLOSURE REVIEW PENDING |  |  | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process |  | Closure Review Pending
226 | T227 | 472 | OSS | Other Applications Integrations with OSS | Create trouble ticket by BSS CRM |  |  | Venkatesh |  | COMPLETED & APPROVED | 2025-05-26 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\OSS\T227 | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
227 | T228 | 472 | OSS | Other Applications Integrations with OSS | Creation of technical incident by Helpdesk | 17-05-2025: Under observation. Seek approval from Sivakumar 26-06-2025: closed from OSS end, help desk to start using |  | Venkatesh |  | CLOSURE REVIEW PENDING |  |  | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process |  | Closure Review Pending
228 | T229 | 472 | OSS | DWDM Integration with OSS | DWDM Network Alarms integration has been completed in HPE OSS. However, all alarm counts are not in sync with Ciena MCP to HPE vTeMIP. |  |  | Venkatesh |  | COMPLETED & APPROVED | 2025-05-29 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\OSS\T229 | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
229 | T230 | 472 | OSS | DWDM Integration with OSS | Hardware inventory integration has been completed in HPE OSS. |  |  | Venkatesh |  | COMPLETED & APPROVED | 2025-05-26 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\OSS\T230 | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
230 | T231 | 472 | OSS | DWDM Integration with OSS | Ciena DWDM Network Topology has been created in HPE OSS topology MAP along with neighbour NE details. Adding the geographical map in the background of HPE OSS is possible with openstreet map.. Not posisble to integarted with GIS map | 09-09-2025: topology available but bordering not feasible |  | Venkatesh |  | CLOSURE REVIEW PENDING |  |  | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process |  | Closure Review Pending
231 | T232 | 472 | OSS | DWDM Integration with OSS | Auto Ticket Generation- Fiber Cut | 15-09-2025: Demonstrated in the Demo/UAT call |  | Venkatesh |  | COMPLETED & APPROVED | 2025-05-26 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\OSS\T232 | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
232 | T233 | 472 | OSS | DWDM Integration with OSS | Auto Ticket Generation- Hardwares Failures |  |  | Venkatesh |  | COMPLETED & APPROVED |  | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\OSS\T233 | Completed & Approved | Closed before june-2025 | Closed after June |  | Completed & Approved
233 | T234 | 472 | OSS | DWDM Integration with OSS | Auto Ticket Generation- Infra Failure |  |  | Venkatesh |  | COMPLETED & APPROVED | 2025-05-26 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\OSS\T234 | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
234 | T235 | 472 | OSS | DWDM Integration with OSS | Network and service performance monitoring KPIs report in HPE OSS |  |  | Venkatesh |  | COMPLETED & APPROVED | 2025-05-26 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\DWDM\Artefact - T101 | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
235 | T236 | 472 | OSS | DWDM Integration with OSS | Bandwidth utilization data in HPE OSS is available and under validation. |  |  | Venkatesh |  | COMPLETED & APPROVED | 2025-05-26 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\OSS\T236 | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
236 | T237 | 472 | OSS | DWDM Integration with OSS | Service inventory data availability in HPE OSS | 17-05-2025: Dependancy on NSO 26-06-2025: Cisco to be onboarded then it will take ~30 days to complete(timeline is given concidering NSO support available on 1st July) |  | Venkatesh |  | Open |  |  | Open | Open | Open |  | Open
237 | T238 | 472 | OSS | DWDM Integration with OSS | For planned event service impact analysis data / report | 17-05-2025: Dependancy on NSO 26-06-2025: Cisco to be onboarded then it will take ~30 days to complete(timeline is given concidering NSO support available on 1st July) |  | Venkatesh |  | CLOSURE REVIEW PENDING |  |  | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process |  | Closure Review Pending
238 | T239 | 472 | OSS | IPMPLS Integration with OSS | FMS (Inventory, Alarm, Auto TT) Ref 226 | 24-05-2025:Working with some operational challenges like frequent NNMi and OBM hung issue, queue increase. |  | Venkatesh |  | CLOSURE REVIEW PENDING |  |  | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process |  | Closure Review Pending
239 | T240 | 472 | OSS | IPMPLS Integration with OSS | PMS reports for IPMPLS domain network elements | 17-05-2025: Data collection rom internal (SME & NOC team) and then OT support is required for NPS to enable all permormance parameters. 24-06-2025: NPS reports available and NOC came back with some observation of wrong data, for which OT has asked evidences which are awaited from NOC |  | Venkatesh |  | CLOSURE REVIEW PENDING |  |  | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process |  | Closure Review Pending
240 | T241 | 472 | OSS | IPMPLS Integration with OSS | Dashboards for IPMPLS Domain | 17-05-2025: OOB dashboards are already available in NNMi, L&T NOC team needs to review and confirm if any descripancy observed. |  | Venkatesh |  | CLOSURE REVIEW PENDING |  |  | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process |  | Closure Review Pending
241 | T242 | 472 | OSS | IPMPLS Integration with OSS | Reports | 24-05-2025: Operational Challenges 26-06-2025: Multiple reports are already available, need clarity if anything is missing from IPMPLS |  | Venkatesh |  | CLOSURE REVIEW PENDING |  |  | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process |  | Closure Review Pending
242 | T243 | 472 | OSS | GPON-NOKIA Integration with OSS | CR for Nokia API integration to close BW query and PMS related issues | 13-Sep-2025: Having dependency on A&O/NSO and service inventory deployment. 29-Aug-2025: Having dependency on A&O/NSO and service inventory deployment. 07-July-2025: L&T Remarks: As per the Tfiber suggestion, this is feasible and will be considered during A&O OEM solution deployemenet. 05-July-2025 : TFiber Comments: Available bandwidth has to be calculated before provisioning service to a customer. Available bandwidth can be achieved either from OSS or from Service Inventory systems- which already have the services provisioned data Internal discussion planned on 07-July-2025 30-June-2025 : To arrange a call with Tfiber for the discussion and conclusion Nokia provided the available upload bandwidth on PON Port but Nokia claiming that devices/AMS does not support to provide the available download bandwidth of a PON Port. This feature is not available with Nokia |  | Venkatesh |  | CLOSURE REVIEW PENDING |  |  | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process |  | Closure Review Pending
243 | T244 | 472 | OSS | Other Applications Integrations with OSS | Fetch trouble ticket status for ticket(s) by BSS CRM |  |  | Venkatesh |  | COMPLETED & APPROVED | 2025-05-26 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\OSS\T244 | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
244 | T245 | 472 | OSS | Passive Infra Integration with OSS | Integration with DG - HPE |  |  | Venkatesh |  | COMPLETED & APPROVED | 2025-05-26 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\OSS\T245 | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
245 | T246 | 472 | OSS | Passive Infra Integration with OSS | Integration with UPS - HPE |  |  | Venkatesh |  | COMPLETED & APPROVED | 2025-05-26 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\OSS\T246 | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
246 | T247 | 472 | OSS | Other Applications Integrations with OSS | Inventory Synch - Physical devices with GIS | 24-05-2025:WIP with HPE 26-06-2025: To be tested post GIS integration |  | Venkatesh |  | Open |  |  | Open | Open | Open |  | Open
247 | T248 | 472 | OSS | GPON | Nokia API integration - . PMS ( Chassi OLT ), Inventory, Device Status (ONT ) | 17-05-2025: HPE team will deliver post application upgradation 23-06-2025: for Device status, HPE said the the Nokia alarm format is wrong; post having calls with Nokia HPE reviewing the NBI documentation. 17-07-2025: Solution deplyed for one package, for other 2 package need to raise PE on 22nd July |  | Venkatesh |  | CLOSURE REVIEW PENDING |  |  | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process |  | Closure Review Pending
248 | T249 | 472 | OSS | GPON-NOKIA Integration with OSS | OLT & ONT devices status in OSS is not as per AMS | 06-06-2025: HPE requested a call with Nokia 11-06-2025: Nokia call happened and inputs were shared with HPE 23-06-2025: Post having calls with Nokia one more time last week they have share NBI documents with HPE today which they are reviewing. 22-07-2025: count matching, confirmation awaited from NOC |  | Venkatesh |  | CLOSURE REVIEW PENDING |  |  | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process |  | Closure Review Pending
249 | T250 | 472 | OSS | GPON-NOKIA Integration with OSS | ONT devices have been recovered and validated as per AMS count | 15-06-2025: validation pending from NOC |  | Venkatesh |  | CLOSURE REVIEW PENDING |  |  | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process |  | Closure Review Pending
250 | T251 | 472 | OSS | Other Applications Integrations with OSS | Fetch SLA violation by BSS billing | 26-06-2025: table to exposed with BSS, awating sevice ID from BSS and same needs to implemented in Network |  | Venkatesh |  | DEPENDENCY(Client/Ext.) |  |  | Open | Open | Open |  | Open
251 | T252 | 472 | OSS | Other Applications Integrations with OSS | Circuit performance data to BSS CRM | 26-06-2025: table to exposed with BSS, awating sevice ID from BSS and same needs to implemented in Network |  | Venkatesh |  | WIP |  |  | Open | Open | Open |  | Open
252 | T253 | 472 | OSS | DWDM | Alarm Sync issue with MCP |  |  | Venkatesh |  | COMPLETED & APPROVED | 2025-05-29 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\OSS\T253 | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
253 | T254 | 472 | OSS | GPON | Co-located OLT topology view | 17-05-2025: As per previous joint discussion with TFIBER and HPE team, this is not required.(to be discuss and remove/close) 26-06-2025: Completed, need confirmation from NOC |  | Venkatesh |  | COMPLETED & APPROVED | 2025-11-18 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\OSS\52 Artefcats_18112025 | Closed after 14-Nov-25 | Closed after 14-Nov-25 | Completed but Verification undrer Process |  | Completed & Approved
254 | T255 | 472 | OSS | Other Applications Integrations with OSS | Send SMS communication to SMS gateway |  |  | Venkatesh |  | COMPLETED & APPROVED |  | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\OSS\T255 | Completed & Approved | Closed before june-2025 | Closed after June |  | Completed & Approved
255 | T256 | 472 | OSS | IPMPLS | EPNM & PI Inventory | 09-09-2025: to show only integrated devices, need take up with HPE to change select query to excluse non SNMP device |  | Venkatesh |  | CLOSURE REVIEW PENDING |  |  | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process |  | Closure Review Pending
256 | T257 | 472 | OSS | Other Applications Integrations with OSS | Syslog Sync to Syslog Server | 17-06-2025: Support required from Sys-log team/Sarmendra & Ravikishore |  | Venkatesh |  | Open |  |  | Open | Open | Open |  | Open
257 | T258 | 472 | OSS | GIS | GIS integration | 17-05-2025: WIP with HPE team |  | Venkatesh |  | Open |  |  | Open | Open | Open |  | Open
258 | T259 | 472 | OSS | E2E | TOPOLOGY | 17-05-2025: WIP with HPE team |  | Venkatesh |  | Open |  |  | Open | Open | Open |  | Open
259 | T260 | 472 | OSS | E2E | Cross domain RCA corelation | 17-05-2025: WIP with HPE team |  | Venkatesh |  | WIP |  |  | Open | Open | Open |  | Open
260 | T261 | 472 | OSS | Infra | Data enrichment - Location information PKG A B C, etc | 17-05-2025: GIS Integration with UTM is WIP(OT dependancy) 24-06-2025: OT has shared the API for attributes required by HPE |  | Venkatesh |  | COMPLETED & APPROVED | 2025-11-18 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\OSS\52 Artefcats_18112025 | Closed after 14-Nov-25 | Closed after 14-Nov-25 | Completed but Verification undrer Process |  | Completed & Approved
261 | T262 | 472 | OSS | DC - Active infra Alarm and Auto TT | DC-Active infra Alarm, RCA and Auto TT | 17-05-2025: URL unreachable alarms are there but tickets are not getting generated. OT support required. 26-06-2025: Functionality is delivered,under stabilization. |  | Venkatesh |  | CLOSURE REVIEW PENDING |  |  | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process |  | Closure Review Pending
262 | T263 | 472 | OSS | Documentation - LLD, FAT, HA Testing | OSS Documentation - LLD, FAT, HA Testing | 17-05-2025: OT support is required. 26-06-2025: OT & HPE working on preparing the document concidering the BSOW |  | Venkatesh |  | CLOSURE REVIEW PENDING |  |  | Open | Open | Open |  | Open
263 | T264 | 472 | OSS | MoM Action | Network Downtime, fault reported to be mapped with BSS to consider during billing process | 26-06-2025: Post NSO integration |  | Venkatesh |  | WIP |  |  | Open | Open | Open |  | Open
264 | T265 | 472 | OSS | MoM Action | Feasibility Engine | 18-Nov-25: To be discussed further- BSS Dependancy 24-05-2025: WIP with HPE, OT dendancy for data. 26-06-2025: OT has provided necessary data to HPE, HPE to complete remaining development |  | Venkatesh |  | CLOSURE REVIEW PENDING |  |  | Reopened | Reopened | Completed but Verification undrer Process |  | Open
265 | T266 | 472 | OSS | MoM Action | Commercial engine to be designed along with rules to Budgetory calculation for network and customer feasibilies | 26-06-2025: this needs to be taken care by BSS side |  | Venkatesh |  | DEPENDENCY(Client/Ext.) |  |  | Open | Open | Open |  | Open
266 | T267 | 472 | OSS | MoM Action | Port Block (reservation) against Service ID | DUPLICATE POINT |  | Venkatesh |  | Duplicate |  |  | Open | Open | Open |  | Open
267 | T268 | 472 | OSS | Design & Documentation | LLD | DUPLICATE POINT |  | Venkatesh |  | Duplicate |  |  | Open | Open | Open |  | Open
268 | T269 | 472 | OSS | MoM Action | Change management process (eg. planned /Unplanned ) activities to be demonstrated | 17-05-2025: OT Team has to work and deliver 26-06-2025: change managemnt is delivered, NOC team has to confirm |  | Venkatesh |  | CLOSURE REVIEW PENDING |  |  | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process |  | Closure Review Pending
269 | T270 | 472 | OSS | MoM Action | Device status in OSS ciena inventory, details received from Ciena |  |  | Venkatesh |  | COMPLETED & APPROVED | 2025-05-26 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\OSS\T270 | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
270 | T271 | 472 | OSS | GPON | ONT & OLT vendor name should be mapped to OSS Inventory & PMS Inventory. |  |  | Venkatesh |  | COMPLETED & APPROVED |  | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\OSS\T271 | Completed & Approved | Closed before june-2025 | Closed after June |  | Completed & Approved
271 | T272 | 472 | OSS | Design & Documentation | Infra team to maintain the SSL connectivity | 17-05-2025: Dependancy on HPE upgrade and OT PS Team support 23-06-2025: New VM was requested by OT and same is provided. OT will to the testing in TND and confirm for production by 27th June 2025 |  | Venkatesh |  | COMPLETED & APPROVED | 2025-11-18 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\OSS\52 Artefcats_18112025 | Closed after 14-Nov-25 | Closed after 14-Nov-25 | Completed but Verification undrer Process |  | Completed & Approved
272 | T273 | 472 | OSS | Deployment and Installations | Deployment process - Process of building network & passive device connectivity to T-NOC through SG350, ONT (One port Voice, 2nd - Data, 3rd - Video & 4th port to T-NOC for SNMP traps) . Along with , and also all other Services to be test and provision in SG350 | 09-09-2025: Needs to be closed along with IPMPLS(RS Rao) & GPON(Sayyad) |  | Venkatesh |  | CLOSURE REVIEW PENDING |  |  | Open | Open | Open |  | Open
273 | T274 | 472 | OSS | Development and unit testing | In OSS Script File, both Nokia Primary and Secondary IPs are mentioned, however OSS is considering only the first mentioned IP even if Secondary IP is master. Due to this alarms are not reflecting in OSS. Infra team has to setup Virtual IP. |  |  | Venkatesh |  | COMPLETED & APPROVED | 2025-05-26 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\OSS\T274 | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
274 | T275 | 472 | OSS | MoM Action | In OSS management dashboard, Block count should count only Mandal OLTs and not GP OLTs. |  |  | Venkatesh |  | COMPLETED & APPROVED |  | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\OSS\T275 | Completed & Approved | Closed before june-2025 | Closed after June |  | Completed & Approved
275 | T276 | 472 | OSS | MoM Action | DG Set integration with OSS is in progress for Package A, details for DG set integration with OSS awaited from Package B and C. | 26-06-2025: Functionality is delivered, but system is not stable; same issue is escalated to HPE and OT. 22-07-2025: genset alarms are working now, confirmation required from NOC |  | Venkatesh |  | COMPLETED & APPROVED | 2025-11-18 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\OSS\52 Artefcats_18112025 | Closed after 14-Nov-25 | Closed after 14-Nov-25 | Completed but Verification undrer Process |  | Completed & Approved
276 | T277 | 472 | OSS | MoM Action | UPS and DG Device status, GP Name and LGD code & Block Name and LGD code are not available in the Passive Infra (Non-IT) inventory | 09-09-2025: Status available in NNMi & PowerBI. All other atributes available in UOC |  | Venkatesh |  | CLOSURE REVIEW PENDING |  |  | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process |  | Closure Review Pending
277 | T278 | 472 | OSS | Firewall | OSS firewall ports required for Security compliance | 09-09-2025: Security team is already taking care with help of MTR sharma |  | Venkatesh |  | CLOSURE REVIEW PENDING |  |  | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process |  | Closure Review Pending
278 | T279 | 472 | OSS | Security | Security policies to evolve related to DOT/CDOT etc.. from internal and intigration | 26-06-2025: Dependacy on Cross domain delivery |  | Venkatesh |  | CLOSURE REVIEW PENDING |  |  | Open | Open | Open |  | Open
279 | T280 | 472 | OSS | Correlations | Cross domain Corelation and exact reason for any outage in Network till ONT Port with E2E topology | 17-05-2025: WIP with HPE team |  | Venkatesh |  | Open |  |  | Open | Open | Open |  | Open
280 | T281 | 472 | OSS | MoM Action | Problem Management report for various recurring outages for the given period like i) one Unique LGD code >5 times in a Month ii) Fiber cut SPAN/Link >2 times in a month iii) Unique LGD code Down for >2 times with Same RFO iv) etc. | 18-Nov-25: Latest Records shoule be shown as a test results |  | Venkatesh |  | CLOSURE REVIEW PENDING |  |  | Reopened | Reopened | Open |  | Open
281 | T282 | 472 | OSS | MoM Action | For ONT Down cases, Some of the Alarms and cause code given by OEM is not matching with RFO provided by field engg., for example incase of Particular ONT goes down at GP level then exact RFO should be available for NOC to correlate with outages due to UPS power or other issue? | 15-09-2025: Demostrated in the Demo/UAT call |  | Venkatesh |  | CLOSURE REVIEW PENDING |  |  | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process |  | Closure Review Pending
282 | T283 | 472 | OSS | Dashboards | Alert Mechanism (event rule) when power supply is through UPS which is running on Battery backup mode then there should be alert in the form of SMS sent to field team so outages can be avoided or minimized proactively. threshold can be configured (TBD) )for given range for Battery backup status i) <50%- - Minor ii) <40%-Major iii) <30% -Critical) |  |  | Venkatesh |  | CLOSURE REVIEW PENDING |  |  | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process |  | Closure Review Pending
283 | T284 | 472 | OSS | Dashboards | Weekly, Monthly E2E Network Availability Trend for each Packages and over all per District, Zone level. | Weekly Availability is not getting calculated hence it is not-feasible |  | Venkatesh |  | Not Feasible |  |  | Open | Open | Open |  | Open
284 | T285 | 472 | OSS | Dashboards | District wise Performance report for period of infra, fiber, ISP, config issues etc. | 09-09-2025: user can download reports as on his requirement |  | Venkatesh |  | CLOSURE REVIEW PENDING |  |  | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process |  | Closure Review Pending
285 | T286 | 472 | OSS | Dashboards | Individual NOC Engineer and shift Lead Performance Measurement for handling the TT's | 17-05-2025: Artefacts needs to be collected from Sivakumar and seek approval. 26-06-2025: Waiting for Sivakumar's approval |  | Venkatesh |  | CLOSURE REVIEW PENDING |  |  | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process |  | Closure Review Pending
286 | T287 | 472 | OSS | MoM Action | Exact SPAN/Link details must be taken from GIS(Including Lat,Long) for Fiber cut/outage scenario to undserstand fix is permanent or temporarary in nature and impact on Multiple Nodes/GP’s . | 16-Oct-25: We don’t have Fiber monitoring system hence we can not achieve it 17-05-2025: Common span scenarios solution needs to be finalization pending with L&T and will be finalized based on data coming from GIS integration. 26-06-2025: Dependancy on GIS integration. Expected to be completed by 16th July and then ~30 days needed for Common span |  | Venkatesh |  | Not Feasible |  |  | Open | Open | Open |  | Open
287 | T288 | 472 | OSS | MoM Action | Report for Backup Status (success/failure) of all VM (source it from Vcenter Report) |  |  | Ravi Kishore |  | COMPLETED & APPROVED | 2025-07-05 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\OSS\Artifact-T288 | Completed & Approved | Closed before june-2025 | Closed after June |  | Completed & Approved
288 | T289 | 472 | OSS | MoM Action | DC Active infra-Health check-up /Utilization and Resource Availability report.—Hardware and Servers. (Source it from Vcenter to OSS tool) | 26-06-2025: data available in OBM, need confirmation from DC team |  | Venkatesh |  | CLOSURE REVIEW PENDING |  |  | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process |  | Closure Review Pending
289 | T290 | 472 | OSS | MoM Action | IP MPLS node status report to be automated(Zonal / Mandal/GP) along with Alias Name(Like Actual Mandal /GP names) -Feasibility check required if Alias can be updated & fetched by OSS tool | 26-06-2025: IPMPLS node status available in NNMi, need confirmation from NOC |  | Venkatesh |  | CLOSURE REVIEW PENDING |  |  | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process |  | Closure Review Pending
290 | T291 | 472 | OSS | Dashboards | IP MPLS Node/Link/Port availability & Utilization | 17-05-2025: Utilization is already available. Node and Link availability is WIP. OT Support not available to check port availability, it needs to resume. 26-06-2025: all data available now except Link availability, need confirmation from NOC |  | Venkatesh |  | CLOSURE REVIEW PENDING |  |  | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process |  | Closure Review Pending
291 | T292 | 472 | OSS | MoM Action | Customised dashboard template with available set of fields for different set of users views | 17-05-2025: OOB is available, to be reviewed with NOC |  | Venkatesh |  | CLOSURE REVIEW PENDING |  |  | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process |  | Closure Review Pending
292 | T293 | 472 | OSS | Dashboards | Service VLAN status report from EMS (Nokia and Tejas) | 24-05-2025: Inhouse solution being built by rishik |  | Venkatesh |  | CLOSURE REVIEW PENDING |  |  | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process |  | Closure Review Pending
293 | T294 | 472 | OSS | MoM Action | OSS MTTR report to include additional columns like RFO, Sub RFO, Resolution etc. |  |  | Venkatesh |  | COMPLETED & APPROVED |  | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\OSS\T294 | Completed & Approved | Closed before june-2025 | Closed after June |  | Completed & Approved
294 | T295 | 472 | OSS | MoM Action | Service Management tool has having duplicate tickets for same node which is impacting availability, outage reports. Issue needs to be fixed. | 12-06-2025: duplicate ticket booking needs to be handle by HPE, HPE working on a script to handle it. 26-06-2025: Script deplyed by HPE, need confirmation from NOC |  | Venkatesh |  | CLOSURE REVIEW PENDING |  |  | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process |  | Closure Review Pending
295 | T296 | 472 | OSS | MoM Action | Service Management dashboard should list planned outages and corelate TT if that is on same device or NW component. | 17-05-2025: OT & NSO support required |  | Venkatesh |  | Open |  |  | Open | Open | Open |  | Open
296 | T297 | 472 | DC-IT | Servers and Strorage (Deployment and Installations) | VM's Deployment Application Installations | Applications installation completed in the given VM's. Storage/resource Allocation details captured in the TNOC IT Infra Server & Storage-LLD_v_1.5 & DC Inventory master sheet. Artifacts are captured. |  | Ravi Kishore |  | COMPLETED & APPROVED |  | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\DC IT-Infra\Artifact for - T297 | Completed & Approved | Closed before june-2025 | Closed after June |  | Completed & Approved
297 | T298 | 472 | GPON | Tejas-MoM Action | Deployment process - Process of building network & passive device connectivity to T-NOC through SG350, ONT (One port Voice, 2nd - Data, 3rd - Video & 4 th port to T-NOC for SNMP traps) . Along with , and also all other Services to be test and provision in SG350 |  |  | Sayyad Pasha |  | COMPLETED & APPROVED | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T298 | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
298 | T299 | 472 | OSS | Integrating AD so that there is single user ID for all apps and they can integrate better in future if there is a need | Integration testing done for all apps that are ready currently except Alepo. Apps like HP OSS, Cisco ISE and other such applications are already integrated. We can switch IDs to AD anytime | 28-Nov-25: The Alepo team is integrating AD Once done these points will be closed. Once AD integration happen for Aleppo this point also will be closed along with T333. |  | Bajiba Shaik |  | WIP |  |  | Open | Open | Open |  | Open
299 | T300 | 472 | OSS | Configuration and best practices | User IDs created. Need to work with users for testing for NOC desktops | Artifacts will be created and submitted on 03 Jul 25 |  | Bajiba Shaik |  | COMPLETED & APPROVED |  | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\NW-Security\T300 | Completed & Approved | Closed before june-2025 | Closed after June |  | Completed & Approved
300 | T301 | 472 | Security & Regulatory Compliance | Configuration | On A-10 -Configuration done on LB side. WAF will be configure with License | 28-Nov-25: Gathering artifacts from other teams. A10 AMC not renewed , Awaiting AMC renewal with WAF features |  | Bajiba Shaik |  | WIP |  |  | Open | Open | Open |  | Open
301 | T302 | 472 | Security & Regulatory Compliance | Functional AT | Will start next week as KT happened this week for all the new resources | 28-Nov-25: Document preparation in progress once done points will be closed. KT has been done. |  | Bajiba Shaik |  | CLOSURE REVIEW PENDING |  | Artefacts to be Submitted | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process |  | Closure Review Pending
302 | T303 | 472 | OSS | Configuration | OSS- Redware LB-There were configuration issues and have been sorted our by having multiple sessions over the past few weeks | Artifact created and will be submitted to customer on 03 Jul 25. |  | Bajiba Shaik |  | COMPLETED & APPROVED | 2025-10-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\NW-Security\T303_28-Oct-25.pdf | Closed | Closed After 14-Oct | Completed but Verification undrer Process |  | Completed & Approved
303 | T304 | 472 | Security & Regulatory Compliance | Functional AT | Radware LB - Will start next week as KT happened this week for all the new resources | 28-Nov-25: Document preparation in progress once done points will be closed. KT has been done. |  | Bajiba Shaik |  | WIP |  |  | Open | Open | Open |  | Open
304 | T305 | 472 | OSS | Configuration | We have identified memory needed. Need help with space allocation for VM and also need license for a syslog server. ( we can also use Default Linux daemon) Syslog | [17/09/2025] Syslog integration with both Redhat and Windows servers Completed. |  | Ravi Kishore |  | COMPLETED & APPROVED | 2025-09-19 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\OSS\T305 | Completed & Approved | Closed before june-2025 | Closed after June |  | Completed & Approved
305 | T306 | 472 | Security & Regulatory Compliance | Documentation | Customer has requested a complete Security LLD that states how our security architechture is and how different security products talk to each other | 28-Nov-25: Document preparation in progress once done points will be closed. Completed and Review pending. New changes will be incorporated as an addendum to design. |  | Bajiba Shaik |  | WIP |  |  | Open | Open | Open |  | Open
306 | T307 | 472 | Security & Regulatory Compliance | User Access Rights | Cisco: PKGA-testing in WIP, PKGB&C-will be replicated after PKGA completion GPON: Segregation is done, implementation is WIP DWDM: Segregation is done, implementation is WIP HPE OSS: User to access mapping is done, implementation WIP by hp team Other Apps: Will have meetings this week and sort it out. | #VALUE! |  | Bajiba Shaik |  | COMPLETED & APPROVED | 2025-11-01 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\NW-Security\M1133.pdf | Completed & Approved | Closed After 14-Oct | Open |  | Completed & Approved
307 | T308 | 472 | Security & Regulatory Compliance | IPDR | Developing in-house solution, also exploring with external vendors. 3 vendors declined. | 27.06.25 , IPDR solution operational , pending document will be submitted by 1st week of Jul'25 |  | Jayant Madavi |  | COMPLETED & APPROVED | 2025-10-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\NW-Security\T303_28-Oct-25.pdf | Closed | Closed After 14-Oct | Open |  | Completed & Approved
308 | T309 | 472 | Security & Regulatory Compliance | Storage | Storage requirement worked out and given to contract team. PO to be issued(Syslog) | 25-Sep-2025: Artefacts to be uploaded, Need to provide current consumption of storage, incremental log will be added to existing storage after adding 18 TB additional storage . |  | Bajiba Shaik |  | COMPLETED & APPROVED |  | Artefacts Need to upload | Completed & Approved | Closed before june-2025 | Closed after June |  | Completed & Approved
309 | T310 | 472 | Security & Regulatory Compliance | NAT | Developed in-house solution, also exploring with external vendors. 3 vendors declined. In-house solution is ready for demo, tested with the sample data.( | 25-Sep-2025: Detailed discussion will be taken up later(Sanjay will brief background against this point) |  | Bajiba Shaik |  | COMPLETED & APPROVED | 2025-10-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\NW-Security\T303_28-Oct-25.pdf | Completed & Approved | Closed before june-2025 | Closed after June |  | Completed & Approved
310 | T311 | 472 | Security & Regulatory Compliance | QoS Reporting | QoS Reporting related to all parameters | Completed and Review pending.FAT documents were submitted to TPA , However it has some common observation which will be discussed with TPA team by Mr Sharma. |  | Bajiba Shaik |  | COMPLETED & APPROVED | 2025-10-30 | \\172.28.9.23\tnocreports\Approved Process and SOP_ T Fiber\SOP | Closed | Closed After 14-Oct | Open |  | Completed & Approved
311 | T312 | 472 | Security & Regulatory Compliance | Regulatory compliance | SLA Reporting for Cell Tower and GIs |  |  | Siva Kumar |  | COMPLETED & APPROVED | 2025-05-13 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\T312 | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
312 | T313 | 472 | Security & Regulatory Compliance | Regulatory compliance | Communication made to T-Fiber. Procedure need to be finalized for remote access | 28-Nov-25: Gathering artifacts from other teams |  | Bajiba Shaik |  | DEPENDENCY(Client/Ext.) |  |  | Open | Open | Open |  | Open
313 | T314 | 472 | Security & Regulatory Compliance | External Audit and VAPT | External Audit and VAPT (Tfiber will be arranging a partner for third party audit) | 28-Nov-25: VAPT is going on, once VAPT is done points will be closed. T Fiber to conduct the Audit and VAPT |  | Bajiba Shaik |  | DEPENDENCY(Client/Ext.) | 2025-12-19 |  | Open | Open | Open |  | Completed & Approved
314 | T315 | 472 | BMS | Fire and Safety Drill | Certificate and artefacts of last fire & safety drill submitted |  |  | Bajiba Shaik |  | COMPLETED & APPROVED |  | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\NW-Security\T315 | Completed & Approved | Closed before june-2025 | Closed after June |  | Completed & Approved
315 | T316 | 472 | Security & Regulatory Compliance | User Traceability | User access traceability |  |  | Bajiba Shaik |  | COMPLETED & APPROVED | 2025-05-19 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\NW-Security\T316 | Completed & Approved | Closed before june-2025 | Closed after June |  | Completed & Approved
316 | T317 | 472 | OSS | Certifications | ITIL Product certification |  |  | Venkatesh |  | COMPLETED & APPROVED | 2025-09-12 | \\172.28.9.34\SHARE DRIVE\Artefacts_T-Fiber TNOC Tracker\OSS | Completed & Approved | Closed before june-2025 | Closed after June |  | Completed & Approved
317 | T318 | 472 | Security & Regulatory Compliance | Policy Implementation | Network Forensic |  |  | Bajiba Shaik |  | COMPLETED & APPROVED | 2025-05-19 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\NW-Security\T318 | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
318 | T319 | 472 | Security & Regulatory Compliance | Policy Implementation | Network Hardening | All unauthorised access has been blocked at firwall level. All USB is disables at NOC . All unysed port has been hardened |  | Bajiba Shaik |  | COMPLETED & APPROVED | 2025-10-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\NW-Security\T36_28-Oct-25.pdf | Closed | Closed After 14-Oct | Open |  | Completed & Approved
319 | T320 | 472 | Security & Regulatory Compliance | Policy Implementation | Network Penetration Test | 28-Nov-25: VAPT is going on, once VAPT is done points will be closed. PT will conducted once Ext audit team arrives |  | Bajiba Shaik |  | DEPENDENCY(Client/Ext.) |  |  | Open | Open | Open |  | Open
320 | T321 | 472 | Security & Regulatory Compliance | MoM Action | Firewall policy compare from DC to DR validation check for redundancy | May be clubed with point T 71 all Policy will be compared with current configuration of firewall and be submitted . 30-Oct-25: Duplicate to Point T71. DR does not have a public-facing application, and DR and DC firewalls are different |  | Bajiba Shaik |  | COMPLETED & APPROVED | 2025-11-01 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\NW-Security\T71_31-Oct-25.pdf | Completed & Approved | Closed After 14-Oct | Open |  | Completed & Approved
321 | T322 | 472 | Security & Regulatory Compliance | MoM Action | Day 0 attacks for any government departments lifecycle (GIBB to be protected from the day of connection) | 28-Nov-25: Gathering artifacts from other teams. will be closed with implementation of URL filtering facilities at IPS |  | Bajiba Shaik |  | DEPENDENCY(Client/Ext.) |  |  | Open | Open | Open |  | Open
322 | T323 | 472 | Security & Regulatory Compliance | Storage | User access logs& Commands to be maintained for 2 years | Completed and approved |  | Bajiba Shaik |  | COMPLETED & APPROVED | 2025-05-19 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\NW-Security\T323 | Completed & Approved | Closed before june-2025 | Closed after June |  | Completed & Approved
323 | T324 | 472 | Security & Regulatory Compliance | Deployment and Installations | Syslog to maintain for 2 years |  |  | Ravi Kishore |  | COMPLETED & APPROVED | 2025-05-14 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\Security\T324 | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
324 | T325 | 472 | Security & Regulatory Compliance | Policy Implementation | Organizational Security Policy | 28-Nov-25: Document preparation in progress once done points will be closed. Security policy has been made , however same need clarification from customer to incorporate deviation from actual points. |  | Bajiba Shaik |  | DEPENDENCY(Client/Ext.) |  |  | Open | Open | Open |  | Open
325 | T326 | 472 | Security & Regulatory Compliance | Report | IPDR static IP report |  |  | Bajiba Shaik |  | COMPLETED & APPROVED | 2025-10-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\NW-Security\T303_28-Oct-25.pdf | Closed | Closed After 14-Oct | Closed after June |  | Completed & Approved
326 | T327 | 472 | Security & Regulatory Compliance | Report | Syslog NAT report |  |  | Bajiba Shaik |  | COMPLETED & APPROVED | 2025-05-19 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\NW-Security\T327 | Completed & Approved | Closed before june-2025 | Closed after June |  | Completed & Approved
327 | T328 | 472 | Security & Regulatory Compliance | AAA | ISE-Completed, Alepo-Completed for Nokia GPON, Accounting feature demo to be done for Tejas GPON and Ciena DWDM | Confirmation of purchase of ISE. License needed to upgrade for HA |  | Bajiba Shaik |  | COMPLETED & APPROVED | 2025-10-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\NW-Security\M1139_29-Oct-25.pdf | Closed | Closed After 14-Oct | Completed but Verification undrer Process |  | Completed & Approved
328 | T329 | 472 | Security & Regulatory Compliance | MoM Action | Cisco ISE to be integrated with AD for Authentication |  |  | Bajiba Shaik |  | COMPLETED & APPROVED | 2025-05-19 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\NW-Security\T153 | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
329 | T330 | 472 | Security & Regulatory Compliance | MoM Action | syslog storage requirement for respective OEM devices |  |  | Bajiba Shaik |  | COMPLETED & APPROVED |  | Artefacts Need to upload | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
330 | T331 | 472 | Security & Regulatory Compliance | MoM Action | Tejas OLT to integrate with Alepo AAA Tejas EMS to integrate with Alepo AAA | Alepo AMC Support required for Evidence submission to customer |  | Bajiba Shaik |  | COMPLETED & APPROVED | 2025-11-12 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T171 | Completed & Approved | Closed after 07-Nov-25 | Open |  | Completed & Approved
331 | T332 | 472 | Security & Regulatory Compliance | MoM Action | Nokia AMS to integrate with Alepo AAA |  |  | Bajiba Shaik |  | COMPLETED & APPROVED |  | Artefacts Need to upload | Completed & Approved | Closed before june-2025 | Closed after June |  | Completed & Approved
332 | T333 | 472 | Security & Regulatory Compliance | MoM Action | Alepo AAA to be integrated with AD | 28-Nov-25: The Alepo team is integrating AD Once done these points will be closed. SOW, CR and BOQ Shared for approval and consideration. |  | Bajiba Shaik |  | DEPENDENCY(Client/Ext.) |  |  | Open | Open | Open |  | Open
333 | T334 | 472 | Security & Regulatory Compliance | Functional AT | Cisco Firewall, ISE, IPS/IDS Functional AT | 28-Nov-25: Document preparation in progress once done points will be closed. Completed and Review pending. |  | Bajiba Shaik |  | WIP |  |  | Open | Open | Open |  | Open
334 | T335 | 472 | Security & Regulatory Compliance | Design & Documentation | Security LLD to finalised and submitted to T-Fiber for approval. Customer has requested a complete Security LLD that states how our security architechture is and how different security products talk to each other | 28-Nov-25: Document preparation in progress once done points will be closed. Duplicate of point 306 |  | Bajiba Shaik |  | WIP |  |  | Open | Open | Open |  | Open
335 | T336 | 472 | IP/MPLS | T-Cell Solution Design | Egress QoS policy for ASR907 |  |  | RS Rao |  | COMPLETED & APPROVED | 2025-05-05 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\QOS for TFiber Network LLD V2.0 - T339, T340, T341, T342.pdf | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
336 | T337 | 472 | IP/MPLS | T-Cell Solution Design | Egress QoS policy for ASR920 – QoS policy to be applied on Gigabit interfaces instead of on Port Channel (LAG) which is not suitable for CIR application |  |  | RS Rao |  | COMPLETED & APPROVED | 2025-05-05 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\TFIBER T-CELL Service Design & Solution V4.3 T197, T336, T337, T338.pdf | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
337 | T338 | 472 | IP/MPLS | T-Cell Solution Design | Additional scenarios for generic Cell tower Solution shared with Cisco, Cisco to check and provide the design |  |  | RS Rao |  | COMPLETED & APPROVED | 2025-05-05 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\TFIBER T-CELL Service Design & Solution V4.3 T197, T336, T337, T338.pdf | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
338 | T339 | 472 | IP/MPLS | MPLS Core network QoS | Egress Policy structure and BW as per discussion |  |  | RS Rao |  | COMPLETED & APPROVED | 2025-05-05 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\QOS for TFiber Network LLD V2.0 - T339, T340, T341, T342.pdf | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
339 | T340 | 472 | IP/MPLS | MPLS Core network QoS | Egress QoS policy for ASR99xx |  |  | RS Rao |  | COMPLETED & APPROVED | 2025-05-05 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\QOS for TFiber Network LLD V2.0 - T339, T340, T341, T342.pdf | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
340 | T341 | 472 | IP/MPLS | MPLS Core network QoS | Egress QoS policy for ASR907 |  |  | RS Rao |  | COMPLETED & APPROVED | 2025-05-05 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\QOS for TFiber Network LLD V2.0 - T339, T340, T341, T342.pdf | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
341 | T342 | 472 | IP/MPLS | MPLS Core network QoS | Egress QoS policy for ASR920 |  |  | RS Rao |  | COMPLETED & APPROVED | 2025-05-05 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\QOS for TFiber Network LLD V2.0 - T339, T340, T341, T342.pdf | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
342 | T343 | 472 | IP/MPLS | Service Solution | Design Document require SDC content to GI | 22-Sep-25: Need to review plan and approve 12-Sep-25 : Peering plan submitted as per discussion on 11-Sep-25 01-Jul-25 : Design document submitted with suggested approaches. Require inputs from TFiber to conduct PoC and finalize service design. |  | RS Rao |  | Completed & Approved | 2025-10-31 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\T-Fiber & SDC Peering Plan V1.1 - T193 T343.pdf | Closed | Closed After 14-Oct | Open |  | Completed & Approved
343 | T344 | 472 | IP/MPLS | Service Solution | Solution document for GI connectivity (intranet & internet) TVPN | 22-Sep-25:Artefacts to be uploaded 01-Jul-25 : Design document submitted with suggested approaches. Require inputs from TFiber to conduct PoC and finalize service design. |  | RS Rao |  | COMPLETED & APPROVED | 2025-09-23 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\T-FIBER RYTHUVEDIKA VC L3VPN Solution LLD V1.0.docx | Completed & Approved | Closed before june-2025 | Closed after June |  | Completed & Approved
344 | T345 | 472 | TNOC-Ops | NOC Operation | OEM Professional services for all products post NOC operationalization | AMC and TAC support provided | Not interlinked to Go live | Ahmad |  | Open |  |  | Open | Open | Open |  | Open
345 | T346 | 472 | BSS | TNOC-Ops | all EMS Devices for provisioning through BSS | BSS will not directly interact with any EMS, it will be via A&O. |  | Sandeep Deshmukh |  | Open |  |  | Open | Open | Open |  | Open
346 | T347 | 472 | BSS | Functional AT | Lead to Cash, Order to cash & Request to resolution to operate and demonestrate |  |  | Sandeep Deshmukh |  | CLOSURE REVIEW PENDING |  |  | Open | Open | Open |  | Closure Review Pending
347 | T348 | 472 | TNOC-Ops | NOC Operation | Placement of T-Fiber logo and Telangana State emblem in TNOC reception area | Logo design agreed with customer. Additional places sign boards to be placed as part of CR, give to commercail for quotation. | Not interlinked to Go live | Ahmad |  | Open |  |  | Open | Open | Open |  | Closure Review Pending
348 | T349 | 472 | Security & Regulatory Compliance | Design & Documentation | TNOC operational framework with respect to processes (Incident, Problem, Major Event, Change, Version, Security, AAA, Planned Event, SLA Management etc) | Customer has to choose what framework they ned to follow for end to end governance i.e COBIT, COSO, SABSA etc. Security SOP is in progress. will be aligned only after policy is approved |  | Bajiba Shaik |  | COMPLETED & APPROVED | 2025-11-01 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\NW-Security\T349_31-Oct-25.pdf | Completed & Approved | Closed After 14-Oct | Open |  | Completed & Approved
349 | T350 | 472 | TNOC-Ops | NOC Operation | Manpower Structure for TNOC Operationalization |  |  | Ahmad |  | COMPLETED & APPROVED | 2025-05-13 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\T166 | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
350 | T351 | 472 | TNOC-Ops | Design & Documentation | Helpdesk Readiness Plan | 01-Dec-25: its documentation 1. Soft training completed on 06&07 Sep-24 2. All Resources will be from L&T only- Resource available to handle current calls 3. updated process document shared, Pending for discussion 4. SOP Submitted for inbound and outbound calls- Discussion Pending 5. Regulatory reports were available(DOT) 6. Integration with OSS and BSS is Pending 7. Based on trainer suggestion, implemented day to day and weekly assestments 8. Neox call Manager functioanlity validated as standlone 9. All Features required for Call Manager completed including Business Helpdesk 10. LLD and RFP Compliance also ready for review |  | Siva Kumar |  | WIP |  |  | Open | Open | Open |  | Open
351 | T352 | 472 | TNOC-Ops | MoM Action | Induction Training program – To be developed and feedback mechanism to be considered, for newly on-boarded resources |  |  | Siva Kumar |  | COMPLETED & APPROVED | 2025-05-13 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\T166 | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
352 | T353 | 472 | TNOC-Ops | Helpdesk | Regulatory Compliance_PMR on QoS |  |  | Siva Kumar |  | COMPLETED & APPROVED | 2025-05-13 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\T353 | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
353 | T354 | 472 | TNOC-Ops | NOC Operation | Resource deployment at TNOC |  |  | Ahmad |  | COMPLETED & APPROVED | 2025-05-13 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\T166 | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
354 | T355 | 472 | TNOC-Ops | NOC Operation | Interlocking and Interdependencies with resources of package B & C operating at TNOC |  |  | Ahmad |  | COMPLETED & APPROVED | 2025-05-26 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\T166 | Completed & Approved | Closed before june-2025 | Closed after June |  | Completed & Approved
355 | T356 | 472 | TNOC-Ops | NOC Operation | OEM Escalation processes for NOC Applications, DBs, IT Infra and Network along with TATs aligned to SLA |  |  | Siva Kumar |  | COMPLETED & APPROVED | 2025-07-08 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\TNOC | Completed & Approved | Closed before june-2025 | Closed after June |  | Completed & Approved
356 | T357 | 472 | TNOC-Ops | NOC Operation | Spare for Business continuity - RS&R for NOC and DR elements and assets | List shared with commercial for ordering. WIP | Not interlinked to Go live | Ahmad | Dependent on Commercials | WIP |  |  | Open | Open | Open |  | Open
357 | T358 | 472 | TNOC-Ops | Functional AT | Network HOTO and KT from Respective Domain and Packages | BSS, NSO and Security SOP training pending. Rest all done |  | Siva Kumar |  | WIP |  |  | Open | Open | Open |  | Open
358 | T359 | 472 | OSS | NOC Operation | OSS - stability and Operational issues with respect to inventory, ticketing and utilization modules | 26-06-2025: Frequent stability issues are because of NNMi, OBM instability and Vendor asking for upgrade |  | Venkatesh |  | Open |  |  | Open | Open | Open |  | Open
359 | T360 | 472 | TNOC-Ops | NOC Operation | Domain wise training | BSS, NSO and Security SOP training pending. On the job training happening for OSS. Rest all domains done. | Not interlinked to Go live | Ahmad |  | Open |  |  | Open | Open | Open |  | Open
360 | T361 | 472 | TNOC-Ops | Helpdesk | Updated Process document Submission after last Meeting with T Fiber Management |  |  | Siva Kumar |  | COMPLETED & APPROVED | 2025-05-13 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\T361 | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
361 | T362 | 472 | TNOC-Ops | Helpdesk | Categorisation of incoming calls to be detailed and IVR to bilingual(Incoming IVR call flow) |  |  | Siva Kumar |  | COMPLETED & APPROVED | 2025-05-13 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\T362 | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
362 | T363 | 472 | TNOC-Ops | Helpdesk | IVR Recording file required for call landing and Hold time |  |  | Siva Kumar |  | COMPLETED & APPROVED | 2025-05-13 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\T363 | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
363 | T364 | 472 | TNOC-Ops | Helpdesk | Integration with BSS and OSS | 01-Dec-25:Depends on IVR flow approval 11-Sep-25: Basic integration completed with BSS and HPSM(Ticketing). IVR has to be freezed to implement same. As per Neox is one time configuration but Since its ongoing changes will happen in IVR, So it would be configurble as per L&T/T Fiber- Which to be discussed. 360 View also Pending from BSS |  | Siva Kumar |  | WIP |  |  | Open | Open | Open |  | Open
364 | T365 | 472 | TNOC-Ops | Helpdesk | Integration of SMS, E-Mail | 29-Nov-25:E-mail & SMS Integration completed. SMS testing pending due to no balance in SMS striker portal. 28 Apri-2025: TFIBER to share SMS GW details to integrate with OSS/BSS. Integration must be configurable without any cost impact to TFIBER. |  | Siva Kumar |  | WIP |  |  | Open | Open | Open |  | Open
365 | T365 | 472 | TNOC-Ops | Helpdesk | Integration of Whatsapp, Chatbot | 01-Dec-25:Not feasible 11-Sep-25: Not Part of RFP and Existing product didn’t support, need to upgrade to Omni based Solution. |  | Siva Kumar |  | Not Feasible |  |  | Open | Open | Open |  | Open
366 | T366 | 472 | TNOC-Ops | Helpdesk | Fancy 4 digit number for Helpdesk or Tollfree number Availability |  |  | Siva Kumar |  | COMPLETED & APPROVED | 2025-07-19 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\T366 | Completed & Approved | Closed before june-2025 | Closed after June |  | Completed & Approved
367 | T367 | 472 | TNOC-Ops | Helpdesk | Training for Agents and Helpdesk Manager |  |  | Siva Kumar |  | COMPLETED & APPROVED | 2025-05-13 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\T367 | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
368 | T368 | 472 | TNOC-Ops | Helpdesk | Interface mechanism between T-NOC Helpdesk and District Collector offices for complaints that may be made directly(Walk-in) to District Collector office, provision for a mini-Helpdesk node at each district, provide a facility/ hotline using which an authorised person can log a call / complaint on behalf of the District Collector Office, such mechanism to be similar to the Direct walk-in channel for customer complaints at T-NOC |  |  | Siva Kumar |  | COMPLETED & APPROVED | 2025-07-19 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\T368 | Completed & Approved | Closed before june-2025 | Closed after June |  | Completed & Approved
369 | T369 | 472 | TNOC-Ops | Helpdesk | If T-NOC is totally down for some reason like fire, earthquake, lockdown etc….then how Helpdesk will work from DR? | 01-Dec-25: Helpdesk plan ready, but expecting was complete BCP Solution |  | Siva Kumar |  | WIP |  |  | Open | Open | Open |  | Open
370 | T370 | 472 | TNOC-Ops | Helpdesk | If all 10 lines are engaged for a longer time. Can the Helpdesk system call back to that missed call? | 11-Sep-25: OEM confirmed this feature is not available/feasible Based on CDR record with Agent and Manager Login, Call back can be done manually with CDR or Agent Call report. It will be displayed in queue to agent. But Missed call to be handled by outbound team. Which required complete Set of call Center. If required Helpdesk Manager will review missed call to take action accordingly. |  | Siva Kumar |  | WIP |  |  | Open | Open | Open |  | Open
371 | T371 | 472 | GPON | Nokia | * Testing done for new build in T-Fiber test lab . * Plan event for OLTs new SW upgradation in production environment. | 15-Nov-25: Below is the breakup of pending OLT status PKG-A : 875/883 PKG-B : 622/653 PKG-C : 419/420 All the OLTs reachabled to AMS are upgraded successfully. Having dependecny on PKG-A/B/C field teams to make unreachable OLTs to reachable |  | Sayyad Pasha |  | DEPENDENCY(Client/Ext.) |  |  | Open | Open | Open |  | Open
372 | T372 | 472 | GPON | Nokia | TACACS Feature |  |  | Sayyad Pasha |  | COMPLETED & APPROVED | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T372 | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
373 | T373 | 472 | NSO | Deployment and Installations | HSI (High Speed Internet to Household) implementation | Post 24.06.25 review and direction, working for a alternate options for NSO. will come back as earliest with closure plan. |  | Jayant Madavi |  | DEPENDENCY(Client/Ext.) |  |  | Open | Open | Open |  | Open
374 | T374 | 472 | NSO | Deployment and Installations | IPTV to Household implementation | Post 24.06.25 review and direction, working for a alternate options for NSO. will come back as earliest with closure plan. |  | Jayant Madavi |  | DEPENDENCY(Client/Ext.) |  |  | Open | Open | Open |  | Open
375 | T375 | 472 | NSO | Deployment and Installations | VOIP to Household implementation | Post 24.06.25 review and direction, working for a alternate options for NSO. will come back as earliest with closure plan. |  | Jayant Madavi |  | DEPENDENCY(Client/Ext.) |  |  | Open | Open | Open |  | Open
376 | T376 | 472 | NSO | Deployment and Installations | Internet to GI (Govt. Institution) implementation | Post 24.06.25 review and direction, working for a alternate options for NSO. will come back as earliest with closure plan. |  | Jayant Madavi |  | DEPENDENCY(Client/Ext.) |  |  | Open | Open | Open |  | Open
377 | T377 | 472 | NSO | Deployment and Installations | CCTV Unicast implementation | Post 24.06.25 review and direction, working for a alternate options for NSO. will come back as earliest with closure plan. |  | Jayant Madavi |  | DEPENDENCY(Client/Ext.) |  |  | Open | Open | Open |  | Open
378 | T378 | 472 | NSO | Deployment and Installations | CCTV Multicast implementation | Post 24.06.25 review and direction, working for a alternate options for NSO. will come back as earliest with closure plan. |  | Jayant Madavi |  | DEPENDENCY(Client/Ext.) |  |  | Open | Open | Open |  | Open
379 | T379 | 472 | NSO | Deployment and Installations | Cell Tower L2VPN implementation | Post 24.06.25 review and direction, working for a alternate options for NSO. will come back as earliest with closure plan. |  | Jayant Madavi |  | DEPENDENCY(Client/Ext.) |  |  | Open | Open | Open |  | Open
380 | T380 | 472 | NSO | Deployment and Installations | Dhanush Telemedicine Application implementation | Post 24.06.25 review and direction, working for a alternate options for NSO. will come back as earliest with closure plan. |  | Jayant Madavi |  | DEPENDENCY(Client/Ext.) |  |  | Open | Open | Open |  | Open
381 | T381 | 472 | NSO | Deployment and Installations | SDC content to Household and GI implementation | Post 24.06.25 review and direction, working for a alternate options for NSO. will come back as earliest with closure plan. |  | Jayant Madavi |  | DEPENDENCY(Client/Ext.) |  |  | Open | Open | Open |  | Open
382 | T382 | 472 | BSS | Development and unit testing | EY need to present landing page for suggestion - Design features of web page |  |  | Sandeep Deshmukh |  | Open | 2025-07-16 | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\BSS\Artifact_T382 | Open | Open | Open |  | Open
383 | T383 | 472 | DC-IT | Functional AT | Cisco prime infrastructure AT | 22-Sep-25: IPMPLS Domain team to submit detailed remarks on raised queries. 08-Jul-2025 - Sandeep will come back by EoD today on extension of Cisco support renewal 01-Jul-25 : Revised FAT documents submission pending (TPA observations to be included) OEM(Cisco) suport is required to show the new test cases, Inputs provided to OEM on 14th May & 30th Jun. OEM onboarding is in progress & LnT Contracts team is coordinating |  | RS Rao |  | Open |  |  | Open | Open | Open |  | Closure Review Pending
384 | T384 | 472 | IP/MPLS | Security | GCT implementation | Confirmed from IP-MPLS team for GCT implementation. |  | Bajiba Shaik |  | COMPLETED & APPROVED | 2025-11-01 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\NW-Security\T384_31-Oct-25.pdf | Closed | Closed After 14-Oct | Open |  | Completed & Approved
385 | T385 | 472 | NSO | Design & Documentation | solution document - GI internet solution |  |  | RS Rao |  | COMPLETED & APPROVED | 2025-05-05 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\IPMPLS\T-FIBER T-Net for GI Broadband Service Design LLD V1.1 - T188.pdf | Completed & Approved | Closed before june-2025 | Closed after June |  | Completed & Approved
386 | T386 | 472 | Security & Regulatory Compliance | Testing | Network audit and certification by ISO certified agency(Tfiber will be arranging a partner for third party audit) | 28-Nov-25: VAPT is going on, once VAPT is done points will be closed. Subject to start of certification process. |  | Bajiba Shaik |  | DEPENDENCY(Client/Ext.) | 2025-12-19 |  | Open | Open | Open |  | Completed & Approved
387 | T387 | 472 | Security & Regulatory Compliance | Regulatory compliance | SLA Reporting for products other than Cell Tower and GIs |  |  | Siva Kumar |  | COMPLETED & APPROVED | 2025-05-13 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\HELPDESK\T387 | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
388 | T388 | 472 | OSS | Helpdesk | OSS Integration with Helpdesk | 17-05-2025: Artefacts needs to be collected from Sivakumar and seek approval. 26-06-2025: completed from OSS end |  | Venkatesh |  | CLOSURE REVIEW PENDING |  |  | Completed but Verification undrer Process | Completed but Verification undrer Process | Completed but Verification undrer Process |  | Closure Review Pending
389 | T389 | 472 | OSS | OSS | BBNL Report stabilization |  |  | Venkatesh |  | COMPLETED & APPROVED |  | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\OSS\T389 | Completed & Approved | Closed before june-2025 | Closed after June |  | Completed & Approved
390 | T390 | 472 | OSS | OSS Dashboards | OSS Power BI Dashboard | 18-Nov-25: Power BI not there, Same to be shown in new Application 09-09-2025: Requested reports are available, if any additional reports needed that can be incorporated |  | Venkatesh |  | CLOSURE REVIEW PENDING |  |  | Reopened | Reopened | Completed but Verification undrer Process |  | Open
391 | T391 | 472 | OSS | OSS | Auto TT for Genset | 26-06-2025: Confirmation awaited from NOC |  | Venkatesh |  | COMPLETED & APPROVED | 2025-11-18 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\OSS\52 Artefcats_18112025 | Closed after 14-Nov-25 | Closed after 14-Nov-25 | Completed but Verification undrer Process |  | Completed & Approved
392 | T392 | 472 | OSS | OSS | BBNL Status and Availability API integration |  |  | Venkatesh |  | COMPLETED & APPROVED |  | \\172.28.9.34\share drive\Artefacts_T-Fiber TNOC Tracker\OSS\T392 | Completed & Approved | Closed before june-2025 | Closed after June |  | Completed & Approved
393 | 394 | 472 | DC-IT | License | Once excel license for VM |  |  | Ravi Kishore |  | COMPLETED & APPROVED | 2025-07-08 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\TNOC\Artifact for - 394 | Completed & Approved | Closed before june-2025 | Closed after June |  | Completed & Approved
394 | T395 | 472 | TNOC-Ops | Payments | SMS Gateway recharge | SMS payment pending from Tfiber |  | Ahmad |  | COMPLETED & APPROVED | 2025-07-08 | Artefacts not Required | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
395 | 396 | 472 | TNOC-Ops | AMC | AMC status including HPE/OT | In Place |  | Ahmad |  | COMPLETED & APPROVED | 2025-07-08 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\TNOC | Completed & Approved | Closed before june-2025 | Closed after June |  | Completed & Approved
396 | 397 | 472 | TNOC-Ops | Security | Access cards - 38 QTY | Access card procured |  | Ahmad |  | COMPLETED & APPROVED | 2025-07-08 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\TNOC | Completed & Approved | Closed before june-2025 | Closed after June |  | Completed & Approved
397 | 398 | 472 | GPON | Tejas | L&T is asked to submit response against untdertakings for the GPON Tejas issues |  |  | Sayyad Pasha |  | COMPLETED & APPROVED | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\Tejas Undertaking | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
398 | 399 | 472 | GPON | Tejas | Requested Tejas to enable the TR-069 for T-Fiber deployed elements | 20-Sep-25: Artefacts submiited and approved MoM point Not in RFP and L&T confirmed this is not in scope. However, confirmation awaited from OEM on the shared list of parameters |  | Sayyad Pasha |  | COMPLETED & APPROVED | 2025-09-20 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\399 | Completed & Approved | Closed before june-2025 | Closed after June |  | Completed & Approved
399 | T400 | 472 | GPON | Tejas | Accounting for Tejas OLT and EMS |  |  | Sayyad Pasha |  | COMPLETED & APPROVED | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T167 | Completed & Approved | Closed before june-2025 | Closed |  | Completed & Approved
400 | 401 | 472 | GPON | Tejas | Accounting: All the parameters are not available in service created and Activated log(Including creation/activation of UNI) |  |  | Sayyad Pasha |  | COMPLETED & APPROVED | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T167 | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
401 | 402 | 472 | GPON | Tejas | Accounting: All the parameters are not available in service deactivated and deleted log(Including deactivation/deletion of UNI) |  |  | Sayyad Pasha |  | COMPLETED & APPROVED | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T167 | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
402 | 403 | 472 | GPON | Tejas | Accounting: Log is not available for OLT reboot |  |  | Sayyad Pasha |  | COMPLETED & APPROVED | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T167 | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
403 | 404 | 472 | GPON | Tejas | Accounting: Log is not available for ONT reboot |  |  | Sayyad Pasha |  | COMPLETED & APPROVED | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T167 | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
404 | 405 | 472 | GPON | Tejas | Accounting: Log is not available for the change of OLT location parameter from EMS |  |  | Sayyad Pasha |  | COMPLETED & APPROVED | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T167 | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
405 | 406 | 472 | GPON | Tejas | Enabling TACACS in Tejas OLT |  |  | Sayyad Pasha |  | COMPLETED & APPROVED | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T167 | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
406 | 407 | 472 | GPON | Tejas | CIR/PIR in OLT/EMS | 20-Sep-25: CIR and PIR are different parameters but Tejas OLT considered only CIR not PIR, After combined recent meeting with OEM agreed to provide an alternate solution for config CIR and PIR seperately. Update awaited from OEM Tejas to provide the solution and demo for this issue. Update awaited from OEM |  | Sayyad Pasha |  | DEPENDENCY(Client/Ext.) |  |  | Open | Open | Open |  | Open
407 | 408 | 472 | GPON | Tejas | Port Description is not available for ONT Eth Ports |  |  | Sayyad Pasha |  | COMPLETED & APPROVED | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\ONT Ports description | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
408 | 409 | 472 | GPON | Tejas | Unable to modify the Service Name |  |  | Sayyad Pasha |  | COMPLETED & APPROVED | 2025-07-03 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\409 | Completed & Approved | Closed before june-2025 | Closed after June |  | Completed & Approved
409 | 410 | 472 | GPON | Tejas | Special Characters not allowing in User Creation in EMS |  |  | Sayyad Pasha |  | COMPLETED & APPROVED | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\Special Characters | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
410 | 411 | 472 | GPON | Tejas | Unable to add 4th UNI in a service with 1Gb bandwidth |  |  | Sayyad Pasha |  | COMPLETED & APPROVED | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\Report of ONT UNI in a Service | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
411 | 412 | 472 | GPON | Tejas | End Customer MAC Address report from EMS |  |  | Sayyad Pasha |  | COMPLETED & APPROVED | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\Ens users MAC address report | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
412 | 413 | 472 | GPON | Tejas | If Mixed service deleted from EMS and discovered then service type is changing to HIS |  |  | Sayyad Pasha |  | COMPLETED & APPROVED | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\Discovery of Mixed Service | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
413 | 414 | 472 | GPON | Tejas | Live PM monitoring per UNI in EMS service Window |  |  | Sayyad Pasha |  | COMPLETED & APPROVED | 2025-07-10 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\416 | Completed & Approved | Closed before june-2025 | Closed after June |  | Completed & Approved
414 | 415 | 472 | GPON | Tejas | Required Consolidated Service invenotry report with ONT UNI details from EMS |  |  | Sayyad Pasha |  | COMPLETED & APPROVED | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\Serivce Report | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
415 | 416 | 472 | GPON | Tejas | Unable to Enable PM from EMS |  |  | Sayyad Pasha |  | COMPLETED & APPROVED | 2025-07-07 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\414 | Completed & Approved | Closed before june-2025 | Closed after June |  | Completed & Approved
416 | 417 | 472 | GPON | Tejas | While creating service profile, maximum bandwidth is not taking 1024000 only considering 1000000 |  |  | Sayyad Pasha |  | COMPLETED & APPROVED | 2025-07-31 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\417 | Completed & Approved | Closed before june-2025 | Closed after June |  | Completed & Approved
417 | 418 | 472 | GPON | Tejas | Report of Syslog enabled in OLT |  |  | Sayyad Pasha |  | COMPLETED & APPROVED | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\Report of Syslog enabled in Tejas OLTs | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
418 | 419 | 472 | GPON | Tejas | Report of Radius enable in OLT |  |  | Sayyad Pasha |  | COMPLETED & APPROVED | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\Report of Radius enabled in Tejas OLTs | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
419 | 420 | 472 | GPON | Tejas | OLT (SNMP-V3) status is not updating in EMS |  |  | Sayyad Pasha |  | COMPLETED & APPROVED | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T167 | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
420 | 421 | 472 | GPON | Tejas | ONT status showing as Unexpected |  |  | Sayyad Pasha |  | COMPLETED & APPROVED | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\ONT Unexpected State | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
421 | 422 | 472 | GPON | Tejas | Unable to add multiple unis while creating mixed service |  |  | Sayyad Pasha |  | COMPLETED & APPROVED | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\Create Service with Mulitple UNIs | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
422 | 423 | 472 | GPON | Tejas | ONT ETH Port status monitoring from OSS |  |  | Sayyad Pasha |  | COMPLETED & APPROVED | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\Tejas LAN LOS | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
423 | 424 | 472 | GPON | Tejas | Unable to create service with same vlans on 2 diferent UNI ports |  |  | Sayyad Pasha |  | COMPLETED & APPROVED | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\Service Report | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
424 | 425 | 472 | GPON | Tejas | OLT Node not reachable alarm clearance and regeneration |  |  | Sayyad Pasha |  | COMPLETED & APPROVED | 2025-07-05 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\425 | Completed & Approved | Closed before june-2025 | Closed after June |  | Completed & Approved
425 | 426 | 472 | GPON | Tejas | Port Description is not available for all ONT UNI Ports |  |  | Sayyad Pasha |  | COMPLETED & APPROVED | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\ONT Ports description | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
426 | 427 | 472 | GPON | Tejas | In the Manage ONT Page we need have'(District name Location Name) 'In the Location field |  |  | Sayyad Pasha |  | COMPLETED & APPROVED | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\OLT Partition Label in ONT Page | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
427 | 428 | 472 | GPON | Tejas | Automatically services converting from Active to Conflict - EMS |  |  | Sayyad Pasha |  | COMPLETED & APPROVED | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T167 | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
428 | 429 | 472 | GPON | Tejas | DIAGUSER credentials getting reset after OLT Reboot |  |  | Sayyad Pasha |  | COMPLETED & APPROVED | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\DIAGUSER Credentials are Not Resetting | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
429 | 430 | 472 | GPON | Tejas | while adding uni in EMS, list of downstream profiles are highlighting in the bottom |  |  | Sayyad Pasha |  | COMPLETED & APPROVED | 2025-07-05 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\430 | Completed & Approved | Closed before june-2025 | Closed after June |  | Completed & Approved
430 | 431 | 472 | GPON | Tejas | Unable to add uni without translation in a translation service |  |  | Sayyad Pasha |  | COMPLETED & APPROVED | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\Add UNI in Translated Service | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
431 | 432 | 472 | GPON | Tejas | Nokia ONT ethernet port status is not updating under Tejas OLT | 15-Nov-25: A call will be scheduled with Tejas and Nokia, along with Tfiber for the conclusion of this issue 13-Sep-2025: Testing is in progress for the ONT ETH status for different 3rd party ONTs under Tejas OLT 30-Aug-2025: Having dependency on both Tejas and Nokia. Also to test and verify the behaviour of the ONT ETH status for different 3rd party ONTs under Tejas OLT 18-Aug-2025 : Tejas updated as below As per ITU-T 988 standard, Section 9.5.1 – Physical path termination point Ethernet UNI, the Operational State attribute indicated whether the ME is capable of performing its function. As this is function of ONU, the operational state of the ONU Ethernet UNI is updated to OLT via AVC indications from the ONU. As per debugging done, the AVC indications are not received from Nokia ONU because of which OLT is not able to update UI about the “Operational State” of the ONU Ethernet port. 08-Aug-2025 : This point has been discussed in the call and TFiber asked to provide the solution. Tejas confirmed that they will check and confirm 02-Aug-2025 : This issue has been discussed with TFiber. When a LAN cable is connected to or removed from the ONT Ethernet port, the operational status is not updating in the OLT. However, the corresponding alarm is being generated and cleared as expected. This matter will be raised during the Tejas call scheduled for 04-Aug-2025 at 4:00 PM. 22-July-2025 : As per Nokia they are having the status update by alarm notification but not with the seperate byte for the status update. Same has been checking with Tejas to get the solution 18-July-2025 : A call scheduled with Nokia on 21-July-2025 to discuss on this issue 11-July-2025 : Also observed that ONT ethernet status is not updating only when Eth port is bridge mode whereas in Route status is updating. Same has been highlighted to Tejas. Working with both Nokia and Tejas for the closure 04-July-2025 : Nokia checking internally on the shared logs 03-July-2025 : Tejas responded that whenever ONT eth status is updating Nokia ONT is not sending the expected OMCI message. In the OMCI message, 3rd byte represents the status of ONT Eth which is not updating. Same has been checking with Nokia 30-June-2025 : Tejas analysing the shared logs on 23-June-2025 and Tejas has to revert with update Nokia ONT ethernet port status is not updating when connected under Tejas OLT however alarms are receiveing on ont eth port. Workaround applied as alarms available for the ONT ETH port status. Nokia has provided the required logs and Tejas is working on the same |  | Sayyad Pasha |  | DEPENDENCY(Client/Ext.) |  |  | Open | Open | Open |  | Open
432 | 433 | 472 | GPON | Tejas | Tejas ONT Software Upgrade which are connected under Nokia OLT | 15-Nov-25: ONT upgrade is in progress 20-Sep-25: During the ONT software upgradation 11 ONTs got faulty, So GPON Team asked the Tejas team to provided RCA for the 11 ONTs and hold the upgradation activity temporarely. Tejas team provided the RCA 11 ONt Stating that 11 ONTs got faulty not because of upgradation activity . The reason for faulty is 3 ONTs of component and 8 ONTs of Memory corrupted due to multiple reboots. Note: Based on RCA, Now upgradation activity is being taken up(1312 ONTs upgradation completed out of 9530 as on today) 13-Sep-2025: Tejas confirmed that they don't have the 9logs to provide but shared the RCA by verifyting the ONTs at the time of repair 30-Aug2025: Having dependency on Tejas. Asked Tejas to provide the supporting logs. As per Tejas RCA ONT got faulty due to component faulty and memory corruption but these ONTs are working fine before the upgarde activity and only went faulty while performing the upgrade. Tejas have provide the clarity on this to proceed the upgrade for the remaining ONTs 08-Aug-2025 : Tejas provided the below RCA As per analysis, the ONT software upgrade from NOC is not the cause for ONT going down. On 3 ONTs a component was entering faulty state, this has been replaced. Remaining 8 ONTs had a file corruption in memory due to earlier multiple reboot events, this has been resolved by Re-Programming the ONT 02-Aug-2025 : Tejas yet to respond on this issue, same will be raised during the Tejas call scheduled for 04-Aug-2025 at 4:00 PM. 25-July-2025 : Tejas working on the delivered ONTs at their repair center. Tejas yet to share the update on this 14-July-2025 : ONTs delivered at Tejas repair center on 14-July-2025. Same has been communicated to Tejas team to expedite the process and share the RCA 14-July-2025 : ONT still not delivered at Tejas repai center, seems to be courier issue. Informed to concerned team to check and make it to delivier 07-July-2025 : ONTs are intransit to Tejas repair center To provide the contract of RMA on faulty devices replacement or repair 30-June-2025 : Successfully upgraded 600 ONTs in the production environment. All of them came up operational with no issue observed. However, 11 ONTs went unresponsive, and RMA raised for those. 23-June-2025 : RMA raised with Tejas for the ONTs ONTs which are running software version lower than 2.3.5.53 are upgrading locally |  | Sayyad Pasha |  | WIP |  |  | Open | Open | Open |  | Open
433 | 434 | 472 | GPON | Tejas | Script to change the pasword of DIAGUSER and tejas users |  |  | Sayyad Pasha |  | COMPLETED & APPROVED | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\434 | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
434 | 435 | 472 | GPON | Tejas | Unable to configure downstream profiles to the ONT UNIs -- This option is available in production EMS but not available in latest released EMS |  |  | Sayyad Pasha |  | COMPLETED & APPROVED | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T167 | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
435 | 436 | 472 | GPON | Tejas | MAC address of end device is not reflecting in COLT FDB entries whereas MAC address is available in service level FDB entries |  |  | Sayyad Pasha |  | COMPLETED & APPROVED | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T167 | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
436 | 437 | 472 | GPON | Tejas | Whenever the ONT software is being downloaded to the OLT, the OLT management going down |  |  | Sayyad Pasha |  | COMPLETED & APPROVED | 2025-07-31 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\437 | Completed & Approved | Closed before june-2025 | Closed after June |  | Completed & Approved
437 | 438 | 472 | GPON | Tejas | The download bandwidth is not controlled for Nokia ONTs connected to the Tejas OLT |  |  | Sayyad Pasha |  | COMPLETED & APPROVED | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T167 | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
438 | 439 | 472 | GPON | Tejas | Unable to add node in EMS with TACACS user |  |  | Sayyad Pasha |  | COMPLETED & APPROVED | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\T167 | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
439 | 440 | 472 | GPON | Tejas | API for ONT creation (Bridge/Route), location name update |  |  | Sayyad Pasha |  | COMPLETED & APPROVED | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
440 | 441 | 472 | GPON | Tejas | API for GI-BB Service, combo port, mixed service - Bridge Mode with/without translation, including uplink port configuration |  |  | Sayyad Pasha |  | COMPLETED & APPROVED | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
441 | 442 | 472 | GPON | Tejas | API for GI-BB Service, combo port, mixed service - Route Mode with/without translation, including uplink port configuration |  |  | Sayyad Pasha |  | COMPLETED & APPROVED | 2025-08-06 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\442 | Completed & Approved | Closed before june-2025 | Closed after June |  | Completed & Approved
442 | 443 | 472 | GPON | Tejas | API for TDIA Service, combo port, mixed service - Bridge Mode(Tag, Untag) including uplink port configuration |  |  | Sayyad Pasha |  | COMPLETED & APPROVED | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
443 | 444 | 472 | GPON | Tejas | API for TDIA Service, combo port, mixed service - Route Mode, including uplink port configuration |  |  | Sayyad Pasha |  | COMPLETED & APPROVED | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
444 | 445 | 472 | GPON | Tejas | API for Household Services, including uplink port configuration |  |  | Sayyad Pasha |  | COMPLETED & APPROVED | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
445 | 446 | 472 | GPON | Tejas | AP for IPTV services, including uplink port configuration |  |  | Sayyad Pasha |  | COMPLETED & APPROVED | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
446 | 447 | 472 | GPON | Tejas | API for VOIP services, including uplink port configuration |  |  | Sayyad Pasha |  | COMPLETED & APPROVED | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
447 | 448 | 472 | GPON | Tejas | API required to provision ONT along with selecting specific UNI port in ONT |  |  | Sayyad Pasha |  | COMPLETED & APPROVED | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
448 | 449 | 472 | GPON | Tejas | API required to provision ONT with multiple services along with selecting specific UNI port in ONT |  |  | Sayyad Pasha |  | COMPLETED & APPROVED | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
449 | 450 | 472 | GPON | Tejas | API required to provision ONT with same service on all ports |  |  | Sayyad Pasha |  | COMPLETED & APPROVED | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
450 | 451 | 472 | GPON | Tejas | API to configure multiple vlans on single ONT UNI Port |  |  | Sayyad Pasha |  | COMPLETED & APPROVED | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
451 | 452 | 472 | GPON | Tejas | API for the Q&Q services |  |  | Sayyad Pasha |  | COMPLETED & APPROVED | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
452 | 453 | 472 | GPON | Tejas | Configuration, API for extedning services to enterprise customers for cell towers |  |  | Sayyad Pasha |  | COMPLETED & APPROVED | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
453 | 454 | 472 | GPON | Tejas | API to configure Rythuvedika, MRO, School Services, CCTV |  |  | Sayyad Pasha |  | COMPLETED & APPROVED | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
454 | 455 | 472 | GPON | Tejas | API to verify and enable the PM |  |  | Sayyad Pasha |  | COMPLETED & APPROVED | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
455 | 456 | 472 | GPON | Tejas | API to configure Vlan and Profiles in OLT |  |  | Sayyad Pasha |  | COMPLETED & APPROVED | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
456 | 457 | 472 | GPON | Tejas | Verification of the services configured by NSO through Playbook(Cisco Tool) |  |  | Sayyad Pasha |  | COMPLETED & APPROVED | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API to validate the configured Services | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
457 | 458 | 472 | GPON | Tejas | API to configure ONT UNI Port as tagged vlan |  |  | Sayyad Pasha |  | COMPLETED & APPROVED | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
458 | 459 | 472 | GPON | Tejas | API to validate the profiles, vlans available in OLT,ONT |  |  | Sayyad Pasha |  | COMPLETED & APPROVED | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API to validate the configured Services | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
459 | 460 | 472 | GPON | Tejas | API to change the ONT ETH Port to Bridge to Route and Vice versa |  |  | Sayyad Pasha |  | COMPLETED & APPROVED | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
460 | 461 | 472 | GPON | Tejas | API to suspend/delete the service from a ONT UNI Port |  |  | Sayyad Pasha |  | COMPLETED & APPROVED | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
461 | 462 | 472 | GPON | Tejas | API to suspend/delete the complete service |  |  | Sayyad Pasha |  | COMPLETED & APPROVED | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
462 | 463 | 472 | GPON | Tejas | API to modify the service- ONT, UNI Port, bandwidth, vlan, description, unatgged to tag or vice versa., | 15-Nov-25: Having dependency on NSO and BSS |  | Sayyad Pasha |  | DEPENDENCY(Client/Ext.) |  |  | Open | Open | Open |  | Open
463 | 464 | 472 | GPON | Tejas | API to configure and delete the WAN profiles in WiFi ONT |  |  | Sayyad Pasha |  | COMPLETED & APPROVED | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
464 | 465 | 472 | GPON | Tejas | API to make PON Port admin up / down |  |  | Sayyad Pasha |  | COMPLETED & APPROVED | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
465 | 466 | 472 | GPON | Tejas | API to create/delete service Profile |  |  | Sayyad Pasha |  | COMPLETED & APPROVED | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
466 | 467 | 472 | GPON | Tejas | Required complete API and Template developer document |  |  | Sayyad Pasha |  | COMPLETED & APPROVED | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\API Document | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
467 | 468 | 472 | GPON | Nokia | ONT Ethernet Port PM Report |  |  | Sayyad Pasha |  | COMPLETED & APPROVED | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\ONT ETH PM Report | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
468 | 469 | 472 | GPON | Nokia | ONT Wifi/Route Mode PM Report |  |  | Sayyad Pasha |  | COMPLETED & APPROVED | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\ONT WiFi PM Report | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
469 | 470 | 472 | GPON | Nokia | PM Report for 24hrs of OLT,ONT,ONT Eth Port(Bridge/Route), Wifi |  |  | Sayyad Pasha |  | COMPLETED & APPROVED | 2025-07-31 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\470 | Completed & Approved | Closed before june-2025 | Closed after June |  | Completed & Approved
470 | 471 | 472 | GPON | Nokia | ONT ETH Port status monitoring from OSS |  |  | Sayyad Pasha |  | COMPLETED & APPROVED | 2025-04-30 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\Tejas LAN LOS | Completed & Approved | Closed before june-2025 | Closed before june-2025 |  | Completed & Approved
471 | 472 | 472 | GPON | Nokia | Unable to browse Internet when IPV6 configured in wifi ONT |  |  | Sayyad Pasha |  | COMPLETED & APPROVED | 2025-07-31 | \\172.28.9.34\Artefacts_T-Fiber TNOC Tracker\GPON\472 | Completed & Approved | Closed before june-2025 | Closed after June |  | Completed & Approved
472 | T2A | 472 | Security & Regulatory Compliance | Security | Ciena to comply the password policy for MCP and field nodes, though Alepo AAA. | 28-Nov-25: To discuss with mr Sanjay to get clarifications on the points. Password managment policy for ciena need to be finalised and to be approved by authority prior implentations |  | Bajiba Shaik |  | WIP |  |  | Open | Open | Open |  | Open

## OtherTasks
Meetings | Purpose | Planned | Visited Date | Location | Comments
Sanjay | NSO Artifacts Review | 25/02/2026 | 27/02/2026
Ravibhushan/Rajiv | LLD Document(Mail there is Note any discussion happened on this points with sanjay) Asked about HLD Document(Reached Sandeep, There is no Specific HLD document for NSO, His Comment(There is nothing called NSO HLD, we have application HLD. The SDD and LLD) He provided HLD LLD SDD documents ) | 2026-06-03 | 2026-07-03 | Madhapur | 1.Reviewed and asked to provide end to end flow for each point with images and configuration . 2.check with TNOC team on these points. 3.provide by status by MonDay evening, 4.provide 1 point end to end flow on tuesday, 4.complete all points by friday.
Sandeep | BSS Dependency Artifacts(Need Help) | 2026-06-03 |  |  | Done-Got screenshots.
TNOC Visit | Test Lab Demo and LLD discussion with govind | 2026-09-03 |  | TNOC
Jyothi | Python Scripts,PowerBI,Topology,PHP | 17/03/2026

## Tracker
Date | Activity / Task | Project Module | Owner | Status | Dependencies | Next Steps | KT Done | Docs/Links | Remarks
2026-03-17